## Project Schedule
Health | % Complete | Task Name | Task ID | Panel/Piece Count | System | Responsible Person | Duration | Start Date | Finish Date | Predecessors | Comments | Status | Hierarchy | Parent | Job Name | Job Number | PM | Task
|  | Summary | [10 empty] | 0 | 5 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
|  | SHORT JOB NO | <<SHORT JOB NO>> | [9 empty] | 1 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
. | . | JOB NAME | <<JOB NAME>> | [9 empty] | 1 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
. | . | PM | <<PM>> | [9 empty] | 1 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
. | . | JOB HEALTH | Green | [9 empty] | 1 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
. | . | % COMPLETE | 0% | [9 empty] | 1 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
|  | Navigation | [10 empty] | 0 | 10 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
|  | Budget | [10 empty] | 1 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Navigation: Budget
|  | Project Charter | [10 empty] | 1 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Navigation: Project Charter
|  | Project Schedule | [10 empty] | 1 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Navigation: Project Schedule
|  | Earned Value Management | [10 empty] | 1 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Navigation: Earned Value Management
|  | Forecast | [10 empty] | 1 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Navigation: Forecast
|  | Project Summary Dashboard | [10 empty] | 1 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Navigation: Project Summary Dashboard
|  | Production workbook | [10 empty] | 1 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Navigation: Production workbook
|  | Change Order Request Log | [10 empty] | 1 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Navigation: Change Order Request Log
|  | Change Order Budget | [10 empty] | 1 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Navigation: Change Order Budget
|  | Schedule of Values | [10 empty] | 1 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Navigation: Schedule of Values
|  | PM Notes | [10 empty] | 0 | 4 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
[13 empty] | 1 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | PM Notes:
[13 empty] | 1 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | PM Notes:
[13 empty] | 1 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | PM Notes:
[13 empty] | 1 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | PM Notes:
Green | 0% | Project Schedule |  |  |  |  | 192d | 2026-08-20 | 2027-05-14 |  |  | Not Started | 0 | 7 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
Gray | 0% | PM Front loading / Admin |  |  |  |  | 94d | 2026-09-01 | 2027-01-11 |  |  | Not Started | 1 | 11 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
Gray | 0% | Receive NTP / Contract go ahead |  |  |  |  | 2d | 2026-09-01 | 2026-09-02 |  |  | Not Started | 2 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | PM Front loading / Admin: Receive NTP / Contract go ahead
Gray | 0% | Estimating Turnover |  |  |  |  | 1d | 2026-09-03 | 2026-09-03 | 25 |  | Not Started | 2 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | PM Front loading / Admin: Estimating Turnover
Gray | 0% | Review Project Scope |  |  |  |  | 5d | 2026-09-04 | 2026-09-10 | 26 |  | Not Started | 2 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | PM Front loading / Admin: Review Project Scope
Gray | 0% | Prepare Project Schedule |  |  |  |  | 10d | 2026-09-04 | 2026-09-17 | 26 |  | Not Started | 2 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | PM Front loading / Admin: Prepare Project Schedule
Gray | 0% | Prepare Project Phase Code, and Time Cost Plan |  |  |  |  | 10d | 2026-09-04 | 2026-09-17 | 26 |  | Not Started | 2 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | PM Front loading / Admin: Prepare Project Phase Code, and Time Cost Plan
Gray | 0% | Prepare Project SOV |  |  |  |  | 10d | 2026-09-04 | 2026-09-17 | 26 |  | Not Started | 2 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | PM Front loading / Admin: Prepare Project SOV
Gray | 0% | Prepare Project Equipment Plan - Construction Plan |  |  |  |  | 10d | 2026-09-04 | 2026-09-17 | 26 |  | Not Started | 2 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | PM Front loading / Admin: Prepare Project Equipment Plan - Construction Plan
Gray | 0% | Enter Project into Spectrum and Smart Sheet Schedules |  |  |  |  | 1d | 2026-09-11 | 2026-09-11 | 27 |  | Not Started | 2 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | PM Front loading / Admin: Enter Project into Spectrum and Smart Sheet Schedules
Gray | 0% | Prepare documentation for Engineering Turnover |  |  |  |  | 5d | 2026-12-01 | 2026-12-07 | 34SF |  | Not Started | 2 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | PM Front loading / Admin: Prepare documentation for Engineering Turnover
Gray | 0% | Engineering Turnover (PM to Drafting Manager) |  |  |  |  | 2d | 2026-12-08 | 2026-12-09 | 99SS -15d |  | Not Started | 2 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | PM Front loading / Admin: Engineering Turnover (PM to Drafting Manager)
Gray | 0% | Field Turnover (PM to foreman and Labor) |  |  |  |  | 0 | 2027-01-11 | 2027-01-11 | 112SS -15d |  | Not Started | 2 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | PM Front loading / Admin: Field Turnover (PM to foreman and Labor)
Gray | 0% | Submittals |  |  |  |  | 65d | 2026-08-20 | 2026-11-18 |  |  | Not Started | 1 | 2 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
Gray | 0% | FS-01 |  |  |  |  | 50d | 2026-09-10 | 2026-11-18 |  |  | Not Started | 2 | 11 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
Gray | 0% | Engineering Shop drawing production |  |  |  |  | 23d | 2026-09-10 | 2026-10-12 | 41SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01: Engineering Shop drawing production
Gray | 0% | Prepare Submittal Pack |  |  |  |  | 23d | 2026-09-10 | 2026-10-12 | 40SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01: Prepare Submittal Pack
Gray | 0% | Submit Submittal pack |  |  |  |  | 1d | 2026-10-13 | 2026-10-13 | 42SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01: Submit Submittal pack
Gray | 0% | Submit Shop Drawings |  |  |  |  | 1d | 2026-10-13 | 2026-10-13 | 43SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01: Submit Shop Drawings
Gray | 0% | Receive reviewed Submittal pack |  |  |  |  | 10d | 2026-10-14 | 2026-10-27 | 44SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01: Receive reviewed Submittal pack
Gray | 0% | Receive reviewed Shop Drawings |  |  |  |  | 10d | 2026-10-14 | 2026-10-27 | 45SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01: Receive reviewed Shop Drawings
Gray | 0% | Resubmit Submittal pack |  |  |  |  | 10d | 2026-10-28 | 2026-11-10 | 46SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01: Resubmit Submittal pack
Gray | 0% | Resubmit Shop Drawing |  |  |  |  | 10d | 2026-10-28 | 2026-11-10 | 47SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01: Resubmit Shop Drawing
Gray | 0% | Receive Approved FINAL submittals back |  |  |  |  | 1d | 2026-11-11 | 2026-11-11 | 48SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01: Receive Approved FINAL submittals back
Gray | 0% | Receive Approved FINAL Shop drawings back |  |  |  |  | 1d | 2026-11-11 | 2026-11-11 | 48SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01: Receive Approved FINAL Shop drawings back
Gray | 0% | Prepare Buy lists |  |  |  |  | 5d | 2026-11-12 | 2026-11-18 | 70SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01: Prepare Buy lists
Gray | 0% | FS-02 IMP |  |  |  |  | 50d | 2026-08-20 | 2026-10-28 |  |  | Not Started | 2 | 11 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
Gray | 0% | Engineering Shop drawing production |  |  |  |  | 23d | 2026-08-27 | 2026-09-28 | 53SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-02 IMP: Engineering Shop drawing production
Gray | 0% | Prepare Submittal Pack |  |  |  |  | 23d | 2026-08-20 | 2026-09-21 | 52SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-02 IMP: Prepare Submittal Pack
Gray | 0% | Submit Submittal pack |  |  |  |  | 1d | 2026-09-22 | 2026-09-22 | 54SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-02 IMP: Submit Submittal pack
Gray | 0% | Submit Shop Drawings |  |  |  |  | 1d | 2026-09-29 | 2026-09-29 | 55SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-02 IMP: Submit Shop Drawings
Gray | 0% | Receive reviewed Submittal pack |  |  |  |  | 10d | 2026-09-23 | 2026-10-06 | 56SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-02 IMP: Receive reviewed Submittal pack
Gray | 0% | Receive reviewed Shop Drawings |  |  |  |  | 5d | 2026-09-30 | 2026-10-06 | 57SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-02 IMP: Receive reviewed Shop Drawings
Gray | 0% | Resubmit Submittal pack |  |  |  |  | 10d | 2026-10-07 | 2026-10-20 | 58SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-02 IMP: Resubmit Submittal pack
Gray | 0% | Resubmit Shop Drawing |  |  |  |  | 10d | 2026-10-07 | 2026-10-20 | 59SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-02 IMP: Resubmit Shop Drawing
Gray | 0% | Receive APPROVED FINAL submittals back |  |  |  |  | 1d | 2026-10-21 | 2026-10-21 | 60SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-02 IMP: Receive APPROVED FINAL submittals back
Gray | 0% | Receive APPROVED FINAL Shop drawings back |  |  |  |  | 1d | 2026-10-21 | 2026-10-21 | 60SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-02 IMP: Receive APPROVED FINAL Shop drawings back
Gray | 0% | Prepare Buy lists |  |  |  |  | 5d | 2026-10-22 | 2026-10-28 | 88SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-02 IMP: Prepare Buy lists
Gray | 0% | Close out Documentation |  |  |  |  | 1d | 2027-03-26 | 2027-03-26 |  |  | Not Started | 1 | 1 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
Gray | 0% | Warranties etc. |  |  |  |  | 1d | 2027-03-26 | 2027-03-26 | 120 |  | Not Started | 2 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Close out Documentation: Warranties etc.
Gray | 0% | Procurement |  |  |  |  | 71d | 2026-10-22 | 2027-01-28 |  |  | Not Started | 1 | 2 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
Gray | 0% | FS-01 |  |  |  |  | 51d | 2026-11-19 | 2027-01-28 |  |  | Not Started | 2 | 4 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
Gray | 0% | Extrusions |  |  |  |  | 51d | 2026-11-19 | 2027-01-28 |  |  | Not Started | 3 | 3 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
Gray | 0% | Order |  |  |  |  | 5d | 2026-11-19 | 2026-11-25 | 67SF |  | Not Started | 4 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Extrusions: Order
Gray | 0% | Lead time |  |  |  |  | 45d | 2026-11-26 | 2027-01-27 | 68SF |  | Not Started | 4 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Extrusions: Lead time
Gray | 0% | Receive |  |  |  |  | 1d | 2027-01-28 | 2027-01-28 | 96SF |  | Not Started | 4 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Extrusions: Receive
Gray | 0% | ACM |  |  |  |  | 51d | 2026-11-19 | 2027-01-28 |  |  | Not Started | 3 | 3 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
Gray | 0% | Order |  |  |  |  | 5d | 2026-11-19 | 2026-11-25 | 71SF |  | Not Started | 4 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | ACM: Order
Gray | 0% | Lead time |  |  |  |  | 45d | 2026-11-26 | 2027-01-27 | 72SF |  | Not Started | 4 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | ACM: Lead time
Gray | 0% | Receive |  |  |  |  | 1d | 2027-01-28 | 2027-01-28 | 96SF |  | Not Started | 4 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | ACM: Receive
Gray | 0% | Z Girt |  |  |  |  | 51d | 2026-11-19 | 2027-01-28 |  |  | Not Started | 3 | 3 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
Gray | 0% | Order |  |  |  |  | 5d | 2026-11-19 | 2026-11-25 | 75SF |  | Not Started | 4 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Z Girt: Order
Gray | 0% | Lead time |  |  |  |  | 45d | 2026-11-26 | 2027-01-27 | 76SF |  | Not Started | 4 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Z Girt: Lead time
Gray | 0% | Receive |  |  |  |  | 1d | 2027-01-28 | 2027-01-28 | 96SF |  | Not Started | 4 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Z Girt: Receive
Gray | 0% | Insulation |  |  |  |  | 51d | 2026-11-19 | 2027-01-28 |  |  | Not Started | 3 | 3 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
Gray | 0% | Order |  |  |  |  | 5d | 2026-11-19 | 2026-11-25 | 79SF |  | Not Started | 4 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Insulation: Order
Gray | 0% | Lead time |  |  |  |  | 45d | 2026-11-26 | 2027-01-27 | 80SF |  | Not Started | 4 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Insulation: Lead time
Gray | 0% | Receive |  |  |  |  | 1d | 2027-01-28 | 2027-01-28 | 96SF |  | Not Started | 4 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Insulation: Receive
Gray | 0% | FS-02 IMP |  |  |  |  | 51d | 2026-10-22 | 2026-12-31 |  |  | Not Started | 2 | 2 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
Gray | 0% | Z girt |  |  |  |  | 45d | 2026-10-30 | 2026-12-31 |  |  | Not Started | 3 | 3 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
Gray | 0% | Order |  |  |  |  | 5d | 2026-12-25 | 2026-12-31 | 84FF |  | Not Started | 4 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Z girt: Order
Gray | 0% | Lead Time |  |  |  |  | 45d | 2026-10-30 | 2026-12-31 | 85FF |  | Not Started | 4 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Z girt: Lead Time
Gray | 0% | Recieve |  |  |  |  | 1d | 2026-12-31 | 2026-12-31 | 107FF |  | Not Started | 4 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Z girt: Recieve
Gray | 0% | IMP |  |  |  |  | 51d | 2026-10-22 | 2026-12-31 |  |  | Not Started | 3 | 3 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
Gray | 0% | Order |  |  |  |  | 5d | 2026-10-22 | 2026-10-28 | 88SF |  | Not Started | 4 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | IMP: Order
Gray | 0% | Lead Time |  |  |  |  | 45d | 2026-10-29 | 2026-12-30 | 89SF |  | Not Started | 4 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | IMP: Lead Time
Gray | 0% | Receive |  |  |  |  | 1d | 2026-12-31 | 2026-12-31 | 107FF |  | Not Started | 4 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | IMP: Receive
Gray | 0% | Shop |  |  |  |  | 32d | 2026-12-17 | 2027-01-29 |  |  | Not Started | 1 | 3 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
Gray | 0% | Shop Turnover (Full ACM Scope) (PM to Shop Manager) |  |  |  |  | 1d | 2026-12-17 | 2026-12-17 | 97FF |  | Not Started | 2 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Shop: Shop Turnover (Full ACM Scope) (PM to Shop Manager)
Gray | 0% | FS-01 (Area 1) |  |  |  |  | 31d | 2026-12-18 | 2027-01-29 |  |  | Not Started | 2 | 12 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
Gray | 0% | Receive Extrusions |  |  |  |  | 1d | 2027-01-27 | 2027-01-27 | 67FF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01 (Area 1): Receive Extrusions
Gray | 0% | Receive Insulation |  |  |  |  | 1d | 2027-01-27 | 2027-01-27 | 79FF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01 (Area 1): Receive Insulation
Gray | 0% | Receive Z Girts |  |  |  |  | 1d | 2027-01-29 | 2027-01-29 | 112SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01 (Area 1): Receive Z Girts
Gray | 0% | Receive ACM Material |  |  |  |  | 1d | 2027-01-29 | 2027-01-29 | 112SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01 (Area 1): Receive ACM Material
Gray | 0% | Scan Readiness |  |  |  |  | 0 | 2026-12-18 | 2026-12-18 | 98SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01 (Area 1): Scan Readiness
Gray | 0% | Field Dimensions (per Zone, Per Area) |  |  |  |  | 7d | 2026-12-18 | 2026-12-28 | 99SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01 (Area 1): Field Dimensions (per Zone, Per Area)
Gray | 0% | Panel Sketches (per Zone, Per Area) |  |  |  |  | 7d | 2026-12-29 | 2027-01-06 | 100SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01 (Area 1): Panel Sketches (per Zone, Per Area)
Gray | 0% | Machine Programming (per Zone, Per Area) |  |  |  |  | 2d | 2027-01-07 | 2027-01-08 | 101SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01 (Area 1): Machine Programming (per Zone, Per Area)
Gray | 0% | Cut, Fabricate (per Zone, Per Area) |  |  |  |  | 2d | 2027-01-11 | 2027-01-12 | 102SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01 (Area 1): Cut, Fabricate (per Zone, Per Area)
Gray | 0% | Crating (per Zone, Per Area) |  |  |  |  | 2d | 2027-01-13 | 2027-01-14 | 103SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01 (Area 1): Crating (per Zone, Per Area)
Gray | 0% | Dispatch Material (per Zone, Per Area) |  |  |  |  | 1d | 2027-01-15 | 2027-01-15 | 104SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01 (Area 1): Dispatch Material (per Zone, Per Area)
Gray | 0% | Float |  |  |  |  | 10d | 2027-01-18 | 2027-01-29 | 110SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01 (Area 1): Float
Gray | 0% | FS-02 IMP (Area 2) |  |  |  |  | 1d | 2026-12-30 | 2027-01-01 |  |  | Not Started | 2 | 2 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
Gray | 0% | Receive |  |  |  |  | 0 | 2026-12-30 | 2026-12-30 | 88 |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-02 IMP (Area 2): Receive
Gray | 0% | Dispatch |  |  |  |  | 0 | 2027-01-01 | 2027-01-01 | 118SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-02 IMP (Area 2): Dispatch
Gray | 0% | Field Install | FD-FULL |  |  |  | 101d | 2026-12-25 | 2027-05-14 |  |  | Not Started | 1 | 2 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
Gray | 0% | FS-01 (Area 1) |  |  |  |  | 75d | 2027-02-01 | 2027-05-14 |  |  | Not Started | 2 | 5 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
Gray | 0% | Deliver Material to site (per Zone, Per Area) |  |  |  |  | 45d | 2027-02-01 | 2027-04-02 |  |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01 (Area 1): Deliver Material to site (per Zone, Per Area)
Gray | 0% | Equipment on site |  |  |  |  | 2d | 2027-04-26 | 2027-04-27 | 112 |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01 (Area 1): Equipment on site
Gray | 0% | ACM field Install (per Zone, Per Area) |  |  |  |  | 60d | 2027-02-01 | 2027-04-23 | 110SS |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01 (Area 1): ACM field Install (per Zone, Per Area)
Gray | 0% | Punch List |  |  |  |  | 14d | 2027-04-26 | 2027-05-13 | 112 |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01 (Area 1): Punch List
Gray | 0% | Punch List complete |  |  |  |  | 1d | 2027-05-14 | 2027-05-14 | 113 |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-01 (Area 1): Punch List complete
Gray | 0% | FS-02 IMP (Area 2) |  |  |  |  | 65d | 2026-12-25 | 2027-03-25 |  |  | Not Started | 2 | 5 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>>
Gray | 0% | Deliver Material to site (per Zone, Per Area) |  |  |  |  | 5d | 2026-12-25 | 2026-12-31 | 118SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-02 IMP (Area 2): Deliver Material to site (per Zone, Per Area)
Gray | 0% | Equipment on site |  |  |  |  | 2d | 2026-12-30 | 2026-12-31 | 118SF |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-02 IMP (Area 2): Equipment on site
Gray | 0% | IMP field Install (per Zone, Per Area) |  |  |  |  | 45d | 2027-01-01 | 2027-03-04 |  |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-02 IMP (Area 2): IMP field Install (per Zone, Per Area)
Gray | 0% | Punch List |  |  |  |  | 14d | 2027-03-05 | 2027-03-24 | 118 |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-02 IMP (Area 2): Punch List
Gray | 0% | Punch List complete |  |  |  |  | 1d | 2027-03-25 | 2027-03-25 | 119 |  | Not Started | 3 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | FS-02 IMP (Area 2): Punch List complete
Gray | 0% | Completion |  |  |  |  | 0 | 2027-05-14 | 2027-05-14 | 120, 114 |  | Not Started | 1 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | Project Schedule: Completion
[13 empty] | 0 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | :
[13 empty] | 0 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | :
[13 empty] | 0 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | :
[13 empty] | 0 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | :
[13 empty] | 0 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | :
[13 empty] | 0 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | :
[13 empty] | 0 | 0 | <<JOB NAME>> | <<SHORT JOB NO>> | <<PM>> | :

## Summary
% Complete | 0%
Overall Project Health | Green
Task Not Started | 99
Task In Progress | 0
Task Completed | 0
Project Manager | <<PM>>
Job Number | <<SHORT JOB NO>>
Job Name | <<JOB NAME>>
Project Start Date | 2026-08-20
Project End Date | 2027-05-14