## Field Daily Report
Job Number / Numero de Trabajo | Job Name | Date / Fecha | Submitters name / Su nombre | Notes / Notas | Subcontractor or JWMCD team | Project Manager / Gerente De Proyecto | Delays / retrasos | Describe Delay / describir el retraso | Material / Hardware Needed | What material or hardware is needed | Weather / tiempo | Total Men Onsite / total de hombres en el sitio | Daily Work Hours / horas de trabajo diarias | Deliveries? / entregas? | What was delivered? / lo que fue entregado? | Equipment Onsite? Equipo en el sitio? | Any Onsite Injuries/ lesiones | Employee Name / quien? | Describe Injury / describir lesion? | Was Layout for install done prior to install | What Elevations have completed Layout | What was installed? / que fue instalado? | ACM Qty Installed | ACM - Total Man Hours | Plate Panels Qty Installed | Plate Panels - Total Man Hours | Perforated Garage Panels Qty | Perforated Garage Panel Total Man Hours | Single Skin Qty Installed | Single Skin - Total Man Hours | IMP Qty Installed | IMP - Total Man Hours | Trespa Panel Qty | Trespa Total Man Hours | Overly Roof Panels Qty Installed | Overly Roof Panels - Total Man Hours | Genesis Panel Qty Installed | Genesis Panel - Total Man Hours | Terracota Panel Qty | Terracota Total Man Hours | Mapes Canopy Unit Qty | Mapes Canopy Total Man Hours | Caulking LF Installed | Caulking - Total Man Hours | Corrugated / screen wall Panels Installed | Corrugated / screen wall Panel - Total Man Hours | Louver Qty Installed | Louver - Total Man Hours | Insulation SQFT Installed | Insulation - Total Man Hours | Tubing Linear Ft Installed | Tubing - Total Man Hours | Subgirt Zee Linear Ft Installed | Subgirt Zee - Total Man Hours | Flashing Linear Ft Installed | Flashing - Total Man Hours | Hat Channel Linear Ft Installed | Hat Channel - Total Man Hours | Trim Linear Ft Installed | Trim Install - Total Man Hours | AWB SQFT Installed | AWB - Total Man Hours | Coping Linear Ft Installed | Coping - Total Man Hours | Other (Please Describe) | Other - Total Man Hours | End Date | Allocation % | Duration | Predecessors
25031 | LLU Mars US Warehouse | 2026-10-03 | Abner aguilar | 1 pallet insulation we need to water proof the flashing in the next build as in the picture below | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | Yes | Insulation | Boom lift | No |  |  | Yes | South elevation west | ACM Insulation Subgirt Zee | 10 | 44 | [24 empty] | 288 | 44 |  |  | 17 | 44
25040 | Moses Lincoln Vitrine | 2026-08-01 | Abner aguilar | Fabricate panels |  | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | Yes | West | ACM | 8 | 44
24077 | IAD 667 TI | 2026-04-16 | Fredy veliz | Elvation sc2. Is 100% complete , we working on last 3 section of elevation sc3 ,EREED is requesting to all trades 2 guys for composed cleaning crew all Friday's starting tomorrow on 668, i will not participate on the one they doing tomorrow because we haven't been on 668 at all ,we will have to discuss about this because we have one of the smaller crews on site and we working a lot on house keeping to avoid any complaints | Subcontractor | Chris Buttrey | No |  | No |  | Hot | 8 | 80 | No |  | 2 150 articulate boom ,65 straight boom lift ,10 k load | No |  |  | No |  | Louvre | [24 empty] | Installing Chanel's on elevation sc3 section 1,2 and 3 ,installing blades elav sc2 section 6 at the door | 80
25022 | Vantage VA15 | 2026-04-16 | Ricardo | We experienced significant delays today. We had an inspection for the metal Z, and we also had to perform adjustments to the swing stage. | Subcontractor | Thomas Mooers | Yes | The delays occurred in the northwest area of the building, where we were unable to work due to a piping inspection and concrete installation for the light pole bases. Additionally, in the southwest area of the building, where the swing stage is installed, we had an inspection of the metal Z, which lasted approximately two hours. We also had to readjust the swing stage basket due to improper installation. This process took about an hour and a half, as roof bins had to be moved to complete the adjustment. | Yes | Metal z and screws 5/16 2” and 1 1/2” | 59 | 9 | 90 | Yes | Plastic shims by the louvers | Boom Lift scaffold | No |  |  | Yes | Northwest and southwest | ACM Caulking Insulation | 10 | 40 | [18 empty] | 130 | 20 |  |  |  |  | 546 | 30
25031 | LLU Mars US Warehouse | 2026-04-16 | Abner aguilar | No | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | Yes | No | Insulation Subgirt Zee | [26 empty] | 640 | 44 |  |  | 45 | 44
24079 | Nashville Youth Campus | 2026-04-16 | Obed Bermudez | Crew one and two are working on section B level three west and south wall, while crew three continues working on section D east wall. All moving material, installing delta tape for z-girt, insulation, flashing, and fiber cement panels. We broke down empty panels and boxes. We removed and reinstalled 2 panels where we made the mock up and cut them to make 3/4 against sill flashing | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 11 | 10 | No |  | Buggy, forklift, conex, boom lifts | No |  |  | Yes | West | Subgirt Zee Terracotta | [16 empty] | 10 | 50 | [12 empty] | 148 | 60
24089 | BSU Innovation Center | 2026-04-16 | Obed Bermudez | We continue installing Morin panels, cover flashing, insulation, and z girt. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 4 | 10 | No |  | Boom lift | No |  |  | Yes | West | Flashing Insulation Single Skin Subgirt Zee | [6 empty] | 2 | 10 | [18 empty] | 110 | 10 |  |  | 55 | 10 | 30 | 10
25031 | LLU Mars US Warehouse | 2026-04-15 | Abner aguilar | Fixing trim and flashing layout on the other small building | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 40 | No |  | Boom lift | No |  |  | Yes | West | Trim | [36 empty] | 1 | 40
24079 | Nashville Youth Campus | 2026-04-15 | Obed Bermudez | Crew one and two are working on section B level three west wall, while crew three continues cutting fiber cement panels for the south elevation. All moving material, installing delta tape for z-girt, insulation, flashing, and fiber cement panels. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 11 | 10 | Yes | Acm | Buggy, forklift, conex, boom lifts | No |  |  | Yes | West | Insulation Subgirt Zee Terracotta | [16 empty] | 6 | 20 | [8 empty] | 432 | 50 |  |  | 340 | 40
24072 | LCK064 | 2026-04-15 | Mauricio Chavez | Can't take pictures onsite. Finished E4 elevation except for sections 32-33. Began fastening screws on joints of panels. | Subcontractor | Joe Hoyle | No |  | No |  | Sunny | 4 | 10 | No |  | Yes | No |  |  | Yes | Partial SW elevations, sections 31-32. | Corrugated / Screen wall Trim | [22 empty] | 15 | [13 empty] | 50
24077 | IAD 667 TI | 2026-04-15 | Fredy veliz | On elevation sc4 we had the clips installed since dicember but they move the flue pipe over to the right ,to make fit so doing that some of out clips were in the same spot where they install the angle supports , so they remove some of clips and we have to do a new layout fro those and moved the rest on clips | Subcontractor | Chris Buttrey | Yes | Slow doing for crane work | No |  | Hot | 8 | 80 | No |  | 2 150 articulate boom lifts ,1 65 straight boom lift 10k load | No |  |  | No |  | Louvre | [24 empty] | Installing Channels sc3 section 1 ,2 and 3 installing blades elevation sc3 entrances section 10 | 80
25002 | Med Center Health | 2026-04-15 | Marvin Blanco | Waiting on material we don't have anything to install in the building everything we have is install | Subcontractor | Carlos Silva | Yes | Columns and panels for the canopies | Yes | Columns and panels for the canopy | Good condition | 4 | 10 | No |  | Boomlift | No |  |  | No |  | Caulking | [20 empty] | 100 | 40
24081 | DLR DFW37 | 2026-04-15 | Marvin Blanco | Checking all the panels because it's a big mess with the panels and it's holding us to install panels | Subcontractor | Cole Norona | No |  | No |  | Good condition | 4 | 12 | No |  | Boomlift forklift | No |  |  | No |  | Plate |  |  | 10 | 48
24089 | BSU Innovation Center | 2026-04-15 | Obed Bermudez | We received and unloaded a delivery of ACM panels, then moved the longboard from the laydown area to the site, then proceeded to install insulation and panels on the west elevation. | Subcontractor | Marc Ribar | Yes | Thunderstorm | No |  | Rain | 4 | 5 | Yes | Acm panels. | Boom lift | No |  |  | No |  | Insulation Single Skin | [6 empty] | 5 | 10 | [18 empty] | 32 | 10
24077 | IAD 667 TI | 2026-04-14 | Fredy veliz | Sc2 elevation almost done ,sc3 elvation is going good , crane working on sc4 flue pipe ,don't have much run to work until the move out | Subcontractor | Chris Buttrey | No |  | No |  | Hot | 8 | 80 | No |  | 2 150 articulate boom lifts ,65 straight boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing blades on sc2 section 8,9,10,13,14,15,16. Screw clips on elevation sc3 section 3 | 80
25022 | Vantage VA15 | 2026-04-14 | Ricardo | Material was moved from the first floor to the roof area, including large panels required for installation on the southwest side of the building in the scaffolding area. | Subcontractor | Thomas Mooers | Yes | Two ACM panels had to be removed because the door framing was not yet ready and two pipes from Sutherland had not been installed. Two flashing pieces were also removed, as the area was not ready for installation due to required wall modifications. Time was also lost due to the installation of the swing stage, which is needed to proceed with work on the southwest side of the building. Additionally, delays were caused while waiting for a safety inspection. | Yes | 5/16 Screws of 2” and 1 1/2 | 62 | 9 | 90 | No |  | Boom lift and scaffold | No |  |  | Yes | South and west soffit elevation | ACM Subgirt Zee | 11 | 60 | [28 empty] | 360 | 30
24072 | LCK064 | 2026-04-14 | Mauricio Chavez | Can't take pictures onsite. | Subcontractor | Joe Hoyle | No |  | No |  | Sunny | 4 | 10 | No |  | Yes | No |  |  | Yes | Partial SW elevation, sections 31-32 | Corrugated / Screen wall Trim | [22 empty] | 30 | [13 empty] | 90
24039 | The Visionary | 2026-04-14 | Wilton Lorenzo | Two crews installed coping on the south and east sides and completed it. After that, they removed the protective plastic from the coping and applied caulking at the joints where the coping sections meet. They also removed the plastic from the panels and installed the reveal on the panels that were missing it. One crew applied caulking on the east side and then moved to the north stair tower to apply caulking on both sides. Another crew applied caulking in the northwest patio. One crew installed the two remaining panels to complete level 2. Another crew cut ACM sheets to fabricate reveals. The protective plastic was removed from the level 2 panels, and two panels were installed on level 1. | Subcontractor | Carlos Silva | Yes | One crew fabricated and installed 2 panels that were not shown on the drawings We ran out of coping around the atrium; we need 60 FT of FL30. We are also missing one of the FL33 clips. We have one clip an the coping but cannot be installed | Yes | Coping | Cloudy | 18 | 10 | Yes | Caulking, baker rod, tek screws | 6 boom lift, 3 scissor lift | No |  |  | Yes | South, north | ACM Caulking Coping | 3 | 2 | [18 empty] | 210FT | 3 | [18 empty] | 60FT | 2
24079 | Nashville Youth Campus | 2026-04-14 | Obed Bermudez | Crew one is working on section B level three west wall, while crew two started cutting fiber cement panels for the west elevation. Crew three continues working at section D south wall. All moving material, installing delta tape for z-girt, insulation, flashing, and fiber cement panels. We modified 24 fiber cement panels. 6 to separate 3/4 from sill flashing on B section west elevation. Another 18 were modified on section B south elevation because they were 5/8 longer. | Subcontractor | Joe Hoyle | Yes | We modified 24 fiber cement panels. 6 to separate 3/4 from sill flashing on B section west elevation. Another 18 were modified on section B south elevation because they were 5/8 longer. | Yes | Base and drip flashing. | Clear | 11 | 10 | Yes | We picked up and brought Acm panels to job site. | Buggy, forklift, conex, boom lifts | No |  |  | Yes | West | Flashing Insulation Subgirt Zee | [26 empty] | 168 | 30 |  |  | 351 | 50 | 110 | 30
24089 | BSU Innovation Center | 2026-04-14 | Obed Bermudez | We managed to get the boom lift that was trapped out in the afternoon. Then, the boom lift wasn't working properly, so we switched and grabbed another to install insulation and Morin panels on the west elevation. | Subcontractor | Marc Ribar | Yes | We managed to get the boom lift that was trapped out in the afternoon, then proceeded to install insulation and Morin panels on the west elevation. | No |  | Rain | 4 | 10 | No |  | Boom lift | No |  |  | No |  | Insulation Single Skin | [6 empty] | 5 | 20 | [18 empty] | 32 | 20
24077 | IAD 667 TI | 2026-04-13 | Fredy veliz | Everything going good | Subcontractor | Chris Buttrey | No |  | No |  | Good | 8 | 88 | No |  | 2 150 articulate boom lift ,65 straight boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing blades sc3 section 4 and 5 ,and sc2 section 18,19,20 | 88
25059 | Allen Samuels CDJR and LC | 2026-04-13 | Chad McCoy | We removed all the caulking and the panels with the column and the 12 inch section of panels. I also measured couple other problem spots for Andrea. | Subcontractor | Andre Van Der Merwe | No |  | No |  | Partly cloudy. | 2 | 9.5 | Yes | I brought material for install | 45 foot boom | No |  |  | No |  | ACM Caulking | 4 | 6 | [18 empty] | 85 | 1
24039 | The Visionary | 2026-04-13 | Wilton Lorenzo | Two crews installed coping around the atrium. Another crew finished installing a missing panel on Level 2, east side. One crew installed panels on Level 4 east, 2 workers fabricated 3 panels in 2 hours. Another crew installed panels at the east lobby but could not complete the work because the flashing was not delivered. One crew applied caulking and fixed details at the west patio on Level 4. After lunch , I reassigned two crews One crew installed an ACM sheet on the first floor cap because the pink waterproofing was visible. Another crew installed Z girts and insulation on the north side of Level 1. Two panels need to be installed. | Subcontractor | Carlos Silva | Yes | Two guys fabricated 3 panels for the east side since they were not shown on the drawings. One crew installed an ACM plate below panel level on the first-floor ramp, as there were no panels provided for that area. We are unable to complete the installation of all the east vestibule panels because the flashing has not arrived. I also have coping for two elevations, but I cannot install it because the clips have not been delivered. | Yes | Black/gray caulking, tek screws | Cloudy | 22 | 10 | No |  | 6 boom lift, 3 scissor lift | No |  |  | Yes | South, east, | ACM Caulking Coping | 6 | 4 | [18 empty] | 60FT | 2 | [18 empty] | 150FT, 310FT of clip | 6
24072 | LCK064 | 2026-04-13 | Mauricio Chavez | Can't take pictures onsite. There was a crane at our work area, had to shift focus to South elevation. | Subcontractor | Joe Hoyle | Yes | Crane was in the way, moved our lifts and moved to work area. | No |  | Sunny | 4 | 12 | No |  | Yes | No |  |  | Yes | Partial SW elevation. Sections 30-31 | Corrugated / Screen wall Trim | [22 empty] | 35 | [13 empty] | 110
25022 | Vantage VA15 | 2026-04-13 | Ricardo | Material was moved from the first floor to the roof area, including large panels required for installation on the southwest side of the building in the scaffolding area. | Subcontractor | Thomas Mooers | Yes | Work could not be performed in the west ceiling area due to ongoing pipe inspections. Additionally, personnel were working below our equipment, which prevented us from operating in that area due to congestion and safety concerns. | Yes | 5/16 Screws of 2” and 1 1/2 | 59 | 9 | 90 | No |  | Boom lift and scaffold | No |  |  | Yes | South and west soffit elevation | ACM Insulation Subgirt Zee | 11 | 50 | [24 empty] | 640 | 20 |  |  | 150 | 20
24079 | Nashville Youth Campus | 2026-04-13 | Obed Bermudez | Crew one started doing layouts for Acm on section B level three west wall, while crew two and three are working at the south wall. All moving material, installing delta tape for z-girt, insulation, flashing, and fiber cement panels. | Subcontractor | Joe Hoyle | No |  | Yes | Base and drip flashing. | Clear | 11 | 10 | Yes | We picked up and brought Acm panels to job site. | Buggy, forklift, conex, boom lifts | No |  |  | Yes | West elevation | Flashing Subgirt Zee | [30 empty] | 260 | 50 | 340 | 60
24089 | BSU Innovation Center | 2026-04-13 | Obed Bermudez | We moved material by hand from lay-down area to site because there wasn't a forklift or boom lift available. | Subcontractor | Marc Ribar | Yes | No boom lift available to work | No |  | Clear | 3 | 10 | No |  | Boom lift | No |  |  | No |  | Flashing | [32 empty] | 9
25022 | Vantage VA15 | 2026-04-12 | Ricardo | All material required for the roof area on the southwest side of the building was moved and organized from the first floor up to the roof. | Subcontractor | Thomas Mooers | No |  | Yes | 5/16 Screws of 2” and 1 1/2 | 59 | 9 | 90 | No |  | Boom lift and scaffold | No |  |  | Yes | South and west soffit elevation | ACM Insulation Subgirt Zee | 17 | 50 | [24 empty] | 704 | 20 |  |  | 350 | 20
24072 | LCK064 | 2026-04-12 | Mauricio Chavez | Can't take pictures onsite. | Subcontractor | Joe Hoyle | No |  | No |  | Cloudy | 4 | 12 | No |  | Yes | No |  |  | Yes | Partial SW elevations, from sections 29-30 | Corrugated / Screen wall Trim | [22 empty] | 40 | [13 empty] | 110
24077 | IAD 667 TI | 2026-04-11 | Fredy veliz | Today EERED has a crew removing all the tarps and scissor lifts from gen yard ,we will close those section next week | Subcontractor | Chris Buttrey | No |  | No |  | Good | 7 | 56 | No |  | 2 150 articulate boom lift ,65 straight boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | ,installing channels elevation sc3 Section 4 ,installing channels elevation sc3 section 3 | 56
24039 | The Visionary | 2026-04-11 | Wilton lorenzo | Three crews finished installing panels on Level 2 inside the parking garage. One crew completed panel installation on Level 2 behind the stair tower. Another crew installed coping. One crew installed panels in the east vestibule. Another crew took measurements and fabricated one panel for the east side of Level 4. Additionally, one crew applied caulking in the west patio on Level 4. | Subcontractor | Carlos Silva | Yes | One guy opened the remaining coping edge at FL29. It took 5 hours. Two guys spent 2 hours modifying the last panel on the east side of Level 2 because it came too large. | Yes | Back/gray caulking, 2 inch tek screws | Cloudy | 22 | 8 | No |  | 6 booms lift, 3 scissor lift | No |  |  | Yes | East side inside of parking garage | ACM Coping | 26 | 8 | [38 empty] | 90FT | 3
24072 | LCK064 | 2026-04-11 | Mauricio Chavez | Can't take pictures onsite | Subcontractor | Joe Hoyle | No |  | No |  | Sunny | 4 | 12 | No |  | Yes | No |  |  | Yes | Partial SW elevation. From section 28-29 | Corrugated / Screen wall Trim | [22 empty] | 40 | [13 empty] | 110
24079 | Nashville Youth Campus | 2026-04-11 | Obed Bermudez | All crews worked on North elevation taking dimensions and measuring windows,heights for fiber cement panels. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 10 | 8 | No |  |  | No |  |  | No |  | Insulation | [26 empty] | 10
24077 | IAD 667 TI | 2026-04-10 | Fredy veliz | We received confirmation this morning from EEREED to proceed and close allá the section on sc2 ,w started installing Channels,they continue removing the tarps on the gens to get the scissor lifts out of there ,elevation sc3 we got 5 sections left be almost done by the end of next week ,EEREED is requesting for 2 man 1 day every week for cleaning creek we need to discuss that | Subcontractor | Chris Buttrey | No |  | No |  | Good | 8 | 80 | No |  | 2 150 articulate boom lifts ,65 straight,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing channels and braces sc3 sention 5 ,installing clips sc3 sention 4 ,installing channels and braces sc2 section 13,17,18,19,20 | 80
24039 | The Visionary | 2026-04-10 | Wilton lorenzo | Four crews installed ACM panels on Level 2, east side, inside the parking garage. Another crew installed panels at the south stair tower on Level 2. One crew installed the two remakes for the columns. Another crew worked on coping inside the atrium, but had to stop after 3:00 PM due to rain. One crew installed sill flashing on the south side and then moved to the roof to begin caulking. | Subcontractor | Carlos Silva | Yes | Two guys opened the edge of the coping that came closed from the factory. It took 5 hours. | Yes | Black/gray caulking, 2" tek screws | Rainy | 24 | 10 | No |  | 6 boom lift, 3 scissor lift, | No |  |  | Yes | East | ACM Coping Subgirt Zee | 32 | 8 | [28 empty] | 80FT | 2 | [8 empty] | 80FT | 3
24079 | Nashville Youth Campus | 2026-04-10 | Obed Bermudez | Crew one started taking measurements on North elevation, while crew two and three are working at the south wall. All moving material, installing delta tape for z-girt, insulation, flashing, and fiber cement panels | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 11 | 10 | No |  | Buggy, forklift, conex, boom lifts | No |  |  | Yes | West | Flashing Insulation Subgirt Zee | [26 empty] | 2042 | 75 |  |  | 580 | 34 | 4 | 1
24077 | IAD 667 TI | 2026-04-09 | Fredy veliz | We are about to be done on the elevation sc2 we only have about 4 more days of work ,but still not getting answers on the entrences ,i give them an ultimatum to get those ares ready by 4/13 if not we will have to close those areas or get a stop order and I don't have and other area for the boom lift and those guys until we can move to 668 | Subcontractor | Chris Buttrey | No |  | No |  | Good | 8 | 80 | No |  | 2 150 articulate boom lifts ,65 straight boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing blades elevation sc3 section 6 and 7 ,installing blades elevation sc2 section 11 and 12 | 80
25022 | Vantage VA15 | 2026-04-09 | Ricardo | All material required for the roof area on the southwest side of the building was moved and organized from the first floor up to the roof. | Subcontractor | Thomas Mooers | Yes | Operations were impacted by heavy equipment congestion, as well as ongoing material movement and organization. | No |  | 42 | 9 | 126 | No |  | Boom lift and scaffold | No |  |  | Yes | North and west soffit elevation | ACM Insulation | 16 | 84 | [24 empty] | 576 | 43
24072 | LCK064 | 2026-04-09 | Mauricio Chavez | Can't take pictures onsite. | Subcontractor | Joe Hoyle | No |  | Yes | Need Tek 5 screws, already ordered, ETA is tomorrow | Sunny | 4 | 12 | No |  | Yes | No |  |  | Yes | Partial of Elevation E4 - Sections 26, 27, and 28 complete | Corrugated / Screen wall Trim | [22 empty] | 37 | [13 empty] | 165
24079 | Nashville Youth Campus | 2026-04-09 | Obed Bermudez | Crew one is working on section B level three east wall, while crew two and three are working at the south wall. All moving material, installing delta tape for z-girt, insulation, flashing, and fiber cement panels. | Subcontractor | Joe Hoyle | No |  | Yes | Drip flashing and base flashing. | Clear | 11 | 10 | Yes | Acm panels | Buggy, forklift, conex, boom lifts | No |  |  | Yes | West | Flashing Insulation Subgirt Zee | [26 empty] | 114 | 10 |  |  | 522 | 80 | 60 | 20
24077 | IAD 667 TI | 2026-04-08 | Fredy veliz | I walked the job this morning with EERRED and other trades the has un finish work in the areas to discuss a solución so we can close the walls in the areas where they are holding us ,they toll me to proceed and close those areas except for one where stairs are not installed ,i will notify them tomorrow in the meeting ,if they don't remove the steel plates from the door i will request a stop order and charge for come back because is not much work left in the area other than that | Subcontractor | Chris Buttrey | No |  | No |  | Cool | 8 | 80 | No |  | 2 150 articulate boom lifts ,65 straight boom lift 10k load | No |  |  | No |  | Louvre | [24 empty] | Installing Channels on sc3 section 6 ,installing clips on sc3 section 5 ,installing blades on sc2 section 11,12,13,14,15 | 80
25002 | Med Center Health | 2026-04-08 | Marvin Blanco | Working in the stone panels and also putting silicone around the brick and acm panels cleaning everything | Subcontractor | Carlos Silva | Yes | Columns panels and also missing panels | Yes | 1¼ backroll 2 boxes 📦 or ⅞ works also | Good condition | 7 | 10 | No |  | Boomlift | No |  |  | No |  | Terracotta | [16 empty] | 12 | 70
25029 | Lourdes CC Phase 2 | 2026-04-08 | Marvin Blanco | Finish all the panels silicone and cleaning | Subcontractor | Dillon Bowman | No |  | No |  | Good condition | 4 | 12 | No |  | Boomlift | No |  |  | No |  | ACM | 10 | 40
24081 | DLR DFW37 | 2026-04-08 | Marvin Blanco | Trying to work but the material we have it's horrible because the paint not good and also there's a lot of scratches in the panels some black spots and 1 panel is made wrong they made the little leg in the wrong side | Subcontractor | Cole Norona | No |  | No |  | Good condition | 5 | 12 | No |  | Boomlift and forklift | No |  |  | No |  | Plate |  |  | 11 | 50
24072 | LCK064 | 2026-04-08 | Mauricio Chavez | Can't take pictures onsite. Superintendent walked job site to advise on issue with steel, told us to proceed, we just need longer screws. | Subcontractor | Joe Hoyle | No |  | Yes | Longer Tek 5 screws, already ordered. | Sunny | 4 | 12 | No |  | Yes | No |  |  | Yes | Partial South elevation | Corrugated / Screen wall Trim | [22 empty] | 17 | [13 empty] | 77
24079 | Nashville Youth Campus | 2026-04-08 | Obed Bermudez | Crew one is working on level two west elevation, while crew two and three continue working at the south elevation level two. The fourth crew continues moving material, installing delta tape for z-girt, insulation, flashing, and fiber cement panels. | Subcontractor | Joe Hoyle | Yes | Someone stepped on 3 fiber panels and broke them. | Yes | Drip and base flashing. | Clear | 11 | 10 | Yes | 2 crates of Acm panels. | Buggy, forklift, conex, boom lifts | No |  |  | Yes | West and south | Flashing Subgirt Zee Terracotta | [16 empty] | 4 | 20 | [12 empty] | 628 | 70 | 99 | 20
24039 | The Visionary | 2026-04-08 | Wilton Lorenzo | Two crews stayed finishing the panel installation on Level 1 inside the parking garage. Three crews started installing panels on Level 2 inside the parking garage. One crew applied caulking on the south side, but after 2:00 PM I reassigned them to clean up and remove all the trash from the floor. Another crew completed the panel installation on the roof at the south stair tower. | Subcontractor | Carlos Silva | Yes | One crew spent 8 hours fabricating 5 panels. Another crew opened the edge of the coping 2 workers, 4 hours | Yes | Black caulking, shims, tek screws | Sunny | 24 | 12 | No |  | 6 boom lift | No |  |  | Yes | East inside of parking garage lvl 1 and 2 | ACM Subgirt Zee | 46 panels | 12 | [28 empty] | 200FT | 4
24077 | IAD 667 TI | 2026-04-07 | Fredy veliz | Continué working on 667 everything is going well | Subcontractor | Chris Buttrey | No |  | No |  | Good | 8 | 80 | No |  | 2 150 articulate boom lift ,65 straight boom ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing clips sc3 section 6 ,installing Chanel's sc3 section 7 ,installing braces sc2 section 9 to 15 | 80
25073 | QTS Rebranding | 2026-04-07 | Chad McCoy | We removed 12 panels and cleaned the area up and took trash with us. We went to the yard and finish cutting acm that gets turned into corrugated. And prepped for tomorrows panel fab | Subcontractor | Andre Van Der Merwe | No |  | No |  | Partly cloudy 75 | 2 | 10 | No |  | 86 foot boom | No |  |  | No |  | ACM | -12 | 3
25022 | Vantage VA15 | 2026-04-07 | Ricardo | We have experienced some challenges in certain areas due to limited accessibility for installing the Z metal. We are also currently waiting for the swing stage on the southwest side of the building. Additionally, a significant amount of material was offloaded yesterday. | Subcontractor | Thomas Mooers | Yes | The installation of the swing stage is required on the southwest side of the building, as this area currently has the highest quantity of panels ready for installation. However, we are unable to proceed because the swing stage has not yet been installed. On the north side, we were also waiting for material, as it was not available, similar to the situation yesterday. Material was moved, organized | Yes | 5/16 Screws of 2” and 1 1/2 | 43 | 9 | 90 | Yes | Seven pallets of ACM panels were received, along with four pallets of perforated panels. | Boom lift and scaffold | No |  |  | Yes | North and west soffit elevation | Subgirt Zee | [30 empty] | 470 | 50
25002 | Med Center Health | 2026-04-07 | Kevin Morris | Finished caulking soffit and lights on South, installed acm panels on South, caulk and peel south, loaded and brought back to the shop 3 bundles of strong girt. | Subcontractor | Carlos Silva | No |  | Yes | Copper acm | Good | 7 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM Caulking | 6 | 6 | [18 empty] | 200 | 10
24072 | LCK064 | 2026-04-07 | Mauricio Chavez | Can't take pictures of job site. Issue with the steel structure, some sections are 1-1 1/2 inches out, GC approved that we continue work. | Subcontractor | Joe Hoyle | No |  | Yes | Longer tek 5 screws, already ordered | Sunny | 4 | 12 | No |  | Yes | No |  |  | No |  | Corrugated / Screen wall Trim | [22 empty] | 18 | [13 empty] | 75
24039 | The Visionary | 2026-04-07 | Wilton Lorenzo | Six crews installed panels on Level 1 inside the parking garage. Another crew applied caulking on the south side, and another removed plastic and applied caulking. One crew installed panels on the roof at the south stair tower. We received two deliveries; they were unloaded and moved to Level 2. One crew started laying out for panel installation, and another crew installed insulation on Level 2. | Subcontractor | Carlos Silva | No |  | Yes | Black caulking, 2" tek screws | Sunny | 24 | 12 | Yes | Acm panels for lvl 2. | 6 boom lift, 2 scissor lift, | No |  |  | Yes | Lvl1 east side, south | ACM Insulation Subgirt Zee | 67 | 14 | [24 empty] | 430FT | 4 |  |  | 200FT | 4
24079 | Nashville Youth Campus | 2026-04-07 | Obed Bermudez | Crew one is working on level two west elevation, while crew two and three continue working at the south elevation level two. The fourth crew continues moving material, installing delta tape for z-girt, insulation, flashing, and fiber cement panels. | Subcontractor | Joe Hoyle | No |  | Yes | Drip and base flashing. | Clear | 11 | 10 | No |  | Buggy, forklift, conex, boom lifts | No |  |  | Yes | West and south | Flashing Insulation Subgirt Zee Terracotta | [16 empty] | 8 | 30 | [8 empty] | 280 | 20 |  |  | 724 | 58 | 32 | 2
24039 | The Visionary | 2026-04-06 | Wilton lorenzo | Four crews installed panels in the Level 1 parking garage. One of the crews experienced slow progress due to the large number of pipes, and the panels arrived without extruction , so holes had to be made to accommodate the pipes. Another crew installed panels inside the east vestibule; however, they will need to fabricate three panels due to the same issue we had on the exterior, where smaller panels were sent instead of one large panel. Another crew installed z girts and insulation at the back of the south stair tower. One crew worked on the installation and fabrication of the reveal to cover the expansion joint. another crew installed one panel on Level 2 and then moved to install the hat channel on the south side to allow for the RGB light installation. | Subcontractor | Carlos Silva | No |  | Yes | Black and gray caulking, 3/4" tek screws | Sunny | 22 | 12 | No |  | 6 boom lift, 3 scissor lift, 1 lull | No |  |  | Yes | East vestibule, east parking garage | ACM Caulking Hat Channel Insulation Subgirt Zee | 45 panels | 10 | [18 empty] | 116 ft | 2 |  |  |  |  | 96FT | 2 |  |  | 620FT | 4 |  |  | 40FT | 2
24077 | IAD 667 TI | 2026-04-06 | Fredy veliz | We are back on site ,set up equipment ,and continue installing ,we still have some areas of hold because equipment inside the gen yard and steel hand rails are u complete | Subcontractor | Chris Buttrey | Yes | Demobilization for 2 weeks for asphalt work | Yes | 1/2 drills bits | Good | 8 | 80 | No |  | 2 150 articulate boom lift ,65 straight boom lift ,10k load , | No |  |  | No |  | Louvre | [24 empty] | Installing clips sc3 section 7 ,installing braces on sc2 sectio 10 and 11 ,set up boom lifts the was delivered,moving Chanel's | 80
25002 | Med Center Health | 2026-04-06 | Kevin Morris | Installed acm on South had to fab 7 panels smaller, pulled measurements for 3 missing panels for Carlos, caulked soffits on South | Subcontractor | Carlos Silva | Yes | Canopies not done yet to pull measurements | No |  | Good | 7 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM Caulking Subgirt Zee | 9 | 8 | [18 empty] | 150 | 10 | [8 empty] | 80 | 2
24079 | Nashville Youth Campus | 2026-04-06 | Obed Bermudez | Crew one is working on level two west elevation, while crew two and three continue working at the south elevation level two. The fourth crew continues moving material, installing delta tape for z-girt, insulation, flashing, and fiber cement panels. | Subcontractor | Joe Hoyle | No |  | Yes | Drip and base flashing. | Clear | 9 | 10 | No |  | Buggy, forklift, conex, boom lifts | No |  |  | Yes | West and south | Subgirt Zee Terracotta | [16 empty] | 13 | 50 | [12 empty] | 192 | 40
24072 | LCK064 | 2026-04-06 | Mauricio Chavez | Can't take pictures onsite. Mobilized to job site today. Could not start work when we arrived, other trade was in the way, in the meantime we moved our material inside the job site. | Subcontractor | Joe Hoyle | No |  | No |  | Sunny | 4 | 7 | No |  | Yes | No |  |  | Yes | Partial South elevation | Corrugated / Screen wall Trim | [22 empty] | 3 | [13 empty] | 77
24079 | Nashville Youth Campus | 2026-04-04 | Obed Bermudez | Crew one is working on level two west elevation, while crew two and three continue working at the south elevation level two. The fourth crew continues moving material, installing delta tape for z-girt, insulation, flashing, and fiber cement panels. | Subcontractor | Joe Hoyle | No |  | Yes | Drip and base flashing. | Clear | 6 | 8 | No |  | Buggy, forklift, conex, boom lifts | No |  |  | Yes | South | Flashing Subgirt Zee Terracotta | [16 empty] | 6 | 24 | [12 empty] | 192 | 20 | 20 | 4
24079 | Nashville Youth Campus | 2026-04-03 | Obed Bermudez | Crew one is working on level two west elevation, while crew two and three continue working at the south elevation level two. The fourth crew continues moving material, installing delta tape for z-girt, insulation, flashing, and fiber cement panels | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 9 | 10 | No |  | Buggy, forklift, conex, boom lifts | No |  |  | Yes | West and south | Subgirt Zee Terracotta | [16 empty] | 28 | 60 | [12 empty] | 296 | 30
24039 | The Visionary | 2026-04-03 | Wilton lorenzo | Four crews installed panels in the Level 1 parking garage. One of the crews experienced delays due to multiple pipes and limited access for installation. Another crew applied caulking to the south panels; that panel line requires caulking at the top and bottom horizontally. Another crew finished installing panels on the exterior side of the east vestibule and started laying out. Another crew finished moving all the material to another area and removed the trash we had on the second floor. | Subcontractor | Carlos Silva | Yes | One group moved all the material, and received and disposed of the trash from Level 2. | Yes | 2" teck screws, | Sunny | 20 | 10 | No |  | 6 boom lift, 1 sicssor lift | No |  |  | Yes | East, | ACM | 44 | 12
25002 | Med Center Health | 2026-04-03 | Kevin Morris | Installed zee, insulation, and caulking on South elevations. Installed flashing and stone panels on generator pad. Still waiting for canopies to get framed and dens glasses | Subcontractor | Carlos Silva | No |  | Yes | Copper acm flat sheet | Good | 6 | 10 | No |  | 3 boom lifts | No |  |  | No |  | Caulking Flashing Insulation Terracotta | [16 empty] | 21 | 10 |  |  | 160 | 10 |  |  |  |  | 200 | 8 |  |  |  |  | 60 | 3
25002 | Med Center Health | 2026-04-02 | Kevin Morris | Installed zee, acm panels, and caulked on South elevations. Installed stone panels on generator pad | Subcontractor | Carlos Silva | No |  | No |  | Good | 6 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM Caulking Flashing Subgirt Zee Terracotta | 5 | 4 | [14 empty] | 11 | 10 |  |  | 200 | 10 | [8 empty] | 100 | 4 | 10 | 1
24079 | Nashville Youth Campus | 2026-04-02 | Obed Bermudez | Crew one is working on level two west elevation, while crew two and three started working at the south elevation level two. The fourth crew continues moving material, installing delta tape for z-girt, insulation, flashing, and fiber cement panels. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 9 | 10 | No |  | Buggy, forklift, conex, boom lifts | No |  |  | Yes | West/south | Flashing Subgirt Zee Terracotta | [16 empty] | 10 | 40 | [12 empty] | 330 | 40 | 30 | 10
24039 | The Visionary | 2026-04-02 | Wilton Lorenzo | Two crews installed panels in the parking garage Level 1. One crew installed panels on the roof at the back of the stair tower. Another crew installed panels on the 4th floor ceiling. One crew completed panel installation on the north elevation of the 4th floor. Another crew removed plastic and installed sill flashing. One crew painted the exposed screws, as they were delivered in white, and then applied caulking on the south side. | Subcontractor | Carlos Silva | Yes | We had to relocate all our materials and move all trash and materials from the 4th floor, as Hydrotech installation is scheduled to begin. | Yes | 2" tek screws, Acm flat sheet | Sunny | 21 | 12 | No |  | 6 boom lift, 1 scissor lift | No |  |  | Yes | South, east | ACM Insulation Subgirt Zee | 56 panels | 12 | [24 empty] | 220FT | 4 |  |  | 90FT | 4
25005 | CAT Financial Nashville HQ | 2026-04-01 | Starlin | Today, I installed all the missing screws and put the first bottom piece in place; however, the Site Supervisor arrived and said it was too short. He spoke with Chris, and new measurements were taken. We left everything tidy, gathered the trash, cleaned the pieces that had already been installed, and painted the screws that were already in place, as they were all scratched. | JWMCD Crew | Chris Buttrey | Yes | Today I had to go to the shop this morning to paint the screws and modify a part; I also picked up some double-sided tape and 1199 sealant. | Yes | There are only four pieces left, but their dimensions are different; they need to be remade. Cris already has the measurements. | Hot | 2 | 10 | No |  | No | No |  |  | No |  | Plate |  |  | 2 | 10
24072 | LCK064 | 2026-04-01 | Mauricio Chavez | Can’t take pictures on-site. Finished installing North elevation panels. Began fastening panels on joints | Subcontractor | Joe Hoyle | No |  | No |  | Rain | 4 | 13 | No |  | Yes | No |  |  | No |  | Perforated Grage Panels |  |  |  |  | 5
25002 | Med Center Health | 2026-04-01 | Kevin Morris | Installed flashing, acm panels, and caulking on South elevations. Installed flashing, clip rails, and stone panels on generator pad | Subcontractor | Carlos Silva | No |  | No |  | Good | 6 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM Caulking Flashing Terracotta Tubing | 8 | 10 | [14 empty] | 10 | 5 |  |  | 120 | 10 | [6 empty] | 250 | 5 |  |  | 160 | 10
24079 | Nashville Youth Campus | 2026-04-01 | Obed Bermudez | All crews are working on level two west elevation, moving material, installing delta tape for z-girt, flashing, insulation, panels, rivets, and sleeves. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 9 | 10 | No |  | Buggy, forklift, conex, boom lifts | No |  |  | Yes | West | Flashing Subgirt Zee Terracotta | [16 empty] | 36 | 50 | [12 empty] | 430 | 39 | 8 | 1
24039 | The Visionary | 2026-04-01 | Wilton lorenzo | One crew installed panels in the east vestibule. Another crew installed panels on the 4th floor. One crew fabricated two panels for the 4th floor due to incorrect materials being sent. Another crew installed flashing and removed protective plastic on the south side. Two crews started working on the Level 1 garage entrance. Another crew installed panels on the 4th floor ceiling. | Subcontractor | Carlos Silva | Yes | We had to stop installing panels on the ceiling of the NE patio because the sprinklers were too low. We had to wait for confirmation that they could be raised without removing the panel. 3 guys 2 guys | Yes | Flashing, caulking, 2 inch tek screws | Sunny | 21 | 12 | No |  | 6 boomlift, 1 scissor lift, 1 lull | No |  |  | Yes | Lvl 1 parking garage | ACM Insulation Subgirt Zee | 36 panels | 14 | [24 empty] | 320ft | 8 |  |  | 380ft | 6
25059 | Allen Samuels CDJR and LC | 2026-04-01 | Chad McCoy | General clean up | Subcontractor | Andre Van Der Merwe | No |  | Yes | Caulking | Partly cloudy | 2 | 6 | No |  | 46 foot boom | No |  |  | No |  | ACM | General clean up | General clean up
25005 | CAT Financial Nashville HQ | 2026-03-31 | Starlin | We were working today, and we actually ran into a problem: the heads of some of the screws were protruding about 1/16 of an inch. I tried to fix it as best I could—in fact, I even bought some putty to match the color. | JWMCD Crew | Chris Buttrey | No |  | No |  | Hot | 2 | 8 | No |  | No | No |  |  | No |  | Plate |  |  | 14 | 8
24039 | The Visionary | 2026-03-31 | Wilton Lorenzo | One crew installed panels on the NE ceiling. Two crews installed panels around the atrium; one of them finished and moved to the south to install flashing. Two crews installed the west corner panels; once they finished, one moved to the east vestibule to install panels, and the other moved to the north to install a missing panel, install flashing, and remove protective plastic. Another crew fabricated panels and also helped unload material. | Subcontractor | Carlos Silva | Yes | Two crews lifted panels from the first floor to the roof using a boom lift, with two workers in the basket and two on the roof receiving them. A total of 32 panels, insulation, and girts were moved. Two workers fabricated 4 panels for the east vestibule and helped me unload materials. One of them also helped me move 3 crates from the south to the north, which were the panels that were lifted to the roof. | No |  | Sunny | 21 | 12 | Yes | Parking garage panels, coping | 6 boom lift, 1 scissor lift | No |  |  | Yes | NE patio, atrium | ACM Insulation Subgirt Zee | 33 | 10 | [24 empty] | 168FT | 4 |  |  | 80FT | 4
24079 | Nashville Youth Campus | 2026-03-31 | Obed Bermudez | All crews are working on level two west elevation, moving material, installing delta tape for z-girt, flashing, insulation, panels, rivets, and sleeves. | Subcontractor | Joe Hoyle | No |  | Yes | 1" screws | Clear | 8 | 10 | No |  | Buggy, forklift, conex, boom lifts | No |  |  | Yes | West | Flashing Subgirt Zee Terracotta | [16 empty] | 37 | 50 | [12 empty] | 280 | 29 | 12 | 1
25022 | Vantage VA15 | 2026-03-31 | Ricardo | Yes, we coordinated with the person who will be installing the SWIFT, since we’ve been experiencing delays because of that. We have also been a bit limited in available work areas, as we are unable to install the louvers due to heavy equipment working in front of those areas, and the steel is not ready yet for louver installation. | Subcontractor | Thomas Mooers | Yes | We are short on work areas because we cannot proceed with the louver installation—the steel on the west side still needs to be completed. We need to install them, but we are unable to do so due to heavy equipment working in front of that area. Additionally, we only have access to the south and east sides of the building for panel installation, but we currently do not have the swing stage installed in those areas. | No |  | 84 | 9 | 90 | No |  | Boom lift and scaffold | No |  |  | Yes | North and west elevation | ACM Insulation Subgirt Zee | 4 | 30 | [24 empty] | 125 | 10 |  |  | 240 | 30
25002 | Med Center Health | 2026-03-31 | Kevin Morris | caulked and peeled South elevations, finished installing soffit on South, took down and shortened soffit panel by light, fixed and leveled soffit panel at louver, peeled soffit | Subcontractor | Carlos Silva | No |  | Yes | Drip flashing for stone panels | Good | 6 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM Caulking | 6 | 10 | [18 empty] | 200 | 10
24072 | LCK064 | 2026-03-31 | Mauricio Chavez | Can’t take pictures on-site. | Subcontractor | Joe Hoyle | No |  | No |  | Windy | 4 | 13 | Yes | 65ft boomlift | Yes | No |  |  | Yes | North | Perforated Grage Panels |  |  |  |  | 30 | 13
25059 | Allen Samuels CDJR and LC | 2026-03-31 | Chad McCoy | Caulked all skyward joints on lube center. Caulked all remaining joints on main building amd peeled all panels. Tripped in 4vrrveals . Caulked the soffit panels to single skin soffit on 2 remaining sides of small canopy. Fabbed a small panel cap at end of small canopy soffit. Starting caulking from coping to tpo | Subcontractor | Andre Van Der Merwe | No |  | Yes | Caulking | Partly cloudy 78 | 2 | 10.15 | No |  | 46 foot boom | No |  |  | No |  | ACM | See notes | See notes
25005 | CAT Financial Nashville HQ | 2026-03-30 | Starlin | ! | JWMCD Crew | Chris Buttrey | Yes | Carry the material up to the second floor and go to Home Depot twice. Also, prepare the materials and remove any stagnant stock. | No |  | Hot | 1 | 10 | Yes | Staircase bars | No | No |  |  | No |  | Plate |  |  | 9 | 7
24039 | The Visionary | 2026-03-30 | Wilton Lorenzo | Two crews installed panels around the atrium. Another crew installed panels in the NE patio, level 3. Two more crews installed the remaining panels on the west side, and another crew fabricated panels for that same area four ceiling panels and the corner piece that came undersized. | Subcontractor | Carlos Silva | Yes | One group fabricated 5 panels for the NW, and two other groups installed them. | Yes | Caulking, shims, baker rod, flashing | Sunny | 18 | 12 | No |  | 6 boom lifts, 1 scissor lift | No |  |  | Yes | North, west, east patios | ACM Insulation | 33 | 10 | [24 empty] | 120FT | 4
25002 | Med Center Health | 2026-03-30 | Working in the vertical column with silicone and also moving material and Installing clips for the stone panels | We need 30 pieces of clips for the stone panels 20' flashing for the bottom of the stone panels and 3 missing panels for the vertical column | Subcontractor | Carlos Silva | Yes | 3 panels for the vertical column | Yes | 3 panels for the vertical column Flashing for the stone panels and also clips for the stone panels 30 pieces 20' long | Good condition | 6 | 10 | No |  | Boomlift | No |  |  | No |  | Caulking Hat Channel | [20 empty] | 200 | 20 | [12 empty] | 250 | 30
25007 | QTS ATL2 DC10 | 2026-03-30 | Marvin Blanco | Today the guys couldn't work because Hitt guys don't help closing the entry of the building | Subcontractor | Nick Akins | No |  | No |  | Good condition | 4 | 10 | No |  | Boomlift | No |  |  | No |  | ACM | 2 | 40
25029 | Lourdes CC Phase 2 | 2026-03-30 | Marvin Blanco | Installing ACM panels and also working with the electric guys because they're moving pipes from one side to the other | Subcontractor | Dillon Bowman | No |  | No |  | Good condition | 4 | 12 | No |  | Boomlift | No |  |  | No |  | ACM | 13 | 40
25022 | Vantage VA15 | 2026-03-30 | Ricardo Banegas | The ACM panels that were installed were also modified in the same manner. The modification process took approximately four hours, with two workers assigned to modify the panels and two additional workers assigned to install them. The four-hour duration was due to the panel modifications. | Subcontractor | Thomas Mooers | Yes | We have experienced delays due to limited accessibility to install our materials in certain areas, as we currently do not have the scaffold or swing stage available for installation. At the moment, I am making sure that all my crew stays productive by working in areas where we do have access to install the metal Z. | No |  | 51 | 9 | 90 | No |  | Boom Lift and scaffold | No |  |  | Yes | Southwest and north elevation | ACM Insulation Subgirt Zee | 9 | 40 | [24 empty] | 320 | 10 |  |  | 470 | 30
24072 | LCK064 | 2026-03-30 | Mauricio Chavez | Mobilized to job site, arrived at 12pm. Cant take pictures onsite | Subcontractor | Joe Hoyle | No |  | No |  | Windy | 4 | 7 | No |  | Yes, had to request another boom lift due to issues. | No |  |  | No |  | Perforated Grage Panels |  |  |  |  | 20
24079 | Nashville Youth Campus | 2026-03-30 | Obed Bermudez | All crews are working on level two west elevation, moving material, installing delta tape for z-girt, flashing, insulation, panels, rivets, and sleeves. | Subcontractor | Joe Hoyle | No |  | Yes | 1" screws | Clear | 8 | 10 | No |  | Buggy, forklift, conex, boom lifts | No |  |  | Yes | West | Flashing Subgirt Zee Terracotta | [16 empty] | 9 | 40 | [12 empty] | 430 | 38 | 12 | 2
25002 | Med Center Health | 2026-03-30 | Kevin Morris | Installed 700 LF of clip rails on generator pad, caulked and peeled South elevations | Subcontractor | Carlos Silva | No |  | Yes | Drip flashing for stone panels | Good | 5 | 10 | No |  | 3 boom lifts | No |  |  | No |  | Caulking | [20 empty] | 200
25059 | Allen Samuels CDJR and LC | 2026-03-30 | Chad McCoy | We cut and installed all vertical window flashing. W installed the last 3 top of column flashing. Tripped in 4 reveals. Cut down and installed all the reveals on the soffit panels on the big canopy. Caulked on side of.the small canopy from panel to existing single skin soffit | Subcontractor | Andre Van Der Merwe | No |  | Yes | Caulking | Clear 75 | 2 | 9.5 | No |  | 46 foot boom | No |  |  | No |  | ACM | See notes | See notes
24039 | The Visionary | 2026-03-28 | Wilton Lorenzo | Three crews installed panels on the 4th floor around the atrium, another crew installed panels in the west vestibule, and another crew installed panels on the 4th floor ceiling. | Subcontractor | Carlos Silva | Yes | One group fabricated 2 out of 5 panels that arrived one inch short, | Yes | Caulking, shims, sill flashing, tek screws | Sunny | 20 | 12 | No |  | 6 boom lift, 1 scissor lift | No |  |  | Yes | NE patios, north, west | ACM Flashing | 30 | 12 | [30 empty] | 60FT | 4
25073 | QTS Rebranding | 2026-03-28 | Chad McCoy | We removed 5 panels and 11 aluminum brackets. We took the old panels to our staging area and we remade all the panels and prepped the trailer for tomorrow’s install. | Subcontractor | Andre Van Der Merwe | No |  | No |  | Partly cloudy 55 | 2 | 8 | No |  | 85 foot boom | No |  |  | No |  | ACM | -5 | 1.5
24079 | Nashville Youth Campus | 2026-03-28 | Obed Bermudez | All crews are working on level two west elevation, moving material, installing delta tape for z-girt, flashing, insulation, panels, rivets, and sleeves. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 6 | 8 | No |  | Buggy, forklift, conex, boom lifts | No |  |  | Yes | West | Subgirt Zee Terracotta | [16 empty] | 5 | 24 | [12 empty] | 210 | 24
24039 | The Visionary | 2026-03-27 | Wilton lorenzo | Three crews installed panels in the North patio Level 4 around the atrium. One crew installed panels in the Level 2 patio. Another crew installed panels in the west vestibule, but had to fabricate four panels because the ones delivered came in two pieces and the light fixture ended up centered on the panel joint. Another crew applied caulking and removed protective plastic on the south side. | Subcontractor | Carlos Silva | Yes | One group fabricated 4 panels for the west vestibule. These should have been a single panel matching the glass dimensions, but two panels were sent instead, leaving a joint in the middle of the light. The superintendent requested this to be corrected. (3 guys, 4 panels) | Yes | Tek screws, caulking, shims, sill flashing | Sunny | 17 | 12 | No |  | 6, boom lift, 1 siccsor lift | No |  |  | Yes | East, west, north | ACM Flashing Insulation Subgirt Zee | 37 | 12 | [24 empty] | 230 | 6 |  |  | 60FT | 2 | 80FT | 4
25059 | Allen Samuels CDJR and LC | 2026-03-27 | Chad McCoy | Fabbed and installed the last 2 panels on the job. Tripped in 7 revels. Caulked one side of the big canopy panels to the single skin soffit. Also caulked skyward joints on the big canopy and peeled panels. Caulked 3 vertical joints and made a small filler piece for the coping. | Subcontractor | Andre Van Der Merwe | No |  | Yes | Caulking | Partly cloudy 64 | 2 | 8.75 | No |  | 46 foot boom | No |  |  | No |  | ACM | 1 | 1
25073 | QTS Rebranding | 2026-03-27 | Chad McCoy | Boom moved | Subcontractor | Andre Van Der Merwe | Yes | Equipment moved | No |  | Rain | 2 | 0 | No |  | 85 foot boom | No |  |  | No |  | ACM | 0 | 0
25002 | Med Center Health | 2026-03-27 | Kevin Morris | Installed acm panels on South, took down panels on lower soffit on South to put in correct order | Subcontractor | Carlos Silva | No |  | Yes | Flashing for stone panels | Good | 7 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM Flashing | 25 | 10 | [30 empty] | 200 | 5
24079 | Nashville Youth Campus | 2026-03-27 | Obed Bermudez | All crews are working on level two west elevation, moving material, installing delta tape for z-girt, flashing, insulation, panels, rivets, and sleeves. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 8 | 10 | No |  | Buggy, forklift, conex, boom lifts | No |  |  | Yes | West | Insulation Subgirt Zee Terracotta | [16 empty] | 14 | 40 | [8 empty] | 108 | 10 |  |  | 190 | 30
25002 | Med Center Health | 2026-03-26 | Marvin Blanco | Working in the south elevation around the windows and also top eyebrow cleaning our areas of work | Subcontractor | Carlos Silva | No |  | No |  | Good condition | 7 | 10 | No |  | Boomlift | No |  |  | No |  | ACM | 17 | 70
25007 | QTS ATL2 DC10 | 2026-03-26 | Marvin Blanco | Working in the vertical column with the little boomlift but we still have to put the silicone in the vertical column | Subcontractor | Nick Akins | No |  | Yes | One replace panel in top of the eyebrow and also flashing | Good condition | 4 | 12 | No |  | Boomlift | No |  |  | No |  | ACM | 9 | 48
25029 | Lourdes CC Phase 2 | 2026-03-26 | Marvin Blanco | Installing flashing, Zs insulation and ACM panels the walls are to bad not level and not straight | Subcontractor | Dillon Bowman | No |  | No |  | Good condition | 4 | 12 | No |  | Boomlift | No |  |  | No |  | Subgirt Zee | [30 empty] | 200 | 40
25002 | Med Center Health | 2026-03-26 | Kevin Morris | Installed acm panels on South elevations, installed window closure reveals and acm copping, picked up FS11 crate #7 from shop | Subcontractor | Carlos Silva | No |  | No |  | Good | 7 | 10 | Yes | FS11 crate 7 | 3 boom lifts | No |  |  | No |  | ACM | 25 | 10
25059 | Allen Samuels CDJR and LC | 2026-03-26 | Chad McCoy | Installed 12 panels installed, I if them had to be routed. | Subcontractor | Andre Van Der Merwe | Yes | Panel fab | Yes | Caulking | Clear 65 | 2 | 8 | No |  | 46 foot boom | No |  |  | No |  | ACM | 12 | 6
25073 | QTS Rebranding | 2026-03-26 | Chad McCoy | We installed 16 acm panels on QTs on Shellhorn. We cleaned up and get everything ready to move to manassas | Subcontractor | Andre Van Der Merwe | No |  | No |  | Partly cloudy 71 | 2 | 10 | No |  | 85 foot boom | No |  |  | No |  | ACM | 16 | 9
24079 | Nashville Youth Campus | 2026-03-26 | Obed Bermudez | All crews are working on level two west elevation, moving material, installing delta tape for z-girt, flashing, insulation, panels, rivets, and sleeves. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 8 | 10 | No |  | Buggy, forklift, conex, boom lifts | No |  |  | Yes | West | Subgirt Zee Terracotta | [16 empty] | 26 | 70 | [12 empty] | 148 | 10
25002 | Med Center Health | 2026-03-25 | Kevin Morris | These are photos showing job progress, areas that have not been completed, and scratched or damaged panels | Subcontractor | Carlos Silva | No |  | No |  | Good | 7 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM | 0 | 0
25002 | Med Center Health | 2026-03-25 | Kevin Morris | These are photos showing job progress, areas that have not been completed, and scratched or damaged panels | Subcontractor | Carlos Silva | No |  | No |  | Good | 7 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM | 0 | 0
25002 | Med Center Health | 2026-03-25 | Kevin Morris | These are photos showing job progress, areas that have not been completed, and scratched or damaged panels | Subcontractor | Carlos Silva | No |  | No |  | Good | 7 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM | 0 | 0
25002 | Med Center Health | 2026-03-25 | Kevin Morris | Installed acm panels on South side elevations. | Subcontractor | Carlos Silva | No |  | Yes | FS11 crate 7 picking up tomorrow morning | Good | 7 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM | 34 | 10
25073 | QTS Rebranding | 2026-03-25 | Chad McCoy | 16 panels were fabbed today and yard cleaned up after we got the lull unstuck. MCV acm was used today. But what we took down was 4mm. The only MCV we have is 3mm | Subcontractor | Andre Van Der Merwe | Yes | Lull stuck | No |  | Cloudy 72 | 2 | 11 | No |  | 85 foot boom | No |  |  | No |  | ACM | 0 | 0
25059 | Allen Samuels CDJR and LC | 2026-03-25 | Chad McCoy | Installed last soffit panel. Then took down 9 panels on wall that needs to be furred out. Installed 7 panels on that wall. All 7 of them needed to be cut and routed. Total 8 panels installed | Subcontractor | Andre Van Der Merwe | Yes | Cut and routed | Yes | One case of caulking was sent but 2-3 were needed | Partly cloudy 81 | 2 | 9.5 | No |  | 46 foot boom | No |  |  | No |  | ACM | 8 | 4
25022 | Vantage VA15 | 2026-03-25 | Ricardo Banegas | The layout of the south wall was completed in order to begin installing the panel system, and the installation method was coordinated. | Subcontractor | Thomas Mooers | Yes | The delay is due to one of the boom lifts being down and not yet repaired. We are currently waiting for it to be repaired or replaced, as this has prevented us from making progress in one of the work areas. | No |  | 53 | 10 | 10 | No |  | Boom Lift and scaffold | No |  |  | Yes | South and west elevation | Caulking Subgirt Zee | [20 empty] | 160 | 40 | [8 empty] | 1200 | 60
25022 | Vantage VA15 | 2026-03-25 | Ricardo Banegas | The layout of the south wall was completed in order to begin installing the panel system, and the installation method was coordinated. | Subcontractor | Thomas Mooers | Yes | The delay is due to one of the boom lifts being down and not yet repaired. We are currently waiting for it to be repaired or replaced, as this has prevented us from making progress in one of the work areas. | No |  | 53 | 10 | 10 | No |  | Boom Lift and scaffold | No |  |  | Yes | South and west elevation | Caulking Subgirt Zee | [20 empty] | 160 | 40 | [8 empty] | 1200 | 60
24039 | The Visionary | 2026-03-25 | Wilton Lorenzo | Four crews installed panels in the NE patios. One of the crews lost access to the boom lift and had to use scaffolding to install ceiling panels. Another crew had to move to the west side to start installing panels in the vestibule, since they couldn’t continue on the sloped wall panels in the east due to the handrail being too close to the panel. Another crew finished and then started installing panels on the 4th floor. One more crew installed panels on the north side of the 4th floor. Additionally, one crew finished applying caulking on the north side and removing protective plastic. After that, I moved them to disassemble crates and remove trash since there was a large amount of it. Coping measurements were also taken. We also received two deliveries: one of insulation and another of panels for the west and east vestibules. | Subcontractor | Carlos Silva | No |  | Yes | Caulking, shims, tek screws | Sunny | 18 | 12 | Yes | Insulation, vestibule panels | 6 boom lift, 1 scissor, 1 lull | No |  |  | Yes | NE patios, west | ACM Flashing Insulation Subgirt Zee | 37 | 12 | [24 empty] | 200FT | 4 |  |  | 120FT | 2 | 40FT | 2
24079 | Nashville Youth Campus | 2026-03-25 | Obed Bermudez | All crews are working on level two west elevation, moving material, installing delta tape for z-girt, flashing, insulation, panels, rivets, and sleeves. | Subcontractor | Joe Hoyle | Yes | 1 Boom lift leak | No |  | Clear | 8 | 10 | Yes | 1 pallet of rivets. | Buggy, forklift, conex, boom lifts | No |  |  | Yes | West and south | Subgirt Zee Terracotta | [16 empty] | 3 | 20 | [12 empty] | 460 | 60
25022 | Vantage VA15 | 2026-03-24 | Ricardo Banegas | We experienced delays due to equipment issues, as the machine was not operational and was not repaired. This caused additional delays in both work progress and installation. | Subcontractor | Thomas Mooers | Yes | We experienced delays due to equipment issues, as the machine was not operational and was not repaired. This caused additional delays in both work progress and installation. | No |  | 56 | 10 | 10 | Yes | Screws | Boom Lift and scaffold | No |  |  | Yes | North, west elevation | ACM Coping Insulation Subgirt Zee Trim | 7 | 20 | [24 empty] | 235 | 10 |  |  | 260 | 20 |  |  |  |  | 700 | 20 |  |  | 230 | 30
24039 | The Visionary | 2026-03-24 | Wilton Lorenzo | Five crews installed panels at the NE patio on Levels 1, 2, and 3. One crew installed panels at the south patio on Level 4. Another crew applied caulking and removed protective plastic from the panels at the NW patio. Delays: Yes The crew on Level 3 waited approximately two hours for a sprinkler to be relocated, as it was too close to the joint of the ceiling panels. On the opposite side, there was also a light fixture interfering, which will be moved tomorrow. After that, paver cutting began, creating excessive dust, so the crew was moved to Level 4 to continue panel installation. The NW crew was reassigned at 5:00 PM to clean up debris in the west and south areas. | Subcontractor | Carlos Silva | Yes | The crew on Level 3 waited approximately two hours for a sprinkler to be relocated, as it was too close to the joint of the ceiling panels. On the opposite side, there was also a light fixture interfering, which will be moved tomorrow. After that, paver cutting began, creating excessive dust, so the crew was moved to Level 4 to continue panel installation. | Yes | 1/16 shims, caulking black/gray, insulation | Sunny | 18 | 12 | No |  | 6 boom lift, 1 scissor lift | No |  |  | Yes | NE patios | ACM | 54 panels | 12
25022 | Vantage VA15 | 2026-03-24 | Ricardo Banegas | We experienced delays due to equipment issues, as the machine was not operational and was not repaired. This caused additional delays in both work progress and installation. | Subcontractor | Thomas Mooers | Yes | One of the machines is still out of service, and a crane was installed in the north area, which prevented access to install the metal Z and panels. | No |  | 30 | 10 | 10 | Yes | 24 crates of louvers | Boom Lift and scaffold | No |  |  | No |  | Caulking Coping Subgirt Zee Trim | [20 empty] | 83 | 20 | [8 empty] | 270 | 20 |  |  |  |  | 240 | 20 |  |  | 80 | 20
24079 | Nashville Youth Campus | 2026-03-24 | Obed Bermudez | The first crew is working on level two west elevation, while the second crew is working at the courthouse level two east elevation. The third crew is working on the west elevation level 2, moving material, installing delta tape for z-girt, insulation, and flashing. | Subcontractor | Joe Hoyle | Yes | Boom lift leaking fluid | No |  | Clear | 8 | 10 | No |  | Buggy, forklift, conex, boom lifts | No |  |  | Yes | West and south | Flashing Insulation Subgirt Zee | [26 empty] | 734 | 50 |  |  | 322 | 20 | 104 | 10
25002 | Med Center Health | 2026-03-24 | Kevin Morris | Installed acm panels on South elevation, measured lower soffit panels on South to determine correct order of install with Nick, trim missing for corrugated panels on roof, took measurements for Carlos inside main entrance, sent photos to Carlos for missing/ wrong size acm panels on South | Subcontractor | Carlos Silva | No |  | No |  | Good | 8 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM Flashing | 25 | 10 | [30 empty] | 80 | 3
25073 | QTS Rebranding | 2026-03-24 | Chad McCoy | 17 panels were removed and one put back that didn’t have holes in it. 16 panels were taken to the yard for tomorrow fab | Subcontractor | Andre Van Der Merwe | No |  | No |  | Windy and 78 | 2 | 5 | No |  | 85 foot boom | No |  |  | No |  | ACM | 1 | 0.5
25059 | Allen Samuels CDJR and LC | 2026-03-24 | Chad McCoy | Installed the last column panel. Took all the females off of the soffit panels and put angles on them and screwed them to the steel and squared them. Then we fabbed 7 soffit panels and installed 6 of them. | Subcontractor | Andre Van Der Merwe | Yes | Panel mods | Yes | Caulking 2-3 cases | Partly cloudy and windy 78 | 2 | 9.15 | No |  | 46 foot boom | No |  |  | No |  | ACM | 7 | 5
24079 | Nashville Youth Campus | 2026-03-23 | Obed Bermudez | The first crew is working on level 2 west elevation, while the second crew is working at the courthouse south elevation. The third crew is working on the west elevation, moving material, installing z-girt, insulation, tape, and flashing. | Subcontractor | Joe Hoyle | No |  | Yes | Drip flashing | Clear | 6 | 10 | Yes | 2 boxes of rivets | Buggy, forklift, conex, boom lifts. | No |  |  | Yes | West/south | Flashing Insulation Subgirt Zee | [26 empty] | 293 | 20 |  |  | 240 | 20 | 292 | 20
25059 | Allen Samuels CDJR and LC | 2026-03-23 | Chad McCoy | We installed 6 panels had to modify to panels on the last column. Like always we had to take off and cut down all extrusions. The last column was hell to get level amd square. | Subcontractor | Andre Van Der Merwe | Yes | Panel mods | Yes | Caulking. 2-3 cases | Partly cloudy 68 | 2 | 8.5 | No |  | 46 foot boom | No |  |  | No |  | ACM | 6 | 5
25022 | Vantage VA15 | 2026-03-22 | Ricardo Banegas | The layout for each panel installation area was completed, and material was moved and organized in Levels 6, 7, and 8. | Subcontractor | Thomas Mooers | No |  | No |  | 44 | 10 | 10 | Yes | Caulking and plastic shims | Boom Lift and scaffold | No |  |  | Yes | North | ACM Coping Insulation Subgirt Zee Trim | 17 | 40 | [24 empty] | 1152 | 20 |  |  | 230 | 20 |  |  |  |  | 510 | 20 |  |  | 120 | 20
24077 | IAD 667 TI | 2026-03-22 | Fredy veliz | We are demobilizing for asphalt work ,all materials are organized out the way ,both oft the 150 articulate are out of service real bad leaks one on the block one on the wheel ,70% of the job is 100% complete Need 4 week maximum 5 to get the rest of the work done if get the equipment in good conditions | Subcontractor | Chris Buttrey | Yes | Demobilization for asphalt work | No |  | Good | 8 | 6 | No |  | 2 150 articulated boom lift ,65 straight boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing blades on elevation sc3 section 10, installing blades on elvation sc2 section 16 ,organizing materials | 48
25022 | Vantage VA15 | 2026-03-22 | Ricardo Banegas | The layout for each panel installation area was completed, and material was moved and organized in Levels 6, 7, and 8. | Subcontractor | Thomas Mooers | No |  | No |  | 44 | 10 | 10 | No |  | Boom Lift and scaffold | No |  |  | Yes | North | ACM Coping Insulation Subgirt Zee Trim | 9 | 20 | [24 empty] | 760 | 20 |  |  | 230 | 20 |  |  |  |  | 800 | 30 |  |  | 220 | 20
24039 | The Visionary | 2026-03-22 | Wilton lorenzo | One crew install panels on the SW patio, another crew installed panels on the south | Subcontractor | Carlos Silva | No |  | Yes | Insulation, tek screws | Sunny | 6 | 8 | No |  | 6 boom lift, 1 siccsor lift | No |  |  | Yes | South | ACM | 16 panels | 4
24079 | Nashville Youth Campus | 2026-03-21 | Obed Bermudez | The first crew is working on level 2 south elevation, while the second crew is installing at the courthouse. The third crew is working on the west elevation, moving material, installing z-girt, insulation, and flashing. | Subcontractor | Joe Hoyle | No |  | Yes | Drip flashing above window | Clear | 6 | 5 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | Yes | West and south | Flashing Insulation Subgirt Zee | [26 empty] | 96 | 10 |  |  | 130 | 10 | 160 | 10
25073 | QTS Rebranding | 2026-03-21 | Chad McCoy | We finished the second set of lovkridge and cleaned up for the boom to be moved to | Subcontractor | Andre Van Der Merwe | No |  | No |  | Partly cloudy 71 | 2 | 6 | No |  | 85 foot boom | No |  |  | No |  | ACM | 9 | 5
25059 | Allen Samuels CDJR and LC | 2026-03-21 | Chad McCoy | Routed 3 soffit panels and installed the 5 soffit panels. Had to drill through weld so took a little bit. Broke a bunch of bits. Modified the lengths of the 2 column panels. Had to cut down the extrusions because they were too long. Installed 3 column panels total 7 panels | Subcontractor | Andre Van Der Merwe | Yes | Routed 3 soffit panels and installed the 5 soffit panels. Had to drill through weld so took a little bit. Broke a bunch of bits. Modified the lengths of the 2 column panels. Had to cut down the extrusions because they were too long. Installed 3 column panels total 7 panels. To install the column panels I've had to cut down the female extrusion to gain the space to square the panel. I have to take the extrusion off of the panel then secure the extrusion to the table to cut it. I put the extrusion back on. I have to take off and cut down other extrusions on the panels because they are too long and impede the reveal going to the other extrusion. ( modifying panels that come incorrect from the shop) . | No |  | Clear 79 | 2 | 8.5 | No |  | 46 foot boom | No |  |  | No |  | ACM | 7 | 6
24039 | The Visionary | 2026-03-21 | Wilton Lorenzo | Two crews finished installing panels on the north elevation. After that, I moved one crew to the SW patio level 4 and another crew to the south patio level 4. One crew installed panels at the NE patio level 1. Two additional crews installed panels on the south eyebrow, and one crew applied caulking to the vertical joints on the west side. | Subcontractor | Carlos Silva | No |  | Yes | Insulation, caulking, tek screws | Sunny | 18 | 9 | No |  | 6 boom lift, 1 scissor lift, | No |  |  | Yes | NW, south | ACM Caulking | 34 panels | 12 | [18 empty] | 40FT | 2
25031 | LLU Mars US Warehouse | 2026-03-21 | Abner aguilar | 2 crated delivered panel and we put the flashing on the other building and clean the site and peel all the cam panel | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | Yes | Screws and acm panels | Boom lift | No |  |  | No |  | ACM | 2 | 44
24077 | IAD 667 TI | 2026-03-20 | Fredy veliz | We are getting ready to demobilize today and tomorrow ,we are trying to install as much we can so we don't have to organize to much materials for asphalt work ,leaving some areas open at the doors for gc equipment | Subcontractor | Chris Buttrey | Yes | Getting prep for demobilization for 2 weeks | No |  | Good | 8 | 80 | No |  | 2 150 articulate boom lifts ,65 straight,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing blades sc2 section 8,9 and 10 ,installing braces and blades sc2 section 8 | 80
24039 | The Visionary | 2026-03-20 | Wilton Lorenzo | 4 crews installed panels on the north elevation, 2 crews installed panels on the south elevation, and 1 crew installed panels on the roof. 4 ground helpers | Subcontractor | Carlos Silva | No |  | Yes | Insulation, screws, shims, | Sunny | 18 | 12 | No |  | 6 boom lift, 1 scissor lift, | No |  |  | Yes | NW, south | ACM Insulation Subgirt Zee | 48 | 14 | [24 empty] | 300 | 6 |  |  | 200Ft | 6
24079 | Nashville Youth Campus | 2026-03-20 | Obed Bermudez | The first crew continues working on level 2 south elevation, the second crew continues installing at the courthouse while the third continues working on the west elevation, moving material, installing z girt, insulation, and flashing. | Subcontractor | Joe Hoyle | No |  | Yes | Drip flashing above window | Clear | 8 | 10 | Yes | Insulation | Buggy, forklift, conex, boom lifts. | No |  |  | Yes | West and south | Flashing Insulation Subgirt Zee | [26 empty] | 1360 | 50 |  |  | 610 | 25 | 50 | 5
25073 | QTS Rebranding | 2026-03-20 | Chad McCoy | We finished one side of shellhorn. And we started the second side till it started storming. | Subcontractor | Andre Van Der Merwe | Yes | Weather. Wind and lightning | No |  | Partly cloudy and evening storms | 2 | 10 | No |  | 85 foot boom | No |  |  | No |  | ACM Caulking | 21 | 9 | [18 empty] | 15 | 0.5
25059 | Allen Samuels CDJR and LC | 2026-03-20 | Chad mccoy | Modified and installed the remaining 4 panels on the column. Squared the soffit panels on one side of the big canopy. We then got dimensions and fabbed 3 soffit panels. | Subcontractor | Andre Van Der Merwe | Yes | Modified and installed the remaining 4 panels on the column. Squared the soffit panels on one side of the big canopy. We then got dimensions and fabbed 3 soffit panels. | No |  | Partly cloudy | 2 | 8 | No |  | 46 foot boom | No |  |  | No |  | ACM | 4 | 3
25022 | Vantage VA15 | 2026-03-20 | Ricardo Banegas | The layout for each panel installation area was completed, and material was moved and organized in Levels 6, 7, and 8. | Subcontractor | Thomas Mooers | No |  | No |  | 44 | 10 | 10 | Yes | Caulking and plastic shims | Boom Lift and scaffold | No |  |  | Yes | North | ACM Insulation Subgirt Zee | 21 | 60 | [24 empty] | 1046 | 20 |  |  | 230 | 20
24077 | IAD 667 TI | 2026-03-19 | Fredy veliz | We are getting everything organized to demobilize this week ,the areas that we can work do on 668 are not big enough to move there and it will affect 667 if we do that, so we gonna have to demobilize until they get the asphalt work done | Subcontractor | Chris Buttrey | No |  | No |  | Good | 8 | 88 | No |  | 2 150 articulate boom lift ,65 straight boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing channel and braces elevation sc3 section 8,9 and 10 , installing braces and blades elevation sc2 section 17 and 18 | 88
24039 | The Visionary | 2026-03-19 | Wilton Lorenzo | Four crews installed panels on the west parapet. After 4:00 PM, they finished, and two of those crews moved to the north side to continue working. The other two crews installed panels on the north reflecting ceiling, and one crew installed panels on the west side of the roof. There are two panels for the reflecting ceiling that have not arrived, and one corner piece came in undersized. JWM will send ACM sheets so they can be fabricated in the field. | Subcontractor | Carlos Silva | No |  | Yes | Insulation, 2" tek screws, | Sunny | 18 | 12 | No |  | 6 boom lift, 1 scissor lift | No |  |  | Yes | North west | ACM Insulation Subgirt Zee | 40 panels | 14 | [24 empty] | 330 | 6 |  |  | 130 | 4
25022 | Vantage VA15 | 2026-03-19 | Ricardo Banegas | Material was moved from the 1st floor to the 6th floor. A boom lift was used because the panels were too large and did not fit in the north elevator on the day we needed to transport them. Therefore, we had to find an alternative way to move them up. | Subcontractor | Thomas Mooers | Yes | The delay we experienced occurred in the morning due to congestion in the north area. Work started at 9:00 AM in the north area and continued in the scaffold area as well. We also experienced delays in material movement from the 1st floor to the 6th floor. A gully/telehandler was used due to the large size of the panels. | No |  | 22 | 10 | 10 | Yes | Metal z | Boom Lift scaffold | No |  |  | Yes | North side | ACM Insulation Subgirt Zee | 18 | 60 | [24 empty] | 1046 | 30 |  |  | 230 | 10
24079 | Nashville Youth Campus | 2026-03-19 | Obed Bermudez | The first crew continues working on level 2 south elevation, the second crew continues installing at the courthouse while the third continues working on the west elevation, moving material, installing z girt, insulation, and flashing. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 8 | 10 | Yes | Fiber cement panels | Buggy, forklift, conex, boom lifts. | No |  |  | Yes | West | Flashing Insulation Subgirt Zee | [26 empty] | 1056 | 40 |  |  | 620 | 35 | 24 | 5
25059 | Allen Samuels CDJR and LC | 2026-03-19 | Chad McCoy | Took down 2 panels on first column. Installed 6 panels on that column all had to be modified. Then took down 2 panels on the other column modified them and installed the 2 back up. Total 8 panels | Subcontractor | Andre Van Der Merwe | Yes | Columns are wrong and don’t wrap correct | Yes | Caulking | Partly cloudy 53 | 2 | 8.15 | No |  | 46 foot boom | No |  |  | Yes | Small canopy columns | ACM | 8 | 6
25073 | QTS Rebranding | 2026-03-19 | Chad McCoy | We made 25 panels today and prepped everything for install tomorrow. We cleaned up and restated the yard. For the Shellhorn job | Subcontractor | Andre Van Der Merwe | No |  | No |  | Partly cloudy 68 | 2 | 10 | No |  | 85 foot boom | No |  |  | No |  | ACM | 0 | 10
24077 | IAD 667 TI | 2026-03-18 | Fredy veliz | One of the 150 boom lifts has some issues we called for service ,the mechanic show up and check the machine ,they say the conditions of the ground is the cause ,we set the machine level but still having those codes comping up ,the machine is working we just have to turn it off and on and keep trying ,some of those machines are different and work different | Subcontractor | Chris Buttrey | No |  | No |  | Cold | 8 | 80 | No |  | 2 150 articulate boom lift , 65 straight boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing Channels on elev sc3 section 9 and installing clips on section 8 ,installing braces and blades elevation sc2 section 19 and 20 | 80
25059 | Allen Samuels CDJR and LC | 2026-03-18 | Chad McCoy | I need this job to finish. But Everytime we turn around there is more crap to fix. Installed 7 panels. One coping corner glue up was fabbed on both lengths. One lennel soffit was fabbed. | Subcontractor | Andre Van Der Merwe | No |  | Yes | Caulking | Partly cloudy 41 | 2 | 8.15 | No |  | 46 foot boom | No |  |  | Yes | Everything has to be played out to see if it even fits or how we can fix these issues | ACM | 7 | 6
25073 | QTS Rebranding | 2026-03-18 | Chad McCoy | This morning we went to QTs and played out all electrical penetrations for the GC. Then we went to our lay down and started cutting out Panels. 30 panels were laid out and cut and 8 were fully fabbed | Subcontractor | Andre Van Der Merwe | No |  | No |  | Partly cloudy 41 | 2 | 10.5 | No |  | 85 foot boom | No |  |  | No |  | ACM | 0 | 0
24039 | The Visionary | 2026-03-18 | Wilton Lorenzo | Two crews installed panels on the NW reflecting ceiling. Two additional crews installed panels on the north reflecting ceiling. One crew installed panels on the west roof, and another crew installed panels on the level 1 ceiling. | Subcontractor | Carlos Silva | No |  | Yes | Insulation, 2" tek screws | Sunny | 17 | 12 | No |  | 6 boom lift, 1 siccsor lift | No |  |  | Yes | North west | ACM Insulation Subgirt Zee | 40 panels | 12 | [24 empty] | 256FT | 6 |  |  | 80 FT | 2
24079 | Nashville Youth Campus | 2026-03-18 | Obed Bermudez | The first crew continues working on level 2 south elevation, the second crew continues installing at the courthouse while the third continues working on the west elevation, moving material, installing z girt, insulation, and flashing. | Subcontractor | Joe Hoyle | No |  | No |  | Cloudy | 8 | 10 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | Yes | West/south | Flashing Insulation Subgirt Zee | [26 empty] | 496 | 30 |  |  | 400 | 30 | 270 | 20
25031 | LLU Mars US Warehouse | 2026-03-18 | Abner aguilar | No | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | No |  | Coping | [40 empty] | 20 | 44
25050 | LTW062 Fit Out | 2026-03-17 | Mauricio Chavez | Completed all work, mobilizing back home | Subcontractor | Dillon Bowman | No |  | No |  | Windy | 5 | 8 | No |  | Yes | No |  |  | Yes | All elevations | Trim | [36 empty] | 10
24077 | IAD 667 TI | 2026-03-17 | Fredy veliz | The sections on the doors we have to leave open because gc has equipment inside the gen yard and steel company don't have the stairs and hand rails complete | Subcontractor | Chris Buttrey | Yes | Windy ,steel company have incomplete work ,Gc equipment inside the gen yard | No |  | Cold and windy | 8 | 64 | No |  | 2 150 articulate boom lift ,65 straight boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing channels sc3 section 10 installing clips on section 9 ,installing braces And blades ,sec2 section 7,8 | 64
24039 | The Visionary | 2026-03-17 | Wilton Lorenzo | Two crews installed panels on the NE reflecting ceiling. One crew installed panels in the north area but experienced delays because the panels were out of square and did not fit properly. One crew finished installing panels on the south ceiling. Another crew installed panels on the roof, and one more crew started installing panels on the east ceiling at level 1. The boom lift is still down, and I’m unable to assign another crew to work on the exterior. | Subcontractor | Carlos Silva | Yes | The boom lift is still down, and I’m unable to assign another crew to work on the exterior. | Yes | 2" tek screws, shims, insulation, flashing | Sunny | 17 | 12 | No |  | 6 boom lift, 1 scissor lift | No |  |  | Yes | NW corner, east, | ACM Insulation | 43 | 12 | [24 empty] | 130 | 4
25022 | Vantage VA15 | 2026-03-17 | Ricardo | Material was moved and distributed starting at 4:30 a.m. due to the removal of the exterior elevator. | Subcontractor | Thomas Mooers | Yes | Most of the delays we experience are due to a lack of proper work area distribution. On this particular day, we were unable to work because there was heavy equipment operating in the north area for steel installation. For this reason, I had to reassign my crew in order to install as many panels as possible. | Yes | Metal z and Coulking | 21 | 10 | 12 | No |  | Boom Lift and scaffold | No |  |  | Yes | Northwest and west area | ACM Insulation Subgirt Zee | 12 | 40 | [24 empty] | 532 | 20 |  |  | 210 | 20
25031 | LLU Mars US Warehouse | 2026-03-17 | Abner aguilar | No | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | No |  | ACM Coping | 11 | 44 | [38 empty] | East Elevation 4 | 44
24079 | Nashville Youth Campus | 2026-03-17 | Obed Bermudez | The first crew started working on level 2 south elevation, the second crew continues installing at the courthouse while the third continues working on the west elevation, moving material, installing z girt, insulation, and flashing. | Subcontractor | Joe Hoyle | No |  | Yes | Black caulking | Clear | 8 | 10 | Yes | 1 pallet of flashing and 1 crate of hardware. | Buggy, forklift, conex, boom lifts. | No |  |  | No |  | Flashing Insulation Subgirt Zee | [26 empty] | 400 | 40 |  |  | 190 | 20 | 120 | 20
25059 | Allen Samuels CDJR and LC | 2026-03-17 | Chad McCoy | Took down 15 panels and installed 16. 3 had to be fabbed including 2 glue up corners | Subcontractor | Andre Van Der Merwe | No |  | Yes | Caulking | Clear 35 | 2 | 8 | No |  | 46 foot boom | No |  |  | No |  | ACM | 16 | 6
25073 | QTS Rebranding | 2026-03-17 | Chad mccoy | 15 panels were removed. And we had to remove all the insulation. We took all the trash to our laydown for disposal and set up for fabrication tomorrow | Subcontractor | Andre Van Der Merwe | No |  | No |  | Cloudy and windy 36 | 2 | 6.5 | No |  | 85 foot boom | No |  |  | No |  | ACM | -15 | 2.5
24039 | The Visionary | 2026-03-16 | Wilver Quiroz | Two teams worked installing panels, insolation in the sky on the south elevation A team worked installing panels in the southwest corner of the building and worked on the north side of the building Two teams worked installing panels in the sky on the west elevation of the building A team worked installing panels and insulation on the walls of the patios on the east side of the building And three guys worked preparing panels and passing material to the installers. We couldn’t work well today due to the bad weather and we saw that we had to retire early | Subcontractor | Carlos Silva | No |  | No |  | Cloudy, strong wind | 17 | 3 | No |  | 6 boom lift, 1 scissor lift and 1 lull | No |  |  | Yes | North, south, east and west | ACM | 10 | 36
24077 | IAD 667 TI | 2026-03-16 | Fredy veliz | No work because the rail | Subcontractor | Chris Buttrey | Yes | Raining | No |  | Raining | 1 | 0 | No |  | 2 150 articulate boom lift ,65 straight boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | Didn't work | 0
25050 | LTW062 Fit Out | 2026-03-16 | Mauricio Chavez | Can’t take photos in site. Left early due to severe thunderstorm moving in area | Subcontractor | Dillon Bowman | No |  | No |  | Windy and rain | 5 | 7 | No |  | Yes | No |  |  | Yes | All elevations | Coping | [40 empty] | 100 ft
25031 | LLU Mars US Warehouse | 2026-03-16 | Abner | No | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | Yes | South elevation | ACM | 14 | 44
24079 | Nashville Youth Campus | 2026-03-16 | Obed Bermudez | Two crews continue working on the east elevations of the courthouse, while a third crew continues working on the south elevation, moving material, installing flashing, z-girt, and insulation. | Subcontractor | Joe Hoyle | No |  | Yes | Jamb flashing, black caulking | Windy | 7 | 10 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | Yes | Courthouse. | Flashing Insulation Subgirt Zee | [26 empty] | 444 | 30 |  |  | 182 | 20 | 36 | 10
25059 | Allen Samuels CDJR and LC | 2026-03-16 | Chad McCoy | Just continuing with these crazy panels | Subcontractor | Andre Van Der Merwe | No |  | Yes | Caulking | Cold windy 38 | 2 | 8.15 | No |  | 46 foot boom | No |  |  | No |  | ACM | 19 | 7
25073 | QTS Rebranding | 2026-03-16 | Chad McCoy | We took down 15 panels and all insulation, and hauled off all material, We set our laydown area up and | Subcontractor | Andre Van Der Merwe | Yes | Storms and tornado warning for a couple hrs | No |  | Storms? Tornado high winds | 2 | 7 | No |  | 85 foot boom | No |  |  | No |  | ACM | -15 | 3
25022 | Vantage VA15 | 2026-03-16 | Ricardo Banegas | We’ve had many delays due to the weather conditions. We only moved and distributed the material to the bus side since we were not able to complete the material mobilization. We will be starting tomorrow at 4:30 a.m. to continue moving materials, as the exterior elevator will be removed. | Subcontractor | Thomas Mooers | Yes | We’ve had many delays due to the weather conditions. We only moved and distributed the material to the bus side since we were not able to complete the material mobilization. We will be starting tomorrow at 4:30 a.m. to continue moving materials, as the exterior elevator will be removed. | Yes | Metal Z | 33 | 10 | 5 | No |  | Boom lift scaffold | No |  |  | No |  | Subgirt Zee | [30 empty] | 0 | 50
24077 | IAD 667 TI | 2026-03-15 | Fredy veliz | We are trying to close the elevation sc2 but gc still have equipment inside and hang rails are not complete | Subcontractor | Chris Buttrey | Yes | Can't close sc2 walls until the get done with the scissor lifts on gen yard | No |  | Good | 8 | 64 | No |  | 2 150 reticulate boom lift ,65 straight boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing blades and blades sc2 section 6 and 7 ,installing clips elvation sc3 sections 6 to 10 | 64
25031 | LLU Mars US Warehouse | 2026-03-15 | Abner aguilar | We change a damage panel remove 6 panel that have a fabric disperfecation and never 2 of the ceiling reflecting panel because the gc said the need to move a star case and the door frame need to be coulking before we put the panelcl | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | No |  | ACM | 6 | 44
24077 | IAD 667 TI | 2026-03-14 | Fredy veliz | Elevation sc2 at the door we have to leave those section out ,the hand rail company need to move the material in before we close those areas | Subcontractor | Chris Buttrey | Yes | We have to leave some section out hand rails no complete | No |  | Good | 8 | 64 | No |  | 2 150 articulate boom lift ,65 straight boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing channels sc2 section 14,15 installing clips sc3 sections 6 to 10 | 64
25055 | Mercedes Body Shop Reno | 2026-03-14 | Chad McCoy | The caulking on the columns was finished today. The kick plates at the bottom of the columns was hand rolled and installed today. I made 8 more panels today. Panels were peeled and 4 reveals tripped in | Subcontractor | Andre Van Der Merwe | Yes | Making panels is a delay. | No |  | Partly cloudy. | 4 | 7.5 | No |  | 46 foot boom | No |  |  | No |  | ACM Caulking | 8 | 6 | [18 empty] | 100 | 5
25031 | LLU Mars US Warehouse | 2026-03-14 | Abner aguilar | No | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | Yes | West reflecting ceiling | ACM Subgirt Zee | 17 | 44 | [28 empty] | 15 | 44
24039 | The Visionary | 2026-03-14 | Wilver Quiroz | Two teams worked installing panels, insolation in the sky on the south elevation A team worked installing panels in the southwest corner of the building and worked on the north side of the building Two teams worked installing panels in the sky on the west elevation of the building A team worked installing panels and insulation on the walls of the patios on the east side of the building And three guys worked preparing panels and passing material to the installers. | Subcontractor | Carlos Silva | No |  | No |  | Sunny | 17 | 9 | No |  | 6 boom lift and 1 lull | No |  |  | Yes | North, south, east and west | ACM Insulation Subgirt Zee | 25 | 117 | [24 empty] | 160 | 5 |  |  | 110 FT | 3
24079 | Nashville Youth Campus | 2026-03-14 | Obed Bermudez | Two crews continue working on the east elevations of the courthouse, while a third crew continues working on the south elevation, moving material, installing flashing, z-girt, and insulation. | Subcontractor | Joe Hoyle | No |  | Yes | Jamb flashing, black caulking | Clear | 6 | 8 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | No |  | Flashing Insulation Subgirt Zee | [26 empty] | 596 | 25 |  |  | 284 | 15 | 120 | 8
25002 | Med Center Health | 2026-03-14 | Kevin Morris | Finished cleaning and removing all material from roof, installed acm panels on soffit on South, caulking on South, started base flashing on South, installed last 2 stone panels on South stair tower | Subcontractor | Carlos Silva | No |  | Yes | Flashing already notified Carlos | Good | 10 | 8 | No |  | 5 boom lifts | No |  |  | Yes | South buck hoist area | ACM Caulking Flashing Terracotta | 10 | 8 | [14 empty] | 2 | 2 |  |  | 120 | 8 | [10 empty] | 20 | 1
24079 | Nashville Youth Campus | 2026-03-13 | Obed Bermudez | Three crews continue working on the east elevation of the courthouse, moving materials, installing insulation, flashing, and z-girt. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 6 | 10 | Yes | Z girt | Buggy, forklift, conex, boom lifts. | No |  |  | No |  | Flashing Insulation Subgirt Zee | [26 empty] | 352 | 25 |  |  | 118 | 10 | 384 | 25
24077 | IAD 667 TI | 2026-03-13 | Fredy veliz | Move the equipment take a lot time ,this morning we spent 2 hours to move the boom lifts to the next sections ,o lot materials in the areas ,and we had to stop all activities at noon because of the wind | Subcontractor | Chris Buttrey | Yes | Materials on the way and high winds afternoon | No |  | Windy | 8 | 48 | No |  | 2 150 articulate boom lift ,65 straight boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | Moving boom lifts ,installing clips elevation sc3 section 6 to 10 ,installing channels sc2 section 14 and 15 | 48
25050 | LTW062 Fit Out | 2026-03-13 | Mauricio Chavez | Can’t take pictures inside jobsite | Subcontractor | Dillon Bowman | No |  | No |  | Very windy | 5 | 9.5 | No |  | Yes | No |  |  | No |  | Trim | [36 empty] | 100ft
24039 | The Visionary | 2026-03-13 | Wilver quiroz | Two teams worked installing panel, insolation in the sky on the southern elevation Two teams worked half a day installing a panel in the southwest elevation sky. The other half day they worked installing a panel in the southwest corner. Two teams worked installing a panel on the northwest elevation of the building A team worked installing panel and insulation on the walls of the courtyards on the east side of the building And three guys worked preparing panels and passing material to the installers. Two deliveries of material arrived. | Subcontractor | Carlos Silva | Yes | They have not placed a water protector in the areas where the water is filtered to be able to install our panels | No |  | Sunny | 19 | 12 | Yes | Acm panel | 6 boom lift and 1 lull | No |  |  | Yes | South, east and west | ACM Insulation Subgirt Zee | 33 | 180 | [24 empty] | 96FT | 4 |  |  | 100 FT | 4
25031 | LLU Mars US Warehouse | 2026-03-13 | Abner aguilar | No | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | Yes | South elevation reflecting ceiling | ACM Insulation Subgirt Zee Trim | 13 | 44 | [24 empty] | 156 | 44 |  |  | 120 | 44 |  |  |  |  | South elevation | 44
25002 | Med Center Health | 2026-03-13 | Kevin Morris | Installed acm panels on South, clean roof, caulking on South | Subcontractor | Carlos Silva | No |  | No |  | Good | 11 | 10 | No |  | 5 boom lifts | No |  |  | No |  | ACM Caulking Terracotta | 16 | 10 | [14 empty] | 2 | 2 |  |  | 200 | 10
25055 | Mercedes Body Shop Reno | 2026-03-13 | Chad McCoy | 10 panels removed. 12 panels installed. All panels have to be cut and routed or made out of older panels bc of elevation bust with the only horizontal joint tha was missed. | Subcontractor | Andre Van Der Merwe | Yes | More making panels | No |  | Partly cloudy. Windy | 4 | 8.5 | No |  | 46 foot boom | No |  |  | Yes | Panels are made off of layout done on windows | ACM Caulking | 12 | 8 | [18 empty] | 110 | 7
24039 | The Visionary | 2026-03-12 | Wilver Quiroz | Two teams installed panels on the south reflective roof Level 4. Two teams installed panels on the SW reflective roof. A team installed a panel in the tower of the south staircase. And then he worked on the layout of the west side of the building Another team installed panels on the roof. A team made panels for the balcony on the east side Another team installed panels on the walls of the east balconies | Subcontractor | Carlos Silva | Yes | Wait for them to seal the water filter where the panels were removed | No |  | Sunny | 19 | 12 | No |  | 6 boom lift, 1 lull | No |  |  | Yes | West,south | ACM Insulation Subgirt Zee | 30 | 156 | [24 empty] | 352ft | 3 |  |  | 100ft | 2
24077 | IAD 667 TI | 2026-03-12 | Fredy veliz | No work | Subcontractor | Chris Buttrey | Yes | Weather | No |  | Raining | 1 | O | No |  | 2 150 articulate boom lift | No |  |  | No |  | Louvre | [24 empty] | N/a | 0
25031 | LLU Mars US Warehouse | 2026-03-12 | Abner aguilar | No | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | Yes | South elevation | ACM | 16 | 44
25050 | LTW062 Fit Out | 2026-03-12 | Mauricio Chavez | Can’t take pictures inside jobsite | Subcontractor | Dillon Bowman | Yes | Got rained/snowed out | No |  | Windy, rain, and snow | 5 | 8 | Yes | Z trim | Yes | No |  |  | No |  | Coping Trim | [36 empty] | 175 ft |  |  |  | 90 ft
24079 | Nashville Youth Campus | 2026-03-12 | Obed Bermudez | Two crews continue working on the south elevation third floor, moving material, installing flashing, z girt, insulation. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 4 | 10 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | No |  | Flashing Insulation Subgirt Zee | [26 empty] | 444 | 20 |  |  | 222 | 16 | 48 | 4
25055 | Mercedes Body Shop Reno | 2026-03-12 | Chad McCoy | Columns caulking was started. The problem with this is the structure moves. So as u caulk the horizontals it belly’s out. Flashing z and insul was installed for when the rest of my guys get here | Subcontractor | Andre Van Der Merwe | Yes | Drop selling guys on canopy are in the way | Yes | Caulking | Storms coming | 1 | 8 | No |  | 46 foot boom | No |  |  | No |  | Caulking Flashing Insulation Subgirt Zee | [20 empty] | 140 | 4.5 |  |  |  |  | 60 | 1.5 |  |  | 100 | 1 | 45 | 1.5
24089 | BSU Innovation Center | 2026-03-12 | Obed Bermudez | The crew replaced three channels on the south elevation, moved the longboard material to the lay-down area and cleaned up the site. | Subcontractor | Marc Ribar | Yes | We are leaving site | No |  | Clear | 3 | 9 | No |  | Boom lift | No |  |  | Yes | North soffit | Flashing | [32 empty] | 1
24039 | The Visionary | 2026-03-11 | Wilver Quiroz | Two crews installed panels in the South reflecting ceiling Level 4. Two crews installed panels in the SW reflecting ceiling. One crew installed panels in the South stair tower. Another crew installed panels on the roof. Two crews spent about 3 hours trying to locate where the water is entering the building. One crew removed 3 panels, and the other crew removed 17 panels. This took about 4 hours with two guys, since there is an area where water is ponding and staying trapped. | Subcontractor | Carlos Silva | Yes | Trying to find where the water filters into the building | No |  | Cloudy | 20 | 12 | No |  | 5 boom lifts and 1 lull | No |  |  | Yes | Sur west | ACM Insulation Subgirt Zee | 21 | 140 | [24 empty] | 256Ft | 20 |  |  | 120Ft | 20
24077 | IAD 667 TI | 2026-03-11 | Fredy veliz | We still have areas the still in hold on sc2 because GC AND CAT has equipment inside and hand rail company has materials to get in ,there is a lot materials of other trades that we have to move because no buddy is there to move it | Subcontractor | Chris Buttrey | Yes | Áreas on hold on sc2 equipment inside the gen yard the need to be remove | No |  | Good | 8 | 88 | No |  | 2 150 articulate boom lifts ,65 straight boom lift ,10k forklift | No |  |  | No |  | Louvre | [24 empty] | Installing blades on elev sc3 section 11,12,13 100% done ,installing bolts on channels sc2 section 6 to 13 organizing materials | 88
25002 | Med Center Health | 2026-03-11 | Kevin Morris | Installed stone panels and corrugated panels on roof, remade and installed facia panel on west lower soffit, installed soffit on South East lower level, installed acm and flashing under upper eyebrow. | Subcontractor | Carlos Silva | No |  | No |  | Good | 11 | 10 | No |  | 5 boom lifts | No |  |  | No |  | ACM Corrugated / Screen wall Flashing Terracotta | 16 | 10 | [14 empty] | 15 | 10 |  |  |  |  | 14 | 10 | [8 empty] | 160 | 10
25022 | Vantage VA15 | 2026-03-11 | Ricardo Banegas | Approximately three days have been lost due to downtime because there has not been an available work area. Some days we only work half a day and then have to wait. Crane operations in the area have also slowed down our progress. | Subcontractor | Thomas Mooers | Yes | The delays are due to not having the necessary material and not having an available work area. There is a lot of crane activity and other crews installing asphalt and working in the area. There is also heavy congestion with equipment and machinery. Because of this, we have experienced many delays installing our Z metal and panels in the roof area. There are also unfinished areas where we cannot install our Z metal due to pending inspections. | Yes | 2” screws | 62 | 10 | 10 | No |  | Boom Lift scaffold | No |  |  | Yes | North elevation | Subgirt Zee | [30 empty] | 240 | 100
25031 | LLU Mars US Warehouse | 2026-03-11 | Abner aguilar | Clean all the site working | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | Yes | South elevation | ACM Insulation Subgirt Zee | 14 | 44 | [24 empty] | 296 | 44 |  |  | 16 | 44
25050 | LTW062 Fit Out | 2026-03-11 | Mauricio Chavez | Mobilized to job site; Can’t take pictures in jobsite | Subcontractor | Dillon Bowman | No |  | Yes | L trim, deliver should be arriving tomorrow morning. | Windy and rain | 5 | 9 | Yes | H channel - 20 pc | Yes | No |  |  | Yes | All elevations | Hat Channel | [34 empty] | 192 ft | 5
24079 | Nashville Youth Campus | 2026-03-11 | Obed Bermudez | Two crews continue working on the south elevations third floor, moving material, installing flashing, z-girt, and insulation. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 4 | 10 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | No |  | Flashing Insulation Subgirt Zee | [26 empty] | 112 | 17 |  |  | 50 | 3 | 214 | 20
25059 | Allen Samuels CDJR and LC | 2026-03-11 | Chad McCoy | Installed 10 panels. Unloaded delivery and made sure all materials were strapped down and secure | Subcontractor | Andre Van Der Merwe | Yes | Making panels | Yes | New panels more caulking | Partly cloudy | 3 | 8 | Yes | A crate of replacement panels | 45 foot boom | No |  |  | No |  | ACM | 10 | 8
25036 | TCAT Chattanooga | 2026-03-11 | Obed Bermudez | The crew continues working, on the north soffit and south entrance, moving material, installing flashing and panels. | Subcontractor | Josh McPherson | No |  | No |  | Clear | 3 | 10 | No |  | Scissors lift | No |  |  | Yes | North and south. | Flashing Single Skin | [6 empty] | 2 | 10 | [24 empty] | 110 | 20
24039 | The Visionary | 2026-03-10 | Wilton Lorenzo | Two groups installed ceiling panels in the South patio level 4. Three groups installed ceiling panels in the SW patio level 4. Another group installed the two remaining panels in the North patio since Hydrotech will be working there and we will not have access to use the scissor lift, and they also removed the protective plastic. One group installed panels in the South. We had three ground helpers. | Subcontractor | Carlos Silva | No |  | Yes | 2" tek screws, gray caulking | Sunny | 20 | 12 | Yes | East patios panels | 6 boom lift, 1 scissor lift | No |  |  | Yes | South | ACM Insulation Subgirt Zee | 39 | 16 | [24 empty] | 384FT | 8 |  |  | 120FT | 6
24077 | IAD 667 TI | 2026-03-10 | Fredy veliz | We never get any parking list so we have to open all almos all the crates to find materials ,and we also organizing materials for asphalt work ,we are trying to install as much we can before the demobilization ,there is scissor lift in the gen yard and materials missing fro hand rail company so we have to leave some sections out | Subcontractor | Chris Buttrey | Yes | We have to leave some section out ,there is scissors lifts in the gen yard and materials missing for handrail company | No |  | Good | 8 | 88 | No |  | 65 straigth boom lifts ,150 articulate boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing Chanel's elev sc2 sections 10,11,12 and installing braces at sc3 section 11,12,13 ,organizing materials | 88
24089 | BSU Innovation Center | 2026-03-10 | Obed Bermudez | The crew continues working on the North elevation, moving material from the lay-down area to the site, cutting insulation, and installing a girt and strap metal. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 3 | 10 | No |  | Boom lift | No |  |  | Yes | North soffit | Insulation Subgirt Zee | [26 empty] | 544 | 25 |  |  | 50 | 5
25002 | Med Center Health | 2026-03-10 | Kevin Morris | Installed flashing on west lower facia, installed stone panels on South stair tower, installed acm panels on South East, had to move materials off of dirt areas and clean around whole building | Subcontractor | Carlos Silva | No |  | No |  | Good | 11 | 10 | No |  | 5 boom lifts | No |  |  | Yes | Lower soffit on South East | ACM Flashing Terracotta | 31 | 10 | [14 empty] | 6 | 10 | [14 empty] | 120 | 8
25055 | Mercedes Body Shop Reno | 2026-03-10 | Chad McCoy | Columns were finished today. | Subcontractor | Andre Van Der Merwe | Yes | Am storms | Yes | Replacement panels | Am storms | 1 | 10 | No |  | 46 foot boom | No |  |  | Yes | Column elevations were laser transferred | ACM | 16 | 9
25059 | Allen Samuels CDJR and LC | 2026-03-10 | Chad McCoy | Installed 6 panels 1 was fabbed columns are not planning out like they should | Subcontractor | Andre Van Der Merwe | Yes | Structure out of level | Yes | Replacement panels and caulking | Clear 72 | 3 | 8 | No |  | 40 foot boom | No |  |  | Yes | Small canopy columns | ACM | 6 | 5
24079 | Nashville Youth Campus | 2026-03-10 | Obed Bermudez | Two crews continue working on the south soffit, and the third crew continues on the east elevation, moving material, installing flashing, z-girt, and insulation. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 7 | 10 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | No |  | Flashing Insulation Subgirt Zee | [26 empty] | 288 | 15 |  |  | 463 | 35 | 254 | 20
24039 | The Visionary | 2026-03-09 | Wilton Lorenzo | Four groups installed panels in the SW patio, level 4. Two other groups worked on the layout and installed some panels on the south ceiling, level 4. Another group installed panels on the SW corner. Delays: Yes. After 9:30 AM we were informed that we could proceed with installing the panels even though the sprinklers are too high, and they can still adjust them after the panels are installed. | Subcontractor | Carlos Silva | Yes | After 9:30 AM we were informed that we could proceed with installing the panels even though the sprinklers are too high, and they can still adjust them after the panels are installed. | Yes | 2" Tek screws | Sunny | 20 | 11 | No |  | 6 boom lift, 1 scissor lift | No |  |  | Yes | South reflecting ceiling | ACM Insulation Subgirt Zee | 42 | 16 | [24 empty] | 64FT | 4 |  |  | 110FT | 6
24077 | IAD 667 TI | 2026-03-09 | Fredy veliz | On elev sc2 at the doors we have to leave sections out ,they have scissor lifts inside and some metal plates to move the lifts the don't. Fit in the door so today we had to removed 2 channels to set those plates | Subcontractor | Chris Buttrey | Yes | Have to leave some channels out for other trades, CAT need scissor lift to work in the generators | No |  | Good | 8 | 80 | No |  | 65 boom lift ,150 articulate boom lift ,10 k load | No |  |  | No |  | Louvre | [24 empty] | Installing Chanel's on sc2 section 6 to 9 ,installing channels on sc3 section 11,12,13 | 80
24089 | BSU Innovation Center | 2026-03-09 | Obed Bermudez | The crew continues working on the North elevation, moving material from the lay-down area to the site, cutting insulation, and installing a girt and strap metal. Strap metal installed was 70 lf. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 3 | 10 | No |  | Boom lift | No |  |  | Yes | North soffit | Subgirt Zee | [30 empty] | 150 | 30
25002 | Med Center Health | 2026-03-09 | Kevin Morris | Fabed and installed soffit panels on west, installed upper eyebrow corner on west, installed Stone panels on South stair tower, installed remake panels on penthouse, installed zee, insulation and ACM panels on South East | Subcontractor | Carlos Silva | No |  | No |  | Good | 13 | 10 | Yes | ACM FS11, flat strap | 5 boom lifts | No |  |  | No |  | ACM Insulation Subgirt Zee Terracotta | 24 | 10 | [14 empty] | 6 | 10 | [8 empty] | 300 | 2 |  |  | 100 | 1
25059 | Allen Samuels CDJR and LC | 2026-03-09 | Chad McCoy | Acm is continued, job should have been done by now | Subcontractor | Andre Van Der Merwe | Yes | Awaiting replacement panels | Yes | Replacement panels, caulking | Am storms | 3 | 10 | No |  | 40 foot boom | No |  |  | Yes | 2 sided canopy | ACM | 34 | 10
24079 | Nashville Youth Campus | 2026-03-09 | Obed Bermudez | Two crews continue working on the south soffit, and the third crew continues on the east elevation, moving material, installing flashing, z-girt, and insulation. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 7 | 10 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | No |  | Flashing Insulation Subgirt Zee | [26 empty] | 32 | 2 |  |  | 640 | 40 | 200 | 28
24077 | IAD 667 TI | 2026-03-07 | Fredy veliz | N/A | Subcontractor | Chris Buttrey | No |  | No |  | Good | 8 | 64 | No |  | 150 articulate boom lift | No |  |  | No |  | Louvre | [24 empty] | Installing Chanel's on sc3 section 11,12 and 13 and installing channels on sc2 section 6,7,8,and 9 , installing blades sc5 section 1 ,elev sc5 100% done | 64
24079 | Nashville Youth Campus | 2026-03-07 | Obed Bermudez | The crew continues installing flashing on the west elevation. | Subcontractor | Joe Hoyle | No |  | No |  | Inclement weather. | 6 | 5 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | Yes | West and south. | Flashing | [32 empty] | 100 | 10
24039 | The Visionary | 2026-03-06 | Wilton lorenzo | One crew installed panels at the SW corner. Four crews installed panels on the south ceiling, and one crew installed the remaining panels on the south side. One crew finished modifying the coping 13 pieces total, which took 3 hours with 2 guys. After that, I moved them to the north side to remove the girt so the corner panel joint can close properly and it will end up at 2 1/2 inches. Delays: Yes. We did not have access to part of the south area, so that crew modified 2 panels 2 hours with 2 guys. We are also getting delayed on the ceiling installation because we need to make sure our layout is correct before continuing. | Subcontractor | Carlos Silva | Yes | We did not have access to part of the south area, so that crew modified 2 panels 2 hours with 2 guys. | No |  | Sunny | 19 | 11 | No |  | 6 boom lift, | No |  |  | Yes | South | ACM Insulation Subgirt Zee | 25 | 8 | [24 empty] | 256ft | 4 |  |  | 130FT | 4
24077 | IAD 667 TI | 2026-03-06 | Fredy veliz | We have some of the. Chanel's that have the clip backwards we had to fix those because those are splices and have to go in a specific spot | Subcontractor | Chris Buttrey | Yes | Need one more boom lift | No |  | Light rain | 8 | 64 | No |  | 150 articulate boom lift ,65 straight boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing channels on sc3 ,section 11,12 and 13 installing blades on sc2 section 4 and 5 installing Channels sc2 section 6 and 7 | 64
24079 | Nashville Youth Campus | 2026-03-06 | Obed Bermudez | The crew continues taking opening,windows and panel dimension on the level 1 and 2 on North elevation. The second crew continues confirming panels dimensions on west elevation level 1 and 2. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 6 | 10 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | Yes | West and south. | Flashing | [32 empty] | 1 | 60
24089 | BSU Innovation Center | 2026-03-06 | Obed Bermudez | The crew continues working on the North elevation, installing z girt and flashing. | Subcontractor | Marc Ribar | No |  | No |  | Rain | 2 | 8 | No |  | Boom lift | No |  |  | Yes | North | Subgirt Zee | [30 empty] | 40 | 16
25022 | Vantage VA15 | 2026-03-06 | Ricardo Banegas | The material was moved and reorganized, and all the necessary material for the penthouse was relocated. | Subcontractor | Thomas Mooers | Yes | There is a delay due to the lack of material needed to continue the elevations. Additionally, some areas are ready, but we cannot access them because there are workers currently working in those areas. | No |  | 47 | 10 | 10 | No |  | Boom lift scaffold | No |  |  | Yes | Penthouse and north side | ACM Insulation Subgirt Zee | 13 | 50 | [24 empty] | 546 | 30 |  |  | 220 | 20
25055 | Mercedes Body Shop Reno | 2026-03-06 | Chad McCoy | 2 columns were completed, and the one replacement convoy panel was installed. Then we started installing the flat wall panels until the horizontal joint was pointed out that doesn’t line up and we quit bc of it. | Subcontractor | Andre Van Der Merwe | Yes | Panels don’t line up where the owner wants them to | Yes | Replacement panels | Party cloudy and windy 81 | 2 | 9.5 | Yes | One panel and caulking | 45 foot boom | No |  |  | Yes | Flat wall panels at building entry | ACM Flashing Subgirt Zee | 15 | 7 | [28 empty] | 40 | 1 | 20 | 0.5
25059 | Allen Samuels CDJR and LC | 2026-03-06 | Chad McCoy | Installed 23 panels 1 was fabbed. Also strapped down material and made sure nothing will fly during storm. | Subcontractor | Andre Van Der Merwe | Yes | Panel fab | Yes | Remake panels | Partly cloudy windy 78 | 3 | 7.45 | Yes | One crate of replacement panels | 45 foot boom | No |  |  | No |  | ACM | 23 | 7.45
24039 | The Visionary | 2026-03-05 | Wilton Lorenzo | Two groups installed the columns in the south patio level 4 to make sure they are properly aligned so the ceiling panels won’t have any issues. Two groups installed panels on the south side and another group worked on the corner. Another group attempted to install panels on the north side but couldn’t because the corners came too short. Two other groups focused on fixing caulking details and installing the missing reveals. A total of 12 coping pieces were cut and bent 5 hours, 1 guy. | Subcontractor | Carlos Silva | Yes | I can’t install all the silver panels yet because the wall needs to be properly sealed first. Water is getting into the building. | No |  | Sunny | 20 | 11 | Yes | ACM panels | 6 boom lift, 2 scissor lift | No |  |  | Yes | South | ACM Insulation Subgirt Zee | 22 | 8 | [24 empty] | 320 | 4 |  |  | 200FT | 4
24077 | IAD 667 TI | 2026-03-05 | Fredy veliz | United 150 articulate boom was pick up today ,also i had a conversation with the GC they are asking us to demobilize from 667 in 2 weeks ,they gonna be installing Need asphalt and is going to take 2 weeks that we will not have access to the 667,are asking us to start on 668 using some of the materials from 667 | Subcontractor | Chris Buttrey | Yes | Don't have enough equipment,some areas are not ready | No |  | Good | 8 | 80 | No |  | 150 articulate boom lift ,65 straight boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing channels sc3 section 11,12 and 13 ,installing blades sc5 section 2,3 and sc2 sectio 2,3 and 4 | 80
24079 | Nashville Youth Campus | 2026-03-05 | Obed Bermudez | The crew started and spent the whole day making layout and taking dimensions on the level 3 tower north,south,east, and west. The second crew continued taking dimensions on level 1/2 on North elevation. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 6 | 10 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | Yes | West elevation | Subgirt Zee | [30 empty] | 1 | 60
24089 | BSU Innovation Center | 2026-03-05 | Obed Bermudez | No work due to inclement weather | Subcontractor | Marc Ribar | No |  | No |  | Rainy day | 3 | 0 | No |  | Boom lift | No |  |  | Yes | North soffit | Flashing | [32 empty] | 1
25031 | LLU Mars US Warehouse | 2026-03-05 | Abner aguilar | 1pallet delivered of insulation | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | Yes | Insulation and rial | Boom lift | No |  |  | Yes | West | ACM Flashing | 14 | 44 | [30 empty] | 4 windows | 44
25055 | Mercedes Body Shop Reno | 2026-03-05 | Chad McCoy | Columns were stated but there was an issue with the bottom panels so there were left out. | Subcontractor | Andre Van Der Merwe | Yes | Panels were talked about with owners rep if that’s what they want | Yes | Remake panel. Caulking | Clear 71 | 2 | 8.5 | No |  | 46 foot boom 5 k lull | No |  |  | Yes | Columns | ACM | 13 | 7
25059 | Allen Samuels CDJR and LC | 2026-03-05 | Chad McCoy | Installed 45 zs at 84" also 25 is at 36". Got layout and installed 2 panels and ran 2 string lines. We took a lil bit to square out the corner | Subcontractor | Andre Van Der Merwe | Yes | Just waiting on panels to come correct | Yes | Replacement panels. Caulking. Patients | Clear 72 | 3 | 8 | No |  | 45 foot boom | No |  |  | Yes | North canopy | ACM Subgirt Zee | 2 | 1 | [28 empty] | 400 | 7
24039 | The Visionary | 2026-03-04 | Wilton Lorenzo | Three crews installed the column panels in South Patio 4 and had to carry four corners up the stairs. Three corners were modified by cutting one inch off them. Another three crews laid out the ceiling in the NW patio. The remaining workers helped with cleanup, since it rained all day. | Subcontractor | Carlos Silva | Yes | Thunderstorm | No |  | Rainy | 20 | 11 | Yes | Panels for south elevation | 6 boom lift, 2 scissor lift | No |  |  | Yes | South | ACM Insulation Subgirt Zee | 12 | 6 | [24 empty] | 80FT | 2 |  |  | 140 | 4
24077 | IAD 667 TI | 2026-03-04 | Fredy veliz | We had little bit of rain today ,and the 150 articulate boom from united still not working | Subcontractor | Chris Buttrey | Yes | Equipment not working | No |  | Light rain | 6 | 60 | No |  | 2 150 articulate boom lift ,65 straight boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing blades sc2 section 1 and 2 , screw clips sc3 section 11 to 13 | 60
24079 | Nashville Youth Campus | 2026-03-04 | Obed Bermudez | The crew continues working on the west/North elevation, moving material and installing z girt, insulation, and flashing. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 6 | 10 | Yes | Flashing | Buggy, forklift, conex, boom lifts. | No |  |  | Yes | West 2nd floor | Insulation Subgirt Zee | [26 empty] | 828 | 35 |  |  | 570 | 25
24089 | BSU Innovation Center | 2026-03-04 | Obed Bermudez | The crew started lay out do the North soffit. | Subcontractor | Marc Ribar | No |  | No |  | Inclement weather | 2 | 6 | No |  | Boom lift | No |  |  | Yes | North soffit | Flashing | [32 empty] | 1 | 12
25002 | Med Center Health | 2026-03-04 | Kevin Morris | Installed stone panels on South stair tower, installed zee, insulation, and ACM panels on South East side, installed corrugated panels on roof | Subcontractor | Carlos Silva | No |  | No |  | Good | 13 | 10 | No |  | 5 boom lifts | No |  |  | No |  | ACM Corrugated / Screen wall Insulation Subgirt Zee Terracotta | 14 | 10 | [14 empty] | 12 | 10 |  |  |  |  | 20 | 10 |  |  | 200 | 5 |  |  | 120 | 10
25022 | Vantage VA15 | 2026-03-04 | Ricardo Banegas | We have experienced delays due to the assigned work areas. We have had to move materials, and the designated work areas have been somewhat difficult to work in because there are many personnel working in those areas. | Subcontractor | Thomas Mooers | Yes | The areas are not ready to work in. We cannot access them because there are many personnel working in those areas. | Yes | JR2 | 46 | 10 | 10 | No |  | Boom Lift scaffold swing stage | No |  |  | Yes | Penthouse and North | ACM Insulation Subgirt Zee | 8 | 50 | [24 empty] | 420 | 20 |  |  | 380 | 30
25055 | Mercedes Body Shop Reno | 2026-03-04 | Chad McCoy | Compound was continued today but on the last panel we found that the panel will leave a 3 inch gap. So we took everything back off over the roof and moved the corners in and got it to 2 1/4 gap. So we measured the canopy and one side is 3 inches long the the other so we will not be finishing that today. We moved to the flat wall bc the columns can not be installed due to the electricians not having the electrical ran. On the flat wall the panels that go to the concrete have to be broke and routed due to it being 1 inch to long on lay out. But as we installed the first panel the GC came and said that’s not what was promised. And after digging into things with Andre it wasn’t. So phone calls were made and flashing was designed and it should be here tomorrow. So yet again work has stopped | Subcontractor | Andre Van Der Merwe | Yes | Improper panels with on canopy improper detail ending next to glass on flat wall no electrical ran on columns | Yes | I have Gray caulking, but on the prints, it says that the black panels have to be caulked to the gray wall, but I don’t know what color that caulking supposed to be and I do not think I have enough caulking for all of the Scarborough joints and the back ledge of the canopy plus the flat wall panels plus the columns so caulking needs to be sent out whether it’s black for the black panels or gray for the silver panels | Cloudy and windy | 2 | 10 | No |  | 5k lull and 46 foot boom | No |  |  | Yes | Layout was done on the canopy to find the bust in the wraparound panels and layout was done on the flat wall to find that bust on elevation | ACM | 7 | 6
25059 | Allen Samuels CDJR and LC | 2026-03-04 | Chad McCoy | Installed 21 panels 4 of them had to be fabbed bc of panels over laying on preexisting corrugated | Subcontractor | Andre Van Der Merwe | Yes | Cut and routed | Yes | Remake panels. Caulking | Clear 68 | 3 | 8.5 | No |  | 45 foot boom. My scaffolding | No |  |  | Yes | Non stop | ACM | 21 | 8
24039 | The Visionary | 2026-03-03 | Two crews installed the columns on the south side. Two other crews installed the panels on the back side of the stair tower. I need to make one panel smaller and cut notches in two panels due to a louver. I assigned two crews to seal holes that were left in the south wall and the canopy because it will rain tomorrow, to make sure no water gets inside the building. | Two crews installed the columns on the south side. Two other crews installed the panels on the back side of the stair tower. I need to make one panel smaller and cut notches in two panels due to a louver. I assigned two crews to seal holes that were left in the south wall and the canopy because it will rain tomorrow, to make sure no water gets inside the building. | Subcontractor | Carlos Silva | No |  | Yes | Shims, tek screws, panels, | Sunny | 20 | 11 | No |  | 6 boom lift | No |  |  | Yes | South | ACM Insulation Subgirt Zee | 16 | 6 | [24 empty] | 150FT | 2 |  |  | 70FT | 2
24077 | IAD 667 TI | 2026-03-03 | Fredy veliz | Did not work today because the weather we will see tomorrow ,i was notified that the 150 articulate boom lift was repair haven't test yet | Subcontractor | Chris Buttrey | Yes | Weather raining all day | No |  | Raining and snowing | 1 | 0 | No |  | 2 150 articulate 150 boom lift ,65 straight boom lift ,10 k load | No |  |  | No |  | Louvre | [24 empty] | 0 | 0
24079 | Nashville Youth Campus | 2026-03-03 | Obed Bermudez | The crew continues working on the west elevation, moving materials and installing z girt, insulation, and flashing. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 4 | 10 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | Yes | West | Flashing Insulation Subgirt Zee | [26 empty] | 657 | 12 |  |  | 270 | 15 | 36 | 3
24089 | BSU Innovation Center | 2026-03-03 | Obed Bermudez | We received and unloaded a delivery. No work installation due to inclement weather. | Subcontractor | Marc Ribar | Yes | Inclement weather | Yes | Long board clips | Rainy day | 1 | 1 | Yes | Channels | Boom lift | No |  |  | Yes | All | Single Skin | [6 empty] | 0
25036 | TCAT Chattanooga | 2026-03-03 | Obed Bermudez | Crew continues working on the west elevation, installing flashing, caulking, pac clad panels and cleaning the whole area. | Subcontractor | Josh McPherson | No |  | Yes | Flashing for north soffit and flashing for south entrance where Pac Clad meets vertical face cap. | Clear | 2 | 8 | No |  | Boom lift and forklift. | No |  |  | Yes | All | Caulking Flashing Single Skin | [6 empty] | 2 | 2 | [12 empty] | 17 | 7 | [10 empty] | 64 | 7
25055 | Mercedes Body Shop Reno | 2026-03-03 | Chad McCoy | Panels arrived this morning at 630. I unloaded these panels in the street, bc this was yet another poor decision!!! These panels were sent on a 18 wheeler with a 54 foot trailer. There is no room for this truck on this site. It is unloaded and staged. During the layout of the canopy we found that the panels are 13.5 and 15.9 feet long. How am I suppose to hang these panels with one single boom. If it physically impossible. I had to get with the GC that I just met to borrow his scissor lift. This type of first impression is not how CWMcCoy Sheetmetal wants to be remembered or known for. The 1 3/4 screws in spots are also not long enough when shimming panels on the canopy. So 2 to 2-1/4 Are having to be used which I also borrows from the GC and I will replace his tomorrow. The columns can not be installed bc the electrical is not ran. And on the flat wall panels a water Spicket has to be moved due to the wrong stand off of face of panels and a decision has to be made over a section that is suppose to be flashing that might need a panel. | Subcontractor | Andre Van Der Merwe | Yes | Not enough equipment to reach the end of a 16 foot horizontal panel, improper screws, and elctical not installed in columns | No |  | Partly cloudy 71 | 2 | 11 | Yes | 4 crates of panels. 1 skid of flat stock, 1 pallet of insul, and 1 pallet of a hand full of shims and screws and caulking | 46 foot boom | No |  |  | Yes | The entire canopy | ACM | 9 | 7
25059 | Allen Samuels CDJR and LC | 2026-03-03 | Chad McCoy | Small canopy was continued today. 17 panels was installed. 3 cut and routed and one filler spot for a 4 inch cavity | Subcontractor | Andre Van Der Merwe | Yes | Where the canopy met the main structure there was a 4 inch cavity that was address to Hyatt Hayes for direction on how they wanted this filled. This was a hole all the way thru the building | Yes | Panels. Caulking. | Partly cloudy 69 | 3 | 8 | No |  | 45 foot boom. A borrowed scissor lift. My scaffolding | No |  |  | Yes | 12/204 | ACM | 17 | 8
24039 | The Visionary | 2026-03-02 | Wilton Lorenzo | Two crews installed panels on the roof at the back of the south stair tower. Another crew finished installing panels on the south stair tower. One crew installed panels inside the level 3 balcony. Another crew installed the remaining panels on the south side. One crew removed the protective plastic and applied caulk to some of the joints in the atrium. Another crew fabricated panels that had been damaged. One crew was caulking the coping screws. Delays: Yes. We tried to install the south columns since we only have access after 5 PM, but we were not able to install them because they are too wide on the sides. | Subcontractor | Carlos Silva | No |  | Yes | 2" tek screws, shims, coping | Sunny | 19 | 11 | No |  | 6 boom lift, 2 scissor lift | No |  |  | Yes | South | ACM Caulking Insulation Subgirt Zee | 26 | 8 | [18 empty] | 60 | 2 |  |  |  |  | 120FT | 4 |  |  | 30FT | 2
24077 | IAD 667 TI | 2026-03-02 | Fredy veliz | Still don't have updates on the boom lift form united ,we have to stop at noon because the snow ,elevation sc2,sc6 east 100% done | Subcontractor | Chris Buttrey | Yes | Wether and 150 boom lift not working | No |  | Snowing | 8 | 48 | No |  | 2 65 articulate boom lift ,65 straight Boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing blades elevation sc2,sc6 east ,installing clips sc3 section 11 to 13 prep blades for elvation sc2 section 1 to 5 | 48
24079 | Nashville Youth Campus | 2026-03-02 | Obed Bermudez | The crew continues working on the west elevation, moving materials and installing z girt, insulation, and flashing. | Subcontractor | Joe Hoyle | No |  | No |  | Inclement weather | 3 | 10 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | Yes | West | Flashing | [32 empty] | 120 | 27
24089 | BSU Innovation Center | 2026-03-02 | Obed Bermudez | Crew continues working on the west elevation, installing flat metal, aluminum channel, flashing and strongirt. | Subcontractor | Marc Ribar | No |  | Yes | Longboard clips | Snowing | 2 | 8 | No |  | Boom lift | No |  |  | Yes | West elevation | Flashing Single Skin | [6 empty] | 5 | 8 | [24 empty] | 30 | 8
25002 | Med Center Health | 2026-03-02 | Marvin Blanco | Today was raining all morning so we couldn't make to much but we were cleaning moving material from the west to the south east also working in the top Eyebrow installing ACM panels everything is running good the only thing we need is flashing for the lower Eyebrow 4 panels for the penthouse and stone panels for finished the face of the stairs tower | Subcontractor | Carlos Silva | No |  | Yes | 4 panels for the penthouse and also L acm for around the doors and flashing | Cold | 13 | 10 | No |  | Boomlift | No |  |  | No |  | ACM | 15 | 130
25036 | TCAT Chattanooga | 2026-03-02 | Obed Bermudez | Crew continues working on the west elevation, installing pac clad panels. | Subcontractor | Josh McPherson | No |  | Yes | Flashing for north soffit and flashing for south entrance where Pac Clad meets vertical face cap. | Rainy | 2 | 8 | No |  | Boom lift, scissor lift and forklift. | No |  |  | Yes | All | Single Skin | [6 empty] | 19 | 16
25050 | LTW062 Fit Out | 2026-03-02 | Mauricio Chavez | We are unable to take pictures inside the jobsite. Was still unable to acquire access for Vicente Martinez, he has been waiting since Thursday. | Subcontractor | Dillon Bowman | Yes | Need H Channel | Yes | H Channel | Windy | 5 | 6 | No |  | Yes | No |  |  | No |  | Louvre | [24 empty] | 33 | 6
25055 | Mercedes Body Shop Reno | 2026-03-02 | Chad McCoy | I lot of hurry up and wait was done today. I was told panels were leaving mcdougal first at 7am. Then 1030 am. And they left at 250 pm. The driver didn’t have enough time to get to me to unload so this was another waste of a day and resources | Subcontractor | Andre Van Der Merwe | Yes | Panel shipping | Yes | Everything that I was suppose to receive at 11 am | Cloudy 68 | 2 | 4 | No |  | 5 k lull 46 foot boom | No |  |  | No |  | ACM | 0 | 0
25059 | Allen Samuels CDJR and LC | 2026-03-02 | Chad McCoy | Nick was on site today and he got panels prepped and ready to start installing on the coping caps. And he got everything to the roof and the caps are a foot too short. So after finding even more problems on this horrible job he left bc there was no need for him to be there in my place. | Subcontractor | Andre Van Der Merwe | Yes | This job is a delay | Yes | Replacement panels. Caulking. | Clear 71 | 4 | 8 | No |  | 45 foot boom. A borrowed lull. My scaffolding | No |  |  | Yes | Everywhere for the caps panels | ACM Subgirt Zee | 14 | 7 | [28 empty] | 20 | 0.15
24077 | IAD 667 TI | 2026-03-01 | Fredy veliz | United 150 articulate boom lift still not working | Subcontractor | Chris Buttrey | Yes | Boom lift 150 articulate not working | No |  | Good | 4 | 32 | No |  | 2 15o articulate boom lift ,65 straight boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing clips elevation sc3 section 11 to 13 ,installing blades elevation sc5 | 32
24039 | The Visionary | 2026-02-28 | Wilton Lorenzo | One crew installed panels on the south stair tower and I needed help from another crew to install one corner. After that, the same crew installed panels that were missing from the previous delivery. One crew applied caulking to the atrium joints and installed flashing at the window areas. Two helpers moved panels up to the roof, and two other crews prepared the back side of the south stair tower. One crew applied caulk to the coping joint on the east side. The delivery arrived at 9:00 AM. There were two trucks. | Subcontractor | Carlos Silva | Yes | Material was arrive at 9 am | Yes | 2" tek screws, caulking, flashing, coping | Sunny | 20 | 8 | Yes | 2 deliveries, panels and coping | 6 boom lift, | No |  |  | Yes | South | ACM Caulking Insulation Subgirt Zee | 6 | 4 | [18 empty] | 120FT | 4 |  |  |  |  | 150FT | 4 |  |  | 60FT | 2
24077 | IAD 667 TI | 2026-02-28 | Fredy veliz | Lay out is 100% done on elevation sc3 we working on i getting clips install | Subcontractor | Chris Buttrey | Yes | United articulate 150 boom lift no working | No |  | Good | 8 | 64 | No |  | 2 150 articulate boom ,65 straight boom lift,10k load | No |  |  | Yes | Elevation sc3 section 6 to 10 | Louvre | [24 empty] | Installing clips lev sc3 section 11 to 13 ,installing blades sc2 ,sc6 east ,layout sc3 section 6 to 10 | 64
24079 | Nashville Youth Campus | 2026-02-28 | Obed Bermudez | The crew continues working on the west elevation, moving materials and installing z girt, insulation, and flashing. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 5 | 8 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | Yes | West elevation | Flashing Insulation Subgirt Zee | [26 empty] | 140 | 16 |  |  | 80 | 8 | 120 | 16
24089 | BSU Innovation Center | 2026-02-28 | Obed Bermudez | Crew continues working on the west elevation, installing flat metal, aluminum channel, flashing and strongirt. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 2 | 20 | No |  | Boom lift | No |  |  | Yes | West | Flashing Insulation Subgirt Zee | [26 empty] | 226 |  |  |  | 180 |  | 50
25002 | Med Center Health | 2026-02-28 | Kevin Morris | Install Stone panels, zee and insulation on South stairwell Tower, installed ACM panels on Southeast, caulked west lower soffit | Subcontractor | Carlos Silva | No |  | No |  | Good | 13 | 8 | No |  | 5 boom lifts | No |  |  | No |  | ACM Caulking Insulation Subgirt Zee Terracotta | 19 | 8 | [14 empty] | 16 | 8 |  |  | 100 | 8 |  |  |  |  | 500 | 8 |  |  | 420 | 8
25059 | Allen Samuels CDJR and LC | 2026-02-28 | Chad mccoy | The line center was peeled and caulked today so the GC can get there CO on the building. What is not finished is the flashing at the top and the skyward joints. But they do not need that for there CO. We also did not Run the z on the canopy all the way down bc the framing falls in 1 1/2 inches over the first 14 inches. So we ran it just enough to catch the first panel | Subcontractor | Andre Van Der Merwe | Yes | Delays are every where in this job. | Yes | Replacement panels. Caulking. New flashing. | Clear 72 | 4 | 8 | No |  | 45 foot boom. 5 k lull. My scaffolding | No |  |  | Yes | East canopy to get the proper distance for the starter panel | ACM | 1 | 1
24039 | The Visionary | 2026-02-27 | Wilton Lorenzo | Two crews installed the two remaining corners in the south patio. One crew installed the corner that we had removed due to the expansion joint and had to cut one inch off one side, 3 guys worked 3.5 hours. Another crew fabricated one panel for the south tower, 2 guys worked 1 hour. One crew removed the plastic in the atrium and applied caulking. Another crew finished installing the coping pieces and started applying caulking to close the joint. One crew removed the plastic on the north side. Insulation was installed at the SW corner and preparation work was done in the patio level 3. | Subcontractor | Carlos Silva | Yes | We don’t have panels. | Yes | Caulking, 2" tek screws, flashing, the rest of coping for east, | Sunny | 20 | 8 | No |  | 6 boom lift, 2 scissor lift | No |  |  | Yes | South | ACM Insulation Subgirt Zee | 4 | 4 | [24 empty] | 132 | 4 |  |  | 50Ft | 2
24077 | IAD 667 TI | 2026-02-27 | Fredy veliz | United 150 articulate boom still not working ,mechanic been working on it today but didn't get it done ,we will be working the weekend and other trade is gonna let us use his boom to get all the layout done on the elevation sc3 to verify measurements ,we will that boom | Subcontractor | Chris Buttrey | Yes | Boom lift not working | No |  | Good | 8 | 80 | No |  | 2 150 articulate boom lifts ,65 straight boom lift ,10k load | No |  |  | Yes | Lay out elevation sc3 section 5 and 6 | Louvre | [24 empty] | Installing clips sc3 section 11,12,13 ,installing blaces and blades sc2,sc6 east | 80
24079 | Nashville Youth Campus | 2026-02-27 | Obed Bermudez | Crew continues working on the west elevation, moving material and installing flashing. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 3 | 10 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | Yes | West | Flashing | [32 empty] | 250 | 30
24089 | BSU Innovation Center | 2026-02-27 | Obed Bermudez | Crew continues working on the west elevation, installing flat metal, aluminum channel, flashing and strongirt. 16 lf of aluminum channel and 16 lf of strap metal installed. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 2 | 10 | No |  | Boom lift | No |  |  | Yes | West south east | Flashing Subgirt Zee | [30 empty] | 55 | 10 | 86 | 10
25022 | Vantage VA15 | 2026-02-27 | Ricardo Banegas | The material was moved and distributed properly across the different work areas. | Subcontractor | Thomas Mooers | Yes | None of the installed panels had the extrusions screwed in. | Yes | Panel screws insulation | 34 | 10 | 10 | No |  | Boom Lift Scaffold and swing stage | No |  |  | Yes | North and West | ACM Insulation Subgirt Zee | 18 | 50 | [24 empty] | 896 | 30 |  |  | 240 | 20
25031 | LLU Mars US Warehouse | 2026-02-27 | Abner aguilar | No | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | No |  | ACM Insulation | 19 | 44 | [24 empty] | 95 | 44
25036 | TCAT Chattanooga | 2026-02-27 | Oned Bermudez | Crew continues caulking on the North elevation. Cleaned up all trash and moved material to the parking lot. | Subcontractor | Josh McPherson | No |  | Yes | 202-1c12A Corner ACM panel that came damaged from the shop. Panel 203-1D02 that was damaged by others. Flashing for south entrance. | Clear | 2 | 7 | No |  | Scissors lift and boom lift | No |  |  | Yes | All | Caulking | [20 empty] | 36 | 14
25059 | Allen Samuels CDJR and LC | 2026-02-27 | Chad mccoy | 4 panels were made to wrap the back of the line center on to the roof. Panels were also continue to the east canopy. 3 panels were cut and routed where they meet in the corner | Subcontractor | Andre Van Der Merwe | Yes | The panels that go under the canopy are 9 1/4 to big. They have nothing to attach to. This will be a problem. They all will have to be cut and routed to fit the canopy an stay closer to the steel | Yes | Remake panels, more caulking. | Clear 72 | 5 | 9 | No |  | 45 foot boom. My scaffolding 5k lull | No |  |  | Yes | Everywhere. | ACM | 17 | 8
24039 | The Visionary | 2026-02-26 | Wilton lorenzo | One crew installed panels inside the south patio level 3. Another crew installed panels on the south roof. One crew installed coping on the east side roof. Two crews removed the plastic protection from the south panels. Two other crews installed the column corners on the south side patio level 3. One crew applied caulking in the atrium and removed the plastic protection. | Subcontractor | Carlos Silva | Yes | Three corners were modified, two hours, three guys. We do not have panels available to install. One crew removed and reinstalled a panel on the north side that was damaged by another company. | Yes | Sill lashing. Panels, coping | Sunny | 20 | 11 | No |  | 6 boom lift, 2 scissor lift | No |  |  | Yes | South | ACM Flashing Insulation Subgirt Zee | 18 panels | 4 | [24 empty] | 50FT | 2 |  |  | 120 | 2 | 80FT | 2
24046 | UAB Biomedical Research and Psycholgy | 2026-02-26 | naza padron | 6 panels were fabricated for South columns 10 hours | Subcontractor | Wylie McDougall | Yes | Drains in the southern eyebrow elevation have not been installed | No |  | sunny | 6 | 60 | Yes | Crate of ACM, Palet of flat sheets | N/A | No |  |  | No |  | ACM Flashing Trim | 26 | 30 | [30 empty] | 90 | 10 |  |  | 90 | 10
24077 | IAD 667 TI | 2026-02-26 | Fredy veliz | United 150 articulated still broken have no updates from united yet ,the 135 straight was was pick it up at 8:30 am leaving us with one boom lift to work ,the 150 from sunbelt was delivered at noon but it and i took us to hours to get it in because they had 2 cranes on the way ,after we got the boom set up started raining so we have to leave | Subcontractor | Chris Buttrey | Yes | Equipment broken and weather | No |  | Raining | 8 | 56 | No |  | 65 straight boom lifts ,2 65 articulated boom ,10k load | No |  |  | No |  | Louvre | [24 empty] | Chennels sc2,sc6 east complete ,cutting Channels | 56
24079 | Nashville Youth Campus | 2026-02-26 | Obed Bermudez | Crew continues working on the west/south/east elevation, installing flashing | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 3 | 10 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | No |  | Flashing Insulation | [26 empty] | 640 | 20 |  |  |  |  | 100 | 10
24089 | BSU Innovation Center | 2026-02-26 | Obed Bermudez | Crew moved material with the forklift from the lay-down area to the site and continued installing corner flashing and panels on the west elevation. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 2 | 9 | Yes | Received 16 boxes of caulking (bronze), painted screws, and rivets. | Boom lift | No |  |  | Yes | West | Single Skin | [6 empty] | 9 | 18
25002 | Med Center Health | 2026-02-26 | Kevin Morris | Installed stone panels and rail clips on South stair tower, installed acm panels, zees, and insulation on Southeast. Caulked west side lower soffit | Subcontractor | Carlos Silva | No |  | No |  | Good | 13 | 10 | No |  | 5 boom lifts | No |  |  | No |  | ACM Caulking Subgirt Zee Terracotta | 12 | 10 | [14 empty] | 15 | 10 |  |  | 190 | 10 | [8 empty] | 540 | 10
25022 | Vantage VA15 | 2026-02-26 | Ricardo Banegas | Layout/field measurements were completed in each panel installation area. Material was unloaded and organized in different zones. | Subcontractor | Thomas Mooers | Yes | Work was paused while generators were being started up, as we were working nearby. For safety reasons, operations had to stop intermittently. | No |  | 34 | 10 | 10 | Yes | 7 crates of ACM | Boom Lift Swing Stage scaffold | No |  |  | Yes | North and West | ACM Insulation Subgirt Zee | 12 | 40 | [24 empty] | 740 | 40 |  |  | 210 | 20
25022 | Vantage VA15 | 2026-02-26 | Ricardo Banegas | The material has been transported from the first floor to the sixth floor. We have experienced delays because we are waiting for the elevator, as there is not enough space on the sixth floor to store the material. | Subcontractor | Thomas Mooers | Yes | The material has been transported from the first floor to the sixth floor. We have experienced delays because we are waiting for the elevator, as there is not enough space on the sixth floor to store the material. And the panels are coming without the fasteners installed. And the panels are coming without the fasteners installed. And the panels are coming without the fasteners installed. | Yes | We need screws for the panel extrusion system. | 34 | 10 | 10 | No |  | Boom Lift scaffold | No |  |  | Yes | North and West | ACM Insulation Subgirt Zee | 21 | 50 | [24 empty] | 960 | 30 |  |  | 320 | 20
25031 | LLU Mars US Warehouse | 2026-02-26 | Abner aguilar | No | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | Yes | North | ACM | 23 | 44
25036 | TCAT Chattanooga | 2026-02-26 | Obed Bermudez | We continue caulking the South elevation soffit and finished it. | Subcontractor | Josh McPherson | No |  | Yes | 202-1c12A Corner ACM panel that came damaged from the shop. Panel 203-1D02 that was damaged by others. Flashing for north soffit and flashing for south entrance. | Rainy | 2 | 10 | No |  | Scissor lift and boom lift | No |  |  | No |  | Caulking | [20 empty] | 120 | 20
25050 | LTW062 Fit Out | 2026-02-26 | Mauricio Chavez | Can’t take any pictures onsite | Subcontractor | Dillon Bowman | No |  | Yes | More louvers and H-channel | Windy | 4 | 10 | Yes | Scissor lift | Yes | No |  |  | Yes | North and West | Louvre Trim | [24 empty] | 80 | 6 | [10 empty] | 95 | 3
25059 | Allen Samuels CDJR and LC | 2026-02-26 | Chad mccoy | On 19/206 the customer doesn’t like the bump/miss alignment in the panels that will continue around the canopy. On this wall they want to furred out equally and not half way. So to do this7 panels have to be remade. And parks field adjusted to make this work. The lube center has 2 parks to being done. It will be peeled and caulked by tomorrow except the missing flashing on roof | Subcontractor | Andre Van Der Merwe | Yes | East elevation on main building with 2 inch step. On the man building face above the windows. The wall falls in 1 1/2 from window to Para pit top | Yes | Remake panels, more caulking, no rain next week | 71 partly cloudy | 5 | 11 | No |  | 45 foot boom 5 k lull. My scaffolding and a stolen scissor lift | No |  |  | Yes | Everywhere | ACM | 38 | 8.5
24039 | The Visionary | 2026-02-25 | Wilton lorenzo | 5 crews installed panels on the south elevation. One crew spend bending 12 coping pieces (2 guys, 6 hours). Another crew installed L trim at the SE canopy where the panel was set too low. Two crews ran out of panels and currently have no panels to install. | Subcontractor | Carlos Silva | Yes | We will run out of panel tomorrow | Yes | Anthracite sill flashing | Sunny | 20 | 11 | No |  | 6 boom lift, 2 scissor lift | No |  |  | Yes | South, east | ACM Flashing Insulation Subgirt Zee | 52 | 12 | [24 empty] | 736FT | 10 |  |  | 660 | 12 | 120 | 4
24046 | UAB Biomedical Research and Psycholgy | 2026-02-25 | Zarur N Padron | Panels will have to be skipped because the drains have not been installed at the eyebrow at South side elevation | Subcontractor | Wylie McDougall | No |  | No |  | cloudy | 7 | 70 | No |  | N/A | No |  |  | No |  | ACM Insulation Subgirt Zee | 18 | 28 | [24 empty] | 880 | 26 |  |  | 320 | 16
24077 | IAD 667 TI | 2026-02-25 | Fredy veliz | 150 articulate boom still not working ,mechanic showed up in the afternoon, but the machine need some sensor that he need to order,he is working on availability to swap the machine ,the 135 it was leaking too I reported and the mechanic fix the issue | Subcontractor | Chris Buttrey | Yes | Boom lifts not working | No |  | Good | 8 | 80 | No |  | 65 straight boom lift ,135 straight boom lift ,150 articulate boom lift ,10 k load | No |  |  | No |  | Louvre | [24 empty] | Installed channel sc2 south and sc2 and sc6 east | 80
24079 | Nashville Youth Campus | 2026-02-25 | Obed Bermudez | Crew continues working on the west, south and east elevation, installing flashing, z girt, and insulation. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 3 | 10 | Yes | A pallet of flashing (40 sticks). | Buggy, forklift, conex, boom lifts. | No |  |  | No |  | Flashing Insulation Subgirt Zee | [26 empty] | 208 |  |  |  | 300 |  | 32
24089 | BSU Innovation Center | 2026-02-25 | Obed Bermudez | Crew moved material with the forklift from the lay-down area to the site and continued installing corner flashing and panels. | Subcontractor | Marc Ribar | Yes | Crew had to stop work due to high wind conditions. | Yes | Caulking (we only have half a box left) Painted screws for aluminum channel, long painted rivets. | Windy conditions | 3 | 9 | No |  | Boom lift | No |  |  | Yes | South and west | Flashing Single Skin | [6 empty] | 7 | 25 | [24 empty] | 10 | 2
25002 | Med Center Health | 2026-02-25 | Kevin Morris | Caulked on west side upper eyebrow, installed stone panels on South stair tower, installed zee insulation and ACM on South East | Subcontractor | Carlos Silva | No |  | No |  | Good | 13 | 10 | No |  | 5 boom lifts | No |  |  | No |  | ACM Caulking Subgirt Zee Terracotta | 19 | 10 | [14 empty] | 12 | 10 |  |  | 200 | 10 | [8 empty] | 60 | 3
25031 | LLU Mars US Warehouse | 2026-02-25 | Abner aguilar | No | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | Yes | North | ACM | 15 | 44
25036 | TCAT Chattanooga | 2026-02-25 | Obed Bermudez | We continue working on North elevation, installing ACM panels and flashing on the roof south elevation and cleaning up a the trash. | Subcontractor | Josh McPherson | No |  | Yes | 202-1c12A Corner ACM panel that came damaged from the shop. Panel 203-1D02 that was damaged by others. Flashing for north soffit and flashing for south entrance. | Rainy | 2 | 10 | No |  | Scissors lift and boom lift | No |  |  | Yes | All. | ACM Flashing | 3 | 10 | [30 empty] | 70 | 10
25050 | LTW062 Fit Out | 2026-02-25 | Mauricio Chavez | Can’t take any pictures of jobsite | Subcontractor | Dillon Bowman | No |  | No |  | Windy | 4 | 10 | No |  | Yes, but still missing scissor lift. Only have 1 boom lift | No |  |  | Yes | North Elevation | Louvre Trim | [24 empty] | 85 | 5 | [10 empty] | 100 | 5
25059 | Allen Samuels CDJR and LC | 2026-02-25 | Chad mccoy | 2 big corners were cut and routed and 3 caps on the line center. On the big building there is another 1 1/2 bust to the stucco where they were suppose to be even but it does not. There are a lot of panels that are laying on top of each other with no protection. These panels are laying on excursions and the vibrations have ruined the panel | Subcontractor | Andre Van Der Merwe | Yes | Cuts and routes. | Yes | New flashing for the club center. The flashing at the top is all one size. But on the east side it’s 3 inches short | Partly cloudy 53 | 5 | 11 | Yes | Flashing | 45 foot boom 5k lull and my scaffolding | No |  |  | Yes | Layout has to be done on every panel | ACM Flashing | 36 | 9 | [30 empty] | 160 | 1.5
24039 | The Visionary | 2026-02-24 | Wilton Lorenzo | 6 crews installed panels and Z-girts with insulation on the south elevation. One crew installed coping on the SE canopy, and another crew caulked the vertical joints at the atrium corners and removed the protective plastic. | Subcontractor | Carlos Silva | Yes | The first row panels below the south curtain wall had to be resized. A total of 7 panels were modified, which took approximately 8 hours. | Yes | 2" tek screws | Sunny | 20 | 11 | No |  | 6 boom lift, 2 scissor lift | No |  |  | Yes | South | ACM | 49 | 10
24077 | IAD 667 TI | 2026-02-24 | Fredy veliz | The 150 articulated is been. Down for the last 2 days we request service yesterday but no buddy have been working on it ,we been trying to do some progress on the lower wall but we can't close everything because hand rails are not done | Subcontractor | Chris Buttrey | Yes | Articulated boom not working | No |  | Cold and windy | 8 | 80 | No |  | 65 straight boom lift ,135 straight boom lift ,150 articulated boom lift ,10 k load | No |  |  | No |  | Louvre | [24 empty] | Installing channels sc2 south easta corner ,screw clips sc2,sc6 east ,cutting Chanel's for sc2 | 80
24079 | Nashville Youth Campus | 2026-02-24 | Obed Bermudez | Crew continues working on the south and west elevation, installing insulation and a Z-girt. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 3 | 10 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | No |  | Insulation Subgirt Zee | [26 empty] | 320 | 12 |  |  | 390 | 18
24089 | BSU Innovation Center | 2026-02-24 | Obed Bermudez | Crew continues working on the third floor south elevation, with panel installation. | Subcontractor | Marc Ribar | No |  | Yes | Caulking (we only have half a box left) Painted screws for aluminum channel, long painted rivets. | Clear | 3 | 10 | No |  | Boom lift | No |  |  | Yes | West and south | Single Skin | [6 empty] | 56 | 30
25002 | Med Center Health | 2026-02-24 | Kevin Morris | Install Stone panels on South stairwell Tower, installed ACM panels on Southeast wall also installed z and insulation on Southside of building | Subcontractor | Carlos Silva | No |  | No |  | Cold | 12 | 10 | No |  | 5 boom lifts | No |  |  | No |  | ACM Insulation Subgirt Zee Terracotta | 10 | 10 | [14 empty] | 28 | 10 | [8 empty] | 360 | 5 |  |  | 420 | 6
25002 | Med Center Health | 2026-02-24 | Marvin Blanco | Working in the store panels in the stairs tower #1 we have a lot of damaged panels that needs to be replaced soon as we finished checking every single panel I'll send all the numbers of the panels and also working in the ACM panels in the vertical column south east and in the soffit east elevation | Subcontractor | Carlos Silva | No |  | Yes | 4 panels for the penthouse and also L acm for around the doors | Cold | 13 | 10 | No |  | Boomlift | No |  |  | No |  | ACM Terracotta | 12 | 50 | [14 empty] | 19 | 80
25036 | TCAT Chattanooga | 2026-02-24 | Obed Bermudez | On the North elevation, we are having to change extrusions and will have to caulk bottom joints due to the 4 vertical panels not having a return. | Subcontractor | Josh McPherson | No |  | Yes | 202-1c12A Corner ACM panel that came damaged from the shop. Panel 203-1D02 that was damaged by others. Flashing for north soffit and flashing for south entrance. | Clear | 2 | 10 | No |  | Scissors lifts | No |  |  | Yes | All elevations | ACM Flashing | 1 | 10 | [30 empty] | 20 | 10
25050 | LTW062 Fit Out | 2026-02-24 | Mauricio Chavez | Cannot take any pictures inside the site | Subcontractor | Dillon Bowman | Yes | We still could not get access into the site. We could only unload material | No |  | Cold and windy | 4 | 10 | Yes | Material and hardware - louvers and trims | Yes | No |  |  | No |  | Louvre | [24 empty] | 0 | 0
25059 | Allen Samuels CDJR and LC | 2026-02-24 | Chad McCoy | We split up today. One team plugged in the panels on the lube center, my team played out the main building and fabbed and installed panels on second building. First team installed 15 panels with 5 cut and routes, One panel was built wrong from mcdougall on the remakes so we fixed that. The layout on the big building was pretty heavy. The windows on the south elevation stick out 5/8 and the east elevation sink in 1 inch to 1 3/4. They are also out of level so lasers were level lined and columns were spaced where they will meat the upper panels. The panels for the columns range from 5 1/2 inches to wide to 6 inches to wide. So everything inbetween the windows so far have to be cut and routed. Each column in the bottom also has a pipe that goes thru it. So layout on elevation is importantly due to these holes | Subcontractor | Andre Van Der Merwe | Yes | Panel sizes again, windows are wrong, | Yes | Flashing that was submitted to Andre to fix window areas | Partly cloudy 48 | 5 | 11 | Yes | One solo crate | 5k lull. 45 foot boom. I also brought all my scaffolding for extra elevational work | No |  |  | Yes | Every where. This is continuous | ACM | 25 | 9
24039 | The Visionary | 2026-02-23 | Wilton Lorenzo | 5 crews installed panels on the south elevation. One crew installed coping at the SE, and one crew installed sill flashing and L trim at the atrium. | Subcontractor | Carlos Silva | Yes | We tried to install the last two corners of the atrium that go up to Patio Level 4, but we were not able to because the Hydrotech is not installed yet. I moved that crew to the south elevation. The panels on one south wall below the curtain wall are too large, and I have to cut all of those panels. We cut 2 panels with 3 guys in 1 hour. The panels for the south stair tower are incomplete, and several panels from delivery FS16 were missing | Yes | Panels, 2" tek screws | Sunny | 18 | 11 | No |  | 5 boom lift, 2scissor lift | No |  |  | Yes | South | ACM Flashing Insulation Subgirt Zee | 36 | 10 | [24 empty] | 192FT | 4 |  |  | 230FT | 4 | 120FT | 2
24077 | IAD 667 TI | 2026-02-23 | Fredy veliz | We started late today the job was close in the morning because the weather ,we continue having issues with 150 articulated boom lift ,spent 3 hours trying to make it work but did not work | Subcontractor | Chris Buttrey | Yes | 150 boom lift not working ,weather issues high wind in the east elevation | No |  | Cold and windy | 7 | 38 | No |  | 65 straight boom lift ,135 straight boom lift ,150 articulated boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing clips sc2 south | 38
24079 | Nashville Youth Campus | 2026-02-23 | Obed Bermudez | Crew continues working on the south and west elevation, installing insulation and a Z-girt. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 3 | 10 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | No |  | Insulation Subgirt Zee | [26 empty] | 336 | 15 |  |  | 350 | 15
24089 | BSU Innovation Center | 2026-02-23 | Obed Bermudez | Crew continues working on the south elevation, with panel installation. | Subcontractor | Marc Ribar | No |  | Yes | Caulking (we only have half a box left) Painted screws for aluminum channel, long painted rivets. | Clear | 3 | 10 | No |  | Boom lift | No |  |  | Yes | South and west | Single Skin | [6 empty] | 36 | 30
25002 | Med Center Health | 2026-02-23 | Marvin Blanco | Working in the stone panels in the stairs tower 1 working in the ACM panels in the vertical column south east and working with the corrugated panels in the roof, we have a couple of areas not ready by Kelly construction framing is holding us also weatherproofing in the stairs tower #1 missing a couple of areas and also in the ground | Subcontractor | Carlos Silva | No |  | Yes | 4 panels for the penthouse and also L acm for around the doors | Cold | 15 | 10 | No |  | Boomlift | No |  |  | No |  | ACM Single Skin Terracotta | 10 | 40 |  |  |  |  | 20 | 30 | [8 empty] | 8 | 18
25002 | Med Center Health | 2026-02-23 | Kevin Morris | Installed corrugated panels on roof, installed stone panels on North west stair tower, installed acm on North west side of building | Subcontractor | Carlos Silva | Yes | Framing on roof for corrugated panels | No |  | Cold | 15 | 10 | No |  | 5 boom lifts | No |  |  | No |  | ACM Corrugated / Screen wall Terracotta Trim | 12 | 10 | [14 empty] | 24 | 10 |  |  |  |  | 14 | 10 | [12 empty] | 170 | 4
25036 | TCAT Chattanooga | 2026-02-23 | Obed Bermudez | We started moving our material to the site and installed panels on the north elevation and flashing on the south. | Subcontractor | Josh McPherson | No |  | Yes | 202-1c12A Corner ACM panel that came damaged from the shop. Panel 203-1D02 that was damaged by others. Flashing for north soffit and flashing for south entrance. | Clear | 2 | 10 | No |  | Scissor lifts and forklift. | No |  |  | Yes | North | Flashing Single Skin | [6 empty] | 24 | 18 | [24 empty] | 8 | 2
25050 | LTW062 Fit Out | 2026-02-23 | Mauricio Chavez | The job site does not allow pictures | Subcontractor | Dillon Bowman | Yes | We mobilized to job site but were not able to enter due to paperwork issues. | Yes | Waiting on delivery of material, should arrive 02/24/26 | Cold, cloudy, and windy | 4 | 0 | No |  | Yes | No |  |  | No |  | Louvre | [24 empty] | 0 | 0
25059 | Allen Samuels CDJR and LC | 2026-02-23 | Chad mccoy | Waited all day on a shipment. When the shipment arrived panels were just laying in crates. And panels were not secure. | Subcontractor | Andre Van Der Merwe | Yes | Shipment | No |  | Partly cloudy 26 | 5 | 4 | Yes | 5 crates | 5k lull, 45 foot boom | No |  |  | No |  | ACM | 0 | 0
24077 | IAD 667 TI | 2026-02-21 | Fredy veliz | We are trying to work we the layouts the we have done where the clips are installed already ,because the drawing the we have it was different we probably have to move some of the clips | Subcontractor | Chris Buttrey | No |  | No |  | Good | 8 | 64 | No |  | 65 straight boom lift ,135 straight boom lift ,150 articulate boom ,10k load | No |  |  | Yes | Elevation sc3 section 11,12, and 13 | Louvre | [24 empty] | Installing clips sc2 ,sc6 east | 64
24079 | Nashville Youth Campus | 2026-02-21 | Obed Bermudez | Crew 1 continues doing layout for fiber panels. Crew 2 continues installing z girt and insulation. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 3 | 8 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | No |  | Insulation Subgirt Zee | [26 empty] | 280 | 12 |  |  | 220 | 12
24089 | BSU Innovation Center | 2026-02-21 | Obed Bermudez | Crew continues working on the west elevation, with panel installation. | Subcontractor | Marc Ribar | No |  | Yes | Caulking (we only have half a box left) Painted screws for aluminum channel, long painted rivets. | Clear | 3 | 7 | No |  | Boom lift | No |  |  | Yes | West | Single Skin | [6 empty] | 39 | 21
25002 | Med Center Health | 2026-02-21 | Kevin Morris | Installed stone panels on South stair tower, installed corrugated panels on roof and J trim, fabed facia panel | Subcontractor | Carlos Silva | No |  | No |  | Good | 15 | 6 | No |  | 5 boom lifts | No |  |  | No |  | Corrugated / Screen wall Terracotta Trim | [16 empty] | 28 | 6 |  |  |  |  | 10 | 6 | [12 empty] | 210 | 6
24039 | The Visionary | 2026-02-20 | Wilton lorenzo | Three crews installed panels at the South Stair Tower. One crew installed panels in the Atrium. Another crew installed panels on the West elevation. One crew installed roof panels on the South side. One crew installed coping at the East canopy. | Subcontractor | Carlos Silva | Yes | The wall is very out of square, and we need to install at least 5” of Z-girts. We are installing them both horizontally and vertically, which is slowing down the panel installation at the South Stair Tower. | No |  | Sunny | 18 | 11 | No |  | 5 boom lift,2 scissor lift | No |  |  | Yes | South, west, atrium | ACM Coping Flashing Insulation Subgirt Zee | 48 | 10 | [24 empty] | 352 | 4 |  |  | 200FT | 2 | 20FT | 2 | [6 empty] | 15 galvanized clip. 5 hay channel, 6 coping | 2
24077 | IAD 667 TI | 2026-02-20 | Fredy veliz | Started working late because the rain | Subcontractor | Chris Buttrey | Yes | Was raining all morning | No |  | Raining | 8 | 48 | No |  | 65 straight boom lift ,135 straight boom lift ,150 articulate boom ,10k load | No |  |  | No |  | Louvre | [24 empty] | 4 man Installing blades sc3 section 14,15,and 16 , 2 man installing clips east elevation sc2 ,2 man moving materials | 48
24079 | Nashville Youth Campus | 2026-02-20 | Obed Bermudez | Crew continues working on the east elevation, installing Z girt and insulation. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 3 | 10 | Yes | Truck load of insulation. | Buggy, forklift, conex, boom lifts. | No |  |  | No |  | Insulation Subgirt Zee | [26 empty] | 280 | 10 |  |  | 210 | 20
24089 | BSU Innovation Center | 2026-02-20 | Obed Bermudez | Crew started installing bottom row of panels but we were by the Gc due to high winds. | Subcontractor | Marc Ribar | Yes | Go stopped us early due to high winds | Yes | Caulking (we only have half a box left) Painted screws for aluminum channel, long painted rivets. | Windy | 3 | 4 | No |  | Boom lift. | No |  |  | Yes | West | Single Skin | [6 empty] | 11 | 12
25002 | Med Center Health | 2026-02-20 | Kevin Morris | Fabed and installed 2 panels on west, installed 15 stone panels on South stair tower, installed 10 corrugated panels on roof roof | Subcontractor | Carlos Silva | Yes | Had to uninstall stone panels on west side of South stair tower to fix joints | No |  | Good | 13 | 10 | Yes | I brought 4 flat sheets of acm | 5 boom lifts | No |  |  | No |  | ACM Corrugated / Screen wall Terracotta | 2 | 8 | [14 empty] | 15 | 10 |  |  |  |  | 10 | 10
25017 | Nashville Yards Park | 2026-02-20 | Marvin Blanco | Finishing the column panels but the panels are a little different with the rollers and also one is bigger and the next one shorter the guys try to do the best but it's to much | Subcontractor | Dillon Bowman | No |  | No |  | Good condition | 3 | 10 | No |  | Boomlift | No |  |  | No |  | ACM | 6 | 30
25059 | Allen Samuels CDJR and LC | 2026-02-20 | Chad mccoy | Flashing that was installed by the GC had to be removed for mcdougals flashing of stucco | Subcontractor | Andre Van Der Merwe | Yes | Lots of layout for future trip in parks | Yes | Remake panels. | Lear 72 | 2 | 6 | Yes | Proper wood screws | 45 foot boom | No |  |  | Yes | This is an everywhere layout job 100 times more than normal. Not by prints. But by panels sizes. Bc they don’t all match prints . | ACM Flashing | 20 | 6 | [30 empty] | 35 | 1
24039 | The Visionary | 2026-02-19 | Wilton lorenzo | Two crews installed panels on the stair tower, and after midday I moved one more crew to help them. Two crews installed coping on the east elevation, and one crew installed panels in the atrium. | Subcontractor | Carlos Silva | Yes | on the west side we had to wait about one hour for them to finish installing the TPO. We are also moving slower on the south stair tower because the wall is very uneven, which is taking extra time to level the panels properly. | Yes | Black caulk, | Sunny | 18 | 11 | No |  | 5 boom lift, 2 scissor lift | No |  |  | Yes | South, west | ACM Coping Flashing Insulation Subgirt Zee | 35 | 10 | [24 empty] | 192FT | 4 |  |  | 200FT | 4 | 30FT | 2 | [6 empty] | 240FT of galvanized clip. And 100FT of coping ocean | 4
24077 | IAD 667 TI | 2026-02-19 | Fredy veliz | We are hanging blades on elvation sc3 sections 14 to 16 and clips on elevations sc2 ,sc6 east but we had to stop at noon because of the rain. | Subcontractor | Chris Buttrey | Yes | Weather | No |  | Raining | 8 | 48 | No |  | 65 straight boom lift ,135 straight boom lift ,150 articulates boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | 4 man hanging blades ,2 guys installing clips 2 guys prep materials | 48
24089 | BSU Innovation Center | 2026-02-19 | Obed Bermudez | Aluminum channel installed 20 lf. Strap metal installed 20 lf. Crew continues working on the west elevation installing strongirt, insulation, aluminum channel, strap metal, and flashing. | Subcontractor | Marc Ribar | No |  | Yes | Caulking (we only have half a box left) Painted screws for aluminum channel, long painted rivets. | Clear | 3 | 10 | No |  | Boom lift | No |  |  | Yes | West | Flashing Insulation Subgirt Zee | [26 empty] | 224 | 10 |  |  | 128 | 10 | 139 | 10
25002 | Med Center Health | 2026-02-19 | Kevin Morris | Installed acm and corrugated panels on roof, caulked on North, installed stone panels on South stair tower but had to remove one wall bc Paul and architect did not like joints | Subcontractor | Carlos Silva | Yes | Paul and architect did not like two joints on stair tower had to remove panels on west side to fix | Yes | Acm flat sheets to fab panels in field | Good/ windy | 16 | 10 | No |  | 5 boom lifts | No |  |  | No |  | ACM Caulking Corrugated / Screen wall Terracotta Trim | 5 | 2 | [14 empty] | 16 | 10 |  |  | 200 | 10 | 7 | 4 | [12 empty] | 120 | 3
25022 | Vantage VA15 | 2026-02-19 | Ricardo Banegas | The layout of all panel dimensions was completed in preparation for installation. Overtime hours were worked because we assisted HITT by removing their flag and signage. | Subcontractor | Thomas Mooers | Yes | The scaffold was not ready yet; it was completed and assembled today. | No |  | 36 raining | 10 | 13 | No |  | Boom lift scaffold and swing stage | No |  |  | Yes | West and North | ACM Caulking Flashing Insulation Subgirt Zee | 8 | 40 | [18 empty] | 45ft | 2 |  |  |  |  | 512 | 40 |  |  | 410 | 40 | 20 | 2
25036 | TCAT Chattanooga | 2026-02-19 | Obed Bermudez | We continue working on the south elevation soffit, then cleaned up the job site and moved all our material to the parking lot. | Subcontractor | Josh McPherson | Yes | Gc kept stopping our work. | Yes | Panel 203-1D02 that was damaged by others, brake metal for south soffit, 407 flashing on south elevation where pac clad meets entrance, 202-1c12A Corner Acm panel that came damaged from shop. | Clear | 3 | 12 | No |  | Scissors lifts. | No |  |  | Yes | North/South | Flashing Single Skin | [6 empty] | 26 | 30 | [24 empty] | 40 | 6
25059 | Allen Samuels CDJR and LC | 2026-02-19 | Chad McCoy | Every elevation is a surprise, it’s like Christmas but instead of gifts it’s a nice punch in the face. We installed 23 panels yesterday. 13 field modified and 10 regular. When we got to the elevation of the glass door we found tha yet again the panels that wrap had changed to some other kind of dimension and 4 more panels can not be installed due to the bust. The panels also stick off the building to the point where my 1 3/4 screws will not even reach the structure to hold. So either I cut and route 8 additional panels or 3 inch screws are brought to fill this void. I can’t wait to see what tomorrow brings!!! | Subcontractor | Andre Van Der Merwe | Yes | 4 panels are the wrong size and there is a 7 inch bust | Yes | 3 inch screws or some kind of marital to fit out the wall. | Party cloudy 74 | 2 | 7.5 | No |  | 45 foot boom | No |  |  | Yes | Everywhere | ACM | 23 | 7
24039 | The Visionary | 2026-02-18 | Wilton Lorenzo | Two crews installed ACM on the west elevation. Two crews worked on the south stair tower; there were delays due to excavation activities and limited access. One crew installed coping on the east elevation, and after 2:00 pm, I moved another crew to the east to install coping before access is restricted. Another crew installed panels in the atrium. We had 4 ground helpers. | Subcontractor | Carlos Silva | Yes | Limited access on south | Yes | Anthracite flashing | Sunny | 18 | 11 | No |  | 5 boom lift, 2 scissor lift | No |  |  | Yes | East, south, west | ACM Coping Insulation Subgirt Zee | 36 | 10 | [24 empty] | 448FT | 6 |  |  | 660FT | 6 | [8 empty] | 80FT and 120 galvanized clip, L | 4
24077 | IAD 667 TI | 2026-02-18 | Fredy veliz | Elevation sc3 section 14,15,and 17 are ready to install blades ,sc3 east section 18 and 19 are 100% complete ,on elevation sc2 east section 21,22 and 23 all clips had to be modify because of the bar grating ,same for elevation sc6 section 1 and 2 | Subcontractor | Chris Buttrey | No |  | No |  | Good | 8 | 80 | No |  | 65 straight boom lift ,135 straight boom lift ,150 articulate boom ,10k load | No |  |  | Yes | Elevation sc2 and sc6 east | Louvre | [24 empty] | Installing braces ,elevation sc2 section 14,15 and 17 ,2 man ,installing trim pcs on elevation sc3 east termination 2 man ,modify clips for sc2 east 2 man ,installing clips sc2 east 2 man | 80
24089 | BSU Innovation Center | 2026-02-18 | Obed Bermudez | We continue moving material from lay-down area to site and started installing strongirt, strap metal, and insulation on the west elevation. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 3 | 10 | No |  | Boom lift. | No |  |  | Yes | West | Flashing Insulation Subgirt Zee | [26 empty] | 64 | 10 |  |  | 60 | 10 | 30 | 10
25002 | Med Center Health | 2026-02-18 | Kevin Morris | Installed acm on penthouses, caulked on North, installed stone panels on South stair tower | Subcontractor | Carlos Silva | No |  | No |  | Good | 16 | 10 | No |  | 5 boom lifts | No |  |  | No |  | ACM Caulking Terracotta | 20 | 10 | [14 empty] | 19 | 10 |  |  | 300 | 10
25036 | TCAT Chattanooga | 2026-02-18 | Obed Bermudez | We continue working on the North/south elevation installing pac clad panels and modified an Acm panel. | Subcontractor | Josh McPherson | No |  | Yes | Panel 203-1D02 that was damaged by others, brake metal for south soffit, 407 flashing on south elevation where pac clad meets entrance, 202-1c12A Corner Acm panel that came damaged from shop. | Rainy | 3 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | North and south | ACM Single Skin | 1 | 10 |  |  |  |  | 18 | 20
25059 | Allen Samuels CDJR and LC | 2026-02-18 | Chad McCoy | We are continuing on this grand install and finding more and more panels that are engineered wrong. Panels 1A04 x2 are suppose to be corner panels but they are indeed flat panels. So on a stack of 8 panels 6 are corners and 2 are flat. So these panels and 10 others were turned in today for refab. We installed 22 panels today. 3 were complete fabs, 10 were just installed, and 9 were modified by length and how they finish for this install | Subcontractor | Andre Van Der Merwe | Yes | fabing panels out of panels that are to small, multiple layouts to be sure that panels submitted are the right length and height, and imagination time on how these panels need to be field fabbed for there install!! We left at 8 hrs when we went to install comer panels but they were flat instead | Yes | More caulking will be needed for the other building, flat strapping is also going to be needed bc the started track on the bottom in spots has nothing to attach to bc the layout of the first panels hover over the concrete and there is a void in between the concrete and plywood structure where the screws hold | Over cast and 70 | 2 | 8 | No |  | 45 foot boom | No |  |  | Yes | Everywhere | ACM | 22 | 8
24039 | The Visionary | 2026-02-17 | Wilton Lorenzo | Two crews installed panels on the west elevation. Two other crews started squaring the south stair tower since the wall is about 2” out of level. One crew installed the missing reveal on the east elevation and installed the coping where panels were missing. After that, I moved them to the SE canopy due to high winds. At 1:00 PM, the 45 ft scissor lift was replaced, and I moved one crew to start installing panels in the atrium. | Subcontractor | Carlos Silva | No |  | Yes | 2" z | Sunny | 17 | 11 | No |  | 5 boom lift, 2 scissor lift | No |  |  | Yes | North, west, south | ACM Coping Flashing Subgirt Zee | 26 panels | 8 | [28 empty] | 130FT | 4 | 20FT | 2 | [6 empty] | 40FT | 2
24077 | IAD 667 TI | 2026-02-17 | Fredy veliz | We are done moving the channels on sections 14 ,15,16 and 17 where lay out was wrong because drawings ,had to do little notch on the channels because steel plates are on the ways | Subcontractor | Chris Buttrey | Yes | Wrong layout because incorrect | No |  | Cold | 8 | 80 | No |  | 65 straight boom lift ,135 straight boom lift ,150 articulate boom lift ,10k load | No |  |  | Yes | Blade lay out sc3 sectioon 15 and 16 | Louvre | [24 empty] | Installing blades souths east corners sc3 ,moving channels sc3 sections 14,15,and 17 | 80
24089 | BSU Innovation Center | 2026-02-17 | Obed Bermudez | We received and unloaded a delivery, then checked the area to make sure they were ready and proceeded to move material from the lay-down area to the site. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 2 | 10 | Yes | 40 pieces of 8" strap and 1 bundle of Morin panels. | Boom lift | No |  |  | No |  | Insulation | [26 empty] | 64
25002 | Med Center Health | 2026-02-17 | Kevin Morris | Installed acm panels on penthouses, caulking on North, acm panels on west upper eyebrow, and stone panels and clip rails on South stair tower | Subcontractor | Carlos Silva | No |  | No |  | Good | 15 | 10 | No |  | 5 boom lifts | No |  |  | No |  | ACM Caulking Terracotta | 40 | 10 | [14 empty] | 16 | 10 |  |  | 250 | 10
25022 | Vantage VA15 | 2026-02-17 | Ricardo Banegas | The layout was completed for the installation, and there were significant delays. | Subcontractor | Thomas Mooers | Yes | The wall waterproofing was still incomplete, and work was stopped because the generators on the north side were going to be turned on. This is the area where we are currently working with the swing stage, and it is the only available area to work in at the moment. | No |  | 33 | 10 | 10 | No |  | Boom lift scaffold and swing stage | No |  |  | Yes | West | Subgirt Zee | [30 empty] | 110ft | 10
25036 | TCAT Chattanooga | 2026-02-17 | Obed Bermudez | We modified and installed 5 panels for the eyebrow on west and north elevation. | Subcontractor | Josh McPherson | No |  | Yes | Panel 203-1D02 that was damaged by others, brake metal for south soffit, 407 flashing on south elevation where pac clad meets entrance, 202-1c12A Corner Acm panel that came damaged from shop. | Clear | 3 | 10 | No |  | Boom lifts and forklift | No |  |  | No |  | ACM Flashing | 5 | 25 | [30 empty] | 20 | 5
25059 | Allen Samuels CDJR and LC | 2026-02-17 | Chad McCoy | As we wrap the building installing where we can we find more and more panels are wrong and need modifying due to them being to long or protruding into spots where they do not need to stop at. 24 panels were installed today. 10 was unmodified and 14 were modified by cutting and routing one side Or complete build. Andre came out today. And the pm from Hoyt Hayes. Multiple FaceTime calls were done today as well, to try and figure out the best way to attack the continuous panel in field modification, and installation on this field, engineered and designed install | Subcontractor | Andre Van Der Merwe | Yes | We are installing the best that we can and skipping over areas where panels are gonna have to be made or figured out due to sizes not being able to be justified at a panel that are on site. On this 408 system, we are running into corner excursions that impact each other as the panels are folded for install. We are shortening excursions as we find them | Yes | Proper wood screws, I’ll probably go buy them bc they have to meet engineering standards, | Over cast and chilly 56 | 2 | 10 | Yes | Screws and gutted female excursions | 45 foot boom | No |  |  | Yes | Layout has to be done as we go let each stack of panels due to nothing fitting, there are even panels sizes on the prints that don’t match reality | ACM | 24 | 7
24039 | The Visionary | 2026-02-16 | Wilton Lorenzo | Two crews installed panels on the south wall, two other crews installed on the north, and one crew installed on the west. Delays: Yes. From 3:00 to 4:30, I moved one crew to remove a corner panel at the north stair tower because the GC needs to finish an expansion joint. | Subcontractor | Carlos Silva | Yes | From 3:00 to 4:30, I moved one crew to remove a corner panel at the north stair tower because the GC needs to finish an expansion joint. | No |  | Sunny | 16 | 11 | No |  | 5 boom lift | No |  |  | Yes | South, north, west | ACM Insulation Subgirt Zee | 41 | 10 | [24 empty] | 150FT | 4 |  |  | 100FT | 4
24077 | IAD 667 TI | 2026-02-16 | Fredy veliz | We working on getting the layout fix on elevation 14,15,16, and 17 that was wrong because the drawing was not correct | Subcontractor | Chris Buttrey | Yes | Had to move splices because the drawing was wrong | No |  | Cold | 8 | 80 | No |  | 65 straight boom lift ,135 straight boom lift ,150 articulate boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing blades east elevation ,moving channels splices elevation sc3 sect 14,15,16,17 4 guys 20 hours total ,screw clips sc2 south | 80
25002 | Med Center Health | 2026-02-16 | Kevin Morris | Install panels on west and penthouses. Install stone panels on South stair tower, caulking on North side | Subcontractor | Carlos Silva | No |  | No |  | Good | 15 | 10 | No |  | 5 boom lifts | No |  |  | No |  | ACM Caulking Terracotta | 33 | 10 | [14 empty] | 9 | 10 |  |  | 120 | 10
25036 | TCAT Chattanooga | 2026-02-16 | Obed Bermudez | Crew received and unloaded delivery of pac clad panels and started installing perforated vent on south soffit but GC kept stopping them. | Subcontractor | Josh McPherson | Yes | GC moving us from elevations. | Yes | Panel 203-1D02 that was damaged by others, brake metal for south soffit, 407 flashing on south elevation where pac clad meets entrance, 202-1c12A Corner Acm panel that came damaged from shop. | Clear | 3 | 10 | Yes | Musket gray panels and silver metallic pac clad panels. | Boom lifts and forklift | No |  |  | No |  | Flashing | [32 empty] | 110 | 30
25059 | Allen Samuels CDJR and LC | 2026-02-16 | Chad McCoy Aka Panel Fuckers | Well, where to start on this job. On the first wall. Out of 36 panels, 6 panels do not have to be modified or cut and routed for install. The bottom row of panels are 6 inches to short, Then on the next elevation the are fine. Every panels next to the stucco is to long on the first 5 panels. Then and the last 4 they are to short, at this elevation these panels are suppose to wrap the end of the building and return 7 1/4 inches. They don’t wrap at all. At the garage doors the panels turn into the door openings. But if you do this the panels are too short to cover the walls before the turns. So to combat this we are finishing the panels at the turn like it suppose to be. The panels above the garage door, 1a14 are 7 1/2 to short on elevation so these panels will have to be remade. These two rows of panels are also to short in comparison to the door opening. So one row can be used but the other row will have to be made longer to fill a 3 1/2-4 inch gap. This is at all garage doors on the smaller building. I do not know if I’m being punished or if this is just pure ignorance on these jobs, or if they are just so rushed to be done, but I don’t know how much of these panels I can actually save. I’ll do my best like always but just so it’s stated that will to battle thru it on back to back jobs like this is wearing THIN! 3 panels cut and routed and 2 panels modified to be able to install be garage doors | Subcontractor | Andre Van Der Merwe | Yes | Read notes, talk to Dennis or Andre | Yes | Wood screws. We are screwing into 5/8 plywood with steel drillers, this was tried at Lansing ford and failed after a storm came thru!!! | Sunny 66 | 2 | 8 | Yes | 2 crates of panels that are so unorganized all the panels have to come out to get to starter panels. A crate of flashing and a small pallet of hardware | 5 k lull. 45 foot boom | No |  |  | Yes | Layout was done on 2/201 and 6/202 to find errors | ACM | 8 | 4
24039 | The Visionary | 2026-02-14 | Wilton Lorenzo | Four crews installed panels at the NW corner since it was raining and we couldn’t work on the south side. | Subcontractor | Carlos Silva | Yes | It rained all day | No |  | Rainy | 18 | 8 | No |  | 5 boom lift, 2 scissor lift | No |  |  | Yes | West | ACM Insulation Subgirt Zee | 22 | 8 | [24 empty] | 130ft | 4 |  |  | 80FT | 2
24079 | Nashville Youth Campus | 2026-02-14 | Obed Bermudez | Crew 1 continues doing layout for fiber panels. Crew 2 continues installing z girt and insulation on the east elevation. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 4 | 8 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | No |  | Insulation Subgirt Zee | [26 empty] | 320 |  |  |  | 180
24039 | The Visionary | 2026-02-13 | Wilton Lorenzo | Two crews installed panels on the south elevation, and another crew installed flashing and starter track. One crew installed panels at Patio Level 4, and two other crews started working on layout, installing Z-girts and insulation, and installing panels to the north wall. One guy installed hat channel and L trim at the SE canopy. | Subcontractor | Carlos Silva | No |  | No |  | Sunny | 18 | 11 | Yes | Panels for south stair tower | 5 boom lift, 2 scissor lift, 1 lull | No |  |  | Yes | South, west | ACM Flashing Hat Channel Insulation Subgirt Zee | 48 | 10 | [24 empty] | 448FT | 6 |  |  | 240FT | 8 | 110FT | 6 | 80FT | 1
24077 | IAD 667 TI | 2026-02-13 | Fredy veliz | We have issues with the blade length the drawing there i have had wrong dimensions | Subcontractor | Chris Buttrey | Yes | Wrong lay out ,incorrect drawings | No |  | Cold | 8 | 64 | No |  | 65 straight boom lift ,135 straight boom ,150 articulate boom ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing bolts ,sc3 sections 14,15,16 installing braces sc3 east ,installing clips sc2 ,south | 64
24079 | Nashville Youth Campus | 2026-02-13 | Obed Bermudez | Crew 1 continues doing layout for fiber panels. Crew 2 continues installing z girt and insulation on the south/east elevation. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 4 | 10 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | No |  | Insulation Subgirt Zee | [26 empty] | 310 | 20 |  |  | 330 | 20
25002 | Med Center Health | 2026-02-13 | Kevin Morris | Installed insulation and ACM on penthouses, caulked on North, and installed Stone panels and clip rails on South stair tower | Subcontractor | Carlos Silva | No |  | No |  | Good | 12 | 10 | No |  | 2 boom lifts | No |  |  | No |  | ACM Caulking Insulation Terracotta | 28 | 10 | [14 empty] | 12 | 10 |  |  | 260 | 10 |  |  |  |  | 200 | 2
24039 | The Visionary | 2026-02-12 | Wilton lorenzo | Four crews installed panels on the south elevation. After midday, I assigned another crew to install flashing and starter track above the windows. | Subcontractor | Carlos Silva | No |  | No |  | Sunny | 18 | 11 | Yes | Panels for NW corner and flashing | 5 boom lift | No |  |  | Yes | South | ACM Flashing Insulation Subgirt Zee | 42 | 10 | [24 empty] | 224FT | 6 |  |  | 200FT | 6 | 120FT | 4
24077 | IAD 667 TI | 2026-02-12 | Fredy veliz | Continue installing channel and we found out that some of the 10" tubes are sticking out 2" because those were installed upside down | Subcontractor | Chris Buttrey | No |  | No |  | Cold | 8 | 80 | No |  | 65 straight boom lift ,135 straight boom lift ,150 articulate boom , 10k load | No |  |  | No |  | Louvre | [24 empty] | Installed 35 Chanel's on south elevation sc3 ,isntalling clips sc2 south ,installing braces on east sc3 | 80
24079 | Nashville Youth Campus | 2026-02-12 | Obed Bermudez | Crew 1 continues doing layout for fiber panels. Crew 2 continues installing z girt and insulation on the south/east elevation. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 5 | 10 | Yes | We picked up 4 pallets of insulation at the shop. | Buggy, forklift, conex, boom lifts. | No |  |  | Yes | West/south | Insulation Subgirt Zee | [26 empty] | 440 | 20 |  |  | 230 | 30
25002 | Med Center Health | 2026-02-12 | Kevin Morris | Installed panels and insulation on penthouses, caulked around lights on North, installed stone panels on South stair tower | Subcontractor | Carlos Silva | No |  | No |  | Good | 10 | 10 | No |  | 2 boom lifts | No |  |  | No |  | ACM Flashing Insulation Terracotta | 23 | 10 | [14 empty] | 6 | 8 | [8 empty] | 200 | 2 |  |  |  |  | 20 | 1
24039 | The Visionary | 2026-02-11 | Wilton lorenzo | Four crews installed panels on the south elevation using the boom lift. After lunch, I assigned two workers to clean up all of our debris throughout the building. We need anthracite-colored flashing in order to continue installing the panels on the south elevation. | Subcontractor | Carlos Silva | Yes | I need the flashing for the windows on south and the galvanized L for SE canopy | Yes | Flashing, screws, L, panels | Sunny | 18 | 11 | No |  | 5 boom lift | No |  |  | Yes | South | ACM Insulation Subgirt Zee | 35 | 8 | [24 empty] | 128FT | 3 |  |  | 15FT | 2
24077 | IAD 667 TI | 2026-02-11 | Fredy veliz | Installinh clips and Chanel's eats and south | Subcontractor | Chris Buttrey | No |  | Yes | Drill bits | Cold | 8 | 80 | No |  | 65 straight boom lifts ,135 straight boom lift ,150 articulate boom lift, 10k load | No |  |  | No |  | Louvre | [24 empty] | Installing clips souths sc2, installing Channels sc3 south | 80
24079 | Nashville Youth Campus | 2026-02-11 | Obed Bermudez | Crew continues working on the west/South elevation, installing Z girt and insulation. We started checking layout for panel. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 5 | 10 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | No |  | Insulation Subgirt Zee | [26 empty] | 410 | 30 |  |  | 310 | 20
25002 | Med Center Health | 2026-02-11 | Marvin Blanco | Working in the penthouse but there is a issues with the louvers they're not doing the weatherproofing in side of the louvers weather can go inside of the building | Subcontractor | Carlos Silva | No |  | No |  | Good condition | 8 | 10 | No |  | Boomlift | No |  |  | No |  | ACM | 10 | 80
25002 | Med Center Health | 2026-02-11 | Kevin Morris | Installed zee, insulation, and ACM panels on penthouses. Panels above door are 1/2" to 3/4" to narrow pic attached | Subcontractor | Carlos Silva | No |  | No |  | Cold | 8 | 10 | Yes | Insulation | 3 boom lifts | No |  |  | No |  | ACM Insulation Subgirt Zee | 33 | 10 | [24 empty] | 500 | 5 |  |  | 260 | 3
25022 | Vantage VA15 | 2026-02-11 | Ricardo Banegas | The work has been delayed due to issues with the caulking, caulking inspections, and caulking approval. | Subcontractor | Thomas Mooers | Yes | The work has been delayed due to issues with the caulking, caulking inspections, and caulking approval. | No |  | 28 | 10 | 12 | Yes | Two pallets of ACM, two pallets of flashing. | Boom Lift Scaffolds and swing stage | No |  |  | Yes | North west east south | Subgirt Zee | [30 empty] | 0 | 120
24039 | The Visionary | 2026-02-10 | Wilton Lorenzo | Two crews installed panels on the south curtain wall. After 10:30, a delivery arrived, we unloaded it, and after lunch two crews started pulling layout lines and installing stringline. Another crew installed flashing on the north side, and another crew installed flashing in the atrium up to the height the scissor lift could reach. | Subcontractor | Carlos Silva | Yes | 45 scissor lift still no reach the required height to install panels | Yes | Shims, flat strap, L, anthracite flashing, 1" z, | Sunny | 18 | 11 | Yes | South panels | 5 boom lift, 2 scissor lift | No |  |  | Yes | South | ACM Flashing Insulation Subgirt Zee | 27 panels | 8 | [24 empty] | 120FT | 2 |  |  | 80FT | 4 | 250FT | 3
24077 | IAD 667 TI | 2026-02-10 | Fredy veliz | We got all the materials on site ,we working from east to west and we gonna complete every section 100% done | Subcontractor | Chris Buttrey | No |  | Yes | Drill bits | Cold | 8 | 80 | No |  | 65 straight boom lift ,135 straight boom lift ,150 articulate boom ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing channels sc3 south and east ,installing clips sc2 south | 80
24079 | Nashville Youth Campus | 2026-02-10 | Obed Bermudez | Crew continues working on the west/South elevation, installing Z girt and insulation. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 5 | 10 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | No |  | Insulation Subgirt Zee | [26 empty] | 624 | 20 |  |  | 610 | 30
25002 | Med Center Health | 2026-02-10 | Kevin Morris | Installed 27 acm panels, 200 sq ft insulation, and 160 LF of zees on penthouses. Installed 10 stone panels on South stair tower | Subcontractor | Carlos Silva | No |  | No |  | 60 | 10 | 10 | Yes | Stone panels and ACM | 3 boom lifts | No |  |  | No |  | ACM Insulation Subgirt Zee Terracotta | 27 | 10 | [14 empty] | 10 | 10 | [8 empty] | 200 | 2 |  |  | 160 | 1
25022 | Vantage VA15 | 2026-02-10 | Ricardo Banegas | Each panel was cut and modified according to the dimensions on the drawings. Several panels were adjusted due to changes in the installation caused by equipment issues. | Subcontractor | Thomas Mooers | Yes | The measurements for the roof coupling were taken, since we currently do not have the materials and panels needed for installation. | Yes | Panel and Flashing | 11 | 10 | 10 | No |  | Boom lift scaffold and swing stage | No |  |  | Yes | West and North elevation | Corrugated / Screen wall Subgirt Zee | [22 empty] | 6 | 48 | [6 empty] | 140 ft | 32
24039 | The Visionary | 2026-02-09 | Wilton Lorenzo | Two crews installed panels on top of the Level 4 canopy. After 9:00 AM the delivery arrived, and after lunch they started working on the south side. One crew removed and disposed of trash, then installed flashing on the north side. We have very limited access to the south and east areas. The delivery included coping for the SE canopy and panels for a curtain wall, but the coping cannot be installed because one angle did not arrive and there is no access. The scissor lift in the atrium still does not reach the top level to install the remaining panels, and the articulating boom lift is still not repaired. | Subcontractor | Carlos Silva | Yes | The articulated boom lift has still not been repaired. The scissor lift in the atrium is still not reaching the required height to install the panels. The coping arrived, but the L angle needed for installation did not. Site access remains limited. We do not have the L trim for the expansion joints, and we do not have enough panels to continue the work. | Yes | Panels. L trim. Flashing | Sunny | 18 | 11 | Yes | South paneles. Coping | 5 boom lift, 2scissor lift | No |  |  | Yes | South | ACM Flashing Subgirt Zee | 22 | 6 | [28 empty] | 130FT | 4 | 160 | 4
24077 | IAD 667 TI | 2026-02-09 | Fredy veliz | Clips modify approved on elevation sc2 and sc6 east elev bar grating issues ,moving materials from energy park to site work | Subcontractor | Chris Buttrey | Yes | Weather and steel issues | Yes | Drills bits 7/32 and 21-64 | Cold | 8 | 83 | No |  | 65 straight boom ,135 straight boom ,150 articulate boom ,10 load | No |  |  | No |  | Louvre | [24 empty] | Installing clips elavation sc2 sections 16 to 20 ,installing clips elevation sc3 sections 13 to 16 installing Chanel's sc3 easts section 18 and 19 ,moving materials from energy park | 83
24079 | Nashville Youth Campus | 2026-02-09 | Obed Bermudez | Crew continues working on the west elevation, installing Z girt and insulation. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 4 | 10 | Yes | We picked up 4 pallets of insulation from shop. | Buggy, forklift, conex, boom lifts. | No |  |  | No |  | Insulation Subgirt Zee | [26 empty] | 920 | 20 |  |  | 440 | 20
25002 | Med Center Health | 2026-02-09 | Kevin Morris | Installed insulation, zees and panels on penthouses, reworked expansion joint, trim installed incorrect. Received a shipment of stone panels. | Subcontractor | Carlos Silva | No |  | No |  | 60 | 10 | 10 | Yes | Stone panels | 3 boom lifts | No |  |  | No |  | ACM Insulation Subgirt Zee | 26 | 10 | [24 empty] | 200 | 2 |  |  | 100 | 1
25002 | Med Center Health | 2026-02-09 | Kevin Morris | Installed insulation, zees and panels on penthouses, reworked expansion joint, trim installed incorrect. Received a shipment of stone panels. | Subcontractor | Carlos Silva | No |  | No |  | 60 | 10 | 10 | Yes | Stone panels | 3 boom lifts | No |  |  | No |  | ACM Insulation Subgirt Zee | 26 | 10 | [24 empty] | 200 | 2 |  |  | 100 | 1
24039 | The Visionary | 2026-02-07 | Wilton Lorenzo | One group installed panels on the north stair tower roof. Two groups installed panels above the canopy at the 4th floor . Progress was limited because several panels had to be resized, causing delays while waiting. Two groups installed the remaining panels on the east elevation. There are no more available work areas at this time. Material has not arrived, and the 45’ scissor lift is not reaching the required height to install the panels in the atrium. | Subcontractor | Carlos Silva | Yes | We don't have material. 45 scissor lift still not working | Yes | Panels, caulking, 2" tek 3, flat strap | Sunny | 18 | 8 | No |  | 5 boom lift, 2 scissor lift | No |  |  | Yes | East, north | ACM | 18 | 6
25002 | Med Center Health | 2026-02-07 | Kevin Morris | Installed 15 panels and modified 1 on roof penthouse, installed trim and reinstalled 10 panel on North expansion joint | Subcontractor | Carlos Silva | No |  | No |  | Cold | 8 | 8 | No |  | 3 boom lifts | No |  |  | Yes | Penthouse | ACM Trim | 25 | 8 | [34 empty] | 80 | 3
24039 | The Visionary | 2026-02-06 | Wilton Lorenzo | Two crews installed panels on the north wall. Two other crews installed panels on the roof at the north stair tower. One crew started working above the canopy at north level 4. | Subcontractor | Carlos Silva | Yes | I don't have caulk, flat strap, anthracite flashing, panels coping | Yes | Caulking, flat strap, tek screws, trim for expansion joint, 2 damaged panels and 1 missing 227-1z33 227-1z34 227-1z23 | Sunny | 18 | 10 | No |  | 5 boom lift | No |  |  | Yes | North | ACM Flashing Insulation Subgirt Zee | 23 | 6 | [24 empty] | 288FT | 4 |  |  | 150FT | 4 | 50FT | 2
24077 | IAD 667 TI | 2026-02-06 | Fredy veliz | Continue installing clips sc2,sc3 south and east | Subcontractor | Chris Buttrey | Yes | Weather ,steel issues | No |  | Cold | 6 | 48 | No |  | 65 straight boom ,135 straight boom ,150 articulate boom ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing clips sc3,sc2 east and south | 48
24079 | Nashville Youth Campus | 2026-02-06 | Obed Bermudez | Crew continues working on the west elevation, installing Z girt. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 4 | 10 | No |  | Buggy, forklift, conex, boom lifts. | No |  |  | No |  | Subgirt Zee | [30 empty] | 330 | 40
25002 | Med Center Health | 2026-02-06 | Kevin Morris | Installed zee and insulation on penthouses | Subcontractor | Carlos Silva | No |  | No |  | Cold | 8 | 10 | No |  | 3 boom lifts | No |  |  | Yes | Penthouse | Insulation Subgirt Zee | [26 empty] | 500 | 8 |  |  | 800 | 10
24039 | The Visionary | 2026-02-05 | Wilton Lorenzo | Two crews installed panels on the north wall. Another crew attempted to install panels near the north stair tower, but installation was not possible because the panels were too wide, so they will need to be resized. Two crews installed panels on the roof, following the sequence from the north stair tower. We lifted panels from the 2nd floor to the 4th floor using a scissor lift. Delays: The boom lift is still down. The scissor lift is still not reaching the required height to install the remaining canopy panels. I have not received a response from JWM regarding resizing the panels on level 4 above the canopy. I also have not received a response regarding the panels with the L trim, which is too small. Also , we do not have caulking, anthracite flashing, ocean reveal | Subcontractor | Carlos Silva | Yes | The boom lift is still down. The scissor lift is still not reaching the required height to install the remaining canopy panels. I have not received a response from JWM regarding resizing the panels on level 4 above the canopy. I also have not received a response regarding the panels with the L trim, which is too small. Also , we do not have caulking, anthracite flashing, ocean reveal | Yes | Caulking, flat strap, flashing | Sunny | 18 | 18 | No |  | 5 boom lift, 2 scissor lift | No |  |  | Yes | North | ACM Flashing Insulation Subgirt Zee | 27 panels | 6 | [24 empty] | 448FT | 4 |  |  | 160 | 6 | 30FT | 2
24065 | QTS NAL2 DC2 | 2026-02-05 | Chad McCoy | They are doing a floor inspection on the inside of the main entrance where the freedom wall is. We can not work in there today. So one guy caulked out the inside of the vestibule. 2 guys caulked and flashed out the top back of the blade all and one guy caulked all the skyward joints on the eye brow. A decision today was made to make the freedom wall panels and get more flat stock for the blade wall. That will be tomorrow | Subcontractor | Joe Hoyle | No |  | Yes | More flat stock | 29 partly cloudy | 4 | 7.5 | No |  | 35 foot boom | No |  |  | No |  | Caulking Flashing | [20 empty] | 210 | 6 | [10 empty] | 15 | 2
24077 | IAD 667 TI | 2026-02-05 | Fredy veliz | We continue installing clips ,still have little snow but we are getting better temperatures ,still waiting on updates about the grating issues on the east elevation | Subcontractor | Chris Buttrey | Yes | Weather ,steel issues | No |  | Cold | 6 | 60 | No |  | 65 straight boom ,135 straight boom ,150 articulate boom , 10k load | No |  |  | No |  | Louvre | [24 empty] | Clips on sc2 ,sc3 south | 60
24079 | Nashville Youth Campus | 2026-02-05 | Oned Bermudez | We started safety orientation and received delivery of equipment and materials. We also moved the equipment to the starting location and started installing Z girt. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 4 | 10 | Yes | Equipment and material. | Buggy, forklift, conex, boom lifts. | No |  |  | No |  | Subgirt Zee | [30 empty] | 80 | 40
25002 | Med Center Health | 2026-02-05 | Kevin Morris | Two crews one on each penthouse, installed flashing, strong girt and caulked fasteners on roof | Subcontractor | Carlos Silva | No |  | No |  | Cold | 7 | 10 | No |  | 3 boom lifts | No |  |  | No |  | Caulking Flashing Subgirt Zee | [20 empty] | 1000 | 5 | [8 empty] | 1000 | 10 | 340 | 5
25022 | Vantage VA15 | 2026-02-05 | Ricardo Banegas | Each panel was cut and modified according to the dimensions on the drawings. Several panels were adjusted due to changes in the installation caused by equipment issues. | Subcontractor | Thomas Mooers | Yes | The area where we are installing the corrugated panels is considered a high-risk zone, so we must take extra precautions. | Yes | Flashing | 15 | 10 | 10 | Yes | Painting screws and rivets | Boom lift scaffold and swing stage | No |  |  | Yes | West and North elevation | Corrugated / Screen wall Subgirt Zee | [22 empty] | 20 | 60 | [6 empty] | 570 ft | 40
25022 | Vantage VA15 | 2026-02-05 | Ricardo Banegas | Each panel was cut and modified according to the dimensions on the drawings. Several panels were adjusted due to changes in the installation caused by equipment issues. | Subcontractor | Thomas Mooers | Yes | The area where we are installing the corrugated panels is considered a high-risk zone, so we must take extra precautions. | Yes | Flashing | 15 | 10 | 10 | Yes | Painting screws and rivets | Boom lift scaffold and swing stage | No |  |  | Yes | West and North elevation | Corrugated / Screen wall Subgirt Zee | [22 empty] | 36 | 120 | [6 empty] | 630 ft | 60
25022 | Vantage VA15 | 2026-02-05 | Ricardo Banegas | Each panel was cut and modified according to the dimensions on the drawings. Several panels were adjusted due to changes in the installation caused by equipment issues. | Subcontractor | Thomas Mooers | Yes | The area where we are installing the corrugated panels is considered a high-risk zone, so we must take extra precautions. | Yes | Flashing | 15 | 10 | 18 | Yes | Painting screws and rivets | Boom lift scaffold and swing stage | No |  |  | Yes | West and North elevation | Corrugated / Screen wall Subgirt Zee | [22 empty] | 36 | 120 | [6 empty] | 630 ft | 60
24039 | The Visionary | 2026-02-04 | Wilton lorenzo | Panels were completed on the east roof wall. Two groups installed the corners at the north stair tower, and once one group finished, they continued following the sequence toward the roof. Another group installed panels on the north wall, and one more group installed panels on the north side near the expansion joint. We lifted 16 panels from the 2nd floor to the 5th floor using a scissor lift. There were delays. One boom lift broke down, so I cannot install the panels above the west canopy because they are too large. I also cannot install the panels below that canopy because there is a return going toward the door, and it is too short and does not cover the wall. Also , I am out of flashing for the north wall and ocean reveal they don't send enough | Subcontractor | Carlos Silva | Yes | One boom lift broke down, so I cannot install the panels above the west canopy because they are too large. I also cannot install the panels below that canopy because there is a return going toward the door, and it is too short and does not cover the wall. | Yes | Caulking, tek screws, flashing, reveal, coping | Sunny | 18 | 11 | No |  | 5 boom lift, 2 scissor lift | No |  |  | Yes | North | ACM Insulation Subgirt Zee | 32 | 8 | [24 empty] | 480FT | 4 |  |  | 230FT | 6
24065 | QTS NAL2 DC2 | 2026-02-04 | Chad McCoy | The freedom wall was peeled but upon peeling. Damage was found yet again under the peel. One was a snake like ripple and the out is a heavy crease. In all the vestibule panels there is a rolled spot that is 5/8 wide and roughly 3 inches tall in all the panels | Subcontractor | Joe Hoyle | Yes | Continuous damage in panels tha we are replacing because of damage from the shop. Not our install but damaged panels that are coming to us | Yes | Panels from the shop that are undamaged | Cloudy and cold 22 | 4 | 8 | No |  | 35 foot boom | No |  |  | No |  | Caulking Flashing | [20 empty] | 300 | 7 | [10 empty] | 270 | 3
24077 | IAD 667 TI | 2026-02-04 | Fredy veliz | Continue installing clips on the east elevation,the 150 articulate boom is been down since yesterday the mechanic show up to work on it ,still not working and he say will be back tomorrow to get it done | Subcontractor | Chris Buttrey | Yes | Weather and issues with the equipment | No |  | Cold | 6 | 54 | No |  | 65 straight boom ,135 straight boom ,150 articulate boom ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing clips on sc2 south and sc3 east | 54
25002 | Med Center Health | 2026-02-04 | Kevin Morris | Craned materials to roof for penthouses, installed drip flashing and caulked | Subcontractor | Carlos Silva | No |  | No |  | Cold | 5 | 10 | No |  | 3 boom lifts and crane | No |  |  | No |  | Caulking Flashing Subgirt Zee | [20 empty] | 160 | 1 | [8 empty] | 20 | 1 | 160 | 3
24039 | The Visionary | 2026-02-03 | Wilton lorenzo | Two groups installed panels on the 5th floor roof, and two groups installed the corners of the north stair tower. One group started installing panels on the adjacent wall, and the others located panels and installed clips on them. The 45 ft scissor lift is still not working. One boom lift has been repaired. | Subcontractor | Carlos Silva | Yes | 45ft scissor lift still not working | Yes | Caulking. Flat trap, panels, reveal, coping for east side | Sunny | 18 | 11 | No |  | 5 boom lift, 2 scissor lift, 1 lull | No |  |  | Yes | North and east wall | ACM Insulation Subgirt Zee | 44 panels | 12 | [24 empty] | 576FT | 4 |  |  | 370 FT | 6
24065 | QTS NAL2 DC2 | 2026-02-03 | Chad McCoy | The material for the wing wall will be here tonight. We will make them tomorrow. The back side of the vestibule was removed and the inside of the vestibule was installed. All but 3. | Subcontractor | Joe Hoyle | Yes | Awaiting material for stock | Yes | Flat stock | 26 windy | 4 | 8 | No |  | 35 foot electric boom | No |  |  | No |  | ACM | 21 | 8
24077 | IAD 667 TI | 2026-02-03 | Fredy veliz | We continue installing clips and Chanel's on the east ,me and Chris hand a conversation about the issues with the steel where 10" tube sticking out ,he told me to go head and swap the Chanel's and use the 3" Chanel's designed to be installed in the vertical tubes ,es still waiting on answers about other issues | Subcontractor | Chris Buttrey | Yes | Weather and Steels issues | No |  | Cold | 7 | 60 | No |  | 65 straight boom ,135 straight boom ,150 articulate boom ,10k load | No |  |  | Yes | Elevation sc3 section 14 | Louvre | [24 empty] | Clips and Chanel's east elevation | 60
25002 | Med Center Health | 2026-02-03 | Marvin Blanco | Finishing installing the brackets in the stairs tower for the stone panels and moving material for the penthouse we have issues in the penthouse the weatherproofing it's not good | Subcontractor | Carlos Silva | No |  | No |  | Cold | 5 | 10 | Yes | ACM panels for the penthouse | Boomlift | No |  |  | No |  | Hat Channel | [34 empty] | 300 | 50
25002 | Med Center Health | 2026-02-03 | Kevin Morris | Installed flashing on penthouse, prepped for crane arriving tomorrow, unload FS10 acm panels, installed 230 LF of clip rails for stone panels on South stair tower | Subcontractor | Carlos Silva | No |  | No |  | Cold/ice | 5 | 10 | Yes | Acm FS10 | 3 boom lifts | No |  |  | No |  | Flashing | [32 empty] | 200 | 10
25017 | Nashville Yards Park | 2026-02-03 | Marvin Blanco | Working in the stairs tower with ACM panels almost done but we have a couple of issues we couldn't finish because those issues | Subcontractor | Dillon Bowman | No |  | No |  | Cold | 3 | 10 | No |  | Boomlift | No |  |  | No |  | ACM | 8 | 30
25022 | Vantage VA15 | 2026-02-03 | Ricardo Banegas | Each panel has been cut and modified according to the dimensions shown on the drawings. | Subcontractor | Thomas Mooers | Yes | The area where we are installing the corrugated panels is considered a high-risk zone, so we must take extra precautions. | Yes | Flashing | 18 | 10 | 10 | No |  | Boom Lift, scaffolding, swing stage | No |  |  | Yes | West | Corrugated / Screen wall Subgirt Zee | [22 empty] | 9 | 60 | [6 empty] | 470 ft | 40
25031 | LLU Mars US Warehouse | 2026-02-03 | Abner aguilar | The windows guy removed the flashing wnd damaged 2 panel on the north side | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | No |  | ACM Insulation Subgirt Zee | 12 | 44 | [24 empty] | 256 | 44 |  |  | 17 | 44
24039 | The Visionary | 2026-02-02 | Wilton Lorenzo | Two crews installed ACM on the east wall at the roof level. Two other crews worked on the canopy on the same wall. one crew installed coping, and after they finished, I moved two crews to the north wall. The panels were fabricated incorrectly, and they will not be covered by the wall return. The 45’ scissor lift still does not reach the height required to install the panels. | Subcontractor | Carlos Silva | Yes | 45' scissor lift sill not working, | Yes | Caulking. Flashing color anthracite | Sunny | 18 | 11 | No |  | 5 boom lift, 3scissor lift | No |  |  | Yes | North. East wall roof | ACM Coping Flashing Insulation Subgirt Zee | 46 | 10 | [24 empty] | 320FT | 6 |  |  | 230FT | 6 | 30FT | 2 | [6 empty] | 7 coping and 12 pieces of galvanized L and clips | 3
24065 | QTS NAL2 DC2 | 2026-02-02 | Chad McCoy | Freedom wall was finished. And wing wall was taken down and we put all panels back up except the 2 mcdougal forget to send. I will have to make them | Subcontractor | Joe Hoyle | Yes | Missing panels | Yes | Patience | 17 cold snowing | 4 | 10.5 | No |  | 35 foot electric | No |  |  | No |  | ACM | 26 | 10
24077 | IAD 667 TI | 2026-02-02 | Fredy veliz | We are working slow because the excess of snow in the areas ,we been moving materials to the fence to clear out the areas for GC they gonna be cleaning | Subcontractor | Chris Buttrey | Yes | Snow and low temperatures | No |  | Cold | 7 | 70 | No |  | 65 straight boom ,135 straight boom ,150 articulate boom ,10k load | No |  |  | Yes | Elevation sc3 east ,sc2 south east corner | Louvre | [24 empty] | Installing clips on sc2 south,sc3 south and east ,moving materials to clean snow | 70
25002 | Med Center Health | 2026-02-02 | Marvin Blanco | Working in the stairs tower one and also checking the roof the penthouse for install the ACM there's is a couple of areas that needs weatherproofing | Subcontractor | Carlos Silva | No |  | No |  | Cold | 5 | 10 | No |  | Boomlift | No |  |  | No |  | Hat Channel | [34 empty] | 600 | 50
25002 | Med Center Health | 2026-02-02 | Kevin Morris | Installed clip rails for stone panels | Subcontractor | Carlos Silva | No |  | No |  | Cold | 5 | 10 | No |  | 3 boom lifts | No |  |  | Yes | South stair tower | Tubing | [28 empty] | 500 | 10
25022 | Vantage VA15 | 2026-02-02 | Ricardo Banegas | The panels have been modified and cut according to each of the dimensions shown on the plans. | Subcontractor | Thomas Mooers | Yes | We have had very low temperatures, and the area where we are installing the panels is considered high risk. | Yes | Flashing | 6 | 10 | 10 | No |  | Boom lift, swing stage, scaffolds | No |  |  | Yes | West | Corrugated / Screen wall Subgirt Zee | [22 empty] | 14 | 60 | [6 empty] | 56 | 40
25031 | LLU Mars US Warehouse | 2026-02-02 | Abner aguilar | No | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | Yes | West | ACM Insulation Subgirt Zee | 16 | 44 | [24 empty] | 232 | 44 |  |  | 15 | 44
24065 | QTS NAL2 DC2 | 2026-02-01 | Chad mccoy | Continuation of freedom wall | Subcontractor | Joe Hoyle | Yes | Panels had to be made bc they were made wrong at mcdougal | No |  | Cold -17 with wind | 4 | 8 | No |  | 35 foot electric | No |  |  | No |  | ACM | 14 | 8
24039 | The Visionary | 2026-01-31 | Wilton Lorenzo | Two crews installed the galvanized piece, L, and coping on the east side. Two crews started working on the east wall on the 4th floor since the lower flashing was completed yesterday by Crossland. Two other crews installed panels on the same wall at the roof level. One boomlift was down and would not start, so the rest of the crew focused on installing clips on the panels. | Subcontractor | Carlos Silva | Yes | One boom lift is broke down, the 45 scissor lift still not working and we can't finish the atrium | Yes | Caulking, flat strap, panels, coping | Sunny | 18 | 8 | No |  | 5 boom lift, 2 scissor lift, | No |  |  | Yes | East wall lvl4 | ACM Coping Insulation Subgirt Zee | 26 panels | 6 | [24 empty] | 160 ft | 2 |  |  | 140ft | 2 | [8 empty] | 250FT galvanizes clips and L, 70FT of ocean metallic coping | 4
24065 | QTS NAL2 DC2 | 2026-01-31 | Chad McCoy | Continuation on the freedom wall | Subcontractor | Joe Hoyle | Yes | Sick crew | No |  | 18 cold | 2 | 8 | No |  | 35 electric boom | No |  |  | No |  | ACM | 16 | 8
25002 | Med Center Health | 2026-01-31 | Kevin Morris | Installed remakes on upper facia north side, fabed and installed lower soffit north elevation | Subcontractor | Carlos Silva | No |  | No |  | Cold/ice | 3 | 6 | No |  | 3 boom lifts | No |  |  | No |  | ACM | 3 | 6
25022 | Vantage VA15 | 2026-01-31 | Ricardo Banegas | Each panel has been cut and modified according to the dimensions shown in the plans. | Subcontractor | Thomas Mooers | Yes | The weather is extremely cold, which makes it difficult to work. We are using scaffolding, which limits our ability to make fast progress. The work areas are complicated, and we do not have a stable workspace. | Yes | Flashing | 3 | 10 | 10 | No |  | Boom Lift and sccafold | No |  |  | Yes | West | Corrugated / Screen wall Subgirt Zee | [22 empty] | 19 | 60 | [6 empty] | 570 ft | 40
24039 | The Visionary | 2026-01-30 | Wilton lorenzo | Three crews installed panels on the north elevation until 10:00 a.m. I am unable to complete the elevation because the expansion joints are not finished. From 12:30 p.m. to 3:00 p.m., I used 12 workers to move panels, Z girts, insulation, three Baker scaffolds, flashing, and plywood from the 2nd floor to the 4th floor using a scissor lift. We received a coping delivery for the east canopy, but the color is incorrect. It was supposed to be Sunrise Silver Metallic, but it arrived blue. Two crews installed coping on the east side. The 45-ft scissor lift is still damaged. | Subcontractor | Carlos Silva | Yes | I am unable to complete the elevation because the expansion joints are not finished. From 12:30 p.m. to 3:00 p.m., I used 12 workers to move panels, Z girts, insulation, three Baker scaffolds, flashing, and plywood from the 2nd floor to the 4th floor using a scissor lift. We received a coping delivery for the east canopy, but the color is incorrect. It was supposed to be Sunrise Silver Metallic, but it arrived blue. Two crews installed coping on the east side. The 45-ft scissor lift is still damaged. | Yes | Coping, caulking | Sunny | 18 | 10 | Yes | Coping and flashing | 5 boom lift, 3 scissor lift | No |  |  | Yes | North, east wall roof | ACM Coping Insulation Subgirt Zee | 12 | 6 | [24 empty] | 134FT | 4 |  |  | 90FT | 2 | [8 empty] | 10 Coping color ocean metallic and 24 galvanized pieces | 3
24065 | QTS NAL2 DC2 | 2026-01-30 | Chad McCoy | No work. Two guys sick. | Subcontractor | Joe Hoyle | Yes | Guy sick | Yes | Vestibule panels and patience to make new panels | 23 cloudy below freezing in am | 3 | 0 | No |  | 35 foot boom | No |  |  | No |  | ACM | 0 | 0
24077 | IAD 667 TI | 2026-01-30 | Fredy veliz | We working half days because the temperatures is very cold | Subcontractor | Chris Buttrey | Yes | Weather is very cold | No |  | Very cold | 6 | 24 | No |  | 65 straight boom ,135 straight boom ,150 articulate boom ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing clips | 24
24039 | The Visionary | 2026-01-29 | Wilton lorenzo | 4 crews installed panels on the north elevation. We cannot install all the north panels because the expansion joints on the north side are not finished yet. We also cannot install the panels on the 4th floor due to the Hydrotech. One crew installed coping until noon, and after lunch they cut and bent 15 coping pieces for 5 hours (3 guys). The scissor lift still doesn’t go all the way up. We are running low on panels. | Subcontractor | Carlos Silva | Yes | I cannot install the panels near the expansion joints because they are not finished. I also cannot install the panels on the 4th floor because the Hydrotech has not been installed. I cannot install the roof panels on the east wall because the flashing is in the way. I am running out of panels to install, and I am working on the coping pieces that need to be bent. The scissor lift still does not reach the floor where we need to install panels. | Yes | Panels. Flashing | Sunny | 18 | 10 | No |  | 5 boom lift, 3 scissor lift, 1 lull | No |  |  | Yes | North | ACM Insulation Subgirt Zee | 41 panels | 50 | [24 empty] | 320FT | 40 |  |  | 150FT | 20
24065 | QTS NAL2 DC2 | 2026-01-29 | Chad McCoy | Freedom wall continued. But 6 panels are the wrong size I have to make them | Subcontractor | Joe Hoyle | Yes | 6 m28 panels are the wrong size again | Yes | Vestibule panels | 22 cloudy | 3 | 10 | No |  | 35 foot electrical boom | No |  |  | Yes | Panels are the wrong size so we are checking everything | ACM | 14 | 9
24077 | IAD 667 TI | 2026-01-29 | Fredy veliz | We come back to work today but is very difficult to work a lot snow and low temperatures | Subcontractor | Chris Buttrey | Yes | We Had big storm this week the job was close | No |  | Cold | 6 | 48 | No |  | 65 straight boom ,135 straight boom ,150 articulate boom ,10k load | No |  |  | Yes | Elevation sc2 section 18 ,19 and 20 | Louvre | [24 empty] | Clips on sc2 and sc3 south | 48
25002 | Med Center Health | 2026-01-29 | Kevin Morris | Installed panels on lower soffit west side, removed 9 panels at expansion joint, caulked 60 LF on north lower soffit | Subcontractor | Carlos Silva | No |  | No |  | Cold | 4 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM Caulking | 16 | 10 | [18 empty] | 60 | 6
25022 | Vantage VA15 | 2026-01-29 | Ricardo | Each panel has been cut and modified according to the dimensions specified in the plans. | Subcontractor | Thomas Mooers | Yes | Material unloading has caused heavy traffic in the area where we are working, and we do not have a fixed work area. | Yes | Flashig | 4 | 10 | 10 | No |  | Boom Lift and Sccafolf | No |  |  | Yes | East and north elevation | Corrugated / Screen wall Flashing Subgirt Zee Trim | [22 empty] | 18 | 60 | [6 empty] | 70 ft | 10 | 80 ft | 10 |  |  | 20 ft | 10
24039 | The Visionary | 2026-01-28 | Wilton Lorenzo | Four groups installed panels on the north side. Delays: Yes. After 3 PM, I moved one group from the north to install panels in the atrium because they brought a 45 ft scissor lift, but it does not fully raise. We tried to level it, but it didn’t work. Also, a two guys crew bent 7 coping pieces over 3 hours. They had to go up and down repeatedly to take measurements and bend the pieces. | Subcontractor | Carlos Silva | Yes | After 3 PM, I moved one group from the north to install panels in the atrium because they brought a 45 ft scissor lift, but it does not fully raise. We tried to level it, but it didn’t work. Also, a two guys crew bent 7 coping pieces over 3 hours. They had to go up and down repeatedly to take measurements and bend the pieces. | Yes | Tek screws, shims, flat traps, | Sunny | 18 | 10 | No |  | 5 boom lift, 3 scissor lift, 1 lull | No |  |  | Yes | North | ACM Coping Flashing Insulation Subgirt Zee | 27 panels | 80 | [24 empty] | 256FT | 40 |  |  | 170 | 20 | 60FT | 20 | [6 empty] | 30FT | 20
24065 | QTS NAL2 DC2 | 2026-01-28 | Chad McCoy | Freedom wall was continued | Subcontractor | Joe Hoyle | No |  | Yes | Vestibule panels | Cloudy 15 | 3 | 10 | No |  | 35 foot boom | No |  |  | No |  | ACM | 19 | 9
25002 | Med Center Health | 2026-01-28 | Marvin Blanco | Working in the soffit modifying panels and also cleaning our areas of work and checking our drawings for start working in the stone stairs tower but there is a little issue with the joints we have ½ joints and it's going to be visible the insulation and also in the roof my guy talk to the GC to start working in the corrugated panels in the roof but they change the details and drawings and we don't have anything any updates only old drawings | Subcontractor | Carlos Silva | No |  | Yes | Panels | Cold | 7 | 10 | No |  | Boomlift | No |  |  | No |  | ACM | 9 | 70
25002 | Med Center Health | 2026-01-28 | Kevin Morris | Installed panels on west side soffit, caulked north soffit, installed zee and insulation south stair tower, removed 2 damaged panels on north upper facia, peeled north stair tower | Subcontractor | Carlos Silva | Yes | Need framing for morin panels on roof, 2 boom lifts were down in the morning | No |  | Cold/ice | 7 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM Caulking Insulation Subgirt Zee | 16 | 10 | [18 empty] | 120 | 10 |  |  |  |  | 200 | 5 |  |  | 60 | 5
25022 | Vantage VA15 | 2026-01-28 | Ricardo Banegas | Each panel has been cut and modified according to the dimensions shown on the plans. | Subcontractor | Thomas Mooers | Yes | The boom lifts were relocated. We did not have a work area in the morning. Weather conditions were very poor | Yes | Flashing | 8 | 10 | 10 | Yes | The swing stage lifelines and screws | Boom Lift and Scaffold | No |  |  | Yes | East and North elevation | Corrugated / Screen wall Flashing Subgirt Zee Trim | [22 empty] | 18 | 60 | [6 empty] | 60ft | 20 | 110ft | 20 |  |  | 30ft | 20
25031 | LLU Mars US Warehouse | 2026-01-28 | Abner aguilar | No | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | No |  | ACM Insulation | 19 | 44 | [24 empty] | 370 | 44
24039 | The Visionary | 2026-01-27 | Wilton lorenzo | Four crews worked installing ACM on the north wall. One crew installed ACM on the 4th floor. One crew attempted to install coping on the east side, but the two back and front pieces are one inch too long, so tomorrow I will start bending them. | JWMCD Crew | Carlos Silva | Yes | The battery on a boom lift was dead, and we had to jump-start it to get it running. We need to modify two pieces of the coping system so it fits the required dimensions, and the 45-ft scissor lift is still damaged. | Yes | Caulking, flashing, tek screws, 1/16 shims, | Sunny | 18 | 8 | No |  | 5 boom lift, 2 scissor lift | No |  |  | Yes | North | ACM Insulation Subgirt Zee | 30 panels | 8 | [24 empty] | 224FT | 6 |  |  | 30FT | 2
24065 | QTS NAL2 DC2 | 2026-01-27 | Chad McCoy | Do to snow and weather delays we have not been able to get in to work. We removed 34 panels. And installed 11 installed We have to dig out our strapping. So old reveals were used as strapping until we can dig and find the strapping in yard with 13 inches of snow | Subcontractor | Joe Hoyle | Yes | 13 inches of snow. And zero and below temps | Yes | Vestibule panels | 13 inches of snow and zero degree temps | 3 | 10 | No |  | 35 foot boom | No |  |  | Yes | Freedom wall | ACM | -34 panels removed and 11 installed | 11
25002 | Med Center Health | 2026-01-27 | Kevin Morris | Installed soffit on west side lower level, peeled north stair tower, did sample caulk on north soffit, installed zee on south stair tower, talked to Paul about morin panels on roof Kelly want panels going vertical instead of horizontal, i notified Carlos of changes | Subcontractor | Carlos Silva | Yes | Booms didn't want to start or function properly due to ice and cold | No |  | Cold/ice | 7 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM Caulking Subgirt Zee | 7 | 10 | [18 empty] | 1 | 1 | [8 empty] | 40 | 5
24065 | QTS NAL2 DC2 | 2026-01-24 | Chad McCoy | The freedom wall take down was started today. 30 panels removed. K | Subcontractor | Joe Hoyle | No |  | Yes | Vestibule panels | Cold cloudy | 3 | 8 | No |  | 35 foot boom | No |  |  | No |  | ACM | -30 | 8
24039 | The Visionary | 2026-01-23 | Wilton Lorenzo | Two crews installed panels on the 4th floor, and when one of them finished, they moved to the north stair tower to install Z flashing, insulation, and panels. Three crews installed panels, flashing, and insulation on the north elevation, and one crew worked on installing coping on the east side. | Subcontractor | Carlos Silva | Yes | 47ft scissor lift is broke down can't install panel on lvl 4 because they need to instal hydrotech and we need flashing for roof panels | Yes | Flashing, caulking | Cloudy | 18 | 10 | No |  | 3 scissor lift, 5 boom lift | No |  |  | Yes | North | ACM Flashing Insulation Subgirt Zee | 41 | 80 | [24 empty] | 340FT | 40 |  |  | 160FT | 20 | 60FT | 4
24077 | IAD 667 TI | 2026-01-23 | Fredy veliz | We covered all the clips and screws with plastic to avoid the snow cover the material ,job probably gonna be close for couple of days after the storm | Subcontractor | Chris Buttrey | Yes | Areas not ready ,materials on the way and weather | No |  | Cold and windy | 6 | 48 | No |  | 65 straight boom lift ,135 straight boom ,150 articulate boom ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing clips east and south sc3,installing braces sc2 | 48
25002 | Med Center Health | 2026-01-23 | Kevin Morris | Installed 10 panels on west elevation below soffit and above windows, installed 20 lf of flashing, fabed 5 soffit panels for lower soffit on west elevation | Subcontractor | Carlos Silva | Yes | Lights had to be adjusted electrician finished today | No |  | Cold | 5 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM Flashing | 10 | 9 | [30 empty] | 20 | 1
25022 | Vantage VA15 | 2026-01-23 | Ricardo Banegas | We are having problems with the work area. | Subcontractor | Thomas Mooers | Yes | The area is not finished, and we don’t have a fixed work area. | Yes | Painted screws and flashing | 18 | 10 | 10 | No |  | Boom Lift Baker Scaffold | No |  |  | No |  | Subgirt Zee | [30 empty] | 350 | 35
24039 | The Visionary | 2026-01-22 | Wilton lorenzo | One crew installed panels in the atrium. The 47 ft scissor lift is out of calibration, and maintenance said they ordered sensors and will probably install them tomorrow. Two crews started getting the north area ready to install panels. Two crews installed panels on the 4th floor on the east side. One crew installed hat channel on the east side and started working on the coping frame. | Subcontractor | Carlos Silva | Yes | The 47 ft scissor lift is out of calibration, and maintenance said they ordered sensors and will probably install them tomorrow. We won’t be able to install the panels on the north side near the expansion joint because Crossland needs to modify two expansion joints. I can’t install panels in the 4rd floor patio because I have to wait for the Hydrotech. For the roof panels, I need the modified flashing in Ocean Metallic color. | Yes | Caulking, flashing for roof, | Sunny | 18 | 10 | Yes | Insulation | 5 boom lift, 3 scissor lift | No |  |  | Yes | North and atrium | ACM Flashing Hat Channel Insulation Subgirt Zee | 30 panels | 10 | [24 empty] | 672Ft | 10 |  |  | 310ft | 10 | 30ft | 2 | 30FT | 2
24046 | UAB Biomedical Research and Psycholgy | 2026-01-22 | Naza Padron | north canopy 180' LF flat strap 12 hours | Subcontractor | Wylie McDougall | No |  | No |  | sunny | 7 | 70 | No |  | N/A | No |  |  | No |  | ACM Insulation Subgirt Zee Trim | 37 | 44 | [24 empty] | 128 | 8 |  |  | 120 | 10 |  |  |  |  | 40 | 8
24077 | IAD 667 TI | 2026-01-22 | Fredy veliz | We continue workin in the areas where we can work stills a lot material on the way | Subcontractor | Chris Buttrey | Yes | Weather and many material and equipment on the way | No |  | Cold | 6 | 54 | No |  | 65 straight boom lift ,135 straight boom lift ,150 articulate boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | 54 | Installing Chanel's on sc5 and braces ,installing braces on sc2 south section 1 to 5 ,installing clips east sc3
25002 | Med Center Health | 2026-01-22 | Kevin Morris | Installed panels and flashing on west side between upper soffit and windows, electrician started moving lights on lower soffit | Subcontractor | Carlos Silva | No |  | No |  | Cold | 5 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM Flashing | 12 | 8 | [30 empty] | 50 | 2
25022 | Vantage VA15 | 2026-01-22 | Ricardo Banegas | We are having problems with the work area. | Subcontractor | Thomas Mooers | Yes | The area is not finished, and we don’t have a fixed work area. | Yes | Painted screws and flashing | 18 | 10 | 10 | Yes | One palet of metal Z | Boom Lift Baker Scaffold | No |  |  | Yes | South Penthouse | Subgirt Zee | [30 empty] | 600 ft | 60
25040 | Moses Lincoln Vitrine | 2026-01-22 | Abner aguilar | 1 pallet | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | Yes | Acm | Boom lift | No |  |  | No |  | ACM Caulking | 6 | 44 | [18 empty] | Yes | 44
24039 | The Visionary | 2026-01-21 | Wilton lorenzo | Two crews installed panels in the atrium. The large scissor lift is out of calibration. A technician came to try to repair it and was on site for a couple of hours, but said it could not be fixed and needs to be replaced. They do not have the same unit available nearby. Two crews installed hat channel as soon as it arrived this morning, and one crew installed panels on the 4th-floor patio. With the help of Crossland superintendents, the crane was used to fly one scissor lift and six crates of panels up to the 4th floor. | Subcontractor | Carlos Silva | Yes | There are two expansion joints on the north side, and I cannot install panels near them because they need to be repaired and work has not started yet. Also, I cannot install panels on the 4th floor above the canopy because something needs to be installed at the expansion joint first. The 45 ft scissor lift is out of calibration, causing it to operate very slowly and requiring multiple shutdowns throughout the day. A technician came today to inspect it but was unable to repair it. A significant amount of time was lost while troubleshooting the issue. | No |  | Sunny | 16 | 10 | Yes | Hat channel | 5 boom lift 3 scissor lift | No |  |  | Yes | East, atrium | ACM Flashing Hat Channel Insulation Subgirt Zee | 24 panels | 6 | [24 empty] | 416ft | 4 |  |  | 30ft | 2 | 10ft | 2 | 380ft | 4
24046 | UAB Biomedical Research and Psycholgy | 2026-01-21 | Naza Padron | N/A | Subcontractor | Wylie McDougall | No |  | No |  | sunny | 7 | 70 | No |  | N/A | No |  |  | No |  | ACM Insulation | 39 | 46 | [24 empty] | 640 | 24
24072 | LCK064 | 2026-01-21 | Mauricio Chavez | Installed trims and kinetic panels. Completed the NW elevation (elevation 3 on drawings) | Subcontractor | Joe Hoyle | No |  | No |  | Windy | 6 | 12 | No |  | Yes | No |  |  | Yes | Elevation 3 and 2 | Corrugated / Screen wall Trim | [22 empty] | 45 | [13 empty] | 120 ft
24077 | IAD 667 TI | 2026-01-21 | Fredy veliz | We are having progress on the Chanel installs but we have to stop when wind get to high ,me and Chris walked the job to review the issues and possible solutions | Subcontractor | Chris Buttrey | Yes | Weather conditions slowing down the process | No |  | Cold and windy | 7 | 56 | No |  | 65 straight boom lift ,135 straight boom lift ,150 articulate boom lift ,10k load | No |  |  | Yes | Lay out elevation sc3 sections 15 ,16 and 17 | Louvre | [24 empty] | Installed Chanel's and clips | 56
25002 | Med Center Health | 2026-01-21 | Kevin Morris | Installed panels on west lower soffit, and cut out fees so lights can be moved | Subcontractor | Carlos Silva | No |  | No |  | Rain | 5 | 10 | Yes | Caulk | 3 boom lifts | No |  |  | No |  | ACM | 18 | 10
25022 | Vantage VA15 | 2026-01-21 | Ricardo Banegas | Today we experienced several delays. Two of the machines were not operational for the remainder of the day, resulting in a significant loss of time due to repair efforts. Material was also unloaded. | Subcontractor | Thomas Mooers | Yes | Today’s delays were due to machines being out of service for almost the entire remainder of the day. | Yes | Painted screws | 18 | 10 | 10 | Yes | Six pallets of insulation and two pallets of metal were unloaded. | Boom Lift Baker Scaffold | No |  |  | Yes | East | Flashing | [32 empty] | 30ft | 4
25036 | TCAT Chattanooga | 2026-01-21 | Obed bermudez | We fabricated 3 panels, fabricated and installed closure angles for south elevation columns, then cleaned up all the trash and moved all the material left to the parking lot. Continued caulking and installing flashing. | Subcontractor | Josh McPherson | Yes | Yes misssing material. | Yes | Panel 203-1D02 that was damaged by others, 16 musket gray pac clad that measure 8 feet long. 13’ plus long pac clad anodized clear for south soffit, brake metal for south soffit, 407 flashing on south elevation where pac clad meets entrance, 202-1c12A Corner Acm panel that came damaged from shop. | Clear | 6 | 12 | No |  | Boom lifts and equipment | No |  |  | Yes | North and south | Caulking Flashing | [20 empty] | 210 | 36 | [10 empty] | 160 | 36
25040 | Moses Lincoln Vitrine | 2026-01-21 | Abner aguilar | No | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | No |  | Caulking Coping | [20 empty] | Yes | 44 | [18 empty] | South elevation | 44
24039 | The Visionary | 2026-01-20 | Wilton Lorenzo | Two crews installed panels on the east and south sides of the atrium. One crew installed panels on the north side, and another crew installed panels on the east side of the 4th floor. We received a delivery of flashing and coping however, the galvanized coping piece came too large, so it had to be cut and re bent. Two workers worked on that. 7 pieces 5 hours | Subcontractor | Carlos Silva | No |  | Yes | South panels, hat channel | Sunny | 16 | 10 | Yes | Panels, coping or east | 5 boom lift, 2 scissor lift | No |  |  | Yes | Atrium, north elevation | ACM Flashing Insulation Subgirt Zee | 24 panels | 8 | [24 empty] | 426ft | 4 |  |  | 140ft | 4 | 80ft | 4
24046 | UAB Biomedical Research and Psycholgy | 2026-01-20 | Naza Padron | North Canopy 62 flat staping 620' 24 hours | Subcontractor | Wylie McDougall | Yes | McDougall was supposed to use two boom lifts; McDougall was unable to use the second lift the crew was doing clean up on the min time | No |  | sunny | 7 | 70 | No |  | N/A | No |  |  | No |  | ACM Trim | 31 | 38 | [34 empty] | 90 | 8
24072 | LCK064 | 2026-01-20 | Mauricio Chavez | Installed J-trim and panels. (We cannot take photo or video of the job site) | Subcontractor | Joe Hoyle | No |  | No |  | Windy | 6 | 12 | Yes | Equipment | Yes | No |  |  | Yes | E3 | Perforated Grage Panels Trim |  |  |  |  | 15 | [31 empty] | 30
24077 | IAD 667 TI | 2026-01-20 | Fredy veliz | We started cutting and installing Chanel's at elevation sc2 sention 1,1 and 3 ,cooper guys fixed the tubes on the south elevation,we have other issues with bar grating on the south me and Chris will Walk the job Tomorrow to propose a solution | Subcontractor | Chris Buttrey | Yes | Steel issues horizontal tubes installed upside down | No |  | Cold | 7 | 70 | No |  | 65 straight boom lift ,135 straight boom lift ,150 articulate boom lift ,10 k load | No |  |  | Yes | Elevation sc6 | Louvre | [24 empty] | Installed 43 Chanel's | 70
25002 | Med Center Health | 2026-01-20 | Marvin Blanco | Working in the south west elevation with the soffit panels and also with the face panels today we don't have any issues the only problem is the light we have to leave that panel out for the electric guys can fix his lights | Subcontractor | Carlos Silva | No |  | No |  | Cold | 5 | 10 | No |  | Boomlift | No |  |  | No |  | ACM | 18 | 50
25002 | Med Center Health | 2026-01-20 | Kevin Morris | Installed acm on west elevation lower facia and soffit, installed 40 ft zee, and cleaned up work areas. Also need to fab panels to fill in left side of facial and soffit | Subcontractor | Carlos Silva | No |  | No |  | Cold | 6 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM Subgirt Zee | 20 | 10 | [28 empty] | 40 | 1
25022 | Vantage VA15 | 2026-01-20 | Ricardo Banegas | All panels have been cut and modified according to the dimensions shown on the drawings. | Subcontractor | Thomas Mooers | Yes | We do not have a fixed work area, and two of the machines broke down today. | Yes | Painted screws | 17 | 10 | 10 | No |  | Boom Lift Baker scaffold | No |  |  | Yes | East | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 8 | 600 | [6 empty] | 33 | 10 | 50 | 10
25036 | TCAT Chattanooga | 2026-01-20 | Obed Bermudez | We fabricated panel 203-1f01, 203-1f10, 202-1c01. Crew continues working on the North elevation/south, installing z-girt, flashing, insulation, rivets, moving material,caulking and cleaning up. | Subcontractor | Josh McPherson | No |  | Yes | Panel 203-1D02 that was damaged by others, 16 musket gray pac clad that measure 8 feet long. 13’ plus long pac clad anodized clear for south soffit, brake metal for south soffit, 407 flashing on south elevation where pac clad meets entrance, 202-1c12A Corner Acm panel that came damaged from shop. | Clear | 6 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | North and south | ACM Caulking Flashing | 5 | 30 | [18 empty] | 120 | 25 | [10 empty] | 50 | 5
25040 | Moses Lincoln Vitrine | 2026-01-20 | Abner aguilar | No | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | No |  | ACM Caulking Coping Trim | 17 | 44 | [18 empty] | Yes | 22 | [14 empty] | East elevation | 22 |  |  | East Elevation | 22
24039 | The Visionary | 2026-01-19 | Wilton lorenzo | Two crews installed panels on the south and north sides of the atrium. One crew installed panels on the east side of the 4th floor, and another crew installed panels on the north side. Two workers lifted panels to the 4th floor, and the rest of the crew helped locate and prepare panels. The atrium panel installation has been progressing at a slower pace, possibly due to the scissor lift taking more time when operating at higher elevations with heavier loads. | Subcontractor | Carlos Silva | Yes | No flashing, no hat channel | Yes | South panels, flashing color anthracite, hat channel for RGB light | Cloudy | 16 | 10 | No |  | 5 boom lift, 1 scissor lift | No |  |  | Yes | Atrium, north elevation | ACM Flashing Insulation Subgirt Zee | 21 panels | 6 | [24 empty] | 100ft | 4 |  |  | 50ft | 2 | 30ft | 2
24046 | UAB Biomedical Research and Psycholgy | 2026-01-19 | NazaPadron | 340' flat straping 26 hours | Subcontractor | Wylie McDougall | No |  | No |  | cloudy | 5 | 50 | No |  | N/A | No |  |  | No |  | ACM | 18 | 24
24072 | LCK064 | 2026-01-19 | Mauricio Chavez | Mobilized to job site, took field dimensions, moved material, and began installing J-trim (note: we cannot take pictures onsite) | Subcontractor | Joe Hoyle | No |  | No |  | Windy | 6 | Only 6 hrs today due to the mobilization | No |  | Not yet, we’re supposed to receive it tomorrow | No |  |  | Yes | E1 | Trim | [36 empty] | 25
24077 | IAD 667 TI | 2026-01-19 | Fredy veliz | We continue having issues with the steel ,some of the horizontal tube were installed upside down ,me and cooper steel foreman had conversation and they agree to fix the ones not involve crane work but there is couple of those the gonna be pending until we get a solution ,we had to removed part of the clips the we had installed already because of that issue loosing have of the day | Subcontractor | Chris Buttrey | Yes | Steel tubes issues ,some of the steel was installed incorrect | No |  | Cold | 7 | 70 | No |  | 1 straight 65 boom lifts,1 articulate 150 boom ,10 k load | No |  |  | Yes | Elevations sc2 sections. 12 to 20 | Louvre | [24 empty] | Installing clips on elevation sc2 south section 12 to 20. Installing screw on clips elevation sc3 section 3 , installed chanes elevation sc2 south 1 2 3 and 4 | 70
25002 | Med Center Health | 2026-01-19 | Marvin Blanco | Working in the west elevation taking layout for the panels in the soffit and solo taking paper out of the panels in the north elevation cleaning our areas of work | Subcontractor | Carlos Silva | No |  | No |  | Cold | 5 | 10 | No |  | Boomlift | No |  |  | No |  | ACM | 4 | 50
25002 | Med Center Health | 2026-01-19 | Kevin Morris | Installed lower soffit panels on north and peeled still missing one light fixture to finish, started facial and soffit panels on lower level west elevation | Subcontractor | Carlos Silva | Yes | Missing light fixture on north soffit | No |  | Cold | 5 | 10 | No |  | 3 boom lifts | No |  |  | Yes | West lower level facial and soffit | ACM | 9 | 10
25022 | Vantage VA15 | 2026-01-19 | Ricardo Banegas | Each of the panels has been modified and cut according to the dimensions shown in the plans. | Subcontractor | Thomas Mooers | Yes | We do not have an available area to work. There are many delays, a lot of machinery, and we have to wait for the other crews working ahead of us. | Yes | We need painted screws and bottom flashing. | 19 | 10 | 10 | No |  | Boom Lift Baker sccaffold | No |  |  | Yes | East | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 26 | 80 | [6 empty] | 120 ft | 5 | 130ft | 5
25036 | TCAT Chattanooga | 2026-01-19 | Obed Bermudez | Crew continues working on the North elevation/south, installing z-girt, flashing, insulation, rivets, moving material,caulking and cleaning up | Subcontractor | Josh McPherson | No |  | Yes | Panel 203-1D02 that was damaged by others, 2 boxes of anodized aluminum caulking, 1 roll of 7/8 backer rod (350 ft), we need 304 corner flashing (wood grain) for the northwest corner, 16 musket gray pac clad that measure 8 feet long. 13’ plus long pac clad anodized clear for south soffit, brake metal for south soffit, 407 flashing on south elevation where pac clad meets entrance, 202-1c12A Corner Acm panel that came damaged from shop. | Clear | 6 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | North | Caulking Flashing Insulation Subgirt Zee | [20 empty] | 6 | 5 |  |  |  |  | 150 | 15 |  |  | 130 | 20 | 120 | 20
25040 | Moses Lincoln Vitrine | 2026-01-19 | Abner | South | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | No |  | ACM | 12 | 44
25036 | TCAT Chattanooga | 2026-01-18 | Obed Bermudez | Crew continues working on the North elevation/south, installing z-girt, flashing, ACM/Flushpanels, moving material,caulking and cleaning up | Subcontractor | Josh McPherson | No |  | Yes | 2 boxes of anodized aluminum caulking, 1 roll of 7/8 backer rod (350 ft), we need 304 corner flashing (wood grain) for the northwest corner, 16 musket gray pac clad that measure 8 feet long. 13’ plus long pac clad anodized clear for south soffit, brake metal for south soffit, 407 flashing on south elevation where pac clad meets entrance, 202-1c12A Corner Acm panel that came damaged from shop. | Clear | 4 | 5 | No |  | Boom lifts and forklift | No |  |  | Yes | North | Single Skin Subgirt Zee | [6 empty] | 12 | 15 | [22 empty] | 35 | 5
25040 | Moses Lincoln Vitrine | 2026-01-18 | Abner aguilar | No | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 32 | No |  | Boom lift | No |  |  | Yes | South elevation | ACM | 6 | 32
24039 | The Visionary | 2026-01-17 | Wilton lorenzo | Two crews installed panels on the north and south sides of the atrium. Another crew installed panels on the 4th floor, east side, and another crew installed panels on the north side. We received a delivery of panels, but it is necessary for flashing to be sent first because we cannot install panels without flashing. we unloaded the material and then moved it inside the parking garage. I assigned two people to perform cleanup. | Subcontractor | Carlos Silva | Yes | We need flashing, hat channel, and coping | Yes | Coping,hat channel, coping for east elevation | Sunny | 16 | 8 | Yes | Panels for north elevation | 5 boom lift, 4 scissor lift | No |  |  | Yes | North elevation, atrium | ACM Insulation Subgirt Zee | 22 panels | 8 | [24 empty] | 192ft | 4 |  |  | 100ft | 2
24046 | UAB Biomedical Research and Psycholgy | 2026-01-17 | NazaPadron | N/A | Subcontractor | Wylie McDougall | No |  | No |  | cloudy | 6 | 30 | No |  | N/A | No |  |  | No |  | ACM Subgirt Zee | 18 | 24 | [28 empty] | 40 | 6
25036 | TCAT Chattanooga | 2026-01-17 | Obed Bermudez | Crew continues working on the North elevation/south, installing z-girt, flashing, ACM/Flushpanels, moving material,caulking and cleaning up. | Subcontractor | Josh McPherson | No |  | Yes | 2 boxes of anodized aluminum caulking, 1 roll of 7/8 backer rod (350 ft), we need 304 corner flashing (wood grain) for the northwest corner, 16 musket gray pac clad that measure 8 feet long. 13’ plus long pac clad anodized clear for south soffit, brake metal for south soffit, 407 flashing on south elevation where pac clad meets entrance, 202-1c12A Corner Acm panel that came damaged from shop. | Clear | 6 | 8 | No |  | Boom lift and forklift | No |  |  | Yes | North | Caulking Flashing Single Skin | [6 empty] | 12 | 30 | [12 empty] | 45 | 3 | [10 empty] | 160 | 15
25040 | Moses Lincoln Vitrine | 2026-01-17 | Abner aguilar | No | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 10 | No |  | Boom lift | No |  |  | No |  | ACM | 12 | 40
24039 | The Visionary | 2026-01-16 | Wilton Lorenzo | Two crews installed panels on the south and north walls of the atrium. Today we received a delivery for the 4th floor of the east patio. Two crews installed panels in the area where the panels were delivered. Tomorrow we will receive panels for the north elevation, and one person installed insulation on the south side. | Subcontractor | Carlos Silva | No |  | Yes | Flashing, hat channel, panels for south | Sunny | 16 | 10 | Yes | Panels for lvl 4 | 5 boom lift, 2 scissor lift, 1 lull | No |  |  | Yes | North and south wall of the atrium | ACM Flashing Insulation Subgirt Zee | 28 panels | 6 | [24 empty] | 768ft | 4 |  |  | 30 ft | 2 | 120ft | 4
24046 | UAB Biomedical Research and Psycholgy | 2026-01-16 | NazaPadron | N/A | Subcontractor | Wylie McDougall | No |  | No |  | sunny | 6 | 60 | No |  | N/A | No |  |  | No |  | ACM Flashing Insulation Subgirt Zee Trim | 18 | 24 | [24 empty] | 64 | 6 |  |  | 80 | 14 | 30 | 6 |  |  | 60 | 10
24065 | QTS NAL2 DC2 | 2026-01-16 | Chad McCoy | Louvers were continued. 16 brackets. 14 cross members. 80 fins. 8 verticals | Subcontractor | Joe Hoyle | No |  | Yes | Replacement panels | Cloudy and snowing 12 | 6 | 7 | No |  | 85 foot boom. 65 foot boom. | No |  |  | Yes | Layout continues as you install louvers. | Louvre | [24 empty] | 80 | 7
24077 | IAD 667 TI | 2026-01-16 | Fredy veliz | We having many issues with the steel causing us delays ,also we have issues with Channels many of those made backwards and some of then are missing ,there is a lot materials on the way we spending a lot time cleaning the areas because other trades has stuff all over the place unorganized | Subcontractor | Chris Buttrey | Yes | Chanels and steels issues | No |  | Cold | 7 | 28 | No |  | 2 65 straight boom lifts ,150 articulate boom ,10k load | No |  |  | Yes | Elevation sc3 ,section 3 | Louvre | [24 empty] | Clips on elev sc3 section organizing Chanel's and screws | 28
25002 | Med Center Health | 2026-01-16 | Marvin Blanco | Working in the soffit panels and also modifications all the panels around the light | Subcontractor | Carlos Silva | Yes | Silicone | Yes | Silicone | Cold | 7 | 10 | No |  | Boomlift | No |  |  | No |  | ACM | 10 | 70
25002 | Med Center Health | 2026-01-16 | Kevin Morris | Installed panels on north lower soffit, installed insulation on south stair tower, installed flashing on west above windows | Subcontractor | Carlos Silva | No |  | No |  | Cold | 8 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM Flashing Insulation | 15 | 10 | [24 empty] | 500 | 6 |  |  |  |  | 50 | 4
25022 | Vantage VA15 | 2026-01-16 | Ricardo Banegas | Each one of the panels has been cut to the dimensions required by the plans. | Subcontractor | Thomas Mooers | Yes | The delay is because we don’t have a fixed and continuous area to work in. There is a lot of machinery parked in different zones, and there are also areas where we can’t work because other people are already working there. This limits us and slows down our progress. | Yes | Painting screws | 21 | 8 | 10 | No |  | Boom lift and baker scaffold | No |  |  | Yes | West east and south | Corrugated / Screen wall Flashing Subgirt Zee Trim | [22 empty] | 26 | 80 hours | [6 empty] | 140 ft |  | 160 ft |  |  |  | 40 ft
25036 | TCAT Chattanooga | 2026-01-16 | Obed Bermudez | Crew continues working on the North elevation/south, installing z-girt, flashing, ACM/Flushpanels, moving material,caulking and cleaning up. | Subcontractor | Josh McPherson | No |  | Yes | 2 boxes of anodized aluminum caulking, 1 roll of 7/8 backer rod (350 ft), we need 304 corner flashing (wood grain) for the northwest corner, 16 musket gray pac clad that measure 8 feet long. 13’ plus long pac clad anodized clear for south soffit, brake metal for south soffit, 407 flashing on south elevation where pac clad meets entrance, 202-1c12A Corner Acm panel that came damaged from shop. | Clear | 8 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | North | Caulking Flashing Single Skin | [6 empty] | 56 | 50 | [12 empty] | 55 | 10 | [10 empty] | 160 | 20
25040 | Moses Lincoln Vitrine | 2026-01-16 | Abner aguilar | No | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | No |  | ACM | 21 | 44
24039 | The Visionary | 2026-01-15 | Wilton Lorenzo | Three crews installed panels in the atrium. One crew started installing flashing on the 4th floor on the side where the panels are being delivered. One crew installed Z-girts and insulation on the south elevation. Another crew installed insulation in the north stair tower. We need to figure out how we will get the scissor lift and the panels up to the 4th floor. | Subcontractor | Carlos Silva | No |  | Yes | Flashing color anthracite and ocean metallic for south, north and atrium, hat channel for RGB light, starter track, coping for east elevation | Sunny | 16 | 10 | No |  | 5 Boom Lift, 3 Scissor Lift, 1 Lull | No |  |  | Yes | Atrium, north, south | ACM Flashing Insulation Subgirt Zee | 26 panels | 6 | [24 empty] | 1,440ft | 6 |  |  | 50ft | 2 | 210 ft | 6
24046 | UAB Biomedical Research and Psycholgy | 2026-01-15 | NazaPadron | 8 of the 15 panels installed were cut or routed 12 hours spent, 10 panels removed due to framing work... 12 hours | Subcontractor | Wylie McDougall | No |  | No |  | sunny | 6 | 60 | No |  | N/A | No |  |  | No |  | ACM Insulation Subgirt Zee Trim | 15 | 18 | [24 empty] | 128 |  |  |  | 40 | 10 |  |  |  |  | 40 | 8
24065 | QTS NAL2 DC2 | 2026-01-15 | Chad McCoy | Louvers were continued off of the scaffolding. 26 verticals. 52 brackets and 20 fins. Were installed. We did not continue with fins bc of wind gust of 40 plus | Subcontractor | Joe Hoyle | Yes | Wind gust 40 plus made it unsafe to install 19’ 10” fine | Yes | Replacement panels | 10 degrees and strong winds. | 6 | 7 | No |  | 85 foot boom. 65 foot boom. 35 foot electric | No |  |  | Yes | Layout is continuous bc of bracket play out | Louvre | [24 empty] | 20 | 7
24077 | IAD 667 TI | 2026-01-15 | Fredy veliz | Me and Chris had a conversation today about need plan to continue working,we will swap one of the 65 boom lift for a 135 to start workin on the east elevation and work from east to west ,we been organizing channels for couple of days and we found issues with some of the channels ,the clips on the channels are backwards | Subcontractor | Chris Buttrey | Yes | Cannels size issues no answer yet | No |  | Cold | 7 | 63 | No |  | 2 65 boom lifts ,150 articulate ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing screws on clips elev sc3 section 1 and 2 | 63
25002 | Med Center Health | 2026-01-15 | Kevin Morris | Installed 17 acm panels and modified 6 around lights on north soffit, installed 500 LF of strong girt and 480 SQ ft of insulation on south stair tower, roof parapet not framed | Subcontractor | Carlos Silva | No |  | No |  | 28° | 8 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM Insulation Subgirt Zee | 17 | 10 | [24 empty] | 480 | 4 |  |  | 500 | 6
25022 | Vantage VA15 | 2026-01-15 | Ricardo Banegas | Each one of the panels has been cut to the dimensions required by the plans. | Subcontractor | Thomas Mooers | Yes | The delay is because we don’t have a fixed and continuous area to work in. There is a lot of machinery parked in different zones, and there are also areas where we can’t work because other people are already working there. This limits us and slows down our progress. | Yes | Painting screws | 28 | 8 | 10 | Yes | Caulking | Boom lift, baker scaffold | No |  |  | Yes | East,west and south elevation | Corrugated / Screen wall | [22 empty] | 22 | 80
25036 | TCAT Chattanooga | 2026-01-15 | Obed Bermudez | Crew continues working on the North elevation/south, installing z-girt, flashing, ACM/Flushpanels, moving material,caulking and cleaning up | Subcontractor | Josh McPherson | No |  | Yes | 16 musket gray pac clad that measure 8 feet long. 12’ plus long pac clad anodized clear for south soffit, brake metal for south soffit. 202-1c12A Corner Acm panel that came damaged from shop. | Clear | 8 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | North and south | Caulking Flashing Single Skin Subgirt Zee | [6 empty] | 49 | 50 | [12 empty] | 50 | 10 | [8 empty] | 170 | 15 | 50 | 5
25040 | Moses Lincoln Vitrine | 2026-01-15 | Abner aguilar | No | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | No |  | ACM | 6 | 44
24039 | The Visionary | 2026-01-14 | Wilton Lorenzo | Three crews installed ACM panels, flashing, insulation, and Z girts in the atrium. One crew (three people) installed insulation on the south side, and another crew started installing the coping panels on the north wall of the atrium. We need the flashing under those panels, detail number 92/521. Three people helped locate and install clips on the panels. | Subcontractor | Carlos Silva | No |  | Yes | Starter track, flashing color anthracite for south and for BACK PARAPET NORTH ELEVATION, flashing for the windows on the atrium | Sunny | 15 | 10 | No |  | 5 boom lift, 2 scissor lift, 1 lull | No |  |  | Yes | Atrium, south | ACM Flashing Insulation Subgirt Zee | 30 panels | 80 | [24 empty] | 928ft | 40 |  |  | 160 ft | 60 | 30 | 20
24065 | QTS NAL2 DC2 | 2026-01-14 | Chad McCoy | We installed the last section of corrugated on the expansion joint. This has to be done off a 30 foot plank going across ac units bc there is no other way to reach this area. | Subcontractor | Joe Hoyle | No |  | Yes | Remake panels | Cloudy and 38 | 6 | 6.5 | No |  | 85 foot boom. 65 foot boom. 35 foot electric boom | No |  |  | Yes | Expansion joint area had to have a 4 inch void | Coping Corrugated / Screen wall Hat Channel | [22 empty] | 9 | 3 | [10 empty] | 100 | 1.5 |  |  |  |  | 45 | 1.5
24077 | IAD 667 TI | 2026-01-14 | Fredy veliz | We are organizing materials but we are running out work ,we only have work on the articulate boom for 2 guys ,we need get updated on the channel modify | Subcontractor | Chris Buttrey | Yes | Waiting on channel modify approval | No |  | Cold | 7 | 10 | No |  | 2 65 straight boom lifts ,150 articulate boom ,10k load | No |  |  | Yes | Chanel lay out sc4 ,sc3 ,and sc5 | Louvre | [24 empty] | Installed 14 Chanel's ,organizing Chanel's per sizes | 70
25002 | Med Center Health | 2026-01-14 | Marvin Blanco | Working in the soffit panels and also modifications in the light making work the panels | Subcontractor | Carlos Silva | No |  | No |  | Cold | 7 | 10 | No |  | Boomlift | No |  |  | No |  | ACM | 13 | 70
25002 | Med Center Health | 2026-01-14 | Kevin Morris | Installed 15 panels and fabed 3 panels for lights on first level north soffit. Installed zees and insulation on 1st level west side. Installed zees on south stair tower east side. | Subcontractor | Carlos Silva | No |  | No |  | Rain/ cold | 7 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM Insulation Subgirt Zee | 15 | 10 | [24 empty] | 100 | 2 |  |  | 500 | 8
25040 | Moses Lincoln Vitrine | 2026-01-14 | Abner aguilar | Layout | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | Yes | South elevation | ACM Soffit | 10 | 44
24039 | The Visionary | 2026-01-13 | Wilton Lorenzo | Three crews installed panels, flashing, and insulation in the atrium. One crew installed Z girts on the south side, and another crew installed insulation. We received a delivery today for the last atrium wall. | Subcontractor | Carlos Silva | No |  | Yes | Anthracite flashing, panels for south and north | Sunny | 16 | 10 | Yes | Panels for east atrium wall | 5 boom lift, 3 sicssor lift, 1 lull | No |  |  | Yes | Atrium | ACM Flashing Insulation Subgirt Zee | 16 panels | 6 | [24 empty] | 704FT | 6 |  |  | 300FT | 4 | 50FT | 2
24046 | UAB Biomedical Research and Psycholgy | 2026-01-13 | naza padron | roof west wing three panels were fab... Southeast corner elevation: two panels were installed, west side grown level 1 panel fab and instaled. | Subcontractor | Wylie McDougall | Yes | south east corner swingstage It needed modifications, we couldn't continue, it wasn't safe | No |  | sunny | 6 | 60 | No |  | N/A | No |  |  | No |  | ACM Flashing Subgirt Zee | 22 | 44 | [28 empty] | 120 | 10 | 30 | 6
24068 | QTS NAL1 DC2 | 2026-01-13 | Chad McCoy | Scaffolding was moved and set up and new plywood there is missing pieces on my scaffolding bc people have been taken pieces and it is not considered safe so we have to shut down to get the new pieces. | Subcontractor | Joe Hoyle | Yes | Missing scaffolding pieces | Yes | Replacement panels | Cloudy and windy | 6 | 4 | No |  | 85 foot boom 65 foot boom and electric 35 foot boom | No |  |  | No |  | ACM | 0 | 0
24077 | IAD 667 TI | 2026-01-13 | Fredy vleiz | Still waiting on channels modify approval,we need get updated and and get more room to layout more areas | Subcontractor | Chris Buttrey | Yes | Waiting on Chanel's modify approvals ,other trades materials on the way | No |  | Good | 7 | 63 | No |  | 2 65 straight boom lifts ,150 articulate boom ,10k load | No |  |  | Yes | Channels layout sc4 | Louvre | [24 empty] | Installed 5 Chanel's for vertical layout sc4 ,screw clips ,prep bolts ,open crates | 63
25002 | Med Center Health | 2026-01-13 | Kevin Morris | Installed 16 soffit panels on north skipping panels for lights to be relocated again, talked to Paul with Kelly about cracks in water proofing on south stair tower, I left at 3 pm to pickup 19 pieces of 3/4 angle, 7/8 backer rod, blue tape and rags from shop | Subcontractor | Carlos Silva | No |  | No |  | Cold | 6 | 10 | Yes | FL09 drip flashing | 3 boom lifts | No |  |  | Yes | North soffit | ACM | 16 | 10
25036 | TCAT Chattanooga | 2026-01-13 | Obed Bermudez | We fabricated panel 207-2k02 due to scratch panel. Crew continues working on the North elevation/south, installing z-girt, flashing, ACM/Flushpanels, moving material,caulking and cleaning up. | Subcontractor | Josh McPherson | No |  | Yes | 10' plus long wood grain plac clad panels on North elevation, (Woodgrain) colored rivets, 16 musket gray pac clad that measure 8 feet. 12’ plus long pac clad anodized clear for south soffit, brake metal for south soffit, closure angle. 202-1c12A Corner Acm panel that came damaged. | Clear | 8 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | North south | ACM Caulking Flashing Insulation Single Skin Subgirt Zee | 10 | 20 |  |  |  |  | 13 | 20 | [12 empty] | 27 | 10 |  |  |  |  | 32 | 5 |  |  | 160 | 20 | 28 | 5
25036 | TCAT Chattanooga | 2026-01-13 | Obed Bermudez | Crew continues working on the North elevation/south, installing z-girt, flashing, ACM/Flushpanels, moving material,caulking and cleaning up. | Subcontractor | Josh McPherson | No |  | Yes | 16 musket gray pac clad that measure 8 feet long. 12’ plus long pac clad anodized clear for south soffit, brake metal for south soffit. 202-1c12A Corner Acm panel that came damaged from shop. | Clear | 8 | 10 | Yes | We received 40 pac clad panels 20 feet long, rivets, 1 box of anodized aluminum, Acm sheet. | Forklift and boom lifts. | No |  |  | Yes | North | ACM Flashing Insulation Single Skin Subgirt Zee | 6 | 13 |  |  |  |  | 30 | 40 | [18 empty] | 40 | 5 |  |  | 180 | 20 | 6 | 2
25040 | Moses Lincoln Vitrine | 2026-01-13 | Abner aguilar | 2 crated delivered | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | Yes | Screws and acm panels | Boom lift | No |  |  | No |  | ACM | 8 | 44
24018 | QTS-NAL1-DC1 | 2026-01-12 | Marvin Blanco | Finishing all the louvers blades and leaving everything clean up the work is done | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 4 | 12 | No |  | Boomlift | No |  |  | No |  | Louvre | [24 empty] | 20 | 48
24039 | The Visionary | 2026-01-12 | Wilton Lorenzo | Three crews installed flashing and flashing in the atrium. One crew caulked the Z girts on the north side, and another installed flashing on the south side. | Subcontractor | Carlos Silva | No |  | Yes | Tek 5, panels, flashing, L trim | Sunny | 16 | 10 | No |  | 5 boom lift, 2 sicssor lift, 1 lull | No |  |  | Yes | Atrium, south | ACM Flashing Insulation Subgirt Zee | 16 | 4 | [24 empty] | 256FT | 4 |  |  | 130FT | 4 | 210FT | 4
24046 | UAB Biomedical Research and Psycholgy | 2026-01-12 | naza padron | Connector over the bridge 8 panels they were cut and routed 13 instaled 30 hours | Subcontractor | Wylie McDougall | No |  | No |  | sunny | 6 | 60 | Yes | Zee's and ACM Creates | N/A | No |  |  | No |  | ACM Insulation Trim | 12 | 14 | [24 empty] | 320 | 8 | [8 empty] | 30 | 8
24068 | QTS NAL1 DC2 | 2026-01-12 | Chad McCoy | We finished the expansion section of the corrugated today. We also got all louver material to the roof. | Subcontractor | Joe Hoyle | No |  | Yes | All remake panels | Cloudy 34 | 6 | 8 | No |  | 85 foot boom. 65 foot boom. 35 foot electric boom | No |  |  | No |  | Coping Corrugated / Screen wall Trim | [22 empty] | 9 | 2 | [12 empty] | 25 | 0.5 |  |  | 25 | 0.5
24068 | QTS NAL1 DC2 | 2026-01-12 | Marvin Blanco | Waiting for tubes support for finish the job we didn't have enough to finish | Subcontractor | Joe Hoyle | Yes | Tubes support | Yes | Tubes support for the louvers blades | Cold | 4 | 12 | No |  | Boomlift | No |  |  | No |  | Louvre | [24 empty] | 20 | 48
24077 | IAD 667 TI | 2026-01-12 | Fredy veliz | We are running out of work in the areas where we are and is a lot Materials in the other areas ,we need updates about Chanel's modify to continue sc2 elevation ,on sc1 section we had to cut the blades to line up the joint with elevation sc5 on the top ,i did a lay out on the south elevation sc2 and the structure is 2-1/2" bigger so we have to ,make all the joints little bigger to fix that issue | Subcontractor | Chris Buttrey | Yes | Waiting on approval to cut Chanel's for sc2 ,other trades materials on the way and equipment | No |  | Good | 8 | 64 | No |  | 2 65 straight boom lifts ,150 articulate boom ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing miscellaneous screws o clips elev sc3 section 1 and 2 ,installing braces and at blades elevation sc1 section 11 and 12 , | 64
25002 | Med Center Health | 2026-01-12 | Marvin Blanco | Installing the panels in the eyebrow in the south west elevation and also starting Installing the soffit panels but there is a issues with the light the electric guys need to much their light because they're not in the center of the panels | Subcontractor | Carlos Silva | Yes | Flashing and silicone | Yes | Flashing and silicone | Cold | 6 | 10 | No |  | Boomlift | No |  |  | No |  | ACM | 11 | 60
25002 | Med Center Health | 2026-01-12 | Kevin Morris | Installed 14 acm panels on west eyebrow, moved to North soffit level 1 installed 2 acm panels, lights still not in correct location Paul asked if Marvin could install panels in-between lights to give electricians reference points to install light in center correctly and he agreed. Flashing needed for above window and below eye row scheduled for delivery tomorrow | Subcontractor | Carlos Silva | No |  | Yes | Flashing showing up tomorrow | Cold | 7 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM | 16 | 10
25036 | TCAT Chattanooga | 2026-01-12 | Obed Bermudez | Crew continuesworking on the North elevation/south, installing z-girt, flashing, ACM/Flushpanels, moving material,caulking and cleaning up | Subcontractor | Josh McPherson | No |  | Yes | 10' plus long wood grain plac clad panels on North elevation, (Woodgrain) colored rivets, 16 musket gray pac clad that measure 8 feet. 12’ plus long pac clad anodized clear for south soffit, brake metal for south soffit, closure angle. 202-1c12A Corner Acm panel that came damaged. | Clear | 8 | 10 | No |  | Boom lift and forklift. | No |  |  | Yes | North | ACM Flashing Insulation Single Skin Subgirt Zee | 5 | 30 |  |  |  |  | 1 | T | [18 empty] | 102 | 20 |  |  | 100 | 20 | 13 | 5
25040 | Moses Lincoln Vitrine | 2026-01-12 | Abner aguilar | No | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | No |  | ACM | 20 | 44
25036 | TCAT Chattanooga | 2026-01-11 | Obed Bermudez | We fabricated panel 207-2X01 due to it being scratched. Crew continuesworking on the North elevation/south, installing z-girt, flashing, ACM/Flushpanels, moving material,caulking and cleaning up | Subcontractor | Josh McPherson | No |  | Yes | 10' plus long wood grain plac clad panels on North elevation, (Woodgrain) colored rivets, 16 musket gray pac clad that measure 8 feet. 12’ plus long pac clad anodized clear for south soffit, brake metal for south soffit, closure angle. 202-1c12A Corner Acm panel that came damaged. | Clear | 8 | 8 | No |  | Boom lifts and forklift | No |  |  | Yes | North | ACM Flashing Single Skin Subgirt Zee | 1 | 4 |  |  |  |  | 36 | 50 | [22 empty] | 25 | 2 | 35 | 8
25040 | Moses Lincoln Vitrine | 2026-01-11 | Abner aguilar | Fabricate panels | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 40 | No |  | Boom lift | No |  |  | No |  | ACM | 8 | 40
24039 | The Visionary | 2026-01-10 | Wilton lorenzo | Three crews installed ACM panels on the south and north sides of the atrium. One crew caulked the Z girts on the north side, and another crew installed flashing on the south. After lunch, those same four guys cleaned up, broke down, and threw away all our trash. Four guys were looking for panels and installing clips. | Subcontractor | Carlos Silva | No |  | Yes | Tek 5 and panels | Sunny | 16 | 8 | No |  | 5 boom lift, 2 sicssor lift, 1 lull | No |  |  | Yes | Atrium | ACM Flashing Insulation Subgirt Zee | 14 | 6 | [24 empty] | 224 FT | 6 |  |  | 250FT | 6 | 40FT | 2
25002 | Med Center Health | 2026-01-10 | Kevin Morris | Installed 12 acm panels, and zees on back of roof, raining all day | Subcontractor | Carlos Silva | No |  | No |  | Rain | 6 | 8 | No |  | 3 boom lifts | No |  |  | No |  | ACM Subgirt Zee | 12 | 10 | [28 empty] | 70 | 10
25036 | TCAT Chattanooga | 2026-01-10 | Obed Bermudez | No work due to inclement weather | Subcontractor | Josh McPherson | Yes | No work due to inclement weather | Yes | 10' plus long wood grain plac clad panels on North elevation, (Woodgrain) colored rivets, 16 musket gray pac clad that measure 8 feet. 12’ plus long pac clad anodized clear for south soffit, brake metal for south soffit, closure angle. 202-1c12A Corner Acm panel that came damaged. | Rainy day | 1 | 0 | No |  |  | No |  |  | Yes | North | Single Skin | [6 empty] | 1
25040 | Moses Lincoln Vitrine | 2026-01-10 | Abner aguilar | No | Subcontractor | Laura Forero | No |  | No |  | Rainy | 4 | No | No |  | Boom lift | No |  |  | No |  | ACM | No | No
24039 | The Visionary | 2026-01-09 | WiltonLorenzo | Three crews installed panels, Z girts, and insulation in the atrium. One crew installed flashing on the south side, and another crew installed Z girts at the Level 4 north patio. Four workers helped locate and install clips on the panels. We need Tek 5 screws because there is steel above the windows on the north side of the atrium. | Subcontractor | Carlos Silva | No |  | Yes | Panels for south elevation and tek 5 | Sunny | 16 | 10 | No |  | 5 boom lift, 2 sicssor lift, 1 lull | No |  |  | Yes | Atrium, south | ACM Flashing Insulation Subgirt Zee | 18 panels | 6 | [24 empty] | 260FT | 4 |  |  | 180 | 4 | 120FT | 4
24046 | UAB Biomedical Research and Psycholgy | 2026-01-09 | naza padron | Connector around the bridge 15 panels they were cut and routed 11 instaled 30 hours | Subcontractor | Wylie McDougall | No |  | No |  | sunny | 6 | 60 | No |  | N/A | No |  |  | No |  | ACM Insulation | 20 | 24 | [24 empty] | 192 | 6
24068 | QTS NAL1 DC2 | 2026-01-09 | Chad McCoy | 16 panels installed. One panel cut out. Everything peeled and we started tripping in and recalling everything. The wing wall is completely done. The freedom wall needs a little caulking and some more reveals | Subcontractor | Joe Hoyle | No |  | No |  | Rain and 38 | 6 | 8 | No |  | Stolen 85 foot boom. 35 foot electric boom and 45 foot electric scissor | No |  |  | No |  | ACM | 16 | 8
24077 | IAD 667 TI | 2026-01-09 | Fredy veliz | Eats elevation steel is completed ,will ask in the monday meeting if we can start on that end ,will need swap one boom lift 65 for a 135 ,on elevation sc2 south the half of the clips are installed | Subcontractor | Chris Buttrey | Yes | Waiting on Chanel modifying approval | No |  | Light rain | 7 | 63 | No |  | 2 65 straight boom lifts ,120 articulated boom ,10k load | No |  |  | Yes | Elevation sc3 | Louvre | [24 empty] | Installing clips elev sc3 sectio 1 and 2 ,building platforms for boom lift ,installed braces and miscellaneous bolts on Chanel's ,and braces elev sc1 section 9,10,11,12 | 63
25002 | Med Center Health | 2026-01-09 | Kevin Morris | Installed 17 acm panels on west eyebrow, installed 100 SQ ft of insulation on south stair tower, set up lifelines on roof, cleaned up empty crates and trash | Subcontractor | Carlos Silva | No |  | No |  | 70 | 6 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM Insulation | 17 | 10 | [24 empty] | 100 | 2
25036 | TCAT Chattanooga | 2026-01-09 | Obed Bermudez | Crew continuesworking on the North elevation/west, installing z-girt, flashing, ACM/Flushpanels, moving material,caulking and cleaning up | Subcontractor | Josh McPherson | Yes | We had to stop work due to inclement weather. | Yes | 10' plus long wood grain plac clad panels on North elevation, (Woodgrain) colored rivets, 16 musket gray pac clad that measure 8 feet. 12’ plus long pac clad anodized clear for south soffit, brake metal for south soffit, closure angle. 202-1c12A Corner Acm panel that came damaged. | Rainy day | 8 | 2.5 | No |  | Boom lift and forklift | No |  |  | Yes | North | ACM Flashing Insulation Single Skin Subgirt Zee | 1 | 4 |  |  |  |  | 1 | 4 | [18 empty] | 10 | 4 |  |  | 10 | 4 | 14 | 4
25040 | Moses Lincoln Vitrine | 2026-01-09 | Abner aguilar | Fabricate panels | Subcontractor | Laura Forero | Yes | Panels missing | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | Yes | North west | ACM | 9 | 44
24039 | The Visionary | 2026-01-08 | Wilton Lorenzo | Three crews installed panels, Z girts, and insulation in the atrium. One crew started installing flashing on the south side so everything will be ready when the panels arrive, and another crew installed Z girts in the LVL 4 north patio. Four workers helped locate and install clips on the panels. Work was stopped for approximately two hours due to rain. | Subcontractor | Carlos Silva | Yes | It rained for 2 hours | Yes | Panels for outside of the building | Cloudy | 16 | 10 | No |  | 5 boom lift, 2 sicssor lift, 1 lull | No |  |  | Yes | Atrium and South | ACM Flashing Insulation Subgirt Zee | 16 panels | 6 | [24 empty] | 224FT | 4 |  |  | 410FT | 6 | 80FT | 4
24046 | UAB Biomedical Research and Psycholgy | 2026-01-08 | Naza Padron | crew #2 was waiting for a boom to continue with instalation of panels at connector around the bridge | Subcontractor | Wylie McDougall | Yes | crew #2 was waiting for a boom to continue with instalation of panels at connector around the bridge | No |  | cloudy | 6 | 60 | Yes | two crates ot ACM and palet of Zee's | N/A | No |  |  | No |  | ACM Insulation Trim | 30 | 34 | [24 empty] | 1024 | 18 | [8 empty] | 60 | 8
24068 | QTS NAL1 DC2 | 2026-01-08 | Chad McCoy | 23 panels installed. 8 on freedom wall. And 15 on wing wall. Nick was there today so we shuffled back and forth to grays job looking at spots in panels. | Subcontractor | Joe Hoyle | No |  | No |  | Clear 52 | 6 | 7.5 | Yes | 2 panels in a sprinter van | Stolen 85 foot boom. 35 foot electric boom. And 45 foot scissor | No |  |  | No |  | ACM | 23 | 7.5
24077 | IAD 667 TI | 2026-01-08 | Fredy veliz | Only 3 man on site we waiting on approval for Chanel's modify at sc2 elevation ,boom is working but need services has warnings popping up every is going up | Subcontractor | Chris Buttrey | Yes | Waiting on approvals for Chanel's modify ,other trades materias on site are on the way | No |  | Good | 3 | 30 | No |  | 2 65 straight boom ,150 articulate boom ,10k load | No |  |  | Yes | Elevation sc3 section 1 and 2 | Louvre | [24 empty] | Layout and installing clips at sc3 section 1 and 2 | 30
25002 | Med Center Health | 2026-01-08 | Kevin Morris | Installed 14 acm panels on west eyebrow panel 22 was made with angel on wrong side , 250 LF of strong girt, and 400 SQ ft on insulation on south stair tower, 95 ft boom lift was switched out for 125 ft boom lift, missing louver opening on penthouse it's in our drawings but the gc doesn't show it in his drawings, | Subcontractor | Carlos Silva | No |  | No |  | 70 | 6 | 10 | Yes | 125 boom lift | 3 boom lifts | No |  |  | No |  | ACM Insulation Subgirt Zee | 14 | 10 | [24 empty] | 400 | 5 |  |  | 250 | 5
25036 | TCAT Chattanooga | 2026-01-08 | Obed Bermudez | Crew continuesworking on the North elevation/west, installing z-girt, flashing, ACM/Flushpanels, moving material,caulking and cleaning up. | Subcontractor | Josh McPherson | No |  | Yes | 10' plus long wood grain plac clad panels on North elevation, (Woodgrain) colored rivets, 16 musket gray pac clad that measure 8 feet. 12’ plus long pac clad anodized clear for south soffit, brake metal for south soffit, closure angle. 202-1c12A Corner Acm panel that came damaged. | Clear | 8 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | North | ACM Caulking Flashing Insulation Single Skin Subgirt Zee | 8 | 20 |  |  |  |  | 42 | 30 | [12 empty] | 60' 2" | 10 |  |  |  |  | 40 | 5 |  |  | 80 | 10 | 35 | 5
24018 | QTS-NAL1-DC1 | 2026-01-07 | Marvin Blanco | Working on installing angles tubes support for the louvers blades | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 4 | 12 | Yes | Screws | Boomlift forklift | No |  |  | No |  | Louvre | [24 empty] | 10 | 48
24039 | The Visionary | 2026-01-07 | Wilton Lorenzo | Three crews installed panels in the atrium. Four guys were looking for panels and putting clips on them. Three people were caulking the Z girts outside the building, and two were installing Z girts on the north side. | Subcontractor | Carlos Silva | No |  | Yes | Exterior panels for the building | Sunny | 16 | 10 | No |  | 5 boom lift, 2 sicssor lift, 1 lull | No |  |  | Yes | North, atrium | ACM Flashing Insulation Subgirt Zee | 15 panels | 6 | [24 empty] | 160FT | 4 |  |  | 410FT | 6 | 20FT | 2
24046 | UAB Biomedical Research and Psycholgy | 2026-01-07 | Naza padron | N/A | Subcontractor | Wylie McDougall | No |  | No |  | sunny | 6 | 60 | No |  | N/A | No |  |  | No |  | ACM Insulation Subgirt Zee Trim | 21 | 26 | [24 empty] | 640 | 12 |  |  | 180 | 12 |  |  |  |  | 140 | 10
24068 | QTS NAL1 DC2 | 2026-01-07 | Marvin Blanco | Working on installing angles tubes support for the louvers blades | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 4 | 12 | Yes | Screws | Boomlift forklift | No |  |  | No |  | Louvre | [24 empty] | 11 | 48
24068 | QTS NAL1 DC2 | 2026-01-07 | Chad McCoy | We are just continuing on removal of bad acm and install on new acm as areas are ready for new install. We went to grays job site and took a mcdougal 85 foot boom and drove it all the way to this job to do work. 25 panels removed. 14 installed | Subcontractor | Joe Hoyle | No |  | No |  | Cloudy 40 | 6 | 7.5 | No |  | Stolen 85 foot boom. 45 foot scissor and 35 foot electric boom | No |  |  | No |  | ACM | 14 | 7.5
24077 | IAD 667 TI | 2026-01-07 | Fredy veliz | We only had the 150 articulate boom working on cs5 full day ,the rest of the guys only couple hours finish prep clips ,we didn't have any other areas to work until we get answers about the Chanel's ,me and Nick walked the job and I explained to him all this details and issues | Subcontractor | Chris Buttrey | Yes | Waiting on modification approval,cranes and materials on the way | No |  | Good | 8 | 50 | No |  | 2 65 straight boom ,150 articulate boom ,10k load | No |  |  | Yes | Sc5 | Louvre | [24 empty] | Installed clips and Chanel's lay out elevation sc5 | 50
25002 | Med Center Health | 2026-01-07 | Marvin Blanco | Today the window guys was on our way to keep moving with our insulation in the west elevation | Subcontractor | Carlos Silva | No |  | Yes | Flashing 30 pics | Good | 5 | 10 | Yes | Pywood, insulation and material for the stone | Boomlift | No |  |  | No |  | ACM | 10 | 50
25002 | Med Center Health | 2026-01-07 | Kevin Morris | Installed 8 ACM panels on west eyebrowglass guys where working underneath the out guys so we had to move locations til lunch, and 1000 SQ ft of insulation on south stair tower, received 4 deliveries plywood insulation moron panels and rails for stone cleaned up area at north stair tower, | Subcontractor | Carlos Silva | Yes | Glass guys where working in area had to move locations till they were done | Yes | Drip flashing for above window under soffit already contacted Carlos | 70 | 6 | 10 | Yes | Insulation, plywood, moran panels, and rails for stone | 3 boom lifts | No |  |  | No |  | ACM Insulation | 8 | 10 | [24 empty] | 1000 | 10
25036 | TCAT Chattanooga | 2026-01-07 | Obed Bermudez | Crew continuesworking on the North elevation/west, installing z-girt, flashing, ACM/Flushpanels, moving material,caulking and cleaning up. | Subcontractor | Josh McPherson | No |  | Yes | 10' plus long wood grain plac clad panels on North elevation, (Woodgrain) colored rivets, 16 musket gray pac clad that measure 8 feet. 12’ plus long pac clad anodized clear for south soffit, brake metal for south soffit, closure angle. 202-1c12A Corner Acm panel that came damaged. | Clear | 8 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | West and North | ACM Flashing Insulation Single Skin Subgirt Zee | 10 | 30 |  |  |  |  | 22 | 40 | [18 empty] | 21 |  |  |  | 60 | 5 | 32 | 5
24018 | QTS-NAL1-DC1 | 2026-01-06 | Marvin Blanco | Working in the screenwall with the louvers blades | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 4 | 12 | No |  | boomlift and forklift | No |  |  | No |  | Louvre | [24 empty] | 15 | 48
24039 | The Visionary | 2026-01-06 | Wilver Quiroz | A team worked installing subgirts zee on the east and west elevation. Three guys worked putting caulking on the subgirt zee on the south and west side that had been pending, three teams worked installing insulation and ACM in the atrium and four guys worked preparing panels and passing material to the installers | Subcontractor | Carlos Silva | No |  | Yes | 3/4 and 1-1/4 screws | Sunny | 16 | 10 | No |  | 5 boom lift, 2 scissor lift and 1 lull | No |  |  | Yes | North and south | ACM Flashing Insulation Subgirt Zee | 20 | 60 | [24 empty] | 256FT | 20 |  |  | 430FT | 30 | 30FT | 20
24065 | QTS NAL2 DC2 | 2026-01-06 | Chad mccoy | 2 panels were cut and routed th finish off the top of the freedom wall install. We now are tripping in reveals and peeling the panels. But the are roller marks in the freedom wall panels. | Subcontractor | Joe Hoyle | No |  | No |  | Misty cloudy | 3 | 6.5 | No |  | 65 foot boom. 85 foot boom. 30 foot electric boom | No |  |  | No |  | ACM | 2 | 2.5
24068 | QTS NAL1 DC2 | 2026-01-06 | Chad McCoy | We removed 3 panels and then cut out 6 more. This is all but one panel that needed to be removed. I talked to Joe Hoyle and there was one more panel that needed to be removed bc of marks. We made it today out of left over red acm. So today we removed 9 panels and brought over 3 crates of material. And we installed 6 new panels. One of which I made that wasn’t in the list | Subcontractor | Joe Hoyle | Yes | Panel fab. Fire alarm on next door building | Yes | 2 remake panels as fast as we can get them | Misty and cloudy | 3 | 8 | No |  | 45 foot scissor and 30 foot boom | No |  |  | No |  | ACM | 6 | 2.5
24068 | QTS NAL1 DC2 | 2026-01-06 | Marvin Blanco | Working in the screenwall with the louvers blades | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 4 | 12 | No |  | boomlift and forklift | No |  |  | No |  | Louvre | [24 empty] | 10 | 48
24077 | IAD 667 TI | 2026-01-06 | Fredy veliz | Had to drill new holes on the clips for elevation sc5 because the drawing show I beam ,instead we have tubes on the structure,we only worked on the 150 boom lift today because was not room for the other booms because the cranes and we waiting on the approval to cut Chanel's to continue the Install,had the rest of the crew preparing clips but running out of work if not get approval to continue | Subcontractor | Chris Buttrey | Yes | Waiting on approval to cut Chanel's ,cranes on the way | No |  | Cold | 8 | 64 | No |  | 2 65 boom lifts ,150 articulate boom ,10k load | No |  |  | Yes | Elevation sc5 | Louvre | [24 empty] | 42 clips installed ,prep clips | 64
25002 | Med Center Health | 2026-01-06 | Marvin Blanco | Working in the eyebrow and also in the stairs #1 with strong and insulation | Subcontractor | Carlos Silva | No |  | No |  | Good condition | 5 | 10 | No |  | Boomlift | No |  |  | No |  | ACM | 13 | 50
25002 | Med Center Health | 2026-01-06 | Kevin Morris | Installed 13 acm panels on west eyebrow, installed 960 SQ ft of insulation on south stair tower, walked job with crane guy and talked to gc about best place to set up crane to stage material on the roof for penthouses, pulled measurements for louver openings on penthouse for Carlos, and measurements on southeast canopy for Dennis. | Subcontractor | Carlos Silva | No |  | No |  | 60 | 6 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM Insulation | 13 | 10 | [24 empty] | 960 | 10
25036 | TCAT Chattanooga | 2026-01-06 | Obed Bermudez | We fabricated a panel on 203/8 west elevation that wasn't made in the shop nor did it have a panel number on drawings. Crew continues working on the North elevation/west, installing z-girt, flashing, ACM/Flush panels, moving material,caulking and cleaning up. | Subcontractor | Josh McPherson | No |  | Yes | 10' plus long wood grain plac clad panels on North elevation, (Wood grain) colored rivets, 16 musket gray pac clad that measure 8 feet. 12' plus long pac clad anodized clear for south soffit, brake metal for south soffit, closure angle. | Clear | 8 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | North | ACM Flashing Insulation Subgirt Zee | 14 | 30 | [24 empty] | 32 | 5 |  |  | 114 | 20 | 145 | 25
24018 | QTS-NAL1-DC1 | 2026-01-05 | Marvin Blanco | Working in the louvers blades in the screenwall the guys just started today installing the angles and vertical support | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 4 | 12 | No |  | Boomlift forklift | No |  |  | No |  | Louvre | [24 empty] | 0 | 48
24039 | The Visionary | 2026-01-05 | Wilver Quiroz | A team worked installing subgirts zee on the north elevation. Another team worked by putting caulking on the zee subgirts on the south side that had been pending, three teams worked installing insulation and ACM in the atrium and three people worked preparing panels and passing material to the installers | Subcontractor | Carlos Silva | No |  | Yes | I need 1-1/4 and 3/4 screws | Sunny | 14 | 10 | No |  | 5 boom lift, 2 scissor lift and 1 lull | No |  |  | Yes | North, south and east | ACM Flashing Insulation Subgirt Zee | 17 | 60 | [24 empty] | 160FT | 20 |  |  | 300FT | 30 | 30FT | 20
24046 | UAB Biomedical Research and Psycholgy | 2026-01-05 | Naza padron | N/A | Subcontractor | Wylie McDougall | No |  | No |  | sunny | 4 | 40 | No |  | N/A | No |  |  | No |  | ACM Subgirt Zee Trim | 20 | 26 | [28 empty] | 50 | 4 |  |  |  |  | 160 | 10
24046 | UAB Biomedical Research and Psycholgy | 2026-01-05 | Naza padron | two panels were cut and router 6 hours | Subcontractor | Wylie McDougall | No |  | No |  | sunny | 6 | 60 | No |  | N/A | No |  |  | No |  | ACM Insulation Subgirt Zee Trim | 17 | 24 | [24 empty] | 176 | 8 |  |  | 50 | 6 |  |  |  |  | 170 | 16
24068 | QTS NAL1 DC2 | 2026-01-05 | Marvin Blanco | Working in the louvers blades in the screenwall the guys just started today installing the angles and vertical support | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 4 | 12 | No |  | Boomlift forklift | No |  |  | No |  | Louvre | [24 empty] | 16 | 48
24068 | QTS NAL1 DC2 | 2026-01-05 | Chad McCoy | We started cutting out panels instead of taken everything down. This will eliminate the chance of damage on panels when they are taken down stored and reinstalled. We removed 24 panels and we stopped at the panels we needed to try and save | Subcontractor | Joe Hoyle | No |  | Yes | 2 panels that can’t be removed with out breaking routes | Cloudy | 2 | 8 | No |  | 45 foot scissor and 30 foot electric boom | No |  |  | No |  | ACM | 0 | 0
24077 | IAD 667 TI | 2026-01-05 | Fredy veliz | Today we didn't have good progress today ,it was a crane on the area making impossible continuing with the lay out on the upper walls ,on lower wall we waiting on answer about the Chanel that need to be cut | Subcontractor | Chris Buttrey | Yes | Incorrect Chanel's size waiting on approval to cut it down ,crane on the way | No |  | Cold | 8 | 48 | No |  | 2 65 straight boom lift ,150 articulate boom ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installed clips on section 11 sc2 ,prep clips ,screw clips,sc4,mock up for cutting Chanel's | 48
25002 | Med Center Health | 2026-01-05 | Marvin Blanco | Working in the north elevation in the corner of the building and also installing strong girt in the stair 1 the only thing we have issues it's in the north side with the soffit light the electric guy are installing the lights in the wrong spot | Subcontractor | Carlos Silva | No |  | No |  | Good condition | 6 | 10 | No |  | Boomlift | No |  |  | No |  | ACM | 10 | 60
25002 | Med Center Health | 2026-01-05 | Kevin Morris | Installed zees on south stair tower, finished panels on north started installing facia panels on west eyebrow. Cut back zees on north soffit so lights can be moved. Did inventory of materials onsite | Subcontractor | Carlos Silva | Yes | Lights on north lower soffit not in correct location | Yes | Roof protection | 60's | 7 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM Subgirt Zee | 14 | 10 | [28 empty] | 340 | 5
25036 | TCAT Chattanooga | 2026-01-05 | Obed Bermudez | Crew continues working on the North elevation/west, installing z-girt, flashing, ACM/Flush panels, moving material,caulking and cleaning up. | Subcontractor | Josh McPherson | No |  | Yes | (Wood grain) colored rivets, 16 musket gray pac clad that measure 8 feet. | Clear | 8 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | West and North | ACM Caulking Flashing Insulation Subgirt Zee | 11 | 30 | [18 empty] | 118 | 10 |  |  |  |  | 64 | 10 |  |  | 80 | 10 | 120 | 20
25036 | TCAT Chattanooga | 2026-01-04 | Obed Bermudez | Crew continues working on the North elevation, installing perforated vents, z-girt, flashing, ACM/Flush panels, moving material, and cleaning up. | Subcontractor | Josh McPherson | No |  | Yes | 16 musket gray pac clad that measure 8 feet. | Clear | 4 | 8 | No |  | Boom lift and forklift | No |  |  | Yes | North | ACM Insulation Subgirt Zee | 7 | 22 | [24 empty] | 64 | 5 |  |  | 55 | 5
24039 | The Visionary | 2026-01-03 | Wilver Quiroz | A team worked installing subgirts zee on the north elevation. Another team worked by putting caulking on the zee subgirts on the south side that had been pending, three teams worked installing insulation and ACM in the atrium and three people worked preparing panels and passing material to the installers | Subcontractor | Carlos Silva | No |  | No |  | Cloudy | 14 | 8 | No |  | 5 boom lift, 2 scissor lift and 1 lull | No |  |  | Yes | North, south and east | ACM Flashing Insulation Subgirt Zee | 14 | 60 | [24 empty] | 288FT | 20 |  |  | 480FT | 20 | 23FT | 20
25036 | TCAT Chattanooga | 2026-01-03 | Obed Bermudez | Crew continues working on the south elevation, installing perforated vents, z-girt, flashing, ACM/Flush panels, moving material, and cleaning up. | Subcontractor | Josh McPherson | No |  | Yes | 16 musket gray pac clad that measure 8'. | Clear | 2 | 8 | No |  | Boom lifts and forklift | No |  |  | Yes | South | Flashing Insulation Single Skin | [6 empty] | 7 | 5 | [18 empty] | 128 | 8 |  |  |  |  | 25 | 3
24039 | The Visionary | 2026-01-02 | Wilver quiroz | A team worked installing subgirts zee on the north elevation. Another team worked by putting caulking on the zee subgirts on the south side that had been pending, three teams worked installing insulation and ACM in the atrium and three people worked preparing panels and passing material to the installers | Subcontractor | Carlos Silva | No |  | No |  | Sunny | 14 | 10 | No |  | 5 boom lift, 2 scissor lift and 1 lull | No |  |  | Yes | North, south and east | ACM Flashing Insulation Subgirt Zee | 19 | 60 | [24 empty] | 160 FT | 20 |  |  | 350FT | 30 | 20 FT | 6
24077 | IAD 667 TI | 2026-01-02 | Fredy veliz | We have and issue with Chanel, not match the horizontal steels ,need to discuss a solution that's holding us to continue the installs,having hard time finding materials don't have parking list | Subcontractor | Chris Buttrey | Yes | Chanel's no match the Chanel's ,don't have parking list hard time finding materials | No |  | Cold | 8 | 48 | No |  | 2 65 boom lift ,150 articulate boom ,10k load | No |  |  | Yes | Elevation sc2 sention 10 and 11 | Louvre | [24 empty] | Spearing materials screwing clips | 48
25002 | Med Center Health | 2026-01-02 | Kevin Morris | No work Saturday | Subcontractor | Carlos Silva | No |  | No |  | 37° | 6 | 10 | No |  | 3 boom lifts | No |  |  | No |  | ACM Insulation | 16 | 10 | [24 empty] | 1000 | 10
25031 | LLU Mars US Warehouse | 2026-01-02 | Abner aguilar | No | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 40 | No |  | Boom lift | No |  |  | No |  | ACM Insulation Subgirt Zee | 14 | 40 | [24 empty] | 287 | 40 |  |  | 21 | 40
25036 | TCAT Chattanooga | 2026-01-02 | Obed Bermudez | Crew continues working on the south and north elevation, installing perforated vents, z-girt, flashing, ACM/Flush panels, moving material, and cleaning up. | Subcontractor | Josh McPherson | No |  | Yes | 16 musket gray pac clad that measure 8'. | Clear | 1 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | South and North | Flashing Single Skin Subgirt Zee | [6 empty] | 30 | 7 | [22 empty] | 4 | 1 | 24 | 2
24039 | The Visionary | 2025-12-31 | Wilver Quiroz | Two teams worked installing subgirts zee on the north and west elevation. 3 teams worked installing insulation and ACM in the atrium, and three people worked preparing panels and passing material to the installers | Subcontractor | Carlos Silva | No |  | No |  | Sunny | 14 | 8 | Yes | Caulking and screws | 5 Boom lift, 2 scissor lift and 1 lull | No |  |  | Yes | North, south and east | ACM Insulation Subgirt Zee | 14 | 60 | [24 empty] | 192FT | 20 |  |  | 680FT | 60
24077 | IAD 667 TI | 2025-12-31 | Fredy veliz | We found an issue with the Chanel size no match the horizontals tubes distance on elevation sc2 we need to discuss possible solitions | Subcontractor | Chris Buttrey | No |  | No |  | Cold | 8 | 48 | No |  | 2 65 straight boom lifts ,150 articulate boom ,10 k load | No |  |  | Yes | Elevation sc2 | Louvre | [24 empty] | Spearing materials ,installing clips sc4 and sc2 | 48
25002 | Med Center Health | 2025-12-31 | Kevin Morris | Took measurement on southeast side for Carlos | Subcontractor | Carlos Silva | Yes | Had to stop so crane could set a light pole | No |  | 28° | 4 | 8 | No |  | 3 boom lifts | No |  |  | Yes | North stair tower | ACM Subgirt Zee | 7 | 7 | [28 empty] | 175 | 1
24039 | The Visionary | 2025-12-30 | Wilver quiroz | Two teams worked installing subgirts zee on the north and west elevation. 3 teams worked installing insulation and ACM in the atrium, and three people worked preparing panels and passing material to the installers | Subcontractor | Carlos Silva | No |  | Yes | Caulking and 2” screws | Sunny | 15 | 10 | No |  | 5 boom lift, 2 scissor lift and 1 lull | No |  |  | Yes | North, east and west | ACM Insulation Subgirt Zee | 13 | 60 | [24 empty] | 192FT | 20 |  |  | 1110FT | 60
24046 | UAB Biomedical Research and Psycholgy | 2025-12-30 | Naza Padron | N/A | Subcontractor | Wylie McDougall | No |  | No |  | cloudy | 4 | 40 | No |  | N/A | No |  |  | No |  | ACM Insulation Subgirt Zee Trim | 10 | 16 | [24 empty] | 340 | 8 |  |  | 90 | 8 |  |  |  |  | 100 | 8
24077 | IAD 667 TI | 2025-12-30 | Fredy veliz | We waiting on updates about missing horizontals steel tubes ,there is a lot materials of other trades on the areas ,I talked to the GC. And the handrails installers ,to make tube about the handrails on elevation sc5 ,we traying to do all the layout that we can to have a good progress when everybody move out ,modify left over clips from sc1 of the bottom to use on sc2 where tube connections are on the way | Subcontractor | Chris Buttrey | No |  | No |  | Cold and windy over 20mph | 8 | 80 | No |  | 2 straight 65 boom lift ,150 articulate boom lift ,10k load | No |  |  | Yes | Elevation sc2,and sc4 | Louvre | [24 empty] | Installing clips ,layout ,prep clips | 80
25002 | Med Center Health | 2025-12-30 | Marvin Blanco | Working in the stairs 2 installing ACM panels we almost done today and also checking the rest of the areas where we can work cleaning and making everything work | Subcontractor | Carlos Silva | No |  | No |  | Cold | 4 | 10 | No |  | Boomlift | No |  |  | No |  | ACM | 25 | 40
25002 | Med Center Health | 2025-12-30 | Kevin Morris | Did Orientation, installed acm on north stair tower | Subcontractor | Carlos Silva | No |  | No |  | 28° | 5 | 10 | No |  | 2 60' boom lifts | No |  |  | Yes | North | ACM Subgirt Zee | 28 | 10 | [28 empty] | 10 | 1
25036 | TCAT Chattanooga | 2025-12-30 | Obed Bermudez | Crew continues working on the south and north elevation, installing perforated vents, z-girt, flashing, ACM/Flush panels, moving material, and cleaning up. Panel 202-1c12a. | Subcontractor | Josh McPherson | No |  | Yes | 16 musket gray pac clad that measure 8'. | Clear | 4 | 8 | Yes | 2 sheets of west peter mica, 3 pieces of flashing, 1 box of screws, 1 box of corners, 1 bundle of extrusions. | Boom lifts and forklift | No |  |  | Yes | South and North | ACM Insulation Single Skin Subgirt Zee | 6 | 20 |  |  |  |  | 34 | 15 | [18 empty] | 24 | 3 |  |  | 13 | 2
24039 | The Visionary | 2025-12-29 | Wilver Quiroz | 3 teams worked installing subgirt zee on the north, south and west elevation. 2 teams worked installing subgirt zee, insolation and ACM in the atrium. Two people worked preparing panels and passing material to the installers. We need 2” screws, caulking | Subcontractor | Carlos Silva | No |  | Yes | Caulking and 2” screws | Sunny | 15 | 10 | No |  | 5 boom lift, 2 scissor lift and 1 lull | No |  |  | Yes | South and east | ACM Insulation Subgirt Zee | 10 | 60 | [24 empty] | 96FT | 10 |  |  | 1540 FT | 80
24077 | IAD 667 TI | 2025-12-29 | Fredy veliz | I need to know if we are going to use metal studs where the horizontal steel tubes are Missing ,and there one area on elevation sc5 section P where they going to installs hand rails and if gonna be on ours way to install ours vertical Chanels the bar grating is already on and is not way to installs clips ,we will have to modify the holes on the clips to install the clips under the beam ,details on the pictures ,we are trying to get a date to moved all the material but we having issues with other trades that have areas not ready and don't even have Materials on site ,having windy days can't work on the big walls ,must of the doors on the steels are off ,cooper steel is working on it but that's causing delays | Subcontractor | Chris Buttrey | No |  | No |  | Windy | 8 | 80 | No |  | 2 65 straight boom lift ,150 articulated boom lift ,10k load | No |  |  | Yes | Lay out and install clips elevation sc4 ,sc2 | Louvre | [24 empty] | Install and screw clips | 80
25002 | Med Center Health | 2025-12-29 | Marvin Blanco | Working in the stairs tower #2 in the north elevation the GC was saying all the soffit light are installed and they don't have anything only one light in end of the soffit also I talk with the GC in the morning and he was saying we can start the Zs in the penthouse but we don't have any Zs 2" and Calos went this afternoon and he was saying it's 4" Zs I'll confirm with the GC tomorrow morning if it's 2" or 4" | Subcontractor | Carlos Silva | No |  | No |  | Cold | 4 | 10 | No |  | Boomlift | No |  |  | No |  | ACM | 16 | 40
25036 | TCAT Chattanooga | 2025-12-29 | Obed Bermudez | Crew continues working on the south and north elevation, installing perforated vents, z-girt, flashing, ACM/Flush panels, moving material, and cleaning up. | Subcontractor | Josh McPherson | No |  | Yes | Panels screws(panels missing screws on one side), extrusions,chevrons, flashing over the brick at North elevation Panel material to remake panel that Mason’s damaged | Clear | 4 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | South and North | ACM Flashing Insulation Single Skin Subgirt Zee | 2 | 10 |  |  |  |  | 41 | 20 | [18 empty] | 64 | 5 |  |  | 50 | 4 | 3 | 1
25036 | TCAT Chattanooga | 2025-12-28 | Obed Bermudez | Crew continues working on the south and north elevation, installing perforated vents, z-girt, flashing, ACM/Flush panels, moving material, and cleaning up. | Subcontractor | Josh McPherson | No |  | Yes | Panels screws(panels missing screws on one side), extrusions,chevrons, flashing over the brick at North elevation Panel material to remake panel that Mason’s damaged | Clear | 4 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | South and north | ACM Flashing Hat Channel Single Skin | 7 | 20 |  |  |  |  | 33 | 10 | [24 empty] | 30 | 5 | 10 | 5
24039 | The Visionary | 2025-12-27 | Wilver Quiroz | 5 teams worked installing Z-girts on the north, south, west elevation and in the atrium. Panel could not be installed because we did not have flashing. Today two deliveries came in, one at 9 in the morning and one at 3:30 in the afternoon | Subcontractor | Carlos Silva | Yes | Panels could not be installed in the atrium because the flashing arrived late | Yes | 2’’ screws and caulking | Sunny | 12 | 8 | Yes | Panels, scafolding and flashing | 5 boom lift, 2 scissor lift and 1 lull | No |  |  | No |  | Subgirt Zee | [30 empty] | 1910FT | 100
24039 | The Visionary | 2025-12-26 | Wilver Quiroz | 5 teams worked on the north, south and west elevation installing Z-girts one team worked installing panel and z-girts in the atrium. Flashing and caulking have not yet arrived to be able to install more panels in the atrium | Subcontractor | Carlos Silva | Yes | We don’t have sill flashing and flashing to install more panels in the atrium | Yes | Flashing and caulking | Sunny | 13 | 10 | No |  | 5 boom lift, 2 scissor lift and 1 lull | No |  |  | Yes | Atrium | ACM Subgirt Zee | 1 | 4 | [28 empty] | 2440FT | 116
24077 | IAD 667 TI | 2025-12-24 | Fredy veliz | 150 boom lift was leaking in the morning, I called and they fixed couple hours later , the job is close for the rest of the week | Subcontractor | Chris Buttrey | No |  | No |  | Good | 4 | 32 | No |  | 2 65 straight boom lift , 150 articulate boom ,10k load | No |  |  | No |  | Louvre | [24 empty] | Screw clips | Screw clips
24039 | The Visionary | 2025-12-23 | Wilver Quiroz | Four teams worked on the north, east and west elevation installing Z-girts and a group installing insulation and ACM in the atrium and three guys preparing panels and passing material to the installers, we did not receive any deliberation today. We are still waiting for the sill flashing and flashing to install all the atrium panels | Subcontractor | Carlos Silva | Yes | Necesitamos sill flashing y flashing para poder terminar todos los paneles del atrium | Yes | Flashing y caulking | Sunny | 13 | 10 | No |  | 5 boom lift, 2 scissor lift and 1 lull | No |  |  | Yes | Atrium | ACM Insulation Subgirt Zee | 6 | 20 | [24 empty] | 96FT | 20 |  |  | 2440FT | 80
24077 | IAD 667 TI | 2025-12-23 | Fredy veliz | Some places the splice in the blade is located in the horizontal tube conexión to the vertical in areas we will have to install the clip on the face of the tube | Subcontractor | Chris Buttrey | Yes | We rain in the morning | No |  | Raining | 8 | 64 | No |  | 2 65 straight boom , 150 articulated boom ,10k load | No |  |  | Yes | Elevation sc2 section 3 to 10 | Louvre | [24 empty] | Clips lower wall , clips upper wall | 64
25036 | TCAT Chattanooga | 2025-12-23 | Obed Bermudez | Crew continues working on the south and north elevation, installing perforated vents, z-girt, flashing, ACM/Flush panels, moving material, and cleaning up. | Subcontractor | Josh McPherson | No |  | Yes | Panels screws(panels missing screws on one side), extrusions,chevrons, flashing over the brick at North elevation Panel material to remake panel that Mason’s damaged | Clear | 9 | 8 | No |  | Boom lifts and forklift | No |  |  | Yes | South and north | ACM Flashing Hat Channel Insulation Single Skin | 5 | 24 |  |  |  |  | 52 | 20 | [18 empty] | 64 | 10 |  |  |  |  | 40 | 5 | 40 | 5
24018 | QTS-NAL1-DC1 | 2025-12-22 | Marvin Blanco | Working on installing louvers blades also angles and tubes support everything for now is working really well the only thing we are going to need is screws for the angles | Subcontractor | Joe Hoyle | No |  | Yes | Screws for the angles | Cold | 4 | 12 | No |  | Boomlift forklift | No |  |  | No |  | Louvre | [24 empty] | 14 | 48
24039 | The Visionary | 2025-12-22 | Wilver quiroz | Five teams worked on the north, south and west elevation installing zetas and a group installing panels and insulation in the atrium 3 guys worked preparing panels for the atrium, We can’t install all the panels in the atrium because we need the sill flashing and flashing for the windows | Subcontractor | Carlos Silva | Yes | We don't sill flashing and flashing for de atrium | Yes | Caulking, flashing | Sunny | 16 | 10 | No |  | 5 boom lift, 2 scissor lift, 1 lull | No |  |  | Yes | Atrium | ACM Insulation Subgirt Zee | 3 | 20 | [24 empty] | 96 | 20 |  |  | 2430 | 100
24068 | QTS NAL1 DC2 | 2025-12-22 | Marvin Blanco | Working on installing louvers blades also angles and tubes support everything for now is working really well the only thing we are going to need is screws for the angles | Subcontractor | Joe Hoyle | No |  | Yes | Screws for the angles | Cold | 4 | 12 | No |  | Boomlift forklift | No |  |  | No |  | Louvre | [24 empty] | 12 | 48
24077 | IAD 667 TI | 2025-12-22 | Fredy veliz | There is more horizontal tubes missing by the doors elevación sc2,and some of the supports we have to move to diferent location ,some areas is no way to install the clips on top we gonna screw in the face of the tube ,job side is gonna be close from December 23th to 29th next week only close on the 1st,LGMG 65 lift is no good for lifting only works good with 1 person ,cooper steel is not on site they still need to fix 1 door on sc1 traction 12 ,section 12 on sc1 we will have to cut the blades the steel structure is 1-3/4" smaller ,need to be cut to line up with sc2 section 1 at the corner | Subcontractor | Chris Buttrey | Yes | Steel doors need to get fix ,missing steel | No |  | Good | 8 | 80 | No |  | 2 65 straight boom lifts ,150 articulate boom lift ,10k load | No |  |  | Yes | Elevation sc2 sections 1 to 5 | Louvre | [24 empty] | Install Clips elevation sc4 ,section 3,4 install blades sc1 section 7,8 ,install clips sc2 ,section 1,2 | 80
25002 | Med Center Health | 2025-12-22 | Marvin Blanco | Working on silicone and taking plastic off | Subcontractor | Carlos Silva | No |  | No |  | Cold | 6 | 11 | No |  | Boomlift | No |  |  | No |  | Caulking | [20 empty] | 300 | 66
25036 | TCAT Chattanooga | 2025-12-22 | Obed Bermudez | We modified panels 210-1a19, 210-1a21, 210-1a23, and 210-1a25 due to them being too long. Crew continues working on the south and north elevation, installing perforated vents, z-girt, flashing, ACM/Flush panels, moving material, and cleaning up. | Subcontractor | Josh McPherson | No |  | Yes | Panels screws(panels missing screws on one side), extrusions,chevrons, flashing over the brick at North elevation Panel material to remake panel that Mason’s damaged | Clear | 9 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | South and North | ACM Flashing Hat Channel Single Skin Subgirt Zee | 6 | 30 |  |  |  |  | 47 | 40 | [22 empty] | 20 | 5 | 130 | 10 | 30 | 5
24018 | QTS-NAL1-DC1 | 2025-12-21 | Marvin Blanco | Working on installing louvers blades also angles and tubes support everything for now is working really well the only thing we are going to need is screws for the angles | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 4 | 10 | No |  | Boomlift forklift | No |  |  | No |  | Louvre | [24 empty] | 19 | 40
24068 | QTS NAL1 DC2 | 2025-12-21 | Marvin Blanco | Working on installing louvers blades also angles and tubes support everything for now is working really well the only thing we are going to need is screws for the angles | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 4 | 10 | No |  | Boomlift forklift | No |  |  | No |  | Louvre | [24 empty] | 22 | 40
25002 | Med Center Health | 2025-12-21 | Marvin Blanco | Working on silicone and taking plastic off in the stairs tower and also putting insulation in the second stairs tower we finally get the material to start working in the ACM panels after two weeks waiting | Subcontractor | Carlos Silva | No |  | No |  | Cold | 6 | 11 | Yes | ACM PANELS | Boomlift | No |  |  | No |  | Caulking Insulation | [20 empty] | 100 | 33 |  |  |  |  | 240 | 33
25036 | TCAT Chattanooga | 2025-12-21 | Obed Bermudez | Crew continues working on the south and north elevation, installing perforated vents, z-girt, flashing, ACM/Flush panels, moving material, and cleaning up. | Subcontractor | Josh McPherson | No |  | Yes | Panels screws(panels missing screws on one side), extrusions,chevrons, flashing over the brick at North elevation Panel material to remake panel that Mason’s damaged | Clear | 9 | 5 | Yes | Rivets, cover flashing, and J flashing. | Boom lifts and forklift | No |  |  | Yes | South and North | ACM Flashing Insulation Single Skin Subgirt Zee | 5 | 10 |  |  |  |  | 25 | 10 | [18 empty] | 32 | 10 |  |  | 40 | 5 | 40 | 10
24039 | The Visionary | 2025-12-20 | Wilver quiroz | Four teams worked on the south and west elevation installing zetas and a group installing panels and insulation in the atrium 2 guys worked preparing panels for the atrium and one team worked taking measurements from the coping of the northwest elevation | Subcontractor | Carlos Silva | Yes | We don't have sill flashing and flashing for the atrium área | Yes | Or hardware is caulking, flashing needed | Sunny | 16 | 10 | No |  | 5 boom lift, 2 scissor lift, 1 lull | No |  |  | Yes | South, west and atrium | ACM Insulation Subgirt Zee | 3 | 20 | [24 empty] | 96FT | 20 |  |  | 1310FT | 80
24077 | IAD 667 TI | 2025-12-20 | Fredy veliz | We are moving a lot stuff out of the way to set the boom lifts ,that's slowing us down | Subcontractor | Chris Buttrey | No |  | No |  | Good | 8 | 64 | No |  | 2 65 boom lift ,150 articulate boom lift ,10k load | No |  |  | Yes | Sc4 section 3,4 sc2 section 1 | Louvre | [24 empty] | Braces on elevation sc1 section 7 to 10 ,clips sc2 section 1 ,clips elev sc4 section 3,4 | 64
25036 | TCAT Chattanooga | 2025-12-20 | Obed Bermudez | We fabricated a panel on the northeast elevation column that doesn’t have a number on the drawings and modified panels 203-1E10 and 203-1E01. Crew continues working on the south and north elevation, installing perforated vents, z-girt, flashing, ACM/Flush panels, moving material, and cleaning up. | Subcontractor | Josh McPherson | No |  | Yes | Rivets, panels screws(panels missing screws on one side), extrusions, chevrons, cover flashing(wood grain), J flashing (wood grain), 2 inch long screws, panel material to remake panel that masons damaged. | Clear | 9 | 8 | No |  | Boom lifts and forklift | No |  |  | Yes | South and north | ACM Flashing Single Skin Subgirt Zee | 7 | 20 |  |  |  |  | 35 | 30 | [22 empty] | 50 | 10 | 60 | 10
24039 | The Visionary | 2025-12-19 | Wilton lorenzo | Four crews installed Z-girts on the south elevation. Two crews installed Z-girts panels and insulation in the atrium. Three people were sorting the panels that were ready to be installed and installing the clips. One crew worked on the north elevation fixing some pending details. The damaged boom lift was repaired today; it was out of service for a total of six days. The scissor lift still does not reach the height required to install the panels in the atrium. We cannot install all the panels in the atrium because the sill flashing and other required flashing have not arrived yet. | Subcontractor | Carlos Silva | Yes | We don't have sill flashing and flashing for the atrium area | Yes | Caulking, flashing | Sunny | 18 | 10 | No |  | 5 boom lift, 2 scissor lift, 1 lull | No |  |  | Yes | South, atrium | ACM Insulation Subgirt Zee | 9 | 40 | [24 empty] | 64FT | 20 |  |  | 2250FT | 80
24077 | IAD 667 TI | 2025-12-19 | Fredy veliz | Didn't. Work because weather ,united called about the boom lift they said was fix today | Subcontractor | Chris Buttrey | Yes | Raining | No |  | Raining and windy | 1 | 0 | No |  | 2 65 straight boom lift ,150 articulate boom lift | No |  |  | No |  | Louvre | [24 empty] | 0 | 0
25036 | TCAT Chattanooga | 2025-12-19 | Obed Bermudez | We remade panel 203-1E02 due to it being short 5/16. Crew continues working on the south and north elevation, installing perforated vents, z girt, flashing ACM/Flush panels, moving material, and cleaning up. | Subcontractor | Josh McPherson | Yes | Electricians have been working installing the lights since yesterday on the south elevation ceiling and still are so we are moving to another area until they finish. | Yes | Rivets, panels screws(panels missing screws on one side), extrusions, chevrons, cover flashing(wood grain), J flashing (wood grain), 2 inch long screws, panel material to remake panel that masons damaged. | Clear | 9 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | South | ACM Flashing Hat Channel Insulation Subgirt Zee | 15 | 40 | [24 empty] | 288 | 30 |  |  | 145 | 10 | 20 | 5 | 40 | 5
24018 | QTS-NAL1-DC1 | 2025-12-18 | Marvin Blanco | Working in the screenwall with the louvers blades and cleaning everything moving material | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 4 | 12 | No |  | Boomlift forklift | No |  |  | No |  | Louvre | [24 empty] | 12 | 48
24039 | The Visionary | 2025-12-18 | Wilton Lorenzo | Three crews installed Z-girts on the south side. Measurements were taken for the flashing on the south and north sides. Two crews installed panels inside the atrium. We need the flashing to continue installing all the panels. The boom lift is still damaged. | Subcontractor | Carlos Silva | Yes | We need flashing for atrium area, | Yes | Flashing, caulking | Cloudy | 16 | 10 | No |  | 5 boom lift, 2 sicssor lift, 1 lull | No |  |  | Yes | South, atrium | ACM Insulation Subgirt Zee | 5 | 20 | [24 empty] | 128FT | 5 |  |  | 1410FT | 60
24068 | QTS NAL1 DC2 | 2025-12-18 | Marvin Blanco | Working in the screenwall with the louvers blades and cleaning everything moving material | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 4 | 12 | No |  | Boomlift forklift | No |  |  | No |  | Louvre | [24 empty] | 13 | 48
24077 | IAD 667 TI | 2025-12-18 | Fredy veliz | Still not getting response from united about the 150 articulate boom lift is been down four days ,cooper steel is working on moving the door frames we are working around them ,there is a lot going on on the areas a lot material that we have to move that other trades have on our way | Subcontractor | Chris Buttrey | Yes | Doors off the line ,cooper working on ,150 boom lift not working | No |  | Good | 8 | 80 | No |  | 2 65 straight boom lifts ,150 articulate boom lift ,10k load | No |  |  | Yes | Sc1 section b,c,d | Louvre | [24 empty] | 50 Chanel's | 80
25002 | Med Center Health | 2025-12-18 | Marvin Blanco | Waiting on material for install we receive Zs and silicone but not ACM and not flashing yesterday the guy removed a lot of panels for the electric guys also | Subcontractor | Carlos Silva | Yes | Flashing and ACM panels | Yes | Flashing and ACM panels we don't have anything | Cold | 6 | 11 | Yes | Silicone and Zs | Boomlift | No |  |  | No |  | Subgirt Zee | [30 empty] | 100 | 66
25036 | TCAT Chattanooga | 2025-12-18 | Obed Bermudez | Crew continues working on the south elevation, installing perforated vents, z girt, flashing ACM/Flush panels, moving material, and cleaning up. We installed 8 vents. | Subcontractor | Josh McPherson | Yes | Stopped work early due to inclement weather. | Yes | Rivets, panels screws(panels missing screws on one side), extrusions, chevrons, cover flashing(wood grain), J flashing (wood grain), 2 inch long screws. | Rainy day | 9 | 3 | No |  | Boom lifts and forklift | No |  |  | Yes | South | ACM Hat Channel | 3 | [33 empty] | 10
24039 | The Visionary | 2025-12-17 | Wilton lorenzo | Four crews installed Z-girt on the south elevation. One of the crews installed only as far as they could because the lift is damaged. Two crews installed Z-girt and panels inside the atrium. The scissor lift arrived at 3:00 PM; one crew installed only up to the height the damaged scissor lift would reach. | Subcontractor | Carlos Silva | Yes | The boom lift and the scissor lift were broken down | Yes | Caulking | Sunny | 18 | 10 | No |  | 5 boom lift, 2 sicssor lift, 1 lull | No |  |  | Yes | Atrium, south | ACM Flashing Insulation Subgirt Zee | 11 panels | 40hrs | [24 empty] | 128FT | 10 |  |  | 2,240FT | 60 | 30 | 1
24077 | IAD 667 TI | 2025-12-17 | Fredy veliz | The 150 articulate boom still not working is been down for 3 days i talked to united yesterday and not show up to fixe the machine, i need confirmation if cooper steel is gonna fix the door the are not line up ,and the areas where steel tubes are missing if is gonna be replace with metal stubs and who is going to do it ?had only half of the crew today because of the issue with the equipment ,sent the 2 glass racks back | Subcontractor | Chris Buttrey | Yes | Equipment issues ,steel issues | No |  | Cold | 5 | 46 | Yes | United swap the 66 boom lift and we had a second 65 delivered by other company | 150 articulate boom lift ,2 65 straight boom lift ,10k load | No |  |  | Yes | Elevation sc1 section b ,d,c | Louvre | [24 empty] | 10 vertical Chanel ,screw clips | 46
25002 | Med Center Health | 2025-12-17 | Marvin noel blanco | Removing panels in the soffit because we have issues with light there many issues because the GC is not aware with everything we have flashing missing Zs 2x3x2 missing silicone and panels we're kinda delay because we don't have the specific material we need to continue working and the new GC said this is the last job they do with McDougall but it's not because us it's because the delays | Subcontractor | Carlos Silva | Yes | ACM PANELS FLASHING Zs silicone | Yes | ACM panels flashing Zs 2x3x2 and silicone | Cold | 6 | 11 | No |  | Boomlift | No |  |  | No |  | ACM | 4 | 66
25036 | TCAT Chattanooga | 2025-12-17 | Obed Bermudez | Crew continues working on the South/columns under soffit elevation, installing J channel, girt, flashing ACM/Flush panels, moving material, and cleaning up. We remade panel 205-1g33. We also modified columns 207-2k01, 207-2k01, 207-2k01, 207-2k01. due to them being too long in height. | Subcontractor | Josh McPherson | No |  | Yes | Rivets, panels screws(panels missing screws on one side), extrusions, cover flashing(wood grain), J flashing (wood grain). | Clear | 9 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | South | ACM | 20 | 90
24018 | QTS-NAL1-DC1 | 2025-12-16 | Marvin Blanco | Working in the screenwall with the louvers blades everything for now is working really well | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 4 | 12 | No |  | Boomlift forklift | No |  |  | No |  | Louvre | [24 empty] | 20 | 48
24039 | The Visionary | 2025-12-16 | Wilton Lorenzo | Three crews installed Z-girt on the south elevation. One crew did not have a boom lift to work, so they used a borrowed boom lift, but they were not able to use it for very long. One crew installed panels on the south side of the atrium. Another crew used a borrowed scissor lift while the main scissor lift was being repaired; once it was fixed, it did not raise completely. It may be due to the lift being old?.I requested that it be replaced since it is not functioning properly. One crew removed the protective plastic from the north panels and installed a missing sill flashing on the north elevation. | Subcontractor | Carlos Silva | Yes | Scissor/boom lift. Both machines are not working | Yes | Caulking | Sunny | 18 | 10 | No |  | 5 boom lift, 2 scissor lift, 1 lull | No |  |  | Yes | South, atrium | ACM Flashing Insulation Subgirt Zee | 7 | 2 | [24 empty] | 32FT | 2 |  |  | 2,230FT | 10 | 60 | 2
24046 | UAB Biomedical Research and Psycholgy | 2025-12-16 | naza padron | moving material to different location of job site, taking film off the panels 16 hours, routed 10 panels top part at north East tower roof area 8 hours | Subcontractor | Wylie McDougall | No |  | No |  | sunny | 6 | 48 | No |  | N/A | No |  |  | No |  | ACM Trim | 10 | 16 | [34 empty] | 30 | 8 | [6 empty] | 2025-12-16 |  | 1d
24068 | QTS NAL1 DC2 | 2025-12-16 | Marvin Blanco | Working in the screenwall with the louvers blades everything for now is working really well | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 4 | 12 | No |  | Boomlift forklift | No |  |  | No |  | Louvre | [24 empty] | 24 | 48
24077 | IAD 667 TI | 2025-12-16 | Fredy veliz | I had to sent some guys home because united did not show up to fix the 150 boom lift and we move out first thing in the morning ,only Had the 66 to work in one area installing clips ,cooper guys was working in the same area too installing some steels plates to connect horizontal steel tubes ,all the room The we made moving other people materials some buddy took it ,10k load is leaking | Subcontractor | Chris Buttrey | Yes | 150 boom lift down ,areas missing steel | No |  | Extremely cold | 8 | 45 | No |  | 150 boom articulate boom lift ,66 straight boom lift ,10k load | No |  |  | Yes | Elevation ,sc1 section b | Louvre | [24 empty] | 10 vertical Chanel ,80 clips | 45
25002 | Med Center Health | 2025-12-16 | Marvin Blanco | Working in the stairs tower installing ACM panels and we're missing the Zs to continue working in the stairs tower we're missing silicone and also flashing there is a little issue with the GC is saying we don't have the approval drawings for the second stairs tower for the stone panels in our details show the Zgirt vertical and they're saying it's going horizontal | Subcontractor | Carlos Silva | Yes | Zs 2x3x2 silicone flashing and panels | Yes | Zs silicone panels and flashing | Cold | 6 | 11 | No |  | Boomlift | No |  |  | No |  | ACM | 12 | 66
25036 | TCAT Chattanooga | 2025-12-16 | Obed Bermudez | Crew continues working on the North/South/columns under soffit elevation, installing J channel, girt, flashing ACM/Flush panels, moving material, and cleaning up. We remade panels 205-1g11, 205-1g14, 205-1g17, 205-1g20, 205-1g23, 205-1g26, 205-1g30, 205-1g34. We also modified columns 207-2k01, 207-2k01, 207-2k01, 207-2k01, and 207-2k01 due to them being too long in height. | Subcontractor | Josh McPherson | No |  | Yes | Rivets, panels screws(panels missing screws on one side), extrusions, cover flashing(wood grain), J flashing (wood grain). | Clear | 9 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | South | ACM Subgirt Zee | 16 | 70 | [28 empty] | 180 | 20
24039 | The Visionary | 2025-12-15 | Wilton lorenzo | One crew took the coping measurements on the east side, and when they finished, they moved to the south to install Z-girts. Two crews installed Z-girts on the south, and two other crews installed Z-girts; one of them also started laying out for the panels. The scissor lift that was delivered is out of calibration and does not go all the way up. One more guy installed a missing reveal and started removing the protective plastic from the panels on the north side. I moved all the pallets that arrived on Saturday inside the parking garage. Are the coping measurements correct? The GC asked how long it would take to fabricate them. The scissor lift we need for the level 4 patios has to be at least 30 feet, not bigger. Do you have any details about the expansion joint? | Subcontractor | Carlos Silva | Yes | The scissor lift that was replaced is out of calibration and does not go up all the way. They can request a replacement and have them bring a JLG. the articulating boom lift has a damaged joystick and will not move. The technician said it will be repaired tomorrow. | Yes | Caulking | Sunny | 16 | 10 | No |  | 5 boom lift, 2 sicssor lift, 1 lull | No |  |  | Yes | Atrium, south | ACM Flashing Insulation Subgirt Zee | 1 panel | 6hrs | [24 empty] | 96ft | 8 |  |  | 1140FT | 80 | 20FT | 4
24077 | IAD 667 TI | 2025-12-15 | Fredy veliz | Today we had a extremely cold day ,the 150 boom lift did not work has the same code we we got off after lunch ,united guy called couple hours later to check on the machine ,his gonna check the boom tomorrow because he need to move to bigger area it need to make 180 turn to recalibrated,this is gonna be an issue ,did not prep any materials every thing was freeze , | Subcontractor | Chris Buttrey | Yes | Cold weather ,150 boom lift down | No |  | Cold | 7 | 42 | No |  | 150 articulated boom lift ,66 straight boom lift ,10k load | No |  |  | Yes | Elevation sc1 section b | Louvre | [24 empty] | Screw clips ,installed 4 Chanel's | 42
25036 | TCAT Chattanooga | 2025-12-15 | Obed Bermudez | Crew continues working on the South/columns under soffit elevation, installing J channel, girt, flashing ACM/Flush panels, moving material, and cleaning up. We remade panels 205-g01, 205-1g02, 205-1g05, 205-1g08, 206-2j07, 206-2j12, 206-2j18, and 206-2j23. We also modified columns 207-2k03, 207-2k01, and 207-2k01 due to them being too long in height. | Subcontractor | Josh McPherson | No |  | Yes | Rivets, panels, screws(panels missing screws on one side), extrusions, cover flashing(wood grain), J flashing (wood grain). | Clear | 9 | 10 | No |  | Boom lifts and forklift. | No |  |  | Yes | South | ACM Flashing Single Skin Subgirt Zee | 5 | 30 |  |  |  |  | 27 | 40 | [22 empty] | 40 | 10 | 65 | 10
24018 | QTS-NAL1-DC1 | 2025-12-14 | Marvin Blanco | Working in Demo the last panels in the screenwall and also installing angles for the support | Subcontractor | Joe Hoyle | No |  | No |  | Frizzy | 5 | 10 | No |  | Boomlift forklift | No |  |  | No |  | Louvre | [24 empty] | 20 | 50
24068 | QTS NAL1 DC2 | 2025-12-14 | Marvin Blanco | Installing clips in the screenwall for the louvers blades and also cleaning our areas we have to stop working because to much snow ❄️ | Subcontractor | Joe Hoyle | No |  | No |  | Frizzy | 5 | 10 | No |  | Boomlift forklift | No |  |  | No |  | Louvre | [24 empty] | 16 | 50
25002 | Med Center Health | 2025-12-14 | Marvin Blanco | Working in the vertical columns and also installing ACM and insulation | Subcontractor | Carlos Silva | No |  | No |  | Cold | 4 | 11 | No |  | Boomlift | No |  |  | No |  | ACM | 9 | 44
24039 | The Visionary | 2025-12-13 | Wilton Lorenzo | One delivery arrived early in the morning, but it only included panels. The second delivery arrived at 10:30. Five crews were working on the east elevation removing the protective plastic from the panels, cleaning above the level 1 canopy, and installing coping on level 3. Two other crews installed Z-girts in the atrium. The scissor lift that was replaced is not going all the way up for some reason, even though it is properly leveled. Will we need a scissor lift to work on the level 4 south wall? The panels for that area arrived together with the atrium panels. Also, will any flashing be fabricated for the atrium windows since the windows are set back further than the wall? They send incorrect starter track | Subcontractor | Carlos Silva | Yes | The screws arrived at 10:30, and no caulking was included. | No |  | Sunny | 18 | 8 | Yes | ACM panels, tek screws | 5 boom lift, 2 sicssor lift, 1 lull | No |  |  | Yes | Atrium | Coping Insulation Subgirt Zee | [26 empty] | 704FT | 16hrs |  |  | 570FT | 32 | [8 empty] | 50FT | 16
24077 | IAD 667 TI | 2025-12-13 | Fredy veliz | I am going email some photos of the area where we working ,whit detail of missing structure,i gonna add EEREED TEAM on that emails to discuss possible solutions | Subcontractor | Chris Buttrey | Yes | Other trades materials on the way | No |  | Cold | 7 | 56 | No |  | 150 articulate boom lift,60 straight boom lift,10k load | No |  |  | Yes | Elevation sc4 section N 1,2,&3 | Louvre | [24 empty] | Prep and installing clips | 56
25036 | TCAT Chattanooga | 2025-12-13 | Obed Bermudez | Crew continues working on the South/beam wrap under soffit elevation, installing J channel, zgirt, flashing ACM/Flush panels, moving material, and cleaning up. We remade panels 206-2j16, 206-2j20, 206-2j24, 206-2j27, 206-2j02. | Subcontractor | Josh McPherson | No |  | Yes | Rivets, panels, screws(panels missing screws on one side), extrusions, cover flashing(wood grain), J flashing (wood grain). | Clear | 9 | 8 | No |  | Boom lift and forklift | No |  |  | Yes | South | ACM Flashing Single Skin Subgirt Zee | 8 | 40 |  |  |  |  | 23 | 20 | [22 empty] | 60 | 6 | 28 | 6
24039 | The Visionary | 2025-12-12 | Wilton Lorenzo | Two crews finished installing the last panels on the east side near the south. After that, I assigned two crews to take care of some details, such as installing the missing reveals. Two other crews installed coping on the NE balconies, and two more crews installed Zs in the atrium. One scissor lift broke down and had to be replaced. We removed the protective plastic from the SE canopy. | Subcontractor | Carlos Silva | Yes | No panels, no tek screws | Yes | Panels, 2 inch tek screws | Sunny | 18 | 10 | No |  | 5 boom lift, 2 sicssor lift, 1 lull | No |  |  | Yes | East, atrium | ACM Coping Subgirt Zee | 21 panels | 40 | [28 empty] | 860FT | 40 | [8 empty] | 70FT | 40
24077 | IAD 667 TI | 2025-12-12 | Fredy veliz | We had the 150 boom lift down since yesterday morning ,the mechanic show up at noon and spent 2 hours fixing the issue ,other trades is not moving their materials out the way we had to moved to continue working, there is missing structure in different areas will send different email with the info , | Subcontractor | Chris Buttrey | Yes | Boom lift locked in the way for day and half | No |  | Cold | 7 | 63 | No |  | 150 articulate boom lift ,65 straight boom ,10k load | No |  |  | Yes | Elevation b and c | Louvre | [24 empty] | Installing blades and prep clips | 63
25002 | Med Center Health | 2025-12-12 | Marvin Blanco | Caulking the vertical joint in the columns for install the next columns and also installing the Zgirts in the back of the building | Subcontractor | Carlos Silva | No |  | No |  | Cold | 4 | 11 | No |  | Boomlift | No |  |  | No |  | Subgirt Zee | [30 empty] | 400 | 44
25036 | TCAT Chattanooga | 2025-12-12 | Obed Bermudez | Crew continues working on the SW/SE elevation, installing J channel, z girt, flashing ACM/Flush panels, moving material, and cleaning up. We remade panels 206-2j05, 206-2j09, 206-2j13, 205-1g01. | Subcontractor | Josh McPherson | No |  | Yes | Rivets, panels, screws(panels missing screws on one side), extrusions, cover flashing(wood grain), J flashing (wood grain). | Clear | 9 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | South | ACM Flashing Insulation Single Skin Subgirt Zee | 11 | 30 |  |  |  |  | 26 | 30 | [18 empty] | 64 | 10 |  |  | 100 | 10 | 17 | 10
24039 | The Visionary | 2025-12-11 | Wilton Lorenzo | One crew installed Z-girts, insulation, flashing, and starter track above level 1. Another crew was installing anthracite color panels. Another group installed the remaining flashing and some reveal. Another crew installed panels next to the curtain wall all of this work was on the east elevation. Another crew installed coping in the north patios. Two crews installed Z-girts in the atrium on level 2. | Subcontractor | Carlos Silva | Yes | I’m running low on panels and screws. | Yes | Panels, 2 inch tek screws | Sunny | 18 | 10 | No |  | 5 boom lift, 2 sicssor lift, 1 lull | No |  |  | Yes | East, atrium | ACM Flashing Insulation Subgirt Zee | 30 panels | 10 | [24 empty] | 256FT | 10 |  |  | 1030 | 10 | 260FT | 10hrs
24046 | UAB Biomedical Research and Psycholgy | 2025-12-11 | naza padron | 130' flat strips instaled bridge siffit 16 hours | Subcontractor | Wylie McDougall | No |  | No |  | sunny | 9 | 90 | No |  | N/A | No |  |  | No |  | ACM Trim | 33 | 50 | [34 empty] | 140 | 24
24065 | QTS NAL2 DC2 | 2025-12-11 | Chad McCoy | We re installed the loading dock panels. I reinstalled the vestibule 4 panels and cut the Knox box. I installed the access doors in the other QTs. We installed all the acm at the top of the wind wall except the top cap bc it is built wrong. Caulking was continued in the east side | Subcontractor | Joe Hoyle | No |  | Yes | Freedom wall panels | Cloudy and cold | 7 | 7.5 | No |  | 85 foot boom. 65 foot boom. And a broke 85 foot boom no body knew was mcdougals | No |  |  | Yes | Layout had to be done in the vestibule for cuts. Layout also had to be down at the top of wing wall do we could make 2 out of the 3 panels that are wrong | ACM Caulking | 12 | 5 | [18 empty] | 500 | 5
24065 | QTS NAL2 DC2 | 2025-12-11 | Chad McCoy | We are finishing up panels that had to be taken off and reinstalled over grays backward methods. | Subcontractor | Joe Hoyle | Yes | Acm rework on the top of the wing wall yet again has to be fixed bc the panels are wrong. The top cap panel is a formed panels and it’s made wrong. | Yes | Freedom wall panels. | Cloudy and cold | 7 | 8 | No |  | 65 foot boom and 85 foot boom. And 1 85 foot boom that’s from Antonio’s job | No |  |  | Yes | Layout had to be done to cut hole inside the vestibule and for the install of Antonio’s access doors | ACM Insulation Subgirt Zee | 12 | 7 | [24 empty] | 50 | 0.5 |  |  | 40 | 0.5
24077 | IAD 667 TI | 2025-12-11 | Fredy veliz | Some of the blades come with little dents on it visible only when sun hits the wall,our big boom lift is down called united but no buddy come yet ,a lot materials on the way Gc need to clear out the side walk for us to set the big boom lift ,section 3 and 4 no ready on the upper walls ,the pipe for the generators doesn't fit the are taking measurements to make a need one don't know when is going to be ready ,door opening not line up with blades 4" off | Subcontractor | Chris Buttrey | Yes | 150 boom lift not working | No |  | Cold | 7 | 70 | No |  | 150 articulate boom lift ,65 straight boom lift ,10k load | No |  |  | Yes | Elevation cs1 section a & b | Louvre | [24 empty] | Installed 4 sections of blades ,prep Clips ,screw clips | 70
25036 | TCAT Chattanooga | 2025-12-11 | Obed Bermudez | Crew continues working on the SW/SE elevation, installing J channel, z girt, flashing ACM/Flush panels, moving material, and cleaning up. | Subcontractor | Josh McPherson | No |  | Yes | Rivets, panels, screws(panels missing screws on one side), extrusions, cover flashing(wood grain), J flashing (wood grain). | Clear | 9 | 10 | Yes | Hat channel, strap metal, flashing, sheets to remake panels and panels. | Boom lift and forklift. | No |  |  | Yes | South | ACM Flashing Single Skin Subgirt Zee | 10 | 20 |  |  |  |  | 54 | 30 | [22 empty] | 100 | 20 | 115 | 20
24018 | QTS-NAL1-DC1 | 2025-12-10 | Marvin Blanco | Working in the screenwall with the louvers blades and cleaning everything in the roof for the metal shavings | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 5 | 12 | No |  | Forklift and boomlift | No |  |  | No |  | Louvre | [24 empty] | 25 | 60
24039 | The Visionary | 2025-12-10 | Wilton | One crew finished installing panels on the SE canopy, and another crew finished installing Z, insulation, and flashing, and started installing the missing panel row on the east side at level 3 toward the canopy. Another crew was installing Z, insulation, starter track, and flashing on the level 2 row, and another crew was installing only panels. Two other crews installed Z on level 2 in the atrium, and the boom lift arrived after midday, so I assigned two guys to install the coping on the north side balconies at level 2. | Subcontractor | Carlos Silva | No |  | Yes | Panels, 2 inch tek screws | Sunny | 18 | 10 | No |  | Five boom lift, 2 sicssor lift, one lull | No |  |  | Yes | East, atrium | ACM Coping Flashing Insulation Subgirt Zee | 31 | 6 | [24 empty] | 224FT | 4 |  |  | 1130FT | 7 | 150FT | 4 | [6 empty] | 10FT | 2
24046 | UAB Biomedical Research and Psycholgy | 2025-12-10 | naza padron | unloading material 6 hours, flat strap for metal panels 120' 6 hours, 24 siffit panels 12 hourss | Subcontractor | Wylie McDougall | No |  | No |  | sunny | 6 | 60 | Yes | ACM and metal panels | N/A | No |  |  | No |  | ACM Soffit | 32 | 36
24065 | QTS NAL2 DC2 | 2025-12-10 | Chad McCoy | Inventory of all caulking was done, bc this is starting tomorrow with the caulking crew. Nothing was installed today bc the wind gust are over 40 mph. We did go around both QTs building and we collected 5 crates and and took the to the laydown due to gray saying stuff will start being thrown away. | Subcontractor | Joe Hoyle | Yes | Wind gust made installation of top of wing wall and loading dock where we could not install these areas due to safety concerns with these huge panels due to wind gust | Yes | Freedom wall panels and access doors | Windy 35-40 mph gust | 4 | 3 | Yes | 24068 freedom wall panels and wing wall panels | 85 foot boom. 65 foot boom | No |  |  | No |  | ACM | 0 | 0
24065 | QTS NAL2 DC2 | 2025-12-10 | Chad McCoy | It’s to windy to install anything out of the booms. Wind guts up to 45 mph. | Subcontractor | Joe Hoyle | Yes | Windy. No replacement freedom wall panels | Yes | Freedom wall panels. | Cloudy and windy | 4 | 2 | No |  | 85 foot boom. 65 foot boom | No |  |  | No |  | ACM | 0 | 0
24068 | QTS NAL1 DC2 | 2025-12-10 | Marvin Blanco | Working in the screenwall with the louvers blades and also cleaning in the roof the metal shavings everything for now is working really well | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 5 | 12 | No |  | Forklift and boomlift | No |  |  | No |  | Louvre | [24 empty] | 28 | 60
24077 | IAD 667 TI | 2025-12-10 | Fredy veliz | There a lot materials in the areas , I removed the glass racks from boom lifts we do not need call united to get it pick up | Subcontractor | Chris Buttrey | No |  | No |  | Cold and windy | 6 | 54 | No |  | 150 articulate boom lift ,50 straight boom lift ,10k load | No |  |  | Yes | Elevation sc1 section a&b | Louvre | [24 empty] | Installing clips and braces ,installing blades | 54
25002 | Med Center Health | 2025-12-10 | Marvin Blanco | Working in installing Zgirt and also waiting for the approval silicone and for the layout of the soffit light | Subcontractor | Carlos Silva | No |  | No |  | Cold | 4 | 11 | No |  | Boomlift | No |  |  | No |  | Subgirt Zee | [30 empty] | 400 | 44
25036 | TCAT Chattanooga | 2025-12-10 | Obed Bermudez | Crew continues working on the south elevation, installing J, Z girt, and panels. We remade panel 205-1G46 from the corner panel that was damaged. | Subcontractor | Josh McPherson | No |  | Yes | Rivets, strap metal, flashing, cover flashing, extra extrusions/screws for making panels. | Clear | 7 | 10 | No |  | Boom lifts and forklift. | No |  |  | Yes | South | ACM Subgirt Zee | 25 | [29 empty] | 80
24028 | CHI Memorial Hospital | 2025-12-09 | JC panels | Guys finish everything. We are waiting for material to continue | Subcontractor | Josh McPherson | No |  | Yes | Coping, flashing , trims . | Good | 5 | 50 | No |  |  | No |  |  | No |  | Caulking Trespa | [10 empty] | 1 | [9 empty] | 1
24039 | The Visionary | 2025-12-09 | Wilton Lorenzo | One crew installed anthracite panels on level 1 above the east canopy, and another crew was ahead installing Z, insulation, starter track, and sill flashing. We had to cut the back side of eight panels where they return toward the ceiling because they were too big. Two guys spent five hours on that. Two other crews installed panels above the SE canopy, and the scissor lift arrived after noon, so two crews started installing Z in the atrium. I moved the small scissor lift I had over to that area. Another crew installed Z and insulation inside the parking garage on level 1. I have a question about what equipment we’re going to use in the courtyards when the panels arrive. | Subcontractor | Carlos Silva | No |  | Yes | Tek screws, panels | Sunny | 18 | 10 | No |  | 4 boom lift, 2 sicssor lift, 1 lull | No |  |  | Yes | East, south, atrium lvl 2 | ACM Flashing Insulation Subgirt Zee | 20 panels | 6 | [24 empty] | 860FT | 4 |  |  | 860FT | 6 | 170FT | 2
24046 | UAB Biomedical Research and Psycholgy | 2025-12-09 | naza padron | N/A | Subcontractor | Wylie McDougall | No |  | No |  | sunny | 6 | 60 | No |  | N/A | No |  |  | No |  | ACM Insulation Subgirt Zee | 18 | 18 | [24 empty] | 1216 | 18 |  |  | 800 | 24
24065 | QTS NAL2 DC2 | 2025-12-09 | Chad McCoy | So the design on the expansion joint on the east elevation is horrible. There is not an easy way to install these and it’s even worse on this expansion joint on keeping the pieces in place. This has been tried on Antonio’s job and they are falling out. So what I did was I took 2 j tracks for corrugated and screwed them together and I installed this inside the starter tracker area of the panels going up the expansion joint. What this does is it gives me a color matched back plate and it keeps the expansion joints from falling inside the building incase the caulking fails. Once’s this back plate was installed we installed 14’ strips of expansion joints into the pockets. We only caulked one side of the strip so it’s mobile in this pocket. It’s also cut to 1/4 bigger than the opening that way there isn’t an easy way for it to fall out. We installed all the coping on the stair tower and we installed the side flashing around our white and silver doors. | Subcontractor | Joe Hoyle | No |  | Yes | Freedom wall panels | Cloudy snow flurries and rain | 4 | 8 | No |  | 85 foot boom. 65 foot boom | No |  |  | No |  | ACM Flashing | 7 | 6 | [30 empty] | 98 | 2
24077 | IAD 667 TI | 2025-12-09 | Fredy veliz | We are almost done and cs1 a&b only 2 days to do braces and blades but we only have part of the blades the rest of those are at the energy park and is many people and materials on the next sections that's gonna slows us down a little bit | Subcontractor | Chris Buttrey | No |  | No |  | Cold | 6 | 54 | Yes | Drills bits | 150 articulate boom lift ,65 straight boom lift ,10k load | No |  |  | Yes | Section a&b. Elevation sc1 | Louvre | [24 empty] | 22 vertical channels ,line up blades, screw channels | 54
25036 | TCAT Chattanooga | 2025-12-09 | Obed Bermudez | We had to exchange extrusions of 11 panels on the west, and we also exchanged extrusions on 8 panels on the beam wrap south soffit due to the panels being short. So far we found 4 damaged panels: 205-1G33, 205-1G04, 205-1G02, 205-1G46 on the crates, some without the plastic in some areas, even blue tape in some, and others with scratches. | Subcontractor | Josh McPherson | No |  | Yes | Hat channel, strap metal, chevrons for panels (we didn't receive any), flashing, screws for panel and extra extrusions. | Clear | 7 | 10 | No |  | Boom lifts and forklift. | No |  |  | Yes | South | ACM Subgirt Zee | 18 | 60 | [28 empty] | 50 | 10
24039 | The Visionary | 2025-12-08 | Wilton lorenzo | Two crews installed panels above the SE canopy. One crew installed Z, insulation, flashing, and starter track above level 1 on the east side, and another crew started the layout for panel installation. The rest of the crews installed insulation inside the parking garage on level 1. We received a delivery flashing, sill flashing , but not the equipment. I have two crews without equipment. | Subcontractor | Carlos Silva | No |  | Yes | Tek screws 2". panel # 253-3L06 I couldn't find it | Sunny | 18 | 10 | Yes | Flashing, sill flashing | 4 boom lift, 1 sicssor lift, 1 lull | No |  |  | Yes | East | ACM Flashing Insulation Subgirt Zee | 9 | 4 | [24 empty] | 2080FT | 6 |  |  | 760FT | 6 | 20FT | 2
24077 | IAD 667 TI | 2025-12-08 | Fredy veliz | Some of the clips for the bottom has to be modify ,are too big and we gonna eliminate because the concrete is not continuous only concrete pads on the vertical tube | Subcontractor | Chris Buttrey | No |  | Yes | Drill bits | Cold | 7 | 54 | No |  | 150 articulate boom lift ,65 straight boom lift ,10k forklift | No |  |  | Yes | Sc1 section A & B | Louvre | [24 empty] | 53 vertical channel and prep clips | 54
25036 | TCAT Chattanooga | 2025-12-08 | Obed Bermudez | Crew continues working on the SW/SE elevation, installing J channel, panels, moving material, and cleaning up. | Subcontractor | Josh McPherson | No |  | Yes | Rivets, flashing, hat channel, strap metal. | Clear | 7 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | Southwest and southeast. | ACM | 29 | 70
24018 | QTS-NAL1-DC1 | 2025-12-07 | Marvin Blanco | Working in the screenwall with the louvers blades everything for now Working really well there is only one thing the angles for the tubes only comes with 2 holes and needs to be 4 holes | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 5 | 12 | No |  | Boomlift forklift | No |  |  | No |  | Louvre | [24 empty] | 30 | 60
24065 | QTS NAL2 DC2 | 2025-12-07 | Chad McCoy | Today was another day of extra work. We removed 4 finished panels from the loading dock so gray can cut holes in the denglass and fix all the sprinklers. We also cut out 3 panels on the QTs next to us and reinstalled new panels where they were damaged | Subcontractor | Joe Hoyle | Yes | Removal of panels at loading dock and cutting out panels on 24068 | Yes | Freedom walk remakes and caulking | Partly cloudy. 39 | 4 | 8 | No |  | 85 foot boom. 65 foot boom | No |  |  | No |  | ACM | 3 | 5
24068 | QTS NAL1 DC2 | 2025-12-07 | Marvin Blanco | Working in the screenwall with the louvers blades and also drilling 2 more holes in the angles because there's only 2 holes and needs to be 4 holes for every each angle cleaning everything | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 5 | 12 | No |  | Boomlift forklift | No |  |  | No |  | Louvre | [24 empty] | 29 | 60
25002 | Med Center Health | 2025-12-07 | Marvin Blanco | Working in the roof fixing the coping because it was a little issue but everything we can it's fix and clean there's one panels short in the end of the canopy | Subcontractor | Carlos Silva | Yes | Zs 3" and silicone | Yes | Zs 3" silicone | Cold | 4 | 11 | No |  | Boomlift | No |  |  | No |  | ACM | 6 | 44
24028 | CHI Memorial Hospital | 2025-12-06 | JC oanels | Finish canopy south west and finish the ACM of the sour canopy | Subcontractor | Josh McPherson | No |  | Yes | Coping fo southwest canopy. Trims and flashing for south , wood looking trims for south canopy | Good | 5 | 50 | No |  |  | No |  |  | No |  | ACM Trespa | 1 | [9 empty] | 1
24039 | The Visionary | 2025-12-06 | Wilton lorenzo | We installed panels on the fascia of the south canopy and on the east side at the entrance of the parking deck. I need to confirm whether the panels in that area will run level toward the inside of the parking deck, or if they will follow the slope, because the corner panel is level and the wall underneath ends up with a noticeable gap. We also installed insulation on the east side and on the level 4 patio, as well as insulation on the north elevation. Additionally, we installed Z-girts and insulation on the east side. | Subcontractor | Carlos Silva | Yes | We did not receive the delivery. And the sicssor lift | Yes | Panels, sill flashing, flashing al colors. going to need more 2 inch tek screws soon. | Sunny | 16 | 8 | No |  | 4 boom lift, 1 lull, 1 sicssor lift | No |  |  | Yes | South and east | ACM Insulation Subgirt Zee | 7 panels | 2 | [24 empty] | 864FT | 6 |  |  | 470FT | 6
24065 | QTS NAL2 DC2 | 2025-12-06 | Chad McCoy | Today we are making and installing the last east elevation window wrap. And one guy is caulking the vestibule | Subcontractor | Joe Hoyle | Yes | The last window wrap on the east elevation had to have modified panels due to the off set window in the framing. | Yes | Extra caulking and missing freedom wall panels | Chilly and overcast. 31 | 4 | 8 | No |  | 85 foot boom. 65 foot boom | No |  |  | Yes | The hole window had to be measured for each panel due to improper window install | ACM | 14 | 9.5
24077 | IAD 667 TI | 2025-12-06 | Fredy veliz | Need the drill bits asap | Subcontractor | Chris Buttrey | No |  | Yes | Drill bits | Cold | 7 | 8 | No |  | 150 articulate boom lift ,65 straight boom lift ,10k load | No |  |  | Yes | Elevation cs1 section a and b | Louvre | [24 empty] | screwing clips | 56
25036 | TCAT Chattanooga | 2025-12-06 | Obed Bermudez | Crew continues working on the south/west elevation, installing J channel, and panels. We modified panels 206-2J28 and 206-2J03 to fit. | Subcontractor | Josh McPherson | No |  | Yes | Rivets, strap metal, hat channel. | Clear | 5 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | South | ACM | 12 | 40
24039 | The Visionary | 2025-12-05 | Wilton Lorenzo | Two groups installed panels, Z-girts, and insulation on the SE canopy. We also started installing the fascia panels on the canopy, where those panels sit 1-5/8” lower than the building panels. Carlos and I agreed that the RGB light will run level, but there will be at least a 2-inch gap/joint. The rest of the crew installed some of the remaining panels in the level 4 patio, and insulation J-track was installed in all three NE patios. Additionally, Crossland asked me to lend them a boom lift so they could make a hole in the wall and pull a cable through for the sign on the SE canopy. They used it for about two hours. Another group installed Z-girts on the north side where the expansion joint is located. We did not receive the delivery. | Subcontractor | Carlos Silva | Yes | We didn't have flashing | Yes | Sill flashing, flashing all color, ACM panels | Sunny | 16 | 10 | No |  | 4 boom lift, 1 sicssor lift, 1 lull | No |  |  | Yes | East, south | ACM Insulation Subgirt Zee | 14 panels | 6 | [24 empty] | 544FT | 8 |  |  | 660FT | 8
24046 | UAB Biomedical Research and Psycholgy | 2025-12-05 | naza padron | N/A | Subcontractor | Wylie McDougall | No |  | No |  | sunny | 9 | 72 | No |  | N/A | No |  |  | No |  | ACM | 54 | 72
24065 | QTS NAL2 DC2 | 2025-12-05 | Chad McCoy | We finished wrapping the vestibule except where the panels had to be removed for the fire marshall | Subcontractor | Joe Hoyle | Yes | All of the outside panels that finished to the top had to be cut and routed due to a change in the installation that needs to match the other QTs. | Yes | Freedom wall panels. And caulking | Cold and windy 27 | 4 | 8 | No |  | 85 foot boom. 65 foot boom | No |  |  | Yes | The vestibule is a constant layout | ACM Insulation Subgirt Zee | 19 | 7 | [24 empty] | 80 | 0.5 |  |  | 90 | 1
24077 | IAD 667 TI | 2025-12-05 | Fredy veliz | We need updates on drill bits and will need an other 65 boom lift possible next week all depends if they clear the areas | Subcontractor | Chris Buttrey | Yes | Weather | Yes | Drills bits | Snowing | 7 | 56 | No |  | 150 boom lifts articulate ,65 straight boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | 75 clips prep and install | 56
25036 | TCAT Chattanooga | 2025-12-05 | Obed Bermudez | Crew continues working on the south/east elevation, installing J channel, Z girt, and panels. We modified panels 206-2J01 and 206-2J26 to fit. | Subcontractor | Josh McPherson | No |  | Yes | Rivets, flat metal, hat channel. | Clear | 5 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | South | ACM Subgirt Zee | 15 | 35 | [28 empty] | 50 | 15
24005 | GCDC Building 2/VA1.2 | 2025-12-04 | Obed Bermudez | We continue removing the top screen wall panel to remove the bottom, left the top one installed, and then placed the bottom panel under the platform for storage per HITT direction, and with that we finished removing the panels. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 2 | 9 | No |  | None | No |  |  | No |  | Corrugated / Screen wall | [22 empty] | 0 | 18
24018 | QTS-NAL1-DC1 | 2025-12-04 | Marvin Blanco | Working in the louvers blades in the screenwall and also Demo the the metal panels and one of my guys dropped a Zs to the roof and we damaged the roof | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 5 | 12 | No |  | Boomlift forklift | No |  |  | No |  | Louvre | [24 empty] | 15 | 60
24039 | The Visionary | 2025-12-04 | Wilton Lorenzo | Two crews installed panels on the SE canopy, and two other crews installed the interior panels in the patio on levels 3 and 4. Another crew worked on finishing details, such as installing the missing reveal. Three workers spent about three hours resizing three panels from the first horizontal row above the canopy because they were too tall. A superintendent asked me to remove one panel on the SE canopy because they are going to make a hole in the wall to run a cable for the sign. | Subcontractor | Carlos Silva | Yes | We do not have the flashing needed to continue. | Yes | Sill flashing, flashing all color | Cloudy | 16 | 10 | No |  | 4 boom lift, 1 scissor lift, 1 lull | No |  |  | Yes | East | ACM Insulation Subgirt Zee | 17 | 7 | [24 empty] | 450FT | 4 |  |  | 400FT | 6
24046 | UAB Biomedical Research and Psycholgy | 2025-12-04 | naza padron | N/A | Subcontractor | Wylie McDougall | No |  | No |  | sunny | 9 | 90 | No |  | N/A | No |  |  | No |  | ACM Subgirt Zee Trim | 66 | 70 | [28 empty] | 20 | 6 |  |  |  |  | 90 | 14
24065 | QTS NAL2 DC2 | 2025-12-04 | Chad McCoy | Panels inside the vestibule hade to be taken down due to fire marshall | Subcontractor | Joe Hoyle | Yes | Panels had to be removed again for fire marshal knock box | Yes | Missing freedom wall panels and for gray to stop having us take panels down | Cold. Snow | 4 | 8 | No |  | 85 foot boom. 65 foot boom | No |  |  | Yes | The vestibule is a constant layout | ACM Insulation Subgirt Zee | 17 | 6 | [24 empty] | 200 | 1 |  |  | 120 | 1
24068 | QTS NAL1 DC2 | 2025-12-04 | Marvin Blanco | Working with the louvers blades in the screenwall and everything is going well | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 5 | 12 | No |  | Boomlift forklift | No |  |  | No |  | Louvre | [24 empty] | 20 | 60
24077 | IAD 667 TI | 2025-12-04 | Fredy veliz | Still having issues with other trades materials on the way ,and we have to move out the way for owner deliveries at the loading dock | Subcontractor | Chris Buttrey | Yes | Othe trades materials on the way | Yes | Drills bits | Cold | 7 | 70 | No |  | 150 articulate boom lift ,65 straight boom lift ,10k load | No |  |  | Yes | Elevation sc1 section B | Louvre | [24 empty] | 80 clips drills and prep | 70
25002 | Med Center Health | 2025-12-04 | Marvin Blanco | Working with the ACM panels in the canopy | Subcontractor | Carlos Silva | No |  | Yes | Clips for the ACM panels we need those ASAP | Cold | 4 | 11 | No |  | Boomlift | No |  |  | No |  | ACM | 9 | 44
25036 | TCAT Chattanooga | 2025-12-04 | Obed Bermudez | Crew continues working on the facia of south elevation installing z girt, and panels. We modified corner panel 206-2H04 to fit. | Subcontractor | Josh McPherson | No |  | Yes | Rivets, flat metal, hat channel. | Clear | 5 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | South facia | ACM Subgirt Zee | 4 | 30 | [28 empty] | 60 | 20
24005 | GCDC Building 2/VA1.2 | 2025-12-03 | Obed Bermudez | We continue removing the top screen wall panel to remove the bottom, left the top one installed, and then placed the bottom panel under the platform for storage per HITT direction. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 2 | 10 | No |  | None | No |  |  | No |  | Corrugated / Screen wall | [22 empty] | 0
24039 | The Visionary | 2025-12-03 | Wilton lorenzo | Two crews installed the Z panels and insulation on top of the SE canopy, while two other crews installed the interior panels in the Level 3 courtyard. Another crew worked on details on the North side, including installing the missing reveal. Three workers resized three small panels, which took about three and a half hours. A delivery arrived, but it only included screws. I did not receive the flashing, so I can’t continue progressing with that part of the work. | Subcontractor | Carlos Silva | No |  | Yes | Sill flashing, flashing all color | Sunny | 14 | 10 | Yes | Tek screws | 4 boom lifts, 1 lull | No |  |  | Yes | East | ACM Insulation Subgirt Zee | 18 | 6 | [24 empty] | 200FT | 4 |  |  | 80FT | 4
24046 | UAB Biomedical Research and Psycholgy | 2025-12-03 | naza padron | Material was unloaded, and the truck had to be parked far from the job site and then brought the material from there because a crane was using the unloading area | Subcontractor | Wylie McDougall | No |  | No |  | sunny | 9 | 90 | Yes | 7 Crates of ACM | N/A | No |  |  | No |  | ACM Subgirt Zee Trim | 36 | 50 | [28 empty] | 40 | 8 |  |  |  |  | 120 | 18
24065 | QTS NAL2 DC2 | 2025-12-03 | Chad McCoy | So upon further inspection into the freedom wall. We have found that a total of 10 panels are missing from this install. They were damaged at mcdougal and never remade is what I was told. We installed as far as we could go with the acm on the freedom wall and now we are at a stand still. The diffuser was lowered in the vestibule. So soffit is being made to fit the openings. | Subcontractor | Joe Hoyle | Yes | Missing panels. Another trade having to lower the diffuser in the soffit area | Yes | Missing panels. Warmer weather | Cold. Snow still everywhere and is turning into ice. | 4 | 8 | No |  | 85 foot boom. 65 foot boom | No |  |  | Yes | The soffit on the inside of the vestibule is a constant layout. Per each panel due to cuts | ACM Flashing Subgirt Zee | 17 | 6 | [28 empty] | 130 | 1 | 20 | 1
24077 | IAD 667 TI | 2025-12-03 | Fredy veliz | Hand rail not removed yet ,traffic on the loading duck unloading materials ,other trades materials on the side walk no room for the boom lift to start on the upper wall | Subcontractor | Chris Buttrey | Yes | Clips missing holes ,traffic in the areas ,other trades materials no getting removed | Yes | Drill bits | Cold | 7 | 70 | No |  | 150 articulate boom lift ,65 straight boom lift ,10 k load | No |  |  | Yes | Elevevation sc1 section 1 to 6 | Louvre | [24 empty] | 20 clips | 70
25036 | TCAT Chattanooga | 2025-12-03 | Obed Bermudez | Crew continues working on the south elevation installing panels. We modified corner panel 206-2h01 to fit. | Subcontractor | Josh McPherson | No |  | Yes | Hat channel, rivets and flat metal. | Clear | 4 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | South facia | ACM | 6 | 40
24028 | CHI Memorial Hospital | 2025-12-02 | JC panels | Me made a full clean up getting all the material and tools out of site for the inspection | Subcontractor | Josh McPherson | No |  | Yes | Coping for canopy southwest , trims and flashing for south | Good | 6 | 48 | No |  |  | No |  |  | No |  | ACM | 5
24039 | The Visionary | 2025-12-02 | Wilton Lorenzo | Two crews installed panels, Z-girts, and insulation above the southeast canopy. Two other crews installed Z-girts and insulation in the patios on levels 1 and 4. Another crew installed panels below the canopy on level 1. When they finished, they helped the other crew prepare and install the remaining panels on the north wall. Also, three guys spent at least six hours making the panels smaller on the first row above the canopy because they were too tall. | Subcontractor | Carlos Silva | No |  | Yes | Tek screws 2" sill flashing, flashing all colors | Sunny | 16 | 10 | No |  | 4 boom lift, 1 lull, 1 sicssor lift | No |  |  | Yes | East | ACM Insulation Subgirt Zee | 14 | 6 | [24 empty] | 448FT | 6 |  |  | 510FT | 6
24046 | UAB Biomedical Research and Psycholgy | 2025-12-02 | naza padron | N/A | Subcontractor | Wylie McDougall | No |  | No |  | sunny | 9 | 90 | No |  | N/A | No |  |  | No |  | ACM Insulation Subgirt Zee Trim | 12 | 18 | [24 empty] | 960 | 36 |  |  | 540 | 28 |  |  |  |  | 30 | 8
24065 | QTS NAL2 DC2 | 2025-12-02 | Chad McCoy | We started the freedom wall panels today. But we have found that panels are missing. As of right now it’s 4 panels. But I will dig deeper into this tomorrow. We also tried to start the soffit in the vestibule. But the system depth to the diffuser is wrong bc of 5/8 sheeting. So we have to wait till in the morning to talk it over with gray. | Subcontractor | Joe Hoyle | Yes | Soffit in vestibule is not ready. | Yes | Missing panels for freedom wall | 6 inches of snow on the ground. Freezing | 4 | 9 | No |  | 85 foot boom. 65 foot boom | No |  |  | Yes | Freedom wall interior | ACM | 12 | 8
24077 | IAD 667 TI | 2025-12-02 | Fredy veliz | We have slow precess moving materials ,only 2 crates per trip ,and many truck unloading materials | Subcontractor | Chris Buttrey | Yes | Rain | No |  | Raining and snowing | 1 | 9 | No |  | 1 articulate boom lift 150 ,1 straight boom lift 65 and 10k load | No |  |  | No |  | Louvre | [24 empty] | 0 | 9
25036 | TCAT Chattanooga | 2025-12-02 | Obed Bermudez | Crew continues working on the south/west elevation installing z girt, hat channel, insulation and panels. | Subcontractor | Josh McPherson | No |  | Yes | Rivets, flat metal, hat channel. | Clear | 4 | 10 | No |  | Boom lift and forklift | No |  |  | No |  | ACM Hat Channel Insulation Subgirt Zee | 1 | [25 empty] | 160 | 15 |  |  | 80 | 10 |  |  | 60 | 10
24005 | GCDC Building 2/VA1.2 | 2025-12-01 | Obed Bermudez | We arrived at 6:00 am for safety orientation then started removing the top screen wall panel to remove the bottom, left the top one installed, and then placed the bottom panel under the platform for storage per HITT direction. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 3 | 11 | No |  | None | No |  |  | No |  | Corrugated / Screen wall | [22 empty] | 0 | 33
24018 | QTS-NAL1-DC1 | 2025-12-01 | Marvin Blanco | Working in the screenwall installing louvers blades and also protecting the roof for the metal shavings and screws | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 5 | 12 | No |  | boomlift and forklift | No |  |  | No |  | Corrugated / Screen wall | [22 empty] | We are Demo the corrugated | 60
24039 | The Visionary | 2025-12-01 | Wilton Lorenzo | Two crews installed Z-girt and insulation above the canopy, and another crew installed ACM panels on the last horizontal row of the 5th floor. An additional crew installed panels below the canopy on Level 1, and another crew installed Z-girt in the patio on Level 3. All of this work was completed on the East elevation. Additionally, I need to reduce the height of 17 panels from the first horizontal row above the canopy, as they are currently too tall and the panels drop excessively. The roof height is significantly elevated, which affects the panel alignment. | Subcontractor | Carlos Silva | No |  | Yes | Tek screws 2", sill flashing, flashing all color | Sunny | 14 | 10 | No |  | 4 boom lift, 1 lull | No |  |  | Yes | East | ACM Flashing Insulation Subgirt Zee | 16 panels | 6 | [24 empty] | 416 | 4 |  |  | 670FT | 8 | 20 | 2
24046 | UAB Biomedical Research and Psycholgy | 2025-12-01 | naza padron | dismantling crates and cleaning up 20 hours | Subcontractor | Wylie McDougall | No |  | No |  | cloudy | 9 | 90 | No |  | N/A | No |  |  | No |  | ACM Flashing Insulation Subgirt Zee Trim | 14 | 18 | [24 empty] | 384 | 10 |  |  | 540 | 20 | 30 | 2 |  |  | 30 | 2
24065 | QTS NAL2 DC2 | 2025-12-01 | Chad McCoy | We started in the outside of the destitute while the inside was install on the walls freedom wall panels where also brought over | Subcontractor | Joe Hoyle | No |  | No |  | Chilly. Over cast | 4 | 5.5 | No |  | 85 foot boom. 65 foot boom | No |  |  | Yes | Vestibule north elevtion outside | ACM Flashing Subgirt Zee | 8 | 2.5 | [28 empty] | 120 | 1 | 30 | 1
24068 | QTS NAL1 DC2 | 2025-12-01 | Marvin Blanco | Working in the screenwall installing vertical tubes for the louvers blades and also protecting the roof damaged | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 5 | 12 | No |  | boomlift and forklift | No |  |  | No |  | Louvre | [24 empty] | 11 tubes | 60
24077 | IAD 667 TI | 2025-12-01 | Fredy veliz | We have areas with no horizontal tube ,detail P/30 Shows beams but has tubes ,section A has hand rail that need to be remove ,section 1 upper wall need bigger boom lift | Subcontractor | Chris Buttrey | No |  | No |  | Cool | 7 | 63 | Yes | 2 boom lift and forklift | 150 articulate boom lift ,65 straight boom ,10k load | No |  |  | No |  | Louvre | [24 empty] | 0 | 63
25002 | Med Center Health | 2025-12-01 | Marvin Blanco | Working in the soffit with the acm panels my guys are asking for more clips for the acm panels | Subcontractor | Carlos Silva | No |  | Yes | Clips for the ACM panels | Cold | 4 | 11 | No |  | Boomlift | No |  |  | No |  | ACM | 8 | 44
25036 | TCAT Chattanooga | 2025-12-01 | Obed Bermudez | Crew continues working on the south elevation installing panels on the roof. | Subcontractor | Josh McPherson | No |  | Yes | Hat channel, rivets, flat metal, cover flashing. | Clear | 4 | 10 | No |  | Boom lifts and forklift. | No |  |  | Yes | Roof and south. | Single Skin | [6 empty] | 35 | 40
24028 | CHI Memorial Hospital | 2025-11-30 | JC panels | Start with the parallel on canopy | Subcontractor | Josh McPherson | No |  | Yes | Coping for screen wall the little piece that we have left to install, flashing for the south elevation barrel and the 2 pieces of trims that cover the joints on the barrel Morin that I have reported long time ago | Good | 7 | 70 | No |  |  | No |  |  | Yes | All | Trespa | [10 empty] | 40
24028 | CHI Memorial Hospital | 2025-11-28 | JC Panels | Canopy finished | Subcontractor | Josh McPherson | No |  | Yes | Parallel trims and flshing | Good | 6 | 60 | No |  |  | No |  |  | Yes | All | ACM Caulking | 8 | [19 empty] | 100
24039 | The Visionary | 2025-11-28 | Wilton Lorenzo | We finished installing the panels on the SE canopy. I need confirmation on whether the fascia panels will be installed as planned or if they will be modified. The building panels that go above the canopy do not have the same height dimension. I will send a screenshot to show the difference. One boom lift was installing Z-girt and insulation, and another boom lift was installing panels above the curtain wall only. Two guys were installing Z-girt in the patio. | Subcontractor | Carlos Silva | No |  | Yes | 2 inch tek screw, sill flashing, flashing all color | Sunny | 14 | 8 | No |  | 4 boom lift, 1 lull, | No |  |  | Yes | East | ACM Insulation Subgirt Zee | 10 | 4 | [24 empty] | 192FT | 2 |  |  | 710FT | 8
24039 | The Visionary | 2025-11-27 | Wilton Lorenzo | Two boom lifts installed panels on the SE canopy. I still need confirmation on whether we should proceed with installing the fascia panels. One boom lift continued installing z-girts on the east elevation, and another boom lift was installing panels. Additionally, two crew members installed z-girts on the patio LVL2 ceiling. One boom lift appears to have a damaged sensor, as the unit is moving very slowly and the basket is not rotating in any direction. | Subcontractor | Carlos Silva | No |  | Yes | Tek screw, sill flashing all color and flashing | Sunny | 14 | 10 | No |  | 4 boom lift, 1 lull, | No |  |  | Yes | East | ACM Flashing Insulation Subgirt Zee | 29 | 6 | [24 empty] | 260FT | 6 |  |  | 550FT | 6 | 20FT | 2
24028 | CHI Memorial Hospital | 2025-11-26 | JC panels | We finish the ACM on the 2nd canopy | Subcontractor | Josh McPherson | No |  | Yes | We need the flashing for south elevation 1st floor and the trims for the parallel panels on canopy | Good | 6 | 60 | No |  |  | No |  |  | Yes | All | ACM | 25
24039 | The Visionary | 2025-11-26 | Wilton lorenzo | Two boom lifts installed ACM panels, z-girt, and insulation on the SE canopy. Another boom lift installed z-girt, insulation, and flashing on the east side, and another boom lift was installing the panels. | Subcontractor | Carlos Silva | No |  | Yes | Sill flashing all colors | Sunny | 12 | 10 | No |  | 4 boom lift, 1 lull | No |  |  | Yes | East | ACM Flashing Insulation Subgirt Zee | 23 | 6 | [24 empty] | 600ft | 6 |  |  | 800FT | 6 | 60FT | 2
24039 | The Visionary | 2025-11-25 | Wilton lorenzo | Two boom lifts installed panels on the southeast canopy, and there was also a boom lift with panels on the second floor, just below the third floor. I had to move that boom lift towards the northeast, closer to the southeast, because I ran out of sill flashing. As a result, I left a gap of three panels since I don’t have the panel for the fourth floor and above. | Subcontractor | Carlos Silva | Yes | Sill flashing | Yes | Sill flashing, flashing silver metallic | Cloud | 12 | 10 | No |  | 4 boom lift | No |  |  | Yes | East | ACM Flashing Insulation Subgirt Zee | 22 papeles | 6 | [24 empty] | 384 | 6 |  |  | 610 | 6 | 80 | 2
24046 | UAB Biomedical Research and Psycholgy | 2025-11-25 | naza padron | N\A | Subcontractor | Wylie McDougall | No |  | No |  | sunny | 9 | 90 | No |  | N\A | No |  |  | No |  | ACM Corrugated / Screen wall Flashing Insulation Subgirt Zee Trim | 16 | 16 | [20 empty] | 40 | 8 |  |  | 734 | 28 |  |  | 460 | 20 | 30 | 6 |  |  | 160 | 12
24046 | UAB Biomedical Research and Psycholgy | 2025-11-25 | zarur n padron | No work was done due to rain and lightning all day long | Subcontractor | Wylie McDougall | No |  | No |  | rainy | 9 | 00 | No |  | N\A | No |  |  | No |  | Insulation | [26 empty] | 0000 | 0000
25002 | Med Center Health | 2025-11-25 | Marvin Blanco | Working on installing ACM panels in the tower and also putting insulation in the soffit because we don't have any revels trims for the joints | Subcontractor | Carlos Silva | Yes | Reveals for the soffit flat straps 3" screws | Yes | Reveals flat straps and 3" screws | Good condition | 7 | 11 | No |  | Boomlift | No |  |  | No |  | ACM | 13 | 77
25036 | TCAT Chattanooga | 2025-11-25 | Obed Bermudez | No work due to inclement weather. | Subcontractor | Josh McPherson | No |  | Yes | Flat metal, rivets, hat channel. | Rainy day | 1 | 0 | No |  | Boom lift and forklift | No |  |  | No |  | Subgirt Zee | [30 empty] | 0
24028 | CHI Memorial Hospital | 2025-11-24 | JC Panels | Start southwest canopy | Subcontractor | Josh McPherson | No |  | No |  | Good | 6 | 66 | No |  |  | No |  |  | Yes | All | ACM | 26
24039 | The Visionary | 2025-11-24 | Wilton Lorenzo | Two boom lifts installed panels on the East elevation, and two other boom lifts installed panels on the SE canopy because the panels are very large. A crew also installed Z-girts in the level 3 patio. | Subcontractor | Carlos Silva | Yes | It rained a little | Yes | Flat strap, tek screws 2", sill flashing, flashing, coping for patios | Rainy | 14 | 10 | No |  | 4 boom lift, 1 lull, | No |  |  | Yes | East | ACM Flashing Insulation Soffit Subgirt Zee | 20 | 8 | [24 empty] | 128 | 2 |  |  | 400ft | 4 | 120FT | 4
25036 | TCAT Chattanooga | 2025-11-24 | Obed Bermudez | We began doing layout on the roof wall, installing Z girt and panels. | Subcontractor | Josh McPherson | Yes | Waterproof and concrete guys. | Yes | Rivets, flat metal, hat channel, flashing goes over brick. | Clear | 5 | 10 | No |  | Boom lift and forklift. | No |  |  | Yes | South on roof. | Single Skin Subgirt Zee | [6 empty] | 7 | 15 | [22 empty] | 420 | 35
24018 | QTS-NAL1-DC1 | 2025-11-23 | Marvin Blanco | Working in the roof with the screenwall everything for know is working really well | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 5 | 12 | No |  | Scaffolding , boomlift and forklift | No |  |  | No |  | Louvre | [24 empty] | 40 | 60
24068 | QTS NAL1 DC2 | 2025-11-23 | Marvin Blanco | Working in the roof with the screenwall | Subcontractor | Joe Hoyle | No |  | No |  | Cold | 5 | 12 | No |  | Scaffolding , boomlift and forklift | No |  |  | No |  | Louvre | [24 empty] | 38 | 60
25002 | Med Center Health | 2025-11-23 | Marvin Blanco | Working in taking off Zs and insulation this is a change order for McDougall it's going to take 4 day to remove Zs and insulation and also for install back to the wall because we never received a notification of this change also we're having issues with material in the job site we're not receiving what we need for continue working in the soffit there is no revils in the job site no flats strapping I have to send my guys to the shop to get clips because the PM doesn't send enough clips | Subcontractor | Carlos Silva | Yes | Revils for the soffit flat strapping silicone | Yes | Revils, flat straps and silicone | Good condition | 4 | 11 | No |  | Boomlift | No |  |  | No |  | ACM | 9 | 44
24039 | The Visionary | 2025-11-22 | Wilton lorenzo | We install ACM panels, flashing, z girt and insulation on the east elevation and on the SE canopy | Subcontractor | Carlos Silva | No |  | No |  | Sunny | 12 | 8 | No |  | 4 boom lift, 1 lull, and 1 sicssor lift | No |  |  | Yes | East | ACM Flashing Insulation Subgirt Zee | 25panels | 6 | [24 empty] | 300ft | 4 |  |  | 100 ft | 2 | 60ft | 2
24065 | QTS NAL2 DC2 | 2025-11-22 | Chad McCoy | Both corners on eye brow have to be complete rebuilds | Subcontractor | Joe Hoyle | Yes | Panel fab | No |  | Clear chilly | 7 | 10 | No |  | 85 foot boom. 65 foot boom | No |  |  | Yes | Lay out in eyebrow is on going | ACM | 25 | 10
25036 | TCAT Chattanooga | 2025-11-22 | Obed Bermudez | Crew continues working on the north/northwest elevation installing flashing insulation, and Z-girt. | Subcontractor | Josh McPherson | Yes | Waiting on waterproofing guy. | No |  | Clear | 5 | 5 | No |  | Boom lift and forklift | No |  |  | Yes | South | Flashing Insulation Subgirt Zee | [26 empty] | 180 | 12 |  |  | 150 | 12 | 20 | 1
24028 | CHI Memorial Hospital | 2025-11-21 | JC Panels | Start canopy installation | Subcontractor | Josh McPherson | No |  | Yes | Flashing for south. Parallel trims | Good | 6 | 60 | No |  |  | No |  |  | Yes | Canopy | ACM | 19
24039 | The Visionary | 2025-11-21 | Wilton lorenzo | Three boom lifts installed Z-girt, insulation, and panels on the east side, and another boom lift installed insulation and panels on the southeast canopy. | Subcontractor | Carlos Silva | No |  | No |  | Sunny | 12 | 10 | No |  | 4 boom lift, 1 siccsor lift, | No |  |  | Yes | East | ACM Insulation Subgirt Zee | 21 | 8 | [24 empty] | 600 ft | 8 |  |  | 510 ft | 8
24046 | UAB Biomedical Research and Psycholgy | 2025-11-21 | naza padron | N\A | Subcontractor | Wylie McDougall | Yes | penetration in South side elevation, GC was informed about it | No |  | sunny | 9 | 90 | No |  | N\A | No |  |  | No |  | ACM Flashing Insulation Subgirt Zee Trim | 19 | 28 | [24 empty] | 512 | 20 |  |  | 440 | 20 | 50 | 6 |  |  | 200 | 16
24065 | QTS NAL2 DC2 | 2025-11-21 | Chad McCoy | Chilly night | Subcontractor | Joe Hoyle | Yes | Panel fab | No |  | Cold | 7 | 10 | No |  | 85 foot boom. 65 foot boom | No |  |  | Yes | Continuation of eyebrow builds | ACM | 30 | 10
25036 | TCAT Chattanooga | 2025-11-21 | Obed Bermudez | We started moving material to the south elevation from the storage area and started doing layouts, then installing flashing and Z-girt. | Subcontractor | Josh McPherson | Yes | Waiting for waterproofing to be done on flashing. | No |  | Clear | 5 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | South | Flashing Subgirt Zee | [30 empty] | 140 | 30 | 60 | 20
24039 | The Visionary | 2025-11-20 | Wilton LorenO | We installed z girt on the SE canopy, some panels above level 3, and panels inside patio lvl 2. It rained all day, so we couldn’t work outside. | Subcontractor | Carlos Silva | Yes | It Rained all day | No |  | Rainy | 12 | 10 | No |  | 4 boom lifts, 1 lull and 1 sicssor lift | No |  |  | Yes | East | ACM Insulation Subgirt Zee | 16 | 6 | [24 empty] | 80FT | 2 |  |  | 510 | 4
24065 | QTS NAL2 DC2 | 2025-11-20 | Chad mccoy | On the eye brow we are making the soffits for the face panels we did yesterday, Every 4 panels the panel with shrinks 5/8. We eventually got to where we could use the older panels. But one side had to be modified to reflect the slant in the curtain wall. And then past that all panel continued to lose 5/8 over 4 panels left to right. | Subcontractor | Joe Hoyle | Yes | Panel fab. On the loading dock. The is a conduit that has to be removed. It’s 1 inch thick and it is equal to panel face. This is hindering how we can attach the panels and the joint lines | No |  | Clear | 7 | 1 team 11. 2 team 9 | No |  | 85 foot boom. 65 foot boom | No |  |  | Yes | Layout has to be done on every panel to match face panels and for the taper. | ACM Insulation Subgirt Zee | 23 | 10 | [24 empty] | 1700 | 9 |  |  | 20 | 0.5
24069 | TCAT Pulaski | 2025-11-20 | JC Panels | We finish the change order of north and south trims | Subcontractor | Chris Buttrey | No |  | Yes | Interior panels | Good | 5 | 50 | No |  |  | No |  |  | Yes | All | Trim | [36 empty] | 100
25036 | TCAT Chattanooga | 2025-11-20 | Obed Bermudez | Crew continues working on the south/NW elevation, installing flashing and insulation. | Subcontractor | Josh McPherson | No |  | No |  | Rainy | 5 | 6 | No |  | Boom lift and forklift | No |  |  | Yes | South | Flashing Insulation | [26 empty] | 384 | 15 |  |  |  |  | 110 | 15
24018 | QTS-NAL1-DC1 | 2025-11-19 | Marvin Blanco | Today we have a fall protection meeting in the morning because yesterday we have a issues with my guys but thanks to JWM and Adam make everything works | Subcontractor | Joe Hoyle | No |  | No |  | Good condition | 5 | 12 | No |  | Scaffolding , boomlift and forklift | Yes | No | No | No |  | Louvre | [24 empty] | 20 | 48
24028 | CHI Memorial Hospital | 2025-11-19 | JC Panels | Doing some punch and installing the coping of the canopy | Subcontractor | Josh McPherson | No |  | Yes | Flashing for south | Good | 6 | 60 | No |  |  | No |  |  | Yes | All | ACM Caulking | 15 | [19 empty] | 100
24039 | The Visionary | 2025-11-19 | Wilton lorenzo | We installed panels on the east, on the 4th floor. We used two boom lifts to install those panels because they are very high. Another boom lift installed Z girt, insulation, panels, and flashing on level 3, and another crew laid out the southeast canopy and installed some Zs. | Subcontractor | Carlos Silva | No |  | No |  | Sunny | 12 | 10 | No |  | 4 boom lift, 1 lull and 1 sicssor lift | No |  |  | Yes | East | ACM Flashing Insulation Subgirt Zee | 17 | 6 | [24 empty] | 320 | 4 |  |  | 360 | 4 | 100 | 2
24046 | UAB Biomedical Research and Psycholgy | 2025-11-19 | Naza Padron | We unloaded material from 5:30pm to 6:30pm 7 Crates | Subcontractor | Wylie McDougall | No |  | No |  | sunny | 9 | 108 | Yes | 7 Crates with ACM panels 4 hour spend total | not equipment owned at this project | No |  |  | No |  | ACM Flashing Insulation Subgirt Zee Trim | 12 | 20 | [24 empty] | 2, 368 | 38 |  |  | 660 | 24 | 150 | 12 |  |  | 90 | 10 | [6 empty] | 2025-11-19 | 100% | 1d
24046 | UAB Biomedical Research and Psycholgy | 2025-11-19 | naza padron | N\A | Subcontractor | Wylie McDougall | No |  | No |  | sunny | 9 | 90 | No |  | N\A | No |  |  | No |  | ACM Flashing Insulation Subgirt Zee Trim | 20 | 28 | [24 empty] | 380 | 12 |  |  | 720 | 26 | 130 | 8 |  |  | 200 | 16 | [6 empty] | 2025-11-19 | 100% | 1d
24046 | UAB Biomedical Research and Psycholgy | 2025-11-19 | Naza padron | N/A Today | Subcontractor | Wylie McDougall | No |  | No |  | sunny | 9 | 90 | No |  | We don't have any equipment being rented by McDougall for this project | No |  |  | No |  | ACM Flashing Insulation Subgirt Zee | 8 | 12 | [24 empty] | 1408 | 32 |  |  | 840 | 34 | 120 | 1246 | [10 empty] | 2025-11-19 |  | 1d
24065 | QTS NAL2 DC2 | 2025-11-19 | Chad mccoy | Continuation of the front of house eye brow. Acm panels are being made and modified and flipped to match up with joints as close as we can without wasting material. We are having to have additional framing to furr out the face of the eye brow bc of the joint misalign ment to the wing wall | Subcontractor | Joe Hoyle | Yes | Panel layout for dimensions. Panel fab of new panels. And we are going thru all panels to pull dimensions to find panels that are close to what we need | No |  | Clear chilly | 7 | 9 | No |  | 85 foot boom. 65 foot boom | No |  |  | Yes | Layout is continuous with the eye brow | ACM Hat Channel Subgirt Zee | 22 | 8 | [28 empty] | 975 | 7 |  |  | 50 | 1
24068 | QTS NAL1 DC2 | 2025-11-19 | Marvin Blanco | Working in the louvers blades with the scaffolding but we need a couple of yellow tags for the scaffolding because WT is saying the green Tags doesn't work on this job , | Subcontractor | Joe Hoyle | No |  | No |  | Good condition | 6 | 12 | No |  | Scaffolding , boomlift and forklift | No |  |  | No |  | Louvre | [24 empty] | 20 | 48
24079 | Nashville Youth Campus | 2025-11-19 | Obed Bermudez | We went back to reinstall the z girt, insulation and panels that were previously removed. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 2 | 10 | No |  |  | No |  |  | No |  | ACM | 4
25002 | Med Center Health | 2025-11-19 | Marvin Blanco | Working in the ACM panels and also taking corrugated panels to the roof | Subcontractor | Carlos Silva | No |  | Yes | Silicone for the soffit and also for the vertical joints in the columns | Good condition | 4 | 11 | No |  | Boomlift | No |  |  | No |  | ACM | 8 | 44
25036 | TCAT Chattanooga | 2025-11-19 | Obed Bermudez | Crew continues working on the south/NW elevation, installing z girt, and insulation. We received two trucks of panels. | Subcontractor | Josh McPherson | No |  | No |  | Clear | 5 | 10 | Yes | Acm/flush panels/flashing | Boom lift and forklift | No |  |  | Yes | South | Insulation Subgirt Zee | [26 empty] | 512 | 30 |  |  | 100 | 20
24039 | The Visionary | 2025-11-18 | Wilton lorenzo | One boom lift finished installing panels above the window on the north side and moved toward the east. The other two boom lifts were installing panels on the east. Four more guys arrived, but the extra boom won’t be here until tomorrow, so I assigned them to install panels on the east side below the canopy on level 1. Tomorrow, I’m going to use the boom lifts to install the panels in the last patio because they’re very high. | Subcontractor | Carlos Silva | Yes | Boom lift doesn't arrive | No |  | Sunny | 14 | 10 | No |  | 3 boom, 1 lull | No |  |  | Yes | North and east | ACM Flashing Insulation Subgirt Zee | 25 | 6 | [24 empty] | 172ft | 6 |  |  | 270 | 6 | 50ft | 2
24065 | QTS NAL2 DC2 | 2025-11-18 | Chad McCoy | Heavy rain and storms | Subcontractor | Joe Hoyle | Yes | Weather | No |  | Heavy rain | 4 | 2.5 | No |  | 85 foot boom. 65 foot boom | No |  |  | No |  | ACM | 0 | 0
24079 | Nashville Youth Campus | 2025-11-18 | Obed Bermudez | We travel to Nyce to remove insulation and we had to cut z girt to remove it so they could redo the waterproofing. | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 2 | 10 | No |  |  | No |  |  | No |  | ACM | 0
25036 | TCAT Chattanooga | 2025-11-18 | Obed Bermudez | Crew continues working on the south elevation, installing z girt, and flashing. | Subcontractor | Josh McPherson | No |  | No |  | Clear | 5 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | South | Flashing Subgirt Zee | [30 empty] | 200 | 30 | 180 | 20
24018 | QTS-NAL1-DC1 | 2025-11-17 | Marvin Blanco | Working in the screenwall with the louvers blades installing angles | Subcontractor | Joe Hoyle | No |  | No |  | Good condition | 6 | 12 | No |  | Boomlift and forklift | No |  |  | No |  | Louvre | [24 empty] | 20 | 72
24028 | CHI Memorial Hospital | 2025-11-17 | JC Panels | We are getting some details and punch’s from McCarthy.. there are some punch that are out of our scope | Subcontractor | Josh McPherson | No |  | Yes | Flashing for south and canopy panels | Good | 6 | 60 | No |  |  | No |  |  | Yes | All | Caulking | [20 empty] | 100
24039 | The Visionary | 2025-11-17 | Wilton Lorenzo | One crew installed panels, Z-girts, insulation, and flashing on the north side above the window. Another crew installed panels on the east side, level 3. A third crew was also installing Z on the east side, but the machine broke down again, so they had to stop working in that area. I’m also waiting for a response regarding the east side where the panel is 2” short. What I could do is give 2 1/4” to each joint to recover those two inches. I also need the boom tomorrow because four people are coming: two installers and two guys who will be locating and prepping panels. They will be working on the SE canopy. | Subcontractor | Carlos Silva | Yes | Boom broke down | No |  | Sunny | 9 | 10 | No |  | 3 boom, 1 lull, 1 scissor lift | No |  |  | Yes | North and east | ACM Flashing Insulation Subgirt Zee | 12 | 6 | [24 empty] | 336gy | 6 |  |  | 350ft | 6 | 60fy | 6
24065 | QTS NAL2 DC2 | 2025-11-17 | Chad McCoy | No matter what. We are going to be off on certain joints to window joints bc we can’t stretch these panels fatter than 5/8-3/4 and it look good. I have to use a lot of panels that are originally 4’ 11 1/2” and a lot of these windows center to center are 4’ 11 7/8”. We are stretching and dabbing all we can to make these areas look good and work great. Out of the 11 panels installed 6 were complete field fab. All eleven had to have excursions moved. The other 5 had to have one to two side cut and routed. To line up do to panels already installed | Subcontractor | Joe Hoyle | Yes | Panel fab | No |  | Clear chilly | 4 | 6.5 | No |  | 85 foot boom. 65 foot boom | No |  |  | Yes | Lay out is continuous on the eye brow to make sure we don’t mess up on field fab. | ACM | 11 | 6
24068 | QTS NAL1 DC2 | 2025-11-17 | Marvin Blanco | Working in the screenwall installing angles for the louvers blades and cleaning everything every single minute | Subcontractor | Joe Hoyle | No |  | No |  | Good condition | 5 | 12 | No |  | Boomlift and forklift | No |  |  | No |  | Louvre | [24 empty] | 20 | 60
24069 | TCAT Pulaski | 2025-11-17 | JC panels | Done with last delivery .. we will have to demon again this is our 3rd demon on this project | Subcontractor | Chris Buttrey | No |  | Yes | Interior panels | Good | 5 | 50 | No |  |  | No |  |  | Yes | All | Genesis | [14 empty] | 15
25022 | Vantage VA15 | 2025-11-17 | Marvin Blanco | Working in the top canopy installing ACM panels in the top canopy another company damaged one panels in the face | Subcontractor | Thomas Mooers | No |  | Yes | Tornillos de 3" Lamina flet Shins Clips Silicon Insulation para la zeta de 3" Terminations and silicone | Good condition | 4 | 11 | No |  | Boomlift | No |  |  | No |  | ACM | 13 | 44
25036 | TCAT Chattanooga | 2025-11-17 | Obed Bermudez | Crew continues working on the south elevation, installing hat channel. | Subcontractor | Josh McPherson | No |  | No |  | Clear | 5 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | South | Hat Channel | [34 empty] | 600 | 50
24039 | The Visionary | 2025-11-15 | Wilton lorenzo | We installed panels on the North above the curtain wall and on the East, in the patios, and also on the area where the wall slopes to the left. I laid out all those panels and the last one ends up with a 4” joint. Should one of those panels have been bigger? I decided not to install them and will wait for your response on Monday, and I moved the guys to install flashing and Z in the meantime | Subcontractor | Carlos Silva | Yes | Made the layout on the east and panels doesn't fit properly 2 inch short | No |  | Sunny | 10 | 8 | No |  | 3 boom lift, 1 lull | No |  |  | Yes | North and east | ACM | 12 | 6
25036 | TCAT Chattanooga | 2025-11-15 | Obed Bermudez | Crew continues working on the south/east/west elevation, installing z girt, flashing and insulation. | Subcontractor | Josh McPherson | No |  | No |  | Clear | 5 | 8 | No |  | Boom lift and forklift | No |  |  | Yes | South | Flashing Insulation Subgirt Zee | [26 empty] | 356 | 20 |  |  | 350 | 10 | 40 | 10
24018 | QTS-NAL1-DC1 | 2025-11-14 | Marvin Blanco | Working in the lower roof with the louvers blades cleaning everything up | Subcontractor | Joe Hoyle | No |  | No |  | Good condition | 11 | 12 | No |  | Scaffolding , boomlift and forklift | No |  |  | No |  | Louvre | [24 empty] | 80 | 132
24039 | The Visionary | 2025-11-14 | Wilton lorenzo | We installed panels on the north and east elevations, but a boom lift broke down and one crew had to stop. Later a delivery arrived and we unloaded the material. | Subcontractor | Carlos Silva | Yes | One boom lift was broke down and we had a Delivery | No |  | Sunnny | 10 | 10 | Yes | Acm | 3 boom lift and 1 lull | No |  |  | Yes | East and south | ACM | 14 panels | 4
24046 | UAB Biomedical Research and Psycholgy | 2025-11-14 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s, flashing and Insulation. 3 guys unloaded delivery. It took each guy 3 hours | Subcontractor | Wylie McDougall | No |  | No |  | Sunny | 9 | 90 | Yes | 2 crates of ACM and 18 bundles of Insulation | 1- swingstage and 2- boomlifts | No |  |  | Yes | South Elevation 202 | ACM Flashing Insulation Subgirt Zee | 6 | 21 | [24 empty] | 736 | 9 |  |  | 740 | 42 | 100 | 9
25002 | Med Center Health | 2025-11-14 | Marvin Blanco | Working in the top canopy and one guy from another company damaged a panel the GC already knows what company | Subcontractor | Carlos Silva | No |  | Yes | Tornillos de 3" Lamina flet Shins Clips Silicon Insulation para la zeta de 3" Terminations and silicone | Good condition | 4 | 11 | Yes | Perforated panels for the roof | Boomlift | No |  |  | No |  | ACM | 9 | 11
25007 | QTS ATL2 DC10 | 2025-11-14 | Marvin Blanco | Everything we have in the job site was install we don't have anything else but we have issues in the ground louvers blades in the sides it doesn't have the plate to cover the blades the GC is going to be asking if McDougall can order ends plates will be awesome that way we don't be in trouble the boomlift are able to be canceled please | Subcontractor | Nick Akins | Yes | Louvers blades | Yes | Louvers blades | Good condition | 4 | 12 | No |  | Boomlift | No |  |  | No |  | Louvre | [24 empty] | 20 | 48
25036 | TCAT Chattanooga | 2025-11-14 | Oned Bermudez | Crew continues working on the south/east/west elevation, installing z girt, insulation and flashing. | Subcontractor | Josh McPherson | No |  | No |  | Clear | 5 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | South | Flashing Insulation Subgirt Zee | [26 empty] | 512 | 30 |  |  | 140 | 15 | 50 | 5
24028 | CHI Memorial Hospital | 2025-11-13 | JC Panels | finish the big canopy on north | Subcontractor | Josh McPherson | No |  | No |  | Good | 5 | 50 | No |  |  | No |  |  | Yes | All | ACM Caulking | 6 | [19 empty] | 100
24039 | The Visionary | 2025-11-13 | Wilton lorenzo | We installed all the panels on the north wall, and I can’t continue with the panels next to the curtain wall because I need to install the vertical flashing first. We also installed panels on the east side | Subcontractor | Carlos Silva | No |  | Yes | Vertical Trim next to north curtain wall detail #11 page 503 | Sunny | 10 | 10 | No |  | 3 boom lift, 1 lull, 1 sicssor lift | No |  |  | Yes | North and east | ACM | 19 | 6
24046 | UAB Biomedical Research and Psycholgy | 2025-11-13 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s, flashing and Insulation. | Subcontractor | Wylie McDougall | Yes | 3 guys held up 3 hours each due to waiting on Waterproofers. | No |  | Sunny | 9 | 90 | No |  | 2-swingstages and 1-boomlift | No |  |  | No |  | ACM Flashing Insulation Subgirt Zee | 12 | 36 | [24 empty] | 512 | 9 |  |  | 960 | 36 | 40 | 3
24065 | QTS NAL2 DC2 | 2025-11-13 | Chad McCoy | We are continuing on the eyebrow and soffit. Every panel has to either be fully made or modified in a certain way. Almost all the panels have to have excursions moved. And all eye brow panels have to be flipped upside down | Subcontractor | Joe Hoyle | Yes | Panel modifications | Yes | Patience | Clear chilly | 3 | 8 | No |  | 85 foot boom. 65 foot boom | No |  |  | Yes | Layout is continuous around the hole eye brow. | ACM Hat Channel | 13 | 7 | [32 empty] | 40 | 1
24069 | TCAT Pulaski | 2025-11-13 | JC Panels | no issues | Subcontractor | Chris Buttrey | No |  | No |  | Good | 5 | 50 | Yes | Panels |  | No |  |  | Yes | All | Genesis | [14 empty] | 34
25036 | TCAT Chattanooga | 2025-11-13 | Obed Bermudez | Crew continues working on the south/east/west elevation, installing z girt and insulation. | Subcontractor | Josh McPherson | No |  | Yes | Insulation pins and washer clips | Clear | 5 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | South | Insulation Subgirt Zee | [26 empty] | 952 | 30 |  |  | 575 | 20
24028 | CHI Memorial Hospital | 2025-11-12 | JC Panels | Getting details done. Field fabrication panels on capony on north | Subcontractor | Josh McPherson | No |  | No |  | Good | 7 | 70 | No |  |  | No |  |  | Yes | All | ACM Trespa | 8 | [9 empty] | 12
24039 | The Visionary | 2025-11-12 | Wilton Lorenzo | Two crews installed panels on the north elevation, and one crew installed panels on the east elevation. The rest of the team looked for and prepared panels with clips to have them ready for the installers. | Subcontractor | Carlos Silva | No |  | No |  | Sunny | 10 | 10 | No |  | 3 boom lift, 1 lull and 1 scissor lift | No |  |  | Yes | North and east | ACM | 30 Acm panels | 6
24046 | UAB Biomedical Research and Psycholgy | 2025-11-12 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s and Insulation. | Subcontractor | Wylie McDougall | Yes | Fabricating 5 of the installed panels. | Yes | Reveal and Insulation | Sunny | 10 | 100 | No |  | 2- swing stages and 1-boomlift | No |  |  | No |  | ACM Insulation Subgirt Zee | 16 | 55 | [24 empty] | 192 | 3 |  |  | 990 | 42
24065 | QTS NAL2 DC2 | 2025-11-12 | Chad McCoy | We started with the eyebrow. All of the eyebrow panels have to be turned upside down and installed upside down so the panels joints line up with the wing wall panels. We also have to install hat channel bc the structure is to small and out of square | Subcontractor | Joe Hoyle | Yes | Modifying panels and installing framing to make panels | Yes | Monsters and cheeseburgers | Cold and winds over 25 | 3 | 8 | No |  | 85 foot boom. 65 foot boom | No |  |  | Yes | 47 on 218. Eyebrow panels have to be plug and played and made to fit windows. | ACM Hat Channel | 8 | 7 | [32 empty] | 300 | 1.5
25036 | TCAT Chattanooga | 2025-11-12 | Obed Bermudez | Crew continues working on the south elevation, installing z girt and insulation. | Subcontractor | Josh McPherson | No |  | No |  | Clear | 5 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | South | Insulation Subgirt Zee | [26 empty] | 592 | 20 |  |  | 650 | 30
24039 | The Visionary | 2025-11-11 | Wilton lorenzo | We installed panels on the north elevation and also on the east, above the level 1 patio. | Subcontractor | Carlos Silva | No |  | No |  | Sunny | 10 | 10 | No |  | 3 boom lift, 1 scissor lift and 1 lull | No |  |  | Yes | North and east | ACM | 17 | 6
24046 | UAB Biomedical Research and Psycholgy | 2025-11-11 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s, insulation and flashing. | Subcontractor | Wylie McDougall | No |  | No |  | Sunny | 10 | 100 | No |  | 1-scaffold, 1-boomlift and 1-swing stage | No |  |  | No |  | ACM Flashing Insulation Subgirt Zee | 19 | 50 | [24 empty] | 192 | 4 |  |  | 1360 | 44 | 60 | 2
24065 | QTS NAL2 DC2 | 2025-11-11 | Chad McCoy | We started installing the last window on the east side. But the spacing for the panels between the windows and the other panels are different than the rest of the windows. So we wrapped up and moved to the eye brow. But in the first panel we found the the soffit joint doesn’t line up with the wing wall panels. Joint. So we wrapped up and called it till answers were gave | Subcontractor | Joe Hoyle | Yes | Framing and panels that were reconfigured | Yes | Answers on wing wall | Cold and cloudy | 3 | 5.5 | No |  | 65 foot boom and 85 foot boom | No |  |  | No |  | ACM | 0 | 5.5
25007 | QTS ATL2 DC10 | 2025-11-11 | Marvin Blanco | Finishing all the louvers blades in the ground | Subcontractor | Nick Akins | No |  | No |  | Cold | 4 | 12 | No |  | Boomlift | No |  |  | No |  | Louvre | [24 empty] | 20 | 48
25036 | TCAT Chattanooga | 2025-11-11 | Obed Bermudez | Crew continues working on the North elevation, installing | Subcontractor | Josh McPherson | Yes | GC stopped our work on the north elevation due to the masons working in the area, so we switched to the south elevation. | No |  | Clear | 4 | 10 | Yes | Flashing and z girt | Boom lift and forklift | No |  |  | Yes | North | Insulation Subgirt Zee | [26 empty] | 256 | 20 |  |  | 240 | 20
24028 | CHI Memorial Hospital | 2025-11-10 | JC Panels | A lot of panels fabrications .. everything have been reported to Luke… the columns are done | Subcontractor | Josh McPherson | No |  | No |  | Good | 6 | 60 | No |  |  | No |  |  | Yes | All | ACM | 16
24039 | The Visionary | 2025-11-10 | Wilton Lorenzo | We screwed and shimmed the vertical Zs on the north side and installed some panels. We also installed the last panel on the northeast corner and covered the northeast patio column with panels. We installed Zs and insulation as well. | Subcontractor | Carlos Silva | No |  | No |  | Sunny | 10 | 10 | No |  | 3 boom lift, 1 lull, 1 scissor lift | No |  |  | Yes | NORTH AND EAST | ACM | 13 | 6
24046 | UAB Biomedical Research and Psycholgy | 2025-11-10 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s and Insulation. | Subcontractor | Wylie McDougall | No |  | No |  | Sunny | 9 | 63 | No |  | 1 scaffold and 1-boomlift | No |  |  | No |  | ACM Insulation Subgirt Zee | 16 | 20 | [24 empty] | 256 | 5 |  |  | 350 | 38
24065 | QTS NAL2 DC2 | 2025-11-10 | Chad McCoy | Continuation on east elevation | Subcontractor | Joe Hoyle | Yes | Weather. | No |  | Cold snow | 3 | 7 | No |  | 85 foot boom. 65 foot boom | No |  |  | No |  | ACM Flashing | 14 | 5 | [30 empty] | 160 | 2
24068 | QTS NAL1 DC2 | 2025-11-10 | Marvin Blanco | Working in the roof with the louvers blades for now everything is working perfectly | Subcontractor | Joe Hoyle | No |  | No |  | Snowing | 8 | 12 | No |  | Boomlift scaffolding and forklift | No |  |  | No |  | Louvre | [24 empty] | 26 | 96
25007 | QTS ATL2 DC10 | 2025-11-10 | Marvin Blanco | Working in the ground louvers blades and also waiting for clips angles for the roof | Subcontractor | Nick Akins | Yes | Angles for the louvers blades in the roof | Yes | Angles for the louvers blades in the roof | Cold | 4 | 13 | No |  | Boomlift scaffolding | No |  |  | No |  | Louvre | [24 empty] | 20 | 52
25022 | Vantage VA15 | 2025-11-10 | Marvin Blanco | We have a little issue in the canopy we need 1¼" Z for attaching the top panel | Subcontractor | Thomas Mooers | No |  | Yes | Flashing and clips for the panels | Snowing | 4 | 12 | No |  | Boomlift | No |  |  | No |  | ACM | 9 | 48
25036 | TCAT Chattanooga | 2025-11-10 | Obed Bermudez | Crew continues working on the North elevation, installing insulation. | Subcontractor | Josh McPherson | No |  | No |  | Clear | 4 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | North. | Insulation | [26 empty] | 192 | 40
24039 | The Visionary | 2025-11-08 | Wilton lorenzo | We install Acm panels on the NE corner and vertical z and insulation on north | Subcontractor | Carlos Silva | No |  | No |  | Sunny | 10 | 8 | No |  | 3 boom lift, 1 lull and 1 scissor lift | No |  |  | Yes | North | ACM Insulation Subgirt Zee | 4 | 3 | [24 empty] | 300FT | 2 |  |  | 336 | 2
25036 | TCAT Chattanooga | 2025-11-08 | Obed Bermudez | We continue working on the north elevation installing z girt. | Subcontractor | Josh McPherson | No |  | No |  | Clear | 4 | 8 | No |  | Boom lifts and forklift | No |  |  | Yes | North elevation | Subgirt Zee | [30 empty] | 300 | 32
24039 | The Visionary | 2025-11-07 | Wilton Lorenzo | We installed the panels at the northeast corner and also a row of panels on the north side going upward. We also installed insulation and Z girts. | Subcontractor | Carlos Silva | No |  | No |  | Sunny | 10 | 11 | Yes | Insulation | 3 boom lift, 1 scissor lift and 1 lull | No |  |  | Yes | North | ACM | 9 | 4
24045 | TMMMS Childcare | 2025-11-07 | Kevin Morris | Fabbed panel and installed walked around and did a final check before walking with gc Everything was good except 2 pieces of trim that was missing and some miss aligned panelson the roof. Cleaned up parked boom lift bottom of hill | JWMCD Crew | Chris Buttrey | No |  | No |  | 70's | 2 | 9 | No |  | 65 boom | No |  |  | No |  | ACM | 1 | 4
24046 | UAB Biomedical Research and Psycholgy | 2025-11-07 | Zarur Nazario Padron Jr | Installing pieces of Metal, moving our ropes on to the other swing stages, installed Zee’s, flashing and moving materials and throwing away crates. | Subcontractor | Wylie McDougall | No |  | No |  | Sunny | 4 | 28 | No |  | 1 swing stage and 1 scaffold | No |  |  | No |  | Flashing Subgirt Zee | [30 empty] | 40 | 4 | 70 | 8
24065 | QTS NAL2 DC2 | 2025-11-07 | Chad McCoy | Rework was done in the stair tower to finish the white acm and finish the silver. I’m waiting on flat stock silver to do expansion joint | Subcontractor | Joe Hoyle | Yes | Rain and lightning, Making panels and reverse installing acm around door | Yes | Loading dock. Flat stock. | Rain | 3 | 6 | No |  | 85 foot boom. 65 foot boom | No |  |  | Yes | Lay out had to be done around the door headers for fabrication of this oanel | ACM Subgirt Zee | 12 | 5 | [28 empty] | 50 | 0.5
24089 | BSU Innovation Center | 2025-11-07 | Obed Bermudez | We continue working on the west elevation and roof, installing strongirt, flashing, insulation, and panels. We also cleaned up all the work areas, then moved all the material to the yard and tied it down. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 4 | 13 | No |  | Boom lift and forklift. | No |  |  | Yes | West and roof. | Flashing Insulation Single Skin Subgirt Zee | [6 empty] | 78 | 24 | [18 empty] | 192 | 10 |  |  | 149 | 10 | 88 | 8
24039 | The Visionary | 2025-11-06 | Wilton Lorenzo | We installed panels on the north side above the balconies, and we also installed panels to the right of the north side and at the northeast corner. | Subcontractor | Carlos Silva | No |  | No |  | Sunny | 10 | 11 | No |  | 3 boom lift, 1 lull, 1 sicssor lift | No |  |  | Yes | North | ACM | 21 | 6
24045 | TMMMS Childcare | 2025-11-06 | Kevin Morris | Finished caulking back of panels on roof, removed panel at front entrance, and started to remake panel. Couldn't get pictures of roof bc everyone was gone and building was locked up, will have pics of roof in tomorrows daily | JWMCD Crew | Chris Buttrey | No |  | No |  | Sunny | 2 | 11 | No |  | 65 boom | No |  |  | No |  | Caulking | [20 empty] | 200 | 9
24046 | UAB Biomedical Research and Psycholgy | 2025-11-06 | Zarur Nazario Padron Jr | Installing ACM panels, Screen wall panels, Zee’s, Flashing and Insulation. 3 guys unloaded material in 3 hours each. | Subcontractor | Wylie McDougall | Yes | Waiting on panels for South west wall and for swing stage to be moved. | No |  | Sunny | 11 | 110 | Yes | 3 crates of flashing and 1 crate of ACM panels | 2 scaffolds | No |  |  | No |  | ACM Corrugated / Screen wall Flashing Insulation Subgirt Zee | 8 | 56 | [20 empty] | 10 | 24 |  |  | 192 | 4 |  |  | 90 | 13 | 40 | 4
24065 | QTS NAL2 DC2 | 2025-11-06 | Chad McCoy | Faster and faster. But panels all have gutted females and they are built backwards. So we are fixing panels as we go | Subcontractor | Joe Hoyle | Yes | Panels all have gutted females. And they are built wrong. Males are where females go and vice versa | Yes | Loading dock panels. Flat stock acm for wing wall | Clear and chilly | 3 | 7 | No |  | 85 foot boom. 65 foot boom | No |  |  | No |  | ACM | 14 | 5
24089 | BSU Innovation Center | 2025-11-06 | Obed Bermudez | We continue working on the west elevation, installing strongirt, flashing, insulation, aluminum channel and panels. Aluminum channel installed 30 lf. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 4 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | West | Flashing Insulation Single Skin Subgirt Zee | [6 empty] | 17 | 10 | [18 empty] | 60 | 10 |  |  | 60 | 10 | 30 | 10
24039 | The Visionary | 2025-11-05 | Wilton Lorenzo | We installed panels near the northeast corner on the balconies, going upward, and another crew installed panels to the right on the north side. | Subcontractor | Carlos Silva | No |  | No |  | Sunny | 8 | 11 | No |  | 3 boom lift, 1 sicssor lift and 1 lull | No |  |  | Yes | North | ACM | 19 | 5
24045 | TMMMS Childcare | 2025-11-05 | Kevin Morris | Caulked back of panels around perimeter of roof | JWMCD Crew | Chris Buttrey | No |  | No |  | Sunny | 2 | 10 | Yes | 65 boom | 65 boom | No |  |  | No |  | Caulking | [20 empty] | 300 | 10
24046 | UAB Biomedical Research and Psycholgy | 2025-11-05 | Zarur Nazario Padron Jr | Installing ACM panels, Screen wall panels, Zee’s, insulation and flashing. Removing film off of panels and cleaning material/work space. | Subcontractor | Wylie McDougall | Yes | Waiting on swing stage to be ready and for answers on the Southwest corner. | No |  | Sunny | 11 | 110 | No |  | 2- swing stages and 1 scaffold | No |  |  | No |  | ACM Corrugated / Screen wall Flashing Insulation Subgirt Zee | 17 | 28 | [20 empty] | 6 | 12 |  |  | 192 | 8 |  |  | 210 | 22 | 250 | 30
24065 | QTS NAL2 DC2 | 2025-11-05 | Chad McCoy | I found a different way to install the panels with out cutting and routing. | Subcontractor | Joe Hoyle | No |  | Yes | Loading dock panels. Flat stock material for eye brow | Clear windy | 3 | 9 | No |  | 85 foot boom. 65 foot boom | No |  |  | Yes | 203 elevations | ACM | 14 | 5
24089 | BSU Innovation Center | 2025-11-05 | Obed Bermudez | We continue working on the west elevation, installing strongirt, flashing, insulation, aluminum channel and panels. | Subcontractor | Marc Ribar | No |  | No |  | Windy | 4 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | West | Flashing Insulation Single Skin Subgirt Zee | [6 empty] | 13 | 10 | [18 empty] | 90 | 10 |  |  | 60 | 10 | 85 | 10
24039 | The Visionary | 2025-11-04 | Wilton Lorenzo | We installed panels near the northeast corner, going up and to the right on the north elevation. I also reported that one panel had a small scratch, and they decided to remake it, so I will not install that panel. The panel number is 220-2A29A | Subcontractor | Carlos Silva | No |  | No |  | Sunny | 8 | 11 | No |  | 3 booms and 1 lull | No |  |  | Yes | North | ACM | 18 ACM panels | 5
24046 | UAB Biomedical Research and Psycholgy | 2025-11-04 | Zarur Nazario Padron Jr | Installing ACM panels, Screen wall panels, Zee’s, Insulation and flashing. | Subcontractor | Wylie McDougall | Yes | Waiting on swing stage to be set and still waiting on a response for ACM panels that don’t line up well. Fabricating the 7 panels we had uninstalled yesterday then reinstalling them. | No |  | Sunny | 10 | 100 | No |  | 1-swing stage and scaffold | No |  |  | No |  | ACM Corrugated / Screen wall Flashing Insulation Subgirt Zee | 14 | 40 | [20 empty] | 8 | 16 |  |  | 128 | 4 |  |  | 70 | 12 | 20 | 4
24065 | QTS NAL2 DC2 | 2025-11-04 | Chad McCoy | So from what we have measured and later out. The panels around the windows on the east elevation. Will not line up with other panels or precast joints. We also have to cut and route the bottom section of panels that touch the precast. | Subcontractor | Joe Hoyle | Yes | Windows are wrong and panels are to big | Yes | Loading dock panels. Flat stock for eyebrow remakes | Clear | 3 | 11 | No |  | 65 foot boom. 85 foot boom | No |  |  | Yes | East elevation on 201 | ACM | 14 | 10
24068 | QTS NAL1 DC2 | 2025-11-04 | Marvin Blanco | Working in the roof installing the louvers blades we have a meeting today with WT and Joe because the roof protection we are doing the best we can because in the roof it's a lot of windy | Subcontractor | Joe Hoyle | No |  | No |  | Good condition | 8 | 12 | No |  | Scaffolding , boomlift and forklift | No |  |  | No |  | Tubing | [28 empty] | 140 | 96
24082 | GTN Cable | 2025-11-04 | Kevin Morris | Caulked what was ready, trimmed back thermal peel and stick around doors, cleaned up area, Robert griggs said he would have roofer finish caulking since they were not ready | JWMCD Crew | Josh McPherson, Nick Akins | Yes | Roofers weren't done | No |  | Cold | 2 | 6 | No |  | None | No |  |  | No |  | Caulking | [20 empty] | 80 | 5
24089 | BSU Innovation Center | 2025-11-04 | Obed Bermudez | We continue working on the west elevation, installing strongirt, flashing, insulation, aluminum channel and panels. Aluminum channel installed 40 lf | Subcontractor | Marc Ribar | No |  | No |  | Clear | 4 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | West | Flashing Insulation Single Skin Subgirt Zee | [6 empty] | 30 | 10 | [18 empty] | 112 | 10 |  |  | 129 | 10 | 85 | 10
25002 | Med Center Health | 2025-11-04 | Marvin Blanco | Working in north face of the building and my guys are asking for shins and screws 2" and 3" also flashing and McDougall is taking forever to bring what we need in the job site in case we have delay in the future it's because McDougall not by Panels installation Designs we have almost 2 weeks asking for this little things and they don't make it happen | Subcontractor | Carlos Silva | Yes | Flashing screws shins | Yes | Flashing screws shins | Good condition | 4 | 12 | No |  | Boomlift | No |  |  | No |  | ACM | 12 | 48
25007 | QTS ATL2 DC10 | 2025-11-04 | Marvin Blanco | Working in the ground louvers blades and we have a couple of angles missing and some bolts we have this delay long time ago and McDougall doesn't put atencion on this kind issues we need someone who can make things happen no matter what | Subcontractor | Nick Akins | Yes | Angles for the louvers blades bolts washers and pressure washers | Yes | Angles for the louvers blades bolts pressure washers and washers | Good condition | 4 | 13 | No |  | Boomlift | No |  |  | No |  | Louvre | [24 empty] | 40 | 48
24028 | CHI Memorial Hospital | 2025-11-03 | JC Panels | Good progress today.. we had to fabricate panels | Subcontractor | Josh McPherson | No |  | No |  | Good | 7 | 70 | No |  |  | No |  |  | Yes | All | ACM Caulking | 25 | [19 empty] | 100
24039 | The Visionary | 2025-11-03 | Wilton Loreno | We installed ACM panels on the northeast side going upward, and I moved another crew to the right side of the north elevation. We also received a delivery of the panels for the east side, color Sunshine Metallic. | Subcontractor | Carlos Silva | No |  | No |  | Sunny | 8 | 11 | Yes | ACM panels | 3 boom, 1 scissor lift and 1 lull | No |  |  | Yes | North | ACM | 13 | 5
24046 | UAB Biomedical Research and Psycholgy | 2025-11-03 | Zarur Nazario Padron Jr | Installing Screen wall panels, Zee’s, insulation and flashing. Cleaning up crates and moving material. Removed 7 panels due to waterproofers request. Bringing down material and scaffold from the roof. | Subcontractor | Wylie McDougall | Yes | Waiting for swing stage to be moved on West side and not being able to work due to Southwest side panels not lining up with the windows good. | No |  | Sunny | 8 | 56 | No |  | 1- swing stage and scaffold | No |  |  | No |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 1 | 2 |  |  | 576 | 12 |  |  | 170 | 16
24065 | QTS NAL2 DC2 | 2025-11-03 | Chad McCoy | We are trying to start back up after we found that the loading dock panels don’t exist and And 60 plus percent of the eye brow is wrong and it can’t be started. So we went through and found the vestibule panels, but the vestibule can’t be started either. The glass and beauty caps are not in. The are also doing the terrazzo so on Wednesday the entrance will be shut off. | Subcontractor | Joe Hoyle | Yes | it’s a continuation on hurry up and wait on areas to work due to panels that were never made areas that are still not ready and trade work ahead of us | Yes | Loading dock panels, flat stock metal for eye brow, | Windy 25 plus gust | 3 | 6 | No |  | 85 foot boom. 65 foot boom | No |  |  | No |  | ACM | 0 | 0
24068 | QTS NAL1 DC2 | 2025-11-03 | Marvin Blanco | Working in the roof in the screenwall for the louvers blades and also taking material from the yard NAL3 to the DC2 moving material from the ground to the roof with the forklift | Subcontractor | Joe Hoyle | No |  | No |  | Cold 🥶 | 7 | 12 | No |  | Scaffolding , boomlift and forklift | No |  |  | No |  | Louvre | [24 empty] | 1 | 84
24082 | GTN Cable | 2025-11-03 | Kevin Morris | Took off trim on louvers and doors to install thermal peel and stick then reinstalled trim, made flashing and caulked to cover holes where pipes came through flashing, replaced damage trim | JWMCD Crew | Josh McPherson, Nick Akins | No |  | No |  | Cold | 2 | 10 | No |  | None | No |  |  | No |  | Trim | [36 empty] | 110 | 3
24089 | BSU Innovation Center | 2025-11-03 | Obed Bermudez | We continue working on the south and west elevation, installing aluminum channel, flashing, strongirt, insulation, and panels. Aluminum channel installed 30 lf. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 4 | 10 | No |  | Boom lifts and forklift. | No |  |  | Yes | West and south | Flashing Insulation Single Skin Subgirt Zee | [6 empty] | 28 | 10 | [18 empty] | 100 | 10 |  |  | 130 | 10 | 70 | 10
25002 | Med Center Health | 2025-11-03 | Marvin Blanco | Working in the canopy with the face panels because we don't have flashing to work around the windows and also the soffit | Subcontractor | Carlos Silva | Yes | Flashing, shins and 2" screws | Yes | Flashing for bottom of the windows 2" screws shins and 3" screws | Good condition | 4 | 12 | No |  | Boomlift | No |  |  | No |  | ACM | 8 | 48
25007 | QTS ATL2 DC10 | 2025-11-03 | Marvin Blanco | Working in the roof cutting louvers blades to make it work in the corner for the 45 this is a extra work for JWMD we're still needing material for the roof and for the ground louvers blades we have missed angles and bolts 🔩 | Subcontractor | Nick Akins | Yes | Angles for the louvers blades and also bolts 🔩 | Yes | Angles for the louvers blades and also bolts 🔩 | Cold 🥶 | 4 | 12 | No |  | Scaffolding , boomlift | No |  |  | No |  | Louvre | [24 empty] | 22 | 48
24039 | The Visionary | 2025-11-01 | Wilton Lorenzo | We installed ACM panels, and since we’re just getting started, we were making sure the panels align perfectly where they’re supposed to go | Subcontractor | Carlos Silva | No |  | No |  | Sunny | 8 | 8 | No |  | 3 boom lifts, one lull and one scissor lift | No |  |  | Yes | North | ACM | 12 | 5
24046 | UAB Biomedical Research and Psycholgy | 2025-11-01 | Zarur Nazario Padron Jr | Installing ACM panels, Screen wall panels, Zee’s, insulation and flashing. Also cleaning up empty crates and material to make space. (4 guys 6 hours each) | Subcontractor | Wylie McDougall | No |  | No |  | Sunny | 9 | 63 | No |  | 2-swing stages | No |  |  | No |  | ACM Corrugated / Screen wall Flashing Insulation Subgirt Zee | 8 | 21 | [20 empty] | 1 | 2 |  |  | 832 | 8 |  |  | 100 | 6 | 40 | 2
24089 | BSU Innovation Center | 2025-11-01 | Obed Bermudez | We continue working on the south and west elevation, installing aluminum channel, flashing, strongirt, insulation, and panels. Aluminum channel installed 60 lf. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 3 | 8 | No |  | Boom lift and Forklift | No |  |  | Yes | South/west | Flashing Insulation Subgirt Zee | [26 empty] | 150 | 8 |  |  | 120 | 8 | 90 | 8
24028 | CHI Memorial Hospital | 2025-10-31 | JC Panels | everything is going well .. we finish the south elevation and we are going forward with the canopy | Subcontractor | Josh McPherson | No |  | No |  | Good | 7 | 70 | No |  |  | No |  |  | Yes | All | ACM Caulking Single Skin | 15 | [5 empty] | 8 | [13 empty] | 100
24039 | The Visionary | 2025-10-31 | Wilton lorenzo | We leveled the panels we installed yesterday and also removed the Z that goes inside the balcony so the horizontal panel above the balcony would fit. We also aligned the vertical Zs properly to install panels on the north side. | Subcontractor | Carlos Silva | No |  | No |  | Sunny | 8 | 11 | No |  | 2 boom lift and 1 lull | No |  |  | Yes | North | ACM | 8 | 6
24046 | UAB Biomedical Research and Psycholgy | 2025-10-31 | Zarur Nazario Padron Jr | Installing ACM panels, Corrugated panels, Zee’s, insulation, flashing and moving material from the roof down to the floor. | Subcontractor | Wylie McDougall | Yes | 4 guys delayed 1 hour each due to another company fixing a hole. | No |  | Sunny | 9 | 90 | No |  | 2- swing stages | No |  |  | No |  | ACM Corrugated / Screen wall Flashing Insulation Subgirt Zee | 27 | 42 | [20 empty] | 3 | 3 |  |  | 512 | 9 |  |  | 516 | 28 | 50 | 4
24089 | BSU Innovation Center | 2025-10-31 | Obed Bermudez | Crews continue working on the south elevation, installing aluminum channel, flashing, strongirt, insulation, and panels. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 5 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | East/south | Flashing Insulation Single Skin Subgirt Zee | [6 empty] | 12 | 10 | [18 empty] | 230 | 20 |  |  | 110 | 10 | 87 | 10
24028 | CHI Memorial Hospital | 2025-10-30 | JC Panels | everything is going well | Subcontractor | Josh McPherson | No |  | No |  | Good | 7 | 70 | No |  |  | No |  |  | Yes | All | ACM Caulking Trespa | 8 | [9 empty] | 10 | [9 empty] | 100
24039 | The Visionary | 2025-10-30 | Wilton lorenzo | We unloaded insulation and I started installing panels on the first floor, but the panel inside the balcony is too big, so I think I need to remove the Z and the insulation. I asked about it but didn’t get a response. I also measured the panel that goes above the handrail, and based on that measurement, I need to remove the 1½” Z. We also installed insulation on the north side where the concrete is and installed some vertical Zs | Subcontractor | Carlos Silva | No |  | Yes | Flat strap, half clips | Sunny | 8 | 11 | Yes | Insulation | 3 boom lift and 1 lull | No |  |  | Yes | NE | ACM | 3 | 4
24046 | UAB Biomedical Research and Psycholgy | 2025-10-30 | Zarur Nazario Padron Jr | Installing ACM panels, Corrugated panels, Zee’s, Insulation and bringing down material from the roof to the ground. Making sure all material is well tied up and secured for potential high winds. | Subcontractor | Wylie McDougall | Yes | 7 panels had been installed but then we had been asked to remove them. 3 guys 3 hours each. | No |  | Cloudy | 9 | 90 | No |  | 2- swing stages and scaffold | No |  |  | No |  | ACM Corrugated / Screen wall Insulation Subgirt Zee | 27 | 39 | [20 empty] | 5 | 6 |  |  | 320 | 12 |  |  | 110 | 18
24089 | BSU Innovation Center | 2025-10-30 | Obed Bermudez | No work due to inclement weather | Subcontractor | Marc Ribar | Yes | Weather | No |  | Rainy | 5 | 0 | No |  | Boom lifts and forklift | No |  |  | Yes | East/south | Single Skin | [6 empty] | 1
25022 | Vantage VA15 | 2025-10-30 | Marvin Blanco | Working in the north side with the ACM panels | Subcontractor | Thomas Mooers | Yes | Flashing for the bottom of the windows and also shims 2" screws | Yes | 2" screws and 3" screws shins 3 or 4 boxes 📦 of each one blue 💙 red 💔 black 🖤💣 | Cold 🥶 | 4 | 12 | No |  | Boomlift | No |  |  | No |  | ACM | 12 | 48
24039 | The Visionary | 2025-10-29 | Wilton Lorenzo | We installed Z inside the parking area and also on the balconies on the 2nd and 3rd floors. We were waiting for the insulation, but I was told the truck broke down and will arrive tomorrow. I also moved some panels to the area where we’ll need them. It rained all day, so we didn’t work on the exterior side of the building. If the insulation and clips arrive tomorrow, we’ll start installing panels. | Subcontractor | Carlos Silva | Yes | It was raining all day. I still waiting for insulation and clips | Yes | Insulation and clips | Rainy | 8 | 11 | No |  | Three boom lift and one lull | No |  |  | Yes | Inside of packing garage and 1, 2 balconies | Subgirt Zee | [30 empty] | 950 | 8
24046 | UAB Biomedical Research and Psycholgy | 2025-10-29 | Zarur Nazario Padron Jr | Had a rain/wind delay all day long. The guys had gotten to the job site at around 12 but were told they were unable to work due to the strong winds. | Subcontractor | Wylie McDougall | Yes | Rain and wind delayed us a whole day | No |  | Rainy | 9 | 90 | No |  | 2- swingstages | No |  |  | No |  | ACM | 0 | 0
24089 | BSU Innovation Center | 2025-10-29 | Obed Bermudez | Crews continue working on the south and east elevation, installing aluminum channel, flashing, strongirt, insulation, and panels. Aluminum channel installed 60 lf. | Subcontractor | Marc Ribar | No |  | No |  | Cloudy | 5 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | South/east/west | Flashing Insulation Single Skin Subgirt Zee | [6 empty] | 10 | 10 | [18 empty] | 112 | 10 |  |  | 90 | 10 | 232 | 20
24018 | QTS-NAL1-DC1 | 2025-10-28 | Marvin Blanco | Working in the scaffolding taking panels out everything is working really well tomorrow we're going to start taking layout for the job DC2 for start the louvers blades with the scaffolding | Subcontractor | Joe Hoyle | Yes | Drill bits for the louvers blades | Yes | Drill bits for drilling steel for the louvers blades | Almost raining 🌧 | 7 | 12 | No |  | Scaffolding forklift and boomlift | No |  |  | No |  | Corrugated / Screen wall | [22 empty] | Nothing we're taking down | 84
24028 | CHI Memorial Hospital | 2025-10-28 | JC Panels | installation on canopy on north . We have an issue with the access door on the soffit | Subcontractor | Josh McPherson | No |  | No |  | Small rain | 7 | 70 | No |  |  | No |  |  | Yes | All | ACM Caulking | 34 | [19 empty] | 100
24039 | The Visionary | 2025-10-28 | Wilton Lorenzo | We installed vertical Z-girts on the north side, but had to stop due to rain. Then we moved inside the parking area to continue installing Z-girts. I also had a meeting with Crossland, and they decided that I need to apply caulk on the top and bottom of the Z-girts. I was waiting for the insulation, but it didn’t arrive today. The boom lift was delivered today | Subcontractor | Carlos Silva | Yes | Raining all day | Yes | Insulation | Rainy | 8 | 11 | No |  | Three boom lift and one lull | No |  |  | Yes | North and inside of Parking deck | Subgirt Zee | [30 empty] | 1200 | 7
24046 | UAB Biomedical Research and Psycholgy | 2025-10-28 | Zarur Nazario Padron Jr | Installing ACM panels, Corrugated panels, Zee’s, insulation and flashing. It took 3 guys 3 hours each to unload truck shipment. | Subcontractor | Wylie McDougall | Yes | 5 guys delayed 1 hour each on both swing stages due to power being cut and not being able to access plug for power because of door being locked. | Yes | Drip flashing | Cloudy | 8 | 80 | Yes | 10 pallets of Insulation and 5 crates of ACM panels | 2- swing stages and scaffold | No |  |  | No |  | ACM Corrugated / Screen wall Flashing Insulation Subgirt Zee | 10 | 20 | [20 empty] | 5 | 12 |  |  | 832 | 14 |  |  | 410 | 18 | 30 | 2
24065 | QTS NAL2 DC2 | 2025-10-28 | Chad McCoy | Material was moved to the yard and installed on the roof. Material was also moved across the roof for quicker access. | Subcontractor | Joe Hoyle | No |  | Yes | Material for eyebrow, Loading dock acm. | Clear | 3 | 8.5 | No |  | 85 foot boom. 65 foot boom | No |  |  | No |  | Coping | [40 empty] | 110 | 6
24069 | TCAT Pulaski | 2025-10-28 | JC Panels | install drip edge. Still missing panels | Subcontractor | Chris Buttrey | No |  | Yes | Panels | Good | 4 | 40 | No |  |  | No |  |  | Yes | All | Flashing | [32 empty] | 100
24089 | BSU Innovation Center | 2025-10-28 | Obed bermudez | Crews continue working on the east elevation, installing aluminum channel, flashing, strongirt, insulation, and panels. Aluminum channel installed 50 lf. | Subcontractor | Marc Ribar | No |  | Yes | 300 Painted screws, 40 flat metal, 450 of clips for panels. | Clear | 5 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | East south west | Flashing Insulation Single Skin Subgirt Zee | [6 empty] | 86 | 20 | [18 empty] | 128 | 10 |  |  | 100 | 10 | 50 | 10
25002 | Med Center Health | 2025-10-28 | Marvin Blanco | Working in the ground for now everything is working well the only thing we need es 2" screws and shins blue red and black 3 boxes 📦 for each one | Subcontractor | Carlos Silva | No |  | Yes | 2" screws and 3" screws shins 3 or 4 boxes 📦 of each one blue 💙 red 💔 black 🖤💣 | Almost raining 🌧 | 4 | 12 | No |  | Boomlift | No |  |  | No |  | ACM | 12 | 48
25007 | QTS ATL2 DC10 | 2025-10-28 | Marvin Blanco | Working in the louvers blades in the roof finishing what we have it's pending the short louvers blades | Subcontractor | Nick Akins | Yes | Angles for the louvers blades and shorts louvers blades | Yes | Angles for attach the tubes for the louvers blades and shorts louvers blades | Almost raining 🌧 | 4 | 12 | No |  | Scaffolding and boomlift | No |  |  | No |  | Louvre | [24 empty] | 15 | 48
24028 | CHI Memorial Hospital | 2025-10-27 | JC Panels | today we couldn’t work cause of the rain | Subcontractor | Josh McPherson | Yes | Rain | No |  | Rain | 7 | 0 | No |  |  | No |  |  | No |  | ACM | O
24039 | The Visionary | 2025-10-27 | Wilton lorenzo | We installed the starter track in the northeast area and started placing the vertical Zs in the section where the concrete is. When the insulation arrives, I’ll slide it in from behind. We’re missing the mid clips, but I expect them to arrive tomorrow so we can start installing the ACM panels. | Subcontractor | Carlos Silva | No |  | Yes | Insulation, clips and 250ft of 1", 2" z | Sunny | 6 | 11 | No |  | 2 boomlift and 1 lull | No |  |  | Yes | North and east | Subgirt Zee | [30 empty] | 300 | 4
24046 | UAB Biomedical Research and Psycholgy | 2025-10-27 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s, Insulation and flashing. | Subcontractor | Wylie McDougall | No |  | No |  | Cloudy | 6 | 48 | No |  | 2- swing stages | No |  |  | No |  | ACM Flashing Insulation Subgirt Zee | 14 | 24 | [24 empty] | 320 | 4 |  |  | 463 | 16 | 60 | 4
24065 | QTS NAL2 DC2 | 2025-10-27 | Chad McCoy | We are wrapping up small areas that need attention. | Subcontractor | Joe Hoyle | Yes | Layout, delivery’s, and trailer unloaded for Marvin to take over | Yes | Coping. Loading dock panels. Panels decisions to be made on eye brow panels. | Partly cloudy | 3 | 8.5 | Yes | Caulking | 85 foot boom. 65 foot boom | No |  |  | Yes | The dimensions were pulled for the loading dock | Corrugated / Screen wall Flashing | [22 empty] | 24 | 4 | [8 empty] | 100 | 1
24069 | TCAT Pulaski | 2025-10-27 | JC panels | we couldn’t install much cause we don’t have the panels yet.. we only got the drip edge and we dot the delivered just 3, I asked for 4 so we can’t cover the entire area we have 3 lfts that is going to be empty till we get the missing drip edge | Subcontractor | Chris Buttrey | Yes | We need the panels | Yes | Panels , 1 drip edge | Good | 4 | 32 | Yes | 3 drip edge and Chris took the unicolores panels |  | No |  |  | Yes | All | Flashing Genesis | [14 empty] | 4 | [17 empty] | 60
24089 | BSU Innovation Center | 2025-10-27 | Obed Bermudez | Crews continue working on the east elevation, installing aluminum channel, flashing, strongirt, insulation, and panels. Aluminum channel installed 60 lf | Subcontractor | Marc Ribar | No |  | No |  | Clear | 5 | 10 | No |  | Boom lifts and forklift. | No |  |  | Yes | East, south and west. | Caulking Flashing Insulation Single Skin Subgirt Zee | [6 empty] | 15 | 10 | [12 empty] | 105 | 10 |  |  |  |  | 150 | 10 |  |  | 120 | 10 | 60 | 10
24039 | The Visionary | 2025-10-25 | Wilton Lorenzo | Today we installed Z on the east side inside the parking deck because it was raining all day. We also unloaded materials. three deliveries of panels arrived | Subcontractor | Carlos Silva | No |  | No |  | Rainy | 6 | 8 | Yes | ACM panels, tek screws, and shims | Two boom lift and one lull | No |  |  | Yes | East | Subgirt Zee | [30 empty] | 450 | 5
24046 | UAB Biomedical Research and Psycholgy | 2025-10-25 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s and insulation. (3 guys spent 2 hours each fabricating 4 panels.) | Subcontractor | Wylie McDougall | No |  | No |  | Sunny | 5 | 40 | No |  | 1- swing stage | No |  |  | No |  | ACM Insulation Subgirt Zee | 16 | 20 | [24 empty] | 384 | 10 |  |  | 40 | 4
24089 | BSU Innovation Center | 2025-10-25 | Obed Bermudez | Crew 1 continues working on the east elevation, installing flashing, insulation, strongirt, and panel. Crew 2 continues caulking on the east elevation. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 5 | 9 | No |  | Boom lift and forklift. | No |  |  | Yes | East,south, | Flashing Single Skin Subgirt Zee | [6 empty] | 30 | 25 | [22 empty] | 30 | 10 | 45 | 10
23051 | Equinix DC2 | 2025-10-24 | Wilver Quiroz | Installation of flashing and corrugated panel | Subcontractor | Dillon Bowman | Yes | Waiting for door installation by another company | No |  | 65 Degrees | 2 | 8 | No |  | No | No |  |  | No |  | Corrugated / Screen wall Flashing | [22 empty] | 11 | 2 | [8 empty] | 60 ft | 3
24039 | The Visionary | 2025-10-24 | Wilton Lorenzo | Today we worked on the east side for a while because it was raining most of the day. Then we moved to the east park entrance area and also installed Z on the first-floor balcony | Subcontractor | Carlos Silva | No |  | Yes | Insulation, shims, 2 inch tek screws, panels | Rainy | 6 | 11 | No |  | Two boom lift and one lull | No |  |  | Yes | East | Subgirt Zee | [30 empty] | 850 | 5
24045 | TMMMS Childcare | 2025-10-24 | Starlin | We start to caulking the roof today and some other things that GRAHAM marked today There will be two Daily Reports because all the photos do not fit in a single Daily Report. | JWMCD Crew | Chris Buttrey | No |  | No |  | Hot | 2 | 10 | No |  | forklift | No |  |  | No |  | Caulking | [20 empty] | 100 | 5
24045 | TMMMS Childcare | 2025-10-24 | Starlin | This is the last checklist Graham and the GC of Toyota gave us to complete this morning when we did the walkthrough. Today we matched the corner panel with the key plate to be aligned correctly. Also we cocked the bottom of the window seals to seal it on every single window and door. I had to pull the reveal off and take down the plastic. We did 2 different areas of push reveal. We checked the entire building and flushed up every reveal with the paneling to make sure it was in line. The last tasks we need to complete is fixing a couple panels on the roof and a little bit more cocking. | JWMCD Crew | Chris Buttrey | No |  | No |  | Hot | 2 | 10 | No |  | forklift | No |  |  | No |  | Caulking Flashing | [20 empty] | 0 | 0 | [10 empty] | 0 | 5
24046 | UAB Biomedical Research and Psycholgy | 2025-10-24 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s and flashing. (3 guys spent 3 hours each fabricating 5 ACM panels.) | Subcontractor | Wylie McDougall | No |  | No |  | Sunny | 7 | 70 | No |  | 2- swing stages | No |  |  | No |  | ACM Flashing Subgirt Zee | 30 | 52 | [28 empty] | 200 | 8 | 30 | 4
24065 | QTS NAL2 DC2 | 2025-10-24 | Chad McCoy | We had a delivery this morning so while I wait waited on this delivery, I looked for the ACM for the loading dock. The ACM for the loading dock is not here upon further investigation. It was never made. So we continued our day after this and after I talked to everybody about the loading dock ACM and we got our crates and everything moved so that we could start doing the eyebrow the very first panel on the eyebrow is 2 inches too long so we measured the next panel is too short so I called Joe and we decided to lay every single panel out left or right in front of back, there’s probably more than 50% of these panels that are wrong and need to be modified. I would say close to 63% of these panels or better has something wrong with the placement Size or orientation in and around the structure it’s supposed to be attached to | Subcontractor | Joe Hoyle | Yes | Lots of lay out | Yes | Loading dock acm, acm strips, caulking, | Clear | 5 | 6 | Yes | Wing wall acm and some coping | 1 85 foot boom and 1 65 foot boom | No |  |  | Yes | All of the eyebrow and its soffit | ACM | 0 | 0
24089 | BSU Innovation Center | 2025-10-24 | Obed Bermudez | Crew 1 continues working on the east elevation, installing strongirt, flashing, insulation, and panels. Crew 2 continues caulking on the east elevation as well. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 5 | 10 | Yes | Morin panels. | Boom lift and forklift | No |  |  | Yes | East/west/south | Caulking Flashing Insulation Single Skin Subgirt Zee | [6 empty] | 22 | 10 | [12 empty] | 110 | 10 |  |  |  |  | 210 | 10 |  |  | 120 | 10 | 30 | 10
23051 | Equinix DC2 | 2025-10-23 | Wilver Quiroz | Installation of flashing and corrugated panel on the doors | Subcontractor | Dillon Bowman | Yes | The material arrived at 9:00 AM and we had to wait for them to install the first door to start installing us | No |  | 60 | 2 | 11 | Yes | The doors | No | No |  |  | No |  | Corrugated / Screen wall Flashing | [22 empty] | 9 | 4 | [8 empty] | 100 ft | 3
24018 | QTS-NAL1-DC1 | 2025-10-23 | Marvin Blanco | Working in the roof taking corrugated panels out of the wall | Subcontractor | Joe Hoyle | No |  | No |  | Good condition | 6 | 12 | No |  | Forklift | No |  |  | No |  | Corrugated / Screen wall | [22 empty] | 0 | 72
24028 | CHI Memorial Hospital | 2025-10-23 | JC Panels | Had to modify and fabricate a lot of panels | Subcontractor | Josh McPherson | No |  | No |  | Good | 7 | 70 | No |  |  | No |  |  | Yes | All | ACM Caulking | 18 | [19 empty] | 100
24039 | The Visionary | 2025-10-23 | Wilton lorenzo | We install Z girt one north, east and on the east side at the parking deck entrance | Subcontractor | Carlos Silva | No |  | Yes | Shims, insulation, 2 inch tek screws | Sunny | 6 | 11 | No |  | Two boom lift and one lull | No |  |  | Yes | North and east | Subgirt Zee | [30 empty] | 900 | 6
24045 | TMMMS Childcare | 2025-10-23 | Starlin | Finish code 715.714.713. 620. 595.(625 is almost done) | JWMCD Crew | Chris Buttrey | No |  | No |  | Hot | 2 | 11 | No |  | forklift | No |  |  | No |  | Caulking | [20 empty] | 20 | 15
24046 | UAB Biomedical Research and Psycholgy | 2025-10-23 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s, insulation and flashing. ( Welders tent went flying into our panels we had ready to install.) ( Window guys had informed us yesterday they were done with the swing stage so we took off the plastic but they’re still working on it.) | Subcontractor | Wylie McDougall | No |  | No |  | Sunny | 7 | 70 | No |  | 2- swing stages | No |  |  | No |  | ACM Flashing Insulation Subgirt Zee | 35 | 42 | [24 empty] | 512 | 7 |  |  | 200 | 14 | 40 | 7
24065 | QTS NAL2 DC2 | 2025-10-23 | Chad McCoy | No work today they were paving on all the sides that we needed to work on or the dump trucks were driving down the paved road, so we took the day off to rest after last night long endeavors to finish the east elevation | Subcontractor | Joe Hoyle | Yes | Paving | Yes | Acm strips. Caulking. Acm for stair tower. | Clear | 1 | 0 | No |  | 85 foot boom | No |  |  | No |  | ACM | 0 | 0
24089 | BSU Innovation Center | 2025-10-23 | Obed Bermudez | We move the crews back to the east elevation per Gc instructions, crew 1 continues installing strongirt, flashing, insulation, and panels. Crew 2 continues caulking on the east elevation. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 5 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | East | Caulking Flashing Insulation Subgirt Zee | [20 empty] | 140 | 10 |  |  |  |  | 502 | 20 |  |  | 283 | 10 | 113 | 10
25002 | Med Center Health | 2025-10-23 | Marvin Blanco | Working in the second level because in the ground we need flashing to start and we don't have it McDougall is delay on that | Subcontractor | Carlos Silva | Yes | Flashing | Yes | Flashing screws 2" and ¾ screws | Good condition | 4 | 10 | No |  | Boomlift | No |  |  | No |  | ACM | 6 | 40
23051 | Equinix DC2 | 2025-10-22 | Wilver Quiroz | The installation of channel and coping angles in the 3 areas was completed | Subcontractor | Dillon Bowman | No |  | No |  | 65 Degrees | 4 | 10 | No |  |  | No |  |  | No |  | Caulking Coping Flashing Hat Channel | [20 empty] | 30 ft | 2 | [10 empty] | 20 ft | 1 | 60 ft | 2 |  |  |  |  | 70 ft | 5
24018 | QTS-NAL1-DC1 | 2025-10-22 | Marvin Blanco | Working in taking metal panels down in the screenwall with the scaffolding | Subcontractor | Joe Hoyle | No |  | Yes | Drill bits for drilling steel for the louvers blades | Good condition | 5 | 12 | No |  | Scaffolding and forklift boomlift | No |  |  | No |  | Corrugated / Screen wall | [22 empty] | 0 | 72
24039 | The Visionary | 2025-10-22 | Wilton lorenzo | Today we worked on setting the layout of the panels and transferring the level to the north curtain wall to make sure the joint would align properly. We also added a Z-girt where the panel joint will be, to make the panel more stable. I laid out the panels on the east side at the parking deck entrance, and checked the flashing above the curtain wall it’s too small and the bends are visible where the paint didn’t cover. I also counted how many flashings we have of each color and informed Carlos about it. | Subcontractor | Carlos Silva | No |  | Yes | Insulation | Sunny | 6 | 11 | No |  | Two boom lift and one lull | No |  |  | Yes | North | Subgirt Zee | [30 empty] | 400 | 4
24045 | TMMMS Childcare | 2025-10-22 | Starlin | Finish code 716 . 626 . 622 . 612 . 610 . 609 .584.664. | JWMCD Crew | Chris Buttrey | Yes | We went to Home Depot to buy a ladder | No |  | Hot | 2 | 12 | No |  | forklift | No |  |  | No |  | Caulking | [20 empty] | 10 | 1
24046 | UAB Biomedical Research and Psycholgy | 2025-10-22 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s, Insulation and flashing. | Subcontractor | Wylie McDougall | No |  | No |  | Sunny | 6 | 60 | No |  | 2-swing stages | No |  |  | No |  | ACM Flashing Insulation Subgirt Zee | 31 | 48 | [24 empty] | 192 | 4 |  |  | 60 | 4 | 30 | 4
24065 | QTS NAL2 DC2 | 2025-10-22 | Chad McCoy | Late night | Subcontractor | Joe Hoyle | No |  | Yes | Caulking, coping. Acm strips for expansion joint. | Cold and clear | 7 | 2 guys 9, 2 guys 14, 2 guys 14.5 | No |  | 85 foot boom | No |  |  | Yes | This was already layed out yesterday | ACM | 76 | 13
24076 | GCDC Security Building | 2025-10-22 | Obed Bermudez | We continue working on the security room, removing the glass, window frame, and reinstalling the frame, glass, and caulking. | Subcontractor | Nick Akins | No |  | No |  | Clear | 3 | 10 | No |  | None | No |  |  | No |  | Trim | [36 empty] | 0
24089 | BSU Innovation Center | 2025-10-22 | Obed Bermudez | Crew 1 continues working on the west elevation, installing strongirt, flashing, insulation and panels. 20 lf of aluminum channel installed. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 5 | 10 | No |  | Boom lift and forklift. | No |  |  | Yes | West | Flashing Insulation Single Skin Subgirt Zee | [6 empty] | 39 | 20 | [18 empty] | 255 | 10 |  |  | 150 | 10 | 165 | 10
25002 | Med Center Health | 2025-10-22 | Marvin Blanco | Working on the second level because in the ground we don't have a flashing that we need | Subcontractor | Carlos Silva | Yes | Flashing, screws 2" and ¾ screws for the clips | Yes | Flashing screws 2" and ¾ screws | Good condition | 4 | 10 | No |  | Boomlift | No |  |  | No |  | ACM | 13 | 40
25002 | Med Center Health | 2025-10-22 | Marvin Blanco | Working in the second level installing ACM panels around the windows because we couldn't work in the ground | Subcontractor | Carlos Silva | Yes | Flashing for the first floor | Yes | Flashing screws 2" and ¾ screws | Good condition | 4 | 10 | No |  | Boomlift | No |  |  | No |  | ACM | 13 | 40
25007 | QTS ATL2 DC10 | 2025-10-22 | Marvin Blanco | Working in the penthouse installing metal panels in the scaffolding and also we're still missing angles for the louvers blades | Subcontractor | Nick Akins | Yes | Clips for the louvers blades | Yes | Clips for the louvers blades | Good condition | 6 | 12 | No |  | Scaffolding | No |  |  | No |  | Corrugated / Screen wall | [22 empty] | 14 | 72
23051 | Equinix DC2 | 2025-10-21 | Wilver Quiroz | Angle installation, Channel and coping section A and B | Subcontractor | Dillon Bowman | No |  | No |  | 65 Degrees | 4 | 10 | No |  | Boom lift | No |  |  | No |  | Coping Hat Channel | [34 empty] | 80 ft | 5 |  |  |  |  | 80 ft | 5
24018 | QTS-NAL1-DC1 | 2025-10-21 | Marvin Blanco | Unloading material and also installing ACM panels in the vestibule the ones we take down for the windows guys because they have a leak | Subcontractor | Joe Hoyle | No |  | No |  | Good condition | 6 | 12 | Yes | Louvers blades | Boomlift and forklift | No |  |  | No |  | ACM | 7 | 72
24028 | CHI Memorial Hospital | 2025-10-21 | JC Panels | Had to stop for 3 hours because of the rain but the. We start working again | Subcontractor | Josh McPherson | No |  | No |  | Rainy | 7 | 70 | No |  |  | No |  |  | Yes | All | ACM Caulking Single Skin | 4 | [5 empty] | 17 | [13 empty] | 100
24039 | The Visionary | 2025-10-21 | Wilton Lorenzo | We are working on the panel layout for the northeast side, but the measurements do not seem to match. Carlos will confirm the correct dimensions tomorrow. In the meantime, we installed the Z-girts on the east and northeast sides | Subcontractor | Carlos Silva | No |  | Yes | Insulation | Sunny | 6 | 11 | No |  | Two boom lifts and one lull | No |  |  | Yes | NE | Subgirt Zee | [30 empty] | 500 | 4
24046 | UAB Biomedical Research and Psycholgy | 2025-10-21 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s, insulation and flashing. Also removing plastic off of panels on East side above the bridge. | Subcontractor | Wylie McDougall | No |  | No |  | Cloudy/drizzling | 7 | 77 | No |  | 2-swing stages | No |  |  | No |  | ACM Flashing Insulation Subgirt Zee | 25 | 49 | [24 empty] | 512 | 8 |  |  | 260 | 12 | 40 | 4
24065 | QTS NAL2 DC2 | 2025-10-21 | Chad McCoy | Continuation of east elevation. | Subcontractor | Joe Hoyle | Yes | Weather | Yes | Extra acm, acm strips for stair tower. Coping. Caulking. | Rainy and storms | 6 | 10 | No |  | 85 foot boom | No |  |  | Yes | East elevation 1/203 | ACM | 75 | 9
24069 | TCAT Pulaski | 2025-10-21 | JC Panels | Working on the screen wall. We also caulk and we were organizing the wrong color panels and finding the good ones | Subcontractor | Chris Buttrey | No |  | Yes | Drip edge flashing | Good | 5 | 50 | No |  |  | No |  |  | Yes | All | Genesis | [14 empty] | 25
24076 | GCDC Security Building | 2025-10-21 | Obed Bermudez | We are working on the security room replacing astricals on two doors and trim around another door. then we started removing caulking around the window to replace the window sill. | Subcontractor | Nick Akins | No |  | No |  | Clear | 2 | 10 | No |  | None | No |  |  | No |  | Trim | [36 empty] | 50 | 20
24089 | BSU Innovation Center | 2025-10-21 | Obed Bermudez | We continue working on the west elevation, installing strongirt, flashing, insulation, caulking, aluminum c channel, and panels. Aluminum channel installed 60 lf. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 5 | 10 | No |  | Boom lift and forklift. | No |  |  | Yes | West | Caulking Flashing Insulation Single Skin Subgirt Zee | [6 empty] | 5 | 5 | [12 empty] | 50 | 15 |  |  |  |  | 100 | 15 |  |  | 65 | 10 | 57 | 10
25007 | QTS ATL2 DC10 | 2025-10-21 | Marvin Blanco | Working in the penthouse with metal panels because in the louvers blades we don't have any angles to continue working and finishing everything | Subcontractor | Nick Akins | Yes | Coping insulation and angles | Yes | Insulation coping and angles for the louvers blades | Good condition | 5 | 12 | No |  | scaffolding | No |  |  | No |  | Corrugated / Screen wall | [22 empty] | 19 | 60
25007 | QTS ATL2 DC10 | 2025-10-21 | Marvin Blanco | Waiting for material all day and the materials arrived at 2:00 we lose our first day to install panels | Subcontractor | Nick Akins | Yes | ACM panels | No |  | Good condition | 4 | 10 | Yes | ACM panels | Boomlift | No |  |  | No |  | Insulation | [26 empty] | 100 | 40
23051 | Equinix DC2 | 2025-10-20 | Wilver Quiroz | The coping of area C was completed and angles, channels and coping were installed in area B | Subcontractor | Dillon Bowman | No |  | No |  | 63 Degrees | 4 | 12 | No |  | Boom lift | No |  |  | No |  | Coping Hat Channel | [34 empty] | 80 | 3 |  |  |  |  | 80 | 3
24028 | CHI Memorial Hospital | 2025-10-20 | JC Panels | 3 crews in 3 different la areas. Installation is going along | Subcontractor | Josh McPherson | No |  | No |  | Good | 7 | 70 | No |  |  | No |  |  | Yes | All | ACM Caulking | 8 | [19 empty] | 100
24039 | The Visionary | 2025-10-20 | Wilton Lorenzo | We install horizontal Z Girt on the north elevation | Subcontractor | Carlos Silva | No |  | Yes | Insulation | Sunny | 6 | 11 | No |  | Two boom lifts and one lull | No |  |  | Yes | North | Subgirt Zee | [30 empty] | Around 700Ft | 4
24046 | UAB Biomedical Research and Psycholgy | 2025-10-20 | Zarur Nazario Padron Jr | Installing ACM panels, Insulation and Zee’s. Cleaning up areas and moving materials as well. | Subcontractor | Wylie McDougall | No |  | No |  | Sunny | 7 | 63 | No |  | 2- swing stages | No |  |  | No |  | ACM Insulation Subgirt Zee | 23 | 25 | [24 empty] | 192 | 8 |  |  | 545 | 16
24065 | QTS NAL2 DC2 | 2025-10-20 | Chad McCoy | Go go go. I started my day moving all of Marvin’s louvers in my yard to the correct location. They continue to disrespect my laydown area with shit organization and trash. | Subcontractor | Joe Hoyle | No |  | Yes | Acm strips for the expansion joint on stair tower. Extra acm to make panels on the stair tower that have a 3-4 inch bust. Coping for everything. Replacement wing wall panels. | Clear chilly | 7 | 13 for 2 guys. 10 hrs for 3 11 hrs for 2 | No |  | One solo 85 foot boom | No |  |  | Yes | Acm layout was done days ago | ACM | 132 | 10.5
24069 | TCAT Pulaski | 2025-10-20 | JC Panels | Installing berridge panels on screen wall.. some panels came with different color. We are classifying that came wrong | Subcontractor | Chris Buttrey | No |  | Yes | Panels for soffit | Good | 5 | 50 | No |  |  | No |  |  | Yes | All | Genesis | [14 empty] | 35
24089 | BSU Innovation Center | 2025-10-20 | Obed Bermudez | We continue working on the west elevation, installing strongirt, flat metal, insulation and panels. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 4 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | West | Insulation Single Skin Subgirt Zee | [6 empty] | 4 | [19 empty] | 80 |  |  |  | 40
24065 | QTS NAL2 DC2 | 2025-10-19 | Chad McCoy | No work. Weather delay | Subcontractor | Joe Hoyle | Yes | Weather | Yes | Acm strips for the expansion joint on stair tower. Extra acm to make panels on the stair tower that have a 3-4 inch bust. Coping for everything. Replacement wing wall panels. | Rain and cold | 1 | 0 | No |  | 85 foot boom, So much money saved on equipment on this job | No |  |  | No |  | ACM | 0 | 0
24039 | The Visionary | 2025-10-18 | Wilton Lorenzo | We install z girt on the north elevation and we stop working cause it started raining | Subcontractor | Carlos Silva | Yes | It was raining | Yes | Insulation | Raining | 7 | 7 | No |  | 2 boom lifts and 1 lull | No |  |  | Yes | North | Subgirt Zee | [30 empty] | 600 ft | 4
24046 | UAB Biomedical Research and Psycholgy | 2025-10-18 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s | Subcontractor | Wylie McDougall | No |  | No |  | Sunny | 4 | 32 | No |  | 1- swing stage | No |  |  | No |  | ACM Subgirt Zee | 12 | 28 | [28 empty] | 30 | 4
24065 | QTS NAL2 DC2 | 2025-10-18 | Chad McCoy | I made the silver panels around the door on the north side of the stair tower. I do not have enough acm to make the top corner. I took down 9 panels. Made 7 and installed 11 there. Plus drip flashing over the door | Subcontractor | Joe Hoyle | No |  | Yes | Acm strips for the expansion joint on stair tower. Extra acm to make panels on the stair tower that have a 3-4 inch bust. Coping for everything. Replacement wing wall panels. | Windy chilly | 7 | 10 | No |  | 1 85 foot boom | No |  |  | Yes | Column line 11 page 203 | ACM Flashing | 118 | 10 | [30 empty] | 3 | 0.5
23051 | Equinix DC2 | 2025-10-17 | Wilver Quiroz | Angle installation, Channel and coping | Subcontractor | Dillon Bowman | No |  | No |  | 67 Degrees | 4 | 8 | No |  | Boom lift | No |  |  | No |  | Coping Hat Channel | [34 empty] | 60 ft | 4 |  |  |  |  | 70 ft | 4
24028 | CHI Memorial Hospital | 2025-10-17 | JC panels | We are done with the lower roof | Subcontractor | Josh McPherson | No |  | No |  | Good | 4 | 40 | No |  |  | No |  |  | Yes | All | ACM | 14
24039 | The Visionary | 2025-10-17 | Wilton Lorenzo | Today We unloaded material and install horizontal z grit on the north elevation. And I took expansion joint measurements North and south | Subcontractor | Carlos Silva | No |  | No |  | Sunny | 6 | 11 | Yes | Z grit and hardware | 2 boom lift | No |  |  | Yes | North | Subgirt Zee | [30 empty] | 680 | 4
24045 | TMMMS Childcare | 2025-10-17 | Starlin | Today we worked on code 624 finished 564 finished 581 replace panel, replaced fascia with scratch | JWMCD Crew | Chris Buttrey | No |  | No |  | Hot | 4 | 9 | No |  | Boom Scissors lift and forklift | No |  |  | No |  | ACM Caulking Trim | 1 | 4 we manufacture a corner panel | [18 empty] | 20 | 1 | [14 empty] | 15 | 1
24046 | UAB Biomedical Research and Psycholgy | 2025-10-17 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s, Insulation and flashing. Also moving material up to roof (2 guys 6 hours each) | Subcontractor | Wylie McDougall | Yes | 5 workers delayed 4 hours each due to having to remove 1 corner panel and the one right next to it to take a picture of color wording on the back. Also having to reinstall the panels. | No |  | Sunny | 8 | 96 | No |  | 2- swing stages | No |  |  | No |  | ACM Flashing Insulation Subgirt Zee | 32 | 44 | [24 empty] | 256 | 4 |  |  | 240 | 12 | 40 | 4
24068 | QTS NAL1 DC2 | 2025-10-17 | Chad McCoy | I gave the guys off yesterday bc of the hrs we have been working. I went in and installed 18 panels and played out to set us up for 154 more panels to come. | Subcontractor | Joe Hoyle | No |  | Yes | Louver material, coping, Extra acm for panel remakes, | Clear | 1 | 8 | No |  | 85 foot boom | No |  |  | Yes | Line 14 on 202, line 12 on 203 | ACM | 18 | 8
23051 | Equinix DC2 | 2025-10-16 | Wilver Quiroz | No | Subcontractor | Dillon Bowman | No |  | No |  | 63 Degrees | 4 | 11 | No |  | Si | No |  |  | No |  | Coping Corrugated / Screen wall Hat Channel | [22 empty] | 4 | 3 | [10 empty] | 60 ft | 2 |  |  |  |  | 60 ft | 6
24028 | CHI Memorial Hospital | 2025-10-16 | JC Panels | We moved to scaffold to finish the lower roof finally, and work with the Morin on south elevation. Panel fabrication | Subcontractor | Josh McPherson | No |  | No |  | Good | 7 | 70 | Yes | Insolation |  | No |  |  | Yes | All | ACM Caulking Single Skin | 2 | [5 empty] | 27 | [13 empty] | 50
24045 | TMMMS Childcare | 2025-10-16 | Starlin | Today we worked on code 573 finish caulk and Nichia 593 finished 618 caulk bittom of Nichia 619 finished 628 misaligned panel finished 629 wrong size panels finished | JWMCD Crew | Chris Buttrey | No |  | No |  | Hot | 4 | 10 | No |  | Boom Scissors lift and forklift | No |  |  | No |  | Caulking Trim | [20 empty] | 190 | 7 | [14 empty] | 20 | 1
24045 | TMMMS Childcare | 2025-10-16 | Starlin | This email is only for reporting photos and code 624 finished 584 592 finished | JWMCD Crew | Chris Buttrey | No |  | No |  | 0 | 4 | 0 | No |  | 0 | No |  |  | No |  | Caulking Trim | [20 empty] | 0 | 0 | [14 empty] | 0 | 0
24046 | UAB Biomedical Research and Psycholgy | 2025-10-16 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s, flashing and removing plastic off panels. | Subcontractor | Wylie McDougall | No |  | No |  | Sunny | 9 | 108 | No |  | 3-swing stages | No |  |  | No |  | ACM Flashing Subgirt Zee | 33 | 54 | [28 empty] | 100 | 18 | 100 | 36
24068 | QTS NAL1 DC2 | 2025-10-16 | Chad McCoy | One guy for orientation, Dc1 had damage happen today on the east stair tower. We started peeling panels today. | Subcontractor | Joe Hoyle | Yes | Orientation, an assessment on the DC one stair tower | Yes | Louver material. Acm for panel rebuilds. Coping. Wing wall replacement panels | Clear chilly | 7 | 2 guys 13. 5 guys 9.5 | No |  | 1 boom lift | No |  |  | Yes | Line 13 on page 202 | ACM | 54 | 9
24069 | TCAT Pulaski | 2025-10-16 | JC Panels | Start with the flashing on the screen eall | Subcontractor | Chris Buttrey | No |  | No |  | Good | 5 | 50 | No |  |  | No |  |  | Yes | All | Flashing | [32 empty] | 70
24089 | BSU Innovation Center | 2025-10-16 | Obed bermudez | Crew 1 continues working on the west elevation, installing strongirt, flashing, insulation, and panels. We found two more damaged panels measuring 15' 5". | Subcontractor | Marc Ribar | No |  | No |  | Clear | 4 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | West | Flashing Insulation Single Skin Subgirt Zee | [6 empty] | 10 | 10 | [18 empty] | 204 | 15 |  |  | 126 | 10 | 41 | 5
25007 | QTS ATL2 DC10 | 2025-10-16 | Marvin Blanco | Installing insulation in the building because we don't have the panels and we need the panels ASAP | Subcontractor | Nick Akins | Yes | ACM panels | Yes | ACM panels and finishing | Good condition | 4 | 10 | No |  | Boomlift | No |  |  | No |  | Insulation | [26 empty] | 500 | 40
23051 | Equinix DC2 | 2025-10-15 | Wilver Quiroz | No | Subcontractor | Dillon Bowman | Yes | Wait for boom lift | No |  | 2 hours late | 4 | 11 | Yes | Coping |  | No |  |  | No |  | Corrugated / Screen wall | [22 empty] | 19 | 9
24030 | Vantage TX-21 | 2025-10-15 | Naza Padron | Trims were made to fill in gaps and areas that the panel did not cover around the doors | Subcontractor | Chris Buttrey | Yes | area on hold due to two windows needing to be replaced and missing interior panels level 2 & 3 | Yes | interior pppanels for level 2 & 3 | sunny | 5 | 40 | No |  | 2- 86' Boom Lifts | No |  |  | No |  | Caulking Trim | [20 empty] | 110 | 26 | [14 empty] | 50 | 14
24039 | The Visionary | 2025-10-15 | Wilton Lorenzo | Unloaded material | Subcontractor | Carlos Silva | Yes | No hardware and no equipment | Yes | Hardware | Sunny | 7 | 7 | Yes | Z Girt | No equipment | No |  |  | No |  | Subgirt Zee | [30 empty] | 0 | 0
24045 | TMMMS Childcare | 2025-10-15 | Starlin | Finished installing # 577 nahitchi 6 panels, continued #611 nahitchi front entrance 17 panels, started reinstalling acm on roof 19 panels Sorry for daily being late worked till 7 then had to go to home Depot | JWMCD Crew | Chris Buttrey | No |  | No |  | hot | 4 | 12 | No |  | Boo Scissors lift and forklift | No |  |  | No |  | ACM Coping Trim | 19 | 5 | [34 empty] | 60 | 2 |  |  | 30 | 1
24045 | TMMMS Childcare | 2025-10-15 | Starlin | Finished #611 front entrance installed last 2 nahitchi panels and trim finished caulking, started #618 caulking bottom of nahitchi, finished installing acm on roof only caulking left | JWMCD Crew | Chris Buttrey | No |  | No |  | Hot | 4 | 11 | No |  | Boom Scissors lift and forklift | No |  |  | Yes | On The roof | ACM Caulking Subgirt Zee Trim | 25 | 6 | [18 empty] | 150 | 3 | [8 empty] | 120 | 1.5 |  |  |  |  | 10 | 0.5
24046 | UAB Biomedical Research and Psycholgy | 2025-10-15 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s and Insulation. 3 guys spent 3 hours each unloading delivery truck. 3 guys moving ACM panels up onto the roof. | Subcontractor | Wylie McDougall | No |  | No |  | Sunny | 9 | 90 | Yes | Insulation and 4 crates of ACM panels | 2-swing stage | No |  |  | No |  | ACM Insulation Subgirt Zee | 8 | 35 | [24 empty] | 960 | 20 |  |  | 40 | 4
24068 | QTS NAL1 DC2 | 2025-10-15 | Chad McCoy | 2 teams. One one stair tower one on south of the east elevation. We have one panel completely missing. I will be making this in the field | Subcontractor | Joe Hoyle | No |  | Yes | Louver material. Acm for panel rebuilds. Coping. Wing wall replacement panels | Clear | 6 | 10.5 | No |  | 1 65 foot boom | No |  |  | No |  | ACM | 59 | 10
24069 | TCAT Pulaski | 2025-10-15 | JC Panels | Start installing panels on soffit | Subcontractor | Chris Buttrey | No |  | No |  | Good | 6 | 60 | No |  |  | No |  |  | Yes | For the soffit we have to do several layout to leave the uninstall panels that we don’t have | Caulking Genesis | [14 empty] | 7 | [5 empty] | 100
24089 | BSU Innovation Center | 2025-10-15 | Obed Bermudez | We continue working on west elevation, installing strongirt, flashing and insulation. 200 lf of aluminum channel installed. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 4 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | West elevation | Flashing Insulation Subgirt Zee | [26 empty] | 52 | 10 |  |  | 200 | 20 | 110 | 10
24028 | CHI Memorial Hospital | 2025-10-14 | JC Panels | Some change orders that I reported to Luke on north elevation | Subcontractor | Josh McPherson | No |  | No |  | Good | 8 | 80 | No |  |  | No |  |  | Yes | All | ACM Single Skin Trespa | 8 | [5 empty] | 8 |  |  |  | 8
24030 | Vantage TX-21 | 2025-10-14 | Naza Padron | area on hold due to two windows needing to be replaced | Subcontractor | Chris Buttrey | Yes | area on hold due to two windows needing to be replaced | Yes | interior pppanels for level 2 & 3 | sunny | 5 | 50 | No |  | 2- 86' Boom Lifts | No |  |  | No |  | ACM Caulking | 7 | 18 | [18 empty] | 180 | 32
24046 | UAB Biomedical Research and Psycholgy | 2025-10-14 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s, flashing and Insulation. Fabricated 12 panels in total 4 guys spent 2 hours each unloading delivery truck. | Subcontractor | Wylie McDougall | No |  | No |  | Sunny | 9 | 82 | Yes | Insulation, ACM panels and 6 crates of Zee’s | 2 swing stages | No |  |  | No |  | ACM Flashing Insulation Subgirt Zee | 17 | 44 | [24 empty] | 192 | 6 |  |  | 265 | 12 | 60 | 12
24068 | QTS NAL1 DC2 | 2025-10-14 | Marvin Blanco | Finishing the freedom wall and also cleaning everything and the only thing we have left it's the vestibule panels we have to remove panels from the wall because WT is getting leaks from the windows guys | Subcontractor | Joe Hoyle | No |  | No |  | Good condition | 4 | 12 | No |  | Scissors lift and boomlift | No |  |  | Yes | Everything | ACM | 9 | 48
24068 | QTS NAL1 DC2 | 2025-10-14 | Chad mccoy | Switching things up | Subcontractor | Joe Hoyle | No |  | Yes | Louver material. Coping material. Extra acm. Replacement panels for wing wall | Clear windy | 6 | 10.5 | No |  | 65 foot boom. The rest is tactically acquired | No |  |  | Yes | Page 201 and east stair tower | ACM Subgirt Zee | 50 | 9 | [28 empty] | 400 | 2
24069 | TCAT Pulaski | 2025-10-14 | JC Panels | Finish punch and change order | Subcontractor | Chris Buttrey | No |  | Yes | Flashings and panels | Good | 6 | 60 | No |  |  | No |  |  | Yes | All | Genesis | [14 empty] | 14
24089 | BSU Innovation Center | 2025-10-14 | Obed Bermdez | Crew 1 continues working on the east, installing the bottom row of panels and cleaning up all trash. | Subcontractor | Marc Ribar | Yes | Waterproof not done on the parapet. | No |  | Clear | 4 | 10 | No |  | Boom lift and forklift. | No |  |  | Yes | South and east | Flashing Insulation Single Skin | [6 empty] | 30 | 20 | [18 empty] | 52 | 10 |  |  |  |  | 60 | 10
25002 | Med Center Health | 2025-10-14 | Marvin Blanco | Working and putting insulation in the wall and also taking dimensions for Carlos for the stone panels | Subcontractor | Carlos Silva | Yes | Finishing for around the windows | Yes | We need ACM panels to start working | Good condition | 4 | 11 | No |  | Boomlift | No |  |  | Yes | Stairs tower for the stone panels | Insulation | [26 empty] | 900 | 44
25007 | QTS ATL2 DC10 | 2025-10-14 | Marvin Blanco | Working in the louvers blades in the roof and we have two corners of louvers blades shorter the one in the left and also the one in the right both are short we need angles to finish this the louvers blades in the roof because with out angles we're not able to finish also we're needing coping for the metal panels penthouse | Subcontractor | Nick Akins | Yes | Coping for the penthouse angles for the louvers blades 4x4x4 ⅜wide also we're going to be short in the insulation also for the penthouse | Yes | Angles and coping and insulation | Good condition | 8 | 12 | No |  | Scaffolding | No |  |  | No |  | Louvre | [24 empty] | 24 | 96
24028 | CHI Memorial Hospital | 2025-10-13 | JC Panels | We finish the parallel panels on the lower roof. And start on the east elevation . also que install caulking, z’s and flashing | Subcontractor | Josh McPherson | No |  | No |  | Good | 8 | 80 | Yes | Acm |  | No |  |  | Yes | All | ACM Trespa | 3 | [9 empty] | 50
24030 | Vantage TX-21 | 2025-10-13 | Naza Padron | still waiting for level 2 & 3 interior panels. 4 hours cleaning lay down area | Subcontractor | Chris Buttrey | No |  | Yes | missing level 3 & 2 interior panels | sunny | 5 | 40 | No |  | 2- 85' Boom Lifts | No |  |  | No |  | ACM Caulking | 5 | 16 | [18 empty] | 280 | 20
24045 | TMMMS Childcare | 2025-10-13 | Starlin | Finished installing nahitchi on # 573, then started installing nahitchi for # 577 10 panels total, continued # 611 fascia and copping on front entrance | JWMCD Crew | Chris Buttrey | No |  | No |  | hot | 4 | 10 | No |  | Boom Scissors lift and forklift | No |  |  | Yes | Front entry | Coping Trim | [36 empty] | 60 | 2 |  |  | 70 cleat and copping | 4
24046 | UAB Biomedical Research and Psycholgy | 2025-10-13 | Zarur Nazario Padron Jr | Installing ACM panels, insulation and flashing. | Subcontractor | Wylie McDougall | No |  | No |  | Sunny | 7 | 56 | No |  | 2- swing stages | No |  |  | No |  | ACM Flashing Insulation | 25 | 43 | [24 empty] | 384 | 9 |  |  |  |  | 10 | 4
24068 | QTS NAL1 DC2 | 2025-10-13 | Chad mccoy | Shitty and getting | Subcontractor | Joe Hoyle | No |  | Yes | Corrugated coping. Replacement panels for wing wall. Acm flat stock for white on stair tower. Louver material | Clear chilly | 6 | 11.5 | No |  | 65 foot boom | No |  |  | No |  | ACM | 100 | 11
24069 | TCAT Pulaski | 2025-10-13 | Chris Henriquez | Soffit canopy missing panels haven’t arrived. | Subcontractor | Chris Buttrey | No |  | No |  | No | 4 | 11 | Yes | Trim pieces for soffit and transportation building entrance, replacement panels, more panels. | 1 boom, 2 scissors, 1 forklift | No |  |  | No |  | Genesis Trim | [14 empty] | 11 | 11 | [20 empty] | All of north side | 11
24069 | TCAT Pulaski | 2025-10-13 | JC Panels | Al the flashing on north elevation was installed | Subcontractor | Chris Buttrey | No |  | Yes | Flashings for the screen wall, rivets, panels for soffit | Good | 6 | 60 | Yes | Flashing |  | No |  |  | Yes | All | Genesis | [14 empty] | 9
24089 | BSU Innovation Center | 2025-10-13 | Obed Bermudez | Crew 1 continue with a girt and panel installation on the east wall. Aluminum channel 26 lf. | Subcontractor | Marc Ribar | Yes | Waterproof not done on parapet. | No |  | Clear | 4 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | East and south | Single Skin Subgirt Zee | [6 empty] | 42 | 25 | [22 empty] | 62 | 15
24068 | QTS NAL1 DC2 | 2025-10-12 | Chad mccoy | Clear day | Subcontractor | Joe Hoyle | No |  | Yes | Acm for the east white stair. Corrugated coping. Replacement panels for back of wing wall remakes | Clear | 3 | 8 | No |  | 65 foot boom | No |  |  | Yes | 210 in prints | ACM | 26 | 8
24030 | Vantage TX-21 | 2025-10-11 | NazaPadron | watin on interior Panels for level 2 & 3 | Subcontractor | Chris Buttrey | No |  | No |  | sunny | 5 | 60 | No |  | 2- 86' Boom Lifts | No |  |  | No |  | ACM Insulation Subgirt Zee | 20 | 36 | [24 empty] | 64 | 6 |  |  | 60 | 8
24046 | UAB Biomedical Research and Psycholgy | 2025-10-11 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s and J-flashing. Cleaning up areas. | Subcontractor | Wylie McDougall | No |  | No |  | Sunny | 6 | 48 | No |  | 1-swing stage | No |  |  | No |  | ACM Flashing Subgirt Zee | 17 | 20 | [28 empty] | 150 | 8 | 20 | 4
24068 | QTS NAL1 DC2 | 2025-10-11 | Chad mccoy | Small crew | Subcontractor | Joe Hoyle | No |  | Yes | Louver material. Panels for wing wall. Caulking/backarod. | Cleat | 3 | 8 | No |  | 85 foot boom | No |  |  | Yes | East | ACM | 18 | 8
24089 | BSU Innovation Center | 2025-10-11 | Obed Bermudez | We continue working on the east and south elevation. We removed 78 panels to make the joints staggered and reinstalled 38. | Subcontractor | Marc Ribar | Yes | Waterproof still not done on parapet. | No |  | Clear | 3 | 8 | No |  | Boom lift and forklift | No |  |  | Yes | East and south | Single Skin | [6 empty] | 53 | 24
24028 | CHI Memorial Hospital | 2025-10-10 | JC Panels | Installation is going well | Subcontractor | Josh McPherson | No |  | No |  | Good | 7 | 70 | No |  |  | No |  |  | Yes | All | ACM Trespa | 18 | [9 empty] | 30
24028 | CHI Memorial Hospital | 2025-10-10 | JC Panels | Going forward | Subcontractor | Josh McPherson | No |  | No |  | Good | 6 | 60 | No |  |  | No |  |  | Yes | All | ACM | 19
24030 | Vantage TX-21 | 2025-10-10 | NazaPadron | watin on interior Panels for level 2 & 3 | Subcontractor | Chris Buttrey | No |  | No |  | sunny | 5 | 65 | No |  | 2- 86' Boom Lifts | No |  |  | No |  | ACM Insulation Subgirt Zee | 30 | 44 | [24 empty] | 128 | 8 |  |  | 90 | 13
24045 | TMMMS Childcare | 2025-10-10 | Starlin | Today we worked on code 573 and also 571 and 624. We located all the material in a different area because they are going to put grass where it was and we cleaned it. | JWMCD Crew | Chris Buttrey | No |  | No |  | sunny | 4 | 10 | No |  | Boom Scissors lift and forklift | No |  |  | No |  | Caulking Trim | [20 empty] | 30 | 1.5 | [14 empty] | 20 | 0.5
24045 | TMMMS Childcare | 2025-10-10 | Starlin | The reason for this email is because the entire photo does not fit in a single daily report. 24045 | JWMCD Crew | Chris Buttrey | No |  | No |  | 0 | 4 | 10 | No |  | 0 | No |  |  | No |  | Trim | [36 empty] | 0 | 0
24046 | UAB Biomedical Research and Psycholgy | 2025-10-10 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s, J-flashing and Insulation on East side and West side of building. | Subcontractor | Wylie McDougall | No |  | No |  | Sunny | 8 | 80 | No |  | 2-swing stage | No |  |  | No |  | ACM Flashing Insulation Subgirt Zee | 25 | 44 | [24 empty] | 1088 | 16 |  |  | 195 | 12 | 20 | 8
24048 | QTS NAL2 DC1 | 2025-10-10 | Antonio Sanchez | Corrugated rib panel louver | Subcontractor | Joe Hoyle | false |  | true |  |  | 6 | 10 | false |  | Boomlift forklift | false |  |  |  |  | Corrugated / Screen wall Louvre | [22 empty] | 20 | 30 |  | 30 | [18 empty] | 2025-10-10 |  | 1d
24068 | QTS NAL1 DC2 | 2025-10-10 | Chad McCoy | Flowing!!!! | Subcontractor | Joe Hoyle | No |  | Yes | Extra acm. Louver parts. Caulking | Clear chilly | 6 | 9 | No |  | 85 foot boom | No |  |  | Yes | East elevation | ACM | 68 | 8
24089 | BSU Innovation Center | 2025-10-10 | Obed Bermudez | We continue working on the south elevation installing strongirt, insulation, flashing, and panels | Subcontractor | Marc Ribar | Yes | Still waiting on waterproof on the parapet. | No |  | Clear | 4 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | South and east | Single Skin Subgirt Zee | [6 empty] | 28 | 30 | [22 empty] | 30 | 10
24028 | CHI Memorial Hospital | 2025-10-09 | JC Panels | We work on the parallel on the low roof | Subcontractor | Josh McPherson | No |  | No |  | Good | 7 | 70 | No |  |  | No |  |  | Yes | All | ACM Single Skin Trespa | 13 | [5 empty] | 9 |  |  |  | 30
24030 | Vantage TX-21 | 2025-10-09 | Naza Padron | N/A | Subcontractor | Chris Buttrey | No |  | No |  | sunny | 5 | 60 | No |  | 2- 86' Boom Lifts | No |  |  | No |  | ACM Insulation Subgirt Zee | 20 | 40 | [24 empty] | 128 | 8 |  |  | 80 | 12
24045 | TMMMS Childcare | 2025-10-09 | Starlin | Today we worked on code 628 fix misaligned panels, also on 575 which was finished and we started 573 we installed 4 Nahitchi panal | JWMCD Crew | Chris Buttrey | No |  | No |  | cloudy | 4 | 10 | Yes | Cleat and fascia | Boom Scissors lift and forklift | No |  |  | No |  | Caulking Trim | [20 empty] | 100 | 5 | [14 empty] | 30 | 1
24046 | UAB Biomedical Research and Psycholgy | 2025-10-09 | Zarur Nazario Padron Jr | Installing Perforated panels, Corrugated panels, Zee’s and flashing. Cleaning up on the roof area aswell. | JWMCD Crew | Wylie McDougall | true | Had to stop work on swing stage above bridge due to Sunbelt fixing swing stage. |  |  | Sunny | 10 | 100 | false |  | 2 scaffolds | false |  |  |  |  | Corrugated / Screen wall Flashing Insulation Other Subgirt Zee | [20 empty] | 0 | 0 | 28 | 50 |  |  | 320 | 4 |  |  | 1080 | 30 | 80 | 10 | [9 empty] | 6
24046 | UAB Biomedical Research and Psycholgy | 2025-10-09 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s, and drip flashing. Wasted most of the day due to Sunbelt having to fix swing stages. 6 guys spent 2 hour each fixing the swing stage on East side above the bridge due to Sunbelt taking too long and holding us back from finishing up this area. | Subcontractor | Wylie McDougall | Yes | (1 crew held up of 4 guys held up 6 hours each due to Sunbelt working on swing stages and it not being safe. From 9AM - 2PM) (1 crew of 4 guys held up 3 hours each due to Sunbelt working on swing stage. From 9AM - 12 PM) (6 guys delayed 2 hours each due to us having to move the swing stage on East side above the bridge. From 2PM- 4PM) | No |  | Sunny | 8 | 80 | No |  | 3 swing stages | No |  |  | No |  | ACM Flashing Subgirt Zee | 3 | 8 | [28 empty] | 168 | 12 | 104 | 12
24068 | QTS NAL1 DC2 | 2025-10-09 | Chad McCoy | A good night but I can do better | Subcontractor | Joe Hoyle | No |  | Yes | Extra acm for stair tower doors. Missing Louver pieces and acm for expansion joint on stair tower. Coping | Clear chilly | 6 | 11 | No |  | 85 foot boom. | No |  |  | Yes | East elevation | ACM | 72 panels | 9.5
24069 | TCAT Pulaski | 2025-10-09 | Chris Henriquez | Clean up and organize panels. | Subcontractor | Chris Buttrey | No |  | No |  | No | 4 | 5 | No |  | 1 boom, 2 scissor, 1 forklift | No |  |  | No |  | Genesis | [14 empty] | Clean up and organize panels. | 5
24069 | TCAT Pulaski | 2025-10-09 | JC Panels | We did a extreme cleaning and get all the material y order | Subcontractor | Chris Buttrey | Yes | We haven’t received the flashing the rivets and the panels | Yes | Flashing rivets panels | Good | 6 | 25 | No |  |  | No |  |  | Yes | all | Flashing | [32 empty] | 50
24089 | BSU Innovation Center | 2025-10-09 | Obed Bermudez | We continue working on south elevation, Installing strongirt, flashing, insulation, and panels. We installed 68 lf of aluminum channel. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 6 | 10 | No |  | Boom lifts and forklift | No |  |  | Yes | South and east | Flashing Insulation Single Skin Subgirt Zee | [6 empty] | 20 | 10 | [18 empty] | 324 | 20 |  |  | 443 | 20 | 96 | 10
24028 | CHI Memorial Hospital | 2025-10-08 | JC Panels | None | Subcontractor | Josh McPherson | No |  | No |  | Good | 7 | 77 | Yes | Flashings panels |  | No |  |  | Yes | All | ACM Single Skin Trespa | 12 | [5 empty] | 13 |  |  |  | 15
24028 | CHI Memorial Hospital | 2025-10-08 | JC Panels | Everything is going well as planned . We field fabricate panels for the southwest elevation | Subcontractor | Josh McPherson | No |  | No |  | Good | 8 | 80 | No |  |  | No |  |  | Yes | All | ACM Caulking Single Skin | 4 | [5 empty] | 9 | [13 empty] | 100
24030 | Vantage TX-21 | 2025-10-08 | Naza Padron | N/A | Subcontractor | Chris Buttrey | No |  | No |  | sunny | 5 | 50 | Yes | reveals and window trim | 2- 85' Boom Lifts | No |  |  | No |  | ACM Caulking | 14 | 32 | [18 empty] | 60 | 18
24045 | TMMMS Childcare | 2025-10-08 | Starlin | Today we started manufacturing 2 panels, code 611 on the roof and front entrance also caulked those areas. started code 628 (miss aligned panel) Today we started on code 575 and 585. The caulking was finished. Kevin and I stopped for an hour to clean the entire front because tomorrow is the state walk through | JWMCD Crew | Chris Buttrey | No |  | No |  | cloudy | 4 | 10 | No |  | Boom Scissors lift and forklift | No |  |  | No |  | ACM Caulking Trim | 2 | 3 | [18 empty] | 120 | 3 | [14 empty] | 20 | 1
24046 | UAB Biomedical Research and Psycholgy | 2025-10-08 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s and drip flashing. Stopped work one hour early due to swing stage being a hazard risk. Still waiting on swing stage on the East side to be fixed by Sunbelt. 4 guys lost 1 hour each. | Subcontractor | Wylie McDougall | Yes | Waiting for Sunbelt to fix swing stage on East side above the bridge. 4 guys lost 1 hour each due to swing stage being unsafe on West side building. | No |  | Sunny | 8 | 80 | No |  | 2 swing stages | No |  |  | No |  | ACM Flashing Subgirt Zee | 16 | 32 | [28 empty] | 585 | 40 | 30 | 4
24048 | QTS NAL2 DC1 | 2025-10-08 | Antonio Sanchez | Put panel back on wing wall and housekeeping | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 3 | 11 | No |  | Boomlift forklift | No |  |  | No |  | Caulking | [20 empty] | 54 | 11
24068 | QTS NAL1 DC2 | 2025-10-08 | Marvin Blanco | Working in the freedom wall | Subcontractor | Joe Hoyle | No |  | No |  | Raining | 1 | 12 | Yes | Boomlift | Scissors lift and boomlift | No |  |  | Yes | Everything | ACM | 9 | 48
24068 | QTS NAL1 DC2 | 2025-10-08 | Chad mccoy | Crates are miss labeled and we are running into Panela with wrong labels | Subcontractor | Joe Hoyle | Yes | Crates are miss labeled and we are running into Panela with wrong labels | Yes | Louver material. Acm for expansion joint and extra acm to remake panels around doors on stair tower | Clear and chilly | 6 | 10 | No |  | 65 foot boom | No |  |  | Yes | Eastvelevation | ACM | 60 | 8.2
24069 | TCAT Pulaski | 2025-10-08 | Chris Henriquez | Completed soffit and walll | Subcontractor | Chris Buttrey | No |  | No |  | No weather | 4 | 11 | No |  | 1 boom, 2 scissor, 1 forklift | No |  |  | Yes | Soffit | Soffit
24069 | TCAT Pulaski | 2025-10-08 | JC Panels | None | Subcontractor | Chris Buttrey | No |  | Yes | Flashing panels rivets | Good | 6 | 60 | No |  |  | No |  |  | Yes | All | Genesis | [14 empty] | 54
24089 | BSU Innovation Center | 2025-10-08 | Obed Bermudez | We continue working on south elevation, Installing strongirt, flashing, insulation, and panels. We found 3 damaged paneles that measure 15' 5" from bundle #5. | Subcontractor | Marc Ribar | No |  | No |  | Clear | 6 | 10 | No |  | Boom lift and forklift | No |  |  | Yes | East and south. | Flashing Insulation Single Skin Subgirt Zee | [6 empty] | 42 | 20 | [18 empty] | 375 | 20 |  |  | 225 | 15 | 83 | 5
25007 | QTS ATL2 DC10 | 2025-10-08 | Marvin Blanco | Today the job site was closed because yesterday night someone caused an accident | JWMCD Crew | Nick Akins | Yes | Coping bolted flat sheets for under the platform | Yes | Flat sheets for under the platform bolts for the louvers blades | Good condition | 4 | 12 | No |  | Scaffolding | No |  |  | No |  | Louvre | [24 empty] | 10 | 48
25022 | Vantage VA15 | 2025-10-08 | Marvin Blanco | Working in installing Zs and insulation | Subcontractor | Thomas Mooers | No |  | Yes | Flashing for around the windows | Good condition | 4 | 10 | No |  | Boomlift | No |  |  | Yes | Everything | Subgirt Zee | [30 empty] | 200 | 40
24028 | CHI Memorial Hospital | 2025-10-07 | JC Pnels | Tomorrow we are going to receive delivery so we are good. | Subcontractor | Josh McPherson | No |  | No |  | Good | 7 | 70 | No |  |  | No |  |  | Yes | South north | ACM Single Skin | 11 | [5 empty] | 6
24030 | Vantage TX-21 | 2025-10-07 | Naza Padron | N/A | Subcontractor | Chris Buttrey | No |  | Yes | blue reveals and window L trim | sunny | 5 | 50 | No |  | 2- 85' Boom Lifts | No |  |  | No |  | ACM Caulking | 14 | 32 | [18 empty] | 60 | 18
24045 | TMMMS Childcare | 2025-10-07 | Starlin |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 4 | 10 | false |  | Boom Scissors lift and forklift | false |  |  |  |  | ACM Other Subgirt Zee Trim | 10 | 4 | [28 empty] | 40 | 1 |  |  |  |  | 30 | 1 |  |  |  |  | Today the guys worked on the back of the building and made the finished 585 detail. And also started 611 parapit in roof today and we are waiting for the facia for main entrance 611 and 5 nahichi panels | 4
24046 | UAB Biomedical Research and Psycholgy | 2025-10-07 | Zarur Nazario Padron Jr | Installing ACM panels, Corrugated panels, Zee’s, Flashing, and cleaning up on the roof. 5 guys held up all day on East side due to waiting on Sunbelt to fix swing stage. | JWMCD Crew | Wylie McDougall | true | 5 guys held up all day due to Sunbelt needing to fix swing stage. Got told they were Sunbelt was showing up to fix it but never did. |  |  | Cloudy | 11 | 104 | false |  | 1 swing stage | false |  |  |  |  | ACM Corrugated / Screen wall Other Subgirt Zee | 12 | 28 | [18 empty] | 0 | 0 | 4 | 6 | [6 empty] | 313 | 20 | [11 empty] | 50
24048 | QTS NAL2 DC1 | 2025-10-07 | Antonio Sanchez | Red caulking and peel of panels | Subcontractor | Joe Hoyle | true | Rain | true |  | Raining all day | 3 |  | false |  | Boomlift forklift | false |  |  |  |  | Caulking Other | [20 empty] | 37 | 18 | [20 empty] | Pee lof panels | 9
24068 | QTS NAL1 DC2 | 2025-10-07 | Chad McCoy | Rain all day, I moved crates over. And cleaned up areas while it was raining | Subcontractor | Joe Hoyle | Yes | Weather | Yes | Acm for expansion joint, louvers, extra acm for stair tower | Rain | 1 | 6 | No |  | 65 foot boom | No |  |  | No |  | ACM | 0 | 0
24030 | Vantage TX-21 | 2025-10-06 | Naza Padron | removing Panel film 10 | Subcontractor | Chris Buttrey | No |  | Yes | blue reveals and window L trim | sunny | 5 | 40 | Yes | ACM panels Crates | 2- 85' Boom Lifts | No |  |  | No |  | Caulking Trim | [20 empty] | 90 | 26 | [14 empty] | 60 | 14
24045 | TMMMS Childcare | 2025-10-06 | Starlin |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 4 | 10 | false |  | boom Scissors lift and forklift | false |  |  |  |  | ACM Other Trim | 6 | 7 | [34 empty] | 50 | 4 |  |  |  |  | fab 2 Acm panels, cut and installed 12 nahitchi panels | 10
24046 | UAB Biomedical Research and Psycholgy | 2025-10-06 | Zarur Nazario Padron Jr | Installing ACM panels, Corrugated panels and Zee’s. 4 guys held up for 6 hours each due to waterproofers working on swing stage. 4 guys 2 hours each throwing trash away. | JWMCD Crew | Wylie McDougall | true | 4 guys held up 6 hours each due to waterproofers working on swing stage. |  |  | Cloudy | 11 | 88 | false |  | 2 swing stages | false |  |  |  |  | ACM Corrugated / Screen wall Insulation Subgirt Zee | 18 | 48 | [18 empty] | 0 | 0 | 9 | 21 |  |  | 192 | 3 |  |  | 450 | 16
24048 | QTS NAL2 DC1 | 2025-10-06 | Antonio Sanchez | Housekeeping East Elevation | Subcontractor | Joe Hoyle | false |  | true |  |  | 3 | 12 | false |  | Boomlift forklift | false |  |  |  |  | Caulking | [20 empty] | 150 | 24
24068 | QTS NAL1 DC2 | 2025-10-06 | Chad McCoy | My other team is slow | Subcontractor | Joe Hoyle | No |  | Yes | Extra acm, louver material, acm 4 1/2 pieces for expansion joint on stair tower | 81 clear | 6 | 8 | No |  | 65 foot boom | No |  |  | Yes | East | ACM | 82 | 8
24069 | TCAT Pulaski | 2025-10-06 | JC Panels | Rivets | Subcontractor | Chris Buttrey | false |  | true |  |  | 5 | 50 | false |  |  | false |  |  |  |  | Genesis | [14 empty] | 72
24089 | BSU Innovation Center | 2025-10-06 | Obed Bermudez | We continue workin on the south elevation, installing aluminum channel, strongirt, insulation, flashing and panels. We found 4 damaged panels that measure 6' on bundle 26. | JWMCD Crew | Marc Ribar | [5 empty] | 5 | 10 |  |  | Boom lift and forklift. | [5 empty] | Flashing Insulation Single Skin Subgirt Zee | [6 empty] | 42 | 15 | [18 empty] | 320 | 20 |  |  | 179 | 10 | 10 | 5
24048 | QTS NAL2 DC1 | 2025-10-05 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 5 | 12 | false |  | Boomlift forklift | false |  |  |  |  | Caulking | [20 empty] | 492 | 56
24048 | QTS NAL2 DC1 | 2025-10-05 | Antonio Sanchez | Housekeeping and caulking | Subcontractor | Joe Hoyle | No |  | No |  | Clear | 5 | 11 | No |  | Boomlift forklift | No |  |  | No |  | Caulking | [20 empty] | 492 | 55
24046 | UAB Biomedical Research and Psycholgy | 2025-10-04 | Zarur Nazario Padron Jr | Installing ACM panels, Corrugated panels, Zee’s and Insulation. | JWMCD Crew | Wylie McDougall | true | 4 guys delayed all day from working on west side swing stage due to waterproofers using swing stage. |  |  | Sunny | 10 | 70 | false |  | 1 swing stage | false |  |  |  |  | ACM Corrugated / Screen wall Insulation Subgirt Zee | 21 | 35 | [18 empty] | 0 | 0 | 20 | 20 |  |  | 320 | 5 |  |  | 330 | 10
24048 | QTS NAL2 DC1 | 2025-10-04 | Antonio Sanchez | Install and make trim for elevation 219,220 | Subcontractor | Joe Hoyle | Yes | Boomlift broke down | No |  | Sunny | 7 | 14 | No |  | Boomlift forklift | No |  |  | No |  | Caulking Coping Trim | [20 empty] | 326 | 20 | [14 empty] | 160 | 28 |  |  | 90 | 32
24065 | QTS NAL2 DC2 | 2025-10-04 | Chad mccoy | Louver parts. Extra acm | Subcontractor | Joe Hoyle | false |  | true |  |  | 3 | 8 | false |  | 85 foot boom | false |  |  |  |  | ACM | 15 | 8
24069 | TCAT Pulaski | 2025-10-04 | Chris Henriquez |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 3 | 9.5 | false |  | 1 boom, 2 scissor, 1 lull. | false |  |  |  |  | Other | [42 empty] | Installed panels. | 9.5
24089 | BSU Innovation Center | 2025-10-04 | Obed Bermudez | We continue working on the east elevation, installing flashing, strongirt, flat metal, insulation, and panels. We found 1 damaged panel that measures 6' from bundle 27. 1 damaged panel that measures 15' 5". | JWMCD Crew | Marc Ribar | [5 empty] | 5 | 8 |  |  | Boom lift and forklift. | [5 empty] | Flashing Single Skin | [6 empty] | 60 | 48 | [24 empty] | 133 | 16
24028 | CHI Memorial Hospital | 2025-10-03 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 3 | 30 | false |  |  | false |  |  |  |  | ACM | 13
24030 | Vantage TX-21 | 2025-10-03 | Naza Padron | moving material and trash 6 hours | Subcontractor | Chris Buttrey | No |  | No |  | sunny | 5 | 50 | No |  | 2- 85' Boom Lifts | No |  |  | No |  | ACM Caulking | 10 | 32 | [18 empty] | 50 | 12
24045 | TMMMS Childcare | 2025-10-03 | Kevin Morris |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 2 | 8 | false |  | 1 boom 1 scissor lift and forklift | false |  |  |  |  | Other Trim | [36 empty] | 50 | 2 |  |  |  |  | Nahitchi panels 11 | 6
24046 | UAB Biomedical Research and Psycholgy | 2025-10-03 | Zarur Nazario Padron Jr | Installing Corrugated panels, Zee’s, flashing, ACM panels and Insulation. Also moving materials from East side of job site on to the West side of job site and cutting Zee’s on the West side of the building. | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 10 | 100 | false |  | 2 swing stages | false |  |  |  |  | ACM Corrugated / Screen wall Flashing Insulation Other Subgirt Zee | 1 | 4 | [18 empty] | 0 | 0 | 7 | 16 |  |  | 1280 | 24 |  |  | 255 | 20 | 50 | 10 | [9 empty] | 26
24065 | QTS NAL2 DC2 | 2025-10-03 | Chad mccoy | Louver material, extra acm | Subcontractor | Joe Hoyle | false |  | true |  |  | 3 | 8 | false |  | 85 foot boom | false |  |  |  |  | ACM | 21 | 10.15
24069 | TCAT Pulaski | 2025-10-03 | JC Panels |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 5 | 50 | false |  |  | false |  |  |  |  | Genesis | [14 empty] | 45
24069 | TCAT Pulaski | 2025-10-03 | Chris Henriquez |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 4 | 10 | false |  | 1 boom lift, 2 scissor lifts, 1 lull lift. | false |  |  |  |  | Other | [42 empty] | Installed Genesis panel 1 ground guy, 1 installer west side, 2 installers soffit south side. | 10.5
24089 | BSU Innovation Center | 2025-10-03 | Obed Bermudez | We continue working on the south elevation, installing flashing, strongirt, aluminum channel, and insulation. Aluminum channel installed 80lf. Flat metal installed 80 lf. | JWMCD Crew | Marc Ribar | [5 empty] | 5 | 10 | true | We received a delivery from Morin. | Boom lift and forklift. | [5 empty] | Flashing Insulation Subgirt Zee | [26 empty] | 456 | 25 |  |  | 290 | 15 | 146 | 10
24030 | Vantage TX-21 | 2025-10-02 | Naza Padron | breaking up crates and cleaning 10 hours | Subcontractor | Chris Buttrey | No |  | No |  | sunny | 5 | 50 | No |  | 2- 85' Boom Lifts | No |  |  | No |  | ACM Insulation Subgirt Zee | 08 | 28 | [24 empty] | 96 | 6 |  |  | 50 | 6
24045 | TMMMS Childcare | 2025-10-02 | Kevin Morris |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 2 | 10 | false |  | Boom, scissor, and forklift | false |  |  |  |  | Caulking Other Trim | [20 empty] | 60 | 3 | [14 empty] | 60 | 2 |  |  |  |  | Moved material we need to work area, Install 15 nahitchi panels | 5
24065 | QTS NAL2 DC2 | 2025-10-02 | Chad mccoy | Louver material. Extra acm. | Subcontractor | Joe Hoyle | true | The panels that wrap the wing wall do not fit. There is a 5 1/4 bust to make these panels work. | true |  | Clear and cool | 6 | 9 | false |  | 85 foot boom. Gave to Antonio for the weekend | false |  |  |  |  | ACM Insulation Subgirt Zee | 27 | 8 | [24 empty] | 100 | 1 |  |  | 150 | 1
24069 | TCAT Pulaski | 2025-10-02 | Chris henriquez |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 5 | 11 | false |  | 1 boom lift, 2 scissor lift, 1 lull lift | false |  |  |  |  | Other | [42 empty] | Installed panels, flashing, prepared panels | 11
24089 | BSU Innovation Center | 2025-10-02 | Obed Bermudez | We continue workin on the south elevation, installing aluminum channel, strongirt, insulation, and flashing. | JWMCD Crew | Marc Ribar | [5 empty] | 5 | 10 |  |  | Boom lifts and forklift. | [5 empty] | Flashing Insulation Subgirt Zee | [26 empty] | 160 | 15 |  |  | 220 | 20 | 50 | 5
24028 | CHI Memorial Hospital | 2025-10-01 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 6 | 60 | false |  |  | false |  |  |  |  | ACM | 15
24030 | Vantage TX-21 | 2025-10-01 | Naza Padron | We are not working today due to inspections carried out by HITT at the job site | Subcontractor | Chris Buttrey | No |  | No |  | sunny | 5 | 00 | No |  | 2- 85' Boom Lifts | No |  |  | No |  | ACM | 0 | 0
24045 | TMMMS Childcare | 2025-10-01 | Kevin Morris |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 2 | 10 | false |  | 1 boom 1 scissor lift and forklift | false |  |  |  |  | Caulking Other | [20 empty] | 220 | 9 | [20 empty] | Counter sink and caulked over screw on soffit | 1
24046 | UAB Biomedical Research and Psycholgy | 2025-10-01 | Zarur Nazario Padron Jr | Installing Perforated panels, Zee’s, drip and J flashing and insulation. | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 10 | 96 | false |  | 2- swing stages and 2 scaffolds | false |  |  |  |  | ACM Flashing Insulation Perforated Subgirt Zee | 10 | 28 | [18 empty] | 0 | 0 | 20 | 18 |  |  | 64 | 2 |  |  | 1150 | 36 | 152 | 12
24065 | QTS NAL2 DC2 | 2025-10-01 | Chad mccoy | Louver material. Coping and acm flat stick for stair tower door. And red caulking | Subcontractor | Joe Hoyle | true | The gap from dens deck to top of window and panel next to it is 3 3/4. It will need a hat channel to fill this void | true |  | Nice and cool | 6 | 8 | true | Nick brought material for Marvin and antonio | 65 foot boom | false |  |  | 2.5 |  | ACM Insulation Layout Subgirt Zee | 22 | 7 | [24 empty] | 450 | 1.5 |  |  | 300 | 1.5
24069 | TCAT Pulaski | 2025-10-01 | JC Panels |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 5 | 50 | false |  |  | false |  |  |  |  | Genesis Other | [42 empty] | We finish the punch list of the first building
24069 | TCAT Pulaski | 2025-10-01 | Chris Henriquez |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 5 | 10 | false |  | 1 boom lift, 2 scissor lift, 1 lull lift | false |  |  |  |  | Other | [42 empty] | Installed panels, put more prepared material on roof, punch list | 10
24089 | BSU Innovation Center | 2025-10-01 | Obed Bermudez |  | JWMCD Crew | Marc Ribar | [5 empty] | 5 | 10 |  |  | Boom lift and forklift | [5 empty] | Flashing Insulation Single Skin Subgirt Zee | [6 empty] | 6 | 10 | [18 empty] | 150 | 18 |  |  | 180 | 18 | 15 | 4
25002 | Med Center Health | 2025-10-01 | Marvin Blanco | Working in the walls installing the Zs and insulation waiting for flashing around the windows | Subcontractor | Carlos Silva | true | Flashing around the windows | true |  | Good condition | 4 | 11 | true | Insulation | Boomlift | false |  |  |  |  | Subgirt Zee | [30 empty] | 35 | 44
25007 | QTS ATL2 DC10 | 2025-10-01 | Marvin Blanco | Needing the metal panels in the roof for the penthouse but JWM needs to rent a crane because HITT doesn't let us use the boomlift we are needing 13 angles 4"×4"×4" for the louvers | Subcontractor | Nick Akins | false |  | true |  |  | 5 | 12 | false |  | Scaffolding | false |  |  |  |  | Louvre | [24 empty] | 20 | 60
24028 | CHI Memorial Hospital | 2025-09-30 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 6 | 60 | false |  |  | false |  |  |  |  | ACM Insulation Subgirt Zee | 8
24030 | Vantage TX-21 | 2025-09-30 | Naza Padron | N/A | Subcontractor | Chris Buttrey | No |  | No |  | sunny | 5 | 40 | No |  | 2- 85' Boom Lifts | No |  |  | No |  | ACM | 8 | 40
24045 | TMMMS Childcare | 2025-09-30 | Kevin Morris |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 2 | 10 | true | Acm panels | 60' boom, scissor lift and forklift | false |  |  |  |  | Caulking Other | [20 empty] | 120 | 8 | [20 empty] | Counter sink and caulk over screw holes on nahitchi panels | 2
24046 | UAB Biomedical Research and Psycholgy | 2025-09-30 | Zarur Nazario Padron Jr | Installing Perforated panels, Zee’s, ACM panels, insulation and j flashing. It took 2 guys 3 hours each to unload the delivery. | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 8 | 80 | true | 6 crates and one pallet | 1 swing stage and 2 scaffolds | false |  |  |  |  | ACM Flashing Insulation Other Perforated Subgirt Zee | 8 | 16 | [18 empty] | 0 | 0 | 15 | 28 |  |  | 64 | 4 |  |  | 425 | 12 | 100 | 14 | [9 empty] | 6
24065 | QTS NAL2 DC2 | 2025-09-30 | Chad McCoy | Louver material. Extra acm to make stair tower panels around doors. | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 8.5 | false |  | 85 foot boom | false |  |  |  |  | ACM Insulation Subgirt Zee | 18 | 7 | [24 empty] | 720 | 2.5 |  |  | 1020 | 2.5
24069 | TCAT Pulaski | 2025-09-30 | Chris Henriquez |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 5 | 10 | false |  | 1 boom, 2 scissors, 1 lull | false |  |  |  |  | Other | [42 empty] | Installed panels, sorted Inventory, Put panels on the roof. | 10
24089 | BSU Innovation Center | 2025-09-30 | Obed Bermudez | We continue working on the east elevation, installing aluminum channel, flashing, strongirt, insulation, and panels. We also continue finding damaged panels when opening bundles. | JWMCD Crew | Marc Ribar | [5 empty] | 5 | 10 |  |  | Boom lift and forklift. | [5 empty] | Flashing Insulation Single Skin Subgirt Zee | [6 empty] | 24 | 20 | [18 empty] | 280 | 10 |  |  | 160 | 10 | 163 | 10
24030 | Vantage TX-21 | 2025-09-29 | Naza Padron | 6 panels cutt and routed 6 hours | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 45 | false |  | 86' boom | false |  |  |  |  | ACM Insulation Subgirt Zee | 8 | 26 | [24 empty] | 64 | 5 |  |  | 80 | 8
24045 | TMMMS Childcare | 2025-09-29 | Kevin Morris |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 2 | 10 | true | Nahitchi J's | 1 60' boom' 1 scissor lift and forklift | false |  |  |  |  | Caulking Other | [20 empty] | 130 | 7 | [20 empty] | Removed 14 panels on roof so gc can cut out scuppers | 3
24046 | UAB Biomedical Research and Psycholgy | 2025-09-29 | Zarur Nazario Padron jr | Installing ACM panels, removing plastic off panels, installing Perforated panels, drip and J flashing and Zee’s | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 48 | false |  | 1 swing stage | false |  |  |  |  | ACM Flashing Perforated Subgirt Zee | 24 | 28 | [18 empty] | 0 | 0 | 10 | 12 | [6 empty] | 120 | 6 | 60 | 2
24065 | QTS NAL2 DC2 | 2025-09-29 | Chad McCoy | Coping. Acm flat stock. Louver material. | Subcontractor | Joe Hoyle | false |  | true |  |  | 4 | 8 | false |  | 85 foot boom | false |  |  |  |  | ACM Flashing Insulation Subgirt Zee | 6 | 5 | [24 empty] | 150 | 1 |  |  | 80 | 1 | 25 | 1.5
24069 | TCAT Pulaski | 2025-09-29 | Chris henriquez |  | Subcontractor | Chris Buttrey | true | Missing panels. Prepared panels with J in the meantime so we can advance. | false |  |  | 4 | 10.3 | false |  | 3 boom lift, 1 lull lift | false |  |  |  |  | Other | [42 empty] | Installed Genesis panels and prepared panels with J for installation. | 10.3
24089 | BSU Innovation Center | 2025-09-29 | Obed Bermudez | We continue installing aluminum channel, flashing, strongirt, and panels. We continue finding damaged panels when opening bundles. 20 lf of aluminum channel installed. | JWMCD Crew | Marc Ribar | [5 empty] | 3 | 10 |  |  | Forklift and boom lift | [5 empty] | Flashing Insulation Single Skin Subgirt Zee | [6 empty] | 28 | 15 | [18 empty] | 110 | 5 |  |  | 70 | 5 | 174 | 10
24048 | QTS NAL2 DC1 | 2025-09-28 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 4 | 8 | false |  | Boomlift forklift | false |  |  |  |  | ACM | 46 | 32
24046 | UAB Biomedical Research and Psycholgy | 2025-09-27 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s, insulation and Perforated panels. | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 9 | 72 | false |  | 1- swing stage | false |  |  |  |  | ACM Flashing Insulation Perforated Subgirt Zee | 8 | 15 | [18 empty] | 0 | 0 | 14 | 10 |  |  | 640 | 12 |  |  | 215 | 30 | 30 | 5
24048 | QTS NAL2 DC1 | 2025-09-27 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 8 | 11 | false |  | Boomlift forklift | false |  |  |  |  | ACM | 68 | 60
24069 | TCAT Pulaski | 2025-09-27 | Chris Henriquez |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 6 | 9.3 | false |  | 3 boom lift, 1 lull lift | false |  |  |  |  | Other | [42 empty] | Installed Genesis panel + received shipment. | 9.3
24069 | TCAT Pulaski | 2025-09-27 | JC Panels | Flashing and cover plates | Subcontractor | Chris Buttrey | false |  | true |  |  | 5 | 50 | false |  |  | false |  |  |  |  | Genesis | [14 empty] | 25
24089 | BSU Innovation Center | 2025-09-27 | Obed Bermudez | We continue installing flashing and panels on the east elevation. | JWMCD Crew | Marc Ribar | [5 empty] | 3 | 8 |  |  | Boom lift and forklift. | [5 empty] | Flashing Single Skin | [6 empty] | 46 | 20 | [24 empty] | 100 | 4
24028 | CHI Memorial Hospital | 2025-09-26 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 6 | 60 | false |  |  | false |  |  |  |  | ACM Single Skin | 7 | [5 empty] | 13
24030 | Vantage TX-21 | 2025-09-26 | Naza Padron | 7 panels cutt and routed 6 hours, 6 light penetrations cut into soffit panels 4 huors | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | ACM Insulation Subgirt Zee | 7 | 26 | [24 empty] | 96 | 6 |  |  | 60 | 8
24045 | TMMMS Childcare | 2025-09-26 | Starlin |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 2 | 9 | false |  | 45 boom Scissors lift and forklift | false |  |  |  |  | Caulking Other | [20 empty] | 160 | 8 | [20 empty] | Closed the gap on the flashing above two windows | 1
24046 | UAB Biomedical Research and Psycholgy | 2025-09-26 | Zarur Nazario Padron Jr | Installing ACM panels, Perforated panels, Zee’s and drip flashing. | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 9 | 90 | false |  | 1- swing stage | false |  |  |  |  | ACM Flashing Perforated | 32 | 40 | [18 empty] | 0 | 0 | 18 | 20 | [6 empty] | 210 | 20 | 30 | 10
24048 | QTS NAL2 DC1 | 2025-09-26 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 8 | 11 | false |  | Boomlift forklift | false |  |  |  |  | ACM | 96 | 88
24069 | TCAT Pulaski | 2025-09-26 | JC Panels |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 5 | 50 | false |  |  | false |  |  |  |  | Genesis | [14 empty] | 14
24069 | TCAT Pulaski | 2025-09-26 | Chris Henriquez |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 6 | 10 | false |  | 2 boom lift, 1 lull lift | false |  |  |  |  | Other | [42 empty] | Installed Genesis Panel and threw away empty pallets. | 10
24089 | BSU Innovation Center | 2025-09-26 | Obed Bermudez | We continue working the east elevation, installing z girt, flashing, and panels. | JWMCD Crew | Marc Ribar | [5 empty] | 3 | 10 |  |  | Boom lift and forklift. | [5 empty] | Flashing Single Skin Subgirt Zee | [6 empty] | 22 | 25 | [22 empty] | 20 | 1 | 21 | 4
24028 | CHI Memorial Hospital | 2025-09-25 | JC Panels | 2” z’s Morin panels and flashings | Subcontractor | Josh McPherson | false |  | true |  |  | 6 | 60 | false |  |  | false |  |  |  |  | ACM | 13
24030 | Vantage TX-21 | 2025-09-25 | Naza Padron | 4 panels cutt and router 6 hours | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | ACM Insulation Subgirt Zee | 9 | 26 | [24 empty] | 192 | 8 |  |  | 120 | 10
24045 | TMMMS Childcare | 2025-09-25 | Starlin |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 3 | 9 | false |  | 45 boom Scissors lift and forklift | false |  |  |  |  | ACM Caulking Other | 1 | 2 | [18 empty] | 90 | 5 | [20 empty] | missing screws on playground area and changed out panel in playground area | 2
24046 | UAB Biomedical Research and Psycholgy | 2025-09-25 | Zarur Nazario Padron Jr | Installing ACM panels, Perforated panels, Zee’s, and J-flashing. | JWMCD Crew | Wylie McDougall | true | 4 guys delayed 2 hours each due to power on the swing stage going out. |  |  | Sunny | 9 | 82 | false |  | 1-swing stage | false |  |  |  |  | ACM Flashing Perforated Subgirt Zee | 28 | 32 | [18 empty] | 0 | 0 | 16 | 20 | [6 empty] | 800 | 20 | 40 | 10
24048 | QTS NAL2 DC1 | 2025-09-25 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 8 | 11 | false |  |  | false |  |  |  |  | ACM Flashing | 40 | [31 empty] | 264 | 22
24069 | TCAT Pulaski | 2025-09-25 | JC Panels |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 5 | 50 | false |  |  | false |  |  |  |  | ACM | 178
24089 | BSU Innovation Center | 2025-09-25 | Obed Bermudez | We continue working on the east elevation installing panels. | JWMCD Crew | Marc Ribar | true |  |  |  | Rain | 3 | 12 |  |  | Boom lift and forklift | [5 empty] | Single Skin | [6 empty] | 24 | 36
24030 | Vantage TX-21 | 2025-09-24 | Naza Padron | N/A | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | ACM Insulation Subgirt Zee | 13 | 40 | [24 empty] | 96 | 4 |  |  | 60 | 6
24045 | TMMMS Childcare | 2025-09-24 | Starlin |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 3 | 10 | false |  | 45 boom scissor lift, and forklift | false |  |  |  |  | Caulking Other | [20 empty] | 110 | 7 | [20 empty] | Countersunk screws-on nahichi soffit panels, replaced nahichi soffit panel with crack | 3
24046 | UAB Biomedical Research and Psycholgy | 2025-09-24 | Zarur Nazario Padron Jr | Installing ACM panels, Perforated panels, Z-spacers, J-flashing and drip flashing. | JWMCD Crew | Wylie McDougall | true | 5 guys only worked 9 hours due to strong winds. |  |  | Cloudy | 10 | 95 | false |  | 1- swing stage | false |  |  |  |  | ACM Flashing Other Perforated | 32 | 45 | [18 empty] | 0 | 0 | 6 | 10 | [6 empty] | 1560 | 20 | 110 | 10 | [9 empty] | 10
24048 | QTS NAL2 DC1 | 2025-09-24 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 8 |  | false |  | Boomlift forklift | false |  |  |  |  | ACM | 40 | 80
24089 | BSU Innovation Center | 2025-09-24 | Obed Bermudez | We continue working on the east elevation, installing z girt, insulation, flat metal, and aluminum channel 20 lf. | JWMCD Crew | Marc Ribar | [5 empty] | 3 | 10 |  |  | Boom lift and forklift | [5 empty] | Flashing Insulation Subgirt Zee | [26 empty] | 300 | 15 |  |  | 170 | 7 | 165 | 8
24028 | CHI Memorial Hospital | 2025-09-23 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 7 | 70 | false |  | 2 boom 1 fork lift | false |  |  |  |  | ACM Other | 11 | [41 empty] | We modify 4 panels that came big to make them work
24046 | UAB Biomedical Research and Psycholgy | 2025-09-23 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s, Window flashing and Insulation. | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 10 | 100 | false |  | 2- swingstages and 1-85’ boomlift | false |  |  |  |  | ACM Insulation Other Subgirt Zee | 27 | 66 | [18 empty] | 0 | 0 | 0 | 0 |  |  | 960 | 14 |  |  | 80 | 6 | [11 empty] | 14
24048 | QTS NAL2 DC1 | 2025-09-23 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 8 | 12 | false |  | Boomlift forklift | false |  |  |  |  | ACM | 60 | 96
24089 | BSU Innovation Center | 2025-09-23 | Obed Bermudez | We continue working on the east elevation, installing z girt, flashing, insulation, and aluminum channel 10 lf. | JWMCD Crew | Marc Ribar | [5 empty] | 3 | 12 |  |  | Boom lift and forklift | [5 empty] | Flashing Insulation Subgirt Zee | [26 empty] | 250 | 12 |  |  | 145 | 12 | 115 | 12
24028 | CHI Memorial Hospital | 2025-09-22 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 7 | 70 | false |  |  | false |  |  |  |  | ACM Caulking | 16
24030 | Vantage TX-21 | 2025-09-22 | Naza Padron | A delivery with ACM Panels material was received, but we cannot obtain the installation Drawings all we received was the engineering... 4 panels were cut and routed by 2 workers spend 5 hours total | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 40 | true | ACM Panels | 86' boom | false |  |  |  |  | ACM Insulation Subgirt Zee | 11 | 35 | [24 empty] | 128 | 4 |  |  | 80 | 6
24046 | UAB Biomedical Research and Psycholgy | 2025-09-22 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s and insulation. Also removing plastic off of panels. | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 10 | 80 | false |  | 1-85’ boomlift, 2-swing stages | false |  |  |  |  | ACM Insulation Other | 24 | 56 | [18 empty] | 0 | 0 | 0 | 0 |  |  | 128 | 2 |  |  | 115 | 16 | [11 empty] | 6
24048 | QTS NAL2 DC1 | 2025-09-22 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 8 | 10 | false |  | Boomlift forklift | false |  |  |  |  | ACM | 43 | 80
24069 | TCAT Pulaski | 2025-09-22 | Kevin Morris |  | Subcontractor | Chris Buttrey | true | Cut down panel 1063 | false |  | Rain/ lightning | 8 | 8.5 | false |  | 3 x 60' boom lifts and a forklift | false |  |  |  |  | Flashing Genesis Subgirt Zee | [14 empty] | 35 | 8 | [14 empty] | 15 | 0.5 | 2 | 0.5
24089 | BSU Innovation Center | 2025-09-22 | Obed Bermudez | We continue working on the east elevation, installing z girt, flashing, and insulation. | JWMCD Crew | Marc Ribar | true |  |  |  | We stopped work due to inclement weather. | 3 | 4 |  |  | Boom lift and forklift. | [5 empty] | Flashing Insulation Subgirt Zee | [26 empty] | 21 | 4 |  |  | 8 | 4 | 16 | 4
24048 | QTS NAL2 DC1 | 2025-09-21 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 5 | 9 | false |  | Boomlift forklift | false |  |  |  |  | ACM | 36 | 40
24030 | Vantage TX-21 | 2025-09-20 | Naza Padron | N/A | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 40 | false |  | 86' boom | false |  |  |  |  | ACM | 14 | 40
24046 | UAB Biomedical Research and Psycholgy | 2025-09-20 | Zarur Nazario Padron Jr | Installing ACM panels and moving materials on to the rooftop. It took 7 guys 5 hours each | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 10 | 70 | false |  | 3- swing stages | false |  |  |  |  | ACM Other | 27 | 35 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | [11 empty] | 35
24048 | QTS NAL2 DC1 | 2025-09-20 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 8 | 11 | false |  | Boomlift forklift | false |  |  |  |  | ACM | 56 | 82
24069 | TCAT Pulaski | 2025-09-20 | Starlin |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 7 | 11 | false |  | 3 boom 65 | false |  |  |  |  | Flashing Genesis | [14 empty] | 128 | 9.5 | [16 empty] | 40 | 1.5
24089 | BSU Innovation Center | 2025-09-20 | Obed Bermudez | We continue working on the east elevation installing strongirt, flat metal and insulation. | JWMCD Crew | Marc Ribar | [5 empty] | 3 | 5 |  |  | Boom lift forklift | [5 empty] | Flashing Insulation Subgirt Zee | [26 empty] | 50 | 5 |  |  | 25 | 5 | 41 | 5
25002 | Med Center Health | 2025-09-20 | Marvin Blanco | Working in installing Zs and also insulation we have one issue around the windows we don't have any flashing and also in the drawings doesn't show anything I hope we can fix this problem soon as possible | Subcontractor | Carlos Silva | true | Flashing around the windows but that is a change order | true |  | Good condition | 4 | 11 | false |  | Boomlift | false |  |  |  |  | Subgirt Zee | [30 empty] | 280 | 48
25007 | QTS ATL2 DC10 | 2025-09-20 | Marvin Blanco | Working in the penthouse installing the corrugated panels and also angles clips for the louvers blades | Subcontractor | Nick Akins | true | Baker scaffolding | true |  | Good condition | 8 | 12 | false |  | scaffolding | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 20 | 96
24030 | Vantage TX-21 | 2025-09-19 | Naza Padron |  | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | ACM Insulation Subgirt Zee | 14 | 38 | [24 empty] | 120 | 4 |  |  | 180 | 8
24045 | TMMMS Childcare | 2025-09-19 | Chris Henriquez |  | Subcontractor | Chris Buttrey | true | Lightning | false |  | 12:30PM - 3:00PM | 4 | 10 | false |  | Lull lift, boom lift, scissor lift | false |  |  |  |  | Other | [42 empty] | Caulking, splice down middle of panels that were missing. Edge of louvres, | 10
24046 | UAB Biomedical Research and Psycholgy | 2025-09-19 | Zarur Nazario Padron Jr | Installing ACM panels, J-flashing, and Zee’s. A lot of time wasted changing out extrusion from left to right. | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 10 | 100 | false |  | 3- swing stages | false |  |  |  |  | ACM Flashing Subgirt Zee | 43 | 64 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 520 | 30 | 16 | 6
24065 | QTS NAL2 DC2 | 2025-09-19 | Chad mccoy | Louvers. Insul. Fri need to be finished by gray so I can work in areas | Subcontractor | Joe Hoyle | false |  | true |  |  | 6 | 7.5 | false |  | 85 foot boom. 3 stolen booms | false |  |  | 1.5 |  | Layout Louvre Other | [24 empty] | 190 | 6 | [16 empty] | 5 verticals. 10 brackets. 150 feet of cross bracing | 4
24068 | QTS NAL1 DC2 | 2025-09-19 | Marvin Blanco | Cleaning all the areas and also finishing all the ACM panels and corrugated panels in the job site the only thing we have left is the freedom wall | Subcontractor | Joe Hoyle | false |  | true |  |  | 4 | 12 | false |  | Boomlift forklift scaffolding | false |  |  |  |  | Other | [42 empty] | Cleaning our areas of work and also taking 2 panels off from the vestibule because the windows guys are getting water inside of the building | 48
24069 | TCAT Pulaski | 2025-09-19 | Kevin Morris |  | Subcontractor | Chris Buttrey | true | Lightning stand down for 45 minutes | false |  | lightning | 5 | 10.5 | true | 60' boom at 11 a.m. | 3 60' boom and 1 forklift | false |  |  |  |  | Flashing Genesis | [14 empty] | 58 | 8 | [16 empty] | 190 | 2.5
24069 | TCAT Pulaski | 2025-09-19 | Starlin |  | Subcontractor | Chris Buttrey | true | 0.5 | false |  | Lightning warning | 5 | 11 | false |  | 3 boom 65 | false |  |  |  |  | Flashing Genesis | [14 empty] | 59 | 8 | [16 empty] | 110 | 3
24089 | BSU Innovation Center | 2025-09-19 | Obed Bermudez | We continue working on the east elevation installing strongirt, flat metal and insulation. aluminum channel 120 lf. | JWMCD Crew | Marc Ribar | [5 empty] | 3 | 10 | true | We received a delivery of mornin mx panels. | Boom lift and forklift | [5 empty] | Flashing Insulation Subgirt Zee | [26 empty] | 64 | 5 |  |  | 36 | 20 | 36 | 5
24028 | CHI Memorial Hospital | 2025-09-18 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 8 | 80 | false |  |  | false |  |  |  |  | ACM Subgirt Zee Trim | 20
24030 | Vantage TX-21 | 2025-09-18 | Naza Padron | 14 panels were cut and routed in total of 20 hours and Zees & insulation were relocated 10 hours | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | ACM | 9 | 20
24045 | TMMMS Childcare | 2025-09-18 | Chris Henriquez |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 4 | 10 | false |  | Boom lift, lull lift, scissor lift | false |  |  |  |  | Other | [42 empty] | Caulking, trim, cut out squares | 10
24046 | UAB Biomedical Research and Psycholgy | 2025-09-18 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s and Insulation. One group of two spent 4 hours each trimming off 5” off of Zee’s so waterproofed could work on corner. | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 10 | 100 | false |  | 3- swing stages | false |  |  |  |  | ACM Insulation Other Subgirt Zee | 34 | 46 | [18 empty] | 0 | 0 | 0 | 0 |  |  | 1088 | 26 |  |  | 360 | 20 | [11 empty] | 8
24065 | QTS NAL2 DC2 | 2025-09-18 | Chad mccoy | Louvers insul. The rest of acm | Subcontractor | Joe Hoyle | false |  | true |  |  | 6 | 12 | true | 8 crates of acm | 85 foot boom that’s ours. 3 stolen booms | false |  |  |  |  | Louvre Other | [24 empty] | 190 | 9 | [16 empty] | 24 louver verticals. 22 louver brackets. 180 feet of cross braces. | 6
24069 | TCAT Pulaski | 2025-09-18 | JC Panels |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 5 | 50 | false |  |  | false |  |  |  |  | ACM | 45
24069 | TCAT Pulaski | 2025-09-18 | Kevin Morris |  | Subcontractor | Chris Buttrey | true | Had to remove panels to change bottom row to correct size panels | false |  |  | 4 | 10.5 | false |  | 2 60' boom and forklift | false |  |  |  |  | Genesis | [14 empty] | 35 | 10.5
24089 | BSU Innovation Center | 2025-09-18 | Obed Bermudez | We continue working on the east elevation installing strongirt, flat metal and insulation. Flat metal 62 lf and aluminum channel 20 lf. | JWMCD Crew | Marc Ribar | [5 empty] | 3 | 10 |  |  | Boom lift | [5 empty] | Insulation Subgirt Zee | [26 empty] | 80 | 15 |  |  | 40 | 15
24028 | CHI Memorial Hospital | 2025-09-17 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 6 | 60 | false |  |  | false |  |  |  |  | ACM Insulation Single Skin Subgirt Zee Trim | 29
24030 | Vantage TX-21 | 2025-09-17 | Naza Padron | 16 ACM Panels were cut and routed by two employees in 22 hours | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | ACM | 10 | 28
24045 | TMMMS Childcare | 2025-09-17 | Chris henriquez |  | Subcontractor | Chris Buttrey | true | Lightning alert | false |  | 1:30pm - 3:30pm | 4 | 10 | false |  | Lull lift boom lift scissor lift | false |  |  |  |  | Other | [42 empty] | Panels and holes that GC asked for. | 10
24046 | UAB Biomedical Research and Psycholgy | 2025-09-17 | Zarur Nazario Padron Jr | Installing ACM panels and Zee’s. We had another delivery truck come in with 6 crates on it. It took 3 guys 4 hours each to look for the guy and unload him. | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 10 | 100 | true | 6 crates | 3-swing stages | false |  |  |  |  | ACM Other Subgirt Zee | 40 | 60 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 120 | 28 | [11 empty] | 12
24065 | QTS NAL2 DC2 | 2025-09-17 | Chad mccoy | Insul Louvers acm | Subcontractor | Joe Hoyle | true | Before I talked about needing addition booms for louvers. We only have one so I stole the rest | true |  | Clear 83 | 6 | 8 | false |  | 85 foot boom | false |  |  |  |  | Louvre | [24 empty] | 160 | 8
24069 | TCAT Pulaski | 2025-09-17 | Kevin Morris |  | Subcontractor | Chris Buttrey | true | Panels not numbered have to measure each panel | false |  | Lightning watch 30 minutes | 4 | 10 | true | Flashing and panels (4 crates) | 2 60' booms and 1 forklift | false |  |  |  |  | Flashing Genesis Trim | [14 empty] | 9 | 7 | [16 empty] | 60 | 1.5 |  |  | 40 | 1
24089 | BSU Innovation Center | 2025-09-17 | Obed Bermudez | We continue working on the east elevation, doing layout, installing strongirt and insulation. We had to move strongirt because the soffit was lowered 1” after we had already installed. | JWMCD Crew | Marc Ribar | [5 empty] | 3 | 10 |  |  | Boom lift | [5 empty] | Flashing Insulation Subgirt Zee | [26 empty] | 144 |  |  |  | 218
24030 | Vantage TX-21 | 2025-09-16 | Naza Padron | N/A | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | ACM Insulation | 18 | 38 | [24 empty] | 180 | 12
24045 | TMMMS Childcare | 2025-09-16 | Chris Henriquez |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 4 | 10 | false |  | Boom lift, scissor lift, lull lift | false |  |  |  |  | Other | [42 empty] | Panels, kick plate, trim | 10
24046 | UAB Biomedical Research and Psycholgy | 2025-09-16 | Zarur Nazario Padron Jr | Installing ACM panels, j-flashing, Insulation, and Zee’s. Unloading truck for delivery took about 3 hours total for 3 guys each | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 10 | 100 | true | 8 crates | 3-swingstages | false |  |  |  |  | ACM Flashing Insulation Other Subgirt Zee | 12 | 50 | [18 empty] | 0 | 0 | 0 | 0 |  |  | 1152 | 20 |  |  | 80 | 9 | 100 | 12 | [9 empty] | 9
24065 | QTS NAL2 DC2 | 2025-09-16 | Chad mccoy | Acm Louvers insulation | Subcontractor | Joe Hoyle | false |  | true |  |  | 6 | 8 | false |  | 85 foot boom | false |  |  |  |  | Corrugated / Screen wall Other | [22 empty] | 20 | 3 | [18 empty] | The south side elevation we installed 160 feet of cross bracing and all the bolts. | 7
24089 | BSU Innovation Center | 2025-09-16 | Obed Bermudez | First thing in the morning, we started with safety orientation. Then, we received three deliveries and spent the rest of the day moving material with the trailer to the job site. | JWMCD Crew | Marc Ribar | [5 empty] | 3 | 10 | true | We received three deliveries of strongirt, insulation, flashing and channels. | Boom lift
24030 | Vantage TX-21 | 2025-09-15 | Naza Padron |  | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 40 | false |  | 86' boom | false |  |  |  |  | ACM | 14 | 40
24045 | TMMMS Childcare | 2025-09-15 | Chris Henriquez |  | Subcontractor | Chris Buttrey | true | We were not allowed to work because of lightning. | false |  | Until 10AM | 3 | 8 | false |  | Boom lift, lull lift, scissor lift. | false |  |  |  |  | ACM | 5 | 8
24046 | UAB Biomedical Research and Psycholgy | 2025-09-15 | Zarur Nazario Padron Jr | Installing Zee’s. Sunbelt came out to move a swing stage towards bridge side of the building. 5 guys wasted 8 hours each waiting on swing stage | JWMCD Crew | Wylie McDougall | true | 5 guys held up all day due to Sunbelt moving swing stage. |  |  | Sunny | 9 | 72 | false |  | 3- swing stages | false |  |  |  |  | Subgirt Zee | [20 empty] | 0 | 0 | 0 | 0 | [6 empty] | 565 | 40
24065 | QTS NAL2 DC2 | 2025-09-15 | Chad mccoy | Acm Louvers insulation | Subcontractor | Joe Hoyle | true | I cleaned the yard up today bc of everybody else’s trash | true |  | Clear. 86 | 6 | 8 | false |  | 85 foot boom | false |  |  |  |  | Coping Corrugated / Screen wall Flashing Hat Channel | [22 empty] | 54 | 4 | [8 empty] | 80 | 1.5 | 8 | 0.5 |  |  |  |  | 40 | 1.5
24028 | CHI Memorial Hospital | 2025-09-13 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 6 | 60 | false |  |  | false |  |  |  |  | ACM Caulking Trim | 5
24030 | Vantage TX-21 | 2025-09-13 | Naza Padron |  | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 40 | false |  | 86' boom | false |  |  |  |  | ACM | 9 | 40
24030 | Vantage TX-21 | 2025-09-12 | Naza Padron | Waiting for and unloading ACM Crates 10 hours, moving material 6 hours | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 40 | true | Crates ACM Panels | 86' boom | false |  |  |  |  | ACM | 5 | 24
24045 | TMMMS Childcare | 2025-09-12 | Chris Henriquez |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 4 | 10 | false |  | Scissor lift, Lull lift | false |  |  |  |  | Other | [42 empty] | Kick plate, and completed the vents. | 10
24046 | UAB Biomedical Research and Psycholgy | 2025-09-12 | Zarur Nazario Padron Jr | Installing ACM panels, flashing and removing plastic off of panels | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 4 | 32 | false |  | 3- swing stages | false |  |  |  |  | ACM Flashing Other | 11 | 20 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 240 | 8 | [9 empty] | 4
24065 | QTS NAL2 DC2 | 2025-09-12 | Chad mccoy | Louvers acm insulation | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 15 | false |  | 85 foot boom | false |  |  |  |  | Corrugated / Screen wall Flashing Insulation Subgirt Zee | [22 empty] | 27 | 7 |  |  | 620 | 2.5 |  |  | 20 | 2 | 175 | 2.5
24045 | TMMMS Childcare | 2025-09-11 | Chris Henriquez |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 4 | 10 | false |  | Scissor lift, Lull lift | false |  |  |  |  | Other | [42 empty] | Installed kick plate | 10
24046 | UAB Biomedical Research and Psycholgy | 2025-09-11 | Zarur Nazario Padron Jr | Installing ACM panels, J-flashing cleaning out material/moving swing stage. | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 9 | 90 | false |  | 3- swing stages | false |  |  |  |  | ACM Flashing Other | 24 | 40 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 42 | 4 | [9 empty] | 46
24046 | UAB Biomedical Research and Psycholgy | 2025-09-11 | Zarur Nazario Padron Jr | Installing ACM panels and J-flashing. 6 workers held up all day due to window guys using sing stage for 2 hours in the morning and swing stages being moved to different location. 60 hours total out of 6 guys | JWMCD Crew | Wylie McDougall | true | Sunbelt and B&G moving swing stages and approving they are safe and well placed. Also window guys using swing stage for 2 hours in the morning. |  |  | Sunny/cloudy | 10 | 100 | true | 320’ of MR2 and 20 boxes of shims. | 3 swing-stages | false |  |  |  |  | ACM Flashing Other | 24 | 32 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 60 | 8 | [9 empty] | 60
24065 | QTS NAL2 DC2 | 2025-09-11 | Chad mccoy | Acm. Louvers. Insulation | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 8 | false |  | 85 foot boom | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 27 | 6 |  |  | 840 | 3 |  |  | 20 | 1
24076 | GCDC Security Building | 2025-09-11 | Obed Bermudez | We threw away 3 pieces of short glass, installed door pin, received a delivery of new glass and proceeded to install. | JWMCD Crew | Nick Akins | [5 empty] | 3 | 10 |  |  | None | [5 empty] | Other | [20 empty] | 15 | [22 empty] | 30
24026 | 1740 Division | 2025-09-10 | JC Panels |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 8 | 80 | false |  |  | false |  |  |  |  | ACM Other | 7 | [41 empty] | Install de trim for both side of the Morin, install flashing for the change order
24046 | UAB Biomedical Research and Psycholgy | 2025-09-10 | Zarur Nazario Padron Jr | Installing ACM panels, removing plastic off of panels, caulking corner in gap between panels. Delivery of 7 crates and 3 guys took 2 hours unloading it each | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 10 | 100 | true | 7 crates of ACM panels | 3- swing stages | false |  |  |  |  | ACM Caulking Other | 24 | 50 | [18 empty] | 98 | 20 | 0 | 0 | [6 empty] | 0 | 0 | [11 empty] | 30
24065 | QTS NAL2 DC2 | 2025-09-10 | Chad mccoy | Acm louvers insulation | Subcontractor | Joe Hoyle | true | We had to get material to the roof and trash off | true |  | Clear | 5 | 8 | false |  | 85 foot boom | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 8 | 1 |  |  | 320 | 2.5 |  |  | 5 | 0.5
24076 | GCDC Security Building | 2025-09-10 | Obed Bermudez | We installed 3 pieces of glass on the doors and installed covers for the bulletproof glass. Caulking 15 lf | JWMCD Crew | Nick Akins | [5 empty] | 3 | 10 |  |  | None | [5 empty] | Other | [43 empty] | 30
24046 | UAB Biomedical Research and Psycholgy | 2025-09-09 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s, J-flashing and Insulation | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 10 | 100 | false |  | 3- swing stages | false |  |  |  |  | ACM Flashing Insulation Subgirt Zee | 15 | 38 | [18 empty] | 0 | 0 | 0 | 0 |  |  | 1344 | 44 |  |  | 148 | 12 | 24 | 6
24048 | QTS NAL2 DC1 | 2025-09-09 | Marvin Blanco | Finishing the soffit panels and silicone | Subcontractor | Joe Hoyle | false |  | true |  |  | 4 | 12 | false |  | Boomlift | false |  |  |  |  | ACM | 7 | 48
24065 | QTS NAL2 DC2 | 2025-09-09 | Chad mccoy | Louvers. Acm. And insul | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 8 | false |  | 85 foot boom | false |  |  |  |  | ACM Subgirt Zee | 20 | 7 | [28 empty] | 23 | 1
24076 | GCDC Security Building | 2025-09-09 | Obed Bermudez | We removed the glass, seals, and caulking to fix the misaligned frame. We also removed and cut a door for the floor mat to fit underneath it. Additionally, we removed three pieces of glass that are short on three doors. | JWMCD Crew | Nick Akins | [5 empty] | 3 | 10 |  |  | None | [5 empty] | Other | [43 empty] | 30
24028 | CHI Memorial Hospital | 2025-09-08 | JCcPanels | Flashing for the ACM on the 1st floor south elevation | Subcontractor | Josh McPherson | false |  | true |  |  | 7 | 70 | true | ACM panels , we finish the screen wall | One boom one fork | false |  |  |  |  | ACM Corrugated / Screen wall Single Skin | 4 | [5 empty] | 3
24046 | UAB Biomedical Research and Psycholgy | 2025-09-08 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s and J-flashing. | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 10 | 80 | false |  | 3-swing stages | false |  |  |  |  | ACM Flashing Subgirt Zee | 17 | 40 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 600 | 48 | 144 | 12
24065 | QTS NAL2 DC2 | 2025-09-08 | Chad mccoy | Insul acm panels. | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 8 | false |  | 85 foot boom | false |  |  |  |  | ACM Subgirt Zee | 45 | 7 | [28 empty] | 31 | 1
24068 | QTS NAL1 DC2 | 2025-09-08 | Marvin Blanco | Working in the coping in the screenwall and also finishing the ACM panels we have a little issue with the coping in the screenwall we don't have enough coping to finish we need another 7 more pieces 70' long clip for the coping also | Subcontractor | Joe Hoyle | false |  | true |  |  | 4 | 12 | true | Silicone | Scaffolding , boomlift and forklift | false |  |  |  |  | Coping | [40 empty] | 200 | 48
25007 | QTS ATL2 DC10 | 2025-09-08 | Marvin Blanco | We are needing more scaffolding to put another crew working in the louvers blades we need more insulation more silicone we don't have any clips for install panels we need tek 5 for install the louvers blades we are asking for this material last week I hope McDougall can get better on this delivery. | Subcontractor | Nick Akins | true | Clips for the metal panels | true |  | Good condition | 4 | 12 | false |  | Scaffolding | false |  |  |  |  | Subgirt Zee | [30 empty] | 200 | 48
25021 | Cooper Steel TN Office | 2025-09-08 | Starlin |  | Subcontractor | Laura Forero | false |  | false |  |  | 2 | 4 | false |  | 60 boom | false |  |  |  |  | Caulking Flashing Other | [20 empty] | 30 | 3 | [10 empty] | 2 | 0.5 | [8 empty] | Peel panel clean our trash and clean our material | 0.5
25021 | Cooper Steel TN Office | 2025-09-07 | Starlin |  | Subcontractor | Laura Forero | false |  | false |  |  | 2 | 9 | false |  | 60 boom | false |  |  |  |  | Caulking Other Trim | [20 empty] | 40 | 4.5 | [14 empty] | 80 | 2.5 |  |  |  |  | Peel Paneles screw Paneles by window clean up | 2
24046 | UAB Biomedical Research and Psycholgy | 2025-09-06 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s and J-flashing. | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 10 | 50 | false |  | 3- swing stages and 1-85’ boomlift | false |  |  |  |  | ACM Flashing Subgirt Zee | 25 | 34 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 90 | 10 | 60 | 6
24028 | CHI Memorial Hospital | 2025-09-05 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 5 | 50 | false |  |  | false |  |  |  |  | ACM Other | 3 | [41 empty] | Side trim on the Morin with rivets.. also few finish the bottom and corners trims on the screen wall
24046 | UAB Biomedical Research and Psycholgy | 2025-09-05 | Zarur Nazario Padron Jr | Installing ACM panels, Insulation and Zee’s. 5 workers held up 2 hours due to waterproofed needing to use smaller swing stages to waterproof missing spot. | JWMCD Crew | Wylie McDougall | true | Waterproofed held up 5 guys for 2 hours |  |  | Sunny/cloudy | 10 | 100 | false |  | 3-swing stages | false |  |  |  |  | ACM Flashing Insulation Other Subgirt Zee | 32 | 55 | [18 empty] | 0 | 0 | 0 | 0 |  |  | 640 | 10 |  |  | 180 | 15 | 60 | 10 | [9 empty] | 10
24065 | QTS NAL2 DC2 | 2025-09-05 | Chad mccoy | Acm, louver missing parts. | Subcontractor | Joe Hoyle | true | Cold form framing had to be adjusted due to area that made panels stick to far out | true |  | Clear | 4 | 8 | false |  | 85 foot boom | false |  |  |  |  | ACM Subgirt Zee | 10 | 4 | [28 empty] | 270 | 2.5
25007 | QTS ATL2 DC10 | 2025-09-05 | Marvin Blanco | Unloading material from the trucks to the roof the guys was waiting all day because the Crane guys took forever to have everything ready they started working at 4 pm all day lose because the Crane guys | Subcontractor | Nick Akins | false |  | true |  |  | 4 | 16 | true | Corrugated panels and louvers blades | Crane | false |  |  |  |  | Other | [42 empty] | Unloading material | 64
25021 | Cooper Steel TN Office | 2025-09-05 | Starlin |  | Subcontractor | Laura Forero | false |  | false |  |  | 3 | 9 | false |  | 60 boom | false |  |  |  |  | Caulking Flashing Other Trim | [20 empty] | 20 | 1 | [10 empty] | 6 | 0.5 |  |  | 100 | 3 |  |  |  |  | Longboard and peel ACM | 4.5
24028 | CHI Memorial Hospital | 2025-09-04 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 5 | 50 | true | We did also caulking and guys are finishing the screen wall of the roof | Boom and fork lift | false |  |  |  |  | ACM | 5
25021 | Cooper Steel TN Office | 2025-09-04 | Starlin |  | Subcontractor | Laura Forero | true | How to change out pre-existing Paneles with new Paneles because the batch didn’t match | false |  | 0.5 | 3 | 8 | false |  | 60 boom | false |  |  |  |  | Flashing Other Trim | [32 empty] | 14 | 0.5 |  |  | 50 | 1 |  |  |  |  | Longboard/knotwood | 6
24028 | CHI Memorial Hospital | 2025-09-03 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 5 | 50 | false |  |  | false |  |  |  |  | ACM Insulation Single Skin Subgirt Zee | 5 | [5 empty] | 9
24030 | Vantage TX-21 | 2025-09-03 | Naza Padron | Day 09/02/25 no work was done, waterproofers needed to seal windows in order to proceed with the installation of panels | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 3 | 30 | false |  | 86' boom | false |  |  |  |  | ACM | 11 | 30
24046 | UAB Biomedical Research and Psycholgy | 2025-09-03 | Zarur Nazario Padron Jr | Installing ACM panels, Insulation and flashing for the windows. 5 guys held up all day due to window guys working on the swing stage from 6AM till 4PM. | JWMCD Crew | Wylie McDougall | true | 5 guys held up from 6AM till 4PM because of window guys working on swing stage. |  |  | Sunny | 9 | 90 | false |  | 3-swing stages | false |  |  |  |  | ACM Flashing Insulation Other | 6 | 8 | [18 empty] | 0 | 0 | 0 | 0 |  |  | 1280 | 32 |  |  | 0 | 0 | 30 | 10 | [9 empty] | 40
24065 | QTS NAL2 DC2 | 2025-09-03 | Chad mccoy | Acm. Corrugated louver missing parts. Prints that actually go with acm | Subcontractor | Joe Hoyle | true | 5 panels had to be removed bc of sign | true |  | Clear | 5 | 8.5 | false |  | 85 foot boom | false |  |  |  |  | ACM Subgirt Zee | 17 | 7 | [28 empty] | 360 | 1.5
25021 | Cooper Steel TN Office | 2025-09-03 | Starlin |  | Subcontractor | Laura Forero | false |  | false |  |  | 3 | 7 | false |  | 60 boom | false |  |  |  |  | ACM | 7 | 7
23064 | Yondr Allegro 2S | 2025-09-02 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Boom lift | [5 empty] | Other | [42 empty] | FRP panels 27 | 60
24028 | CHI Memorial Hospital | 2025-09-02 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 5 | 50 | true | Received insolation flashing panels caulking |  | false |  |  |  |  | ACM Insulation Single Skin | 7 | [5 empty] | 2
24046 | UAB Biomedical Research and Psycholgy | 2025-09-02 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s, J-flashing and insulation. 5 guys have been held up from 8AM all the way till 4PM because window guys are occupying our swing stage. | JWMCD Crew | Wylie McDougall | true | Window guys have been using our swing stage to finish up their work. From 8AM till 4PM |  |  | Cloudy | 9 | 90 | false |  | 3-swing stages | false |  |  |  |  | ACM Flashing Insulation Other Subgirt Zee | 3 | 6 | [18 empty] | 0 | 0 | 0 | 0 |  |  | 192 | 6 |  |  | 400 | 28 | 42 | 6 | [9 empty] | 44
24065 | QTS NAL2 DC2 | 2025-09-02 | Chad mccoy | Corrugated. Missing louver parts. Acm. Insulation. | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 11 | false |  | 85 foot boom | false |  |  | 1.5 |  | ACM Corrugated / Screen wall Insulation Layout Subgirt Zee | 31 | 7 | [20 empty] | 10 | 1 |  |  | 150 | 0.5 |  |  | 1020 | 2.5
25021 | Cooper Steel TN Office | 2025-09-02 | Kevin Morris |  | Subcontractor | Laura Forero | false |  | false |  |  | 3 | 7 | true | Acm | Boom 60' | false |  |  |  |  | ACM | 8 | 7
23064 | Yondr Allegro 2S | 2025-08-30 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Se instalo de regreso los paneles corrugados 8 horas |  |  |  | 5 | 8 | [8 empty] | Other | [42 empty] | Frp 14 | 40
23064 | Yondr Allegro 2S | 2025-08-29 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 5 | 10 |  |  | Boom lifts | [5 empty] | Other | [42 empty] | Frp panels 20 | 50
24045 | TMMMS Childcare | 2025-08-29 | Kevin Morris |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 2 | 6 | false |  | Boom and forklift | false |  |  |  |  | ACM Other | 3 | 2 | [40 empty] | Kick plate 50 LF. unloaded materials cleaned up. | 4
24046 | UAB Biomedical Research and Psycholgy | 2025-08-29 | Zarur Nazario Padron Jr | Installing ACM panels and Zee’s on North side of building. Also installing ACM panels underneath bridge connector. Cleaning up materials and pallets. | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 9 | 90 | false |  | 2- swing stages and 2-boomlifts | false |  |  |  |  | ACM Other Subgirt Zee | 45 | 48 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 360 | 24 | [11 empty] | 18
23064 | Yondr Allegro 2S | 2025-08-28 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 5 | 10 |  |  | Boom lifts | [5 empty] | Other | [42 empty] | Fro panels 19 | 50
24030 | Vantage TX-21 | 2025-08-28 | Naza Padron | We are still waiting for details to resolve the unevenness of the soffit in the photo | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 40 | false |  | 86' boom | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 544 | 16 |  |  | 410 | 24
24045 | TMMMS Childcare | 2025-08-28 | Kevin Morris |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 2 | 10 | false |  | Boom and forklift | false |  |  |  |  | Other | [42 empty] | Kick plate 170 feet | 10
24046 | UAB Biomedical Research and Psycholgy | 2025-08-28 | Zarur Nazario Padron Jr | Installing ACM panels, Insulation and Zee’s on North side wall. 4 guys got delayed 8 hours due to moving area, moving material and boom lift. Also making panels fit in their place because they weren’t fitting well. They got moved to under under bridge on connector. | JWMCD Crew | Wylie McDougall | true | Moving area, moving material and boomlift due to waterproofing guys using our swing stage. |  |  | Cloudy | 9 | 82 | false |  | 2- swing stages and 1- boomlift | false |  |  |  |  | ACM Insulation Other Subgirt Zee | 18 | 44 | [18 empty] | 0 | 0 | 0 | 0 |  |  | 512 | 10 |  |  | 130 | 12 | [11 empty] | 16
24068 | QTS NAL1 DC2 | 2025-08-28 | Marvin Blanco | Working in the roof with the coping and also sealing all the ACM panels | Subcontractor | Joe Hoyle | false |  | true |  |  | 4 | 12 | false |  | Scaffolding | false |  |  |  |  | Coping | [40 empty] | 200 | 48
23064 | Yondr Allegro 2S | 2025-08-27 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 7 | 10 |  |  | Boom lifts | [5 empty] | Other | [42 empty] | Fro panels 25 | 70
24005 | GCDC Building 2/VA1.2 | 2025-08-27 | Obed Bermudez | Received a delivery of a screen wall panel and replaced it, then proceeded to clean up and also clean up some material from the security room. | JWMCD Crew | Joe Hoyle | [5 empty] | 1 | 10 |  |  | None | [5 empty] | Corrugated / Screen wall | [22 empty] | 1
24030 | Vantage TX-21 | 2025-08-27 | Naza Padron | We are waiting for details to be confirmed so we know the solution for modifying this soffit circled in the picture | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | Insulation Subgirt Zee Trim | [26 empty] | 608 | 16 |  |  | 380 | 18 |  |  |  |  | 200 | 16
24045 | TMMMS Childcare | 2025-08-27 | Kevin Morris |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 2 | 6 | false |  | Boom forklift and scissor | false |  |  |  |  | Other | [42 empty] | Kick plate 80 feet | 6
24046 | UAB Biomedical Research and Psycholgy | 2025-08-27 | Zarur Nazario Padron Jr | Installing ACM panels and Zee’s. Moving the swing stage over to work on the next area. B&G required us to move our material once again and it took up 2 hours for 3 guys. | JWMCD Crew | Wylie McDougall | true | Moving materials over to another section B&G gave us. (3 workers 2 hours each). B&G also had delayed us from working so they could put another swing stage up on canopy. (4 guys 1 hour each) |  |  | Sunny | 9 | 90 | false |  | 2- swing stages and 1- boomlift | false |  |  |  |  | ACM Other Subgirt Zee | 28 | 60 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 130 | 10 | [11 empty] | 20
23064 | Yondr Allegro 2S | 2025-08-26 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Remove corrugated panels total 5 hours |  |  |  | 5 | 10 | [8 empty] | Other | [42 empty] | Fro 7 | 10
24028 | CHI Memorial Hospital | 2025-08-26 | JC Panels | Rivets, screen wall screws, insulation, parallel accessories 70 pieces of Morin panels | Subcontractor | Josh McPherson | false |  | true |  |  | 6 | 60 | false |  |  | false |  |  |  |  | ACM Insulation Single Skin Subgirt Zee | 5 | [5 empty] | 10
24030 | Vantage TX-21 | 2025-08-26 | Naza Padron | N/A | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | ACM Insulation Subgirt Zee | 12 | 30 | [24 empty] | 128 | 8 |  |  | 100 | 22
24046 | UAB Biomedical Research and Psycholgy | 2025-08-26 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s, Insulation and removing paper film off of panels on North side of the building. (I had forgotten to put on the daily of 8/25/25 that we had a delivery and it used 4 hours worth of time.) | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 9 | 90 | false |  | 2- swing stages and 1- boomlift | false |  |  |  |  | ACM Insulation Other Subgirt Zee | 31 | 59 | [18 empty] | 0 | 0 | 0 | 0 |  |  | 704 | 9 |  |  | 200 | 20 | [11 empty] | 2
24068 | QTS NAL1 DC2 | 2025-08-26 | Marvin Blanco | Putting silicone in all the panels and finishing the ACM panels what we have ready because WT guys are to slow 🐌 for having areas ready | Subcontractor | Joe Hoyle | false |  | true |  |  | 4 | 12 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM | 8 | 48
23064 | Yondr Allegro 2S | 2025-08-25 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Boom lifts | [5 empty] | Other | [42 empty] | Fro panels 31 | 60
24030 | Vantage TX-21 | 2025-08-25 | Naza Padron | n/a | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 40 | false |  | 86' boom | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 544 | 14 |  |  | 330 | 26
24046 | UAB Biomedical Research and Psycholgy | 2025-08-25 | Zarur Nazario Padron Jr | Installing ACM panels, Zee’s, and J-flashing . | JWMCD Crew | Wylie McDougall | true | 4 guys got delayed from 11:00AM till 2:30 PM due to waterproofing guys needing to use the swing stage to waterproof missing piece on North side wall |  |  | Cloudy | 9 | 90 | false |  | 2-swing stages and 1- boomlift | false |  |  |  |  | ACM Flashing Other Subgirt Zee | 20 | 50 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 180 | 20 | 20 | 2 | [9 empty] | 18
25021 | Cooper Steel TN Office | 2025-08-25 | Starlin |  | Subcontractor | Laura Forero | false |  | false |  |  | 3 | 8 | false |  | 60 booo | false |  |  |  |  | Caulking Flashing Trim | [20 empty] | 120 | 7 | [10 empty] | 12 | 0.5 |  |  | 40 | 0.5
23064 | Yondr Allegro 2S | 2025-08-23 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 6 |  |  |  | Boom lift | [5 empty] | Other | [42 empty] | Fro panels 24 | 8
24028 | CHI Memorial Hospital | 2025-08-23 | JC Panels | Paralel accessories, screen wall screws, insolation, rivets | Subcontractor | Josh McPherson | false |  | true |  |  | 6 | 60 | false |  | Boom lift | false |  |  |  |  | ACM Insulation Single Skin
24046 | UAB Biomedical Research and Psycholgy | 2025-08-23 | Zarur Nazario Padron Jr | Installing ACM panels, Insulation and J-flashing | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 8 | 64 | false |  | 2-swing stages and 1- boomlift | false |  |  |  |  | ACM Flashing Insulation | 31 | 52 | [18 empty] | 0 | 0 | 0 | 0 |  |  | 256 | 6 |  |  | 40 | 2 | 60 | 4
24065 | QTS NAL2 DC2 | 2025-08-23 | Chad McCoy | Acm. Corrugated. Insulation. And louvers | Subcontractor | Joe Hoyle | false |  | true |  |  | 2 | 8 | false |  | 85 foot boom | false |  |  | 4 |  | Layout Other | [42 empty] | 40 verticals were installed and 16 brackets. | 3
24030 | Vantage TX-21 | 2025-08-22 | Naza Padron | n/a | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 25 | false |  | 86' boom | false |  |  |  |  | ACM | 5 | 25
24046 | UAB Biomedical Research and Psycholgy | 2025-08-22 | Zarur Nazario Padron Jr | Installing ACM Panels and Insulation. 4 workers got delayed 4 and half hours due to B&G wanting materials moved to a different location because of pouring of concrete. | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 8 | 80 | false |  | 2- swing stages and 1- boomlift | false |  |  |  |  | ACM Insulation Other | 33 | 54 | [18 empty] | 0 | 0 | 0 | 0 |  |  | 256 | 6 |  |  | 0 | 0 | [11 empty] | 20
24048 | QTS NAL2 DC1 | 2025-08-22 | Marvin Blanco | Working in the soffit but the guys couldn't finish because we have 3 missing panels so we have to stop working and leave the job site | Subcontractor | Joe Hoyle | true | 3 panels | true |  | Good condition | 4 | 12 | false |  | boomlift | false |  |  |  |  | ACM | 8 | 40
24065 | QTS NAL2 DC2 | 2025-08-22 | Chad mccoy | Acm corrugated insulation and a hole wall of louvers were left out of the job | Subcontractor | Joe Hoyle | true | Boom was still down | true |  | Cloudy 65 | 2 | 8 | false |  | 85 foot boom that needed fixing so we stole a boom | false |  |  | 6 |  | Layout Other | [42 empty] | 18 verticals and 70 brackets. 560 holes drilled into steel. | 8
24068 | QTS NAL1 DC2 | 2025-08-22 | Marvin Blanco | Working in the roof half of the day because WT shut down the job site everybody have to go home the rest of the week | Subcontractor | Joe Hoyle | false |  | true |  |  | 8 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Coping | 10 | 40 | [38 empty] | 100 | 40
25021 | Cooper Steel TN Office | 2025-08-22 | Starlin |  | Subcontractor | Laura Forero | false |  | false |  |  | 3 | 10 | false |  | 60 boom | false |  |  |  |  | Soffit Trim | [36 empty] | 220 | 10
23064 | Yondr Allegro 2S | 2025-08-21 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 8 |  |  |  | Boom lift | [5 empty] | Other | [42 empty] | FRP panel 32 Angle steel 14 | 10
24028 | CHI Memorial Hospital | 2025-08-21 | JC Panels | Rivets screws for screen wall parallel accesories | Subcontractor | Josh McPherson | true | Also we install some parallel | true |  |  | 5 | 50 | false |  |  | false |  |  |  |  | ACM Caulking Other Single Skin | 4 | [5 empty] | 15 | [35 empty] | Parallel panel
24030 | Vantage TX-21 | 2025-08-21 | Naza Padron | When installing the panel by the door of elevation 14 of 207, it was noticed that the power box was not flush with the face of the panel. The GC was notified so the electricians could adapt an extension. 4 and a half man hours were lost | JWMCD Crew | Chris Buttrey | true | described in notes! and hour and a half lost due to lightning alerts all Exterior work is suspended |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | ACM | 6 | 38
24046 | UAB Biomedical Research and Psycholgy | 2025-08-21 | Zarur Nazario Padron Jr | Installing ACM panels, Insulation and removing plastic off of ACM panels on the North side wall. Also moving swing stage over to next section of the wall- it took 4 guys 2 hours each | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 9 | 90 | false |  | 2- swing stages and 1- boomlift | false |  |  |  |  | ACM Insulation Other | 28 | 52 | [18 empty] | 0 | 0 | 0 | 0 |  |  | 764 | 30 |  |  | 0 | 0 | [11 empty] | 8
24048 | QTS NAL2 DC1 | 2025-08-21 | Marvin Blanco | Working in the soffit with the ACM panels installing Zs insulation but today the guys have a little issue with the panels they have 3 missing panels but Joe is going to figure out tomorrow morning | Subcontractor | Joe Hoyle | false |  | true |  |  | 4 | 12 | false |  | Boomlift | false |  |  |  |  | ACM | 13 | 48
24065 | QTS NAL2 DC2 | 2025-08-21 | Chad mccoy | Acm corrugated insulation | Subcontractor | Joe Hoyle | true | There is a section of the steel in welded. We had to more beyond it which took time to transfer layout | true |  | Nice cloudy | 2 | 8 | false |  | 85 foot boom | false |  |  | 5 |  | Layout Other | [42 empty] | 28 verticals and 46 brackets. This took a little more time due to going over stair tower framing | 8
24068 | QTS NAL1 DC2 | 2025-08-21 | Marvin Blanco | Working in the ACM panels in the entry and also taking material to the roof our coping finally came to the job site after 3 days waiting we have a little issue inside of the building with the ACM panels in the columns the panels are different one side is with return and the other with out return we need to figure this out soon as possible because we're almost done one last thing we have 4 shorts panels but also Joe knows about it we should be receiving the new panels next Wednesday to finish what we have | Subcontractor | Joe Hoyle | false |  | true |  |  | 8 | 12 | true | Coping for the screenwall silicone and screws | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Other | 10 | 48 | [40 empty] | Taking material to the roof for the screenwall | 48
25021 | Cooper Steel TN Office | 2025-08-21 | Starlin |  | Subcontractor | Laura Forero | false |  | false |  |  | 3 | 10 | false |  | 60 boom | false |  |  |  |  | Soffit
23064 | Yondr Allegro 2S | 2025-08-20 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | Other | [42 empty] | FRP panels 32 Steel angle 14 | 10
24030 | Vantage TX-21 | 2025-08-20 | Naza Padron | moving material 4 hours | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | ACM | 12 | 46
24046 | UAB Biomedical Research and Psycholgy | 2025-08-20 | Zarur Nazario Padron Jr | Installing Zee’s, Insulation and ACM panels on North Side of the building. | JWMCD Crew | Wylie McDougall | true | 2 workers were delayed 2 hours of work each trying to get a boomlift and then taking the boomlift to the building next door trying to remove stains left on panel right next and under the access door. |  |  | Sunny | 9 | 90 | false |  | 2-swing stages and 1-boomlift | false |  |  |  |  | ACM Insulation Subgirt Zee | 4 | 4 | [18 empty] | 0 | 0 | 0 | 0 |  |  | 1408 | 50 |  |  | 330 | 36
24065 | QTS NAL2 DC2 | 2025-08-20 | Chad mccoy | Insulation Corrugated Acm | Subcontractor | Joe Hoyle | false |  | true |  |  | 2 | 8 | false |  | 85 foot boom | false |  |  | 5 |  | Layout Other | [42 empty] | Layout is continuous, we installed 22 verticals on yesterday’s brackets. And the we installed 40 more brackets. 320 holes drilled in steel | 8
25021 | Cooper Steel TN Office | 2025-08-20 | Starlin |  | Subcontractor | Laura Forero | false |  | false |  |  | 3 | 10 | false |  | 60 boom | false |  |  |  |  | Soffit
23064 | Yondr Allegro 2S | 2025-08-19 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 8 |  |  |  | Boom lift | [5 empty] | Other | [42 empty] | FRP panel 28 Steel angle 12 | 10
24028 | CHI Memorial Hospital | 2025-08-19 | JC Panels | Rivets. Screen wall screws, panels for southwest elevation . Parallel accesories | Subcontractor | Josh McPherson | true |  | true |  |  | 6 | 60 | false |  | Boom lift | false |  |  |  |  | ACM Caulking Single Skin | 8 | [5 empty] | 15
24030 | Vantage TX-21 | 2025-08-19 | Naza Padron | moving material 4 hours | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | ACM | 10 | 50
24046 | UAB Biomedical Research and Psycholgy | 2025-08-19 | Zarur Nazario Padron Jr | Installing Zee’s and ACM panels on North side of building. | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 9 | 90 | false |  | 2-swing stages and 1- boomlift | false |  |  |  |  | ACM Subgirt Zee | 22 | 50 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 240 | 40
24065 | QTS NAL2 DC2 | 2025-08-19 | Chad mccoy | Insulation has been walking away off my bundles | Subcontractor | Joe Hoyle | false |  | true |  |  | 2 | 8 | false |  | 85 foot boom | false |  |  | 8 |  | Layout Other | [42 empty] | 50 louver brackets were later out and installed, 8 holes drilled into steel per bracket and then screwed off. 400 holes drilled | 8
24068 | QTS NAL1 DC2 | 2025-08-19 | Marvin Blanco | Working in the penthouse with the Jtrim and also in the entry of the building with the ACM panels today we have a little issue with a guy wasn't tied off but we're working to resolve the problem to not happen no more thanks God nothing happened | Subcontractor | Joe Hoyle | true | Material | true |  | Good condition | 12 | 12 | false |  | Scaffolding boomlift forklift | false |  |  |  |  | ACM | 18 | 144
25021 | Cooper Steel TN Office | 2025-08-19 | Starlin |  | Subcontractor | Laura Forero | false |  | false |  |  | 3 | 9 | false |  | 60 boom | false |  |  |  |  | Soffit
23064 | Yondr Allegro 2S | 2025-08-18 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Boom lift | [5 empty] | Other | [42 empty] | FRP panels 16 Steel angle 10 | 10
24030 | Vantage TX-21 | 2025-08-18 | Naza Padron | moving material 6 hours | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 40 | false |  | 86' boom | false |  |  |  |  | ACM Insulation Subgirt Zee | 4 | 34 | [24 empty] | 62 | 4 |  |  | 62 | 4
24046 | UAB Biomedical Research and Psycholgy | 2025-08-18 | Zarur Nazario Padron Jr | Installing Zee’s, Insulation and ACM panels on North Side of building. Also moving materials per requested by B&G | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 8 | 64 | false |  | 2-swing stages and 1 boom lift | false |  |  |  |  | ACM Insulation Other Subgirt Zee | 22 | 32 | [18 empty] | 0 | 0 | 0 | 0 |  |  | 80 | 16 |  |  | 240 | 13 | [11 empty] | 3
24065 | QTS NAL2 DC2 | 2025-08-18 | Chad McCoy | Corrugated | Subcontractor | Joe Hoyle | false |  | true |  |  | 2 | 8 | false |  | 85 foot boom | false |  |  |  |  | Other | [42 empty] | 65 Louver brackets were installed and layout was continuous. We started our day early with one doing orientation and I prepped the louver material for tonight install. | 8
25021 | Cooper Steel TN Office | 2025-08-18 | Starlin |  | Subcontractor | Laura Forero | false |  | false |  |  | 3 | 5 | false |  | 60 boom | false |  |  |  |  | Soffit
23064 | Yondr Allegro 2S | 2025-08-16 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | didn’t allow us to use the boom lif because they are paving the street |  |  |  | 5 | 8 | [8 empty] | Other | [42 empty] | FRP panels 6 Steel angle 6 | 8
23064 | Yondr Allegro 2S | 2025-08-15 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Don’t allow us to use boom lift because they are pavement the street |  |  |  | 8 | 10 | [8 empty] | Other | [42 empty] | FRP panel 8 Steel angle 8 | 80
24030 | Vantage TX-21 | 2025-08-15 | Naza Padron | N/A | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | ACM | 15 | 50
24046 | UAB Biomedical Research and Psycholgy | 2025-08-15 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | true | We stopped working for two periods during the day due to lightning one hour each |  |  |  | 6 | 481 | false |  | 135' boom and suspended scaffold | false |  |  |  |  | Insulation Subgirt Zee Trim | [26 empty] | 320 | 10 |  |  | 240 | 16 |  |  |  |  | 92 | 22
24028 | CHI Memorial Hospital | 2025-08-14 | JC Panels | Rivets for Morin panels | Subcontractor | Josh McPherson | false |  | true |  |  | 7 | 70 | false |  |  | false |  |  |  |  | ACM Caulking Single Skin
24030 | Vantage TX-21 | 2025-08-14 | Naza Padron | N/A | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | ACM | 11 | 50
24046 | UAB Biomedical Research and Psycholgy | 2025-08-14 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 60 | false |  | 86' boom and suspended scaffold | false |  |  |  |  | Insulation Subgirt Zee Trim | [26 empty] | 840 | 18 |  |  | 460 | 20 |  |  |  |  | 92 | 22
24065 | QTS NAL2 DC2 | 2025-08-14 | Chad McCoy |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 3 | 4 | true | 2 trucks of acm | 85 foot boom | false |  |  |  |  | Other | [42 empty] | Clean up was done and preparation for 2 trucks. | 4
23064 | Yondr Allegro 2S | 2025-08-13 | Ever mendoza |  | Subcontractor | Joe Hoyle | true |  |  |  | Rain | 8 | 48 | [8 empty] | Other | [42 empty] | FRP panels 8 | 48
24028 | CHI Memorial Hospital | 2025-08-13 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 5 | 35 | false |  |  | false |  |  |  |  | Insulation Single Skin Subgirt Zee | [6 empty] | 22
24030 | Vantage TX-21 | 2025-08-13 | Naza Padron | N/A | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | ACM | 16 | 50
24046 | UAB Biomedical Research and Psycholgy | 2025-08-13 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 60 | false |  | 86' boom and suspended scaffold | false |  |  |  |  | Insulation Subgirt Zee Trim | [26 empty] | 1080 | 20 |  |  | 640 | 22 |  |  |  |  | 76 | 18
24065 | QTS NAL2 DC2 | 2025-08-13 | Chad McCoy | Scaffolding was erected over the units and a long board was used to span across the scaffolding. A 65 foot yo-yo is used over the span. We are also having to modify panels that go behind the steel bc the gap is 4 inches and system depth is 4 3/8. | Subcontractor | Joe Hoyle | true | We are modifying corrugated due to system depth where steel is. And there was lightning that shortened our day | true |  | Storms | 4 | 8 | false |  | 85 foot boom | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 12 | 5 |  |  | 120 | 1 |  |  | 110 | 1
23064 | Yondr Allegro 2S | 2025-08-12 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 | [8 empty] | Other | [42 empty] | FRP panels 15 Steel angle 12 | 80
24030 | Vantage TX-21 | 2025-08-12 | Naza Padron | N/A | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | ACM | 20 | 50
24046 | UAB Biomedical Research and Psycholgy | 2025-08-12 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 60 | false |  | 2- 86' Boom Lifts | false |  |  |  |  | ACM Insulation | 8 | 26 | [24 empty] | 660 | 34
24065 | QTS NAL2 DC2 | 2025-08-12 | Chad mccoy | Acm and corrugated | Subcontractor | Joe Hoyle | false |  | true |  |  | 4 | 8 | false |  | 85 foot boom | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 27 | 6 |  |  | 140 | 1.5 |  |  | 50 | 1
24068 | QTS NAL1 DC2 | 2025-08-12 | Marvin Blanco | We have some short panels in the face of the building in the corner it's 2¾ short corner and also we are still waiting for the panels in the stairs tower number 2 waiting for silicone we need about 10 boxes of Grey silicone and about 2 boxes of white and another 2 o 3 of red silicone there is one more issue with the weatherproofing it's not good | Subcontractor | Joe Hoyle | true | Weatherproofing and silicone | true |  | Good condition | 8 | 12 | false |  | Scaffolding boomlift forklift | false |  |  |  |  | ACM Corrugated / Screen wall | 8 | 48 | [20 empty] | 15 | 48
23064 | Yondr Allegro 2S | 2025-08-11 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 8 | 80 |  |  | Boom lift | [5 empty] | Other | [42 empty] | FRP panels 15 Steel angle 14 piezes And end caps on top the panels | 80
24046 | UAB Biomedical Research and Psycholgy | 2025-08-11 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 60 | false |  | 2- 86' Boom Lifts | false |  |  |  |  | ACM Insulation Subgirt Zee | 16 | 30 | [24 empty] | 390 | 12 |  |  | 180 | 16
24065 | QTS NAL2 DC2 | 2025-08-11 | Chad McCoy | Acm and corrugated | Subcontractor | Joe Hoyle | false |  | true |  |  | 4 | 8 | false |  | 85 foot boom | false |  |  | 1 |  | Corrugated / Screen wall Flashing Insulation Layout | [22 empty] | 24 | 6 |  |  | 240 | 1.5 |  |  |  |  | 25 | 1
23064 | Yondr Allegro 2S | 2025-08-09 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Move material to the work area |  |  |  | 9 | [9 empty] | Other | [42 empty] | FRP panels 22 Angles steel 14 piezes | 72
24065 | QTS NAL2 DC2 | 2025-08-09 | Chad McCoy | Acm extra corrugated | Subcontractor | Joe Hoyle | false |  | true |  |  | 4 | 7 | false |  | 80 foot boom | false |  |  | 1 |  | Caulking Flashing Layout Other Subgirt Zee | [20 empty] | 105 | 1.5 | [8 empty] | 480 | 4 | 75 | 1.5 | [8 empty] | 80 louver brackets 32 verticals | 6
23064 | Yondr Allegro 2S | 2025-08-08 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Move material to work area 20 hours |  |  |  | 9 | 10 | [8 empty] | Other | [42 empty] | FRP panel 30 Steel angle 18 piezes | 70
24005 | GCDC Building 2/VA1.2 | 2025-08-08 | Obed Bermudez | We continue working on the screen wall, installing panels and taking down trash from the roof. With that, we finished the installation on the screen wall. | JWMCD Crew | Joe Hoyle | [5 empty] | 4 | 10 | [31 empty] | 1
24030 | Vantage TX-21 | 2025-08-08 | Naza Padron | N/A | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 40 | false |  | 86' boom | false |  |  |  |  | ACM | 18 | 40
24030 | Vantage TX-21 | 2025-08-08 | Naza Padron | N/A | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 460 | 20 |  |  | 360 | 30
24046 | UAB Biomedical Research and Psycholgy | 2025-08-08 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 5 | 50 | false |  | 2- 86' Boom Lifts | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 680 | 20 |  |  | 470 | 30
24065 | QTS NAL2 DC2 | 2025-08-08 | Chad mccoy | 2 bundles of corrugated. And acm | Subcontractor | Joe Hoyle | true | So we had to pull off for a little bit today so that the roofers could water tight their scuppers before we put the panels on | true |  | Clear hot | 4 | 8.5 | false |  | 80 foot boom | false |  |  |  |  | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 19 | 4.5 | [6 empty] | 90 | 1 | 40 | 1
23064 | Yondr Allegro 2S | 2025-08-07 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 9 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Other | [22 empty] | 63 | 20 | [18 empty] | FRP 30 Angles steel | 70
24005 | GCDC Building 2/VA1.2 | 2025-08-07 | Obed Bermudez | We continued working on the screen wall, installing clips, tubes, and panels around the stairs. | JWMCD Crew | Joe Hoyle | [5 empty] | 4 | 10 | [8 empty] | Corrugated / Screen wall Tubing | [22 empty] | 23 | 5 |  |  |  |  | 112 | 5
24028 | CHI Memorial Hospital | 2025-08-07 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 5 | 50 | false |  | Boom lift , scaffold, fork lift | false |  |  |  |  | Single Skin | [6 empty] | 105
24030 | Vantage TX-21 | 2025-08-07 | Naza Padron | N/A | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | ACM Insulation Subgirt Zee | 16 | 24 | [24 empty] | 245 | 12 |  |  | 210 | 14
24045 | TMMMS Childcare | 2025-08-07 | Kevin Morris |  | Subcontractor | Chris Buttrey | true | Cleaned jobsite. Need Jays to complete nitachi panels, need scuppers installedto reinstall panels, | false |  |  | 5 | 10 | false |  | Boom 60' | false |  |  |  |  | ACM | 8 | 10
24046 | UAB Biomedical Research and Psycholgy | 2025-08-07 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 60 | false |  | 2- 86' Boom Lifts | false |  |  |  |  | ACM | 18 | 60
24065 | QTS NAL2 DC2 | 2025-08-07 | Chad mccoy | Acm can start coming in and 2 bundles of corrugated | Subcontractor | Joe Hoyle | true | So we stayed late to clean the roof up all the trash had to come off the roof all the cut off pieces of hat channel that was not gonna be used anything from the crates. Everything had to be cleaned up so we stayed and cleaned up all of our stuff from every | true |  | Partly cloudy | 4 | 10 | false |  | 80 foot boom | false |  |  |  |  | Corrugated / Screen wall Flashing Insulation Subgirt Zee | [22 empty] | 19 | 4 |  |  | 200 | 1.5 |  |  | 350 | 4 | 35 | 1
24068 | QTS NAL1 DC2 | 2025-08-07 | Marvin Blanco | Working in the roof screenwall installing the coping and also taking material to the roof and cleaning our areas of work | Subcontractor | Joe Hoyle | false |  | true |  |  | 3 | 12 | false |  | Scaffolding | false |  |  |  |  | Coping | [40 empty] | 1500 | 36
24069 | TCAT Pulaski | 2025-08-07 | JC Panels | We finished all the transportation building. We are installing berridge panels on the second building | Subcontractor | Chris Buttrey | false |  | true |  |  | 3 | 20 | false |  | 2 boom lifts | false |  |  |  |  | Genesis
23064 | Yondr Allegro 2S | 2025-08-06 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 9 | 10 |  |  | Boom lift | [5 empty] | Insulation Other Subgirt Zee | [26 empty] | 735 | 10 |  |  | 100 | 10 | [10 empty] | FRP panels Angles steel 32 paneles | 70
24005 | GCDC Building 2/VA1.2 | 2025-08-06 | Obed Bermudez | We continued working on the screen wall, installing clips, tubes, and panels around the stairs. | JWMCD Crew | Joe Hoyle | [5 empty] | 4 | 10 |  |  | None | [5 empty] | Corrugated / Screen wall Tubing | [22 empty] | 12 | 3 |  |  |  |  | 84 | 7
24030 | Vantage TX-21 | 2025-08-06 | Naza Padron | N/A | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | ACM | 16 | 50
24045 | TMMMS Childcare | 2025-08-06 | Kevin Morris |  | Subcontractor | Chris Buttrey | true | Out of Jays for nahichi panels. Waiting for scuppers to be installed so we can reinstall panels. | false |  |  | 5 | 10 | false |  | Boom 60' | false |  |  |  |  | Soffit Trim | [36 empty] | 90 | 10
24046 | UAB Biomedical Research and Psycholgy | 2025-08-06 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 60 | true | ACM Panels 8 hours | 2- 86' Boom Lifts | false |  |  |  |  | ACM Other | 14 | 52 | [41 empty] | 8
24048 | QTS NAL2 DC1 | 2025-08-06 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 3 | 11 | false |  | Boomlift, forklift | false |  |  |  |  | ACM | 19 | 33
24065 | QTS NAL2 DC2 | 2025-08-06 | Chad mccoy | 2 bundles of corrugated | Subcontractor | Joe Hoyle | true | There is a penetration high on the southwest wall that looks like it’s but nobody knows what it is | true |  | Partly cloudy. | 4 | 8.5 | false |  | 80 foot boom | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 28 | 5 |  |  | 210 | 2 |  |  | 110 | 1
23064 | Yondr Allegro 2S | 2025-08-05 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 9 | 10 |  |  | Boom lift | [5 empty] | Other | [42 empty] | FRP panels Angles steel 30 paneles | 90
24005 | GCDC Building 2/VA1.2 | 2025-08-05 | Obed bermudez | We removed doors, panic bars, and handles to regulate linkages. | JWMCD Crew | Joe Hoyle | [5 empty] | 5 | 5
24005 | GCDC Building 2/VA1.2 | 2025-08-05 | Obed Bermudez | We lifted the screenwall panels to the roof. | JWMCD Crew | Joe Hoyle | [5 empty] | 5 | 10 | [8 empty] | Corrugated / Screen wall | [22 empty] | 7 | 10
24030 | Vantage TX-21 | 2025-08-05 | Naza Padron |  | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | ACM | 13 | 50
24045 | TMMMS Childcare | 2025-08-05 | Kevin Morris | Running low on J for nahichi panels. Kick plates for bottom. | Subcontractor | Chris Buttrey | false |  | true |  |  | 5 | 10 | false |  | Boom 60' | false |  |  |  |  | Soffit Trim | [36 empty] | 180 | 4 | [6 empty] | 2025-08-05 |  | 1d
24046 | UAB Biomedical Research and Psycholgy | 2025-08-05 | Naza Padron |  | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 60 | false |  | 2- 86' Boom Lifts | false |  |  |  |  | ACM Insulation Subgirt Zee Trim | 4 | 8 | [24 empty] | 192 | 8 |  |  | 90 | 12 |  |  |  |  | 120 | 32
24046 | UAB Biomedical Research and Psycholgy | 2025-08-05 | Naza Padron |  | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 80 | false |  | 2- 86' Boom Lifts | false |  |  |  |  | ACM | 20 | 60
24048 | QTS NAL2 DC1 | 2025-08-05 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 3 |  | false |  | Boomlift, forklift | false |  |  |  |  | ACM | 18 | 33
24065 | QTS NAL2 DC2 | 2025-08-05 | Chad mccoy | Acm can start coming in | Subcontractor | Joe Hoyle | false |  | true |  |  | 4 | 9 | false |  | 80 foot boom | false |  |  |  |  | Corrugated / Screen wall Flashing Insulation Subgirt Zee | [22 empty] | 42 | 6 |  |  | 380 | 2 |  |  | 15 | 1 | 35 | 1
24068 | QTS NAL1 DC2 | 2025-08-05 | Marvin Blanco | Today the guys finished installing the wood blocking and aldo the weatherproofing in the screenwall for the coping but today I call my guys to check about the material and he's saying they don't have enough coping to finish the screenwall they only have 21 pics and we need 101 it's 1,100 sf long the wall so we need to check if the rest of the material is in the shop or what happen. | Subcontractor | Joe Hoyle | false |  | true |  |  | 3 | 12 | false |  | Scaffolding | false |  |  |  |  | Other | [42 empty] | Installing wood blocking and weatherproofing for install the coping in the screenwall | 36 | 2025-08-05 |  | 1d
24069 | TCAT Pulaski | 2025-08-05 | JC Panels |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 8 | 80 | false |  |  | false |  |  |  |  | Genesis
24005 | GCDC Building 2/VA1.2 | 2025-08-04 | Obed Bermudez | We unloaded delivery for screen wall panels then headed to work on the security room | JWMCD Crew | Joe Hoyle | [5 empty] | 3 | 5 | true | Screen wall panels. | None
24005 | GCDC Building 2/VA1.2 | 2025-08-04 | Obed Bermudez | We removed doors, panic bars, handles to install linkage. | JWMCD Crew | Joe Hoyle | [5 empty] | 3 | 9
24030 | Vantage TX-21 | 2025-08-04 | Naza Padron |  | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | ACM | 12 | 50
24045 | TMMMS Childcare | 2025-08-04 | Kevin Morris |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 5 | 10 | false |  | Boom 60' | false |  |  |  |  | Soffit Trim | [36 empty] | 150 | 5
24046 | UAB Biomedical Research and Psycholgy | 2025-08-04 | Naza Padron |  | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 8 | 80 | false |  | 2- 86' Boom Lifts | false |  |  |  |  | ACM | 33 | 80
24048 | QTS NAL2 DC1 | 2025-08-04 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 3 | 11 | false |  | Boomlift forklift | false |  |  |  |  | ACM | 16 | 33
24065 | QTS NAL2 DC2 | 2025-08-04 | Chad mccoy |  | Subcontractor | Joe Hoyle | true | Foreman’s meeting | false |  | Partly cloudy but a nice day | 4 | 9 | false |  | 80 foot boom | false |  |  |  |  | Caulking Corrugated / Screen wall Flashing Insulation Subgirt Zee | [20 empty] | 50 | 0.5 | 15 | 4 |  |  | 360 | 1.5 |  |  | 175 | 1.5 | 50 | 1.5
24068 | QTS NAL1 DC2 | 2025-08-04 | Marvin Blanco | Working in the screenwall installing wood and weatherproofing also unloading materials for the soffit panels everything is working well with out issues | Subcontractor | Joe Hoyle | true | Weatherproofing in the front of the building | true |  | Good condition | 3 | 12 | true | Metal panels for the soffit | Scaffolding | false |  |  |  |  | Other | [42 empty] | Installing wood 🪵 in the top of the steel for the coping and also doing the weatherproofing | 36
23064 | Yondr Allegro 2S | 2025-08-02 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | ACM Other | 2 | 16 | [40 empty] | FRP 22 paneles | 48
24030 | Vantage TX-21 | 2025-08-02 | Naza Padron |  | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 55 | false |  | 86' boom | false |  |  |  |  | ACM | 9 | 40
24048 | QTS NAL2 DC1 | 2025-08-02 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 3 | 11 | false |  | Boomlift, forklift | false |  |  |  |  | ACM | 10 | 33
24069 | TCAT Pulaski | 2025-08-02 | JC Panels |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 8 | 80 | false |  |  | false |  |  |  |  | Genesis | [14 empty] | 62
23064 | Yondr Allegro 2S | 2025-08-01 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | ACM Other | 4 | 20 | [40 empty] | FRP 28 paneles | 60
24030 | Vantage TX-21 | 2025-08-01 | Naza Padron | Insulation was removed to put adhesive and reinstalled 24 hours | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 55 | false |  | 86' boom | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 400 | 13 |  |  | 300 | 18
24045 | TMMMS Childcare | 2025-08-01 | Kevin Morris |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 4 | 10 | false |  | Boom 60' | false |  |  | 4 |  | Layout Soffit Trim | [36 empty] | 120 | 4
24046 | UAB Biomedical Research and Psycholgy | 2025-08-01 | Naza Padron |  | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 8 | 80 | false |  | 2- 86' Boom Lifts | false |  |  |  |  | ACM | 36 | 80
24048 | QTS NAL2 DC1 | 2025-08-01 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 3 | 11 | false |  |  | false |  |  |  |  | ACM | 10 | 33
23064 | Yondr Allegro 2S | 2025-07-31 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 8 |  |  |  | Boom lift | [5 empty] | ACM Other | 8 | 20 | [40 empty] | FRP. Panelis 28 | 60
24028 | CHI Memorial Hospital | 2025-07-31 | JC Panels | Flashing. Phillips screws for panel, screws for parallel and Morin. Panels on north side acm | Subcontractor | Josh McPherson | false |  | true |  |  | 6 | 60 | false |  |  | false |  |  |  |  | Plate |  |  | 25
24030 | Vantage TX-21 | 2025-07-31 | Naza Padron | The insulation on the north elevation was removed and adhesive was applied | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 4 | 40 | false |  | 86' boom | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 1800 | 40 |  |  | 270 | 16
24045 | TMMMS Childcare | 2025-07-31 | Kevin Morris |  | Subcontractor | Chris Buttrey | true | Install soffit mock up and waited for approval to continue. Removed 2 more ACM panels so GC can install parapet wall. | false |  | 105° | 5 | 10 | false |  | Boom 60' | false |  |  |  |  | Caulking Soffit | [20 empty] | 200 | 10
24046 | UAB Biomedical Research and Psycholgy | 2025-07-31 | Naza Padron |  | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 60 | true | ACM Panels 8 hours | 2- 86' Boom Lifts | false |  |  |  |  | ACM Trim | 12 | 32 | [34 empty] | 60 | 20
24048 | QTS NAL2 DC1 | 2025-07-31 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 3 | 10 | false |  | Boomlift forklift | false |  |  |  |  | ACM | 12 | 30
24069 | TCAT Pulaski | 2025-07-31 | JC Panels |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 4 | 40 | false |  |  | false |  |  |  |  | Plate |  |  | 39
25028 | TN Soybean Council | 2025-07-31 | Starlin |  | Subcontractor | Cole Norona | false |  | false |  |  | 2 | 12.5 | false |  | scissor lift | false |  |  |  |  | Caulking Coping | [20 empty] | 140 | 7.5 | [18 empty] | 45 | 5
23064 | Yondr Allegro 2S | 2025-07-30 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | Other | [42 empty] | FRP panels 32 | 80
24028 | CHI Memorial Hospital | 2025-07-30 | JC Panels | Flashings, Phillip screws for panels, screws for parallel | Subcontractor | Josh McPherson | false |  | true |  |  | 5 | 50 | false |  |  | false |  |  |  |  | ACM Plate | 9 |  | 7
24030 | Vantage TX-21 | 2025-07-30 | Naza Padron | The insulation on the north elevation was removed and adhesive was applied | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 4 | 40 | false |  | 86' boom | false |  |  |  |  | Insulation | [26 empty] | 1800 | 40
24045 | TMMMS Childcare | 2025-07-30 | Kevin Morris |  | Subcontractor | Chris Buttrey | true | Removed 18 panels for scuppers and parapet to be installed. Waiting on approval for soffits | false |  | 110° | 5 | 10 | true | MR2, AR2, and FR2 excursion arrived at 5:00pm | Boom 60' | false |  |  |  |  | ACM Caulking | 2 | 2 | [18 empty] | 600 | 20
24046 | UAB Biomedical Research and Psycholgy | 2025-07-30 | Naza Padron | 11 ACM Panels 18 hours | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 60 | false |  | 2- 86' Boom Lifts | false |  |  |  |  | ACM Insulation Subgirt Zee | [26 empty] | 900 | 26 |  |  | 180 | 16
24048 | QTS NAL2 DC1 | 2025-07-30 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 3 |  | false |  | Boomlift forklift | false |  |  |  |  | ACM | 10 | 30
24065 | QTS NAL2 DC2 | 2025-07-30 | Chad McCoy |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 4 | 8 | false |  | 80 foot boom | false |  |  | 2 |  | Flashing Layout Subgirt Zee | [30 empty] | 410 | 4 | 50 | 1.5
25028 | TN Soybean Council | 2025-07-30 | Starlin |  | Subcontractor | Cole Norona | false |  | false |  |  | 2 | 14 | false |  | scissor lift | false |  |  |  |  | ACM | 19 | 14
23064 | Yondr Allegro 2S | 2025-07-29 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 | [8 empty] | Other | [42 empty] | FRP panels 27 | 80
24028 | CHI Memorial Hospital | 2025-07-29 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 6 | 60 | false |  |  | false |  |  |  |  | ACM | 9
24030 | Vantage TX-21 | 2025-07-29 | Naza Padron |  | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 792 | 18 |  |  | 374 | 32
24045 | TMMMS Childcare | 2025-07-29 | Kevin Morris | AR2 and mr2 already discussed with Chris | Subcontractor | Chris Buttrey | true | Roof needs repair before we can install, front needs reframed before we can install, need submittal approved before we can install soffits, made 8 filler panels to install by windows | true |  | 106° | 4 | 8 | false |  | Boom 60' | false |  |  |  |  | ACM
24046 | UAB Biomedical Research and Psycholgy | 2025-07-29 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 8 | 80 | false |  | 2- 86' Boom Lifts | false |  |  |  |  | ACM | 48 | 80
24065 | QTS NAL2 DC2 | 2025-07-29 | Chad McCoy | Coping for lower roof | Subcontractor | Joe Hoyle | false |  | true |  |  | 4 | 8.5 | false |  | 69 foot boom | false |  |  |  |  | Corrugated / Screen wall Hat Channel | [22 empty] | 33 | 6 | [10 empty] | 28 | 2
25028 | TN Soybean Council | 2025-07-29 | Starlin |  | Subcontractor | Cole Norona | false |  | false |  |  | 2 | 5 | false |  | scissor lift | false |  |  |  |  | ACM | 3 | 5
23064 | Yondr Allegro 2S | 2025-07-28 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom let's | [5 empty] | Other | [42 empty] | FRP panels 24 paneles | 80
24028 | CHI Memorial Hospital | 2025-07-28 | JC Panels | Flashing, caulking rivets for north elevation | Subcontractor | Josh McPherson | false |  | true |  |  | 6 | 60 | false |  |  | false |  |  |  |  | ACM Single Skin | 8 | [5 empty] | 36
24030 | Vantage TX-21 | 2025-07-28 | Naza Padron |  | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 4 | 40 | false |  | 86' boom | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 600 | 16 |  |  | 280 | 24
24030 | Vantage TX-21 | 2025-07-28 | Naza Padron | N/A | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 4 | 32 | false |  | 86' Boom Lift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 720 | 14 |  |  | 486 | 18
24046 | UAB Biomedical Research and Psycholgy | 2025-07-28 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 48 | false |  | 2- 86' Boom Lifts | false |  |  |  |  | ACM | 28 | 48
24065 | QTS NAL2 DC2 | 2025-07-28 | Chad McCoy |  | Subcontractor | Joe Hoyle | true | Bomb threat | false |  | Partly cloudy 92 | 4 | 3 | false |  | 80 foot boom | false |  |  |  |  | Other | [42 empty] | Prepped panels and squeegee roof for work. Then another bomb threat happened and all work stopped | 3
25028 | TN Soybean Council | 2025-07-28 | Starlin |  | Subcontractor | Cole Norona | true | preparation of materials | false |  | 3 hours | 3 | 8 | false |  | scissor lift | false |  |  |  |  | ACM | 4 | 8
24065 | QTS NAL2 DC2 | 2025-07-27 | Chad mccoy |  | Subcontractor | Joe Hoyle | true | Afternoon storms and lightning | false |  | Storms | 4 | 5.5 | false |  | 80 foot boom | false |  |  |  |  | Corrugated / Screen wall Hat Channel | [22 empty] | 20 | 4 | [10 empty] | 221 | 1
24068 | QTS NAL1 DC2 | 2025-07-27 | Marvin Blanco | Working in the ACM panels in the front of the building there is a little issue with the weatherproofing it's not all done there is silicone missing in the side of the precast and also installing the very bottom it's missing the weatherproofing we need WT to put some eyes on it it's look right | Subcontractor | Joe Hoyle | true | Weatherproofing | true |  | Good condition | 7 | 12 | true | Screws and silicone | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM | 18 | 84
24030 | Vantage TX-21 | 2025-07-26 | Naza Padron |  | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 4 | 40 | false |  | 65' boom | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 1380 | 18 |  |  | 784 | 22
24045 | TMMMS Childcare | 2025-07-26 | Heyvi | We are doing extra work on extra panels | Subcontractor | Chris Buttrey | false |  | true |  |  | 3 | 8 | false |  | Lift | false |  |  |  |  | ACM |  | 24
24046 | UAB Biomedical Research and Psycholgy | 2025-07-26 | Naza Padron |  | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 5 | 40 | false |  | 65' boom 65' boom | false |  |  |  |  | ACM | 22 | 40
24065 | QTS NAL2 DC2 | 2025-07-26 | Chad mccoy |  | Subcontractor | Joe Hoyle | true | Some panels where different sizes so we took them out with out taken down the wall and changed them out | false |  | Cloudy. Hot 103 | 4 | 6.5 | false |  | 80 foot boom | false |  |  |  |  | Corrugated / Screen wall Other | [22 empty] | 34 | 5.5 | [18 empty] | 30 hat channel | 1
24030 | Vantage TX-21 | 2025-07-25 | Naza Padron |  | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 4 | 44 | false |  | 65' boom | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 1380 | 26 |  |  | 240 | 18
24046 | UAB Biomedical Research and Psycholgy | 2025-07-25 | Naza Padron | waiting on metal flashing and missing panels to start | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 5 | 50 | true | ACM missing Panels and Metal Flashing... unloaded material 4 hours | 65' boom 65' boom | false |  |  |  |  | ACM Flashing Insulation Other Subgirt Zee | 8 | 18 | [24 empty] | 190 | 10 |  |  | 180 | 10 | 60 | 8 | [9 empty] | 4
24065 | QTS NAL2 DC2 | 2025-07-25 | Chad mccoy |  | Subcontractor | Joe Hoyle | true | Bomb threat. Build was closed and everybody sent home | false |  |  | 4 | 3.5 | false |  | 80 foot boom | false |  |  |  |  | Other | [42 empty] | Area prepped and cleaned and some panels prepped | 3
23064 | Yondr Allegro 2S | 2025-07-24 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 7 | 10 | true | FRP panels | Boom lifts | [5 empty] | Other | [42 empty] | FRP 13 panels Angles | 60
24028 | CHI Memorial Hospital | 2025-07-24 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 6 | 60 | false |  |  | false |  |  |  |  | ACM Plate | 9 |  | 12
24030 | Vantage TX-21 | 2025-07-24 | Naza Padron |  | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 4 | 44 | false |  | 65' boom | false |  |  |  |  | Insulation | [26 empty] | 1900 | 44
24046 | UAB Biomedical Research and Psycholgy | 2025-07-24 | Naza Padron |  | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 5 | 25 | false |  | 65' boom 65' boom | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 80 | 10 |  |  | 120 | 15
24065 | QTS NAL2 DC2 | 2025-07-24 | Chad mccoy |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 4 | 8 | false |  | 80 foot boom | false |  |  |  |  | Corrugated / Screen wall Other | [22 empty] | 35 | 6 | [18 empty] | 30 hat channels | 1.5
24068 | QTS NAL1 DC2 | 2025-07-24 | Marvin Blanco | Working in the front of the building installing ACM panels and Zs also insulation thanks God everything is working well and no problems | Subcontractor | Joe Hoyle | false |  | true |  |  | 7 | 12 | false |  | Boomlift | false |  |  |  |  | ACM | 12 | 84
23064 | Yondr Allegro 2S | 2025-07-23 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 7 |  | true | FRP panels and trims | Boom lift | [5 empty] | Other | [42 empty] | FRP panels 12 panels And angles | 60
24005 | GCDC Building 2/VA1.2 | 2025-07-23 | Obed Bermudez | We installed two panic bars, two closures on doors, and two pieces of glass on wooden doors. | JWMCD Crew | Joe Hoyle | [5 empty] | 2 | 10 | true | Panic bars | None
24028 | CHI Memorial Hospital | 2025-07-23 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 7 |  | false |  | 2 boom lifts 1 fork lift | false |  |  |  |  | ACM Other Subgirt Zee | 9 | [41 empty] | Strapping for parallel
24030 | Vantage TX-21 | 2025-07-23 | Naza Padron |  | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 4 | 44 | false |  | 65' boom | false | [35 empty] | 968 | 44
24046 | UAB Biomedical Research and Psycholgy | 2025-07-23 | Naza Padron | unloading material ACM 9 HOURS | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 5 | 50 | false |  | ACM PANELS | false |  |  |  |  | Insulation Other Subgirt Zee Trim | [26 empty] | 120 | 10 |  |  | 110 | 10 |  |  |  |  | 40 | 11 | [5 empty] | 9
24065 | QTS NAL2 DC2 | 2025-07-23 | Chad mccoy |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 4 | 7.5 | false |  | 80 foot boom | false |  |  | 1.5 |  | Layout Other | [42 empty] | 97 hat channels. | 6
24065 | QTS NAL2 DC2 | 2025-07-23 | Chad mccoy |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 4 | 8 | false |  | 80 foot boom | false |  |  |  |  | Other | [42 empty] | 96 hat channel on the low roof. | 8
23064 | Yondr Allegro 2S | 2025-07-22 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 7 |  |  |  | Boom lift | [5 empty] | Other | [42 empty] | FRP Steel angle | 60
24030 | Vantage TX-21 | 2025-07-22 | Naza Padron | half a day taking boomlift training | JWMCD Crew | Chris Buttrey | false |  |  |  |  | 4 | 20 | false |  | 65' boom 65' boom | false |  |  |  |  | Subgirt Zee | [30 empty] | 595 | 20
24046 | UAB Biomedical Research and Psycholgy | 2025-07-22 | Naza Padron |  | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 2 | 20 | false |  | 65' boom 65' boom | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 120 | 10 |  |  | 110 | 10
24065 | QTS NAL2 DC2 | 2025-07-22 | Chad mccoy |  | Subcontractor | Joe Hoyle | true | We left at 130 today and came back at 630. We lulled all 2 inch hat to the roof and all the corrugated for the lower roof. And 2 new ladders | false |  | Partly cloudy | 4 | 8.5 | false |  | 80 foot boom | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 24 | 7
24082 | GTN Cable | 2025-07-22 | Starlin |  | Subcontractor | Josh McPherson, Nick Akins | false |  | false |  |  | 2 | 8 | false |  | 45 boom | false |  |  |  |  | Flashing | [32 empty] | 140 | 8
23064 | Yondr Allegro 2S | 2025-07-21 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 7 | [7 empty] | 2 |  | Layout Other | [42 empty] | Install steel angles on the columns | 58
24045 | TMMMS Childcare | 2025-07-21 | Heyvi | We're cutting materials and the installations are slow because we putt extra wood on top to level it | Subcontractor | Chris Buttrey | true | Lightning and thunder | true |  | 2 hours | 3 | 8 | false |  | Lift | false |  |  |  |  | ACM |  | 24
24065 | QTS NAL2 DC2 | 2025-07-21 | Chad mccoy |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 4 | 7.5 | false |  | 80 foot boom | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 34 | 7.5
24082 | GTN Cable | 2025-07-21 | Starlin |  | Subcontractor | Josh McPherson, Nick Akins | false |  | false |  |  | 2 | 8 | false |  | 45 boom | false |  |  |  |  | Flashing | [32 empty] | 150 | 8
24045 | TMMMS Childcare | 2025-07-18 | Heyvi | We are installing fiber cement | Subcontractor | Chris Buttrey | false |  | true |  |  | 3 | 10 | false |  | Lift | false |  |  |  |  | ACM |  | 30
24065 | QTS NAL2 DC2 | 2025-07-18 | Chad mccoy |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 3 | 8.5 | false |  | 80 foot boom | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 32 | 8.5
23064 | Yondr Allegro 2S | 2025-07-17 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 2 | 10 |  |  | Fort lift | [5 empty] | Other | [42 empty] | Move material to the work area | 10
24045 | TMMMS Childcare | 2025-07-17 | Heyvi | We are finishing details of the area where we couldn't work | Subcontractor | Chris Buttrey | true | Thunder | true |  | 2 hours | 3 | 8 | false |  | Lift | false |  |  |  |  | ACM | 15 | 24
24046 | UAB Biomedical Research and Psycholgy | 2025-07-17 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 60 | false |  | 65' boom 65' boom | false |  |  |  |  | ACM Insulation | 27 | 30 | [24 empty] | 832 | 30
24065 | QTS NAL2 DC2 | 2025-07-17 | Chad mccoy |  | Subcontractor | Joe Hoyle | true | One complete bundle of corrugated was mismatched sizes. | false |  |  | 3 | 2 | false |  | 80 foot boom | false |  |  |  |  | Other | [42 empty] | Still getting answers in corrugated. We staged the good material by the crane to crane it to the roof in the am. | 2
24068 | QTS NAL1 DC2 | 2025-07-17 | Marvin Blanco | Today we received a message from WT saying that we don't clean our areas but they are wrong because everyday the guys are cleaning the areas of work we have proof of everything the problem is WT they don't have guys or the GC taking care the others company's and they have a lot of trash everywhere also the roofer guy is using the backer scaffolding with out protection in the roof we are taking care everything and the others company's don't care even the roofer guy is a mess we finished the penthouse last week and they cleaned everything we even have material in the roof, moving to other thing the guys started working in the front entrance but WT it's not ready it's missing silicone weatherproofing inn the precast and gyp and also in the bottom it's all horrible with out weatherproofing we need a green light to leave the job site and get back whenever they get something ready because this guys are kinda new don't know much | Subcontractor | Joe Hoyle | true | Weatherproofing from WT | true |  | Good condition | 14 | 12 | false |  | Scaffolding and boomlift, forklift | false |  |  |  |  | Corrugated / Screen wall Other | [22 empty] | 20 | 96 | [18 empty] | Waiting for WT to have the areas with weatherproofing and getting material ready | 72
24085 | Stadium Commons Development | 2025-07-17 | Starlin |  | Subcontractor | Cole Norona | false |  | false |  |  | 3 | 6 | false |  | 60 boom | false |  |  |  |  | Perforated
24028 | CHI Memorial Hospital | 2025-07-16 | JC Panels | Flashings insulation flashings | Subcontractor | Josh McPherson | false |  | true |  |  | 4 | 40 | false |  |  | false |  |  |  |  | ACM | 7
24046 | UAB Biomedical Research and Psycholgy | 2025-07-16 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 4 | 40 | false |  | 65' boom 65' boom | false |  |  |  |  | ACM | 21 | 36
24065 | QTS NAL2 DC2 | 2025-07-16 | Chad mccoy |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 3 | 2 | false |  | 80 foot boom | false |  |  |  |  | Other | [42 empty] | Inventory of corrugated by size in yard | 2
24068 | QTS NAL1 DC2 | 2025-07-16 | Marvin Blanco | Today the guys was working in the screenwall because WT it's not ready for McDougall to start hanging panels in the entry or either in the freedom wall so we are waiting for WT to have something for us and start the area because both start tower are done already the penthouse it's done already we only have the screenwall wall panels and we are close to finish installing I think this week will be done the screenwall Also | Subcontractor | Joe Hoyle | false |  | true |  |  | 11 | 12 | false |  | Scaffolding, boomlift and forklift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 26 | 132
24069 | TCAT Pulaski | 2025-07-16 | JC Panels | Insolation flashings for screen wall | Subcontractor | Chris Buttrey | false |  | true |  |  | 3 | 30 | false |  |  | false |  |  |  |  | Subgirt Zee
24085 | Stadium Commons Development | 2025-07-16 | Starlin |  | Subcontractor | Cole Norona | false |  | false |  |  | 3 | 8 | false |  | 60 boom | false |  |  |  |  | Perforated
23064 | Yondr Allegro 2S | 2025-07-15 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | ACM | 7 | 40
24028 | CHI Memorial Hospital | 2025-07-15 | JC Panels | Insulation, flashings | Subcontractor | Josh McPherson | false |  | true |  |  | 3 | 30 | false |  |  | false |  |  |  |  | ACM | 5
24045 | TMMMS Childcare | 2025-07-15 | Heyvi flores | Today we install 25 panels acm in the área we couldn't work we also picked all the trash from the building i talked to chris about some screws we need i will buy them and i will send recipet the reason why i need those screws is beacuse the wood is like hiding a little | Subcontractor | Chris Buttrey | false |  | true |  |  | 3 | 10 | false |  | Lift | false |  |  |  |  | ACM | 25 | 30
24045 | TMMMS Childcare | 2025-07-15 | Heyvi |  | Subcontractor | Chris Buttrey | true | Lightling | false |  | 40 minutos | 3 | 10 | false |  | Lift | false |  |  |  |  | ACM Other | [42 empty] | Fiber cement installations Took plastic off from acm | 30
24046 | UAB Biomedical Research and Psycholgy | 2025-07-15 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 4 | 40 | false |  | 65' boom 65' boom | false |  |  |  |  | ACM | 31 | 40
24065 | QTS NAL2 DC2 | 2025-07-15 | Chad mccoy |  | Subcontractor | Joe Hoyle | true | The corrugated is different sizes. They range from 12 1/2” - 13 3/4” | false |  | Cloudy. Pm storms | 3 | 8.5 | false |  | 80 foot boom | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 24 | 7
24069 | TCAT Pulaski | 2025-07-15 | JC Panels | Flashings, genesis panels | Subcontractor | Chris Buttrey | false |  | true |  |  | 3 | 27 | false |  |  | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 123
24085 | Stadium Commons Development | 2025-07-15 | Starlin |  | Subcontractor | Cole Norona | true | We waited for a new boom for 3 hours | false |  |  | 3 | 8 | false |  | 60 boom | false |  |  |  |  | Perforated
23064 | Yondr Allegro 2S | 2025-07-14 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | ACM | 8 | 40
24028 | CHI Memorial Hospital | 2025-07-14 | JC Panels | Insolation, screws with washers, scaffold new drawings with parallel details | Subcontractor | Josh McPherson | false |  | true |  |  | 4 | 24 | false |  |  | false |  |  |  |  | ACM | 9
24046 | UAB Biomedical Research and Psycholgy | 2025-07-14 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 4 | 40 | false |  | 65' boom 65' boom | false |  |  |  |  | ACM | 26 | 40
24065 | QTS NAL2 DC2 | 2025-07-14 | Chad mccoy | Other trades to finish | Subcontractor | Joe Hoyle | true | We are fighting corrugated being different sizes now. We took back down a section and we had to match up sizes of panels and out of level the first panel so the section would be level | true |  | Storms am. | 3 | 6 | false |  | 80 foot boom | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 14 | 5
24069 | TCAT Pulaski | 2025-07-14 | JC Panels | Flashings for screen wall | Subcontractor | Chris Buttrey | false |  | true |  |  | 3 | 27 | false |  |  | false |  |  |  |  | Corrugated / Screen wall Flashing | [22 empty] | 6
24068 | QTS NAL1 DC2 | 2025-07-13 | Marvin Blanco | Working in the second stairs tower to finish also working in the screenwall and moving material we are needing silicone for the ACM panels | Subcontractor | Joe Hoyle | false |  | true |  |  | 14 | 10 | false |  | Scaffolding, boomlift, forklift | false |  |  |  |  | ACM Corrugated / Screen wall | 23 | 100 | [20 empty] | 19 | 40
24028 | CHI Memorial Hospital | 2025-07-12 | JC Panels | Insolation, flashings , washers | Subcontractor | Josh McPherson | false |  | true |  |  | 3 | 18 | false |  |  | false |  |  |  |  | ACM | 4
24046 | UAB Biomedical Research and Psycholgy | 2025-07-12 | Naza Padron | Relocated Insulation 6 hours | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 7 | 56 | false |  | 65' boom 65' boom | false |  |  |  |  | ACM Insulation Other | 30 | 20 | [24 empty] | 1280 | 30 | [15 empty] | 6
24069 | TCAT Pulaski | 2025-07-12 | JC Panels | Flashings, drill bits 7/32, washers | Subcontractor | Chris Buttrey | false |  | true |  |  | 3 | 15 | false |  |  | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 12
23064 | Yondr Allegro 2S | 2025-07-11 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 5 | 10 | true | FRP panels and ACM panels | Boom lift | [5 empty] | ACM Insulation Subgirt Zee | 5 | 20 | [24 empty] | 200 | 10 |  |  | 140 | 10
24028 | CHI Memorial Hospital | 2025-07-11 | JC Panels | We need the scaffold for the south side, insolation and flashings for the screen wall | Subcontractor | Josh McPherson | false |  | true |  |  | 3 | 24 | true | We got panels the wood looking |  | false |  |  |  |  | ACM | 5
24046 | UAB Biomedical Research and Psycholgy | 2025-07-11 | Naza Padron | Punch list 4 Hours, fab ACM panel to cover blue skin 4 Hours, Screwing Zee's 14 Hours | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 7 | 70 | false |  | 65' boom 65' boom | false |  |  |  |  | ACM Flashing Insulation Other | 40 | 30 | [24 empty] | 380 | 8 |  |  |  |  | 48 | 10 | [9 empty] | 22
24065 | QTS NAL2 DC2 | 2025-07-11 | Chad mccoy | Other trades to get out of the way | Subcontractor | Joe Hoyle | true | It’s hot, the corrugated is different sizes. One end is 12 1/2 and the other will be 13 1/8. Each panel has a different size left to right. | true |  | Hot partly cloudy | 4 | 8 | false |  | 80 foot boom | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 34 | 8
24069 | TCAT Pulaski | 2025-07-11 | JC Panels | Flashing for the screen wall , 7/32 drill bits | Subcontractor | Chris Buttrey | false |  | true |  |  | 3 | 27 | false |  |  | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 46
24028 | CHI Memorial Hospital | 2025-07-10 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 3 | 30 | true | We got panels . We got plywood |  | false |  |  |  |  | ACM | 6
24046 | UAB Biomedical Research and Psycholgy | 2025-07-10 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 7 |  | false |  | 65' boom 65' boom | false |  |  |  |  | ACM Flashing Insulation | 10 | 30 | [24 empty] | 1280 | 20 |  |  |  |  | 140 | 20
24065 | QTS NAL2 DC2 | 2025-07-10 | Chad mccoy | Other trades need to finish | Subcontractor | Joe Hoyle | true | Storms. | true |  | Storms | 4 | 5.5 | false |  | 80 foot boom | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 15 | 4
24069 | TCAT Pulaski | 2025-07-10 | JC Panels | We need the genesis Panels | Subcontractor | Chris Buttrey | false |  | true |  |  | 3 | 27 | false |  |  | false |  |  |  |  | ACM Flashing Other | 5 | [31 empty] | 140 | [9 empty] | Strapping | 12
25036 | TCAT Chattanooga | 2025-07-10 | Starlin |  | Subcontractor | Josh McPherson | false |  | false |  |  | 3 | 8 | false |  |  | false |  |  |  |  | Coping Single Skin Trim | [6 empty] | 12 | 6 | [28 empty] | 40 | 1 |  |  | 10 | 1
24005 | GCDC Building 2/VA1.2 | 2025-07-09 | Obed Bermudez | We made some openings wider for the lights on the west elevation then we cleaned up everything on the east and took all our tools off site. | JWMCD Crew | Joe Hoyle | [5 empty] | 4 | 10
24028 | CHI Memorial Hospital | 2025-07-09 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 3 | 26 | true | We received panels and scaffold. We erect the scaffold and unload the material |  | false |  |  |  |  | ACM | 2
24046 | UAB Biomedical Research and Psycholgy | 2025-07-09 | Naza Padron | the Zee's were re-screwed, 20 hours | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 5 | 50 | true | 4 Crates ACM Panels 6 hours | 65' boom 65' boom | false |  |  |  |  | Insulation Other | [26 empty] | 1152 | 24 | [15 empty] | 20
24065 | QTS NAL2 DC2 | 2025-07-09 | Chad mccoy | Acm. Other trades to let us work | Subcontractor | Joe Hoyle | true | Coping isn’t done on liver sections and around pent house, Expansion joint isn’t completed on west elevation, Lower roof is in progress. | true |  | Cloudy storms | 4 | 6 | false |  | 80 foot boom | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 23 | 6
24068 | QTS NAL1 DC2 | 2025-07-09 | Marvin Blanco | We are needing a panel for the stairs tower #2 because we ha have 1 panels damaged from the crate | Subcontractor | Joe Hoyle | false |  | true |  |  | 14 | 12 | false |  | Scaffolding, boomlift, forklift | false |  |  |  |  | ACM Corrugated / Screen wall | 28 | 120 | [20 empty] | 18 | 48
24069 | TCAT Pulaski | 2025-07-09 | JC Panels |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 3 | 30 | false |  |  | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 48
25036 | TCAT Chattanooga | 2025-07-09 | Starlin |  | Subcontractor | Josh McPherson | false |  | false |  |  | 3 | 4 | false |  |  | false |  |  |  |  | ACM Insulation Subgirt Zee | 5 | 3 | [24 empty] | 16 | 0.5 |  |  | 10 | 0.5
24005 | GCDC Building 2/VA1.2 | 2025-07-08 | Obed Bermudez | We went to clean up east elevation and found a glass hanging on a door installed by the previous crew in the security room so we removed and reinstalled the glass and trim. | JWMCD Crew | Joe Hoyle | [5 empty] | 4 | 10
24046 | UAB Biomedical Research and Psycholgy | 2025-07-08 | Naza Padron | damaged panel replaced 8 hours | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 5 | 50 | false |  | 65' boom 65' boom | false |  |  |  |  | Insulation Other Subgirt Zee | [26 empty] | 768 | 18 |  |  | 600 | 24 | [11 empty] | 8
24065 | QTS NAL2 DC2 | 2025-07-08 | Chad mccoy | Acm, other trades to get out of the way | Subcontractor | Joe Hoyle | true | Storms will be on and off thru the week, Roofers do no have the lower roof, pent house or louver coping finished. | true |  | Cloudy hot | 4 | 8 | false |  | 80 foot boom | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 24 | 6
24065 | QTS NAL2 DC2 | 2025-07-08 | Chad mccoy |  | Subcontractor | Joe Hoyle | true | Upon arrival our scaffolding was dissassembled and moved and reassembled and used by the roofers. We had to get it back and erected. I lined up crane picks for tomorrow am. 2 full bundles of the 21 foot corrugated and 1 bundle of 19 foot corrugated. The rest of the plywood and insulation. | false |  | Partly cloudy | 4 | 8 | false |  | 80 foot boom | false |  |  |  |  | Corrugated / Screen wall Other | [22 empty] | 4 | 2 | [18 empty] | 65 hat channel | 4
24068 | QTS NAL1 DC2 | 2025-07-08 | JC Panels |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 3 | 22.5 | true | Panels and scaffold |  | false |  |  |  |  | Subgirt Zee
24068 | QTS NAL1 DC2 | 2025-07-08 | Marvin Blanco | Wr have one issue with a panels my guys have to use one of the top panels to make it work in the bottom of the panels the panel was to damaged for use in the bottom tomorrow I'll talk to Joe about it if McDougall is able to send the sheet or send the panels with the routers all around because WT is asking to finish the second stairs tower this week so I have 3 crews working on it and one crew in the penthouse | Subcontractor | Joe Hoyle | false |  | true |  |  | 14 | 12 | false |  | Boomlift, forklift scaffolding | false |  |  |  |  | ACM | 20 | 168
23029 | BNA Concourse D | 2025-07-07 | Zarur Nazario Padron Jr | Finishing up punchlists and installing flashing on blockade and corner panel. Installing flashing where theres left needed. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 6 | 54 | false |  | 2-65’ boomlift | false |  |  |  |  | Flashing Other | [20 empty] | 30 | 2 | 0 | 0 | [6 empty] | 0 | 0 | 540 | 40 | [9 empty] | 18
24046 | UAB Biomedical Research and Psycholgy | 2025-07-07 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 4 | 40 | false |  | 65' boom 65' boom | false |  |  |  |  | Subgirt Zee | [30 empty] | 880 | 40
24065 | QTS NAL2 DC2 | 2025-07-07 | Chad mccoy |  | Subcontractor | Joe Hoyle | true | All guys were in Nashville doing safety training and then driving back to Ohio | false |  |  | 1 | 0 | false |  |  | false |  |  |  |  | Other | [42 empty] | Safety training in Nashville. | 9
24069 | TCAT Pulaski | 2025-07-07 | JC Panels | We need flashing for the screen wall | Subcontractor | Chris Buttrey | false |  | true |  |  | 3 | 30 | true | Accesories |  | false |  |  |  |  | Other | [42 empty] | Membrane and strapping
24028 | CHI Memorial Hospital | 2025-07-04 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 4 | 32 | false |  |  | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 18
24065 | QTS NAL2 DC2 | 2025-07-04 | CHad McCoy |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 4 | 8.5 | false |  | 80 foot boom | false |  |  |  |  | Caulking Corrugated / Screen wall Flashing Insulation | [20 empty] | 65 | 1 | 17 | 4 |  |  | 192 | 1.5 |  |  |  |  | 50 | 1 | [10 empty] | 2025-07-04 |  | 1d
24069 | TCAT Pulaski | 2025-07-04 | JC Panels | flashing | Subcontractor | Chris Buttrey | false |  | true |  |  | 3 | 32 | false |  |  | false |  |  |  |  | Other | [42 empty] | Waterproof paper
23029 | BNA Concourse D | 2025-07-03 | Zarur Nazario Padron Jr | Finishing up punchlist. Installing flashing and coping on ladder of Concessions rooftop. Installing flashing on panel and blockade. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 5 | 50 | false |  | 1-65’ boomlift, scaffold, and 2-10’ ladders | false |  |  |  |  | Coping Flashing | [20 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 170 | 32 | [6 empty] | 35 | 18
24005 | GCDC Building 2/VA1.2 | 2025-07-03 | Obed Bermudez | We continue installing middle clips on the screen wall, finished caulking, and peeling protective film on the east elevation, and cleaning. | JWMCD Crew | Joe Hoyle | [5 empty] | 4 | 10 | [8 empty] | Caulking | [20 empty] | 100 | 40
24045 | TMMMS Childcare | 2025-07-03 | Starlin |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 6 | 10 | false |  | 2 boom 45 | false |  |  |  |  | ACM Subgirt Zee | 35 | 8.5 | [28 empty] | 170 | 1.5
23029 | BNA Concourse D | 2025-07-02 | Zarur Nazario Padron Jr | Installing remaining flashing on expansion joint on D5. Fixing a water leakage on back corner of Connector. Finishing up some stuff off of punch lists. Installing/fabricating ACM panels and flashing on Concessions and Record ladders. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 6 | 60 | false |  | 1-65’ boomlift and 1 scaffold | false |  |  |  |  | ACM Coping Flashing IMP Other | 4 | 15 | [6 empty] | 6 | 12 | [10 empty] | 0 | 0 | 0 | 0 | [6 empty] | 12 | 3 | 24 | 12 | [6 empty] | 10 | 3 |  | 3
24005 | GCDC Building 2/VA1.2 | 2025-07-02 | Obed Bermudez | We’re installing middle clips on the screen wall and panels and caulking on the west elevation. Additionally, we cleaned up the roof and removed any debris. | JWMCD Crew | Joe Hoyle | [5 empty] | 3 | 12 | [8 empty] | ACM | 6 | 11 | [18 empty] | 100 | 11
24028 | CHI Memorial Hospital | 2025-07-02 | JC Panels | Flashings, Morin, wood panel, scaffold | Subcontractor | Josh McPherson | false |  | true |  |  | 4 | 40 | false |  |  | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 15
24045 | TMMMS Childcare | 2025-07-02 | Starlin |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 6 | 10 | false |  | 2 boom 45 | false |  |  |  |  | ACM Insulation Subgirt Zee | 32 | 6.5 | [24 empty] | 128 | 1.5 |  |  | 296 | 2
24046 | UAB Biomedical Research and Psycholgy | 2025-07-02 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 5 | 40 | false |  | 65' boom 65' boom | false |  |  |  |  | Subgirt Zee | [30 empty] | 620 | 40
24068 | QTS NAL1 DC2 | 2025-07-02 | Marvin Blanco | Working in the penthouse and also installing Zs in the second stairs tower | Subcontractor | Joe Hoyle | false |  | true |  |  | 14 | 12 | false |  | Boomlift, forklift scaffolding | false |  |  |  |  | Corrugated / Screen wall Hat Channel | [22 empty] | 20 | 96 | [10 empty] | 1800 | 72
24069 | TCAT Pulaski | 2025-07-02 | JC Panels | Genesis panels, flashing . Also we install the membrane on the screen wall | Subcontractor | Chris Buttrey | false |  | true |  |  | 3 | 30 | false |  | Boom and fork lift | false |  |  |  |  | Insulation Subgirt Zee
23029 | BNA Concourse D | 2025-07-01 | Zarur Nazario Padron Jr | Fabricating/Installing IMP panels on Expansion Joint on D5 connector. Installing flashing between L-IMP panel and blockade wall. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 5 | 50 | false |  | 1-65’ boomlift, 12’ ladder, and 1 scissor lift | false |  |  |  |  | ACM Flashing Other | 17 | 24 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 140 | 20 | [9 empty] | 6
24005 | GCDC Building 2/VA1.2 | 2025-07-01 | Obed Bermudez | HITT closed the job site down for 3 days and everyone had to retrain today | JWMCD Crew | Joe Hoyle | [5 empty] | 3 | 3
24028 | CHI Memorial Hospital | 2025-07-01 | JC Panels | Today we had a meeting with Nick and Josh talking about all the material and equipment needed | Subcontractor | Josh McPherson | false |  | true |  |  | 4 | 40 | false |  |  | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 12
24046 | UAB Biomedical Research and Psycholgy | 2025-07-01 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 5 | 50 | false |  | 65' boom 65' boom | false |  |  |  |  | Subgirt Zee | [30 empty] | 820 | 50
24048 | QTS NAL2 DC1 | 2025-07-01 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | true | Rain | false |  | Raining | 3 | 5 | false |  | Boomlift forklift | false |  |  |  |  | ACM | 8 | 15
24068 | QTS NAL1 DC2 | 2025-07-01 | Marvin Blanco | Working in the second stairs tower and also working in the penthouse with the corrugated panels thanks God everything is working well on this second stairs tower because the issues we have the last time in the first stairs tower we are needing material but I'll talk to Joe to explain | Subcontractor | Joe Hoyle | false |  | true |  |  | 14 | 12 | false |  | Scaffolding, boomlift, forklift | false |  |  |  |  | ACM Corrugated / Screen wall | 20 | 96 | [20 empty] | 20 | 72
24069 | TCAT Pulaski | 2025-07-01 | JC Panels | Flashing | Subcontractor | Chris Buttrey | false |  | true |  |  | 3 | 30 | false |  |  | false |  |  |  |  | Subgirt Zee
23029 | BNA Concourse D | 2025-06-30 | Zarur Nazario Padron Jr | Installing flashing under L-ACM panel and blockade. Installing trim on Canopy terrace. Installing flashing on the corner of D10 IMP panels. Putting rivets on all of Coping on the rooftop of Record. Installed a piece of j-flashing on Concessions southside corner. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 4 | 40 | false |  | 1-65 boomlift, 2-10’ ladders, 1-scissor lift | false |  |  |  |  | Flashing Other Trim | [20 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 145 | 26 |  |  | 16 | 8 | [5 empty] | 6
24028 | CHI Memorial Hospital | 2025-06-30 | JC Panels | J flashing for screen wall, washers for screen wall | Subcontractor | Josh McPherson | false |  | true |  |  | 4 | 40 | false |  | Boom and fork lift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 12
24045 | TMMMS Childcare | 2025-06-30 | Starlin |  | Subcontractor | Chris Buttrey | true | Lightning Warning | false |  | 2 | 7 | 10 | false |  | 2 boom 45 | false |  |  |  |  | ACM | 11 | 8
24046 | UAB Biomedical Research and Psycholgy | 2025-06-30 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 4 | 32 | false |  | 65' boom | false |  |  |  |  | Subgirt Zee | [30 empty] | 740 | 32
24048 | QTS NAL2 DC1 | 2025-06-30 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | true | Thunderstorm | false |  | Raining | 3 | 10 | true | Acm sheets and flat metal | Boomlift forklift | false |  |  |  |  | ACM | 18 | 30
24068 | QTS NAL1 DC2 | 2025-06-30 | Marvin Blanco | Working in the stairs tower all the guys because needs to be done this week | Subcontractor | Joe Hoyle | false |  | true |  |  | 14 | 12 | false |  | Scaffolding, boomlift, forklift | false |  |  |  |  | ACM | 48 | 168
24069 | TCAT Pulaski | 2025-06-30 | JC Panels |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 3 | 6 | true | We receive the material berridge hr 16 | Boom and fork lift | false |  |  |  |  | Subgirt Zee
24048 | QTS NAL2 DC1 | 2025-06-29 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 3 | 10 | false |  | Boomlift forklift | false |  |  |  |  | ACM | 10 | 30
24065 | QTS NAL2 DC2 | 2025-06-29 | Chad McCoy | 2 inch hat channel. Insul. 1 1/4 screws | Subcontractor | Joe Hoyle | false |  | true |  |  | 1 | 8 | false |  | 80 foot boom | false |  |  |  |  | Other | [42 empty] | Louver brackets and verticals. 20 brackets. 20 verticals for fins | 8
24045 | TMMMS Childcare | 2025-06-28 | Starlin |  | Subcontractor | Chris Buttrey | true | two-panel routing | false |  | 3 | 7 | 8 | false |  | 2 boom 45 | false |  |  |  |  | ACM Insulation Subgirt Zee | 5 | 3 | [24 empty] | 152 | 1 |  |  | 160 | 1
24046 | UAB Biomedical Research and Psycholgy | 2025-06-28 | Naza Padron |  | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 3 | 18 | false |  | 86' boom | false |  |  |  |  | Subgirt Zee | [30 empty] | 420 | 18
24048 | QTS NAL2 DC1 | 2025-06-28 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 3 | 10 | false |  | Boomlift forklift | false |  |  |  |  | ACM | 10 | 30
24065 | QTS NAL2 DC2 | 2025-06-28 | Chad McCoy | 2 inch hat. Insul. 1 1/4 screws | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 8 | false |  | 80 foot boom | false |  |  | 4 |  | Corrugated / Screen wall Layout Other | [22 empty] | 24 | 6 | [18 empty] | Louver brackets 29 | 3
24005 | GCDC Building 2/VA1.2 | 2025-06-27 | Obed Bermudez | Crew 1 continues caulking and peeling protective film on East elevation. Crew 2 continue installing screen wall panels, middle clips,and tubes on the roof. Middle clips installed 6. Cleaning up east elevation | JWMCD Crew | Joe Hoyle | true | Job site shut down . |  |  |  | 12 | 3 |  |  | Boom lift | [5 empty] | ACM Caulking | 5 | 6 | [18 empty] | 60
24045 | TMMMS Childcare | 2025-06-27 | Starlin |  | Subcontractor | Chris Buttrey | true | Two-panel routing | false |  | 3 | 7 | 10 | false |  | 2 boom 45 | false |  |  |  |  | ACM Insulation Subgirt Zee | 15 | 7 | [24 empty] | 256 | 1.5 |  |  | 168 | 1.5
24046 | UAB Biomedical Research and Psycholgy | 2025-06-27 | Naza Padron |  | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 3 | 30 | false |  | 86' boom | false |  |  |  |  | Subgirt Zee | [30 empty] | 516 | 30
24048 | QTS NAL2 DC1 | 2025-06-27 | Antonio Sanchez | Move boomlift to south elevation bring panels from storage lote to NAL2 dc1 eyebrow panels | Subcontractor | Joe Hoyle | false |  | true |  |  | 3 | 10 | false |  | Boomlift forklift | false |  |  | 30 |  | Layout
24065 | QTS NAL2 DC2 | 2025-06-27 | Chad mccoy | 2 inch hat. Insul. 1 1/4 screws. | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 8 | false |  | 60 foot boom borrowed from antonio | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 24 | 8
23029 | BNA Concourse D | 2025-06-26 | Zarur Nazario Padron Jr | Installing coping up on Record rooftop. Installing/fabricating IMP panels on Concessions rooftop. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 7 | 70 | false |  | 1-65’ boomlift, scaffold, 3- yo-yos | false |  |  |  |  | Coping IMP | [8 empty] | 8 | 30 | [10 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | [8 empty] | 200 | 40
24005 | GCDC Building 2/VA1.2 | 2025-06-26 | Obed Bermudez | Crew 1 continues caulking and peeling protective film on East elevation. Crew 2 continue installing screen wall panels, middle clips,and tubes on the roof. Middle clips installed 60. Cleaning up east elevation | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 10 |  |  | Boom lift and forklift | [5 empty] | Caulking | [20 empty] | 160 | 30
24028 | CHI Memorial Hospital | 2025-06-26 | JC Panels | The scaffold for south side is to short and we can’t install with that scaffold.also all the flashing champagne and grey | Subcontractor | Josh McPherson | false |  | true |  |  | 4 | 32 | true | Scaffold but it isn’t working for our installation | Boom and fork lift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 17
24045 | TMMMS Childcare | 2025-06-26 | Starlin |  | Subcontractor | Chris Buttrey | true | Manufacturing of two panels I also reported about a panel that was damaged and the head of it said the panel was good. | false |  | 5 | 7 | 10 | false |  | 2 boom 45 | false |  |  |  |  | ACM | 8 | 10
24046 | UAB Biomedical Research and Psycholgy | 2025-06-26 | Naza Padron |  | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 3 | 30 | false |  | 86' boom | false |  |  |  |  | Subgirt Zee | [30 empty] | 504 | 30
24048 | QTS NAL2 DC1 | 2025-06-26 | Antonio Sanchez | Coping | Subcontractor | Joe Hoyle | true | Lighting | true |  | Raining | 3 | 10 | false |  | Boomlift forklift | false |  |  |  |  | Coping | [40 empty] | 100 | 30
24065 | QTS NAL2 DC2 | 2025-06-26 | Chad mccoy | 2 inch hat channel. 1 1/4 screws. Insul | Subcontractor | Joe Hoyle | true | Storms | true |  | Storms 72 | 4 | 3 | false |  |  | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 3 | 1
24068 | QTS NAL1 DC2 | 2025-06-26 | Marvin Blanco | Working in the screenwall , penthouse and the stairs tower installing the stairs tower the guys are still working in fixing the hats channels and Zs because yesterday and today was raining so we haven't done yet reinstalling the Hats changing the system deep | Subcontractor | Joe Hoyle | false |  | true |  |  | 12 | 12 | true | Clips for the corrugated panels | Scaffolding, boomlift, forklift | false |  |  |  |  | Corrugated / Screen wall Other | [22 empty] | 20 | 96 | [18 empty] | Reinstalling the hats in the first stairs tower | 48
23029 | BNA Concourse D | 2025-06-25 | Zarur Nazario Padron Jr | Installing coping on Record rooftop. Finishing up installing on Record Circle rooftop ladder. Changing out circle flashing for speakers on Record Terrace. Removing and installing panel for plate to be installed. Moving over scaffold to Concessions ladder on rooftop. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 9 | 90 | false |  | 2-65’ boomlift, scaffold, 2- yo-yo’s | false |  |  |  |  | ACM Coping Flashing Other | 3 | 24 | [18 empty] | 20 | 2 | 0 | 0 | [6 empty] | 0 | 0 | 104 | 10 | [6 empty] | 100 | 50 |  | 4
24005 | GCDC Building 2/VA1.2 | 2025-06-25 | Obed Bermudez | Crew 1 continues caulking and peeling protective film on East elevation. Crew 2 continue installing screen wall panels, middle clips,and tubes on the roof. Middle clips installed 65. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 10 |  |  | Boom lifts and forklift | [5 empty] | Caulking | [20 empty] | 265 | 40
24028 | CHI Memorial Hospital | 2025-06-25 | JC Panels | Scaffold, Morin panels | Subcontractor | Josh McPherson | false |  | true |  |  | 4 | 24 | false |  |  | false |  |  |  |  | Corrugated / Screen wall Flashing Insulation Subgirt Zee | [22 empty] | 9
24045 | TMMMS Childcare | 2025-06-25 | Starlin |  | Subcontractor | Chris Buttrey | true | 1 panel router Lightning Warning | false |  | 3 | 7 | 10 | false |  | 2 boom 45 | false |  |  |  |  | ACM | 19 | 7
24046 | UAB Biomedical Research and Psycholgy | 2025-06-25 | Naza Padron | layouts, moving material, instsling Zee's | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 3 | 30 | false |  | 86' boom | false |  |  | 8 |  | Layout Other Subgirt Zee | [30 empty] | 85 | 18 | [11 empty] | 4
24065 | QTS NAL2 DC2 | 2025-06-25 | Chad McCoy | 2 inch hat. 1 1/4 screws. Insulation. | Subcontractor | Joe Hoyle | true | Lightning all afternoon. Back to back storms | true |  | Storms | 4 | 3 | false |  |  | false |  |  |  |  | Other | [42 empty] | Nothing bc of storms | 3
23029 | BNA Concourse D | 2025-06-24 | Zarur Nazario Padron Jr | Installing vent flashing on Record Circle rooftop. Also installing ACM panels and fabricating IMP panels for ladders on Record rooftop. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 8 | 80 | false |  | Scaffold and ladders | false |  |  |  |  | ACM Flashing IMP | 3 | 6 | [6 empty] | 7 | 24 | [10 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 280 | 50
24005 | GCDC Building 2/VA1.2 | 2025-06-24 | Obed Bermudez | Crew 1 continues installing ACM panels, flatmetal, and J on East elevation. Crew 2 continue installing screen wall panels, middle clips,and tubes on the roof. Middle clips installed 44. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 10 |  |  | Boom lifts and forklift. | [5 empty] | Caulking Trim | [20 empty] | 150 | 20 | [14 empty] | 48 | 30
24028 | CHI Memorial Hospital | 2025-06-24 | JC Panels | Scaffold, Morin panels | Subcontractor | Josh McPherson | true | The scaffold haven’t arrived . McCarthy made us go home because we have not had the ccip insurance so we couldn’t do almost nothing today | true |  |  | 4 | 32 | false |  |  | false |  |  |  |  | Corrugated / Screen wall Flashing Insulation Subgirt Zee | [22 empty] | 9
24045 | TMMMS Childcare | 2025-06-24 | Starlin |  | Subcontractor | Chris Buttrey | true | Three-panel router An installer who arrived after 12 noon | false |  | 4 | 7 | 10 | false |  | 2 boom 45 | false |  |  |  |  | ACM Insulation Subgirt Zee | 15 | 4 | [24 empty] | 160 | 1 |  |  | 120 | 1
24045 | TMMMS Childcare | 2025-06-24 | Zachary Hood | Installing Zee and insulations | Subcontractor | Chris Buttrey | true | lighting | true |  | rainy weather | 6 | 9 | false |  | (3) 45' boomlifts | false |  |  |  |  | ACM | 25 | 0
24046 | UAB Biomedical Research and Psycholgy | 2025-06-24 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 3 | 30 | false |  | 65' boom | false |  |  |  |  | Insulation | [26 empty] | 1216 | 30
24065 | QTS NAL2 DC2 | 2025-06-24 | Chad mccoy | 2 inch hat channel. 1 1/4 screws. | Subcontractor | Joe Hoyle | true | Installing this corrugated from the back off of scaffolding is going to suck. | true |  | Cloudy 107 | 4 | 9 | false |  |  | false |  |  | 2 |  | Corrugated / Screen wall Layout Other | [22 empty] | 8 | 1.5 | [18 empty] | L metal on the top of the steel for the coping to attach to after corrugated is installed | 4
24005 | GCDC Building 2/VA1.2 | 2025-06-23 | Obed Bermudez | We continue caulking around the bulletproof frame. | JWMCD Crew | Joe Hoyle | [5 empty] | 2 | 10 | [8 empty] | Caulking | [20 empty] | 50 | 20
24005 | GCDC Building 2/VA1.2 | 2025-06-23 | Obed Bermudez | Crew 1 continues installing ACM panels, flatmetal, and J on East elevation. Crew 2 continue installing screen wall panels, middle clips,and tubes on the roof. Middle clips installed 22. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 10 |  |  | Boom lifts and forklift | [5 empty] | ACM Caulking | 31 | 70 | [18 empty] | 140 | 10
24028 | CHI Memorial Hospital | 2025-06-23 | JC Panels | We need scaffold, Morin panels for south elevation, cladding panels | Subcontractor | Josh McPherson | false |  | true |  |  | 7 | 32 | false |  | Boom lift and fork lift | false |  |  |  |  | Corrugated / Screen wall Flashing Insulation Subgirt Zee | [22 empty] | 3
24045 | TMMMS Childcare | 2025-06-23 | Starlin |  | Subcontractor | Chris Buttrey | true | Lightning Warning | false |  | 1 | 7 | 9.5 | false |  | 2boom 45 | false |  |  |  |  | ACM Insulation Subgirt Zee | 14 | 6 | [24 empty] | 136 | 1 |  |  | 280 | 1.5
24046 | UAB Biomedical Research and Psycholgy | 2025-06-23 | Naza Padron | 22 bundles of insulation 1,408sf | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 3 | 30 | false |  | 65' boom | false |  |  |  |  | Insulation | [26 empty] | 1408 | 30
24065 | QTS NAL2 DC2 | 2025-06-23 | Chad McCoy | 2 inch hat channel is still needed, We spent today’s time getting material to the roof, There is no easy way to do this. So I’m booming it all up and handing it over. | Subcontractor | Joe Hoyle | true | I picked up the L metal from Nashville, I also picked up all our clips from Cincinnati. The screws after I bought some was dropped off in yard on my trailer | true |  | Cloudy and hot | 4 | 6 | true | I brought L metal, clips and screws | My scaffolding | false |  |  | 0.5 |  | Layout
24068 | QTS NAL1 DC2 | 2025-06-23 | Marvin Blanco | Working in the screenwall, Working in the penthouse and working in the stairs tower fixing all the Zs because in the drawings show a different deep and that doesn't work because the Zs are to big to make the panels work we are using 2" hats and 1" hat, the drawings show 4" Zs and 1" hat but with those Zs doesn't work the layout for the panels and also it's the same in the second stairs | Subcontractor | Joe Hoyle | false |  | true |  |  | 14 | 12 | false |  | Scaffolding and boomlift | false |  |  |  |  | Corrugated / Screen wall Other | [22 empty] | 26 | 96 | [18 empty] | Taking down panels and Zs because the system deep is different in the stairs tower the drawings are wrong | 72
23029 | BNA Concourse D | 2025-06-21 | Zarur Nazario Padron Jr | Installed coping on record rooftop and also installed angle flashing on bottom of corner panels and up against brick wall. Also caulked on record rooftop | JWMCD Crew | Marc Ribar | false |  |  |  |  | 8 | 64 | false |  | 2- yo-yos and 1- scissor lift | false |  |  |  |  | Coping Flashing | [20 empty] | 100 | 16 | 0 | 0 | [6 empty] | 0 | 0 | 160 | 16 | [6 empty] | 120 | 32
24045 | TMMMS Childcare | 2025-06-21 | Starlin |  | Subcontractor | Chris Buttrey | true | Unloading the truck and manufacturing ACM panels | false |  | 1.5 | 6 | 8.5 | true | 200 pcs zee 9 panel ACM 1 1/8 rev 24+lf 1 1/58 2448+lf a few sheets of Acm materials 6 | 2 boom 45 | false |  |  |  |  | ACM Insulation Subgirt Zee | 12 | 5 | [24 empty] | 96 | 1 |  |  | 85 | 1
23029 | BNA Concourse D | 2025-06-20 | Zarur Nazario Padron Jr | Caulking on Record Canopy rooftop | JWMCD Crew | Marc Ribar | false |  |  |  |  | 5 | 50 | false |  | Scaffold, and yo-yos | false |  |  |  |  | Caulking | [20 empty] | 220 | 50 | 0 | 0 | [6 empty] | 0 | 0
23064 | Yondr Allegro 2S | 2025-06-20 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 3 | 9 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 40 | 27
24005 | GCDC Building 2/VA1.2 | 2025-06-20 | Obed Bermudez | We continue working on the punch list cleaning adjusting caulk and seals around window frames and doors. | JWMCD Crew | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lifts and forklift
24005 | GCDC Building 2/VA1.2 | 2025-06-20 | Obed Bermudez | Crew 1 continues installing ACM panels, flat metal, and J on East elevation. Crew 2 continues caulking and peeling protective film on the west elevation. Crew 3 continue installing screen wall panels, middle clips, and tubes on the roof. Middle clips installed 22. Cleaned up all pallets and trash on west elevation. | JWMCD Crew | Joe Hoyle | [6 empty] | 10 |  |  | Boom lifts and forklift. | [5 empty] | ACM Caulking Hat Channel | 30 | 40 | [18 empty] | 290 | 20
24045 | TMMMS Childcare | 2025-06-20 | Starlin |  | Subcontractor | Chris Buttrey | true | panel cutting and routing. | false |  | 1.5 | 6 | 10 | false |  | Two 45 boom | false |  |  |  |  | ACM Insulation Subgirt Zee | 13 | 10 | [24 empty] | 135 | 4 |  |  | 1200 | 6
24045 | TMMMS Childcare | 2025-06-20 | Zachary Hood | Installing Z Girts and continuing acm install | Subcontractor | Chris Buttrey | true | lighting | true |  | rainy weather | 5 | 8 | false |  | (3) 45' boomlifts | false |  |  |  |  | ACM | 35 | 24
24046 | UAB Biomedical Research and Psycholgy | 2025-06-20 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 3 | 24 | false |  | 65' boom | false |  |  |  |  | Flashing Subgirt Zee | [30 empty] | 370 | 20 | 29 | 4
24065 | QTS NAL2 DC2 | 2025-06-20 | Chad mccoy | 2 inch hat. Screws. Clips for corrugated | Subcontractor | Joe Hoyle | true | Some material is missing and material is coming in in the wrong order, Pent house is not done. Wood blocking is wrong. And no term bar. Tpo is not done in key areas. Lower roof is no finished in tpo but we don’t have the L metal in site or the 2 inch hat channel. On the roof there is material everywhere. It will be a battle getting other trades to move there material | true |  | Cloudy hot and windy | 4 | 8 | false |  | My scaffolding | false |  |  |  |  | Hat Channel | [34 empty] | 832 | 8
23064 | Yondr Allegro 2S | 2025-06-19 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | No se pI have to work because there is a crane located near our work area and they allowed us to work for safety 4 hours |  |  |  | 3 | 5 | true | Insulacion | Boom lift | [5 empty] | Other | [43 empty] | 0
24005 | GCDC Building 2/VA1.2 | 2025-06-19 | Obed Bermudez | We continue doing punch list cleaning, adjusting frames, seals, and caulking. | JWMCD Crew | Joe Hoyle | [5 empty] | 4 | 10
24028 | CHI Memorial Hospital | 2025-06-19 | JC Panels | We need the correct panel 210-1A24 because it came inverted and also Carson is asking that when we are going to install that column vertical panel. | Subcontractor | Josh McPherson | true | McCarthy send us back to hotel because there was a heavy rain and we start working again 1pm | true |  | Rainy | 4 | 24 | true |  | Boom and fork lift | false |  |  |  |  | ACM Corrugated / Screen wall Flashing Trim | 2 | [21 empty] | 10
24045 | TMMMS Childcare | 2025-06-19 | Starlin |  | Subcontractor | Chris Buttrey | true | Lightning Warning They also took one of our workers out of work for not being tied up in the roof One more thing, we removed 16 panels because they were poorly installed. | false |  | 2 .5 hour total | 7 | 8 | false |  | 45 boom | false |  |  |  |  | ACM | 21 | 8
24046 | UAB Biomedical Research and Psycholgy | 2025-06-19 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 4 | 40 | false |  | 65' boom | false |  |  |  |  | Subgirt Zee | [30 empty] | 648 | 40
24065 | QTS NAL2 DC2 | 2025-06-19 | Chad mccoy | L metal. I’m not waiting I’ll go get it. Screws that are in route Friday, caulking tips requested 2 inch hat channel for lower corrugated | Subcontractor | Joe Hoyle | true | We are working on south west corner corrugated hat channel, The wood blocking on pent house does not hang over. We do not have the lower corrugated 2 inch hat, there is no continuous section of coping installed for louvers, There are no termination bars on pent house. It’s also missing penetrations, There are multiple areas where the roof is not installed and we can’t work in these areas, We are not allowed to have shaving fall underneath the insulation that goes under the top. We are also working 2 shift into 3rd shift. This is needed due to no room to work with other trades. | true |  | Cloudy, rain on and off. Wind gust around 26 | 4 | 8 | true |  | My scaffolding | false |  |  | 3 |  | Hat Channel Layout | [34 empty] | 53 | 5
24068 | QTS NAL1 DC2 | 2025-06-19 | Marvin Blanco | Cleaning our areas of work because WT is trying to back charge McDougall for something it's not ours the others company's have to many things in the roof in the carpet and they don't care my guys are cleaning 100% everyday because we don't like problem or any issues WT should check the other companies because they don't see anything they just walk 2 minutes in the roof and they think it's McDougall guys are leaving cutting stuff metal panels and metal shavings but they have a lot of areas we haven't been working and there's is a lot metal shaving and horrible under the red carpet | Subcontractor | Joe Hoyle | false |  | true |  |  | 13 | 12 | false |  | Scaffolding and boomlift | false |  |  |  |  | Other | [42 empty] | Cleaning all the roof | 156
23064 | Yondr Allegro 2S | 2025-06-18 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Wait for the insulation that didn’t arrive 4 hours |  |  |  | 7 |  |  |  | Boom lift | [5 empty] | Caulking | [20 empty] | 300 | 30
24005 | GCDC Building 2/VA1.2 | 2025-06-18 | Obed Bermudez | We started fixing everything on the punch list. Cleaning up calling on frames, glass, fixing miss aligned frames, and short rubber on some areas. | JWMCD Crew | Joe Hoyle | [5 empty] | 4 | 9
24005 | GCDC Building 2/VA1.2 | 2025-06-18 | Obed Bermudez | Crew 1 continues caulking and peeling protective film on the west elevation. Crew 2 continues installing screen wall middle clips and tubes on the roof. Middle clips installed: 42. | JWMCD Crew | Joe Hoyle | true | HITT stopped us from working on the east elevation. |  |  | Rainy day | 12 | 10 |  |  | Boom lifts and forklift | [5 empty] | ACM Caulking | [20 empty] | 411 | 30
24028 | CHI Memorial Hospital | 2025-06-18 | JC Panels | Scaffold. We are installing the corners trim of the morin | Subcontractor | Josh McPherson | true | Scaffold and Morin panels for south elevation | true |  |  | 4 | 40 | false |  | Boom and fork lift | false |  |  |  |  | Subgirt Zee Trim
24045 | TMMMS Childcare | 2025-06-18 | Zachary Hood | Installing Zee and insulations | Subcontractor | Chris Buttrey | false |  | true |  |  | 6 | 8 | false |  | (3) 45' boomlifts | false |  |  |  |  | ACM | 29 | 20
24045 | TMMMS Childcare | 2025-06-18 | Zachary Hood | Installing Zee and insulations | Subcontractor | Chris Buttrey | true | lighting | true |  | rainy weather | 6 | 8 | false |  | (3) 45' boomlifts | false |  |  |  |  | ACM | 20 | 20
24045 | TMMMS Childcare | 2025-06-18 | Starlin |  | Subcontractor | Chris Buttrey | true | Expect lightning | false |  | 1.5 | 7 | 10 | false |  | Two boom 45 | false |  |  |  |  | ACM | 29 | 10
24068 | QTS NAL1 DC2 | 2025-06-18 | Marvin Blanco | Working in the penthouse and also installing ACM panels in the stairs tower and metal panels in the screenwall for today we don't have any issues Joe is working in everything else for giving us everything we need | Subcontractor | Joe Hoyle | false |  | true |  |  | 13 | 12 | false |  | Scaffolding and boomlift | false |  |  |  |  | ACM Corrugated / Screen wall | 6 | 48 | [20 empty] | 20 | 108
24088 | Mercedes Benz West Chester | 2025-06-18 | Jhonatan Bernal |  | Subcontractor | Luke Giles | false |  | false |  |  | 2 | 8 | false |  | Bomm lift | false |  |  |  |  | ACM | 17 | 8
23064 | Yondr Allegro 2S | 2025-06-17 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Waiting for the delivery of the Caukin material 2 hours |  |  |  | 7 |  |  |  | Boom lift | [5 empty] | Caulking Flashing | [20 empty] | 300 | 30 | [10 empty] | 300 | 30
24005 | GCDC Building 2/VA1.2 | 2025-06-17 | Obed Bermudez | Crew 1 continues installing ACM panels, flat metal, and J on the east elevation. Crew 2 continues caulking and peeling protective film on the west elevation. Crew 3 continues installing screen wall middle clips and tubes on the roof. Middle clips installed: 32. | JWMCD Crew | Joe Hoyle | true | HITT made us mobilize our equipment outside the east elevation due to them using the parking spaces for a next day event. |  |  |  | 12 | 11 | true | Caulking. | Boom lifts and forklift. | [5 empty] | ACM Caulking Flashing Subgirt Zee | 1 | [19 empty] | 310 | [9 empty] | 20 |  | 20
24028 | CHI Memorial Hospital | 2025-06-17 | JC Panels | Scaffold, Morin for south elevation | Subcontractor | Josh McPherson | false |  | true |  |  | 4 | 40 | false |  | Boom fork lift | false |  |  |  |  | Subgirt Zee Trim
24045 | TMMMS Childcare | 2025-06-17 | Starlin |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 7 | 10 | false |  | Two boom 45 | false |  |  |  |  | ACM | 24 | 10
24045 | TMMMS Childcare | 2025-06-17 | Zachary Hood | Installing Zee and insulations | Subcontractor | Chris Buttrey | true | lighting | true |  | rainy weather | 6 | 0 | false |  | (3) 45' boomlifts | false |  |  |  |  | ACM | 0 | 0
24046 | UAB Biomedical Research and Psycholgy | 2025-06-17 | Naza Padron | lightning rainy day. working on and off | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 2 | 16 | false |  | 65' boom | false |  |  |  |  | Subgirt Zee | [30 empty] | 150 | 16
24068 | QTS NAL1 DC2 | 2025-06-17 | Marvin Blanco | Installing metal panels in the penthouse and also installing the screenwall Also working in the stairs tower installing Zs cleaning ours areas with out issues Thanks God everything is working well the only thing we are going to need is screws and hats channels | Subcontractor | Joe Hoyle | false |  | true |  |  | 13 | 12 | false |  | Scaffolding and boomlift | false |  |  |  |  | Corrugated / Screen wall Hat Channel | [22 empty] | 40 | 120 | [10 empty] | 100 | 36
23029 | BNA Concourse D | 2025-06-16 | Zarur Nazario Padron Jr | Installing ACM panels on canopy of Record rooftop | JWMCD Crew | Marc Ribar | false |  |  |  |  | 6 | 48 | false |  | 1-65’ boomlift, scaffold | false |  |  |  |  | ACM | 32 | 48 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
23064 | Yondr Allegro 2S | 2025-06-16 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 7 |  |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Flashing Insulation Subgirt Zee | [22 empty] | 30 | 20 |  |  | 400 | 10 |  |  | 200 | 20 | 200 | 10
24005 | GCDC Building 2/VA1.2 | 2025-06-16 | Obed Bermudez | Crew 1 continues installing ACM panels, flat metal, and J on East elevation. Crew 2 continues caulking and peeling protective film on the west elevation. Crew 3 continue installing screen wall panels, middle clips, and tubes on the roof. Middle clips installed 30. Cleaned up all pallets and trash on west elevation. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 11 |  |  | Boom lifts forklifts | [5 empty] | ACM Caulking Subgirt Zee | 8 | 30 | [18 empty] | 62 | 20 | [8 empty] | 190 | 20
24028 | CHI Memorial Hospital | 2025-06-16 | JC Panels | Morin for south elevation. Scaffold | Subcontractor | Josh McPherson | false |  | true |  |  | 4 | 40 | true |  | Boom and fork lift | false |  |  |  |  | Insulation Subgirt Zee
24046 | UAB Biomedical Research and Psycholgy | 2025-06-16 | Naza Padron | 18 wheel loads of material arrived at 8am and we had to wait for a forklift to unload. | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 3 | 24 | true | An 18-wheeler was unloaded with six pallets of Zees and two small pallets of shims and bolts from 10 a.m. to 12 p.m., then another 18-wheeler was unloaded with insulation from 12 p.m. to 2 p.m. | 65' boom | false
24065 | QTS NAL2 DC2 | 2025-06-16 | Chad McCoy | In route | Subcontractor | Joe Hoyle | true | No room for lay down around building, We had to off load in nal 1/2/3 parking lot in BFE. | true |  | Cloudy | 4 | 11 | true | Corrugated,plywood and insulation for plywood/material laydown | My scaffolding, | false |  |  |  |  | Other | [42 empty] | Awaited deliveries, kissed hands and shuck baby’s with gray, Corrugated was delivered, plywood and insulation for lay down. I walked the site with gray, Pent house is missing waterproofing, penetrations, termination bar, doors, one side is missing roofing for scaffolding to go on, Louver section is missing coping over 60 percent and 25 percent is missing roofing material( in process of being installed) Corrugated on steel has around 250 yards of coping done so this is ready for hat and corrugated. We just have to get it all to the roof | 11
24068 | QTS NAL1 DC2 | 2025-06-16 | Marvin Blanco | Installing metal panels in the penthouse and also installing the screenwall Also working in the stairs tower installing Zs taking measurements for the louvers blades cleaning ours areas | Subcontractor | Joe Hoyle | false |  | true |  |  | 13 | 12 | false |  | Scaffolding and boomlift | false |  |  |  |  | Corrugated / Screen wall Hat Channel | [22 empty] | 40 | 120 | [10 empty] | 100 | 36
24088 | Mercedes Benz West Chester | 2025-06-16 | Jhonatan bernal |  | Subcontractor | Luke Giles | false |  | false |  |  | 2 | 10 | false |  | Boom lift | false |  |  |  |  | ACM | 17 | 10
24048 | QTS NAL2 DC1 | 2025-06-15 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 5 | 10 | false |  | Boomlift, forklift | false |  |  |  |  | ACM | 10 | 50
24048 | QTS NAL2 DC1 | 2025-06-15 | Antonio Sanchez | ACM housekeeping | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 10 | false |  | Boomlift forklift | false |  |  |  |  | ACM | 6 | 30
24048 | QTS NAL2 DC1 | 2025-06-14 | Antonio Sanchez | ACM PANELS | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 10 | false |  | Boomlift forklift | false |  |  |  |  | ACM | 18 | 50
24005 | GCDC Building 2/VA1.2 | 2025-06-13 | Obed Bermudez | Crew 1 spent the day modifying and installing panels and peeling off protective film. Crew 2 continues working on middle clip connections. Crew 3 continues caulking west elevation and peeling protective film. We had to stop a crew and work on getting scaffold and trash off the roof. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 11 |  |  | Boom lifts and forklift. | [5 empty] | ACM | 8
24028 | CHI Memorial Hospital | 2025-06-13 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 4 | 32 | true |  |  | false |  |  |  |  | ACM Corrugated / Screen wall | 4 | [21 empty] | 20
24045 | TMMMS Childcare | 2025-06-13 | Zachary Hood |  | Subcontractor | Chris Buttrey | true | Rainy weather | false |  | rainy weather | 1 | 0 | false |  | (3) 45' boomlifts | false |  |  |  |  | ACM | 0 | 0
24048 | QTS NAL2 DC1 | 2025-06-13 | Antonio Sanchez | Acm panels louver, housekeeping on north side | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 10 | false |  |  | false |  |  |  |  | ACM Louvre | 23 | 30 | [23 empty] | 20
24082 | GTN Cable | 2025-06-13 | Kevin Morris |  | Subcontractor | Josh McPherson, Nick Akins | false |  | false |  |  | 1 | 6 | false |  | T46 boom & 45 knuckle boom | false |  |  |  |  | Trim | [36 empty] | 90 | 6
23064 | Yondr Allegro 2S | 2025-06-12 | Ever mendoza | I need more insulation 2" and caulk and backer rod | Subcontractor | Joe Hoyle |  |  | true |  |  | 7 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 45 | 30 | [6 empty] | 100 | 10 | 200 | 20
24005 | GCDC Building 2/VA1.2 | 2025-06-12 | Obed Bermudez | Crew 1 continues installing ACM panels, flat metal, and J on East elevation. Crew 2 continues fabricating 1 panel, caulking and peeling protective film on the west elevation. Crew 3 continue installing screen wall panels, middle clips, and tubes on the roof. Middle clips installed 26. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 10 |  |  | Boom lifts and forklift | [5 empty] | ACM Hat Channel Plate Tubing | 30 | 40 | 2 | [17 empty] | 62 | 20 | [6 empty] | 14 | 1 |  |  |  |  | 70 | 10
24045 | TMMMS Childcare | 2025-06-12 | Zachary Hood | Installing Zee and insulations | Subcontractor | Chris Buttrey | false |  | true |  |  | 6 | 10 | false |  | (3) 45' boomlifts | false |  |  |  |  | ACM | 30 | 30
24045 | TMMMS Childcare | 2025-06-12 | Zachary Hood | Installing Zee and insulations | Subcontractor | Chris Buttrey | false |  | true |  |  | 7 | 10 | false |  | (3) 45' boomlifts | false |  |  |  |  | ACM | 40 | 40
24048 | QTS NAL2 DC1 | 2025-06-12 | Antonio Sanchez | Louver corrugated rib panel | Subcontractor | Joe Hoyle | false |  | true |  |  | 6 | 10 | true |  | Boomlift forklift | false |  |  |  |  | Corrugated / Screen wall Louvre | [22 empty] | 18 | 30 |  | 30
24082 | GTN Cable | 2025-06-12 | Kevin is |  | Subcontractor | Josh McPherson, Nick Akins | false |  | false |  |  | 2 | 10 | false |  | T46 boom & 45 knuckle boom | false |  |  |  |  | Trim | [36 empty] | 110 | 10
24088 | Mercedes Benz West Chester | 2025-06-12 | Jhonatan bernal |  | Subcontractor | Luke Giles | false |  | false |  |  | 3 | 10 | false |  | Boom lift | false |  |  |  |  | ACM | 16 | 10
23064 | Yondr Allegro 2S | 2025-06-11 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Move material to the work area 1 hour |  |  |  | 7 | 10 | true | Two trucks materials to FRP panels | Boom lift | [5 empty] | Corrugated / Screen wall Insulation | [22 empty] | 60 | 30 |  |  | 1000 | 30
24005 | GCDC Building 2/VA1.2 | 2025-06-11 | Obed Bermudez | Crew 1 continues installing ACM panels, flat metal, and J on East elevation. Crew 2 continues fabricating 2 panels and peeling protective film on the west elevation. Crew 3 continue installing screen wall panels, clips, and tubes on the roof. Crew 4: caulking windows adding rubber to door, fixing trim, moving material and cleaning up. Total clips installed: 40. Flat metal 250 lf. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 10 | true | Acm sheets | Boom lifts and forklift | [5 empty] | ACM Caulking | 31 | 50 | [18 empty] | 30 | 10
24005 | GCDC Building 2/VA1.2 | 2025-06-11 | Obed Bermudez | We continue installing glass and caulk around a window that we had previously removed and repaired. | JWMCD Crew | Joe Hoyle | [5 empty] | 4 | 10 | [8 empty] | Caulking | [20 empty] | 20 | 40
24009 | Cityside Subaru | 2025-06-11 | Jonathan Bonilla | We continue installing perforated panels and clips on the north elevation. total clips installed on concrete 25. | JWMCD Crew | Chris Buttrey | [5 empty] | 4 | 10 |  |  | Boom lifts
24018 | QTS-NAL1-DC1 | 2025-06-11 | Marvin Blanco | Finishing all the work at NAL 1 DC1 with freedom wall there is one problem there with the plywood in the flooring my guy leave the plywood 1' back from the red panels and them somebody else put it tie to the red panels in case those panels get damaged it's not our fault | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 12 | false |  | Boomlift | false |  |  |  |  | ACM | 1 | 5
24028 | CHI Memorial Hospital | 2025-06-11 | JC Panels | Wood panels, screen wall. This might take a while to get it but for now we are good to work we have plenty material | Subcontractor | Josh McPherson | false |  | true |  |  | 4 | 20 | true | We received screws | Boom and fork lift | false |  |  |  |  | Subgirt Zee
24045 | TMMMS Childcare | 2025-06-11 | Zachary Hood | Installing Zee and insulations | Subcontractor | Chris Buttrey | false |  | true |  |  | 6 | 10 | false |  | (3) 45' boomlifts | false |  |  |  |  | ACM | 40 | 30
24045 | TMMMS Childcare | 2025-06-11 | Zachary Hood | Installing Zee and insulations | Subcontractor | Chris Buttrey | false |  | true |  |  | 6 | 8 | false |  | (3) 45' boomlifts | false |  |  |  |  | ACM | 20 | 24
24048 | QTS NAL2 DC1 | 2025-06-11 | Antonio Sanchez | Louver acm | Subcontractor | Joe Hoyle | false |  | true |  |  | 6 | 10 | true | Boomlift |  | false |  |  |  |  | ACM Louvre | 6 | 30 | [23 empty] | 30
24068 | QTS NAL1 DC2 | 2025-06-11 | Marvin Blanco | Working in the roof with the screenwall and also installing the stairs tower installing the Zs cleaning our areas doble cleaning in the roof because we don't want to get a back charge | Subcontractor | Joe Hoyle | false |  | true |  |  | 13 | 12 | true | Silicone screws | Boomlift scaffolding | false |  |  |  |  | Corrugated / Screen wall Hat Channel | [22 empty] | 120 | 22 | [10 empty] | 100 | 36
24082 | GTN Cable | 2025-06-11 | Kevin Morris |  | Subcontractor | Josh McPherson, Nick Akins | false |  | false |  |  | 2 | 10 | false |  | T46 boom & 45 knuckle boom | false |  |  |  |  | IMP Trim | [8 empty] | 2 | 4 | [26 empty] | 120 | 6
24082 | GTN Cable | 2025-06-11 | Kevin Morris |  | Subcontractor | Josh McPherson, Nick Akins | false |  | false |  |  | 2 | 10 | false |  | T46 boom & 45 knuckle boom | false |  |  |  |  | Flashing IMP | [8 empty] | 4 | 7 | [22 empty] | 60 | 3
23064 | Yondr Allegro 2S | 2025-06-10 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Move material to the work area |  |  |  | 7 |  |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Subgirt Zee | [22 empty] | 60 | 30 | [6 empty] | 400 | 30
24005 | GCDC Building 2/VA1.2 | 2025-06-10 | Obed Bermudez | Crew continues installing bulletproof frame prepping and glass on doors. 6 frame pieces installed and 3 glass. | JWMCD Crew | Joe Hoyle | [5 empty] | 4 | 10
24005 | GCDC Building 2/VA1.2 | 2025-06-10 | Obed Bermudez | Crew 1 spent the day modifying and installing panels and peeling off protective film. Crew 2 continues working on middle clip connections. | JWMCD Crew | Joe Hoyle | true | We couldn’t work on the east elevation due to another crew stripping the pavement. Keep in mind this is only pushing our schedule. |  |  |  | 12 | 10 |  |  | Boom lift and forklift | [5 empty] | ACM Other | 2 | 40 | [40 empty] | 30 | 50
24009 | Cityside Subaru | 2025-06-10 | Jonathan Bonilla | We continue installing perforated panels and clips on the north elevation. total clips installed on concrete. | JWMCD Crew | Chris Buttrey | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | Plate |  |  | 40 | 40
24028 | CHI Memorial Hospital | 2025-06-10 | JC Panels | We need 2” screws asap we don’t have any, also tek 2 1 1/4”.. the cleat 213 | Subcontractor | Josh McPherson | false |  | true |  |  | 4 | 40 | true |  | Boom and fork lift | false |  |  |  |  | Subgirt Zee
24045 | TMMMS Childcare | 2025-06-10 | Zachary Hood | Installing Zee and insulations | Subcontractor | Chris Buttrey | true | Lighting in area went home at 3pm | true |  | inclement weather | 7 | 8 | false |  | (3) 45' boomlifts | false |  |  |  |  | ACM | 20 | 40
24048 | QTS NAL2 DC1 | 2025-06-10 | Antonio Sanchez | Housekeeping on roof metal insulation | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 50 | false |  | Boomlift forklift | false |  |  |  |  | Insulation | [27 empty] | 30
24068 | QTS NAL1 DC2 | 2025-06-10 | Marvin Blanco | Working in the roof with the scaffolding and also cleaning our areas of work but today the guys saw a lot of damage in the roof where we haven't been working yet on those places it's just for cover McDougall and P-I-D back charging for the damaged in the roof carpet | Subcontractor | Joe Hoyle | false |  | true |  |  | 14 | 12 | false |  | Boomlift scaffolding | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 20 | 168
24088 | Mercedes Benz West Chester | 2025-06-10 | Jhonatan Bernal |  | Subcontractor | Luke Giles | true | The project is currently delayed due to panel measurements not matching the approved plans. We are working on correcting the issue as quickly as possible. Thank you for your understanding. Best regards, | false |  | 3 days | 3 | 8 | false |  | Boom litf | false |  |  |  |  | ACM | 5 | 8
23029 | BNA Concourse D | 2025-06-09 | Antonio | We tried to finish installing the last of the roof panels but we ended up getting caught up in the rain | JWMCD Crew | Marc Ribar | true | The weather rained us out |  |  | Thunderstorms | 12 | 3 | false |  | 4 man lifts and a lull | false |  |  |  |  | ACM | 10 | 3
23064 | Yondr Allegro 2S | 2025-06-09 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Move material to the work area 1 hour |  |  |  | 7 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Subgirt Zee | [22 empty] | 60 | 30 | [6 empty] | 400 | 30
24005 | GCDC Building 2/VA1.2 | 2025-06-09 | Obed Bermudez | Crew 1 continues installing ACM panels, flat metal, and J on East elevation. Crew 2 contimues peeling protective film on the west elevation. Crew 3 continue installing screen wall panels, clips, and tubes on the roof. Crew 4: moving material and cleaning up. Total clips installed: 42. Flat metal 250 lf. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 10 |  |  | Boom lifts and forklift | [5 empty] | ACM Plate Tubing | 10 | 50 | 14 | 30 | [24 empty] | 84 | 30
24009 | Cityside Subaru | 2025-06-09 | Jonathan Bonilla | We continue working on North elevation, installing tubes, clips, and perforated panels. | JWMCD Crew | Chris Buttrey | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | Plate Tubing |  |  | 24 | 38 | [24 empty] | 80 | 2
24018 | QTS-NAL1-DC1 | 2025-06-09 | Marvin Blanco | Finishing the red panels in the freedom wall and also cleaning everything we only have one issue on this project it's the silicone in the ceiling and we don't have awser jet I hope tomorrow we can do something about it but everything else it's done with the punch list | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 12 | false |  | Boomlift | false |  |  |  |  | ACM | 8 | 60
24020 | QTS ATL2 DC2 Osgood | 2025-06-09 | Marvin Blanco | Taking down one panel from the entry and changing the panel for a new one and we need some areas ready for us but Hitt guys are not ready for us we have one opening around the pipes to finish and there is some big cables on it and also we don't have any awser in the canopy we are waiting for that seems last year I hope one day we get this little job done and the guys are needing two sheets of stainless steel flats sheets | Subcontractor | Dillon Bowman | true | Canopy and the last two openings around the pipes | true |  | Very good condition hot 🔥 | 3 | 10 | false |  | No equipment | false |  |  |  |  | ACM Other | 1 | 4 | [40 empty] | Losing time on this project | 26
24028 | CHI Memorial Hospital | 2025-06-09 | JC Panels | Cleat 213, screws, scaffold | Subcontractor | Josh McPherson | true | We need the 213 cleat to continue installation | true |  |  | 4 | 40 | true |  | Boom and fork lift | false |  |  |  |  | ACM Corrugated / Screen wall Insulation Subgirt Zee | 4 | [21 empty] | 28
24048 | QTS NAL2 DC1 | 2025-06-09 | Antonio Sanchez | Housekeeping on roof install Z METAL and insulation | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 10 | true | Acm panels wing wall and freedom wall. | Boomlift forklift | false |  |  |  |  | ACM Insulation |  | 30 | [25 empty] | 20
24068 | QTS NAL1 DC2 | 2025-06-09 | Marvin Blanco | Working in the screenwall installing single skin panels and hats channels cleaning our areas of work and doing the best for not being in problems | Subcontractor | Joe Hoyle | false |  | true |  |  | 8 | 12 | false |  | Scaffolding and boomlift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 16 | 96
24088 | Mercedes Benz West Chester | 2025-06-09 | Jhonatan bernal |  | Subcontractor | Luke Giles | true | Delay for bad levels you have to cut the panels | false |  | Delay due to rain | 3 | 7 | true |  | Booom lift | false |  |  |  |  | ACM | 3 | 7
24082 | GTN Cable | 2025-06-08 | Kevin Morris |  | Subcontractor | Josh McPherson, Nick Akins | false |  | false |  |  | 2 | 6 | false |  | T46 boom & 45 knuckle boom | false |  |  |  |  | Flashing IMP | [8 empty] | 3 | 5 | [22 empty] | 30 | 1
24005 | GCDC Building 2/VA1.2 | 2025-06-07 | Obed Bermudez | We had a rainy day but continued working on the east elevation installing flat metal,flashing,hat channel and panels. | JWMCD Crew | Joe Hoyle | true |  |  |  | Rainy day but still managed to install some acm panels and lots of flat metal. | 12 | 8 | [8 empty] | ACM Flashing | 8 | 48 | [30 empty] | 40 | 16
24005 | GCDC Building 2/VA1.2 | 2025-06-07 | Obed Bermudez | We continue working on the security room, installing bulletproof glass frames, leveling windows that are not properly installed, and cleaning them. | JWMCD Crew | Joe Hoyle | [5 empty] | 4 | 11
24045 | TMMMS Childcare | 2025-06-07 | Zachary Hood | Installing Z Girts and continuing acm install | Subcontractor | Chris Buttrey | false |  | true |  |  | 6 | 9 | false |  | (3) 45' boomlifts | false |  |  |  |  | ACM | 24 | 35
24048 | QTS NAL2 DC1 | 2025-06-07 | Antonio Sanchez | Metal coping | Subcontractor | Joe Hoyle | true | Thunderstorm | true |  | Raining | 5 | 10 | true |  | Boomlift forklift | false |  |  |  |  | Coping Other | [40 empty] | 150 | 30 | Install zmetal on wing wall south elevation | 20
24082 | GTN Cable | 2025-06-07 | Starlin |  | Subcontractor | Josh McPherson, Nick Akins | false |  | false |  |  | 2 | 10 | false |  | T46 & 45 knuckle boom | false |  |  |  |  | Flashing IMP | [8 empty] | 6 | 8 | [22 empty] | 70 | 2
23064 | Yondr Allegro 2S | 2025-06-06 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Move material to the work area 1 hour |  |  |  | 7 |  |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 40 | 24 |  |  | 400 | 8 |  |  | 160 | 16
24005 | GCDC Building 2/VA1.2 | 2025-06-06 | Obed Bermudez | Crew 1 continues reinstalling and modifying panels on the west elevation. Crew 1 installed and modified 3 panels. Crew 2 continues working on the screen wall installing tubes and clips. Crew 3 continues working on the east elevation,installing channels, flashing, and panels. | JWMCD Crew | Joe Hoyle | true | HITT stopped our work for half a day due to stripping pavement. |  |  |  | 12 | 11 |  |  | Booms lifts and forklift | [5 empty] | ACM Flashing Hat Channel Tubing | [28 empty] | 140
24045 | TMMMS Childcare | 2025-06-06 | Zachary Hood | Installing Zee and insulations | Subcontractor | Chris Buttrey | true | Lighting in area went home at 2pm | true |  | inclement weather | 7 | 7 | false |  | (3) 45' boomlifts | false |  |  |  |  | ACM | 25 | 35
24048 | QTS NAL2 DC1 | 2025-06-06 | Antonio Sanchez | Louver coping | Subcontractor | Joe Hoyle | true | Stand down due lightning | true |  | Thunderstorm rain | 5 | 10 | false |  | Boomlift forklift | false |  |  |  |  | Coping Louvre | [25 empty] | 20 | [14 empty] | 150 | 30
24082 | GTN Cable | 2025-06-06 | Kevin Morris |  | Subcontractor | Josh McPherson, Nick Akins | true |  | false |  | Rain / lightning | 2 | 6 | false |  | T46 boom & 45 knuckle boom | false |  |  |  |  | Flashing IMP | [8 empty] | 2 | 5 | [22 empty] | 40 | 1
23029 | BNA Concourse D | 2025-06-05 | Antonio | We continued installing roof panels wrapping click wise towards landside. | JWMCD Crew | Marc Ribar | true | We couldn’t work as much counter clockwise due to other contractors |  |  |  | 12 | 10 | false |  | 4 man lifts and a lull | false |  |  |  |  | ACM | 62 | 120
23064 | Yondr Allegro 2S | 2025-06-05 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 7 |  |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 60 | 30 |  |  | 400 | 10 |  |  | 200 | 20
24005 | GCDC Building 2/VA1.2 | 2025-06-05 | Obed Bermudez | Crew 1 continues reinstalling and modifying cap panels on the west elevation. Crew 1 installed and modified 10 panels. Crew 2 continues working on the east elevation,installing channels, flashing, and panels. | JWMCD Crew | Joe Hoyle | true | Gc made us move equipment and material outside of the east due to pavement prepping and cleaning. |  |  |  | 12 | 11 |  |  | Boom lifts and forklift | [5 empty] | ACM Flashing Hat Channel | 22 | 44 | [30 empty] | 20 | 11 | 200 | 22
24005 | GCDC Building 2/VA1.2 | 2025-06-05 | Obed Bermudez | We continue working on the security room installing bulletproof glass frame. | JWMCD Crew | Joe Hoyle | [5 empty] | 4 | 11
24018 | QTS-NAL1-DC1 | 2025-06-05 | Marvin Blanco | Working in the freedom wall we the red panels the guys are almost done maybe together they will be done with the last panels in the top it's taking a little longer because we have issues when we started | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 12 | false |  | Boomlift and scissors lift | false |  |  |  |  | ACM | 14 | 60
24028 | CHI Memorial Hospital | 2025-06-05 | JC Panels | Cleat 213, 2” screws … we had to modify 3 ACM panels . In uploading the pictures | Subcontractor | Josh McPherson | false |  | true |  |  | 5 | 50 | false |  | Boom and fork lift | false |  |  |  |  | ACM Insulation Subgirt Zee
24045 | TMMMS Childcare | 2025-06-05 | Zachary Hood | installing Zgirts and insulation | Subcontractor | Chris Buttrey | false |  | true |  |  | 7 | 9 | false |  | (3) 45' boomlifts | false |  |  |  |  | ACM | 38 | 40
24048 | QTS NAL2 DC1 | 2025-06-05 | Antonio Sanchez | Coping louver | Subcontractor | Joe Hoyle | true | Thunderstorm | true |  | Raining and thunderstorm | 5 | 8 | false |  | Boomlift forklift | false |  |  |  |  | Coping Louvre | [25 empty] | 16 | [14 empty] | 120 | 24
24068 | QTS NAL1 DC2 | 2025-06-05 | Marvin Blanco | Working in the roof we the hats channels for the metal panels in the screenwall also checking details for the silicone because in the drawings it's saying it's by others on the bottom of the IMP panels | Subcontractor | Joe Hoyle | false |  | true |  |  | 6 | 12 | false |  | Boomlift and scaffolding | false |  |  |  |  | Hat Channel | [34 empty] | 1800 | 72
24082 | GTN Cable | 2025-06-05 | Kevin Morris |  | Subcontractor | Josh McPherson, Nick Akins | false |  | false |  |  | 2 | 10 | false |  | T46 boom & 45 knuckle boom | false |  |  |  |  | Flashing IMP | [8 empty] | 3 | 7 | [22 empty] | 90 | 3
23029 | BNA Concourse D | 2025-06-04 | Antonio | Had a crew installing soffit panels above the low roof off of a scaffold, had two crews installing roof panels clockwise on the record note | JWMCD Crew | Marc Ribar | true | People working below us so we needed to stop. ( HP directed ) Concrete being poured so I can’t install counter clockwise on the record note. And our boom can’t reach the last part of the soffit panels |  |  |  | 12 | 10 | false |  | 4 man lifts and a lull | false |  |  |  |  | ACM Coping | 47 | 100 | [38 empty] | 70 | 20
23064 | Yondr Allegro 2S | 2025-06-04 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Move material to the work area 1 hour |  |  |  | 7 |  |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 60 | 30 | [6 empty] | 200 | 20 | 150 | 10
24005 | GCDC Building 2/VA1.2 | 2025-06-04 | Obed Bermudez | We continue working on the security room installing bulletproof glass frame. | JWMCD Crew | Joe Hoyle | [5 empty] | 4 | 11
24005 | GCDC Building 2/VA1.2 | 2025-06-04 | Obed Bermudez | Crew 1 and 2 continue reinstalling cap panels on the west elevation.Crew 1 installed 9 panels, while Crew 2 installed another 9 and 1 panel modified. Crew 3 continues working on east elevation installing channel, flashing and panels and cleaning up empty boxes on the roof. | JWMCD Crew | Joe Hoyle | [5 empty] | 13 | 11 |  |  | Boom lifts and forklift | [5 empty] | ACM Flashing Hat Channel | 42 | 77 | [30 empty] | 30 | 11 | 150 | 11
24028 | CHI Memorial Hospital | 2025-06-04 | JC Panels | Cleat 213. Screws 2” … we are working the much that we are able to in the south side of the building.. I dont know if we can swap out boom for a 120-125 ft for also de north side so we can reach the eyebrow of ACM | Subcontractor | Josh McPherson | false |  | true |  |  | 5 | 50 | true |  | Boom and fork lift | false |  |  |  |  | ACM Insulation Subgirt Zee | 6
24028 | CHI Memorial Hospital | 2025-06-04 | JC Panels | We are getting short of 2” screws also there is a flashing that is not on the list..the number 213 im adding picture of the list | Subcontractor | Josh McPherson | false |  | true |  |  | 5 | 50 | true |  | Boom scissor lift | false |  |  |  |  | ACM Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 26
24045 | TMMMS Childcare | 2025-06-04 | Zachary Hood | Installing Z girts and insulations | Subcontractor | Chris Buttrey | false |  | true |  |  | 7 | 10 | false |  | (3) 45' boomlifts | false |  |  |  |  | ACM | 30 | 40
24048 | QTS NAL2 DC1 | 2025-06-04 | Antonio Sanchez | Corrugated rib panel louver | Subcontractor | Joe Hoyle | false |  | true |  |  | 6 | 10 | false |  | Boomlift, forklift | false |  |  |  |  | Corrugated / Screen wall Louvre | [22 empty] | 20 | 30 |  | 30
24082 | GTN Cable | 2025-06-04 | Starlin |  | Subcontractor | Josh McPherson, Nick Akins | false |  | false |  |  | 2 | 10 | false |  | boom | false |  |  |  |  | IMP | [8 empty] | 6 | 10
23064 | Yondr Allegro 2S | 2025-06-03 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Move material to work area 1 hour |  |  |  | 7 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Flashing Insulation | [22 empty] | 60 | 30 |  |  | 900 | 20 |  |  |  |  | 120 | 10
24001 | McEwen Northside | 2025-06-03 | Marvin Blanco | Working in the soffit with bellara panels talking with Rick today he's asking us to finish this Friday and I think we will be done everything in the and of this week except for the punch list because we will need to replace some panels | Subcontractor | Josh McPherson | false |  | true |  |  | 3 | 11 | false |  | Boomlift and scissors lift | false |  |  |  |  | Other | [42 empty] | Bellara panels | 33
24005 | GCDC Building 2/VA1.2 | 2025-06-03 | Obed Bermudez | We continue working in the security room, installing glass on doors and taking out windows and reinstalling them leveled. | JWMCD Crew | Joe Hoyle | [5 empty] | 4 | 11 | [8 empty] | Other | [43 empty] | 44
24018 | QTS-NAL1-DC1 | 2025-06-03 | Marvin Blanco | Working in the red panels the guys couldn't make much progress because they were waiting for the vertical lights gets install in the wall | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 12 | true | Clips for the ACM panels | Boomlift and scissors lift | false |  |  |  |  | ACM | 11 | 60
24048 | QTS NAL2 DC1 | 2025-06-03 | Antonio Sanchez | Corrugated rib panel louver material | Subcontractor | Joe Hoyle | false |  | true |  |  | 6 | 10 | false |  | Boomlift forklift | false |  |  |  |  | Corrugated / Screen wall Louvre | [22 empty] | 20 | 40 |  | 20
24068 | QTS NAL1 DC2 | 2025-06-03 | Marvin Blanco | Installing hats channels in the screenwall for the metal panels and also the guys went to grab some barricade for the boomlift installing the grand because the WT is asking to use barricade in all the equipment just like OSGOOD | Subcontractor | Joe Hoyle | false |  | true |  |  | 7 | 12 | false |  | Boomlift and forklift | false |  |  |  |  | Hat Channel | [34 empty] | 1460 | 84
24082 | GTN Cable | 2025-06-03 | Kevin Morris |  | Subcontractor | Josh McPherson, Nick Akins | false |  | false |  |  | 2 | 10 | false |  | T46 boom | false |  |  |  |  | IMP | [8 empty] | 9 | 10
24905 | BSU Innovation Center | 2025-06-03 | Obed Bermudez | Crew 1 and 2 continue reinstalling cap panels on the west elevation. Crew 1 installed 15 panels, while Crew 2 installed another 15. Crew 3 continues working on the east elevation, installing channels, flashing, and panels, and cleaning up empty boxes on the roof. | JWMCD Crew | #NO MATCH | [5 empty] | 12 | 11 |  |  | Boom lifts and forklift. | [5 empty] | ACM Flashing Hat Channel | 20 | 28 | [30 empty] | 20 | 6 | 190 | 11
23029 | BNA Concourse D | 2025-06-02 | Antonio | Workers reinstalled 68 soffit acm panels due to joint being off 1” also had a crew working on punchlist | JWMCD Crew | Marc Ribar | false |  |  |  |  | 12 | 10 | false |  | 4 man lifts and lull | false |  |  |  |  | ACM Other | 68 | 100 | [41 empty] | 20
23064 | Yondr Allegro 2S | 2025-06-02 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Move material to the work area 2 hours |  |  |  | 7 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Subgirt Zee | [22 empty] | 60 | 30 | [6 empty] | 400 | 30
24001 | McEwen Northside | 2025-06-02 | Marvin Blanco | Taking off flat sheets of ACM panels in the bridge and also installing the bellara panels in the second level in the bridge today 6/3/25 we are going to start installing in the first level with the bellara panels | Subcontractor | Josh McPherson | false |  | true |  |  | 3 | 11 | false |  | Boomlift and scissors lift | false |  |  |  |  | Other | [42 empty] | Bellara panels | 33
24005 | GCDC Building 2/VA1.2 | 2025-06-02 | Obed Bermudez | Crew 1 and 2 continue reinstalling cap panels on the west elevation. Crew 1 installed 15 panels, while Crew 2 installed another 15. Crew 3 continues channel and panel installation. Today we started doing layout and moving material on the security room. | JWMCD Crew | Joe Hoyle | [5 empty] | 13 | 11 |  |  | Boom lifts and forklift | [5 empty] | ACM Hat Channel | 6 | 22 | [32 empty] | 160 | 22
24018 | QTS-NAL1-DC1 | 2025-06-02 | Marvin Blanco | Working in the freedom wall last week we have to demo the new panels because WT ask us to match our joints with the floor lines so we have to take down 18 the new panels install just because the line in the floor and also we have to demo de gyp because WT is taking a little longer to do something for example taking off the gyp from the wall and also for fix there lights | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 12 | false |  | Boomlift scissors lift | false |  |  |  |  | ACM | 10 | 60
24028 | CHI Memorial Hospital | 2025-06-02 | JC Panels | Wood panels | Subcontractor | Josh McPherson | false |  | true |  |  | 5 | 50 | true |  | Boom and fork lift | false |  |  |  |  | ACM Insulation Subgirt Zee | 15
24045 | TMMMS Childcare | 2025-06-02 | Zachary Hood | Installing Z girt / insulations on block wall | Subcontractor | Chris Buttrey | true | Boom lift went down | true |  | sunny | 6 | 10 | true |  | (2) 45' boomlifts | false |  |  |  |  | ACM | 25 | 40
24048 | QTS NAL2 DC1 | 2025-06-02 | l Antonio Sanchez | Corrugated rib panel louver material | Subcontractor | Joe Hoyle | false |  | true |  |  | 6 | 10 | false |  | Boomlift, forklift | false |  |  |  |  | Corrugated / Screen wall Louvre | [22 empty] | 15 | 30 |  | 30
24068 | QTS NAL1 DC2 | 2025-06-02 | Marvin Blanco | Working in the hats channels in the screenwall for the metal panels and waiting for a longer screws for the penthouse and start working for the metal panels around because last week we have a little issue we the steel in the penthouse it's pushing our IMP panels out | Subcontractor | Joe Hoyle | false |  | true |  |  | 7 | 12 | false |  | Boomlift forklift | false |  |  |  |  | Hat Channel | [34 empty] | 1800 | 84
24082 | GTN Cable | 2025-06-02 | Starlin |  | Subcontractor | Josh McPherson, Nick Akins | false |  | false |  |  | 2 | 10 | false |  | T46 boom | false |  |  |  |  | IMP | [8 empty] | 6 | 10
23029 | BNA Concourse D | 2025-06-01 | Antonio | Two crews worked on the record note soffit, they installed 19 acm panels the third crew installed the panels on the terrace canopy they installed 10 panels and colored the rivets | JWMCD Crew | Marc Ribar | false |  |  |  |  | 12 | 8 | false |  | 4 man lifts 2 scissor lifts | false |  |  |  |  | ACM | 29 | 96
23029 | BNA Concourse D | 2025-05-31 | Antonio | Two crews worked on the record note soffit, they installed 70 acm panels the third crew installed the panels on the terrace canopy they installed 3 panels and 300’ of flashing | JWMCD Crew | Marc Ribar | true | Canopy was not finished |  |  |  | 12 | 10 | false |  |  | false |  |  |  |  | ACM Flashing | 73 | 80 | [30 empty] | 300 | 40
23064 | Yondr Allegro 2S | 2025-05-31 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Move the material to the work area 1 hour |  |  |  | 7 | 7 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Flashing Insulation Subgirt Zee | [22 empty] | 40 | 21 |  |  | 300 | 7 |  |  | 120 | 10 | 80 | 4
24005 | GCDC Building 2/VA1.2 | 2025-05-31 | Obed Bermudez | We continue reinstalling cap panels on the west elevation. We installed 10. | JWMCD Crew | Joe Hoyle | [5 empty] | 5 | 8 |  |  | Boom lifts and forklift.
24048 | QTS NAL2 DC1 | 2025-05-31 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 6 | 10 | false |  | Boomlift forklift | false |  |  |  |  | Corrugated / Screen wall Louvre | [22 empty] | 16 | 40 |  | 20
24048 | QTS NAL2 DC1 | 2025-05-31 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 6 | 10 | false |  | Boomlift forklift | false |  |  |  |  | Corrugated / Screen wall Louvre | [22 empty] | 20 | 30 |  | 30
24005 | GCDC Building 2/VA1.2 | 2025-05-30 | Obed Bermudez | We continue reinstalling cap panels on the west elevation. We installed 15 panels. | JWMCD Crew | Joe Hoyle | [5 empty] | 5 | 11 | true | East acm panels. | Boom lifts and forklift. | [5 empty] | ACM | 15 | 55
24045 | TMMMS Childcare | 2025-05-30 | Zachary Hood | Working on layout checking panels /Zgirt install/ | Subcontractor | Chris Buttrey | true | Dimensional bust on every elevation we setup on .panel 204-1D12 has to be routed | true |  | light rain | 6 | 10 | false |  | (2) 45' boomlifts | false |  |  |  |  | ACM | 16 | 30
24048 | QTS NAL2 DC1 | 2025-05-30 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | true | Raining all day | false |  | Raining | 6 | 4 | false |  | Boomlift forklift | false |  |  |  |  | Corrugated / Screen wall Louvre | [22 empty] | 6 | 12 |  | 8
24082 | GTN Cable | 2025-05-30 | Kevin Morris |  | Subcontractor | Josh McPherson, Nick Akins | false |  | false |  |  | 2 | 10 | true |  | Ht46 | false |  |  |  |  | IMP | [8 empty] | 6 | 10
23064 | Yondr Allegro 2S | 2025-05-29 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Move material for the work area |  |  |  | 7 |  |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 60 | 35 | [6 empty] | 200 | 20 | 100 | 5
24005 | GCDC Building 2/VA1.2 | 2025-05-29 | Obed Bermudez | Crew 1 and 2 began reinstalling cap panels on the west elevation. Crew 1 installed 8 panels, while Crew 2 installed another 7. | JWMCD Crew | Joe Hoyle | [5 empty] | 5 | 11 |  |  | Boom lifts and forklift. | [5 empty] | ACM | 15 | 55
24018 | QTS-NAL1-DC1 | 2025-05-29 | Marvin Blanco | Reinstalling the red panels in the freedom wall cleaning our areas of work with out issues | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 12 | false |  | Boomlift forklift | false |  |  |  |  | ACM | 12 | 60
24045 | TMMMS Childcare | 2025-05-29 | Zachary Hood | Installing Z Girts and continuing acm install | Subcontractor | Chris Buttrey | true | Z girts are too close to the storefront jamb not allowing are panel to terminate correctly | true |  | sunny | 7 | 70 | true | no | (2) 45' boomlifts | false |  |  |  |  | ACM | 27 | 40
24048 | QTS NAL2 DC1 | 2025-05-29 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 6 | 10 | true |  |  | false |  |  |  |  | Corrugated / Screen wall Louvre | [23 empty] | 30 |  | 30
24048 | QTS NAL2 DC1 | 2025-05-29 | Kevin Morris |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 2 | 10 | false |  | Boom 60' | false |  |  |  |  | Flashing IMP | [8 empty] | 7 | 7 | [22 empty] | 60 | 3
24068 | QTS NAL1 DC2 | 2025-05-29 | Marvin Blanco | Finishing installing the IMP panels and starting installing the Hats channels in the penthouse for the metal panels | Subcontractor | Joe Hoyle | false |  | true |  |  | 7 | 12 | false |  | Scaffolding and latter | false |  |  |  |  | Hat Channel IMP | [8 empty] | 10 | 48 | [24 empty] | 20 | 36
23029 | BNA Concourse D | 2025-05-28 | Antonio | Guys continued on record note one crew installed 36 panels another crew installed 16 and 100’ of flashing the third crew installed 28 roof panels | JWMCD Crew | Marc Ribar | false |  |  |  |  | 12 | 10 | false |  | 4 man lifts and a lull | false |  |  |  |  | ACM Flashing | 80 | 100 | [30 empty] | 100 | 20
24018 | QTS-NAL1-DC1 | 2025-05-28 | Marvin Blanco | Working in taking panels down in the freedom wall and cleaning our area of work moving material and moving the old panels to the dumpster. | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 12 | false |  | Scissors lift boomlift forklift | false |  |  |  |  | Other | [42 empty] | Taking panels down | 60
24028 | CHI Memorial Hospital | 2025-05-28 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 4 | 40 | true |  | Boom scissor lift | false |  |  |  |  | ACM Other | 7 | 30 | [40 empty] | 8 Morin | 30
24048 | QTS NAL2 DC1 | 2025-05-28 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 6 | 10 | false |  | Boomlift forklift | false |  |  |  |  | Corrugated / Screen wall Louvre | [22 empty] | 17 | 30 |  | 30
24068 | QTS NAL1 DC2 | 2025-05-28 | Marvin Blanco | Working in the penthouse installing the IMP panels and also working in the screenwall installing Zs for the metal panels | Subcontractor | Joe Hoyle | false |  | true |  |  | 7 | 12 | false |  | Scaffolding and boomlift and latter | false |  |  |  |  | IMP | [8 empty] | 14 | 48
24082 | GTN Cable | 2025-05-28 | Kevin Morris |  | Subcontractor | Josh McPherson, Nick Akins | true | Had to pick up new base flashing at shop, and wait for insulation to be installed back | false |  |  | 2 | 9 | false |  | Boom 60' | false |  |  |  |  | Flashing | [32 empty] | 100 | 9
23029 | BNA Concourse D | 2025-05-27 | Zarur Nazario Padron Jr | Installing ACM panels on Record Terrace and installing Vent Flashing | JWMCD Crew | Marc Ribar | false |  |  |  |  | 7 | 70 | false |  | 3- 65’ boomlifts | false |  |  |  |  | ACM Flashing | 9 | 40 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 36 | 30
23029 | BNA Concourse D | 2025-05-27 | Zarur Nazario Padron Jr | Installing vent flashing on Record ceiling | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  | 1- 65’ boomlift | false |  |  |  |  | Flashing | [20 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 108 | 30
23064 | Yondr Allegro 2S | 2025-05-27 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 7 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 60 | 30 | [6 empty] | 180 | 20 | 100 | 10
24005 | GCDC Building 2/VA1.2 | 2025-05-27 | Obed Bermudez | We worked on the screen wall, taking measurements and cleaning it up. | JWMCD Crew | Joe Hoyle | true |  |  |  | Rainy conditions | 5 | 11 |  |  | Boom lifts and forklift
24028 | CHI Memorial Hospital | 2025-05-27 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 4 | 24 | false |  | Boom and scissor lift | false |  |  |  |  | ACM | 6
24045 | TMMMS Childcare | 2025-05-27 | Zachary Hood | Field conditions | Subcontractor | Chris Buttrey | true | Weather | true |  | Rainy | 1 | 0 | false |  |  | false |  |  |  |  | ACM | 0 | 0
24048 | QTS NAL2 DC1 | 2025-05-27 | Antonio Sanchez | Corrugated rib panel | Subcontractor | Joe Hoyle | false |  | true |  |  | 4 | 10 | false |  | Boomlift forklift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 30 | 40
24048 | QTS NAL2 DC1 | 2025-05-25 | Antonio Sanchez | Corrugated rib panel, trim | Subcontractor | Joe Hoyle | false |  | true |  |  | 4 | 10 | false |  | Boomlift forklift | false |  |  |  |  | Corrugated / Screen wall Trim | [22 empty] | 10 | 40 | [12 empty] | 60
23029 | BNA Concourse D | 2025-05-24 | Zarur Nazario Padron Jr | Installing vent flashing on Record circle | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  | 1- 65’ boomlift | false |  |  |  |  | Flashing | [20 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 108 | 30
23029 | BNA Concourse D | 2025-05-24 | Zarur Nazario Padron Jr | Installing and fabricating IMP panels on Airside of Record | JWMCD Crew | Marc Ribar | false |  |  |  |  | 2 | 20 | false |  | 1- 65’ boomlifts | false |  |  |  |  | Flashing IMP | [8 empty] | 18 | 17 | [10 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 28 | 3
24048 | QTS NAL2 DC1 | 2025-05-24 | Antonio Sanchez | Corrugated rib panel | Subcontractor | Joe Hoyle | false |  | true |  |  | 4 | 10 | false |  | Boomlift forklift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 25 | 40
23029 | BNA Concourse D | 2025-05-23 | Zarur Nazario Padron Jr | Installing IMP panels on corner of Airside Record | JWMCD Crew | Marc Ribar | false |  |  |  |  | 2 | 20 | false |  | 1- 65’ boomlift | false |  |  |  |  | Flashing IMP | [8 empty] | 15 | 18 | [10 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 15 | 2
23064 | Yondr Allegro 2S | 2025-05-23 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 7 | 7 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 30 | 21 | [6 empty] | 180 | 14 | 120 | 7
24005 | GCDC Building 2/VA1.2 | 2025-05-23 | Obed Bermudez | Crew 1 continues installing ACM panels, flat metal, and J on East elevation. Crew 2 and crew 3 continue installing screen wall panels, clips, and tubes. Crew 4: moving material and cleaning up. Total clips installed: 300. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 11 |  |  | Boom lifts and forklift. | [5 empty] | ACM Hat Channel Plate Tubing | 20 | 33 | 100 | 44 | [24 empty] | 700 | 44 |  |  |  |  | 60 | 11
24028 | CHI Memorial Hospital | 2025-05-23 | JCcPanels | Flashing, trim , corners , correct panel | Subcontractor | Josh McPherson | true | We need the flashing corners trim for the Morin panels , rivets | true |  |  | 4 | 36 | true |  | Boom and fork lift | false |  |  |  |  | ACM Flashing Insulation Subgirt Zee | 6
24048 | QTS NAL2 DC1 | 2025-05-23 | Antonio Sanchez | Corrugated rib panel | Subcontractor | Joe Hoyle | false |  | true |  |  | 4 | 10 | false |  | Boomlift forklift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 10 | 40
23029 | BNA Concourse D | 2025-05-22 | Antonio | 1 crew continued on with the ACM panels on the terrace, 2 crews carried on with soffit ACM panels they installed 28 panels, 1 crew installed and changed out IMP panels on connector | JWMCD Crew | Marc Ribar | true | Crews on soffit record note could not install panels constantly getting broken down due to concrete guys working underneath us, IMP panels near record node corner could not be installed due to guys being pulled down due to concrete |  |  | Sunny | 13 | 143 | false |  | 4- boomlifts and 2- scissor lifts | false |  |  |  |  | ACM IMP | 60 | 121 | [6 empty] | 9 | 22 | [10 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
23064 | Yondr Allegro 2S | 2025-05-22 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Move material to the work area 3 hours |  |  |  | 7 |  |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Insulation | [22 empty] | 30 | 20 |  |  | 2500 | 40
24005 | GCDC Building 2/VA1.2 | 2025-05-22 | Obed Bermudez | Today we finished removing cap panels. Crew 1 and 2 continue removing ACM cap panels on the west elevation. Crew 1 removed 10 cap panels, and Crew 2 removed 10. Crew 3 continued installing screen wall panels,clips,tubes,moving material, and cleaning up. Total clips installed: 156. | JWMCD Crew | Joe Hoyle | true | HITT stopped our crews for a few hours on the east due to milling the pavement. |  |  |  | 12 | 11 |  |  | Boom lifts and forklift. | [5 empty] | ACM Plate Tubing | 14 | 44 | 46 | 22 | [24 empty] | 364 | 22
24028 | CHI Memorial Hospital | 2025-05-22 | JC Panels | Flashings rivets | Subcontractor | Josh McPherson | false |  | true |  |  | 4 | 40 | true |  | Boom lift fork lift | false |  |  |  |  | ACM Insulation Subgirt Zee | 6
24045 | TMMMS Childcare | 2025-05-22 | Zachary Hood | Installing Z girts /insulation and panel | Subcontractor | Chris Buttrey | false |  | true |  |  | 7 | 10 | false |  |  | false |  |  |  |  | ACM | 40 | 40
24045 | TMMMS Childcare | 2025-05-22 | Zach hood | All Z grit are installed / all of the incorrect z grits are cut down and reinstalled. | Subcontractor | Chris Buttrey | true | Panels are fabricated too big 3-201 4-201 5-201 | true |  | Sunny | 9 | 10 | false |  | 2 - 40’boom | false |  |  |  |  | ACM | 20 | 40
24048 | QTS NAL2 DC1 | 2025-05-22 | Antonio Sanchez | Acm panels entry of building freedom wall get corrugated rib panel to penhause | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 10 | true | Acm panels on storage yard | Boomlift forklift | false |  |  |  |  | Louvre | [25 empty] | 50
24068 | QTS NAL1 DC2 | 2025-05-22 | Marvin Blanco | Installing IMP panels in the penthouse and also Zs metal in the screenwall and putting silicone in the joints of the IMP panels for the weather today we received the corrugated panels and we have a lot of damaged panels in the truck because the company where those panels are created don't care about the material they don't put protection anywhere so I hope McDougall get enough material to finish the job or extra panels because there is a lot of damaged panels | Subcontractor | Joe Hoyle | false |  | true |  |  | 9 | 12 | true | Corrugated panels and they are a lot of panels damaged | Scaffolding and latter | false |  |  |  |  | Hat Channel IMP | [8 empty] | 10 | 54 | [24 empty] | 180 | 54
24068 | QTS NAL1 DC2 | 2025-05-22 | Marvin Blanco | Working in the penthouse and in the screenwall with the scaffolding and latter with IMP panels and Zs for the corrugated panels everything is working well smoothly and cleaning our areas of work today was raining day so we couldn't make a better number in the panels and Zs also working in the silicone | Subcontractor | Joe Hoyle | false |  | true |  |  | 9 | 12 | false |  | Scaffolding and latter | false |  |  |  |  | Hat Channel IMP | [8 empty] | 9 | 54 | [24 empty] | 180 | 54
23029 | BNA Concourse D | 2025-05-21 | Antonio | We brought the soffit panels onsite and loaded them onto the terrace. We then installed 32 ACM panels | JWMCD Crew | Marc Ribar | true | Couldn’t install last IMP panels due to concrete guys working underneath |  |  | Clear and sunny | 8 | 12 | false |  | 4 man lifts and a lull | false |  |  |  |  | ACM | 32
23064 | Yondr Allegro 2S | 2025-05-21 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 7 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 33 | 30 | [6 empty] | 240 | 20 | 210 | 10
24028 | CHI Memorial Hospital | 2025-05-21 | JC Panels | Flashings, rivets, vertical panel. Cladding paralel panels . We frame all the wall for Morin panels. | Subcontractor | Josh McPherson | true |  | true |  |  | 4 | 40 | false |  | Boom lift fork lift | false |  |  |  |  | ACM | 6 | 30
24048 | QTS NAL2 DC1 | 2025-05-21 | Antonio Sanchez | Louver | Subcontractor | Joe Hoyle | true | Thunderstorm and rain | true |  | Rain | 5 | 10 | false |  | Boomlift forklift | false |  |  |  |  | Louvre | [25 empty] | 50
23029 | BNA Concourse D | 2025-05-20 | Zarur Nazario Padron Jr | Installing ACM panels on Airside of Concessions. Allowed to start work at 8 AM. Got delayed 2 hours because of rain and lightning. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 7 | 70 | false |  | 2- 65’ boomlifts | false |  |  |  |  | ACM | 20 | 70 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
23029 | BNA Concourse D | 2025-05-20 | Antonio | Continued with the soffit panels that surround the terrace also installed panels around the ladders on concessions | JWMCD Crew | Marc Ribar | true | Could not install the last of imp due to hp working in area |  |  | Sunny with random showers | 7 | 10 | true | 3 crates of ACM panels and a box of clips | 4 man lifts @ 85’ | false |  |  |  |  | ACM | 23 | 70
23029 | BNA Concourse D | 2025-05-20 | Zarur Nazario Padron Jr | Installing ACM panels on ceiling of Record | JWMCD Crew | Marc Ribar | false |  |  |  |  | 11 | 108 | false |  | 2- 65’ boomlifts | false |  |  |  |  | ACM | 51 | 108 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
23064 | Yondr Allegro 2S | 2025-05-20 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Move material to the work area 40 minutes |  |  |  | 7 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 45 | 30 | [6 empty] | 250 | 20 | 180 | 10
24005 | GCDC Building 2/VA1.2 | 2025-05-20 | Obed Bermudez | Crew 1 and 2 continue removing ACM cap panels on the west elevation. Crew 1 removed 10 cap panels, and Crew 2 removed 10. Crew 3 continued installing screen wall panels,clips,tubes,moving material and cleaning up. Total clips installed: 120. | JWMCD Crew | Joe Hoyle | true | We brought another crew to start working on the east elevation, but Ian from HITT said we can’t work there due to the waterproofing not being done yet. |  |  |  | 12 | 11 |  |  | Boom lifts and forklift | [5 empty] | Plate Tubing |  |  | 40 | 22 | [24 empty] | 298 | 22
24028 | CHI Memorial Hospital | 2025-05-20 | JC Panels | We need some J’s flashings corner flashing rivets. The panel that is short | Subcontractor | Josh McPherson | false |  | true |  |  | 4 | 36 | true |  | 1 boom lift 1 fork lift | false |  |  |  |  | ACM Subgirt Zee | 2
24045 | TMMMS Childcare | 2025-05-20 | Zach Hood |  | Subcontractor | Chris Buttrey | true | “Z” girt existing are too close to storefront | false |  |  | 8 | 10 | false |  | Forklift | false |  |  |  |  | ACM | 28 | 180
24048 | QTS NAL2 DC1 | 2025-05-20 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | true | Rain on the afternoon | false |  | Raining | 5 | 8 | true |  | Boomlift forklift | false |  |  |  |  | Louvre | [25 empty] | 40
24068 | QTS NAL1 DC2 | 2025-05-20 | Marvin Blanco | Working in the penthouse with the scaffolding and latter with IMP panels everything is working well smoothly and cleaning our areas of work today was raining day so we couldn't make a better number in the panels | Subcontractor | Joe Hoyle | false |  | true |  |  | 4 | 12 | false |  | Scaffolding | false |  |  |  |  | IMP | [8 empty] | 9 | 48
23064 | Yondr Allegro 2S | 2025-05-19 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Moving materials to the work area 1 hour |  |  |  | 7 |  | true | Si girt Zee | Boom lift | [5 empty] | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 42 | 30 | [6 empty] | 300 | 20 | 160 | 10
24005 | GCDC Building 2/VA1.2 | 2025-05-19 | Obed Bermudez | Crew 1 and 2 continue removing ACM cap panels on the west elevation. Crew 1 removed 10 cap panels, and Crew 2 removed 10. Crew 3 continued installing screen wall panels,clips,tubes,moving material and cleaning up. Total clips installed: 96. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 11 |  |  | Boom lifts and forklift | [5 empty] | Plate Tubing |  |  | 32 | 11 | [24 empty] | 224 | 22
24028 | CHI Memorial Hospital | 2025-05-19 | JC Panels | We are needing the details for the bottom area for the Morin panels so we can start framing. We have finish all the ACM that we can install on the west area. | Subcontractor | Josh McPherson | true | We start our day 9am because of the rain. We need the details from the bottom area to start the Morin. We will continue with the eyebrow of the south elevations. We do have ACM panels to start that elevation and don’t stop working | true |  | Rain early morning | 4 | 32 | true |  | 1 boom lift 1 fork lift | false |  |  |  |  | ACM Insulation Subgirt Zee | 7
24048 | QTS NAL2 DC1 | 2025-05-19 | Antonio Sanchez | Louver material | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 10 | true |  | Boomlift forklift | false |  |  |  |  | Louvre | [24 empty] | 4 | 50
24068 | QTS NAL1 DC2 | 2025-05-19 | Marvin Blanco | Working in the penthouse with the scaffolding and latter with IMP panels everything is working well smoothly and cleaning our areas of work | Subcontractor | Joe Hoyle | false |  | true |  |  | 4 | 12 | false |  | Scaffolding | false |  |  |  |  | IMP | [8 empty] | 9 | 48
24048 | QTS NAL2 DC1 | 2025-05-18 | Antonio Sanchez | Louver | Subcontractor | Joe Hoyle | false |  | true |  |  | 6 | 10 | false |  | Boomlift forklift | false |  |  |  |  | Louvre | [25 empty] | 60
23029 | BNA Concourse D | 2025-05-17 | Zarur Nazario Padron Jr | Installing ceiling ACM panels on Record circle | JWMCD Crew | Marc Ribar | false |  |  |  |  | 11 | 110 | false |  | 2- 65’ boomlifts | false |  |  |  |  | ACM | 58 | 110 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
24005 | GCDC Building 2/VA1.2 | 2025-05-17 | Obed Bermudez | Crew 1 and 2 continue removing ACM cap panels on the west elevation. Crew 1 removed 10 cap panels, and Crew 2 removed 10. Crew 3 continued installing screen wall panels,clips,tubes,moving material and cleaning up. Total clips installed: 132. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 8 |  |  | Boom lifts and forklift. | [5 empty] | Plate Tubing |  |  | 22 | 8 | [24 empty] | 14 | 16
24048 | QTS NAL2 DC1 | 2025-05-17 | Antonio Sanchez | Louver | Subcontractor | Joe Hoyle | false |  | true |  |  | 6 | 10 | true |  | Boomlift forklift | false |  |  |  |  | Louvre | [25 empty] | 60
23029 | BNA Concourse D | 2025-05-16 | Zarur Nazario Padron Jr | Caulking and installing/fabricating ACM panels on Concessions Canopy | JWMCD Crew | Marc Ribar | false |  |  |  |  | 7 | 70 | false |  | 2- 65’ boomlift | false |  |  |  |  | ACM Caulking | 11 | 21 | [18 empty] | 100 | 49 | 0 | 0 | [6 empty] | 0 | 0
23064 | Yondr Allegro 2S | 2025-05-16 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Moving materials to the work area 4 hours |  |  |  | 7 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 36 | 30 | [6 empty] | 230 | 20 | 170 | 10
24005 | GCDC Building 2/VA1.2 | 2025-05-16 | Obed Bermudez | Crew 1 and 2 started removing ACM cap panels on the west elevation. Crew 1 removed 10 cap panels, and Crew 2 removed 10. Crew 3 continued installing screen wall panels,clips,tubes and moving material and cleaning up. Total clips installed: 42. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 11 |  |  | Boom lifts and forklift. | [5 empty] | ACM Plate Tubing | 3 | 6 | 10 | 4 | [24 empty] | 224 | 16
24015 | New Pope School | 2025-05-16 | Maria Tino/ Rafael Gomez |  | Subcontractor | Wylie McDougall | false |  | false |  |  | 5 | 9 | false |  | 2 booms lift | false |  |  |  |  | Caulking | [20 empty] | 200 | 9
24028 | CHI Memorial Hospital | 2025-05-16 | JC Panels | New vertical panel | Subcontractor | Josh McPherson | false |  | true |  |  | 4 | 32 | true |  | 1 boom lift 1 fork lift | false |  |  |  |  | ACM Insulation Subgirt Zee | 9 | 24
24048 | QTS NAL2 DC1 | 2025-05-16 | Antonio Sanchez | Louver | Subcontractor | Joe Hoyle | false |  | true |  |  | 6 | 10 | false |  | Boomlift forklift | false |  |  |  |  | Louvre | [25 empty] | 60
23029 | BNA Concourse D | 2025-05-15 | Zarur Nazario Padron Jr | Installing ACM panels and caulking on Canopy of Concessions. Also installing IMP panels up on Record rooftop. | JWMCD Crew | Marc Ribar | true | Delayed from starting installing ACM panels on ceiling of Record. |  |  | Sunny | 14 | 130 | false |  | 3- 65’ boomlift | false |  |  |  |  | ACM Caulking IMP | 5 | 20 | [6 empty] | 25 | 30 | [10 empty] | 88 | 80 | 0 | 0 | [6 empty] | 0 | 0
23064 | Yondr Allegro 2S | 2025-05-15 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Move material to the work area 1 hour |  |  |  | 7 | 10 |  |  | Boom lift | [5 empty] | Flashing Insulation Subgirt Zee | [26 empty] | 1200 | 30 |  |  | 250 | 20 | 150 | 10
24005 | GCDC Building 2/VA1.2 | 2025-05-15 | Obed Bermudez | Crew 1 continues installing ACM panels. 3 copings modified and installed, flat metal, and J on west elevations. Crew 2 and crew 3 continue installing screen wall panels,clips, and tubes. Crew 4: moving material and cleaning up. Total clips installed: 144 | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 11 |  |  | Boom lifts and forklift. | [5 empty] | ACM Plate Tubing | 13 | 44 | 58 | 33 | [24 empty] | 400 | 33
24015 | New Pope School | 2025-05-15 | Maria Tino - Rafael Gomez |  | Subcontractor | Wylie McDougall | false |  | false |  |  | 5 | 9 | false |  | 2 boom lifts | false |  |  |  |  | Caulking Corrugated / Screen wall Insulation Trim | [20 empty] | 200 | 9 | 40 | 9 |  |  | 100 | 9 | [8 empty] | 150 | 9
24028 | CHI Memorial Hospital | 2025-05-15 | JC Panels | Just the vertical panel that was short | Subcontractor | Josh McPherson | true | There is some problems with waterproofing in the ceiling of the west elevation . We haven’t cover it yet but we reported to McCarthy and they said that was ok | true |  |  | 4 | 40 | true |  | Boom lift fork lift | false |  |  |  |  | ACM | 12 | 30
24048 | QTS NAL2 DC1 | 2025-05-15 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | true | Thunderstorm | false |  | Raining | 6 | 10 | false |  | Boomlift forklift | false |  |  |  |  | Louvre | [25 empty] | 60
23029 | BNA Concourse D | 2025-05-14 | Zarur Nazario Padron Jr | Installing ACM panels on Concessions Canopy | JWMCD Crew | Marc Ribar | true | Electricians are delaying us from starting on Terrace/Record. |  |  | Sunny | 8 | 80 | false |  | 2- 65’ boomlifts | false |  |  |  |  | ACM | 26 | 80 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
23064 | Yondr Allegro 2S | 2025-05-14 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | Move material from the yard to work 40 Minutes total 2 people |  |  |  | 7 |  |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 45 | 30 | [6 empty] | 250 | 20 | 150 | 10
24005 | GCDC Building 2/VA1.2 | 2025-05-14 | Obed Bermudez | Crew 1 continues removing damaged panels and reinstalling ACM panels. 6 copings modified and installed, flat metal, and J on west elevations. Crew 2 and crew 3 continue installing screen wall panels,clips, and tubes. Crew 4: moving material and cleaning up. Total clips installed: 168 | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 11 |  |  | Boom lifts and forklift. | [5 empty] | ACM Hat Channel Plate Tubing | 9 | 43 | 35 | 33 | [24 empty] | 392 | 66 |  |  |  |  | 22 | 1
24015 | New Pope School | 2025-05-14 | maria tino/rafael gomez | we need more trims | Subcontractor | Wylie McDougall | false |  | true |  |  | 5 | 9 | false |  | 2 boom lift | false |  |  |  |  | Caulking Corrugated / Screen wall Trim | [20 empty] | 250 | 9 | 30 | 9 | [12 empty] | 250 | 9
24028 | CHI Memorial Hospital | 2025-05-14 | JC Panels | The panel that is short to continue de vertical panels | Subcontractor | Josh McPherson | true | The rain in the morning make us stop for a while … | true |  | Rainy morning | 4 |  | true | Screws | 1 boom lift 1 fork lift | false |  |  |  |  | ACM | 10 | 27
24046 | UAB Biomedical Research and Psycholgy | 2025-05-14 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 3 | 24 | false |  | 40' boom lift | false |  |  |  |  | ACM Caulking | 6 | 12 | [18 empty] | 26 | 12
24048 | QTS NAL2 DC1 | 2025-05-14 | Antonio Sanchez | Louver | Subcontractor | Joe Hoyle | false |  | true |  |  | 6 | 10 | false |  | Boomlift forklift | false |  |  |  |  | Louvre | [25 empty] | 60
24048 | QTS NAL2 DC1 | 2025-05-14 | Antonio Sanchez | Louver | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 10 | false |  |  | false |  |  |  |  | Louvre
23029 | BNA Concourse D | 2025-05-13 | Zarur Nazario Padron Jr | Working on installing ACM panels on Canopy of Concessions. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 8 | 80 | false |  | 2- 65’ boomlifts | false |  |  |  |  | ACM | 27 | 80 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
24015 | New Pope School | 2025-05-13 | maria tino/rafael gomez |  | Subcontractor | Wylie McDougall | false |  | false |  |  | 5 | 9 | false |  | 2 boom lift | false |  |  |  |  | Caulking Corrugated / Screen wall Trim | [20 empty] | 250 | 9 | 30 | 9 | [12 empty] | 150 | 9
24028 | CHI Memorial Hospital | 2025-05-13 | JC Paneñs | 2” screws 2 1/2” screws, reveals, correct measure in one panel | Subcontractor | Josh McPherson | true | Rain is not helping us this week with the project . We have to stop several times because of the heavy rain.. also the panel 210-1A36 is short so we had to hake it down again , we prepare all the panels for that section but we couldn’t install them because of the short panel | true |  | Heavy rain | 4 | 32 | true | We receive 12 crates of Morin panels | Boom lift, fork lift | false |  |  |  |  | ACM | 4
24046 | UAB Biomedical Research and Psycholgy | 2025-05-13 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 3 | 30 | false |  | 40' boom lift | false |  |  |  |  | ACM Caulking Subgirt Zee | 14 | 18 | [18 empty] | 50 | 10 | [8 empty] | 30 | 2
24048 | QTS NAL2 DC1 | 2025-05-13 | Antonio Sanchez | Louver scaffold built-in get material from store yard | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 10 | false |  | Boomlift forklift | false |  |  |  |  | Louvre
23029 | BNA Concourse D | 2025-05-12 | Zarur Nazario Padron Jr | Installing ACM panels on Canopy of Concessions | JWMCD Crew | Marc Ribar | false |  |  |  |  | 7 | 63 | false |  | 2- 65’ boomlift | false |  |  |  |  | ACM | 23 | 63 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
23064 | Yondr Allegro 2S | 2025-05-12 | Ever mendoza |  | Subcontractor | Joe Hoyle | true | In moving material from the yard to the work camp 2 trips 40 minutes for two people t 80 minutes |  |  |  | 7 | 10 |  |  | Boom lift | [5 empty] | Flashing Insulation Subgirt Zee | [26 empty] | 1200 | 30 |  |  | 250 | 20 | 150 | 10
24001 | McEwen Northside | 2025-05-12 | Marvin Blanco | Working in a extra work in the soffit of the bridge and also doing silicone cleaning our areas of work | Subcontractor | Josh McPherson | false |  | true |  |  | 8 | 10 | false |  | Boomlift scissors lift and forklift | false |  |  |  |  | ACM Caulking Soffit | 10 | 50 | [18 empty] | 200 | 30
24005 | GCDC Building 2/VA1.2 | 2025-05-12 | Obed Bermudez | Crew 1 continues removing damaged panels and reinstalling ACM panels. 6 copings modified and installed, flat metal, and J on west elevations. Crew 2 and crew 3 continue installing screen wall panels, clips, and tubes. Crew 4: moving material and cleaning up. Total clips installed: 92 | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 8 |  |  | Boom lifts and forklift. | [5 empty] | ACM Plate Tubing | 6 | 24 | 78 | 48 | [24 empty] | 210 | 24
24015 | New Pope School | 2025-05-12 | maria tino/rafael gomez |  | Subcontractor | Wylie McDougall | false |  | false |  |  | 5 | 9 | true | corrugated panels AND JS' | 2 BOOMS LIFT | false |  |  |  |  | Caulking Insulation Subgirt Zee | [20 empty] | 200 | 9 |  |  |  |  | 100 | 9 |  |  | 150 | 9
24046 | UAB Biomedical Research and Psycholgy | 2025-05-12 | Naza | The ACM material arrived at the job site at 2 p.m. The mucup panels were removed | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 3 | 24 | false |  | 40' boom lift | false |  |  |  |  | ACM Caulking Insulation Other Subgirt Zee | 2 | 6 | [18 empty] | 50 | 6 |  |  |  |  | 26 | 1 |  |  | 10 | 1 | [11 empty] | 10
24048 | QTS NAL2 DC1 | 2025-05-12 | Antonio Sanchez | Louver layout and level layout dliver louver material to job site from parking lot | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 10 | true | Louver material from store yard | Boomlift, forklift | false |  |  |  |  | Louvre | [25 empty] | 50
24048 | QTS NAL2 DC1 | 2025-05-11 | Antonio Sanchez | Housekeeping on data roof, penhause, office roof | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 45 | false |  |  | false |  |  |  |  | Other
23029 | BNA Concourse D | 2025-05-10 | Naza |  | Subcontractor | Marc Ribar | false |  | false |  |  | 8 | 64 | false |  | 3 65' Boom Lifts | false |  |  |  |  | ACM | 30 | 64
24005 | GCDC Building 2/VA1.2 | 2025-05-10 | Obed Bermudez | Crew 1 continues removing damaged panels and reinstalling ACM panels, flat metal, and J on west elevations. Crew 2 and crew 3 continue installing screen wall panels, clips, and tubes. Crew 4: moving material and cleaning up. Total clips installed: 92. | JWMCD Crew | Joe Hoyle | [5 empty] | 7 | 8 |  |  | Boom lifts and forklift. | [5 empty] | Plate Tubing |  |  | 82 | 16 | [24 empty] | 308 | 40
24025 | Madison Elementary | 2025-05-10 | Rudy | 1 man rework in courtyard 1 man @ roof | Subcontractor | Wylie McDougall | false |  | true |  |  | 2 | 8 | false |  | 1 boom | false |  |  |  |  | Insulation Single Skin Subgirt Zee Trim | [7 empty] | 4 | [18 empty] | 4 | 4 |  |  | 4 | 4 | [5 empty] | 4
24048 | QTS NAL2 DC1 | 2025-05-10 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 4 | 40 | false |  | Boomlift forklift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 10 | 40
23029 | BNA Concourse D | 2025-05-09 | Zarur Nazario Padron Jr | Installing ACM panels on Canopy of Concessions | JWMCD Crew | Marc Ribar | false |  |  |  |  | 7 | 77 | false |  | 2- 65’ boomlifts | false |  |  |  |  | ACM | 20 | 77 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
23029 | BNA Concourse D | 2025-05-09 | Zarur Nazario Padron Jr | Working on installing pipe trims and fabricating 1 trim. Also cleaning IMP panels | JWMCD Crew | Marc Ribar | false |  |  |  |  | 2 | 14 | false |  | 65’ boomlift and scissor lift | false |  |  |  |  | Other Trim | [20 empty] | 10 | 4 | 0 | 0 | [6 empty] | 0 | 0 |  |  |  |  | 10 | 8 | [5 empty] | 2
23064 | Yondr Allegro 2S | 2025-05-09 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 7 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 57 | 30 | [6 empty] | 200 | 20 | 100 | 10
24005 | GCDC Building 2/VA1.2 | 2025-05-09 | Obed Bermudez | Crew 1 continues removing damaged panels and reinstalling ACM panels, flat metal, and J on west elevations. Crew 2 and crew 3 continue installing screen wall panels, clips, and tubes. Crew 4: moving material and cleaning up. Total clips installed: 68. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 11 | true | Screen wall material. | Boon lifts and forklift. | [5 empty] | ACM Plate Tubing | 9 | 44 | 86 | 44 | [24 empty] | 238 | 44
24015 | New Pope School | 2025-05-09 | maria tino/rafel gomez | one of the panels came upside down | Subcontractor | Wylie McDougall | false |  | true |  |  | 5 | 9 | false |  | 2 boom lift | false |  |  |  |  | ACM Caulking | 25 | 9 | [18 empty] | 100 | 9
24028 | CHI Memorial Hospital | 2025-05-09 | JC Panels | 2 1/2 screws for top panels. Also we are running out of revels we need them asap | Subcontractor | Josh McPherson | false |  | true |  |  | 4 | 36 | false |  | Boom lift fork lift | false |  |  |  |  | ACM | 12
24048 | QTS NAL2 DC1 | 2025-05-09 | Antonio Sanchez | Install scaffolding penhause | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 10 | false |  | Boomlift, forklift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 10 | 50
23029 | BNA Concourse D | 2025-05-08 | Zarur Nazario Padron Jr | Cleaning IMP panels on D5 connector and installing IMP panels. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 2 | 20 | false |  | 65’ boomlift | false |  |  |  |  | IMP Other | [8 empty] | 2 | 2 | [10 empty] | 0 | 0 | 0 | 0 | [6 empty] | 2 | 1 | [11 empty] | 17
23033 | Iron Mountain VA6 | 2025-05-08 | Marvin Blanco | Remaking panels for Hitt company and Also cleaning our areas of work | Subcontractor | Joe Hoyle | false |  | true |  |  | 3 | 12 | true | Flats sheets of ACM panels | Boomlift | false |  |  |  |  | ACM | 3 | 36
23064 | Yondr Allegro 2S | 2025-05-08 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 7 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Subgirt Zee Trim | [22 empty] | 42 | 30 | [6 empty] | 300 | 20 |  |  |  |  | 105 | 10
24001 | McEwen Northside | 2025-05-08 | Marvin Blanco | Manufacturing panels remaking panels and cleaning our areas of work | Subcontractor | Josh McPherson | true | Bellara panels | true |  | Good condition | 5 | 11 | false |  | Boomlift scissors lift and forklift | false |  |  |  |  | ACM | 8 | 55
24005 | GCDC Building 2/VA1.2 | 2025-05-08 | Obed Bermudez | Crew 1 installing ACM panels, flat metal, and J on west elevations. Crew 2 and crew 3 continue installing screen wall panels, clips, and tubes. Crew 4: moving material and cleaning up. Total clips installed: 144. Crew 1 started removing copings and damaged panels. The Rosendin crew were bringing pipe material up to the roof and scratched one of panels already installed and bent another that was ready to be installed. | JWMCD Crew | Joe Hoyle | true | The owners had a walk around the whole building and would stop our work whenever they were in our area. |  |  | Heavy rain at times. | 12 | 11 |  |  | Boom lifts and forklift. | [5 empty] | ACM Plate Tubing | 3 | 44 | 91 | 22 | [24 empty] | 238 | 33
24015 | New Pope School | 2025-05-08 | maria tino /rafael gomez |  | Subcontractor | Wylie McDougall | false |  | false |  |  | 5 | 9 | false |  | 2 boom lift | false |  |  |  |  | ACM Other | 18 | 9 | [40 empty] | caulking 100 linear ft | 9
24025 | Madison Elementary | 2025-05-08 | Rudy Pineda | 1 man courtyard rework. 1 man @ soffitts | Subcontractor | Wylie McDougall | false |  | true |  |  | 3 | 8 | false |  | 1boom | false |  |  |  |  | AWB Caulking Flashing Insulation Subgirt Zee Trim | [21 empty] | 4 | [5 empty] | 4 |  |  |  | 4 |  | 4 |  |  |  | 4 |  | 4
24028 | CHI Memorial Hospital | 2025-05-08 | JC Panels | We need 2 1/2” screws for the las panel. I will attache the picture | Subcontractor | Josh McPherson | false |  | true |  |  | 4 | 36 | true | We got the 2 7/8” z’s | Boom lift , fork lift | false |  |  |  |  | ACM | 9 | 36
24048 | QTS NAL2 DC1 | 2025-05-08 | Antonio Sanchez | Corrugated rib panel | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 10 | false |  | Boomlift, forklift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 18 | 50
23064 | Yondr Allegro 2S | 2025-05-07 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 7 | 10 | true | Corrugated panels and insulation | Boom lift | [5 empty] | Corrugated / Screen wall Subgirt Zee | [22 empty] | 57 | 30 | [6 empty] | 230 | 20
24001 | McEwen Northside | 2025-05-07 | Marvin Blanco | Remaking panels because McDougall made the panels with the wrong dimensions the guys are working in the outside of the bridge remaking panels in the last column north elevation and cleaning the areas | Subcontractor | Josh McPherson | true | Bellara panels | true |  | Good condition | 5 | 11 | false |  | Boomlift scissors lift and forklift | false |  |  |  |  | ACM | 7 | 55
24005 | GCDC Building 2/VA1.2 | 2025-05-07 | Obed Bermudez | Crew 1 installing ACM panels, flat metal, and J on west elevations. Crew 2 and crew 3 continue installing screen wall panels, clips, and tubes. Crew 4: moving material and cleaning up. Total clips installed: 162. | JWMCD Crew | Joe Hoyle | true | Please keep in mind we are on safety week, so we are missing out on a lot of hours worth of work. |  |  |  | 12 | 11 |  |  | Boom lifts and forklift. | [5 empty] | ACM Plate Tubing | 5 |  | 34 | 22 | [24 empty] | 392 | 33
24015 | New Pope School | 2025-05-07 | maria tino/rafael gomez | we work on elevation 202 | Subcontractor | Wylie McDougall | false |  | true |  |  | 5 |  | false |  | 2 boom lifts | false |  |  |  |  | ACM | 22 | 9
24025 | Madison Elementary | 2025-05-07 | Rudy Pineda | area east | Subcontractor | Wylie McDougall | false |  | true |  |  | 2 | 8 | false |  | 1 boom | false |  |  |  |  | Soffit
24028 | CHI Memorial Hospital | 2025-05-07 | JC Panels |  | Subcontractor | Josh McPherson | true | We couldn’t work today because the brick guys were in our way. McCarthy said that they were going to move them after lunch , we came back and they h didn’t move. We have frame all the west area and there was nothing more for us to do | false |  |  | 4 | 0 | true | We got the screws and shims | 1 boom lift 1 scissor lift | false |  |  |  |  | Other | [42 empty] | We couldn’t install anything | 0
24048 | QTS NAL2 DC1 | 2025-05-07 | Antonio Sanchez | Corrugated rib panel | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 10 | false |  | Boomlift, forklift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 37 | 50
23064 | Yondr Allegro 2S | 2025-05-06 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 6 | 8 |  |  | Boom lift | [5 empty] | Insulation Trim | [26 empty] | 1400 | 40 | [8 empty] | 100 | 8
24001 | McEwen Northside | 2025-05-06 | Marvin Blanco | Remaking panels for the inside of the bridge installing ACM panels inside of the bridge and also cleaning our areas of work we need the bellara panels soon as possible please to be done with this job | Subcontractor | Josh McPherson | true | Bellara panels | true |  | Good condition | 7 | 11 | false |  | Boomlift scissors lift and forklift | false |  |  |  |  | ACM | 10 | 77
24005 | GCDC Building 2/VA1.2 | 2025-05-06 | Obed Bermudez | Crew 1 installing ACM panels, flat metal, and J on east and west elevations. Crew 2 and crew 3 continue installing screen wall panels, clips, and tubes. Crew 4: moving panel boxes, unloading screen wall delivery, and lifting it up to the roof. Total clips installed: 186. We remade panel 206-1j06 because it arrived damage. | JWMCD Crew | Joe Hoyle | true | Our crew was stopped from working due to lighting in the are 2 times for a duration of 2 hours total. |  |  | Lighting around building. | 12 | 12 | true | Screen wall material | Boom lifts and forklift. | [5 empty] | ACM Plate Tubing | 9 | 36 | 60 | 24 | [24 empty] | 434 | 40
24015 | New Pope School | 2025-05-06 | maria tino /rafael gomez | we need single clips | Subcontractor | Wylie McDougall | false |  | true |  |  | 5 | 9 | false |  | 2 boom lift | false |  |  |  |  | ACM Insulation Subgirt Zee | 17 | 9 | [24 empty] | 100 | 9 |  |  | 120 | 9
24028 | CHI Memorial Hospital | 2025-05-06 | JC Panels | Screws and shims.. we need to have this to start installing panels the west area is all done with the framing | Subcontractor | Josh McPherson | true | Screws and shims .. also we need the 2 7/8 z’s | true |  |  | 4 | 8 | false |  | 1 boom lift 1 scissor lift | false |  |  |  |  | Subgirt Zee
24048 | QTS NAL2 DC1 | 2025-05-06 | Antonio Sanchez | Corrugated rib panel | Subcontractor | Joe Hoyle | true | Rain | true |  | Raining | 5 | 5 | true |  |  | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 11 | 25
23029 | BNA Concourse D | 2025-05-05 | Antonio | We reinstalled the panels on low roof D9 due to a joint problem, also finished the window flashing around the record note. | JWMCD Crew | Marc Ribar | true | Could not install high roof D9 due to valleys flat strap going past our panel system. Now roofers have to patch it. Also fixed issues on punch list |  |  | Partly cloudy with showers | 8 | 8 | true | Flashing for the Terrance | 3 85’ man lifts and a 65’ man lift. 1 7k lull | false |  |  |  |  | Flashing IMP | [8 empty] | 37 | 7 | [22 empty] | 60 | 40
23064 | Yondr Allegro 2S | 2025-05-05 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 7 | 8 |  |  | Boom lift | [5 empty] | Insulation Subgirt Zee | [26 empty] | 400 | 16 |  |  | 700 | 32
24001 | McEwen Northside | 2025-05-05 | Marvin Blanco | Installing ACM panels inside the bridge around the columns cleaning our areas of work also we need the bellara panels | Subcontractor | Josh McPherson | false |  | true |  |  | 7 | 11 | false |  | Boomlift scissors lift and forklift | false |  |  |  |  | ACM | 10 | 77
24005 | GCDC Building 2/VA1.2 | 2025-05-05 | Obed Bermudez | Crew 1 installing ACM panels, flat metal, and J on east elevation. Crew 2 installing screen wall panels and tubes. Crew 3 installed 156 clips . Crew 4: moving panel boxes and cleaning up. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 11 |  |  | Boom lifts and forklift. | [5 empty] | ACM Hat Channel Other Plate Tubing | 1 | 2 | 52 | 22 | [24 empty] | 364 | 33 |  |  |  |  | 40 | [8 empty] | 6
24015 | New Pope School | 2025-05-05 | maria tino /rafael gomez | we need J" | Subcontractor | Wylie McDougall | false |  | true |  |  | 5 | 9 | true | ACM PANELS | 2 boom lift | false |  |  |  |  | Corrugated / Screen wall Trim | [22 empty] | 30 | 9 | [12 empty] | 100 | 9
24028 | CHI Memorial Hospital | 2025-05-05 | JC panels | Tek 2 screws shims | Subcontractor | Josh McPherson | true | We are waiting for tek 2 screws and shims | true |  |  | 4 | 10.5 | false |  | 1 boom lift 1 scissor lift | false |  |  |  |  | Subgirt Zee
24028 | CHI Memorial Hospital | 2025-05-05 | JC Panels |  | Subcontractor | Josh McPherson | true | We haven’t received the shims and the screws tek2 for panels | false |  |  | 4 | 10.5 | false |  | 1 boom lift 1 scissor lift | false |  |  |  |  | Subgirt Zee
24048 | QTS NAL2 DC1 | 2025-05-05 | Antonio Sanchez | Corrugated rib panel | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 10 | true | Louver Blades,Gibraltar clips |  | false |  |  |  |  | Corrugated / Screen wall
24005 | GCDC Building 2/VA1.2 | 2025-05-03 | Obed Bermudez | Crew 1 installing ACM panels, flat metal, and J on east elevation. Crew 2 installing screen wall panels and tubes. Crew 3: 52 clips installed. Crew 4: moving panel boxes and cleaning up. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 5 | [8 empty] | ACM Plate Tubing | 9 | 15 | 23 | 15 | [24 empty] | 182 | 15
23064 | Yondr Allegro 2S | 2025-05-02 | Ever mendoza |  | Subcontractor | Joe Hoyle | [5 empty] | 5 | 8 | true | Corrugated panels and Z girt | Boom lift | [5 empty] | Subgirt Zee | [30 empty] | 400 | 32
24005 | GCDC Building 2/VA1.2 | 2025-05-02 | Obed Bermudez | All crews are working on the roof, with two crews installing clips and screen wall panels, and the third crew installing middle clip connections and relocating material. 25 screen wall panels have been installed, 10 clips have been installed. We had to move 2 crews to start east side elevation ACM panels and left another crew peeling protective film in the west elevation. | JWMCD Crew | Joe Hoyle | true | All building interior and roof work was stopped for the day due to a power outage at 10 am. |  |  |  | 12 | 11 |  |  | Boom lifts and forklift. |  |  |  | 6 |  | ACM Flashing Layout Plate | 2 | 2 | 25 | 9 | [28 empty] | 80 | 16
24025 | Madison Elementary | 2025-05-02 | Rudy Pineda | 1 man finishing up caulking in courtyard | Subcontractor | Wylie McDougall | false |  | true |  |  | 2 | 8 | false |  | 1 boom | false |  |  |  |  | Caulking Flashing Insulation Soffit Subgirt Zee | [21 empty] | 3 | [5 empty] | 3 |  |  |  | 3 |  | 3
24045 | TMMMS Childcare | 2025-05-02 | Zachary Hood | installing Z girts/ Insulations | Subcontractor | Chris Buttrey | false |  | true |  |  | 6 | 10 | true |  | (2) 45' boomlifts | false |  |  |  |  | ACM | 26 | 40
24048 | QTS NAL2 DC1 | 2025-05-02 | Antonio Sanchez | Corrugated rib panel | Subcontractor | Joe Hoyle | true |  | true |  | Raining | 5 | 8 | false |  | Boomlift forklift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 10 | 40
23029 | BNA Concourse D | 2025-05-01 | Antonio | I had three crews on site one crew was back tracking and putting the window flashing in all the panels we put on the record note. The second crew installed the last of the panels into landside D9 area then up the glass. They installed 22 panels. Then my third crew was on the D9 low and high roof installing the record note 4’5” panels. They installed the corresponding flashing and mending plate too. | JWMCD Crew | Marc Ribar | true | Small rain showers stopping work |  |  | Sunny with slight showers | 8 | 10 | false |  | 3 85’ man lifts and 1 65’ man lift. A 7k lull | false |  |  |  |  | Flashing IMP | [8 empty] | 43 | 60 | [22 empty] | 110 | 20
23064 | Yondr Allegro 2S | 2025-05-01 | Ever mendoza | Safety orientation | Subcontractor | Joe Hoyle | true | No llegaron | true |  |  | 8 | 6 | true | Insulation, trims and flashing stell angles screw | Boom lift | [5 empty] | ACM Corrugated / Screen wall Insulation Subgirt Zee | 0 | 0 | [20 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
24001 | McEwen Northside | 2025-05-01 | Marvin Blanco | Cleaning our areas of work installing the bellara panels also putting the gasket in the roof for the metal panels we have one problem the bellara panels we are shorts on that no enough for finish the soffit it's only one box left and we don't have not even the haft of the bridge | Subcontractor | Josh McPherson | false |  | true |  |  | 7 | 11 | false |  | Boomlift scissors lift and forklift | false |  |  |  |  | ACM Other | 9 | 44 | [40 empty] | Bellara panels | 33
24005 | GCDC Building 2/VA1.2 | 2025-05-01 | Obed Bermudez | All crews are working on the roof, with two crews installing clips and screen wall panels, and the third crew installing middle clip connections, relocating material and cleaning up. 76 screen wall panels have been installed, 20 clips have been installed, and 7 middle connection clips have been installed. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 11 |  |  | Boom lifts and forklift. | [5 empty] | Plate |  |  | 76 | 110
24025 | Madison Elementary | 2025-05-01 | Rudy Pineda | 2 men in courtyard rework | Subcontractor | Wylie McDougall | false |  | true |  |  | 3 | 8 | false |  | 1 boom | false |  |  |  |  | Caulking Flashing Insulation Soffit Subgirt Zee | [21 empty] | 5 | [5 empty] | 5 |  |  |  | 5 |  | 5
24028 | CHI Memorial Hospital | 2025-05-01 | JC Panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 4 | 7 | false |  | Boom lift, fork lift | false |  |  |  |  | Caulking Subgirt Zee | [21 empty] | 7 | [9 empty] | 7
24048 | QTS NAL2 DC1 | 2025-05-01 | Antonio Sanchez | Corrugated rib panel | Subcontractor | Joe Hoyle | false |  | true |  |  | 6 | 10 | false |  | Boomlift forklift | false |  |  |  |  | Corrugated / Screen wall Trim | [22 empty] | 20 | 40 | [12 empty] | 320 | 20
24005 | GCDC Building 2/VA1.2 | 2025-04-30 | Obed Bermudez | All crews continue working on the roof: two installing clips, and screen wall panels, and the third installing middle clip connection. 60 clips installed. 15 middle connection clips installed. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 11 |  |  | Boom lifts and forklift.
24018 | QTS-NAL1-DC1 | 2025-04-30 | Saul chicas | Was raining outside, we finished with the caulking on the freedom wall, we also pellet the panels and cleaned, we installed all the spline around the lights | Subcontractor | Joe Hoyle | [5 empty] | 4 | 8 |  |  | Scissor lift | [5 empty] | Caulking | [9 empty] | 32 | [10 empty] | 80 | 8
24028 | CHI Memorial Hospital | 2025-04-30 | JC panels |  | Subcontractor | Josh McPherson | false |  | false |  |  | 4 | 6 | true | Z’s insolation screws caulking ACM | Forklift, boom lift | false |  |  |  |  | ACM
24048 | QTS NAL2 DC1 | 2025-04-30 | Antonio Sanchez | Corrugated rib panel | Subcontractor | Joe Hoyle | false |  | true |  |  | 6 | 10 | false |  | Boomlift, forklift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 30 | 60
23029 | BNA Concourse D | 2025-04-29 | Antonio | Today I had three crews, two crews focused mainly on installing the imp panels on the bottom of the CW of the record note. The third crew also was working on the imp for record note but got pulled off to start working on punch items and areas that need our attention. We installed 34 panels and various corresponding flashings and mending plate. | JWMCD Crew | Marc Ribar | true | Work on landside record note was spotty due to having to work around heavy machinery that is working in the area. ( grading prepping for concrete) also HP hasn’t released me to install in the area where Valley did revisions to their framing. |  |  | Clear 92° | 12 | 10 | true | The pallet of flashing and a pallet of flashing that the electricians need. Contacted Henry Ford he will pick them up tomorrow | I have 3 85’ man lifts 1 65’ man lift and a 7 k lull | false |  |  |  |  | Flashing IMP | [8 empty] | 34 | 60 | [22 empty] | 100 | 40
24005 | GCDC Building 2/VA1.2 | 2025-04-29 | Obed Bermudez | All crews continue working on the roof: two installing clips, and screen wall panels, and the third installing middle clip connection. 30 clips installed. 8 middle connection clips installed. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 11 |  |  | Boom lifts and forklift.
24025 | Madison Elementary | 2025-04-29 | Rudy Pineda | 2 men rework in courtyard 8 hours each | Subcontractor | Wylie McDougall | false |  | true |  |  | 3 | 8 | false |  | 1 boom lift | false |  |  |  |  | AWB Caulking Flashing Insulation Single Skin Subgirt Zee Trim | [7 empty] | 3 | [13 empty] | 8 | [5 empty] | 3 |  |  |  | 3 |  | 3 |  |  |  | 3 |  | 3
24048 | QTS NAL2 DC1 | 2025-04-29 | Antonio Sanchez | Corrugated rib panel | Subcontractor | Joe Hoyle | true | Rain | true |  |  | 6 | 9 | false |  | Boomlift forklift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 30 | 54
24001 | McEwen Northside | 2025-04-28 | Marvin Blanco | Working in the columns also cleaning the parking garage the guys are waiting for the bellara panels and Hoar is holding us for Working inside of the bridge | Subcontractor | Josh McPherson | false |  | true |  |  | 7 | 12 | false |  | Boomlift scissors lift and forklift | false |  |  |  |  | ACM Other | 8 | 36 | [40 empty] | Cleaning our areas of work | 48
24005 | GCDC Building 2/VA1.2 | 2025-04-28 | Obed Bermudez | All crews continue working on the roof: two installing clips, and screen wall panels, and the third installing middle clip connection. 60 clips installed. 12 middle connection clips installed. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 11 |  |  | Boom lifts and forklift. | [5 empty] | Other | [43 empty] | 80
24025 | Madison Elementary | 2025-04-28 | Rudy Pineda | 2 men rework courtyard 8 hours | Subcontractor | Wylie McDougall | false |  | true |  |  | 3 | 8 | false |  | 1 boom | false |  |  |  |  | AWB Caulking Flashing Insulation Single Skin Subgirt Zee | [7 empty] | 3 | [13 empty] | 8 | [5 empty] | 3 |  |  |  | 3 |  | 4 | [5 empty] | 3
24048 | QTS NAL2 DC1 | 2025-04-28 | Antonio Sanchez | Box rib corrugated | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 10 | false |  | Boomlift forklift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 16 | 50
24005 | GCDC Building 2/VA1.2 | 2025-04-26 | Obed Bermudez | One crew continues working on the west elevation, modifying coping panels while the other continues working on the roof, installing clips, tubes, and screen wall panels. Five ACM coping panels have been modified and installed. Thirty-two clips have been installed. Five middle connection clips have been installed. Unfortunately, we had to leave early due to inclement weather. | JWMCD Crew | Joe Hoyle | true |  |  |  | Rainy day we left early. | 7 | 4 |  |  | Boom lifts and forklift. | [5 empty] | ACM | 5 | 8
24048 | QTS NAL2 DC1 | 2025-04-26 | Antonio Sanchez | Corrugated rib panel | Subcontractor | Joe Hoyle | false |  | true |  |  | 5 | 10 | true | Corrugated rib panel | Boomlift, forklift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 18 | 50
23029 | BNA Concourse D | 2025-04-25 | Zarur Nazario Padron Jr | Working on installing IMP panels/ J-flashing/ Subgirt Zee on record. Doing layout on Record rooftop for Valley. Valley has also delayed us from installing panels on D9 wall because they are yet to put up flat strap. We also got Rained out | JWMCD Crew | Marc Ribar | true | Valley has delayed us from installing panels on D9 wall because they are yet to put up flat stap. We got rained out 6 hours into working. |  |  | Raining | 10 | 60 | false |  | 3- 65’ boomlifts | false |  |  | 6 |  | Flashing IMP Layout Subgirt Zee | [8 empty] | 37 | 36 | [10 empty] | 0 | 0 | 0 | 0 | [6 empty] | 92 | 9 | 110 | 9
23029 | BNA Concourse D | 2025-04-25 | Zarur Nazario Padron Jr | Working on installing IMP panels/ J-flashing/ Subgirt Zee on Record, also doing layout for Valley | JWMCD Crew | Marc Ribar | true | Rain out |  |  | Raining | 10 | 60 | false |  | 3- 65’ boomlifts | false |  |  | 6 |  | Flashing IMP Layout Subgirt Zee | [8 empty] | 37 | 36 | [10 empty] | 0 | 0 | 0 | 0 | [6 empty] | 92 | 9 | 110 | 9
24005 | GCDC Building 2/VA1.2 | 2025-04-25 | Obed Bermudez | One crew continues working on the west elevation, modifying coping panels while the other continues working on the roof,installing clips,tubes, and screen wall panels. The third crew unloaded a delivery and worked on getting pallets up to the roof. 31 ACM coping panels modified and installed. 65 clips installed. 10 middle connection clips installed. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 10 | true | Screen wall panels. | Boom lifts and forklift. | [5 empty] | ACM | 31 | 40
24025 | Madison Elementary | 2025-04-25 | Rudy Pineda | 2 men rework at courtyard 1 man caulking and touch up | Subcontractor | Wylie McDougall | false |  | true |  |  | 3 | 8 | false |  | 1 boom | false |  |  |  |  | AWB Caulking Flashing Insulation Single Skin Subgirt Zee Trim | [7 empty] | 3 | [13 empty] | 8 | [5 empty] | 3 |  |  |  | 3 |  | 3 |  |  |  | 3 |  | 3
24048 | QTS NAL2 DC1 | 2025-04-25 | Antonio Sanchez | Corrugated rib panel | Subcontractor | Joe Hoyle | true | Rain | true |  | Rain | 6 | 10 | false |  |  | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 22 | 60
23029 | BNA Concourse D | 2025-04-24 | Zarur Nazario Padron Jr | Installing IMP panels on Record and J-flashing | JWMCD Crew | Marc Ribar | true | Rain delay caused us to rainout and only work 6 hours |  |  | Raining | 9 | 54 | false |  | 3- 65’ boomlifts | false |  |  |  |  | Flashing IMP | [8 empty] | 21 | 45 | [10 empty] | 0 | 0 | 0 | 0 | [6 empty] | 80 | 4 | 25 | 5
24005 | GCDC Building 2/VA1.2 | 2025-04-24 | Obed Bermudez | One crew continues working on the west elevation, modifying coping panels while the other continues working on the roof,installing clips,tubes, and screen wall panels. 26 acm coping panels modified and installed. 60 clips installed. 14 middle connection clips installed. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 10 |  |  | Boom lifts and forklift. | [5 empty] | ACM | 26 | 40
24025 | Madison Elementary | 2025-04-24 | Rudy Pineda | 2 men 8 hours rework at courtyard- 1 man caulking and touchup | Subcontractor | Wylie McDougall | false |  | true |  |  | 3 | 8 | false |  | 1boom | false |  |  |  |  | AWB Caulking Flashing Insulation Single Skin Subgirt Zee Trim | [7 empty] | 3 | [13 empty] | 8 | [5 empty] | 3 |  |  |  | 3 |  | 3 |  |  |  | 3 |  | 3
24048 | QTS NAL2 DC1 | 2025-04-24 | Antonio Sanchez | Corrugated rib panel | Subcontractor | Joe Hoyle | false |  | true |  |  | 6 | 10 | true |  | Boomlift, forklift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 33 | 60
23029 | BNA Concourse D | 2025-04-23 | Zarur Nazario Padron Jr | Installing IMP panels on Record and also J-flashing | JWMCD Crew | Marc Ribar | false |  |  |  |  | 4 | 36 | false |  | 65’ boomlift | false |  |  |  |  | Flashing IMP | [8 empty] | 14 | 24 | [10 empty] | 0 | 0 | 0 | 0 | [6 empty] | 40 | 6 | 50 | 6
24005 | GCDC Building 2/VA1.2 | 2025-04-23 | Obed Bermudez | One crew continues working on the west elevation, modifying coping panels while the other continues working on the roof, installing clips,tubes, and screen wall panels. 49 clips installed. 14 middle connection clips installed. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 10 |  |  | Boom lifts and forklift. | [5 empty] | ACM Plate | 14 | 40
24009 | Cityside Subaru | 2025-04-23 | JB | We will need more washers for the bolts | Subcontractor | Chris Buttrey | true | We don’t have all the panels on site, so we have jumped to other area. We also need an answer to install the bottom panel. | true |  |  | 5 | 10 | false |  | 1 forklift 2 boom lift | false |  |  |  |  | Plate Tubing |  |  | 15 | 20 | [24 empty] | 300 | 30
24020 | QTS ATL2 DC2 Osgood | 2025-04-23 | Marvin Blanco | Waiting on Hitt team to take some electrical cables from the last opening we have for install the stanley steel flat sheets we need McDougall to put hands on it because Hitt guys are taking forever | Subcontractor | Dillon Bowman | true | Silicone | true |  | Good condition | 4 | 10 | false |  | Boomlift | false |  |  |  |  | Other | [42 empty] | Waiting all day for Hitt | 48
24025 | Madison Elementary | 2025-04-23 | Rudy Pineda | rework @ courtyard 2 men 8 hours- 1 man caulking and touch up east elevation | Subcontractor | Wylie McDougall | false |  | true |  |  | 3 | 8 | false |  | 1 | false |  |  |  |  | Caulking Flashing Insulation Single Skin Subgirt Zee Trim | [7 empty] | 4 | [13 empty] | 8 | [5 empty] | 4 |  |  |  | 4 |  | 4 |  |  |  | 4
24048 | QTS NAL2 DC1 | 2025-04-23 | Antonio Sanchez | Corrugated rib panel | Subcontractor | Joe Hoyle | false |  | true |  |  | 6 | 10 | true |  |  | false |  |  |  |  | Corrugated / Screen wall Trim | [22 empty] | 21 | 40 | [12 empty] | 120 | 20
24068 | QTS NAL1 DC2 | 2025-04-23 | Marvin Blanco | My guys was installing the Hats channels in the wrong side of the building because I didn't send all the information for the metal panels and the louvers we lose half a day installing Zs making a Hats in the south elevation but others guys was getting the truck ready for moving material from the layout down are over to the job site and one more thing we found some damaged panels IMP panels | Subcontractor | Joe Hoyle | false |  | true |  |  | 6 | 10 | true | Forklift | Boomlift | false |  |  |  |  | Hat Channel Other | [34 empty] | 150 | 36 | [6 empty] | Getting material from the yard | 36
24001 | McEwen Northside | 2025-04-22 | Marvin Blanco | Taking off some column panels in the west elevation and also working in the bridge inside column in the west side columns it's extra work for Hoar because the electric guys didn't put the cables in the right spot and also we will have to remake the column panesl Hoar is holding us in the inside the bridge because they have holes everywhere in the walls | Subcontractor | Josh McPherson | false |  | true |  |  | 8 | 12 | false |  | Scissors lift boomlift forklift | false |  |  |  |  | ACM Other | 8 | 48 | [40 empty] | Taking off panels from the columns | 48
24005 | GCDC Building 2/VA1.2 | 2025-04-22 | Obed Bermudez | One crew continues working on the west elevation while the other continues working on the roof installing clips,tubes, and screen wall panels. 43 clips installed. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 10 |  |  | Boom lifts and forklift. | [5 empty] | ACM Plate Tubing | 23 | 40 | 25 | 30 | [24 empty] | 392 | 50
24009 | Cityside Subaru | 2025-04-22 | JB |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 5 | 10 | false |  | 1 forklift 2 boomlift | false |  |  |  |  | Plate Tubing |  |  | 24 | 20 | [24 empty] | 320 | 30
24020 | QTS ATL2 DC2 Osgood | 2025-04-22 | Marvin Blanco | We are needing silicone ASAP for tomorrow morning because we ask for silicone but McDougall send us the wrong color of silicone we need gray no white the guys are putting all the hours they lose waiting because in the job site it's to much going on in case McDougall said something for the hours all the work they're doing it's extra work around the opening for the pipes and we have problems with the new louvers there's two louvers but 1 it's hitting in the hole for the bracket and the other little louver it's passing the spacing joint it's kinda wrong dimensions | Subcontractor | Dillon Bowman | true | Silicone | true |  | Good condition | 4 | 12 | false |  | Boomlift | false |  |  |  |  | Other | [42 empty] | Working around the pipes with the stanley steel flat sheets and also checking the dimensions for the louvers | 48
24025 | Madison Elementary | 2025-04-22 | Rudy Pineda |  | Subcontractor | Wylie McDougall | false |  | false |  |  | 3 | 8 | false |  | 1 boom | false |  |  |  |  | Caulking Flashing Single Skin Trim | [7 empty] | 8 | [13 empty] | 8 | [11 empty] | 4 |  |  |  | 4
24048 | QTS NAL2 DC1 | 2025-04-22 | Marvin Blanco | Trying to work in the screenwall on this project but it's kinda Osgood it's to much things going on there's no space for anyone everywhere are cranes lifting materials but the guys are trying to install the hats channels in the screenwall but the super it's complaining about the material we have to much materials in the job site and we need to put it in the roof | Subcontractor | Joe Hoyle | false |  | true |  |  | 6 | 10 | false |  | Boomlift | false |  |  |  |  | Other | [42 empty] | Zs in the screenwall | 60
24048 | QTS NAL2 DC1 | 2025-04-22 | Antonio Sanchez | Corrugated rib panel | Subcontractor | Joe Hoyle | false |  | true |  |  | 6 | 1 | false |  |  | false |  |  |  |  | Corrugated / Screen wall Trim | [22 empty] | 14 | 40 | [12 empty] | 350 | 20
23029 | BNA Concourse D | 2025-04-21 | Tony | Today was a rain out | JWMCD Crew | Marc Ribar | true | Rain out |  |  | Thunder storms | 1 | 1 | false |  |  | false
24001 | McEwen Northside | 2025-04-21 | Marvin Blanco |  | Subcontractor | Josh McPherson | false |  | false |  |  | 9 | 5 | false |  | Scissors lift boomlift forklift | false |  |  |  |  | Other | [42 empty] | The guys couldn't work today because the rain but we hope tomorrow will be a good day for everyone | 45
24005 | GCDC Building 2/VA1.2 | 2025-04-21 | Obed Bermudez | One crew continues working on the west elevation, while another crew spent the day unloading screen wall panels and getting them up to the roof. | JWMCD Crew | Joe Hoyle | [5 empty] | 8 | 10 | true | We received a delivery of screen wall panels and another delivery of caulking. | Boom lifts and forklift. | [5 empty] | ACM Hat Channel Tubing | 13 | 29 | [26 empty] | 196 | 10 |  |  |  |  | 30 | 1
24009 | Cityside Subaru | 2025-04-21 | JB |  | Subcontractor | Chris Buttrey | false |  | false |  |  | 5 | 9.5 | true |  | 2 boomlift and 1 forklift | false |  |  |  |  | Perforated Plate Tubing |  |  | 24 | 19 | [24 empty] | 228 | 28.5
24025 | Madison Elementary | 2025-04-21 | Rudy Pineda |  | Subcontractor | Wylie McDougall | false |  | false |  |  | 3 | 8 | false |  | 1 boom | false |  |  |  |  | Flashing Hat Channel Trim | [33 empty] | 8 |  | 8 |  | 8
24048 | QTS NAL2 DC1 | 2025-04-21 | Antonio Sanchez | Corrugated rib panel | Subcontractor | Joe Hoyle | true | Whether conditions | true |  | Winds and rain | 4 | 10 | true | Louver blade |  | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 10 | 40
24015 | New Pope School | 2025-04-19 | Rafael Gomez |  | Subcontractor | Wylie McDougall | false |  | false |  |  | 4 | 8 | false |  | 2 boom lifts | false |  |  |  |  | Coping | [40 empty] | 350 | 8
24048 | QTS NAL2 DC1 | 2025-04-19 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 4 | 20 | false |  | Scaffold | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 19 | 40
23029 | BNA Concourse D | 2025-04-18 | Tony | Installed coping while waiting for more areas to be ready to install panels | JWMCD Crew | Marc Ribar | true | Flat strap not installed on the wall of the record note, also bottom of record note has not been waterproofed yet so I can’t install bottom of panels |  |  | Thunder storms | 4 | 8 | false |  | 4 man lifts and a lull | false |  |  |  |  | Coping | [40 empty] | 230 | 8
24015 | New Pope School | 2025-04-18 | Rafael Gomez |  | Subcontractor | Wylie McDougall | false |  | false |  |  | 4 | 10 | false |  | 2 boom lifts | false |  |  |  |  | Coping | [40 empty] | 300 | 10
24048 | QTS NAL2 DC1 | 2025-04-18 | Antonio Sanchez |  | Subcontractor | Joe Hoyle | false |  | false |  |  | 4 | 10 | false |  |  | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 20 | 40
24001 | McEwen Northside | 2025-04-17 | Marvin Blanco | Working in the bridge with bellara panels and ACM panels tomorrow the guys will be done with a couple of areas but the guys are waiting for Hoar to cover a lot of holes in the wall that is holding my guys to start inside the bridge | Subcontractor | Josh McPherson | false |  |  |  |  | 8 | 12 | false |  | Scissors lift boomlift forklift | false |  |  |  |  | ACM Other | 15 | 60 | [40 empty] | Bellara panels | 36
24005 | GCDC Building 2/VA1.2 | 2025-04-17 | Obed Bermudez | One crew continues installing clips and tubes, while another crew continues installing perforated panels on the screen wall. The third crew is installing ACM panels on the west elevation. There’s an issue preventing me from reporting the number of perforated panels in the daily reports. | JWMCD Crew | Joe Hoyle | [5 empty] | 9 | 10 |  |  | Boom lift. | [5 empty] | ACM Hat Channel Perforated | 24 | 28 | [32 empty] | 30 | 2
24015 | New Pope School | 2025-04-17 | Rafael Gomez | We started to install coping on area 412 and we completed the 4 corners in the roof areas ! | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 2 booms lift | false |  |  |  |  | Coping Corrugated / Screen wall Other Trim | [22 empty] | 8 | 10 | [12 empty] | 30 | 10 |  |  | 117 | 10 | Cleat | 10
24025 | Madison Elementary | 2025-04-17 | Rudy Pineda |  | Subcontractor | Wylie McDougall | false |  | false |  |  | 3 | 8 | false |  | 1 boom | false |  |  |  |  | Caulking Insulation Single Skin Subgirt Zee Trim | [7 empty] | 5 | [13 empty] | 5 | [5 empty] | 5 |  |  |  | 5 | [5 empty] | 5
24048 | QTS NAL2 DC1 | 2025-04-17 | Antonio Sanchez | Penhause rib panel | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 10 | false |  |  | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 20 | 40
23029 | BNA Concourse D | 2025-04-16 | Zarur Nazario Padron Jr | Installing coping on rooftop Connector side and fabricating/installing panels on concessions rooftop | JWMCD Crew | Marc Ribar | false |  |  |  |  | 4 | 32 | false |  | 65’ boomlift | false |  |  |  |  | Coping Flashing IMP | [8 empty] | 4 | 14 | [10 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 8 | 2 | [6 empty] | 70 | 16
24001 | McEwen Northside | 2025-04-16 | Marvin Blanco | Working inside the bridge installing the ACM panels and also working with the bellara panels installing flat metal for attachment cleaning our areas | Subcontractor | Josh McPherson | false |  |  |  |  | 9 | 12 | false |  | Boomlift scissors lift and forklift | false |  |  |  |  | ACM | 18 | 108
24005 | GCDC Building 2/VA1.2 | 2025-04-16 | Obed Bermudez | One crew continues installing clips and tubes, while another crew continues installing perforated panels on the screenwall. The third crew continues installing ACM panels at the west elevation. There's an issue where I can't report the number of perforated panels. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 10 |  |  | Boom lifts and forklift. | [5 empty] | ACM Hat Channel Other Tubing | 20 | 25 | [26 empty] | 378 | 30 |  |  |  |  | 60 | 5
24015 | New Pope School | 2025-04-16 | Rafael Gomez | We installed coping in area 401 | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 2 boom lifts | false |  |  |  |  | Coping Other | [40 empty] | 82 | 10 | Cleap 160 linear ft | 10
24020 | QTS ATL2 DC2 Osgood | 2025-04-16 | Marvin Blanco | Working in the extra work installing Zs insulation and flats sheets of stanley steel around the pipes | Subcontractor | Dillon Bowman | true | Flashing for the top of those flat sheets, silicone, Zs |  |  | Good condition | 4 | 12 | false |  | Boomlift | false |  |  |  |  | Other | [42 empty] | Installing flat sheet of stanley steel | 48
24025 | Madison Elementary | 2025-04-16 | Rudy Pineda |  | Subcontractor | Wylie McDougall | false |  | false |  |  | 3 | 8 | false |  | 2 booms | false |  |  |  |  | AWB Caulking Single Skin Subgirt Zee | [7 empty] | 8 | [13 empty] | 4 | [9 empty] | 4 | [7 empty] | 4
24046 | UAB Biomedical Research and Psycholgy | 2025-04-16 | Naza Padron | 12 hours cleaning wood from creates | JWMCD Crew | Wylie McDougall | true |  |  |  |  | 4 |  | false |  | 65' boom | false |  |  |  |  | Other | [20 empty] | 34 | 28 | [21 empty] | 12
24048 | QTS NAL2 DC1 | 2025-04-16 | Antonio Sanchez | Stock rib panel on the roof | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 10 | true |  |  | false |  |  |  |  | Corrugated / Screen wall
24068 | QTS NAL1 DC2 | 2025-04-16 | Marvin Blanco | Taking layout for the ACM panels in top of the steel but in the job site it's not ready it's to much steel messing horizontal and vertical for us start installing the 4" Zs and hats channels both stairs are the same missing steel | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 10 | true | ACM panels Zs and hats | Boomlift | false |  |  | 40 |  | Layout
23029 | BNA Concourse D | 2025-04-15 | Zarur Nazario Padron Jr | Installing Panels and coping on connector side rooftop. Also getting measurements for coping on Concessions and Record circle 6 hours. Cutting out holes for badge scan on section D6,7 (6 hours). | JWMCD Crew | Marc Ribar | false |  |  |  |  | 8 | 60 | false |  | Boomlift 65’ | false |  |  |  |  | Coping IMP | [8 empty] | 3 | 12 | [10 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | [8 empty] | 50 | 32
24001 | McEwen Northside | 2025-04-15 | Marvin Blanco | Hoar is holding up my guys because they're not ready for the inside of the bridge they're opening holes everywhere in case McDougall and Hoar are saying that we are behind, there is proof because the only thing they know how to say is that we are behind, but they don't realize the mistakes you are making. | Subcontractor | Josh McPherson | false |  |  |  |  | 9 | 12 | false |  | Scissors lift boomlift forklift | false |  |  |  |  | ACM | 23 | 108
24001 | McEwen Northside | 2025-04-15 | Marvin Blanco | Installing ACM panels around the windows and also remaking panels for the north elevation we have a couple of issues in the panels not lining up with the joints so if that comes out in the punch list we will fix those issues | Subcontractor | Josh McPherson | false |  |  |  |  | 11 | 12 | false |  | Scissors lift boomlift forklift | false |  |  |  |  | ACM | 22 | 132
24005 | GCDC Building 2/VA1.2 | 2025-04-15 | Obed Bermudez | The first crew, consisting of three guys, is lifting screen wall material to the roof. The second crew is installing ACM panels on the west elevation, and the third crew is working on the screen wall, installing tubes. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 10 |  |  | Boom lifts and forklift. | [5 empty] | ACM Hat Channel Tubing | 20 | 25 | [26 empty] | 742 | 60 |  |  |  |  | 60 | 5
24015 | New Pope School | 2025-04-15 | Rafael Gomez | We keep working on area 402 | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 2 boom lifts | false |  |  |  |  | Corrugated / Screen wall Subgirt Zee | [22 empty] | 30 | 10 | [6 empty] | 200 | 10
24025 | Madison Elementary | 2025-04-15 | Rudy Pineda |  | Subcontractor | Wylie McDougall | false |  | false |  |  | 4 | 8 | false |  | 2 booms | false |  |  |  |  | Caulking Flashing Insulation Single Skin Subgirt Zee | [7 empty] | 8 | [13 empty] | 8 | [5 empty] | 4 |  |  |  | 8 |  | 4
24046 | UAB Biomedical Research and Psycholgy | 2025-04-15 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | true |  |  |  |  | 4 | 40 | false |  | 65' boom | false |  |  |  |  | ACM | 13 | 40
24048 | QTS NAL2 DC1 | 2025-04-15 | Antonio Sanchez | Install trim penhause | Subcontractor | Joe Hoyle | true | To much Winds |  |  | Rain and wind | 4 | 10 | true | Louvers |  | false |  |  |  |  | Trim | [36 empty] | 90 | 40
23029 | BNA Concourse D | 2025-04-14 | Zarur Nazario Padron Jr | Installing and fabricating IMP panels on Rooftop Elevation 228 and doing layout for 2 hours | JWMCD Crew | Marc Ribar | false |  |  |  |  | 4 | 32 | false |  | 65’ boomlift | false |  |  |  |  | Flashing IMP Other | [8 empty] | 10 | 22 | [10 empty] | 0 | 0 | 0 | 0 | [6 empty] | 8 | 3 | 0 | 0 | [9 empty] | 2
24001 | McEwen Northside | 2025-04-14 | Marvin Blanco | Working in the north elevation installing the columns panels remaking panels for the north elevation and also inside the bridge remaking panels because they're to longer in the side of the windows were McDougall get confused with the dimensions | Subcontractor | Josh McPherson | false |  |  |  |  | 11 | 12 | true | A laser for the columns | Boomlift forklift and scissors lift | false |  |  |  |  | ACM | 26 | 132
24005 | GCDC Building 2/VA1.2 | 2025-04-14 | Obed Bermudez | One crew of 4 spent the day lifting screen wall material to the roof. The second crew continued working on the west elevation with ACM panel installation, and the third crew continued installing clips and tubes on the screen wall. | JWMCD Crew | Joe Hoyle | [5 empty] | 12 | 10 | true | Glass material for the security room and screen wall material. | Boom lifts and forklift | [5 empty] | ACM Tubing | 7 | 30 | [26 empty] | 210
24015 | New Pope School | 2025-04-14 | Rafael Gomez | We start cleaning the area ,so we can start working on installation on area 402 | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | true | Copping,zee,flashing | 2boom lifts | false |  |  |  |  | Corrugated / Screen wall Subgirt Zee | [22 empty] | 20 | 8 | [6 empty] | 2 | 80
24020 | QTS ATL2 DC2 Osgood | 2025-04-14 | Marvin Blanco | Working in a complicated area because the safety in this job is kada hard also we are needing a lot of silicone because all the stanley steel panels and screws are taking silicone around the concrete and Also around the pipes so I hope tomorrow McDougall can send a 8 boxes 📦 | Subcontractor | Dillon Bowman | true | Silicone |  |  | Good condition | 4 | 12 | false |  | Boomlift | false |  |  |  |  | Other | [42 empty] | Stanley steel flat sheets | 48
24025 | Madison Elementary | 2025-04-14 | Rudy Pineda |  | Subcontractor | Wylie McDougall | false |  | false |  |  | 4 | 8 | false |  | 2 booms | false |  |  |  |  | Caulking Flashing Insulation Single Skin Subgirt Zee | [7 empty] | 8 | [13 empty] | 8 | [5 empty] | 8 |  |  |  | 4 |  | 4
24025 | Madison Elementary | 2025-04-14 | Rudy Pineda | install insulation and panels east elevation install panels south elevation caulking all.over | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 7 | false |  | 2 booms | false |  |  |  |  | Caulking Insulation Single Skin | [7 empty] | 14 | [13 empty] | 7 | [5 empty] | 7
24046 | UAB Biomedical Research and Psycholgy | 2025-04-14 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 4 | 40 | false |  | 65' boom | false |  |  |  |  | ACM Caulking Insulation Subgirt Zee | 4 | 24 | [18 empty] | 30 | 8 |  |  |  |  | 80 | 4 |  |  | 20 | 4
24048 | QTS NAL2 DC1 | 2025-04-14 | Antonio Sanchez | West elevation | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 10 | false |  |  | false |  |  |  |  | Hat Channel | [34 empty] | 80
23029 | BNA Concourse D | 2025-04-12 | Antonio | We installed panels on D9 clearstory | JWMCD Crew | Marc Ribar | true | Frame was not in area needed |  |  |  | 6 | 8 | false |  | 4 man lifts a lull | false |  |  |  |  | IMP | [8 empty] | 40 | 48
24025 | Madison Elementary | 2025-04-12 | Rudy Pineda | east elevation panels and insulation south elevation panels and insulation | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 5 | false |  | 2 booms | false |  |  |  |  | Insulation Single Skin | [7 empty] | 10 | [19 empty] | 10
23029 | BNA Concourse D | 2025-04-11 | Zarur Nazario Padron Jr | Working on installing ACM panels on Concessions Northside roof and taking off plastic, installing IMP panels on Connector sector D5 | JWMCD Crew | Marc Ribar | false |  |  |  |  | 8 | 80 | false |  | Scaffold, 65’ Boomlift | false |  |  |  |  | ACM IMP Subgirt Zee | 12 | 40 | [6 empty] | 18 | 36 | [10 empty] | 0 | 0 | 0 | 0 | [6 empty] | 33 | 4
24005 | GCDC Building 2/VA1.2 | 2025-04-11 | Obed Bermudez |  | JWMCD Crew | Joe Hoyle | true |  |  |  | Rainy day. | 11 | 10 | true | We received and unloaded two deliveries of screen wall panels. | Boom lifts and forklift. | [5 empty] | ACM Tubing | 16 | 32 | [26 empty] | 224 | 12
24025 | Madison Elementary | 2025-04-11 | Rudy Pineda | east elevation panels and insulation, south elevation panels and insulation | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 7 | false |  | 2 booms | false |  |  |  |  | Insulation Single Skin
23029 | BNA Concourse D | 2025-04-10 | Antonio | We installed panels on the preexisting wall on landside connector | JWMCD Crew | Marc Ribar | true | A storm rolled in |  |  | Stormy | 4 | 8 | false |  | 4 man lifts a lull | false |  |  |  |  | Flashing IMP | [8 empty] | 22 | 32 | [22 empty] | 34 | 4
23029 | BNA Concourse D | 2025-04-10 | Zarur Nazario Padron Jr | Re-installing and fixing up flashing under the windows from connector on D5 all the way to concessions. Installing coping per Jimmy from HP’s order | JWMCD Crew | Marc Ribar | true | We were delayed on working on the flashing under windows due to pouring of concrete and excavation and also other lifts were being operated there for 5 hours. |  |  | Sunny | 3 | 33 | false |  | 65’ boomlift | false |  |  |  |  | Coping Flashing | [20 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 324 | 30 | [6 empty] | 20 | 3
24005 | GCDC Building 2/VA1.2 | 2025-04-10 | Obed Bermudez | One crew continues working on the west elevation, installing ACM panels, while another crew is working on the roof, installing clips and tubes for the screen wall. We also cleaned up empty boxes. | JWMCD Crew | Joe Hoyle | [5 empty] | 11 | 10 | true | We received a delivery of glass material (caulking) and ply wood and foam for the roof protection. | Boom lifts and forklift | [5 empty] | ACM Tubing | 11 | 50 | [26 empty] | 420 | 60
23029 | BNA Concourse D | 2025-04-09 | Zarur Nazario Padron Jr | Installing and removing flashing on Connector near D5, installing coping on southside of Concessions | JWMCD Crew | Marc Ribar | false |  |  |  |  | 6 | 50 | false |  | 2- 65’ boomlifts | false |  |  |  |  | Coping Flashing | [20 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 50 | 10 | [6 empty] | 340 | 40
24001 | McEwen Northside | 2025-04-09 | Marvin Blanco | Remaking panels for the bridge in the north elevation and also cleaning our areas of material reinstalling 4 panels in the south elevation because we take those panels down for the sprinklers guys that's a change of order | Subcontractor | Josh McPherson | false |  |  |  |  | 10 | 12 | false |  | Scissors lift boomlift forklift | false |  |  |  |  | ACM | 13 | 120
24005 | GCDC Building 2/VA1.2 | 2025-04-09 | Obed Bermudez | We continue working on the west elevation, with panel installation and another crew on the roof doing layout and clips. | JWMCD Crew | Joe Hoyle | [5 empty] | 10 | 10 | true | Glass material. | Boom lifts and forklift. | [5 empty] | ACM | 8 | 50
24020 | QTS ATL2 DC2 Osgood | 2025-04-09 | Marvin Blanco | We lose 7 hours waiting for the soffit to be ready 4 guys because Hitt wasn't ready to install the panels | Subcontractor | Dillon Bowman | true | Electric guys working in the soffit |  |  | Good condition | 4 | 12 | true | Plasma cutting | Scissors lift boomlift | false |  |  |  |  | ACM | 4 | 48
24025 | Madison Elementary | 2025-04-09 | Rudy Pineda | east elevation panels and insulation, south elevation panels and insulation | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 7 | false |  | 2 booms | false |  |  |  |  | Insulation Single Skin | [7 empty] | 14 | [19 empty] | 14
24048 | QTS NAL2 DC1 | 2025-04-09 | Antonio Sanchez | Install hat channel | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 11 | false |  | Forklift, boomlift | false |  |  |  |  | Hat Channel | [34 empty] | 100 | 40
23029 | BNA Concourse D | 2025-04-08 | Antonio | Installed panels on the connector ( landside at night ) | JWMCD Crew | Marc Ribar | true |  |  |  |  | 8 | 8 | false |  | 4 man lifts and a lull | false |  |  |  |  | Flashing IMP | [8 empty] | 38 | 64 | [22 empty] | 200 | 12
23029 | BNA Concourse D | 2025-04-08 | Zarur Nazario Padron Jr | Installing Coping on rooftop between Concessions and the Connector | JWMCD Crew | Marc Ribar | false |  |  |  |  | 5 | 50 | false |  | 65’ boomlift | false |  |  |  |  | Coping | [20 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | [8 empty] | 210 | 50
24005 | GCDC Building 2/VA1.2 | 2025-04-08 | Obed Bermudez | We continue working on the west elevation, and got another crew to start layout on roof for screen wall. | JWMCD Crew | Joe Hoyle | [5 empty] | 10 | 10 |  |  | Boom lifts and fork lift | [5 empty] | ACM | 17
24020 | QTS ATL2 DC2 Osgood | 2025-04-08 | Marvin Blanco | Modifying panels because they're with wrong dimensions trying to finish the inside panels | Subcontractor | Dillon Bowman | false |  |  |  |  | 4 | 12 | false |  | Scissors lift boomlift | false |  |  |  |  | ACM | 8 | 48
24025 | Madison Elementary | 2025-04-08 | Rudy Pineda | install Z girt insulation and panels @ area east and south | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 7 | false |  | 2 booms | false |  |  |  |  | Insulation Single Skin Subgirt Zee | [7 empty] | 7 | [19 empty] | 7 |  |  |  | 14
23029 | BNA Concourse D | 2025-04-07 | Antonio | Installed panels on connector landside next to loading dock. Also walked with Jimmy and CI about an issue they have with waterproofing. They are asking for our flashing to be lowered so they can drill a new weep hole | JWMCD Crew | Marc Ribar | false |  |  |  |  | 10 | 10 | false |  |  | false |  |  |  |  | IMP | [8 empty] | 43 | 430
24001 | McEwen Northside | 2025-04-07 | Marvin Blanco | Making a lot of panels for the east side and also for the bridge because almost all the panels are wrong so it's taking a lot of time for installing panels cleaning our areas and moving material | Subcontractor | Josh McPherson | false |  |  |  |  | 12 | 12 | true | Flats sheets | Scissors lift boomlift forklift | false |  |  |  |  | ACM | 20 | 144
24005 | GCDC Building 2/VA1.2 | 2025-04-07 | Obed Bermudez | We arrived at the Job site but couldn't work due to bad weather | JWMCD Crew | Joe Hoyle | true |  |  |  | Bad weather rainy day
24020 | QTS ATL2 DC2 Osgood | 2025-04-07 | Marvin Blanco | modifying panels because they were with the wrong dimensions also the guys try to work in the ceiling with the ACM panels but it's not ready | Subcontractor | Dillon Bowman | false |  |  |  |  | 4 | 12 | false |  | Boomlift | false |  |  |  |  | ACM | 10 | 48
24025 | Madison Elementary | 2025-04-07 | Rudy Pineda | panels insulation and z girts @ son south and east elevation | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 7 | false |  |  | false |  |  |  |  | Insulation Single Skin Subgirt Zee | [7 empty] | 7 | [19 empty] | 7 |  |  |  | 14
24005 | GCDC Building 2/VA1.2 | 2025-04-05 | Obed Bermudez | The whole crew worked on bringing material up to the roof. | JWMCD Crew | Joe Hoyle | [5 empty] | 8 | 8 |  |  | 3 Boom lifts and 1 forklift.
24025 | Madison Elementary | 2025-04-05 | Rudy Pineda | south elevation and east elevation, install head flashing @ east elevation install panels @ south elevation | Subcontractor | Wylie McDougall | false |  |  |  |  | 2 | 5 | false |  | 2 booms | false |  |  |  |  | AWB Hat Channel Single Skin | [7 empty] | 4 | [26 empty] | 2 | 1 |  |  | 3
23029 | BNA Concourse D | 2025-04-04 | Antonio | We installed flashing and panels on the landside of the connector | JWMCD Crew | Marc Ribar | false |  |  |  |  | 10 | 10 | false |  |  | false |  |  |  |  | Flashing IMP | [8 empty] | 18 | 100 | [22 empty] | 260 | 8
24005 | GCDC Building 2/VA1.2 | 2025-04-04 | Obed Bermudez | We are continuing work on the west elevation, installing panels and lifting the screen wall material up to the roof. | JWMCD Crew | Joe Hoyle | [5 empty] | 9 | 11 | true | We received and unloaded a delivery of screen wall panels and started lifting the pallets up to the roof. | Boom lifts and forklift. | [5 empty] | ACM | 27 | 99
24013 | VA 14.2 | 2025-04-04 | Fredy veliz | Job completed | Subcontractor | Chris Buttrey | [5 empty] | 4 | 6 |  |  | 2 boom lifts | [5 empty] | ACM Other | 12 | 1 | [40 empty] | Installing trim around the door and between the building | 12
24018 | QTS-NAL1-DC1 | 2025-04-04 | Saul chicas | We finished to install the coping on the penthouse we also installed the corners and end flashing | Subcontractor | Joe Hoyle | [5 empty] | 5 | 10 |  |  | Scaffold/ boom lift | [5 empty] | Coping Flashing | [32 empty] | 70 | 10 | [6 empty] | 80 | 10
24025 | Madison Elementary | 2025-04-04 | Rudy Pineda | east elevation openings, insulation z girt and panels. south elevation insulation and channel | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 7 | false |  | 2 booms | false |  |  |  |  | Hat Channel Insulation Single Skin Subgirt Zee | [7 empty] | 14 | [19 empty] | 3 |  |  | 4
23029 | BNA Concourse D | 2025-04-03 | Antonio | It was a rain out | JWMCD Crew | Marc Ribar | true | Rain out |  |  | Thunder storms | 1 | 0 | false |  |  | false
24001 | McEwen Northside | 2025-04-03 | Marvin Blanco | Making panels to finish the east elevation because the panels are wrong dimensions and also working in the bridge installing the sides panels the guys couldn't work well because to much rain | Subcontractor | Josh McPherson | false |  |  |  |  | 12 | 12 | false |  | Scissors lift boomlift forklift | false |  |  |  |  | ACM | 19 | 144
24005 | GCDC Building 2/VA1.2 | 2025-04-03 | Obed Bermudez | We continue working on the west elevation, with panel installation. | JWMCD Crew | Joe Hoyle | [5 empty] | 9 | 10 |  |  | Boom lifts and forklift. | [5 empty] | ACM | 42 | 90
24013 | VA 14.2 | 2025-04-03 | Fredy veliz | We are almost done all the panels area on except for the one that was missing that is gonna be delivery and install tomorrow | Subcontractor | Chris Buttrey | [5 empty] | 4 | 8 |  |  | 2 boom lifts | [5 empty] | ACM | 8 | 8
24018 | QTS-NAL1-DC1 | 2025-04-03 | Saul chicas | Crew1 2 guys Installing coping on the penthouse Crew2 2 guys Working on the fend red panels It was a windy and rain day so we are doing what we can | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Scaffold /boom lift | [5 empty] | Coping | [40 empty] | 80 | 10
24025 | Madison Elementary | 2025-04-03 | Rudy Pineda | south elevation channel, East elevation z girt insulation panels | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 7 | false |  | 2 booms | false |  |  |  |  | Hat Channel Insulation Single Skin Subgirt Zee | [7 empty] | 6 | [19 empty] | 4 |  |  |  | 4 |  |  |  | 7
24025 | Madison Elementary | 2025-04-03 | Rudy Pineda | east elevation z girts flashing and caulking. access 28 213 caulking and trim | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 7 | false |  |  | false |  |  |  |  | Caulking Flashing Subgirt Zee | [21 empty] | 4 | [9 empty] | 14 |  | 3
23029 | BNA Concourse D | 2025-04-02 | Antonio | Removed pre existing panels on airside, and reinstalled them | JWMCD Crew | Marc Ribar | false |  |  |  |  | 10 | 10 | false |  |  | false |  |  |  |  | IMP | [8 empty] | 29 | 100 | [34 empty] | 2025-04-02 |  | 1d
24001 | McEwen Northside | 2025-04-02 | Marvin Blanco | Working in the east side installing ACM panels also cutting a couple of holes for Hoar we have to remake 6 panels for the east side to finish the east side | Subcontractor | Josh McPherson | false |  |  |  |  | 13 | 13 | false |  | Scissors lift boomlift forklift | false |  |  |  |  | ACM | 23 | 169
24005 | GCDC Building 2/VA1.2 | 2025-04-02 | Obed Bermudez | 1 crew of 5 guys took down 9 panels and Z-girt to move the flashing up due to the gap between the precast and base flashing, then reinstalled them on a 10 hour day. | JWMCD Crew | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lifts and forklift | [5 empty] | ACM | 30 | 80
24013 | VA 14.2 | 2025-04-02 | Fredy veliz | Upper elevation almost complete waiting on missing panel to be delivered | Subcontractor | Chris Buttrey | [5 empty] | 4 | 8 |  |  | 2 boom lift | [5 empty] | ACM Other | 4 | 24 | [40 empty] | Peel of panels, modify panels | 8
24018 | QTS-NAL1-DC1 | 2025-04-02 | Saul chicas | Crew1 2 guys Working on the north canopy we reinstall the cornel panel and modify the next the is going to the roof. Crew2 Installing the crips for the coping on the penthouse | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift / scaffold | [5 empty] | Coping | [40 empty] | 60 | 10
23029 | BNA Concourse D | 2025-04-01 | Antonio | Installed panels around ladder locations and clear story and did a big site clean up | JWMCD Crew | Marc Ribar | false |  |  |  |  | 5 | 8 | false |  | 4 man lifts and a lull | false |  |  |  |  | Flashing IMP | [8 empty] | 12 | 40 | [22 empty] | 3 | 1
24005 | GCDC Building 2/VA1.2 | 2025-04-01 | Obed Bermudez | We continue working on the west elevation, with panel installation and cleaning up empty boxes. | JWMCD Crew | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lifts and forklift. | [5 empty] | ACM | 33 | 80
24013 | VA 14.2 | 2025-04-01 | Fredy veliz | Missing one panel | Subcontractor | Chris Buttrey | [5 empty] | 4 | 8 |  |  | 2 boom lifts | [5 empty] | ACM | 7 | 32
24018 | QTS-NAL1-DC1 | 2025-04-01 | Saul chicas | Doing caulking on the vestibule inside and outside We made the panel for the stairs well and we installed | Subcontractor | Joe Hoyle | [5 empty] | 3 | 8 |  |  | Boom lift | [5 empty] | ACM Caulking | 1 | 8 | [18 empty] | 90 | 8
24025 | Madison Elementary | 2025-04-01 | Rudy Pineda | install Z girts and insulation at openings on east elevation | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 7 | false |  | 2 booms | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 100 | 7 |  |  | 70 | 14
24001 | McEwen Northside | 2025-03-31 | Marvin Blanco | Working in the north east corner and also east elevation finishing the panels by the bridge we have a little issue with the panels in the lower flat wall panels north east side in the other column south east the guys couldn't finish because Hoar guys give the area to others guys | Subcontractor | Josh McPherson | false |  |  |  |  | 13 | 13 | true | Flats sheets | Scissors lift boomlift forklift | false |  |  |  |  | ACM | 26 | 169
24005 | GCDC Building 2/VA1.2 | 2025-03-31 | Obed Bermudez | We continue working on the west elevation, and found issues with panels being too short and crating a gap of 2" between panel and precast we spoke to Joe and the engineering team that tomorrow we will remove 7 to 10 panels and lift up the flashing about 1". And we also did layout so the electricians can star moving the lights that are in the wrong spots. | JWMCD Crew | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift and forklift. | [5 empty] | ACM | 8
24013 | VA 14.2 | 2025-03-31 | Fredy veliz | Trying to get done this week but the delivery's may not let us finish today we had to work with electrician and Camera guys to install the panels in the lower area had to modify a panel the was to big | Subcontractor | Chris Buttrey | [5 empty] | 4 | 8 |  |  | 2 boom lift | [5 empty] | ACM | 6 | 32
24025 | Madison Elementary | 2025-03-31 | Rudy Pineda | area c panels | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 7 | false |  | 2 booms | false |  |  |  |  | Single Skin | [7 empty] | 21
24025 | Madison Elementary | 2025-03-31 | Rudy Pineda | area c panels | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 7 | false |  | 2 booms | false |  |  |  |  | Single Skin | [7 empty] | 21
24018 | QTS-NAL1-DC1 | 2025-03-30 | Saul chicas | We removed the protection from the freedom wall 2 hours | Subcontractor | Joe Hoyle | [5 empty] | 2 | 2 |  |  | Boom lift | [5 empty] | ACM | 0 | 2
24005 | GCDC Building 2/VA1.2 | 2025-03-29 | Obed Bermudez | We spend the day getting screen wall panels up to the roof using the hoist. | JWMCD Crew | Joe Hoyle | [5 empty] | 7 | 56 |  |  | Boom lift and forklift | [5 empty] | ACM | 6
24018 | QTS-NAL1-DC1 | 2025-03-29 | Saul chicas | We removed 4 panels on the freedom wall and reinstalled 7 panels, 30 LF of caulking on the freedom wall as well | Subcontractor | Joe Hoyle | [5 empty] | 3 | 6 |  |  | Boom lift | [5 empty] | ACM Caulking | 7 | 6 | [18 empty] | 30 | 6
24025 | Madison Elementary | 2025-03-29 | Rudy Pineda | single skin | Subcontractor | Wylie McDougall | false |  |  |  |  | 2 | 8 | false |  | 2 booms | false |  |  |  |  | Trim
23029 | BNA Concourse D | 2025-03-28 | Antonio | One crew installed the bottom imp of landside concession. Crew 2 installed panels on clearstory roof and fabricated the holes for the ladder brackets also removed a wall of panels in order to install a new EXTRA row below crew number 3 installed imp panels next to concessions corners land side. Crew number 4 caulked the flashing s around expansion joints after they finished installing the vent flashing on concessions | JWMCD Crew | Marc Ribar | false |  |  |  |  | 14 | 12 | true | Two panel remakes for BNA | Four man lifts and a lull | false |  |  |  |  | Caulking Flashing IMP | [8 empty] | 60 | 12 | [10 empty] | 80 | 4 | [10 empty] | 1200 | 4
24005 | GCDC Building 2/VA1.2 | 2025-03-28 | Obed Bermudez |  | JWMCD Crew | Joe Hoyle | [5 empty] | 8 | 10 | true | We received and unloaded two trucks of panels and another delivery of insulation and plywood for the screen wall. | Boom lift and forklift | [5 empty] | ACM | 32 | 80
24013 | VA 14.2 | 2025-03-28 | Fredy veliz | N/A | Subcontractor | Chris Buttrey | [5 empty] | 4 | 32 |  |  | 2 boom lift | [5 empty] | ACM | 4 | 32
24013 | VA 14.2 | 2025-03-28 | Fredy veliz | We only been installed 4 panels a day because delay with delivery on the area | Subcontractor | Chris Buttrey | [5 empty] | 4 | 8 |  |  | 2 boom lift | [5 empty] | ACM | 4 | 32
24015 | New Pope School | 2025-03-28 | Rafael gomez | We continue working on elevation 402, we are short on perforated panels ! | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 2 boom lifts | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 40 | 10
24018 | QTS-NAL1-DC1 | 2025-03-28 | Saul chicas | No works today due to the bad weather | Subcontractor | Joe Hoyle | true | Raining all day |  |  | Bad weather | 1 | 0 |  |  | Boom lift | [5 empty] | ACM |  | 0
24025 | Madison Elementary | 2025-03-28 | Rudy Pineda | insulation z girt | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 8 | false |  | 2 booms | false |  |  |  |  | Flashing Hat Channel Insulation Subgirt Zee
24025 | Madison Elementary | 2025-03-28 | Rudy Pineda | finish opening #15 and repairs @ courtyard | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 7 | false |  | 2 boom lifts | false |  |  |  |  | Corrugated / Screen wall | [23 empty] | 21
24001 | McEwen Northside | 2025-03-27 | Marvin Blanco | Working in the swing stage installing the extra panels in the level 4 we finished today we are waiting for Hoar guys to put weatherproofing in the opening they did for the weather comes out the can put the panel back also working in the east side installing ACM panels with a little issue in the flat columns we are not able to finish the column in the south east corner because the concrete guys are working in that area cleaning our areas | Subcontractor | Josh McPherson | false |  |  |  |  | 14 | 12 | false |  | Scissors lift boomlift forklift | false |  |  |  |  | ACM | 28 | 168
24005 | GCDC Building 2/VA1.2 | 2025-03-27 | Obed Bermudez | We fabricated panel 201-1A39 and made it wider because the previous panel had to be cut to match the window joint on the north elevation. We are continuing work on the west elevation with panel installation. We also cleaned up empty boxes and trash. | JWMCD Crew | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift forklift | [5 empty] | ACM | 16 | 80
24005 | GCDC Building 2/VA1.2 | 2025-03-27 | Obed Bermudez | We fabricated panel 201-1A39 and made it wider because the previous panel had to be cut to match the window joint on the north elevation. We are continuing work on the west elevation with panel installation. We also cleaned up empty boxes and trash. | JWMCD Crew | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift forklift | [5 empty] | ACM | 16 | 80
24015 | New Pope School | 2025-03-27 | Rafael gonez | We continue working on elevation 402 | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | true |  | 2 boom lifts | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 50 | 10
24018 | QTS-NAL1-DC1 | 2025-03-27 | Saul chicas | We removed all the coping on the penthouse and we take it down to put it into the dumpster. We sealed all the holes and proceeded to install the new coping. 50’ LF of coping installed | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | Coping | [40 empty] | 50 | 10
24025 | Madison Elementary | 2025-03-27 | Rudy Pineda | replace flashing and install panels | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 8 | false |  | 2 booms | false |  |  |  |  | Flashing Single Skin
24001 | McEwen Northside | 2025-03-26 | Marvin Blanco | Working in the east side installing Zs, insulation and ACM panels moving plywood ti cover the concrete with insulation also working in the north elevation with the boomlift installing extra panels cleaning our areas today we don't many issues just two one panel because the electricity cable and Also taking one panels out from the roof in the west elevation for the scoper extra work | Subcontractor | Josh McPherson | false |  |  |  |  | 14 | 12 | false |  | Scissors lift boomlift forklift | false |  |  |  |  | ACM | 22 | 168
24005 | GCDC Building 2/VA1.2 | 2025-03-26 | Obed Bermudez | We continue working on the west elevation, cleaning up and installing panels. | JWMCD Crew | Joe Hoyle | [5 empty] | 8 | 10 | true | We spent the morning unloading two deliveries of panels for the west elevation. | Boom lift and forklift | [5 empty] | ACM | 17 | 80
24013 | VA 14.2 | 2025-03-26 | Fredy veliz | We are traying to get done by end of next week but we need to work more hours the office did not authorized to work extra hours this week | Subcontractor | Chris Buttrey | true | The machines work very slowly when the boom is up and we have to drive in about 20' in and out every time we need a panel we have to prep the wall there missing reveal on the panels above |  |  | Windy | 4 | 8 | true | Bottom flashings for upper area and beauty rings for the pipes | 2 boom lifts | [5 empty] | ACM Flashing | 4 | 24 | [30 empty] | 30 | 8
24013 | VA 14.2 | 2025-03-26 | Fredy veliz | Trying to get the upper elevation done by 3/28 but still having delays whit the delivery's | Subcontractor | Chris Buttrey | true | Delivery's coming to the dock and we have to stop working we where told from Hitt to stop and move when delivery need to go in that dock |  |  | Windy | 4 | 9 |  |  | 2 boom lifts | [5 empty] | ACM | 4 | 36
24015 | New Pope School | 2025-03-26 | Rafael Gomez | We continue working on elevation 402 and we continue doing the caulking | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 2 boom lifts | false |  |  |  |  | Caulking Corrugated / Screen wall | [20 empty] | 400 | 10 | 40 | 10
24018 | QTS-NAL1-DC1 | 2025-03-26 | Saul chicas | Crew1 We made 3 panels and install 6 panels Crew2 150’ of caulking | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | ACM Caulking | 6 | 10 | [18 empty] | 150 | 10
24025 | Madison Elementary | 2025-03-26 | Rudy Pineda | east elevation panels insulation and flashing rework | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 7 | false |  | 2 booms | false |  |  |  |  | Flashing Insulation Single Skin | [7 empty] | 4 | [19 empty] | 3 | [5 empty] | 14
23029 | BNA Concourse D | 2025-03-25 | Antonio | A crew ran coping on the connector finishing airside, another crew was installing the vent flashing on the concessions area. Also installed the break metal on connector and readjusted panels | JWMCD Crew | Marc Ribar | false |  |  |  |  | 10 | 10 | false |  | Four man lifts, a lull | false |  |  |  |  | Coping Flashing | [9 empty] | 100 | [22 empty] | 1800 | 10 | [6 empty] | 2200 | 10
24001 | McEwen Northside | 2025-03-25 | Marvin Blanco | installing panels in the east side of the building trying to finish by the first and also moving the 85' boomlift to the north side to work in the extra panels that we have to install moving plywood for protection of the concrete moving materialwe also have a little issue with the panels one panel is bigger and the other panel short in the sides. | Subcontractor | Josh McPherson | false |  |  |  |  | 14 | 13 | false |  | Scissors lift boomlift forklift | false |  |  |  |  | ACM | 26 | 182
24005 | GCDC Building 2/VA1.2 | 2025-03-25 | Obed Bermudez | We continue working on the west elevation, installing hat channel, z girt and panels. We also modified panel 201-1A38 and made to fit glass joint. | JWMCD Crew | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lifts and forklift | [5 empty] | ACM Hat Channel Subgirt Zee | 10 | 30 | [28 empty] | 50 | 10 |  |  | 210 | 30
24013 | VA 14.2 | 2025-03-25 | Fredy veliz | Planing on finish upper section on 3/28 | Subcontractor | Chris Buttrey | [5 empty] | 5 | 8 |  |  | 2 boom lift | [5 empty] | ACM Other | 3 | 10 | [40 empty] | Install insulation, prep all panels and install | 30
24015 | New Pope School | 2025-03-25 | rafael gomez | we start working on elevation 402 | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 2 boom lifts | false |  |  |  |  | Corrugated / Screen wall Trim | [22 empty] | 60 | 10 | [12 empty] | 60 | 10
24025 | Madison Elementary | 2025-03-25 | Rudy Pineda | east elevation flashing rework east elevation panels | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 7 | false |  | 2 booms | false |  |  |  |  | Flashing Single Skin | [7 empty] | 7 | [25 empty] | 14
24005 | GCDC Building 2/VA1.2 | 2025-03-24 | Obed Bermudez | We continue working on the west elevation, installing flat metal, hat channel, z girt, and panels. | JWMCD Crew | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Boom lifts and forklift. | [5 empty] | ACM Hat Channel Layout Subgirt Zee | 11 | 30 | [28 empty] | 120 | 20 |  |  | 80 | 10
24015 | New Pope School | 2025-03-24 | Rafael gomez | We completed elevation 401 | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | true |  | 2 boom lifts | false |  |  |  |  | Corrugated / Screen wall Trim | [22 empty] | 40 | 10 | [12 empty] | 100 | 10
24018 | QTS-NAL1-DC1 | 2025-03-24 | Saul chicas | Today we don't work due to the weather raining | Subcontractor | Joe Hoyle | true | Bad weather |  |  | Bad raining | 1 | 0 |  |  | Boom lift | [5 empty] | ACM | 0 | 0
24025 | Madison Elementary | 2025-03-24 | Rudy Pineda | no work due to weather | Subcontractor | Wylie McDougall | true | weather delay |  |  | rain | 1 | 0 | false |  | 2 booms | false |  |  |  |  | Other | [42 empty] | no work due to weather | 0
24005 | GCDC Building 2/VA1.2 | 2025-03-22 | Obed Bermudez | We continue working on the west elevation,cleaning up empty boxes, installing hat channel, flat metal and panels. | JWMCD Crew | Joe Hoyle | [5 empty] | 6 | 5 |  |  | Boom lifts and forklift. | [5 empty] | ACM Hat Channel Subgirt Zee | 8 | 30 | [28 empty] | 20 |  |  |  | 60
24015 | New Pope School | 2025-03-22 | rafael gomez | we start on elevation 401 and we are doing caulking | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 2 boomlift | false |  |  |  |  | Caulking Corrugated / Screen wall | [20 empty] | 300 | 10 | 40 | 10
24025 | Madison Elementary | 2025-03-22 | Rudy Pineda | install panels | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 5 | false |  | 2 booms | false |  |  |  |  | Insulation Single Skin Subgirt Zee Trim | [7 empty] | 5 | [18 empty] | 5 | 5
23029 | BNA Concourse D | 2025-03-21 | Antonio | We installed acm roof panels and caulked it also installed last of water proof panels land side. On connector. Also installed D9 panels | JWMCD Crew | Marc Ribar | true | Window guys didn’t have d9 area caulked had to wait on them to caulk area |  |  |  | 10 | 10 | false |  | 4 man lifts and a lull | false |  |  |  |  | ACM IMP | 17 | 10 | [6 empty] | 28 | 100 | [10 empty] | 500 | 10
24005 | GCDC Building 2/VA1.2 | 2025-03-21 | Obed Bermudez | We continue working on the west elevation, doing layout, installing hat channel, panels and cleaning up | JWMCD Crew | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Boom lifts and forklift. | [5 empty] | ACM | 26 | 60
24015 | New Pope School | 2025-03-21 | rafael gomez | we complete elevation 406 and 407 | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 2 boomlift | false |  |  |  |  | Corrugated / Screen wall Trim | [22 empty] | 80 | 10 | [12 empty] | 200 | 10
24018 | QTS-NAL1-DC1 | 2025-03-21 | Saul chicas | h Crew1 4 guys We spent 6 hours reinstalling the laminate panels at the loading dock ceiling Crew2 2 guys Installing the trim piece on the stairwell #8 | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Trim | [22 empty] | 18 | 10 | [12 empty] | 50 | 10
24025 | Madison Elementary | 2025-03-21 | Rudy Pineda | [3/21, 12:05PM] Nelson Herrera: Right now we are removing the panels from the first section to change the flashing [3/21, 11:24PM] Nelson Herrera: Here we removed the panels and we are changing the new flashing [3/21, 11:32PM] Nelson Herrera: Here in the canopy on the Roof part I had to remove the panels and the Channel because Brean arrived and told me that the roof workers were not finished | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 21 | false |  | 2 booms | false |  |  |  |  | AWB Caulking Flashing Trim | [21 empty] | 7 | [11 empty] | 7 |  |  |  | 7
23029 | BNA Concourse D | 2025-03-20 | Antonio | We installed flashing and panels on land side concessions also had another crew working on roof acm | JWMCD Crew | Marc Ribar | false |  |  |  |  | 8 | 10 | false |  | 4 man lifts and a lull | false |  |  |  |  | ACM IMP | 12 | 10 | [6 empty] | 22 | 80
24001 | McEwen Northside | 2025-03-20 | Marvin Blanco | Installing ACM panels in west elevation south elevation and east elevation fixing panels and also putting silicone in the joint | Subcontractor | Josh McPherson | false |  |  |  |  | 16 | 11 | true | 3 creates of ACM panels | Scissors lift boomlift forklift | false |  |  |  |  | ACM | 26 | 176
24005 | GCDC Building 2/VA1.2 | 2025-03-20 | Obed Bermudez | We continue doing layout and control lines for panel installation on the west elevation. | JWMCD Crew | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Forklift and boom lifts. | [5 empty] | ACM Hat Channel | 12 | 60 | [32 empty] | 140 | 20
24013 | VA 14.2 | 2025-03-20 | Fredy veliz | Keep working doing what we can do delivery's still coming | Subcontractor | Chris Buttrey | [5 empty] | 4 | 8 |  |  | 2 boom lifts | [5 empty] | Other | [42 empty] | Removing damage panels | 32
24015 | New Pope School | 2025-03-20 | rafael gomez | we star working on area 406 | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 100 | 10
24025 | Madison Elementary | 2025-03-20 | Rudy Pineda | roof panels | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 8 | false |  | 2 booms | false |  |  |  |  | Single Skin
24025 | Madison Elementary | 2025-03-20 | Rudy Pineda | Roof panels | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 7 | false |  | 2 booms | false |  |  |  |  | Single Skin
24025 | Madison Elementary | 2025-03-20 | Rudy Pineda | install Panels @ Roof canopy area | Subcontractor | Wylie McDougall | true | 1 boom lift is not working properly |  |  |  | 3 | 7 | false |  | 2 boom lift | false |  |  |  |  | Corrugated / Screen wall | [23 empty] | 21
23029 | BNA Concourse D | 2025-03-19 | Antonio | We installed panels in the D8 D9 area airside. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 8 | 10 | false |  | 4 man lifts and a lull | false |  |  |  |  | IMP | [8 empty] | 32 | 80
24005 | GCDC Building 2/VA1.2 | 2025-03-19 | Obed Bermudez | We are continuing work on the west elevation with panel installation. I spoke with Ian (HITT superintendent) about the gaps between the face cap and the wall that are not sealed. He asked us not to install those panels until the gaps are sealed. The glass installer also requested that we not install one of the soffit panels because he needs to replace a broken glass panel on the west elevation. | JWMCD Crew | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Boom lifts and forklifts. | [5 empty] | ACM | 17
24013 | VA 14.2 | 2025-03-19 | Fredy veliz | We continue removing this slow process delivery's keeps coming and we have to stop ever time they come | Subcontractor | Chris Buttrey | [5 empty] | 4 | 8 |  |  | 2 boom lift | [5 empty] | Other | [42 empty] | Removing damage acm panels | 32
24015 | New Pope School | 2025-03-19 | rafael gomez | we start working on area 407 | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 1boomlift | false |  |  |  |  | Corrugated / Screen wall Subgirt Zee | [22 empty] | 30 | 10 | [6 empty] | 300 | 10
24018 | QTS-NAL1-DC1 | 2025-03-19 | Saul chicas | We start to reinstall the panels on freedom wall and coordinate with others companies to use the scissor lift, We also started with the caulking 80 LF of caulking | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Scissor lift | [5 empty] | Caulking | [20 empty] | 80 | 10
24025 | Madison Elementary | 2025-03-19 | Rudy Pineda | z girt canopy @ rood | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 8 | false |  | 2 booms | false |  |  |  |  | Subgirt Zee
23029 | BNA Concourse D | 2025-03-18 | Antonio | We focused on preparing and finish installing test areas also continued installing roof panels | JWMCD Crew | Marc Ribar | true | An area requires a sheathing patch and waterproofing |  |  | Clear | 14 | 13 | false |  | 4 man booms and a lull | false |  |  |  |  | Flashing IMP Overly Roof Panel | [8 empty] | 34 | 182 |  |  | 17 | 13 | [18 empty] | 380 | 3
24001 | McEwen Northside | 2025-03-18 | Marvin Blanco | Installing bellara panels in the north elevation and also the little face of bellara panels in the east side and west side working in the columns with ACM panels moving plywood for protection in the concrete moving material preparation for the next areas working in the swing stage in the south east corner | Subcontractor | Josh McPherson | false |  |  |  |  | 16 | 11 | false |  | Scissors lift boomlift forklift | false |  |  |  |  | ACM Other | 18 | 88 | [40 empty] | Installing bellara panels | 66
24005 | GCDC Building 2/VA1.2 | 2025-03-18 | Obed Bermudez | We continue working on the west elevation, with panel installation. | JWMCD Crew | Joe Hoyle | [5 empty] | 7 | 10 |  |  | Boom lifts and forklift. | [5 empty] | ACM | 23 | 70
24013 | VA 14.2 | 2025-03-18 | Fredy veliz | We keep removing what we can these delivery's in the loading dock so we have to stop every time they have one standing tomorrow they say we gonna start at 8 am and work 8 hours a day so the delivery's can be unloaded in the morning from 5am to 8 am they will let me know if they gonna let us work more hours | Subcontractor | Chris Buttrey | true | Deliveries all day |  |  | Good | 4 | 10 |  |  | 1 boom lift | [5 empty] | Other | [42 empty] | Removing damage panels | 40
24018 | QTS-NAL1-DC1 | 2025-03-18 | Saul chicas | We start working to fix the freedom wall issue we removed 8 panels, we have to wait and coordinate with others companies to use the scissor lift, We also started with the caulking 150’ LF | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Scissor lift | [5 empty] | Caulking | [20 empty] | 150 | 10
24025 | Madison Elementary | 2025-03-18 | Rudy Pineda | flqshing canopy @ roof | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 8 | false |  | 2 booms | false |  |  |  |  | Flashing
23029 | BNA Concourse D | 2025-03-17 | Antonio | We installed panels on the swing stance in order to close up the window area on landside connector. Also install panels next to airside expansion joint. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 8 | 10 | false |  | 4 man lifts and a lull | false |  |  |  |  | IMP | [8 empty] | 38 | 80
23029 | BNA Concourse D | 2025-03-17 | Antonio | One crew installed imp on airside concession corner, crew two installed acm panels on the roof.crew three installed window flashing down airside | JWMCD Crew | Marc Ribar | false |  |  |  |  | 10 | 10 | false |  | 4 man lifts and a lull | false |  |  |  |  | ACM Flashing IMP | 14 | 10 | [6 empty] | 26 | 100 | [22 empty] | 1100 | 9
24001 | McEwen Northside | 2025-03-17 | Marvin Blanco | Working in the second level installing ACM panels also finishing the bellara panels in the soffit and Working in the columns cleaning our areas and tomorrow morning we will be working in the east side installing the swing stage and checking our equipment to see what we need and what we don't need | Subcontractor | Josh McPherson | false |  |  |  |  | 16 | 12 | false |  | Scissors lift boomlift forklift | false |  |  |  |  | ACM Other | 22 | 144 | [40 empty] | Bellara panels | 48
24005 | GCDC Building 2/VA1.2 | 2025-03-17 | Obed Bermudez | We continue working on the west elevation, installing panels and flat metal. | JWMCD Crew | Joe Hoyle | [5 empty] | 5 | 10 | true | We received a truck with panels for west elevation. | Boom lift and forklift. | [5 empty] | ACM | 15 | 50
24013 | VA 14.2 | 2025-03-17 | Fredy veliz | Slow process and missing materials | Subcontractor | Chris Buttrey | [5 empty] | 5 | 9.5 | true | Acm panels and insulation | 2 boom lifts | [5 empty] | Other | [42 empty] | Safety orientation getting the area ready Removing panels | 47.5
24018 | QTS-NAL1-DC1 | 2025-03-17 | Saul chica | We finished of peeling the panels on the stairwells We finished with the housekeeping on the roof area, we only leave the scaffold out there to finish with the punch list We also started to look into the punch list item, we went to the penthouse to check the coping issues and retake new dimensions. Also we checked the freedom wall issue | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift / scaffold | [5 empty] | ACM | 0 | 10
24025 | Madison Elementary | 2025-03-17 | Rudy Pineda | no work due to rain | Subcontractor | Wylie McDougall | true | rain |  |  | rain | 1 | 0 | false |  | 2 booms | false |  |  |  |  | Other | [42 empty] | no work | 0
24025 | Madison Elementary | 2025-03-15 | Rudy Pineda | work @ canopy3 | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 5 | false |  | 2 booms | false |  |  |  |  | Insulation Single Skin Subgirt Zee
23029 | BNA Concourse D | 2025-03-14 | Tony | Installed panels connectors expansion joint and flashing also installed roof panels concessions roof | JWMCD Crew | Marc Ribar | true | Vechile parked in work area and stand down due to high wind |  |  | High wind 40 mph gust | 12 | 8 | false |  | 4 manlifts and 1 fork lift | false |  |  |  |  | Flashing IMP Overly Roof Panel | [8 empty] | 20 | 96 |  |  | 6 | 8 | [18 empty] | 70 | 2
24005 | GCDC Building 2/VA1.2 | 2025-03-14 | Obed Bermudez | We continued working on the west elevation with panel installation. In the afternoon, we returned from lunch to find that our equipment and panels had been moved by B&S (the concrete guys) and placed on the ground without any protection. | JWMCD Crew | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lifts and forklift | [5 empty] | ACM | 10 | 32
24025 | Madison Elementary | 2025-03-14 | Rudy Pineda | remove panels @ roof for water test and work @ canopy | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 7 | false |  | 2 booms | false |  |  |  |  | Flashing Insulation Subgirt Zee
23029 | BNA Concourse D | 2025-03-13 | Antonio | Installed acm panels on north roof of concessions. Another crew finished installing imp around concessions | JWMCD Crew | Marc Ribar | false |  |  |  |  | 8 | 10 | false |  | 4 man lifts and a lull | false |  |  |  |  | ACM IMP | 12 | 10 | [6 empty] | 18 | 80
24001 | McEwen Northside | 2025-03-13 | Marvin Blanco | Installing ACM panels in the column at the west elevation putting Zs in the north side and also installing bellara panels in the south elevation cleaning our area | Subcontractor | Josh McPherson | false |  |  |  |  | 12 | 11 | false |  | Scissors lift boomlift forklift | false |  |  |  |  | ACM Other | 16 | 88 | [40 empty] | Bellara panels | 44
24005 | GCDC Building 2/VA1.2 | 2025-03-13 | Obed Bermudez | We continue working on the west elevation, with layout and panel installation. | JWMCD Crew | Joe Hoyle | [5 empty] | 4 | 11 |  |  | Boom lift and forklift. | [5 empty] | ACM | 12 | 11
24018 | QTS-NAL1-DC1 | 2025-03-13 | Saul chicas | Crew1 Stairwells North elevation #6 4 guys 6 panels installed 90 ’ z-girts We move to the loading dock to see the issue and take pictures Crew2 Stairwells north elevation #8 4 guys 8 panels 150’ z-girts | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | ACM Subgirt Zee | 14 | 10 | [28 empty] | 240 | 10
24020 | QTS ATL2 DC2 Osgood | 2025-03-13 | Marvin Blanco | Trying to install panels but Hitt guys they're not ready because today my guys install 3 to 4 panels and they make us to take it down the 4 panels they have to move a couple of electric boxes and leave it flush with the face of the ACM panels we have L angles by others to install that's extra work for PID and we have one more thing with the second line of the panels the panels are short we are missing silicone and also we need more Zs soon as possible because we only have 20 Zs that's nothing for us | Subcontractor | Dillon Bowman | true | Silicone |  |  | Good condition | 4 | 11 | false |  | Scissors lift boomlift | false |  |  |  |  | Other | [42 empty] | Trying to install panels but to many issues | 44
24025 | Madison Elementary | 2025-03-13 | Rudy Pineda | area 21, 22 209 | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 21 | false |  |  | false |  |  |  |  | Caulking Flashing Insulation Single Skin Subgirt Zee
23029 | BNA Concourse D | 2025-03-12 | Antonio | Install panels on Airside first corner and also install metal break flashing on top of it | JWMCD Crew | Marc Ribar | true |  |  |  |  | 6 | 8 | false |  | 4 man lifts and a lull | false |  |  |  |  | Flashing IMP | [8 empty] | 16 | 48 | [22 empty] | 40 | 3
23029 | BNA Concourse D | 2025-03-12 | Antonio | Install metal panels on the side of concessions airside, also had a crew installing roof acm panels | JWMCD Crew | Marc Ribar | true | Window needed to be caulked still |  |  |  | 8 | 10 | false |  | 4 man lifts and a lull | false |  |  |  |  | ACM Flashing IMP | 12 | 10 | [6 empty] | 22 | 80
24001 | McEwen Northside | 2025-03-12 | Marvin Blanco | Installing ACM panels in the west elevation with a little issues in the end of the canopy the panels don't work really well also working in the soffit with the bellara panels doing extra work in tha soffit because the framing it's in the wrong way | Subcontractor | Josh McPherson | false |  |  |  |  | 12 | 11 | false |  | Scissors lift boomlift and forklift | false |  |  |  |  | ACM Other | 18 | 88 | [40 empty] | Bellara panels | 44
24005 | GCDC Building 2/VA1.2 | 2025-03-12 | Obed Bermudez | Today, we started moving our boom lifts to the east wall for layout, but we had to wait for the excavators to let us through. Then, we spend one hour and a half receiving a delivery of glass material, After that we proceeded with the layout on the east wall. | JWMCD Crew | Joe Hoyle | [5 empty] | 4 | 12 | true | Glass material | Boom lift and forklift | [5 empty] | Layout
24018 | QTS-NAL1-DC1 | 2025-03-12 | Saul chicas | Crew1 Stairwells North elevation #6 4 guys 6 panels installed 140’ z-girts We also peeled almost the entire wall Crew2 Stairwells north elevation #8 4 guys 10 panels 120’ z-girts | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | ACM Subgirt Zee | 16 | 10 | [28 empty] | 260 | 10
24020 | QTS ATL2 DC2 Osgood | 2025-03-12 | Marvin Blanco | We supposed get our delivery at 1 pm but we didn't the delivery gets there at 5 pm we have 4 hours wasted waiting for material also my guys notice that they only received 20 "Zs" and he's thinking we need around 60 or 80 more Zs | Subcontractor | Dillon Bowman | true | Material |  |  | Good condition | 4 | 12 | true | Zs and ACM panels | Boomlift forklift | false |  |  |  |  | Other | [42 empty] | Nothing because the delivery was delay | 44
24025 | Madison Elementary | 2025-03-12 | Rudy Pineda | area 21,22 209 | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 7 | false |  | 2 booms | false |  |  |  |  | Flashing Insulation Subgirt Zee
23029 | BNA Concourse D | 2025-03-11 | Antonio | Install panels on land side of D9 also measured the rest of the areas for coping | JWMCD Crew | Marc Ribar | false |  |  |  |  | 6 | 8 | false |  | 4 man lifts and a lull | false |  |  | 4 |  | IMP Layout | [8 empty] | 16 | 48
23029 | BNA Concourse D | 2025-03-11 | Antonio | Install the panels next to D 6 expansion joint | JWMCD Crew | Marc Ribar | true |  |  |  |  | 6 | 8 | false |  | 4 man lifts and a lull | false |  |  |  |  | Flashing IMP | [8 empty] | 16 | 48 | [22 empty] | 40 | 3
24001 | McEwen Northside | 2025-03-11 | Marvin Blanco | Installing ACM panels and Zs" and insulation and cleaning the area and receiving ACM panels | Subcontractor | Josh McPherson | false |  |  |  |  | 13 | 10 | true | 8 creates of ACM panels | Swing stage scissors lift and forklift | false |  |  |  |  | ACM | 18 | 140
24005 | GCDC Building 2/VA1.2 | 2025-03-11 | Obed bermudez | We continue working on the north elevation, installing panels. | JWMCD Crew | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift and forklift | [5 empty] | ACM | 10 | 40
24018 | QTS-NAL1-DC1 | 2025-03-11 | Saul chicas | Crew1 Stairwells North elevation #6 4 guys 15 panels installed 140’ z-girts Crew2 Stairwells north elevation #8 4 guys 10 panels 150’ z-girts | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | ACM Subgirt Zee | 25 | 10 | [28 empty] | 290 | 10
24025 | Madison Elementary | 2025-03-11 | Rudy Pineda | area 21, 22 209 | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 7 | false |  | 2 booms | false |  |  |  |  | Flashing Hat Channel Insulation Subgirt Zee
22061 | 19th and Church | 2025-03-10 | JC Panels | We are done painting the bolts. A panels was damage by an employee working on the site . We report it with Yates and Colton | Subcontractor | Josh McPherson | false |  |  |  |  | 4 | 10 | false |  |  | false |  |  |  |  | ACM
23029 | BNA Concourse D | 2025-03-10 | Antonio | Finished Installing panels around D 7 doors | JWMCD Crew | Marc Ribar | true |  |  |  |  | 6 | 8 | false |  | 4 man lifts and a lull | false |  |  |  |  | IMP | [8 empty] | 22 | 48
24001 | McEwen Northside | 2025-03-10 | Marvin Blanco | Installing ACM panels in the west elevation also installing the bellara panels staring the soffit today and we have issues with the framing because it's in the wrong way so we have to be using the flats straps | Subcontractor | Josh McPherson | false |  |  |  |  | 14 | 11 | false |  | Scissors lift, boomlift, forklift | false |  |  |  |  | ACM Other | 22 | 110 | [40 empty] | Bellara panels | 44
24005 | GCDC Building 2/VA1.2 | 2025-03-10 | Obed Bermudez | We continue working on the north west elevation, with panel installation and flat metal. | JWMCD Crew | Joe Hoyle | [5 empty] | 3 | 10 |  |  | Boom lift and forklift | [5 empty] | ACM Soffit | 10 | 30
24018 | QTS-NAL1-DC1 | 2025-03-10 | Saul chicas | Crew1 Stairwells North elevation #6 4 guys 15 panels installed 130’ z-girts Crew2 Stairwells north elevation #8 4 guys 10 panels 150’ z-girts We also installed protection to the freedom wall | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | ACM Subgirt Zee | 25 | 10 | [28 empty] | 280 | 10
24025 | Madison Elementary | 2025-03-10 | Rodolfo Pineda | area 21 22 209 | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 7 | false |  | 2 booms | false |  |  |  |  | Single Skin
24062 | Moses Collision Center | 2025-03-10 | Marvin Blanco | Finishing installing the ACM panels and cleaning | Subcontractor | Laura Forero | false |  |  |  |  | 3 | 12 | false |  | Boomlift | false |  |  |  |  | ACM | 15 | 36
24001 | McEwen Northside | 2025-03-09 | Marvin Blanco | Installing ACM panels in the north west corner also fixing panels because my guys get confused in the colors of the panels in the south east elevation moving plywood and insulation to cover the concrete in the job site also installing the bellara panels in the west elevation in the soffit | Subcontractor | Josh McPherson | false |  |  |  |  | 13 | 10 | false |  | Scissors lift, forklift, and boomlift | false |  |  |  |  | ACM Other | 20 | 100 | [40 empty] | Bellara panels | 30
24018 | QTS-NAL1-DC1 | 2025-03-09 | Saul chicas | 03/09 5 hours Crew1 Stairwells North elevation #8 4 guys 8 panels installed 180’ z-girts Crew2 Stairwells north elevation #8 4 guys 5 panels 200’ z-girts | Subcontractor | Joe Hoyle | [5 empty] | 8 | 5 |  |  | Boom lift | [5 empty] | ACM Subgirt Zee | 13 | 5 | [29 empty] | 380
24062 | Moses Collision Center | 2025-03-09 | Marvin Blanco | Finishing remaking 3 panels and also manufacturing 3 panels because McDougall make the panels incorrect we are going to be done with the job tomorrow around lunch time in case need anything just let us know before we leave. | Subcontractor | Laura Forero | false |  |  |  |  | 3 | 12 | false |  | Boomlift | false |  |  |  |  | ACM | 10 | 36
23029 | BNA Concourse D | 2025-03-08 | Antonio | We installed the skin panels on existing concourse D | JWMCD Crew | Marc Ribar | false |  |  |  |  | 4 | 8 | false |  | 4 man lifts and a forklift | false |  |  |  |  | Single Skin | [6 empty] | 2 | 8 |  | 32
24018 | QTS-NAL1-DC1 | 2025-03-08 | Saul chicas | Crew1 Stairwells North elevation #6 4 guys 11 panels installed 150’ z-girts Crew2 Stairwells north elevation #8 4 guys 10 panels 130’ z-girts | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | ACM Subgirt Zee | 21 | 10 | [28 empty] | 280 | 10
24025 | Madison Elementary | 2025-03-08 | Rudy Pineda | area 16 17 207 | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 15 | false |  | 2 booms | false |  |  |  |  | Flashing Insulation Subgirt Zee
23029 | BNA Concourse D | 2025-03-07 | Antonio | Install panels around D 7 doors to the signs and install corresponding flashing | JWMCD Crew | Marc Ribar | true |  |  |  |  | 6 | 8 | false |  | 4 man lifts and a lull | false |  |  |  |  | Flashing IMP | [8 empty] | 22 | 48 | [22 empty] | 100 | 3
24005 | GCDC Building 2/VA1.2 | 2025-03-07 | Obed Bermudez | We continue working on the north elevation, installing panels. | JWMCD Crew | Joe Hoyle | [5 empty] | 3 | 10 |  |  | Forklift and boom lifts. | [5 empty] | ACM Hat Channel | 14 | 30 | [32 empty] | 20 | 1
24025 | Madison Elementary | 2025-03-07 | Rudy Pineda | area 16,17 207 | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 7 | false |  | 2 booms | false |  |  |  |  | Single Skin | [7 empty] | 21
23029 | BNA Concourse D | 2025-03-06 | Antonio | Install panels above D6 doors to the signs and install corresponding flashing | JWMCD Crew | Marc Ribar | true |  |  |  |  | 6 | 8 | false |  | 4 man lifts and a lull | false |  |  |  |  | Flashing IMP | [8 empty] | 18 | 48 | [22 empty] | 100 | 3
24001 | McEwen Northside | 2025-03-06 | Marvin Blanco | Working in the west elevation north elevation cleaning also we made a mistake with the panels at the south and east elevation in the triangle panels my guys confused 2 different colors of the panels but we will get it fix soon we get a chance to put a boomlift in the area also one of the lift wasn't working today they company EFI brought it with issues | Subcontractor | Josh McPherson | false |  |  |  |  | 13 | 10 | false |  | Swing stage boomlift scissors lift and forklift | false |  |  |  |  | ACM Other | 17 | 100 | [40 empty] | Bellara panels | 30
24005 | GCDC Building 2/VA1.2 | 2025-03-06 | Obed Bermudez | Today we did layout there was too much wind to do panel installation | JWMCD Crew | Joe Hoyle | [5 empty] | 3 | 8 |  |  | Boom lift and forklift
24018 | QTS-NAL1-DC1 | 2025-03-06 | Saul chicas | Crew1 Stairwells North elevation #6 4 guys 6 panels installed 70’ z-girts We wait for sunbelt to fix the the lift almost all the morning The structure is 2 1/4” uneven so we have to made custom z-girts to make the corner work . Crew2 Stairwells north elevation #8 We make layout and put lines to plumb the corners, this structure is out of level as well so we have to made custom z-girt and use I lot of shims. 4 guys 8 panels 120’ z-girts We also install 3 panels and z-girt on the vestibule We took +- 3 hour to clean the areas because WT was required it. | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | ACM Subgirt Zee | 12 | 10 | [28 empty] | 190 | 10
24025 | Madison Elementary | 2025-03-06 | Rudy Pineda | area 12 205 | Subcontractor | Wylie McDougall | true | Brent wants a change in this area therefore we need to add additional z girts |  |  |  | 3 | 7 | false |  | 2 booms | false |  |  |  |  | Subgirt Zee
23029 | BNA Concourse D | 2025-03-05 | Antonio | Install panels around D6 doors | JWMCD Crew | Marc Ribar | false |  |  |  |  | 6 | 8 | false |  | 4 man lifts and a lull | false |  |  |  |  | IMP | [8 empty] | 21 | 48
24015 | New Pope School | 2025-03-05 | rafael gomez | we continued working on area 305 | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 9 | false |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 25 | 9 |  |  | 100 | 9 |  |  | 100 | 9
24025 | Madison Elementary | 2025-03-05 | Rudy Pineda | canopy area 204 z girt | Subcontractor | Wylie McDougall | false |  |  |  |  | 2 | 7 | false |  | 2 booms | false |  |  |  |  | Subgirt Zee
23029 | BNA Concourse D | 2025-03-04 | Antonio | Started installing landslide acm and finished d7 panels before we got put on standby | JWMCD Crew | Marc Ribar | true | Wind was over 35 mph |  |  | Windy |  | 6 | false |  | 4 man lifts a forklift | false |  |  |  |  | ACM IMP | 4 | 6 | [6 empty] | 18 | 6
24005 | GCDC Building 2/VA1.2 | 2025-03-04 | Obed Bermudez | Today the superintendent told us we couldn't work due to grading and sidewalk being done, so we had to move our boom lift and forklift out of there. | JWMCD Crew | Joe Hoyle | true | Today the superintendent told us we couldn't work due to grading and sidewalk being done, so we had to move our boom lift and forklift out of there. |  |  |  | 3 | 5 | true | We received a delivery around 11:30 am we proceeded to unload our material | Boom lifts and forklift
24015 | New Pope School | 2025-03-04 | rafael gomez | we complete 309 and we star working on area 305 | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 9 | false |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 20 | 9 |  |  | 100 | 9 |  |  | 100 | 9
24018 | QTS-NAL1-DC1 | 2025-03-04 | Saul chicas | Crew1 Stairwells North elevation #6 4 guys 4 panels installed 70’ z-girts The structure is 2 1/4” uneven so we have to made custom z-girts to make the corner work . Crew2 Stairwells north elevation #6 4 guys 8 panels 120’ z-girts We also install 2 panels and z-girt on the vestibule We took +- 3 hour to clean the areas because WT was required it. | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | ACM Subgirt Zee | 12 | 10 | [28 empty] | 190 | 10
24025 | Madison Elementary | 2025-03-04 | Rudy Pineda | worked on canopy area 204 | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 7 | false |  | 2 booms | false |  |  |  |  | AWB Subgirt Zee
23029 | BNA Concourse D | 2025-03-03 | Antonio | Fab and install panels around D 6 and installed the panels missing on the north side of concessions Also installed panels near record node | JWMCD Crew | Marc Ribar | true | Can not work air side due to concrete prep |  |  |  | 8 | 10 | false |  | 4 man lifts a lull | false |  |  |  |  | ACM IMP | 8 | 10 | [6 empty] | 46 | 80
24001 | McEwen Northside | 2025-03-03 | Marvin Blanco | Installing ACM panels in the west elevation south elevation finishing the E1B panels moving material we are needing more of little boomlift and the panels for the south east corner | Subcontractor | Josh McPherson | false |  |  |  |  | 14 | 10 | false |  | Swing stage boomlift forklift scissors lift | false |  |  |  |  | ACM | 26 | 140
24005 | GCDC Building 2/VA1.2 | 2025-03-03 | Obed Bermudez | We received and unloaded a delivery of panels and had to move our boxes of panels again to the sidewalk where the super wanted us to put protection down first. We also got some panels that have scratches on them see the pictures below. | JWMCD Crew | Joe Hoyle | true | We had to find plywood to protect the sidewalk where the superintendent wanted our material |  |  |  | 3 | 10 | true | We received Panels | Boom lift and forklift.
24015 | New Pope School | 2025-03-03 | rafael gomez | we continued working on area 309 | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 9 | false |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall Trim | [22 empty] | 20 | 9 | [12 empty] | 100 | 9
24018 | QTS-NAL1-DC1 | 2025-03-03 | Saul chicas | Crew1 Stairwells North elevation #6 4 guys 12 panels installed 180’ z-girts The structure is 2 1/4” uneven so we have to made custom z-girts to make the corner work . Crew2 Stairwells north elevation #6 4 guys 10 panels 200’ z-girts We also install 2 panels and z-girt on the vestibule Same problems with the structure of steel also the corner is not square. | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | ACM Subgirt Zee | 22 | 10 | [28 empty] | 380 | 10
24025 | Madison Elementary | 2025-03-03 | Rudy Pineda | worked on area 12 205 installing z girts | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 7 | false |  | 2 boom lifts | false |  |  |  |  | Subgirt Zee | [31 empty] | 21
24001 | McEwen Northside | 2025-03-01 | Marvin Blanco | Installing bellara panels in the north west corner finishing the panels in the north east elevation working in the south elevation with the triangle panels my guys couldn't put silicone in the soffit in the south west corner between the bellara and ACM panels but we will get it done soon as possible | Subcontractor | Josh McPherson | false |  |  |  |  | 14 | 8 | false |  | Swing stage boomlift scissors lift and forklift | false |  |  |  |  | ACM Other | 18 | 56 | [40 empty] | Bellara panels | 56
24025 | Madison Elementary | 2025-03-01 | Rudy Pineda | area 12 205 install blue skin and flashing and z girt | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 5 | false |  | 2 boom lifts | false |  |  |  |  | AWB Flashing Subgirt Zee
23029 | BNA Concourse D | 2025-02-28 | Antonio | We finished installing panels and flashing on the swing stage. Then we moved over to air side and fabbed and installed panels at D6 towards expansion joint | JWMCD Crew | Marc Ribar | true | We can not work land side due to concrete being prepped |  |  |  | 5 | 16 | false |  | 4 man lifts and one forklift | false |  |  |  |  | Flashing IMP | [8 empty] | 30 | 80 | [22 empty] | 400 | 6
24005 | GCDC Building 2/VA1.2 | 2025-02-28 | Obed Bermudez | We continue working on the west elevation, installing z girt and hat channel. | JWMCD Crew | Joe Hoyle | [5 empty] | 3 | 9 |  |  | Boom lift and forklift. | [5 empty] | Hat Channel Subgirt Zee | [30 empty] | 480 | 4 |  |  | 670 | 5
24015 | New Pope School | 2025-02-28 | rafael gomez | we put all corner flashing | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 9 | false |  | 1 boomlift | false |  |  |  |  | Flashing | [32 empty] | 150 | 9
24018 | QTS-NAL1-DC1 | 2025-02-28 | Saul chicas | Crew1 Stairwells North elevation #6 4 guys 12 panels installed 180’ z-girts The structure is 2 1/4” uneven so we have to made custom z-girts to make the corner work . Crew2 Stairwells north elevation #6 4 guys 13 panels 200’ z-girts Same problems with the structure of steel also the corner is not square. We also have to move all the material from Northeast corner because was required from WT . | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boon Lift | [5 empty] | ACM Subgirt Zee | 25 | 10 | [28 empty] | 380 | 10
24001 | McEwen Northside | 2025-02-27 | Marvin Blanco | Installing bellara panels in the soffit at the north west corner also working in the north east corner and the south elevation with the triangle panels and cleaning the areas | Subcontractor | Josh McPherson | false |  |  |  |  | 14 | 10 | false |  | Swing stage, boomlift and forklift | false |  |  |  |  | ACM Other | 28 | 80 | [40 empty] | Bellara panels | 60
24005 | GCDC Building 2/VA1.2 | 2025-02-27 | Obed Bermudez | We continue working on the security room, putting plywood on windows and big opening. Then we went back to install Z girt and hat channel on the west elevation. | JWMCD Crew | Joe Hoyle | [5 empty] | 3 | 10 |  |  | Boom lift and forklift | [5 empty] | Hat Channel Subgirt Zee | [30 empty] | 610 | 7 |  |  | 360 | 3
24015 | New Pope School | 2025-02-27 | rafael gomez | we continued on area 309 and we star putting trims on the windows | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 9 | false |  | 1 boomlift | false |  |  |  |  | Insulation Subgirt Zee Trim | [26 empty] | 80 | 9 |  |  | 100 | 9 |  |  |  |  | 120 | 9
24018 | QTS-NAL1-DC1 | 2025-02-27 | Saul chicas | Crew1 Stairwells North elevation #6 4 guys 15 panels installed 180’ z-girts The structure is 2 1/4” uneven so we have to made custom z-girts to make the corner work . Crew2 Stairwells north elevation #6 4 guys 10 panels 200’ z-girts Same problems with the structure of steel also the corner is not square. | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | ACM Subgirt Zee | 25 | 10 | [28 empty] | 380 | 10
24025 | Madison Elementary | 2025-02-27 | Rudy Pineda | installed corrugated @ opening #15 and repairs @ courtyard | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 7 | false |  |  | false |  |  |  |  | Corrugated / Screen wall | [23 empty] | 21
24025 | Madison Elementary | 2025-02-27 | Kevin | Removed and reinstalled 3 window bays in courtyard, installed trim and insulation on south main entrance | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 8 | false |  | 2 boom lifts and Baker scaffolding | false |  |  |  |  | Insulation Single Skin Trim | [6 empty] | 8 | 6 | [18 empty] | 80 | 2 | [8 empty] | 90 | 4
23029 | BNA Concourse D | 2025-02-26 | Antonio | We were installing the bottom section of the panels on d6 area and stopped after the issue then we started installing top panels on the connector | JWMCD Crew | Marc Ribar | true | We can not work airside concessions due to concrete prep work also we ran into a bust on the d6 area we were working at |  |  | Sunny | 7 | 10 | true | 11 bundles to the voulte yard | 4 man lifts and a lull | false |  |  |  |  | Flashing IMP | [8 empty] | 8 | 70 | [22 empty] | 200 | 2
24001 | McEwen Northside | 2025-02-26 | Marvin Blanco | Receiving scissors lift installing ACM panels in the east side and also south elevation putting silicone in the east side installing bellara panels in the north west corner we need 2 day in the south elevation to finish the area | Subcontractor | Josh McPherson | false |  |  |  |  | 14 | 10 | true | Scissors lift | Swing stage, boomlift and forklift | false |  |  |  |  | ACM Other | 18 | 40 | [40 empty] | Bellara panels | 100
24005 | GCDC Building 2/VA1.2 | 2025-02-26 | Obed bermudez | We continued in the morning working on the west elevation, installing a girt and hat channel, and then we stopped work at lunchtime because we went to work in the security room, covering windows with plywood. | JWMCD Crew | Joe Hoyle | [5 empty] | 3 | 11 |  |  | Boom lifts and forklift | [5 empty] | Hat Channel Subgirt Zee | [30 empty] | 150 | 4 |  |  | 20 | 1
24015 | New Pope School | 2025-02-26 | rafael gomez | we work on area 309 | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 9 | false |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 20 | 9 |  |  | 100 | 9 |  |  | 120 | 9
24018 | QTS-NAL1-DC1 | 2025-02-26 | Saul chicas | Crew1 Stairwells North elevation #6 4 guys 8 panels installed 80’ z-girts The structure is 2 1/4” uneven so we have to made custom z-girts to make the corner work . Crew2 Stairwells north elevation #6 4 guys 10 panels 200’ z-girts Same problems with the structure of steel also the corner is not square. | Subcontractor | Joe Hoyle | [5 empty] | 8 | 8 |  |  | Boom lift | [5 empty] | ACM Subgirt Zee | 18 | 8 | [28 empty] | 280 | 8
24025 | Madison Elementary | 2025-02-26 | Kevin | Started trim under drip by window but Travis requested we wait until they do the water testing, so cleaned up roof after done installing panels, and moved to courtyard and south side of building | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 8 | true | Baker scaffolding | 2 boom lifts and Baker scaffolding | false |  |  |  |  | Single Skin Trim | [6 empty] | 40 | 4 | [28 empty] | 40 | 4
23029 | BNA Concourse D | 2025-02-25 | Antonio | Layout left of d6 and installation of flashing and verified layout | JWMCD Crew | Marc Ribar | false |  |  |  |  | 8 | 8 | false |  | 4 man lifts a lull | false |  |  | 2 |  | Flashing Layout Plate |  |  | 24 | 4 | [5 empty] | 64 | [22 empty] | 200 | 2
24001 | McEwen Northside | 2025-02-25 | Marvin Blanco | Moving swing stage working in the north west corner in the soffit with the bellara panels today the guys couldn't install the south elevation because Hoar guys take the area | Subcontractor | Josh McPherson | false |  |  |  |  | 14 | 10 | false |  | Swing stage, boomlift and forklift | false |  |  |  |  | ACM Other | 15 | 40 | [40 empty] | Bellara panels and also moving swing stage | 100
24001 | McEwen Northside | 2025-02-25 | Marvin Blanco | Working in the soffit in the north west corner also installing ACM panels in the south elevation and the east elevation in the end of this week we will get a lot more done because the weather it's better | Subcontractor | Josh McPherson | false |  |  |  |  | 14 | 10 | false |  | Swing stage, boomlift and forklift | false |  |  |  |  | ACM | 36 | 140
24015 | New Pope School | 2025-02-25 | rafael gomez | we completed area306 and star working on area 309 | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 9 | false |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee Trim | [22 empty] | 10 | 9 |  |  | 300 | 9 |  |  | 300 | 9 |  |  |  |  | 150 | 9
24018 | QTS-NAL1-DC1 | 2025-02-25 | Saul chicas | Crew1 Stairwells North elevation #6 4 guys 12 panels installed 80’ z-girts The structure is 2 1/4” uneven so we have to made custom z-girts to make the corner work . Crew2 Stairwells north elevation #8 4 guys 10 panels 200’ z-girts Same problems with the structure of steel also the corner is not square. | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | ACM Subgirt Zee | 22 | 10 | [28 empty] | 280 | 10
24023 | CMU Robotics | 2025-02-25 | Kevin | Lowered upper jay trim to accommodate already cut panels, waterproofing on north | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 8 | false |  | 2 boom lifts | false |  |  |  |  | Insulation Single Skin Subgirt Zee Trim | [6 empty] | 74 | 8 | [18 empty] | 250 | 4 |  |  | 30 | 2 |  |  |  |  | 130 | 4
24025 | Madison Elementary | 2025-02-25 | Norberto Velasquez | Reworking roof | Subcontractor | Wylie McDougall | [5 empty] | 3 | 7 | [8 empty] | Corrugated / Screen wall Insulation Other | [22 empty] | 74 | 7 |  |  | 35 | 3 | [14 empty] | Installation of J Chanel | 4
24046 | UAB Biomedical Research and Psycholgy | 2025-02-25 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | true | delay in installation of panels because the electricians do not have the area ready get |  |  |  | 4 | 32 | false |  | 2. 65' boom lifts | false |  |  |  |  | Caulking | [20 empty] | 160 | 32
24005 | GCDC Building 2/VA1.2 | 2025-02-24 | Obed Bermudez | We started with layout on the west elevation, and installing hat channel. | JWMCD Crew | Joe Hoyle | [5 empty] | 2 | 5 |  |  | Boom lift and forklift | [5 empty] | Hat Channel | [30 empty] | 20 |  |  |  | 420 | 10
24015 | New Pope School | 2025-02-24 | rafael gomez | we continued working on 306 and 307 | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 9 | true |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall Insulation | [22 empty] | 20 | 9 |  |  | 200 | 9
24025 | Madison Elementary | 2025-02-24 | Norberto Velasquez | Reworking roof | Subcontractor | Wylie McDougall | [5 empty] | 3 | 7 | [8 empty] | Corrugated / Screen wall Flashing Other | [22 empty] | 38 | 7 | [8 empty] | 25 | 4 | [8 empty] | Installation of J Channel | 4
24025 | Madison Elementary | 2025-02-24 | Kevin | Install blueskin and caulking | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 8 | false |  | 2 boom lifts | false |  |  |  |  | Flashing Single Skin Subgirt Zee Trim | [6 empty] | 26 | 4 | [22 empty] | 30 | 2 | 30 | 2 |  |  | 80 | 6
23029 | BNA Concourse D | 2025-02-23 | Antonio | We continued running imp panels and flashing on d7 area | JWMCD Crew | Marc Ribar | false |  |  |  |  | 8 | 8 | false |  | 4 man lifts and a lull | false |  |  |  |  | Flashing IMP | [8 empty] | 50 | 64 | [22 empty] | 1200 | 2
23029 | BNA Concourse D | 2025-02-22 | Antonio | We installed imp panels next to d 6 and ran the corresponding flashing | JWMCD Crew | Marc Ribar | false |  |  |  |  | 8 | 10 | false |  | 4 man lifts and a lull | false |  |  |  |  | Flashing IMP | [8 empty] | 63 | 80 | [22 empty] | 1200 | 2
24015 | New Pope School | 2025-02-22 | rafael gomez | we continued woking on 307 and 307 | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 9 | false |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall Insulation | [22 empty] | 35 | 9 |  |  | 300 | 9
24025 | Madison Elementary | 2025-02-22 | Kevin | Had to drop top jay to use existing cut panels | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 8 | false |  | 2 boom lifts | false |  |  |  |  | Insulation Single Skin Trim | [6 empty] | 59 | 16 | [18 empty] | 246 | 4 | [8 empty] | 100 | 16
24025 | Madison Elementary | 2025-02-22 | Norberto Velasquez | Reworking roof | Subcontractor | Wylie McDougall | [5 empty] | 4 | 7 | [8 empty] | Corrugated / Screen wall Insulation Other | [22 empty] | 57 | 7 |  |  | 5 | 2 | [14 empty] | Installation of j channel | 7
24046 | UAB Biomedical Research and Psycholgy | 2025-02-22 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 4 | 32 | false |  | 2. 65' boom lifts | false |  |  |  |  | ACM | 17 | 32
24015 | New Pope School | 2025-02-21 | rafael gomez | we work on area 306 and we only work feb 21 and feb 22 do to short of material | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 9 | true | insulation | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall Insulation | [22 empty] | 50 | 9 |  |  | 350 | 9
24018 | QTS-NAL1-DC1 | 2025-02-21 | Saul chicas | Crew1 East office 3 guys 8 panels installed We modified 3 of them. Crew2 Stairwell north elevation 4 guys 970’ of z-girts | Subcontractor | Joe Hoyle | [5 empty] | 7 | 10 |  |  | Boom lift | [5 empty] | ACM Subgirt Zee | 8 | 10 | [28 empty] | 970 | 10
24025 | Madison Elementary | 2025-02-21 | Norberto Velasquez | Reworking roof | Subcontractor | Wylie McDougall | [5 empty] | 4 | 7 | [8 empty] | Corrugated / Screen wall Insulation Other | [22 empty] | 63 | 7 |  |  | 5 | 3 | [14 empty] | Installation of j channel | 7
24046 | UAB Biomedical Research and Psycholgy | 2025-02-21 | Naza Padron |  | JWMCD Crew | Wylie McDougall | true | The installation of panels on the column with corner has not continued due to the fact that the electricians have not finished yet. |  |  |  | 4 | 32 | false |  | 2. 65' boom lifts | false |  |  |  |  | ACM | 17 | 32
23029 | BNA Concourse D | 2025-02-20 | Antonio | We just bought bundles of panels to the job site from the office of mcdougall | JWMCD Crew | Marc Ribar | true | Weather |  |  | Snowing | 3 | 8 | false |  | 4 man lifts and a fork lift | false | [14 empty] | 24
24018 | QTS-NAL1-DC1 | 2025-02-20 | Saul chicas | Crew1 Penthouse 3 guys 100’ LF coping We finished with this Crew2 Stair tower #6 north elevation 5 guys 10 panels installed We are removing the 4” z-girt and reinstalling the 1 1/2” z-girt | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift and scaffold | [5 empty] | ACM Coping | 10 | 10 | [38 empty] | 100 | 10
24025 | Madison Elementary | 2025-02-20 | Norberto Velasquez | Reworking roof | Subcontractor | Wylie McDougall | true | Rework of the J Channel I needed to lower the J Channel even further to reuse the old panels |  |  |  | 4 | 7 | [8 empty] | Corrugated / Screen wall Insulation Other | [22 empty] | 52 | 4 |  |  | 30 | 3 | [14 empty] | Installation of J Channel | 7
24046 | UAB Biomedical Research and Psycholgy | 2025-02-20 | Naza Padron | The Crate of panels was sent in a truck with a closed box and had to be unloaded by hand 3 guys 6 hours... 30' of starter J 2 hours | JWMCD Crew | Wylie McDougall | true | electricians delaying installation progress |  |  |  | 4 | 32 | true | 1 Crate ACM Panels | 2. 65' boom lifts | false |  |  |  |  | ACM Other | 10 | 24 | [41 empty] | 2
23028 | 1000 Church YMCA | 2025-02-19 | Marvin Blanco | Working in the columns on south elevation and east elevation the out side columns are done we just need to change the inside columns because the paint it's not good the GC told the PM To change all the inside columns | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 12 | false |  | Scaffolding | false |  |  |  |  | Plate |  |  | 12 | 30
24001 | McEwen Northside | 2025-02-19 | Marvin Blanco | Installing ACM panels in the south elevation and east elevation with the swing stage and boomlift cleaning the roof in the east side moving material for now we have everything we need | Subcontractor | Josh McPherson | false |  |  |  |  | 14 | 10 | true | Scissors lift | boomlift, swing stage and forklift | false |  |  |  |  | ACM | 26 | 140
24025 | Madison Elementary | 2025-02-19 | Norberto Velasquez | It's already inspected to continue without stopping | Subcontractor | Wylie McDougall | [5 empty] | 4 | 7 | [8 empty] | Caulking Flashing Insulation Other | [20 empty] | 110 | 2 |  |  |  |  | 15 | 1 |  |  |  |  | 25 | 4 | [8 empty] | Blueskin installation | 6
24046 | UAB Biomedical Research and Psycholgy | 2025-02-19 | Naza Padron | Trash cleaning upper and lower roofs 4 hors | JWMCD Crew | Wylie McDougall | true | electricians delaying installation progress and wetting o missing panels |  |  |  | 4 | 24 | false |  | 2. 65' boom lifts | false |  |  |  |  | ACM Other Subgirt Zee | 4 | 16 | [28 empty] | 110 | 4 | [11 empty] | 4
23029 | BNA Concourse D | 2025-02-18 | Antonio | We focused our attention on installing the base panels on the D6 D7 area also installed all the flashings around the door | JWMCD Crew | Marc Ribar | true | Concessions still hasn’t been water proofed to continue installing the needed panels |  |  | Clear | 6 | 10 | true | I had to go get a mock up from the office of mcdugall | 4 man booms and a Forklift | false |  |  | 3 |  | Flashing IMP Layout Plate |  |  | 14 | 3 |  |  |  |  | 21 | 60 | [22 empty] | 70 | 4
24018 | QTS-NAL1-DC1 | 2025-02-18 | Saul chicas | Crew1 Penthouse 3 guys 100’ LF coping Crew2 Stair tower #6 north elevation 5 guys 15 panels installed | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift and scaffold | [5 empty] | ACM Coping | 15 | 10 | [38 empty] | 10 | 10
24025 | Madison Elementary | 2025-02-18 | Norberto Velasquez | Reworking roofing | Subcontractor | Wylie McDougall | true | problems with wood and level with windows. |  |  |  | 4 | 7 | [8 empty] | Flashing Other | [32 empty] | 100 | 7 | [8 empty] | Blueskin | 7
22061 | 19th and Church | 2025-02-17 | JC Panels | Caulking and peeling | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 10 | false |  |  | false |  |  |  |  | ACM
23028 | 1000 Church YMCA | 2025-02-17 | Marvin Blanco | Installing coping in the roof and kick plate in the bottom of the panels also working in the columns | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 12 | true | Plate panels | Scaffolding | false |  |  |  |  | Plate |  |  | 10 | 30
24001 | McEwen Northside | 2025-02-17 | Marvin Blanco | Installing ACM panels in the east elevation Installing Zs and insulation today was a good day with out rain but Wednesday looks like it's going to be bad we don't know if we are able to work | Subcontractor | Josh McPherson | false |  |  |  |  | 14 | 10 | false |  | Swing stage boomlift and forklift | false |  |  |  |  | ACM | 26 | 140
24025 | Madison Elementary | 2025-02-17 | Norberto Velasquez | We have already finished the two entrances and we are starting the first phase on the roof. | Subcontractor | Wylie McDougall | [5 empty] | 4 | 7 | [8 empty] | Corrugated / Screen wall Flashing Other | [22 empty] | 18 | 7 | [8 empty] | 30 | 7 | [8 empty] | Installation of J Channel and blueskin | 7
22061 | 19th and Church | 2025-02-14 | JC Panels | Caulking around the project. Install the panels with the scaffold in the dog park. We remove the scaffold | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 10 | false |  |  | false |  |  |  |  | ACM
23029 | BNA Concourse D | 2025-02-14 | Antonio | On site clean up all contractors | JWMCD Crew | Marc Ribar | false |  |  |  |  | 4 | 8 | false |  | 4 manlifts a forklift | false | [14 empty] | 32
24001 | McEwen Northside | 2025-02-14 | Marvin Blanco | Installing ACM panels in the east elevation with the swing stage and boomlift also working in the south elevation moving the swing stage from the west elevation over to the east elevation everything is working well with the panels | Subcontractor | Josh McPherson | false |  |  |  |  | 14 | 10 | false |  | Swing stage boomlift and forklift | false |  |  |  |  | ACM | 26 | 140
24018 | QTS-NAL1-DC1 | 2025-02-14 | Saul chicas | Crew1 Finished the freedom wall with spline and peeling the panels Crew2 Installing corner flashing on the PH Installing coping as well We revived a delivery in the morning. At the interior panels on the vestibule panels don’t fit with the opening check pictures attached | Subcontractor | Joe Hoyle | [5 empty] | 9 | 1 |  |  | Scaffold scissor lift and boom lift | [5 empty] | Coping Flashing | [32 empty] | 70 | 10 | [6 empty] | 20 | 10
24025 | Madison Elementary | 2025-02-14 | Norberto Velasquez | We finished a section of partial lifts and started preparing the opening 15 with the first phase. | Subcontractor | Wylie McDougall | true | They delivered and unloaded material at our workplace. |  |  |  | 4 | 7 | [8 empty] | Corrugated / Screen wall Flashing | [22 empty] | 18 | 7 | [8 empty] | 3 | 2
22061 | 19th and Church | 2025-02-13 | JC Panels | Caulking all around the project and also we set the scaffold inside the dog area to install panels | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | false |  |  | false |  |  |  |  | ACM
23029 | BNA Concourse D | 2025-02-12 | Antonio | Ended up installed 6 acm panels on the north side before the rain came out | JWMCD Crew | Marc Ribar | true | Can not install all panels due to testing pucks still on soffit |  |  | Rainy | 4 | 4 | true | 605m bundle and two bundles of coping | 4 man lifts and a forklift | false |  |  |  |  | ACM | 6 | 4 | [7 empty] | 16
24001 | McEwen Northside | 2025-02-12 | Marvin Blanco | Installing ACM panels moving material moving the swing stage from the west over to the east elevation cleaning the parking garage today thanks God everything works really good with no issues | Subcontractor | Josh McPherson | false |  |  |  |  | 15 | 10 | true | Zs | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Other | 20 | 100 | [40 empty] | Moving material and Moving swing stage | 50
24025 | Madison Elementary | 2025-02-12 | Norberto Velasquez | Preparing and installing | Subcontractor | Wylie McDougall | [5 empty] | 4 | 7 | [8 empty] | Corrugated / Screen wall Other | [22 empty] | 18 | 7 | [18 empty] | Installation of J Channel | 4
23029 | BNA Concourse D | 2025-02-11 | Antonio | It rained all day | JWMCD Crew | Marc Ribar | true | It was raining all day |  |  | Rainy | 1 | 5 | false |  | 4 man booms and one fork lift | false | [14 empty] | 5
24001 | McEwen Northside | 2025-02-11 | Marvin Blanco | Today we couldn't work installing panels because it was to much rain, the only thing we could do is clean up the parking garage and started fixing panels for next elevation | Subcontractor | Josh McPherson | false |  |  |  |  | 14 | 4 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | Other | [42 empty] | Cleaning | 56
24018 | QTS-NAL1-DC1 | 2025-02-11 | Saul chicas | Freedom wall area 7 guys 2 scissor lift 10 panels installed We are working on the back side of the wall where is more difficult without space so it takes us more time for installation. We have to carried all the panels from the north road and get into the building one at the time. Crew2 Stair tower North Elevation 2 guys Installing girts from the boom lift 900’ LF installed | Subcontractor | Joe Hoyle | [5 empty] | 9 | 10 |  |  | Boom lift, scaffold and scissor lift | [5 empty] | ACM Subgirt Zee | 10 | 10 | [28 empty] | 900 | 10
24025 | Madison Elementary | 2025-02-11 | Norberto Velasquez | We start the other partial elevation. | Subcontractor | Wylie McDougall | [5 empty] | 4 | 7 | [8 empty] | Corrugated / Screen wall Other | [22 empty] | 16 | 7 | [18 empty] | Installation of J Channel | 7
24046 | UAB Biomedical Research and Psycholgy | 2025-02-11 | Naza Padron | we left work due to rain at 2pm | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 42 | false |  | 2. 65' boom lifts | false |  |  |  |  | ACM | 14 | 42
22061 | 19th and Church | 2025-02-10 | JC Panels | We install the coping that was left to install. We finish the whole installation of panels on the west side . We modified 3 panels | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | false |  |  | false |  |  |  |  | ACM | 10
23029 | BNA Concourse D | 2025-02-10 | Antonio | We continued to install panels on the south side of concessions, I also walked with hp to talk about wall perpendicular to clear story. Panels in that area are installed to our benchmark height but there is exposed water proofing visible below our base of system due to other contractors error | JWMCD Crew | Marc Ribar | true | Areas that still require water testing and also areas that still need waterproofing before acm panel installation |  |  | Cloudy | 6 | 10 | false |  | 4 man booms 1 forklift | false |  |  | 4 |  | ACM Layout | 14 | 6 | [7 empty] | 60
24001 | McEwen Northside | 2025-02-10 | Marvin Blanco | Installing ACM panels in the west elevation and also east elevation working in the swing stage and boomlift installing Zs and insulation we have one panels short I think we need to replace in the west elevation | Subcontractor | Josh McPherson | false |  |  |  |  | 14 | 10 | false |  | Swing stage boomlift and forklift scaffolding | false |  |  |  |  | ACM | 28 | 140
24015 | New Pope School | 2025-02-10 | Rafael gomez | we complet area 411 | Subcontractor | Wylie McDougall | false |  |  |  |  | 6 | 6 | true |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall Subgirt Zee | [22 empty] | 20 | 6 | [6 empty] | 100 | 6
24018 | QTS-NAL1-DC1 | 2025-02-10 | Saul chicas | Freedom wall area 7 guys 2 scissor lift 11panels installed We are working on the back side of the wall where is more difficult without space so it takes us more time for installation. We have to carried all the panels from the north road and get into the building one at the time. Crew2 Stair tower North Elevation 2 guys Installing girts from the boom lift 800’ LF installed | Subcontractor | Joe Hoyle | [5 empty] | 9 | 10 |  |  | Scaffold and scissor lit | [5 empty] | ACM Subgirt Zee | 11 | 10 | [28 empty] | 800 | 10
24020 | QTS ATL2 DC2 Osgood | 2025-02-10 | Marvin Blanco | Finishing installing the canopies today the guys will be cleaning and tomorrow leave Atlanta | Subcontractor | Dillon Bowman | false |  |  |  |  | 6 | 10 | false |  | Boomlift | false |  |  |  |  | Other | [42 empty] | Canopies | 60
24025 | Madison Elementary | 2025-02-10 | Norberto Velasquez | Installing corrugated panels | Subcontractor | Wylie McDougall | [5 empty] | 4 | 7 | [8 empty] | Corrugated / Screen wall | [22 empty] | 20 | 7
24046 | UAB Biomedical Research and Psycholgy | 2025-02-10 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 48 | false |  | 2. 65' boom lifts | false |  |  |  |  | ACM Flashing Insulation Subgirt Zee | 8 | 26 | [24 empty] | 80 | 8 |  |  | 40 | 8 | 20 | 6
24018 | QTS-NAL1-DC1 | 2025-02-08 | Saul chicas | Freedom wall area 7 guys 2 crews working 10 panels installed We have to carried all the panels from the north road and get into the building one at the time. | Subcontractor | Joe Hoyle | [5 empty] | 7 | 10 |  |  | Scaffold and scissor lift | [5 empty] | ACM | 10 | 10
24025 | Madison Elementary | 2025-02-08 | Norberto Velasquez | Installation of panels. | Subcontractor | Wylie McDougall | [5 empty] | 3 | 7 | [8 empty] | Corrugated / Screen wall Other | [22 empty] | 9 | 7 | [18 empty] | Installation of J channel | 7
24046 | UAB Biomedical Research and Psycholgy | 2025-02-08 | Naza Padron | Access door fab 6 hours... | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 48 | false |  | 2. 65' boom lifts | false |  |  |  |  | ACM Insulation Subgirt Zee | 11 | 26 | [24 empty] | 120 | 8 |  |  | 120 | 8
23029 | BNA Concourse D | 2025-02-07 | Antonio | 25 ACM panels on north side of concessions and 12 Imp | JWMCD Crew | Marc Ribar | true | Lay down yard was locked and couldn’t access it |  |  | Clear | 6 | 10 | false |  | 4 man booms | false |  |  |  |  | ACM IMP | 25 | 10 | [6 empty] | 12 | 60
24001 | McEwen Northside | 2025-02-07 | Marvin Blanco | Installing ACM panels in the east side and also west elevation trying to finish the west elevation with the swing stage for now the only issues we have is we are delay | Subcontractor | Josh McPherson | false |  |  |  |  | 11 | 10 | false |  | Boomlift and scissors lift | false |  |  |  |  | ACM | 35 | 110
24015 | New Pope School | 2025-02-07 | rafael gomez | we work on area 411 | Subcontractor | Wylie McDougall | false |  |  |  |  | 6 | 9 | true |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall Subgirt Zee | [22 empty] | 20 | 9 | [6 empty] | 80 | 9
24018 | QTS-NAL1-DC1 | 2025-02-07 | Saul chicas | Freedom wall area 8 guys 2 crews working 12 panels installed We have to carried all the panels from the north road and get into the building one at the time. I have one panel that come with a scratch panel (217-2A35) a have one shit to make it. | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Scissor lift and scaffold | [5 empty] | ACM | 12 | 10
24025 | Madison Elementary | 2025-02-07 | Norberto Velasquez | Finishing preparations to install panels. | Subcontractor | Wylie McDougall | [5 empty] | 3 | 7 | [8 empty] | Other | [42 empty] | Installation of J Channel | 7
24046 | UAB Biomedical Research and Psycholgy | 2025-02-07 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 66 | false |  | 2. 65' boom lifts | false |  |  |  |  | ACM AWB Subgirt Zee | 24 | 42 | [28 empty] | 240 | 16 | [6 empty] | 360 | 8
23029 | BNA Concourse D | 2025-02-06 | Antonio | We finished installing flashings above CW airside and started with panel installation, also started ACM installation on North side of concession. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 6 | 10 | false |  | 4 man booms 1 forklift | false |  |  |  |  | ACM Flashing IMP | 5 | 6 | [6 empty] | 21 | 60 | [22 empty] | 1200 | 4
24015 | New Pope School | 2025-02-06 | rafael gomez | we completed 308 and we start putting zee on 306 | Subcontractor | Wylie McDougall | false |  |  |  |  | 8 | 9 | false |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 20 | 9 |  |  | 70 | 9 |  |  | 400 | 9
24015 | New Pope School | 2025-02-06 | rafael gomez | we are working on area 308 and 307 but we are short on material | Subcontractor | Wylie McDougall | false |  |  |  |  | 8 | 9 | false |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 40 | 9 |  |  | 150 | 9 |  |  | 200 | 9
24018 | QTS-NAL1-DC1 | 2025-02-06 | Saul chicas | Crew1 3 guys Moving all the material from the land yard south elevation, it take us the whole morning. Then we continue working on north canopy peeling the panels and trying to install the la panel that return to the roof but isn’t work we have to make a decision on this issue I’ll reach you by email about. Crew2 4 guys Working on the freedom wall 10 panels installed Crew 3 2 guys Working on wind wall We modified and installed 4 panels, the whole morning this area was closed. Also yesterday was a main event from WT so we spent 3 hours in their meeting so. | Subcontractor | Joe Hoyle | [5 empty] | 9 | 10 |  |  | Scissor lift and boom lift | [5 empty] | ACM | 14 | 10
24046 | UAB Biomedical Research and Psycholgy | 2025-02-06 | Naza Padron | still waiting for acces door at North Elevation... delivery 3 Crates ACM Panels 6 Hours | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 66 | true | 3 Ctrates ACM Panels | 2. 65' boom lifts | false |  |  |  |  | ACM Other | 17 | 60
23028 | 1000 Church YMCA | 2025-02-05 | Marvin Blanco | Installing ACM panels in the soffit we only have 1 problem my guys are out of trim or revils we need that first thing in the morning porfavor please | Subcontractor | Dillon Bowman | true | Revils |  |  | Good | 3 | 10 | false |  | Scaffolding | false |  |  |  |  | ACM | 5 | 30
23029 | BNA Concourse D | 2025-02-05 | Antonio | Continued installation of panels on landslide around doorframe, unloaded two delivery trucks for the remainder of our acm. Did layout for Jarvis ( the sign guys ) on panels also played panels on the ground to allow layout to be transferred to face of panel | JWMCD Crew | Marc Ribar | true | Concrete being poured on airside unable to start above cw with panel installation also on top of north side acm foam is in place of waterproofing HP needs to correct |  |  | Clear | 6 | 10 | true | The remaining of acm and flashings | 4 man lifts | false |  |  | 8 |  | IMP Layout | [8 empty] | 12 | 60
24001 | McEwen Northside | 2025-02-05 | Marvin Blanco | Installing ACM panels, Zs, and insulation working moving the swing stage cleaning the roof | Subcontractor | Josh McPherson | false |  |  |  |  | 11 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM | 35 | 110
24018 | QTS-NAL1-DC1 | 2025-02-05 | Saul chicas | Crew1 North canopy on (East office) 3 guys 1 boom lift We installed the corners panels and one soffit panel , this crew also help to finish loading dock area. Crew2 Wind wall (East office ) 3 guys 1 boom lift The back side on top of the wind wall panels are short so we have to modify 4 panels and made 2 of them. We also peel the Panels, this crew helps to finish loading dock area. Crew3 Freedon wall 3 guys 1 scissor lift 9 panels installed | Subcontractor | Joe Hoyle | true | The back side on top of the wind wall panels are short so we have to modify 4 panels and made 2 of them we also peel the panels this crew helps to finish the loading dock area |  |  | Good | 9 | 10 |  |  | Boom lift, scaffold and scissor lift | [5 empty] | ACM | 9 | 10
24020 | QTS ATL2 DC2 Osgood | 2025-02-05 | Marvin Blanco | Installing canopies with a couple of issues with don't have silicone for the canopy the guys was waiting for a scissors lift all day it's been 2 days delay for this I hope McDougall gets better one day on there's issues it's to many issues in every job | Subcontractor | Dillon Bowman | true | Scissors lift |  |  | Good | 6 | 10 | false |  | Boomlift and scissors lift | false |  |  |  |  | Other | [42 empty] | Canopies | 60
24025 | Madison Elementary | 2025-02-05 | Norberto Velasquez | The insulation was finished and the j-channel was started. The rest of the cleats were also finished. | Subcontractor | Wylie McDougall | [5 empty] | 3 | 7 | [8 empty] | Insulation Other | [26 empty] | 25 | 4 | [14 empty] | Installation of cleats and J Channel | 3
24046 | UAB Biomedical Research and Psycholgy | 2025-02-05 | Naza Padron | instaled 19 blades at roof 20 hours total... Delays at north elevation waiting for acces door | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 66 | false |  | 2. 65' boom lifts | false |  |  |  |  | ACM Other | 12 | 46 | [40 empty] | 19 | 20
23028 | 1000 Church YMCA | 2025-02-04 | Marvin Blanco | Installing ACM panels in the soffit with out issues thanks God | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 10 | true | Trims, or revils | Scaffolding | false |  |  |  |  | ACM | 8 | 30
23029 | BNA Concourse D | 2025-02-04 | Antonio | Install inner acm panels, run layout for north side acm panels, install panels above the door on landside | JWMCD Crew | Marc Ribar | true | Concrete being poured on airside unable to start above cw with panel installation also on top of north side acm foam is in place of waterproofing HP needs to correct |  |  | Clear | 6 | 10 | false |  | 4 man lifts | false |  |  | 8 |  | ACM IMP Layout | 9 | 8 | [6 empty] | 12 | 60
24001 | McEwen Northside | 2025-02-04 | Marvin Blanco | Working in the roof it's all finish the ACM coping and also de metal panels coping tomorrow the guys will be installing in the west elevation and also they will Working moving the swing stage | Subcontractor | Josh McPherson | false |  |  |  |  | 11 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM | 30 | 110
24015 | New Pope School | 2025-02-04 | rafael gomez | we completed 310 and we still working on 308 ! we have a problem with the boomlift as show on the picture | Subcontractor | Wylie McDougall | false |  |  |  |  | 8 | 9 | false |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 50 | 9 |  |  | 250 | 9 |  |  | 500 | 9
24018 | QTS-NAL1-DC1 | 2025-02-04 | Saul chicas | Crew1 Penthouse area 3 guys We finish 100% with the corrugated panels 14 pcs installed Crew2 Loading dock area 6 guys 2 boom lift 25 pcs installed is only 2 pcs left 10 pcs of flashing | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift and scaffold | [5 empty] | Corrugated / Screen wall Single Skin | [6 empty] | 25 | 10 | [14 empty] | 14 | 10
24020 | QTS ATL2 DC2 Osgood | 2025-02-04 | Marvin Blanco | Working in the canopies but we have a little issue we the scissors lift because Hitt is asking for a little that's requirement for use it so we are not able to finish the canopies till we get the lights and also some tire socks | Subcontractor | Dillon Bowman | true | Light for scissors lift |  |  | Good | 6 | 10 | false |  | Boomlift and scissors lift | false |  |  |  |  | Other | [42 empty] | Canopies | 60
24046 | UAB Biomedical Research and Psycholgy | 2025-02-04 | Naza Padron | asking superintendent Kenny for acces door at noth elevation to continue with ACM installation no responses | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 60 | true | 3 Crates with ACM panels | 2. 65' boom lifts | false |  |  |  |  | ACM Insulation Other Subgirt Zee | 14 | 34 | [24 empty] | 280 | 10 |  |  | 210 | 16
22061 | 19th and Church | 2025-02-03 | JC Panels | Panel installation and modification 6 modified | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | false |  |  | false |  |  |  |  | ACM | 8
23029 | BNA Concourse D | 2025-02-03 | Antonio | I had no workers come in. They were on strike | JWMCD Crew | Marc Ribar | false |  |  |  |  | 1 | 4 | false |  | 4 man lifts | false | [14 empty] | 40
24001 | McEwen Northside | 2025-02-03 | Marvin Blanco | Installing ACM panels in the west elevation in the roof also in the east side started installing insulation cleaning the roof in the north west patio I apologize because this morning my guys couldn't make it for the meeting but we will be back in same page | Subcontractor | Josh McPherson | false |  |  |  |  | 12 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM | 22 | 120
24001 | McEwen Northside | 2025-02-03 | Marvin Blanco | Installing ACM panels Zs and insulation trying to finish the west elevation | Subcontractor | Josh McPherson | false |  |  |  |  | 12 | 10 | true | Silicone and ACM panels | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM | 20 | 120
24015 | New Pope School | 2025-02-03 | rafael gomez | we completed 311 and we are working on area 310 and 308 | Subcontractor | Wylie McDougall | false |  |  |  |  | 8 | 9 | false |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 50 | 9 |  |  | 300 | 9 |  |  | 400 | 9
24018 | QTS-NAL1-DC1 | 2025-02-03 | Saul chicas | Crew1 Loading Dock area 5 guys Installing panels (22 pcs) This area is very difficult because the traffic of deliveries Crew2 Penthouse area 4 guys Installed corrugated laminate (9 pcs) We have to move and build the scaffold and also we brought the material by the lift from the ground. | Subcontractor | Joe Hoyle | [5 empty] | 9 | 10 |  |  | Boom lift and scaffold | [5 empty] | Corrugated / Screen wall Single Skin | [6 empty] | 22 | 10 | [14 empty] | 9 | 10
24020 | QTS ATL2 DC2 Osgood | 2025-02-03 | Marvin Blanco | Installing canopies | Subcontractor | Dillon Bowman | false |  |  |  |  | 4 | 12 | false |  | Boomlift | false |  |  |  |  | Other | [42 empty] | Canopy | 48
24025 | Madison Elementary | 2025-02-03 | Norberto Velasquez | Starting with phase 2 in partial south and north elevation. | Subcontractor | Wylie McDougall | [5 empty] | 3 | 7 | [8 empty] | Insulation | [26 empty] | 390 | 7
24046 | UAB Biomedical Research and Psycholgy | 2025-02-03 | Naza Padron | We were supposed to receive a delivery with panels and it did not arrive, we reinstal 17 panels at south elevation 34 hoursn | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 60 | false |  | 2. 65' boom lifts | false |  |  |  |  | ACM Insulation Subgirt Zee | 19 | 44 | [24 empty] | 110 | 6 |  |  | 210 | 10
24018 | QTS-NAL1-DC1 | 2025-02-02 | Saul chicas | 4 guys 6 hours Loading dock ceiling area 15 panels installed | Subcontractor | Joe Hoyle | [5 empty] | 4 | 6 |  |  | Boom lift | [5 empty] | Single Skin | [6 empty] | 15 | 6
22061 | 19th and Church | 2025-02-01 | JC Panels | Panel installation , fabrication and modification.. fins installation 50 | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | false |  |  | false |  |  |  |  | ACM | 9
23029 | BNA Concourse D | 2025-02-01 | Antonio | Continued running acm on concessions airside, continued installing imp above cw, also moved and install flashing on swing stage | JWMCD Crew | Marc Ribar | true |  |  |  |  | 10 | 11 | false |  | 3 man lifts a forklift | false |  |  |  |  | ACM Flashing IMP Trim | 45 | 11 | [6 empty] | 60 | 110 | [22 empty] | 200 | 2
24015 | New Pope School | 2025-02-01 | rafael gomez | we are working on elevation 310 installing zee ,insulation and installing panels on 311 | Subcontractor | Wylie McDougall | false |  |  |  |  | 6 | 9 | false |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 30 | 9 |  |  | 200 | 9 |  |  | 250 | 9
24018 | QTS-NAL1-DC1 | 2025-02-01 | Saul chicas | 02/01 Loading dock ceiling 4 guys 2 boom lift 14 panels installed We have serious problems with this area, there are trucks delivering all day and we have to stop working every hour and WT does not want to block the entrance. | Subcontractor | Joe Hoyle | [5 empty] | 6 | 8 |  |  | Boom lift | [5 empty] | Single Skin | [6 empty] | 14 | 8
22061 | 19th and Church | 2025-01-31 | JC Panels | Panel installation, 2 panels fabricated, 2 panels modified . 39 fins | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | false |  |  | false |  |  |  |  | ACM | 9
23029 | BNA Concourse D | 2025-01-31 | Antonio | We installed acm panels on airside of concessions and the panels below Cw on airside between concessions and record also installed both flashings above Cw | JWMCD Crew | Marc Ribar | false |  |  |  |  | 10 | 10 | false |  | 3 man booms and a forklift | false |  |  |  |  | ACM Flashing IMP Trim | 25 | 10 | [6 empty] | 32 | 100 | [22 empty] | 1500 | 4 |  |  | 400 | 3
23067 | Boeing PAC 3 | 2025-01-31 | Kevin Morris | Finished installing panels on mezzanine only trim left to do | Subcontractor | Chris Buttrey | false |  |  |  |  | 4 | 8 | false |  | Boom 60' x 2 | false |  |  |  |  | IMP | [8 empty] | 7 | 8
24015 | New Pope School | 2025-01-31 | rafael gomez | we completed the ceiling panels on area 411 and we start to install panels on area 311 ! we didn't go to work on Thursday 1/30/2025 do to heavy rain ! | Subcontractor | Wylie McDougall | false |  |  |  |  | 6 | 9 | true |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 20 | 9 |  |  | 200 | 9 |  |  | 300 | 9
23029 | BNA Concourse D | 2025-01-30 | Tony | rained out my guys @ 6am. work will resume as normal tomorrow morning | JWMCD Crew | Marc Ribar | true | weather |  |  | RAINY | 1 | 0 | false |  | 4 man booms, 2 80' 2 60' | false
23067 | Boeing PAC 3 | 2025-01-30 | Kevin Morris | Put extra joint in soffit panel authorized by DPR and Boeing | Subcontractor | Chris Buttrey | false |  |  |  |  | 4 | 10 | false |  | Boom 60' x 2 | false |  |  |  |  | IMP Trim | [8 empty] | 3 | [27 empty] | 40
24018 | QTS-NAL1-DC1 | 2025-01-30 | Saul chicas | Crew1 Penthouse area 7 guys Installing corrugated panels (32pcs) Installing Z-girt (300LF) Building and moving the scaffold Crew2 2 guys Working on expansion joint detail | Subcontractor | Joe Hoyle | [5 empty] | 9 | 10 |  |  | Scaffold and boom lift | [5 empty] | Corrugated / Screen wall Subgirt Zee | [22 empty] | 32 | 10 | [6 empty] | 300 | 10
24046 | UAB Biomedical Research and Psycholgy | 2025-01-30 | Naza Padron | We had to leave the project for areas that were not ready... we had to remove panels because of the electricians 34 hours | JWMCD Crew | Wylie McDougall | false | [6 empty] | false |  | 2. 65' boom lifts | false
24046 | UAB Biomedical Research and Psycholgy | 2025-01-30 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 60 | false |  | 2. 65' boom lifts | false |  |  |  |  | ACM Insulation Subgirt Zee | 22 | 40 | [24 empty] | 192 | 10 |  |  | 190 | 10
22061 | 19th and Church | 2025-01-29 | JC Panels | Panel installation, fins clips installation , caulking | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | false |  |  | false |  |  |  |  | ACM | 6
23029 | BNA Concourse D | 2025-01-29 | Tony | did layout on 209. issues with cw height. ended up doing the lay out on the whole airside wall between concessions and record node also moved a crew over to land lide since an area opened up | JWMCD Crew | Marc Ribar | true | issue with the layout stated above in notes, two holes above door on landside while installation. forklift in laydown yard would not start for some reason, has been fixed now |  |  |  | 6 | 10 | true | a 60' man lift | 4 man booms, 2 80' 2 60' | false |  |  | 4 |  | IMP Layout | [8 empty] | 16 | 60
24015 | New Pope School | 2025-01-29 | rafael gomez | we work on ceiling panels on area 409,411and 311 | Subcontractor | Wylie McDougall | false |  |  |  |  | 6 | 9 | false |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 20 | 9 |  |  | 300 | 9 |  |  | 500 | 9
24018 | QTS-NAL1-DC1 | 2025-01-29 | Saul chicas | Crew1 Penthouse area 7 guys Installing corrugated panels (35pcs) Installing Z-girt (200 LF) Building and moving the scaffold Crew2 2 guys Working on expansion joint detail | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift/scaffold | [5 empty] | Corrugated / Screen wall Subgirt Zee | [22 empty] | 35 | 10 | [6 empty] | 200 | 10
24025 | Madison Elementary | 2025-01-29 | Norberto Velasquez | Openings made are all area A and 33,32,31 of area B | Subcontractor | Wylie McDougall | [5 empty] | 3 | 7 | [8 empty] | Flashing | [32 empty] | 14 | 7
24046 | UAB Biomedical Research and Psycholgy | 2025-01-29 | Naza Padron | We had to leave the project for areas that were not ready... we had to remove panels because of the electricians 34 hours | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 48 | false |  | 2. 65' boom lifts | false |  |  |  |  | Insulation Other Subgirt Zee | [26 empty] | 74 | 6 |  |  | 52 | 8 | [10 empty] | 34 | 34
22061 | 19th and Church | 2025-01-28 | JC Panels | Panel installation, modification, clips installation for fins | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | false |  |  | false |  |  |  |  | ACM | 9
23029 | BNA Concourse D | 2025-01-28 | Tony | We continued installing base panels on airside, had meeting with HP to plan out installation of acm panels on roof. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 6 | 10 | false |  | 2 85’ man lifts, 1 65’ man lift, 1 5k lull | false |  |  |  |  | Coping IMP | [8 empty] | 12 | 60 | [30 empty] | 1600 | 2
23033 | Iron Mountain VA6 | 2025-01-28 | Marvin Blanco | Working in the extra work for Hitt Installing 4 remake panels in the stairs 4 and also installing the corner of the building and also reinstalling 4 panels that we take down for the singing guys in the corner of the building by the entry there's one issues the panels still are getting damaged by others guys the people don't care | Subcontractor | Joe Hoyle | false |  |  |  |  | 3 | 11 | true | 4 ACM panels | Boomlift | false |  |  |  |  | ACM | 4 | 44
23067 | Boeing PAC 3 | 2025-01-28 | Kevin Morris | Cut out lights installed panels and trim | Subcontractor | Chris Buttrey | false |  |  |  |  | 4 | 10 | false |  | 60' boom lifts x 2 | false |  |  |  |  | IMP Trim | [8 empty] | 7 | [27 empty] | 80
23071 | Nashville Yards 9A3 & 9B3 | 2025-01-28 | Marvin Blanco | Fixing the C4 and C1 opening because my guys took the layout wrong so in the C4 they took everything down and put everything right back so they finished today the C4 but we still have to fix the C1 tomorrow it's going to take around 2 to 3 hours and them everything will be done we can cancel every machine the 2 boomlift and a little forklift | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 8 | false |  | Boomlift | false |  |  |  |  | Other | [42 empty] | Fixing tubes | 24
24001 | McEwen Northside | 2025-01-28 | Marvin Blanco | Installing angles for the panels in the south west corner of the building and putting silicone in the north west corner with the scaffolding also installing coping in the screenwall cleaning the roof and parking garage installing the bellara panels in the soffit for today we don't have any issues | Subcontractor | Josh McPherson | false |  |  |  |  | 13 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Caulking Coping Other | 8 | 40 | [18 empty] | 85 | 20 | [18 empty] | 14 | 30 | Bellara panels | 40
24015 | New Pope School | 2025-01-28 | rafael gomez | we repair some damages from ceiling panels ,and we start to install the j's on the windows | Subcontractor | Wylie McDougall | false |  |  |  |  | 5 | 9 | true | boomlift | boomlift | false |  |  |  |  | Corrugated / Screen wall Trim | [22 empty] | 20 | 9 | [12 empty] | 100 | 9
24018 | QTS-NAL1-DC1 | 2025-01-28 | Saul chicas | Crew1 Penthouse area 7 guys Installing corrugated panels (30 pcs) Installing Z-girt (150 LF) Building and moving the scaffold Crew2 2 guys Installing corner angle at all the corners on the screen wall and penthouse | Subcontractor | Joe Hoyle | [5 empty] | 9 | 10 |  |  | Boom lift / scaffold | [5 empty] | Corrugated / Screen wall Subgirt Zee | [22 empty] | 30 | 10 | [6 empty] | 150 | 10
24020 | QTS ATL2 DC2 Osgood | 2025-01-28 | Marvin Blanco | Today the guys was trying to figure out to install the canopies but it looks there's a little issue in the canopies we think they are backwards so we couldn't do anything today because we was waiting for the silicone also it just arrived this afternoon | Subcontractor | Dillon Bowman | false |  |  |  |  | 6 | 11 | true | Silicone | Boomlift | false |  |  |  |  | Other | [42 empty] | Nothing because we just try to work in the canopies but it looks backwards | 66
24025 | Madison Elementary | 2025-01-28 | Norberto Velasquez | continuing with the preparation of the partial elevations (207) 16, 17. | Subcontractor | Wylie McDougall | [5 empty] | 3 | 7 | [8 empty] | Flashing Insulation Other | [26 empty] | 16 | 2 |  |  |  |  | 15 | 7 | [8 empty] | Membrane blueskin installation | 5
24046 | UAB Biomedical Research and Psycholgy | 2025-01-28 | Naza Padron | 5 panels have to be cutter and router at west side above the canopy 20 hours | JWMCD Crew | Wylie McDougall | true | South elevation we had delays due to a window that was not sealed and the brick wall had many edges that need to be cutting |  |  | sunny | 6 | 60 | false |  | 2. 65' boom lifts | false |  |  |  |  | ACM Insulation Other Subgirt Zee | 20 | 20 | [24 empty] | 210 | 8 |  |  | 210 | 12 | [11 empty] | 20
23029 | BNA Concourse D | 2025-01-27 | Tony |  | JWMCD Crew | Marc Ribar | true | top of window sil and sides of cw need to be caulked |  |  | Clear | 6 | 10 | true | 4 bundles of imp | 3 man booms, 2 80' ,1 60' | false |  |  |  |  | Flashing IMP | [8 empty] | 11 | 60 | [22 empty] | 60 | 1
23033 | Iron Mountain VA6 | 2025-01-27 | Marvin Blanco | Doing extra work in the stairs 4 taking panels down for Hitt because they're damaged but others guys also waiting for the new panels we have one little issue with the stairs 3 and 4 electric guys are taking a little longer to finish the singing cables that's the only thing we have left after the 4 new panels that we are going to replace if we get the panels tomorrow we will be done tomorrow if not Wednesday after that it's going to be a waiting for the singing guys there some concrete in the face of the panels because the concrete guys doesn't protect somebody else material they don't care everywhere we have damaged or scratches panels because those guys | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 10 | false |  | Boomlift | false |  |  |  |  | Other | [42 empty] | Waiting for panels and taking down 4 panels | 40
23067 | Boeing PAC 3 | 2025-01-27 | Kevin Morris | Rain so jobsite was muddy installed 2 fascia panels and 4 soffit imp panels cut out 4 holes for lights | Subcontractor | Chris Buttrey | false |  |  |  |  | 4 | 10 | false |  | 2 60' boom lifts | false |  |  |  |  | IMP | [8 empty] | 6
23071 | Nashville Yards 9A3 & 9B3 | 2025-01-27 | Marvin Blanco | Finishing the panels in the north elevation and fixing 5 tubes in the south elevation because one of the guys gets a wrong dimensions for the perforated panels but we will be done tomorrow fixing and finishing the work at plaza and commerce Street | Subcontractor | Dillon Bowman | false |  |  |  |  | 4 | 12 | false |  | Boomlift | false |  |  |  |  | Plate |  |  | 20 | 48
24001 | McEwen Northside | 2025-01-27 | Marvin Blanco | Installing acm panels moving material today was a great day because finally Hoar guys let us work well also the weather it's getting better thanks God for today no issues everything is working good | Subcontractor | Josh McPherson | false |  |  |  |  | 13 | 10 | true | Insulation | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM | 18 | 130
24015 | New Pope School | 2025-01-27 | rafael gomez | we came to the job site an we found to much damage | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 4 | true | zee ,flashing | none | false |  |  |  |  | Other | [43 empty] | 4
24018 | QTS-NAL1-DC1 | 2025-01-27 | Saul chicas | 01/25 Working on south, west wall PH 2 boom lift 4 guys on the scaffold 2 guys on the ground 2 guys working on the south wall from the roof 30 panels corrugated 200’ LF z-girt We cut each panel to follow the dimensions of the drawings | Subcontractor | Joe Hoyle | [5 empty] | 10 | 1 |  |  | Boom lift / scaffold | [5 empty] | Corrugated / Screen wall Subgirt Zee | [22 empty] | 30 | 10 | [6 empty] | 200 | 10
24020 | QTS ATL2 DC2 Osgood | 2025-01-27 | Marvin Blanco | Finishing the panels red panels also We have to glue 1 panel because it was wrong but we fixed in the job site also fixed the louvers blades the ones gets damaged by others guys in the job site waiting for silicone almost a week tomorrow the guys are going to start installing the canopy but we don't have really good drawings I hope tomorrow we can get everything we need to keep moving we need bits for drilling concrete for the canopy and also good drawings for dimensions from the finish floor to the top of the canopy | Subcontractor | Dillon Bowman | true | Silicone |  |  | Cold | 6 | 10 | false |  | Boomlift | false |  |  |  |  | ACM | 10 | 60
24025 | Madison Elementary | 2025-01-27 | Norberto Velasquez | Starting to install flashing and finishing the first phase in the south and north partial elevation 209-21,22. | Subcontractor | Wylie McDougall | [5 empty] | 3 | 7 | [8 empty] | Flashing Insulation Other | [26 empty] | 5 | 2 |  |  |  |  | 5 | 7 | [8 empty] | Membrane blueskin installation | 5
24046 | UAB Biomedical Research and Psycholgy | 2025-01-27 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 6 | 60 | true | Crate with blades, boxes of screws | 2. 65' boom lifts | false |  |  |  |  | ACM Flashing | 29 | 42 | [28 empty] | 140 | 14 | 20 | 4
24018 | QTS-NAL1-DC1 | 2025-01-26 | Saul chicas | 01/26 Working on west&south wall PH 7 guys 8 hours from the roof 26 panels corrugated 100’ z-girt We bring around 70 panels with lift | Subcontractor | Joe Hoyle | [5 empty] | 7 | 7 |  |  | Scaffold /. Boom lift | [5 empty] | Corrugated / Screen wall Subgirt Zee | [22 empty] | 26 | 7 | [6 empty] | 100 | 7
24018 | QTS-NAL1-DC1 | 2025-01-25 | Saul chicas | 01/25 Working on west&east wall PH 2 boom lift 4 guys on the machines 2 guys on the ground 2 guys working on the south wall from the roof 33 panels corrugated We cut each panel to follow the dimensions of the drawings | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Scaffold / boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 38 | 10
24046 | UAB Biomedical Research and Psycholgy | 2025-01-25 | Naza Padron | N/A | JWMCD Crew | Wylie McDougall | false |  |  |  |  | 4 | 32 | false |  | 2. 65' boom lifts | false |  |  |  |  | ACM | 17 | 20 | [28 empty] | 130 | 12
22061 | 19th and Church | 2025-01-24 | JC Panels | Panel installation, clip and caulking | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | false |  |  | false |  |  |  |  | ACM | 4
23067 | Boeing PAC 3 | 2025-01-24 | Kevin Morris | Installed 2 soffit panels and installed front facia trim and starter clips | Subcontractor | Chris Buttrey | false |  |  |  |  | 4 | 8 | false |  | 2 60' boom lifts | false |  |  |  |  | IMP Trim | [8 empty] | 2 | [27 empty] | 120
24025 | Madison Elementary | 2025-01-24 | Norberto Velasquez | Entrances is ready phase 1 for inspection. | Subcontractor | Wylie McDougall | [5 empty] | 3 | 8 | [8 empty] | Other Subgirt Zee | [30 empty] | 12 | 8 | [10 empty] | Membrane blueskin | 4
24046 | UAB Biomedical Research and Psycholgy | 2025-01-24 | Naza Padron | Unloading material | JWMCD Crew | Wylie McDougall | false | [5 empty] | 10 | false |  | 2. 65' boom lifts | false |  |  |  |  | ACM | 8 | 20 | [28 empty] | 60 | 12
22061 | 19th and Church | 2025-01-23 | JC Panels | Panel installation, modification, clips for the fins installation, peel the panels, framing | Subcontractor | Josh McPherson | false |  |  |  |  | 7 |  | false |  |  | false |  |  |  |  | ACM | 4
23033 | Iron Mountain VA6 | 2025-01-23 | Marvin Blanco | Doing extra work in the job site remaking a big panel by the fire thing also taking panels down from the stairs 3 | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 10 | false |  | Boomlift | false |  |  |  |  | ACM Other | 1 | 12 | [40 empty] | Taking panels down in the stairs 3 in the back of the wall | 28
23067 | Boeing PAC 3 | 2025-01-23 | Kevin Morris | Installed trim, cut and installed panels on mezzanine soffit panels a little difficult to engage | Subcontractor | Chris Buttrey | true | Framing for soffit completed at 8am |  |  | 12 | 4 | 10 | true | T650 boom | T650 boom | false |  |  |  |  | Trim | [36 empty] | 50
23071 | Nashville Yards 9A3 & 9B3 | 2025-01-23 | Marvin Blanco | Installing tubes and plate panels cutting angles to make work because we don't have enough angles to finish the job | Subcontractor | Dillon Bowman | false |  |  |  |  | 4 | 10 | false |  | Boomlift | false |  |  |  |  | Plate Tubing |  |  | 20 | 20 | [24 empty] | 10 | 20
24001 | McEwen Northside | 2025-01-23 | Marvin Blanco | Installing Zs" and insulation Also ACM panels taking dimensions for a coping, today we try to work in the west elevation but this job is always something Hoar guys doesn't let us work in the swing stage because the concrete guys needs the area so we are losing to much time moving from one area to an another area. | Subcontractor | Josh McPherson | false |  |  |  |  | 13 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM | 10 | 130
24018 | QTS-NAL1-DC1 | 2025-01-23 | Saul chicas | 01/23 Working on west wall PH 3 boomlift 4 guys on the machines 3 guys on the ground 28 panels corrugated 230’ z-girt We also spent 3 hours 3 guys removing the panels on the vestibules. 2 crews Working on the PH 7 guys 18 panels installed 130’ z-girt Moving material as well | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift and scaffold | [5 empty] | Corrugated / Screen wall Subgirt Zee | [22 empty] | 46 | 10 | [6 empty] | 360 | 10
24020 | QTS ATL2 DC2 Osgood | 2025-01-23 | Marvin Blanco | Installing ACM panels throwing a way some creates and also changing boomlift | Subcontractor | Dillon Bowman | false |  |  |  |  | 6 | 10 | false |  | Boomlift | false |  |  |  |  | ACM | 12 | 60
24025 | Madison Elementary | 2025-01-23 | Norberto Velasquez | Preparing both north and south entrances and completing a portion of the elevations. | Subcontractor | Wylie McDougall | [5 empty] | 3 | 8 | true | Subgirt zee | [6 empty] | Subgirt Zee | [30 empty] | 15 | 8
23033 | Iron Mountain VA6 | 2025-01-22 | Marvin Blanco | Fixing coping in the front of the building in the top of the windows also taking 4 more panels down for the singing this extra work for everyone because we don't supposedly take anything down but Joe talk to the Hitt team to give us a green light also working in the flashing under the panels it's extra work also | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 10 | false |  | Boomlift | false |  |  |  |  | Other | [42 empty] | Fixing coping and taking panels down for the singing guys and snap trim | 40
23067 | Boeing PAC 3 | 2025-01-22 | Kevin Morris | Installed trim and panels and layout for soffit on mezzanine | Subcontractor | Chris Buttrey | true | Framing for soffit not complete |  |  | 5° | 4 | 8 | true | T650 boom | T650 boom | false |  |  |  |  | IMP Layout Trim | [8 empty] | 2 | [27 empty] | 70
23071 | Nashville Yards 9A3 & 9B3 | 2025-01-22 | Marvin Blanco | Installing tubes at the north elevation and cutting tubes also because they are to long also making holes in the tubes for the bolts also cutting plate panels for the openings because they're to longer also | Subcontractor | Dillon Bowman | false |  |  |  |  | 4 | 10 | false |  | Boomlift | false |  |  |  |  | Plate Tubing |  |  | 15 | 20 | [24 empty] | 10 | 20
24001 | McEwen Northside | 2025-01-22 | Marvin Blanco | Moving the swing stage from the north elevation to the west elevation also installing ACM panels in the north west corner working in the soffit with the bellara panels but we have a little issue because I get the wrong dimensions for the panels but tomorrow we are going to try to make it work. | Subcontractor | Josh McPherson | false |  |  |  |  | 13 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Other | 15 | 70 | [40 empty] | Moving the swing stage | 60
24025 | Madison Elementary | 2025-01-22 | Norberto Velasquez | preparations in opening 15 and in partial North elevation. | Subcontractor | Wylie McDougall | [5 empty] | 3 | 8 | [8 empty] | Subgirt Zee | [30 empty] | 10 | 8
22061 | 19th and Church | 2025-01-21 | JC Panels | Panel modification and installation | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | false |  |  | false |  |  |  |  | ACM | 19
23067 | Boeing PAC 3 | 2025-01-21 | Kevin Morris | Installed trim and panels on mezzanine | Subcontractor | Chris Buttrey | false |  |  |  |  | 4 | 10 | true | T650 boom | T650 boom | false |  |  |  |  | IMP Trim | [8 empty] | 9 | [27 empty] | 80
23071 | Nashville Yards 9A3 & 9B3 | 2025-01-21 | Marvin Blanco | Installing tubes and plate panels in the north elevation trying to be finished on this week I hope everything goes well | Subcontractor | Dillon Bowman | false |  |  |  |  | 4 | 10 | false |  | Boomlift | false |  |  |  |  | Plate Tubing |  |  | 19 | 20 | [24 empty] | 14 | 20
24001 | McEwen Northside | 2025-01-21 | Marvin Blanco | Moving swing stage from the south elevation to the west elevation but we have a little issue in the cables they were to short but Colton already ordered a bigger one's he's on top of everything we have guys working in the roof finishing the coping and also guys in the north elevation | Subcontractor | Josh McPherson | false |  |  |  |  | 12 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Coping | 15 | 90 | [38 empty] | 90 | 30
24018 | QTS-NAL1-DC1 | 2025-01-21 | Saul chicas | 2 crews Working on the PH 7 guys 30 panels installed 130’ z-girt Moving material as well. 6 hours We started work late because the weather | Subcontractor | Joe Hoyle | [5 empty] | 7 | 6 |  |  | Boom lift /scaffold | [5 empty] | Corrugated / Screen wall | [22 empty] | 30 | 7
24020 | QTS ATL2 DC2 Osgood | 2025-01-21 | Marvin Blanco | Installing ACM panels but the weather was bad and the job site closed the job site and also tomorrow is going to be closed because to much snow ❄️ today the guys received the canopies | Subcontractor | Dillon Bowman | false |  |  |  |  | 6 | 10 | true | Canopies | Boomlift | false |  |  |  |  | ACM | 10 | 60
24025 | Madison Elementary | 2025-01-21 | Norberto Velasquez | We finished installing partial north and south elevation and starting and another elevation | Subcontractor | Wylie McDougall | [5 empty] | 2 | 8 | [8 empty] | Subgirt Zee | [30 empty] | 54 | 8
23028 | 1000 Church YMCA | 2025-01-20 | Marvin Blanco | Installing plate panels inside of the building plate columns we have a little issues because the paint is coming off of the panels in the corners when we bend the panels | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 10 | false |  | Ladder | false |  |  |  |  | Plate |  |  | 8 | 30
23033 | Iron Mountain VA6 | 2025-01-20 | Marvin Blanco | Installing ACM flashing in the bottom of the stairs 5 it's taking a little longer because there is not space in the bottom | Subcontractor | Joe Hoyle | true | Silicone |  |  | Cold | 4 | 10 | false |  | Boomlift | false |  |  |  |  | Other | [42 empty] | ACM flashing or plate | 40
23067 | Boeing PAC 3 | 2025-01-20 | Kevin Morris | Orientation, got badges, staged materials | Subcontractor | Chris Buttrey | false |  |  |  |  | 4 | 9 | false |  |  | false |  |  |  |  | Other | [42 empty] | Mobilization | 36
23071 | Nashville Yards 9A3 & 9B3 | 2025-01-20 | Marvin Blanco | Installing clips for the tubes in the north elevation for know we have everything we need this morning Dillion change our boomlift because the other one was leaking oil | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 10 | false |  | Boomlift | false |  |  | 30 |  | Layout
24001 | McEwen Northside | 2025-01-20 | Marvin Blanco | Working in the roof screenwall installing coping and also taking material to the roof taking a little longer because the elevator takes forever, Working in the north elevation and also south west elevation but it's to cold so we are not installing panels like we suppose to install | Subcontractor | Josh McPherson | false |  |  |  |  | 11 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Coping | 18 | 80 | [38 empty] | 60 | 30
24018 | QTS-NAL1-DC1 | 2025-01-20 | Saul chicas | Today we do not work due to the bad weather | Subcontractor | Joe Hoyle | true | Bad weather |  |  | To fold and raining | 1 | 0 |  |  | Boom lift scaffold | [5 empty] | ACM | 0 | 0
24020 | QTS ATL2 DC2 Osgood | 2025-01-20 | Marvin Blanco | Trying to install panels acm but the guys are waiting for revils so the started installing the last piece of the louvers blades the one was damaged for others guys in the job site we have one little issue the boomlift doesn't make it where we need it but kaelyn she's going to swap it for us | Subcontractor | Dillon Bowman | true | Revils |  |  | Cold | 6 | 10 | false |  | Boomlift | false |  |  |  |  | Louvre | [24 empty] | 10 | 60
24025 | Madison Elementary | 2025-01-20 | Norberto Velasquez | Working Partial South Elevation. | Subcontractor | Wylie McDougall | [5 empty] | 3 | 8 | [8 empty] | Subgirt Zee | [30 empty] | 30 | 8
23033 | Iron Mountain VA6 | 2025-01-19 | Marvin Blanco | Working in the stairs five installing coping everything is done already the only thing we need is silicone for all the windows opening | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 10 | false |  | Boomlift | false |  |  |  |  | Coping | [40 empty] | 1200 | 40
23071 | Nashville Yards 9A3 & 9B3 | 2025-01-19 | Marvin Blanco | Installing plate panels in the commers street also installing tubes in the north elevation of the building we have a little issues we the boomlift we get on Friday it's leaking oil and also don't work for that elevation we need to swap it for a smaller one please | Subcontractor | Dillon Bowman | false |  |  |  |  | 6 | 10 | false |  | Boomlift | false |  |  |  |  | Plate Tubing |  |  | 12 | 30 | [24 empty] | 12 | 30
24001 | McEwen Northside | 2025-01-19 | Marvin Blanco | Moving boomlift from the west elevation and also finishing north west corner working in the south west corner also we don't have anything issues we have everything we need the only problem we have is on Saturday we just work 6 hours a day | Subcontractor | Josh McPherson | false |  |  |  |  | 11 | 6 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM | 15 | 66
24020 | QTS ATL2 DC2 Osgood | 2025-01-19 | Marvin Blanco | Finishing the screenwall and also installing ACM panels we have one problem my guys don't have any more revils for the joint I don't know why all the time shop guys don't put enough revels or trims I don't know how they call that but I hope on the next one they put some more | Subcontractor | Dillon Bowman | true | Revils for the joint |  |  | Cold | 6 | 10 | false |  | Scaffolding , boomlift | false |  |  |  |  | ACM Coping | 8 | 30 | [38 empty] | 1200 | 30
22061 | 19th and Church | 2025-01-17 | JC Panels | Panel installation and modio | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | false |  |  | false |  |  |  |  | ACM | 10
24025 | Madison Elementary | 2025-01-17 | Norberto Velasquez | We started working on the partial south elevation with the installation of subgrade zee. | Subcontractor | Wylie McDougall | true | We were asked to leave the place where we were working because they were going to unload a delivery for a company that works inside the building. |  |  |  | 4 | 8 | [8 empty] | Caulking Corrugated / Screen wall Subgirt Zee | [20 empty] | 44 | 7 | 6 | 2 | [6 empty] | 195 | 8
22061 | 19th and Church | 2025-01-16 | JC Panels | Panel modification and installation | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | false |  |  | false |  |  |  |  | ACM | 12
24018 | QTS-NAL1-DC1 | 2025-01-16 | Saul chicas | Crew1 3 guys Installing z-girt Installing corrugated laminate 12 panels Crew2 3 guys installing z-girt Installing corrugated laminate 13 panels Crew3 2 guys Bringing material from the ground to the roof by the boom lift | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Ladder boom lift and scaffold | [5 empty] | Corrugated / Screen wall Subgirt Zee | [22 empty] | 25 | 10 | [6 empty] | 400 | 10
24025 | Madison Elementary | 2025-01-16 | Norberto Velasquez | Continuing with the phase 2 and installing panels corrugated. | Subcontractor | Wylie McDougall | [5 empty] | 4 | 8 | [8 empty] | Caulking Corrugated / Screen wall Other | [20 empty] | 41 | 3 | 38 | 8 | [18 empty] | Installation of "J" Channels | 6
22061 | 19th and Church | 2025-01-15 | JC Panels | Panels modifications and installation . 7 panels modified | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | false |  |  | false |  |  |  |  | ACM | 12
24018 | QTS-NAL1-DC1 | 2025-01-15 | Saul chicas | 01/15 Crew 1 3 guys 5 hour ( bc the weather) East office Vestibule 30 clips Knight wall system 35’ track bar 180’ sf insulation We also remake and install the panel on the face of the canopy. Wef Crew 2 Penthouse 4 guys 5 hours 100’ of z-girt 8 pcs laminate | Subcontractor | Joe Hoyle | [5 empty] | 8 | 5 |  |  | Boom lift/scaffold | [5 empty] | Hat Channel Insulation Other Subgirt Zee | [26 empty] | 180 | 5 |  |  | 100 | 5 |  |  | 60 | 5 | [6 empty] | We installed 5 foam panels | 5
24025 | Madison Elementary | 2025-01-15 | Norberto Velasquez | Continuing with the phase 2 and installing panels corrugated. | Subcontractor | Wylie McDougall | [5 empty] | 4 | 8 | [8 empty] | Caulking Corrugated / Screen wall Insulation Other | [20 empty] | 76 | 3 | 20 | 5 |  |  | 66 | 5 | [14 empty] | Installation of "J" Channel | 3
22061 | 19th and Church | 2025-01-14 | JC Panels | Panels modification and installation | Subcontractor | Josh McPherson | false |  |  |  |  | 9 | 10 | false |  | 2 boom lifts and 1 scissor lift | false |  |  |  |  | ACM | 16
23028 | 1000 Church YMCA | 2025-01-14 | Marvin Blanco | Today we received plate panels in the job site but we have a little issue with the panels when my guys fold the panel the paint in the router falls off also they are short in the side of the windows the panels in the creates no protection | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 10 | true | Plate panels | Latter | false |  |  |  |  | Plate |  |  | 1 | 30
23033 | Iron Mountain VA6 | 2025-01-14 | Marvin Blanco | Fixing L angles in the openings by the stairs 2,3,4 because windows guys damaged every single angles with the plastic malet also closing the big gaps in the openings | Subcontractor | Joe Hoyle | true | Grey silicone |  |  | Cold | 4 | 10 | false |  | Boomlift | false |  |  |  |  | Flashing | [32 empty] | 280 | 40
23071 | Nashville Yards 9A3 & 9B3 | 2025-01-14 | Marvin Blanco | Installing plate panels between the tubes and receiving screen panels for the face tomorrow we will know how those panels works | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 10 | true | Face panels for the tubes | Boomlift | false |  |  |  |  | Plate |  |  | 14 | 30
24001 | McEwen Northside | 2025-01-14 | Marvin Blanco | Today we damaged some stones in the job site panels installation Designs will be responsible for paid but we also install ACM panels in the north west corner and east side by the damaged stones I apologize | Subcontractor | Josh McPherson | false |  |  |  |  | 11 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM | 15 | 110
24018 | QTS-NAL1-DC1 | 2025-01-14 | Saul chicas | 01/13 Crew 1 2 guys 7 hour ( bc the weather) East office Vestibule 30 clips Knight wall system 35’ track bar 180’ sf insulation Crew 2 Penthouse 4 guys 7 hours 10 foam panels installed We also brought the panels from the ground by the boom lift 48 pieces of laminate Crew3 2 guys We have to move all the material from the yard to other area because GC requires us to do. | Subcontractor | Joe Hoyle | true | Bad weather |  |  | Snow | 8 | 7 |  |  | Boom lift and scaffold | [5 empty] | Hat Channel Insulation Other | [26 empty] | 180 | 7 | [6 empty] | 80 | 7 | [6 empty] | We installed 30 clips of night wall system also we installed 10 foam panels | 7
24025 | Madison Elementary | 2025-01-14 | Norberto Velasquez | Continuing with the installation of corrugated panels and in other openings phase 2 continues. | Subcontractor | Wylie McDougall | [5 empty] | 4 | 8 | [8 empty] | Caulking Corrugated / Screen wall Other | [20 empty] | 22 | 1 | 37 | 8 | [18 empty] | Installation of "J" Channel | 8
22061 | 19th and Church | 2025-01-13 | JC Panels | Panel modification and installation. 6 panels modified | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | true | Angles | 2 boom lift 1 scissor lift | false |  |  |  |  | ACM | 12
23033 | Iron Mountain VA6 | 2025-01-13 | Marvin Blanco | Today I was checking everything in the job site and it looks like we are going to be done everything we have ready in the end of this week the only thing we have pending is the panels in the stairs 3 and stairs 4 in the back of the wall and Also some extra work in the bottom of the stairs 2,3,4,5 Hitt was us to put some ACM plates under of the panels | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 10 | false |  | Boomlift | false |  |  |  |  | Flashing | [32 empty] | 400 | 40
24001 | McEwen Northside | 2025-01-13 | Marvin Blanco | Today the guys were installing panels in the north elevation and also south elevation ACM panels Zs and insulation working in the west elevation also trying to finish the top area because we want to avoid the swing stage and get it faster with the boomlift everything else is good Colton is giving us everything we need thanks very much | Subcontractor | Josh McPherson | false |  |  |  |  | 11 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM | 10 | 110
24018 | QTS-NAL1-DC1 | 2025-01-13 | Saul chicas | 01/13 Crew 1 3 guys 9.5 East office Vestibule 60 clips Knight wall system 130’ track bar 240’ sf insulation 6 panels installed Crew 2 Penthouse 4 guys 9.5hours 13 foam panels installed We also brought the panels from the ground by the boom lift Crew3 1 guys Peeling panels on east office also bringing panels to the roof with crew2 | Subcontractor | Joe Hoyle | [5 empty] | 8 | 9.5 |  |  | Boom lift / scaffold | [5 empty] | ACM Hat Channel Insulation Other | 6 | 9.5 | [24 empty] | 240 | 9.5 | [6 empty] | 130 | 9.5 | [6 empty] | We installed 13 foam panels | 9.5
24020 | QTS ATL2 DC2 Osgood | 2025-01-13 | Marvin Blanco | Today the guys finished all the insulation that they have in the screenwall and they don't have anything more for install in the screenwall so we are going to stop working in the roof till we get more insulation we need about 2 palets or more of insulation in the ACM panels we something to tie of with the boomlift because my guys they don't riches all away to the precast after that I think we are good | Subcontractor | Dillon Bowman | true | Insulation |  |  | Cold | 6 | 11 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM | 9 | 66
24025 | Madison Elementary | 2025-01-13 | Norberto Velasquez | The second phase and the installation of corrugated panels continue. | Subcontractor | Wylie McDougall | [5 empty] | 4 | 8 | [8 empty] | Caulking Corrugated / Screen wall Other | [20 empty] | 42 | 1 | 48 | 8 | [18 empty] | Installation of J Channel | 8
24018 | QTS-NAL1-DC1 | 2025-01-12 | Saul chicas | 01/12 Crew 1 4 guys 6 hours East office We modified the panels at the ceiling and install it’s Crew 2 4 guys 6 hours East office We modified the 6 panels and install on the vestibule | Subcontractor | Joe Hoyle | [5 empty] | 8 | 6 |  |  | Boom lift / scaffold | [5 empty] | ACM | 3 | 10
24018 | QTS-NAL1-DC1 | 2025-01-11 | Saul chicas | 01/11 Crew 1 3 guys 8hours East office Vestibule 60 clips Knight wall system 130’ track bar 240’ sf insulation Crew 2 3 guys 8 hours East office North Canopy 7 panels installed 64’ sf insulation Both corners on this elevation don’t work. Crew3 2 guys Cleaning our areas and also peeling panels on east office canopy | Subcontractor | Joe Hoyle | [5 empty] | 8 | 8 |  |  | Boom lift / scaffold | [5 empty] | ACM Hat Channel Insulation | 7 | 8 | [24 empty] | 300 | 8 | [6 empty] | 130 | 8
24025 | Madison Elementary | 2025-01-10 | Norberto Velasquez | Ongoing work is underway on the second phase of the project, which entails the installation of the J Channel and insolation. Upon the successful completion of the second phase, the installation of corrugated o panels will commence. | Subcontractor | Wylie McDougall | [5 empty] | 4 | 8 | [8 empty] | Caulking Corrugated / Screen wall Insulation Other | [20 empty] | 36 | 2 | 24 | 8 |  |  | 200 | 5 | [14 empty] | Installation J Channel | 5
24018 | QTS-NAL1-DC1 | 2025-01-09 | Saul chicas | Crew1 West elevation 3 guys Installing coping and clips for the comping 40’ Coping 40’clips of coping Base flashing and comping is done 100% on this elevation We jump to north elevation canopy installing insulation. Crew2 North elevation 3 guys Installing coping and clips for the comping 250’ copings 250’clips of coping Crane is still working on this elevation Only 4 coping left plus 8 copings that is gonna be where the crane! Crew3 East office 3 guys Installing insulation and night wall system 280’ sf insulation 200’ LF track bar 120 clips. | Subcontractor | Joe Hoyle | [5 empty] | 9 | 10 |  |  | Boom lift and scaffold | [5 empty] | Coping Hat Channel Insulation | [26 empty] | 280 | 10 | [6 empty] | 200 | 10 |  |  |  |  | 290 | 10
23033 | Iron Mountain VA6 | 2025-01-08 | Marvin Blanco | Installing ACM panels in the stairs 5 everything is working well for now there is only 1 issue some body else paint the canopy panels we don't know who did it | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 10 | false |  | Boomlift | false |  |  |  |  | ACM | 5 | 40
24001 | McEwen Northside | 2025-01-08 | Marvin Blanco | Installing ACM panels in the north west corner trying to finish that elevation because we had a lot of problems there so we have a couple of they to work with the boomlift and try to finish everything we can because it's all away up | Subcontractor | Josh McPherson | false |  |  |  |  | 11 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM | 10 | 110
24018 | QTS-NAL1-DC1 | 2025-01-08 | Saul chicas | Crew1 North elevation 3 guys Installing coping and clips for the comping 250’ base flashing 250’clips of coping Crane is still working on this elevation. Crew2 West&South elevation 3 guys Installing coping, base flashing and corner piece 50’ copings 50’ clips of copings 2 piece of corners. Crew3 2 guys We unloaded the delivery We start moving material to the east office We start to do the layouts at the vestibules and install the knight wall system. | Subcontractor | Joe Hoyle | [5 empty] | 9 | 10 | true | ACM | Boom lift and scaffold | [5 empty] | Coping Flashing Other | [32 empty] | 250 | 10 | [6 empty] | 50 | 10 | We installed 50 clicks for coping | 10
24020 | QTS ATL2 DC2 Osgood | 2025-01-08 | Marvin Blanco | Installing ACM panels in the column but in the top of the column I think we are going to have a issues for install the coping panels we are not able to reach out all away to the precast also the female strushon it's to big in the 45 they have to be cut in the job site | Subcontractor | Dillon Bowman | false |  |  |  |  | 6 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Corrugated / Screen wall | 5 | 30 | [20 empty] | 15 | 30
22061 | 19th and Church | 2025-01-07 | JC Panels | Panel installation and modification | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | true | Insolation | 2 boom lifts | false |  |  |  |  | ACM | 8
23033 | Iron Mountain VA6 | 2025-01-07 | Marvin Blanco | Installing ACM panels in the stairs 5 but it's very slow because the weather it's to bad Monday the guys have to leave the job site because Hitt construction closed the job site because the weather | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 10 | false |  | Boomlift | false |  |  |  |  | ACM | 6 | 40
23071 | Nashville Yards 9A3 & 9B3 | 2025-01-07 | Marvin Blanco | We were to the job site this morning but we couldn't work because we don't have that city permit to work in the street | Subcontractor | Dillon Bowman | true | Perforated panels |  |  | Cold | 3 | 4 | false |  | Boomlift | false |  |  |  |  | Other | [42 empty] | Nothing | 12
24001 | McEwen Northside | 2025-01-07 | Marvin Blanco | Installing ACM panels in the north west corner and south west elevation we had everything we need except for the silicone bronze | Subcontractor | Josh McPherson | false |  |  |  |  | 11 | 10 | false |  | Scaffolding , boomlift and forklift, swing stage. | false |  |  |  |  | ACM | 12 | 110
24018 | QTS-NAL1-DC1 | 2025-01-07 | Saul chicas | Crew1 North elevation 3 guys Installing coping and base flashing 250’ base flashing 40’ of coping We also have delays bc one crane is working on this elevation too. Crew2 West&South elevation 3 guys Installing coping, base flashing and corner piece 30’ copings 100’ base flashing 3 piece of corners. Crew3 2 guys We unloaded the delivery We start moving material Everything was under snow so we start to clean everything. This climate with low temperatures forces us to stop every so often to warm up inside the building, which makes us lose time, but it is necessary. | Subcontractor | Joe Hoyle | [5 empty] | 9 | 10 | true | ACM delivery | Boom lift and scaffold | [5 empty] | Coping Flashing | [32 empty] | 380 | 10 | [6 empty] | 70 | 10
24020 | QTS ATL2 DC2 Osgood | 2025-01-07 | Marvin Blanco | Installing ACM and metal panels Zs and insulation for now we only have a little issues with the material metal panels they were a little damaged with ACM panels we just need flats straps and 3" screws | Subcontractor | Dillon Bowman | false |  |  |  |  | 6 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Corrugated / Screen wall | 5 | 30 | [20 empty] | 15 | 30
24018 | QTS-NAL1-DC1 | 2025-01-06 | Saul chicas | Today we are not able to work due to the bad weather | Subcontractor | Joe Hoyle | true | Bad weather |  |  | Snow | 1 | 0 |  |  | Boom lift / scaffold | [5 empty] | ACM | 0 | 0
22061 | 19th and Church | 2025-01-03 | JC Panels | Panel fabrication and installation | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | false |  | 2 boom lifts | false |  |  |  |  | ACM | 7
24018 | QTS-NAL1-DC1 | 2024-12-28 | Saul chicas | Crew1 Working on east wall of the PH and north 4 guys We move the scaffold and build 7 foam panels installed. Crew2 Working on south around the door of the PH 4 guys 10 foam panels installed. Crew3 North screen wall 1 guy 25 clips for coping installed 250’ LF | Subcontractor | Joe Hoyle | [5 empty] | 9 | 10 |  |  | Boom lift / scaffold | [5 empty] | Other | [42 empty] | We installed 17 foam panels and also 25 clicks on north screen wall | 10
24018 | QTS-NAL1-DC1 | 2024-12-27 | Saul chicas | Crew1 Working on east wall of the PH 6 guys We move the scaffold and build 7 foam panels installed. Crew2 2 guys Installing coping on west elevation We also bring up to the Roof about 20 foam panels with help of crew1. | Subcontractor | Joe Hoyle | [5 empty] | 8 | 8 |  |  | Boom lift / scaffold | [5 empty] | Coping Other | [40 empty] | 80 | 8 | 7 foam panels installed | 8
24025 | Madison Elementary | 2024-12-27 | Norberto Velasquez | The repairs of the openings windows 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, and 14, respectively, have been completed and are ready for inspection during phase 2. | Subcontractor | Wylie McDougall | [5 empty] | 2 | 8 | [8 empty] | Insulation Other | [26 empty] | 12 | 8 | [14 empty] | J Channel installation | 8
24018 | QTS-NAL1-DC1 | 2024-12-26 | Saul chicas | Today we are not working due to the bad weather | Subcontractor | Joe Hoyle | true | Raining all day |  |  | Bad weather | 1 | 0 |  |  | Boom lift/scaffold | [5 empty] | ACM | 0 | 0
24025 | Madison Elementary | 2024-12-26 | Norberto Velasquez | Continuing with the installation of J Channel, a small strap was possible to ensure the insulation a little more | Subcontractor | Wylie McDougall | [5 empty] | 2 | 8 | [8 empty] | Insulation Other | [26 empty] | 15 | 8 | [14 empty] | J Channel installation | 8
24018 | QTS-NAL1-DC1 | 2024-12-25 | Saul chicas | Crew 1 were working in east office installing ACM panels crew2 were working on south screen wall | Subcontractor | Joe Hoyle | [5 empty] | 8 | 5 |  |  | Scaffold boom lift | [5 empty] | ACM Coping Corrugated / Screen wall Other | 10 | 5 | [20 empty] | 7 | 5 | [16 empty] | 100 | 10 | We installed 50 foot on wood blocking on south screen wall | 5
24025 | Madison Elementary | 2024-12-24 | Norberto Velasquez | The j channel continues to be installed by putting chims for better perfection. | Subcontractor | Wylie McDougall | [5 empty] | 2 | 8 | [8 empty] | Insulation Other | [26 empty] | 9 | 8 | [14 empty] | Installation of J Channel | 8
24025 | Madison Elementary | 2024-12-23 | Norberto Velasquez | The J channel was started with insulation to be placed in each window and shims have been placed for this to perfectly level and square each window. | Subcontractor | Wylie McDougall | [5 empty] | 2 | 8 | true | Reworked cleats | [6 empty] | Insulation Other | [26 empty] | 12 | 8 | [14 empty] | flashing and j channel installation | 8
24018 | QTS-NAL1-DC1 | 2024-12-22 | Saul chicas | Crew1 6 guys 8 hours ( because site close at 3:45pm) Working by the scaffold 10 foam panels Crew2 West elevation 2 guys 12 copings installed with clips | Subcontractor | Joe Hoyle | [5 empty] | 9 | 8 |  |  | Scaffold and boom lift | [5 empty] | Coping Other | [40 empty] | 120 | 8 | We installed 10 foam panels | 8
24018 | QTS-NAL1-DC1 | 2024-12-21 | Saul chicas | Saturday Sunday Crew1 6 guys 8 hours ( because site close at 3:45pm) Working by the scaffold 11 foam panels Crew2 West elevation 2 guys 8 copings installed with clips 8 base flashing | Subcontractor | Joe Hoyle | [5 empty] | 9 | 8 |  |  | Scaffold boom lift | [5 empty] | Coping Flashing Other | [32 empty] | 80 | 8 | [6 empty] | 80 | 8 | We install 11 Foam panels | 8
22061 | 19th and Church | 2024-12-19 | JC Panels | Panel installation | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | true |  | 2 boom lift | false |  |  |  |  | ACM | 15
24018 | QTS-NAL1-DC1 | 2024-12-19 | Saul chicas | Crew1 6 guys We spend 5 hours on the morning reinstalling the foam panels that we removed for the roofers. Then we bring up to the roof 45 foam panels with the boom lift 1 by 1. Crew2 Working on the west elevation Installing the las piece of laminate and the blocking wood, We also when to check the leak we the acm panels | Subcontractor | Joe Hoyle | [5 empty] | 9 | 10 |  |  | Scaffold and boom lift | [5 empty] | Other | [42 empty] | We reninstalled 13 foam panels | 10
24018 | QTS-NAL1-DC1 | 2024-12-18 | Saul chicas | Today we are not working due to the bad weather | Subcontractor | Joe Hoyle | true | Raining all day |  |  | Bad wether | 9 | 0 |  |  | Boom lift | [5 empty] | ACM | 0 | 0
22061 | 19th and Church | 2024-12-17 | JC Panels | Panel installation, modification, panels peeling. | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | false |  | 2 boom lifts | false |  |  |  |  | ACM | 6
23033 | Iron Mountain VA6 | 2024-12-17 | Marvin Blanco | Installing back the panels we take off for the signing guy | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 11 | false |  | Boomlift | false |  |  |  |  | ACM | 6 | 44
23071 | Nashville Yards 9A3 & 9B3 | 2024-12-17 | Marvin Blanco | Installing tubes in the south elevation we just have a couple of angles missing and we should be good | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 10 | false |  | Boomlift | false |  |  |  |  | Tubing | [28 empty] | 200 | 30
24001 | McEwen Northside | 2024-12-17 | Marvin Blanco | Installing Zs in the south elevation and also doing silicone in the north elevation today we couldn't work in the west elevation because others guys take our area so we moving our boomlift to the north elevation | Subcontractor | Josh McPherson | true | Angles in the west elevation from brick guys |  |  | Good condition | 10 | 10 | true | Zs | Scaffolding , boomlift and forklift | false |  |  |  |  | Caulking Subgirt Zee | [20 empty] | 200 | 20 | [8 empty] | 200 | 80
24018 | QTS-NAL1-DC1 | 2024-12-17 | Saul chicas | Crew 1 where working on west elevation installing wood blocking and corrugated panels crew 2 were working on west elevation installing foam panels Crew3 We make a housekeeping on the roof with some crates that we had there. We also spend 4 hours, 4 guys to remove the foam panels from the roof so roofers can install the SS flashing that they forget. | Subcontractor | Joe Hoyle | [5 empty] | 9 | 10 |  |  | Boom lift scaffold | [5 empty] | Corrugated / Screen wall Other | [22 empty] | 6 | 10 | [18 empty] | We installed 200 foot of wood blocking also we installed 10 foam panels at west elevation we have to make 45 cut of the corner and used the 2 boom lift installed the foam panels | 10
24020 | QTS ATL2 DC2 Osgood | 2024-12-17 | Marvin Blanco | Installing metal panels in the screenwall for now we don't have any problems everything is working well thank God | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 10 | false |  | Scaffolding | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 20 | 30
24025 | Madison Elementary | 2024-12-17 | Norberto Velasquez | Preparations and repairs first phase | Subcontractor | Wylie McDougall | [5 empty] | 2 | 8 | [8 empty] | Flashing Other Subgirt Zee | [30 empty] | 96 | 8 | 28 | 8 | [8 empty] | The first phase of the repair continues and preparations have already begun for elevation 211, which is almost ready. | 8
24018 | QTS-NAL1-DC1 | 2024-12-16 | Saul chicas | Today we were working on penthouse installing foam panels due to the rain we only work 3 hours | Subcontractor | Joe Hoyle | true | Raining most of the day |  |  | Bad wether raining all day | 6 | 3 |  |  | Scaffold boom lift | [5 empty] | Other | [42 empty] | We installed 6 foam panels at penthouse | 3
23054 | QTS MAN1 DC2 | 2024-12-14 | Ever MENDOZA | N | Subcontractor | Josh McPherson | [5 empty] | 2 | 10 | [8 empty] | Corrugated / Screen wall Insulation Other Subgirt Zee | [22 empty] | 12 | 5 |  |  | 100 | 5 | [14 empty] | Install coping | 10
23054 | QTS MAN1 DC2 | 2024-12-13 | Ever MENDOZA | N | Subcontractor | Josh McPherson | [5 empty] | 4 | 8 | [8 empty] | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 18 | 20 |  |  | 150 | 6 |  |  | 150 | 6
24018 | QTS-NAL1-DC1 | 2024-12-13 | Saul chicas | Crew1 installed foam panels at penthouse and crew 2 installing ACM panels at East office crew 3 were working on moving the foam panels to the roof | Subcontractor | Joe Hoyle | [5 empty] | 9 | 10 |  |  | Boom lift scaffold | [5 empty] | ACM Hat Channel Insulation | 8 | 10 | [24 empty] | 180 | 10 | [6 empty] | 120 | 10
23054 | QTS MAN1 DC2 | 2024-12-12 | Ever mendoza | N | Subcontractor | Josh McPherson | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | ACM Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 18 | 25 |  |  | 200 | 10 |  |  | 100 | 5
24018 | QTS-NAL1-DC1 | 2024-12-12 | Saul chicas | Crew 1 were working on penthouse installing foam panels we also brought 19 panels with the boom lift to the roof crew 2 were working on East office installing ACM, insulation, clicks, and track and crew 3 were working on getting the foam panels to the roof | Subcontractor | Joe Hoyle | [5 empty] | 9 | 10 |  |  | Scaffold and boom lift | [5 empty] | ACM Hat Channel Insulation Other | 7 | 10 | [24 empty] | 180 | 10 | [6 empty] | 80 | 10 | [6 empty] | We installed 12 phone panels at penthouse and 30 clicks at East office | 10
24020 | QTS ATL2 DC2 Osgood | 2024-12-12 | Marvin Blanco | Installing metal panels for now we don't any big issues just the cold weather is with ice all the panels | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 10 | false |  | Scaffolding | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 20 | 30
24025 | Madison Elementary | 2024-12-12 | Norberto Velasquez | repairs and uninstallation | Subcontractor | Wylie McDougall | [5 empty] | 4 | 8 | [8 empty] | Other | [42 empty] | The repairs have started. We started by removing the windows and repairing the trim. Now it was done as agreed. We did the blueskin and caulking step by step. Now we are waiting for confirmation from GILBANE to continue with the insulation and trim. | 8
24018 | QTS-NAL1-DC1 | 2024-12-11 | Saul chicas | Crew 1 were working on penthouse installing foam panel Crew 2 where working on East office installing ACM panels crew 3 working on north eye brown installing channels and insulation | Subcontractor | Joe Hoyle | true | Raining half of the day |  |  | Bad raining glad of the day we only work 6 hours | 8 | 6 |  |  | Boom lift and and scaffold | [5 empty] | ACM Hat Channel Insulation | 8 | 6 | [24 empty] | 200 | 6 | [6 empty] | 100 | 6
24025 | Madison Elementary | 2024-12-11 |  | No work due to weather. | Subcontractor | Wylie McDougall | [5 empty] | 4 | [9 empty] | Corrugated / Screen wall
23054 | QTS MAN1 DC2 | 2024-12-10 | Ever Mendoza | N | Subcontractor | Josh McPherson | [5 empty] | 4 | 10 | [8 empty] | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 200 | 20 |  |  | 200 | 10 |  |  | 150 | 10
24018 | QTS-NAL1-DC1 | 2024-12-10 | Saul chicas | Crew 1 were working on penthouse East wall installing foam panels, crew 2 were working on East office installing ACM panels and insulation, crew 3 East office north eyebrows installing track and clicks of night wall system | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Scaffold and boon lift | [5 empty] | ACM Hat Channel Insulation | 11 | 10 | [24 empty] | 300 | 10 | [6 empty] | 200 | 10
23054 | QTS MAN1 DC2 | 2024-12-09 | Ever Mendoza | N | Subcontractor | Josh McPherson | [5 empty] | 2 | 10 | [8 empty] | ACM | 5 | 20
24018 | QTS-NAL1-DC1 | 2024-12-09 | Saul chicas | Crew 1 were working on penthouse East wall installing foam panels crew 2 where working on East office installing ACM panels and insulation and crew 3 were working on East office (eye brown ) installing clicks and track channel | Subcontractor | Joe Hoyle | true | All day long we have to be battling with the delivery to be bale to work on East wall penthouse |  |  | Raining in the morning | 9 | 8 |  |  | Boom lift / scaffold | [5 empty] | ACM Hat Channel Insulation Other | 10 | 8 | [24 empty] | 180 | 8 | [6 empty] | 80 | 8 | [6 empty] | We installed 120 clicks of night wall system on north eye brown | 8
23039 | Vantage VA22 | 2024-12-06 | Saul chicas | Today we were working on East yard installing flashing and access doors also we do a good clean up on site we storage or material on a place were WT tell us to put it | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | Flashing Other | [32 empty] | 180 | 10 | [8 empty] | We installed Access door on East yard 4 | 10
24018 | QTS-NAL1-DC1 | 2024-12-06 | Saul chicas | Crew 1 were working on penthouse east wall installing foam panels Crew 2 were working on East office installing ACM panels and insulation and crew 3 were modified panels on East office | Subcontractor | Joe Hoyle | [5 empty] | 9 | 10 |  |  | Scaffold / boom lift | [5 empty] | ACM Insulation Other | 10 | 10 | [24 empty] | 270 | 10 | [14 empty] | We installed 7 foam panels at penthouse | 10
24025 | Madison Elementary | 2024-12-06 | Norberto Velasquez | Work continued on the windows, they were prepared and ready to install corrugated panels. I want to mention that we were asked to move all the material from the area that we had at that time. | Subcontractor | Wylie McDougall | true | They asked us to move all of our material because it was in the way where other people were going to work. It took us half a day to move everything. |  |  |  | 5 | 9 | true | A crate trim aluminum zinc Gray 220 pcs was delivered | [6 empty] | Corrugated / Screen wall Flashing Insulation Subgirt Zee | [22 empty] | 9 | 4 |  |  | 10 | 2 |  |  | 120 | 9 | 30 | 9
22061 | 19th and Church | 2024-12-05 | JC Panels | Panels and reveals installation | Subcontractor | Josh McPherson | false |  |  |  |  | 8 | 10 | false |  | 3 boom lift | false |  |  |  |  | ACM | 7
23054 | QTS MAN1 DC2 | 2024-12-05 |  | No | Subcontractor | Josh McPherson | [5 empty] | 2 | 10 |  |  | Boom lift | [5 empty] | ACM | 4 | 10
24001 | McEwen Northside | 2024-12-05 | Marvin Blanco | Installing ACM panels in the west elevation but the panels They are very wide, there is no way to screw and McDougall is pushing for us to go faster but there is no way to move forward if they do not make the panels correctly and also the project cannot advance much because first we have to drill a steel angle and then drill holes. for concrete it is double or triple work | Subcontractor | Josh McPherson | false |  |  |  |  | 9 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM | 10 | 90
24025 | Madison Elementary | 2024-12-05 | Norberto Velasquez | The panels continued to be installed and windows prepared, which have already been completed. The elevations are already finished. | Subcontractor | Wylie McDougall | true |  |  |  | We started at 9:30 am due to weather it's was raining | 6 | 9 | [8 empty] | Corrugated / Screen wall Flashing Insulation Subgirt Zee | [22 empty] | 40 | 9 |  |  | 30 | 2 |  |  | 30 | 2 | 30 | 3
22061 | 19th and Church | 2024-12-04 | JC Panels | Panel installation | Subcontractor | Josh McPherson | false |  |  |  |  | 8 | 10 | false |  | 3 boom lifts | false |  |  |  |  | ACM | 16
23022 | Bottled Blonde | 2024-12-04 | Marvin Blanco | Installing metal panels today the GC told us to move to the other side of the building because they need the swing stage for the weatherproofing guy so after lunch we have to stop hanging panels in the east side of the building with the swing stage | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 10 | false |  | Scaffolding swing stage | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 20 | 30
23033 | Iron Mountain VA6 | 2024-12-04 | Marvin Blanco | Today my guys started taking panels down in the corner of the building and also moving scaffolding from one roof to the others side of the building in the roof that way it's ready to start taking more panels down in the stairs 4 we have to take 32 panels in the stairs 4 and 3 we just take 6 for now and moving scaffolding tomorrow we will have to build it we need somebody to move material from the roof in the stairs 4 it's on our way | Subcontractor | Joe Hoyle | false |  |  |  |  | 3 | 12 | false |  | Boomlift scaffolding | false |  |  |  |  | Other | [42 empty] | Taking panels down from the wall | 36
23039 | Vantage VA22 | 2024-12-04 | Saul chicas | Today we were working on east elevation | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Flashing | [22 empty] | 7 | 10 | [8 empty] | 50 | 10
23054 | QTS MAN1 DC2 | 2024-12-04 | Ever Mendoza | We are still waiting for WT to put an anchor point to continue with the installation of the corrugated panel | Subcontractor | Josh McPherson | [5 empty] | 3 | 10 |  |  | Boom lift | [5 empty] | ACM | 6 | 30
24001 | McEwen Northside | 2024-12-04 | Marvin Blanco | We are behind on this project it's because we started a month behind and also holidays Hoar closed the building to many day and we need more day open the job site next week we will get it more faster because this week we are still slow because the weather to much wind we supposed to finish the north west corner but anyone don't see all the issue they have weatherproofing not done correctly screws on our way panels are to big in a lot of sections we are trying our best to not remake panels because that we take more time for everybody but McDougall don't see anything don't care about the guys freezing and fixing all the issue's | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 70 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Corrugated / Screen wall | 11 | 50 | [20 empty] | 18 | 20
24018 | QTS-NAL1-DC1 | 2024-12-04 | Saul chicas | Crew 1 were working on east office installing ACM panels clicks and insulation crew2 north screen wall installing coping we were able to work only in the afternoon all roof was freezing crew 3 East office eye brown installing clicks track and insulation | Subcontractor | Joe Hoyle | [5 empty] | 10 | 10 |  |  | Scaffold and boom lift | [5 empty] | ACM Hat Channel Insulation Other | 6 | 10 | [24 empty] | 580 | 10 | [6 empty] | 200 | 10 | [6 empty] | We installed 160 clicks of night wall system | 10
24025 | Madison Elementary | 2024-12-04 | Norberto Velasquez | We prepare all the windows elevation outdoor Corrugated panels were installed, practically the same thing was done as yesterday, preparation and everything | Subcontractor | Wylie McDougall | [5 empty] | 6 | 9 | [8 empty] | Corrugated / Screen wall Flashing Insulation Subgirt Zee | [22 empty] | 44 | 9 |  |  | 78 | 3 |  |  | 120 | 9 | 144 | 9
22061 | 19th and Church | 2024-12-03 | JC Panels | Panel installation | Subcontractor | Josh McPherson | false |  |  |  |  | 8 | 10 | false |  | 2 boom lifts 1 scissor | false |  |  |  |  | ACM | 13
23022 | Bottled Blonde | 2024-12-03 | Marvin Blanco | Installing metal panels and also fixing "Zs" because the one's are install already not good for anything so we have to take those down and reinstalling because it's not hitting the stud or framing | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 11 | false |  | Scaffolding and swing stage | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 45 | 33
23028 | 1000 Church YMCA | 2024-12-03 | Marvin Blanco | Installing metal panels in the screenwall everything works well for now | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 10 | false |  | No equipment | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 21 | 30
23033 | Iron Mountain VA6 | 2024-12-03 | Marvin Blanco | Finishing the canopy also we Installing a extra coping in the top of the windows that it's not ours and also fixing others things because tomorrow we will be leaving the job site | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 12 | false |  | Boomlift | false |  |  |  |  | Coping Other | [40 empty] | 100 | 24 | Canopy | 24
23039 | Vantage VA22 | 2024-12-03 | Saul chicas | We were working on east yard installing some flashing re screw the corrugated panels and also modified the ACM trim to install to cover the steel | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | Flashing | [32 empty] | 100 | 10
23054 | QTS MAN1 DC2 | 2024-12-03 | Ever Mendoza | We are still waiting for someone to put the anchor point to continue with the installation of the corrugated panel | Subcontractor | Josh McPherson | [5 empty] | 3 | 10 |  |  | Boom lift | [5 empty] | ACM Insulation Subgirt Zee | [26 empty] | 150 | 15 |  |  | 150 | 15
24001 | McEwen Northside | 2024-12-03 | Marvin Blanco | Installing ACM panels in the north west corner but we have a problem the boomlift couldn't reach out to the top and now we are going to be in problem to be delay because I didn't expect that it's my fault to not check it out I'm sorry señores it won't happen again I was trying to not just a bigger one | Subcontractor | Josh McPherson | false |  |  |  |  | 11 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Corrugated / Screen wall | 20 | 80 | [20 empty] | 23 | 30
24018 | QTS-NAL1-DC1 | 2024-12-03 | Saul chicas | Crew 1 were working on east office installing clicks insulation and ACM panels crew 2 were working on north screen wall installing coping and blocking wood and crew 3 were working on east office installing clicks track and insulation Also we only work 6 hours on the roof because safety team said it was not safe to work on the roof | Subcontractor | Joe Hoyle | [5 empty] | 9 | 10 |  |  | Boom lift / scaffold | [5 empty] | ACM Coping Insulation | 12 | 10 | [24 empty] | 500 | 10 | [12 empty] | 140 | 10
24025 | Madison Elementary | 2024-12-03 | Norberto Velasquez | Today the insulation was installed with the subgirt zee and also the blueskin, corrugated panels were also placed with their respective flashing, it is now ready, work was done on some outside windows and work was done on the south and east elevations | Subcontractor | Wylie McDougall | [5 empty] | 6 | 9 | [8 empty] | Corrugated / Screen wall Flashing Insulation Subgirt Zee | [22 empty] | 24 | 9 |  |  | 400 | 9 |  |  | 170 | 9 | 164 | 9
22061 | 19th and Church | 2024-12-02 | JC Panels | Panel and fina installation | Subcontractor | Josh McPherson | false |  |  |  |  | 9 | 10 | false |  | 2 boom lift 1 scissor lift | false |  |  |  |  | ACM Other | 9 | [41 empty] | 22 fins
23039 | Vantage VA22 | 2024-12-02 | Saul chicas | Today we were working on east yard installing access door and re screws the corrugated panels | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | Other | [42 empty] | We installed 4 access door | 10
23054 | QTS MAN1 DC2 | 2024-12-02 | Ever Mendoza | Work continued with the corrugated panel but the installation was stopped because an anchor point is needed to be tied so far no one from WT has done anything we are still waiting for it to put an anchor point to be able to continue | Subcontractor | Josh McPherson | true | An anchor point is needed to be able to continue with the installation of the corrugated panel |  |  |  | 6 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 10 | 15 |  |  | 150 | 15 |  |  | 200 | 30
24018 | QTS-NAL1-DC1 | 2024-12-02 | Saul chicas | Crew 1 were working on east office installing ACM panels crew2 were working on north screen wall installing coping and crew3 were working bringing material to the roof and moving the scaffold | Subcontractor | Joe Hoyle | [5 empty] | 9 | 10 |  |  | Boom lift /scaffold | [5 empty] | ACM Coping Insulation Other | 12 | 10 | [24 empty] | 200 | 10 | [12 empty] | 350 | 10 | We modified 12 ACM metal panels | 10
24025 | Madison Elementary | 2024-12-02 | Norberto Velasquez | The zeta and insulation were installed, the blueskin and corrugated panel were also put on, all of this was installed on the south elevation outdoor. | Subcontractor | Wylie McDougall | [5 empty] | 6 | 8 | [8 empty] | Corrugated / Screen wall Flashing Insulation Subgirt Zee | [22 empty] | 3 | 1 |  |  | 480 | 4 |  |  | 300 | 8 | 120 | 5
22061 | 19th and Church | 2024-11-27 | JC Panels | Panels and fins installation | Subcontractor | Josh McPherson | false |  |  |  |  | 8 | 8 | false |  | 3 boom lifts | false |  |  |  |  | ACM Other | 9 | [41 empty] | Fins 11
23033 | Iron Mountain VA6 | 2024-11-27 | Marvin Blanco | Installing the canopy it's taking a little longer because we have to by a lot of drill bits and also waiting for the weatherproofing guy to cover some holes also one more thing my guys broke one light and I apologize for the issue | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 14 | false |  | Boomlift | true | Pollo | Broken a light from tube |  |  | Other | [42 empty] | Installing a canopy | 56
23054 | QTS MAN1 DC2 | 2024-11-27 | Ever Mendoza | N | Subcontractor | Josh McPherson | [5 empty] | 3 | 30 | [8 empty] | ACM Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 16 | 16 |  |  | 200 | 7 |  |  | 15 | 7
24001 | McEwen Northside | 2024-11-27 | Marvin Blanco | Installing ACM panels and metal panels in the screenwall everything is going good for now we don't have any issues we have everything we need for keeping us moving | Subcontractor | Josh McPherson | false |  |  |  |  | 10 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Corrugated / Screen wall | 15 | 60 | [20 empty] | 30 | 40
22061 | 19th and Church | 2024-11-26 | JC Panels | Panel and fins instalation | Subcontractor | Josh McPherson | false |  |  |  |  | 9 | 10 | false |  | 2 boom lift 1 scissor lift | false |  |  |  |  | ACM Other | 14 | [41 empty] | 22 fins
23022 | Bottled Blonde | 2024-11-26 | Marvin Blanco | Moving material all day 4 guys for 12 hrs and this is extra work | Subcontractor | Dillon Bowman | false |  |  |  |  | 4 | 12 | false |  | Scissors lift | false |  |  |  |  | Other | [42 empty] | Moving material from level 4 to the roof level 5 | 48
23039 | Vantage VA22 | 2024-11-26 | Saul chicas | We were working on east elevation re screw the panels and installing flashing around the window | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | Flashing | [32 empty] | 100 | 10
23054 | QTS MAN1 DC2 | 2024-11-26 | Ever Mendoza | N | Subcontractor | Josh McPherson | [5 empty] | 5 | 10 | [8 empty] | ACM | 15 | 50
23071 | Nashville Yards 9A3 & 9B3 | 2024-11-26 | Saul chicas | Today we were working on building 3 at level 34 installing ACM panels | Subcontractor | Dillon Bowman | [5 empty] | 3 | 10 |  |  | Ladders | [5 empty] | ACM | 52 | 10
24018 | QTS-NAL1-DC1 | 2024-11-26 | Saul chicas | Today we were working on east office installing ACM panels also another crew were working on south el action installing coping | Subcontractor | Joe Hoyle | [5 empty] | 9 | 10 |  |  | Boom lift and scaffold | [5 empty] | ACM Coping Corrugated / Screen wall Insulation | 9 | 10 | [20 empty] | 9 | 10 |  |  | 320 | 10 | [12 empty] | 180 | 10
22061 | 19th and Church | 2024-11-25 | JC Panels | Panels and fins installation 22 fins | Subcontractor | Josh McPherson | false |  |  |  |  | 9 | 8 | false |  | 2 boom lift 1 scissor lift | false |  |  |  |  | ACM Other | 8 | [41 empty] | Fins
23039 | Vantage VA22 | 2024-11-25 | Saul chicas | Today we were working on completing the ACM panel on blade wall also doing caulking on the ACM panels | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | ACM Caulking Flashing | 4 | 10 | [18 empty] | 150 | 10 | [10 empty] | 100 | 10
23054 | QTS MAN1 DC2 | 2024-11-25 | Ever Mendoza | Make reveals | Subcontractor | Josh McPherson | [5 empty] | 5 | 10 |  |  | Boom lift | [5 empty] | ACM | 15 | 50
23071 | Nashville Yards 9A3 & 9B3 | 2024-11-25 | Saul chicas | Today we go back on site to received some material and move to the roof | Subcontractor | Dillon Bowman | [5 empty] | 4 | 10 | true | ACM | Ladders | [5 empty] | ACM | 0 | 10
24018 | QTS-NAL1-DC1 | 2024-11-25 | Saul chicas | Crew 1 were working on east office installing ACM la les and insulation, crew 2 were working on east creen wall installing coping and blocking wood, crew 3 breakdown the scaffold on east office to move to the hight roof north elevator it was a crane activity so we move to the east office with the ACM panels we modified 9 panels | Subcontractor | Joe Hoyle | [5 empty] | 10 | 10 |  |  | Scaffold and boom lift | [5 empty] | ACM Coping Corrugated / Screen wall Insulation Other | 18 | 10 | [20 empty] | 7 | 10 |  |  | 360 | 10 | [12 empty] | 140 | 10 | We installed 60 foot of blocking wood | 10
24018 | QTS-NAL1-DC1 | 2024-11-24 | Saul chicas | We were working on south elevation installing coping also on east office screen wall | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Scaffold and boom lift | [5 empty] | Coping Corrugated / Screen wall Other | [22 empty] | 8 | 10 | [16 empty] | 200 | 10 | We installed 140' foot of blocking wood | 10
22061 | 19th and Church | 2024-11-23 | JC Panels | Panel installation and change order fabrication and installation. We finish the change order installation. | Subcontractor | Josh McPherson | false |  |  |  |  | 9 | 10 | false |  | 2 boom lift 1 scissor lift | false |  |  |  |  | ACM | 5
23039 | Vantage VA22 | 2024-11-23 | Saul chicas | Today we were working on blade wall fixing panels | Subcontractor | Joe Hoyle | true | Bad wether |  |  | Raining | 4 | 6 |  |  | Ladder | [5 empty] | ACM | 5 | 10
23054 | QTS MAN1 DC2 | 2024-11-23 | Ever Mendoza | N | Subcontractor | Josh McPherson | [5 empty] | 6 | 8 |  |  | Boom | [5 empty] | ACM Insulation Subgirt Zee | 11 | 30 | [24 empty] | 150 | 8 |  |  | 150 | 10
24018 | QTS-NAL1-DC1 | 2024-11-23 | Saul chicas | Today we were working on east office, south elevation and and east office screen wall | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Scaffold and boom lift | [5 empty] | ACM Coping Corrugated / Screen wall Insulation | 10 | 10 | [20 empty] | 3 | 10 |  |  | 400 | 10 | [12 empty] | 190 | 10
22061 | 19th and Church | 2024-11-22 | JC Panels | Panel installation.. work on change order covering holes | Subcontractor | Josh McPherson | false |  |  |  |  | 9 | 10 | false |  | 2 boom lifts 1 scissor lift | false |  |  |  |  | ACM | 8
23039 | Vantage VA22 | 2024-11-22 | Saul chicas | Today we were working on blade wall fixing coping panels | Subcontractor | Joe Hoyle | true | Rain |  |  | Rain | 4 | 5 |  |  | Ladders | [5 empty] | ACM | 2 | 5
23054 | QTS MAN1 DC2 | 2024-11-22 | Ever Mendoza | Modified panels | Subcontractor | Josh McPherson | true | Modified panels 5 panels |  |  |  | 6 | 10 |  |  | Boom lift | [5 empty] | ACM Corrugated / Screen wall | 7 | 40 | [20 empty] | 14 | 20
23071 | Nashville Yards 9A3 & 9B3 | 2024-11-22 | Saul chicas | Today we don't work because we don't have panels to install | Subcontractor | Dillon Bowman | [5 empty] | 1 |  |  |  | Ladders | [5 empty] | ACM | 0 | 0
24018 | QTS-NAL1-DC1 | 2024-11-22 | Saul chicas | 1 crew were working on south elevation moving material moving scaffold and installing coping another crew were working on east screen wall installing coping and moving material and moving scaffold another crew where working on east office installing insulation ,tracks on night wall system and clicks | Subcontractor | Joe Hoyle | [5 empty] | 10 | 10 |  |  | Boom lift and scaffold | [5 empty] | Coping Insulation Other | [26 empty] | 800 | 10 | [12 empty] | 320 | 10 | We installed 200' LF tracks on night wall system and 60 clicks | 10
24025 | Madison Elementary | 2024-11-22 | Norberto Velasquez | The corrugated panels were installed. The insulation was cut and installed as well. | Subcontractor | Wylie McDougall | [5 empty] | 5 | 6 | [8 empty] | Corrugated / Screen wall Insulation | [22 empty] | 25 | 6 |  |  | 5 | 1
22061 | 19th and Church | 2024-11-21 | JC Panels | Panel installation | Subcontractor | Josh McPherson | false |  |  |  |  | 9 | 10 | false |  | 2 boom lift 1 scissor lift | false |  |  |  |  | ACM | 17
23022 | Bottled Blonde | 2024-11-21 | Marvin Blanco | Installing Zs and insulation the GC installed Zs all around the building but those Zs are not attach to anything only in the gym all those Zs from the GC are wrong | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 10 | false |  | Scissors lift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 20 | 30
23028 | 1000 Church YMCA | 2024-11-21 | Marvin Blanco | Waiting for angles for attach the tubes it's been 2 day waiting for angles because with out those angles we are not able to install anything we try to install the ACM panels but we need the coping panels | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 10 | false |  |  | false |  |  |  |  | Hat Channel | [34 empty] | 120 | 30
23033 | Iron Mountain VA6 | 2024-11-21 | Marvin blanco | Waiting for the team Hitt to cut some steel but it doesn't happen anything also a couple of signs because the inside panels we need to replace the panels and checking some dimensions for the coping that it's not ours | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 12 | false |  | Boomlift | false |  |  |  |  | Other | [42 empty] | Taking some panels down | 48
23039 | Vantage VA22 | 2024-11-21 | Saul chicas | Today the whole crew were working on blade uninstalling and re installing ACM panel | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | ACM | 4 | 10
23054 | QTS MAN1 DC2 | 2024-11-21 | Ever Mendoza | N | Subcontractor | Josh McPherson | [5 empty] | 6 | 10 |  |  | Boom lift | [5 empty] | ACM Corrugated / Screen wall Insulation Subgirt Zee | 27 | 40 | [20 empty] | 20 | 10 |  |  | 300 | 5 |  |  | 200 | 5
23071 | Nashville Yards 9A3 & 9B3 | 2024-11-21 | Saul chicas | Today we were moving some material to the roof since we have at the basement we will be waiting for the next delivery of panel on Monday the 25th | Subcontractor | Dillon Bowman | [5 empty] | 3 | 5 |  |  | Ladders | [5 empty] | Other | [42 empty] | We muere moving some material to the roof | 10
24001 | McEwen Northside | 2024-11-21 | Marvin Blanco | Installing ACM panels and also metal panels in the screenwall we have a couple of issues with the ACM panels are being made to big in the north west corner | Subcontractor | Josh McPherson | false |  |  |  |  | 12 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Corrugated / Screen wall | 15 | 80 | [20 empty] | 25 | 40
24018 | QTS-NAL1-DC1 | 2024-11-21 | Saul chicas | Today 1 crew working on south elevation installing coping from the scaffold, another crew at east office installing night wall system and one more crew working on east office screen wall installing coping form the scaffold | Subcontractor | Joe Hoyle | [5 empty] | 10 | 10 |  |  | Boom lift / scaffold | [5 empty] | Coping Insulation Other | [26 empty] | 260 | 10 | [12 empty] | 320 | 10 | We installed 80 clicks at east office | 10
22061 | 19th and Church | 2024-11-20 | JC Panela | Panels installation | Subcontractor | Josh McPherson | false |  |  |  |  | 9 | 10 | false |  | 2 boom lift 1 scissor lift | false |  |  |  |  | ACM | 15
23028 | 1000 Church YMCA | 2024-11-20 | Marvin Blanco | Waiting for clips for attach the tubes because shop didn't send all the clips we are missing 20 clips and also taking some layout for the tubes and checking ACM panels | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 10 | false |  |  | false |  |  |  |  | ACM | 2 | 4
23033 | Iron Mountain VA6 | 2024-11-20 | Marvin Blanco | Installing coping and also remaking panels we have a little problem with a steel needs to be cut in the stairs 3 | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 12 | false |  | Boomlift | false |  |  |  |  | Coping | [40 empty] | 1500 | 48
23039 | Vantage VA22 | 2024-11-20 | Saul chicas | Today we were working on east yard also we remove all the trash we have on the roof we re screw all the elavation where the scaffold is | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 | true | 4 panels for blade wall | Boom lift scaffold | [5 empty] | Flashing | [32 empty] | 100 | 10
23054 | QTS MAN1 DC2 | 2024-11-20 | Ever Mendoza | N | Subcontractor | Josh McPherson | [5 empty] | 6 | 10 |  |  | Boom | [5 empty] | ACM Insulation | 12 | 40 | [24 empty] | 200 | 20
23071 | Nashville Yards 9A3 & 9B3 | 2024-11-20 | Saul chicas | Today we start installing panels on south,west and north elevation at level 34 | Subcontractor | Dillon Bowman | [5 empty] | 3 | 10 |  |  | Ladders | [5 empty] | ACM | 25 | 10
24001 | McEwen Northside | 2024-11-20 | Marvin Blanco | Installing L angles in the roof for the metal panels before we continue with the screenwall metal panels I need to talk about the extra L angles because today we had a little issue with another job for the extra work we did I would like to start taking about it or something else before we get in trouble we already have a couple of problems with the ACM panels are to big and we fixed already and install now we had also some problems with some screws from the window guys Colton and I told Hoar about it long time ago but never happen L 3 all around north and west elevation | Subcontractor | Josh McPherson | true | Hoar take forever for cut some screws |  |  | Colder | 12 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Hat Channel | 15 | 80 | [32 empty] | 400 | 40
24018 | QTS-NAL1-DC1 | 2024-11-20 | Saul chicas | Today we were installing coping at south elevation also we move the scaffold from high roof to the east office also we were installing clicks at east office eye brown | Subcontractor | Joe Hoyle | [5 empty] | 8 | 5 |  |  | Boom lift / scaffold | [5 empty] | Coping Other | [40 empty] | 150 | 10 | We installed 40 foot of wood blocking at east office and also we installed 200 clicks on east office eye brown | 10
24025 | Madison Elementary | 2024-11-20 | Norberto Velasquez | No comments | Subcontractor | Wylie McDougall | [5 empty] | 5 | 8 | [8 empty] | Corrugated / Screen wall Flashing Insulation | [22 empty] | 74 | 8 |  |  | 40 | 8 |  |  |  |  | 42 | 8
23022 | Bottled Blonde | 2024-11-19 | Marvin Blanco | Installing metal panels Zs" and insulation it's taking a little longer because the panels don't come with the right way to install also we have to cut some flashing to make it work because it's to big the wall it's not like the drawings show it's different we are cutting all the panels | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 10 | false |  | Scissors lift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 20 | 30
23028 | 1000 Church YMCA | 2024-11-19 | Marvin Blanco | We are installing tubes in the screenwall in the roof and we are missing 20 angles to finish installing the tubes and we have to cut 6 tubes also and insulation hats channels | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 10 | false |  | No equipment | false |  |  |  |  | Hat Channel Tubing | [28 empty] | 130 | 20 |  |  |  |  | 120 | 10
23033 | Iron Mountain VA6 | 2024-11-19 | Marvin Blanco | Installing coping and checking L angles for side of the windows because we have a 2" joint and that's no good we need something to close that big gap there remaking panels for the top of the new canopy | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 12 | false |  | Boomlift | false |  |  |  |  | Coping | [40 empty] | 100 | 48
23039 | Vantage VA22 | 2024-11-19 | Saul chicas | Today we were working on East yard also we went to fix some caulking at the roof and caulk the blade wall | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Ladder/boom lift | [5 empty] | Caulking Corrugated / Screen wall Flashing | [20 empty] | 100 | 10 | 8 | 10 | [8 empty] | 60 | 10
23054 | QTS MAN1 DC2 | 2024-11-19 | Ever Mendoza | No | Subcontractor | Josh McPherson | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | ACM Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 22 | 25 |  |  | 286 | 15 |  |  | 30 | 5
23071 | Nashville Yards 9A3 & 9B3 | 2024-11-19 | Saul chicas | Today we were installing tubes on south and east elevation at level 35 | Subcontractor | Dillon Bowman | [5 empty] | 3 | 5 |  |  | Ladder | [5 empty] | Tubing | [28 empty] | 200 | 10
24001 | McEwen Northside | 2024-11-19 | Marvin Blanco | Working in the screenwall with metal panels and also with ACM panels in the north west corner of the building we are missing flashing for the metal panels to finish the screenwall by the 11/26/24 I hope we can get it tomorrow and for the ACM panels we told Hoar about some angles in the north west corner to cut that and they never did we are being waiting for two weeks for that to be cut maybe one day they can cut it | Subcontractor | Josh McPherson | false |  |  |  |  | 12 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Corrugated / Screen wall | 8 | 80 | [20 empty] | 20 | 40
24018 | QTS-NAL1-DC1 | 2024-11-19 | Saul chicas | Today we start working on East office installation clicks also on south east and north we were installing caping | Subcontractor | Joe Hoyle | true | On north and east elevation it was a crane that was holding us for work |  |  | Bad weather raining until 12:00pm | 8 | 5 |  |  | Boom lift scaffold | [5 empty] | Coping Other | [40 empty] | 300 | 5 | We installing 200 clicks on East office | 5
24025 | Madison Elementary | 2024-11-19 | Norberto Velasquez | No comments | Subcontractor | Wylie McDougall | true | We had to wait for the blue skin membrane and they sent the order to pick up and when we arrived it was not available there was a delay of 2 hours we will have to go today to see if they already have it available there would probably be another delay of 2 hours |  |  |  | 5 | 8 | [8 empty] | Corrugated / Screen wall Flashing Insulation | [22 empty] | 74 | 8 |  |  | 21 | 2 |  |  |  |  | 37 | 8
23033 | Iron Mountain VA6 | 2024-11-18 | Marvin Blanco | Checking all the materials for remake panels and we don't have enough materials to finish the building we are going to be done with everything else except for the stairs 5 about Wednesday next week we will be done with all we have in the building | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 12 | false |  | Boomlift | false |  |  |  |  | ACM | 12 | 48
23039 | Vantage VA22 | 2024-11-18 | Saul chicas | We were working on East yard | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | Coping Corrugated / Screen wall Flashing | [22 empty] | 9 | 10 | [8 empty] | 70 | 10 | [6 empty] | 60 | 10
23054 | QTS MAN1 DC2 | 2024-11-18 | Ever | No | Subcontractor | Josh McPherson | [5 empty] | 4 | 10 | true |  | Boom lift | [5 empty] | Flashing Subgirt Zee | [30 empty] | 70 |  | 82
23071 | Nashville Yards 9A3 & 9B3 | 2024-11-18 | saul chicas | Today we start working on level 35 installing tube on south north and west elevation | Subcontractor | Dillon Bowman | [5 empty] | 3 | 10 |  |  | Ladder | [5 empty] | Tubing | [28 empty] | 500 | 10
24001 | McEwen Northside | 2024-11-18 | Marvin Blanco | Today was a slow day before Hoar doesn't have everything ready and also we are delay 2 weeks because this guy don't want to spend money fixing a little corner north west corner to put our boomlift level but finally they fixed last Friday and now everybody wants to work in the area Hoar supposed to cut some angles every floor in the north west corner like 2 weeks ago and they didn't also one more thing we are installing heavy angles in the face of the brick and I don't think that brick is strong enough for hold that big angle it's in last round of the brick I don't feel good doing this. | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Corrugated / Screen wall | 8 | 20 | [20 empty] | 20 | 40
24015 | New Pope School | 2024-11-18 | rafael gomez | we continued working on elevation 313,314,315 | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 9 | false |  | 2 boom lift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 20 | 9
24018 | QTS-NAL1-DC1 | 2024-11-18 | Saul chicas | Today we were installing blocking wood and coping on south and west elevation also we have to move material to the east elevation (ACM) | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Scaffold /. Boom lift | [5 empty] | Coping Other | [40 empty] | 200 | 10 | We were installing wood blocking on East and south elevation we installed 460 foot of wood blocking | 10
24025 | Madison Elementary | 2024-11-18 | Norberto Velasquez | No comments | Subcontractor | Wylie McDougall | [5 empty] | 5 | 8 | [8 empty] | Corrugated / Screen wall Flashing Insulation | [22 empty] | 43 | 8 |  |  | 37 | 3 |  |  |  |  | 37 | 8
22061 | 19th and Church | 2024-11-16 | JC panels | Find and panel installation | Subcontractor | Josh McPherson | false |  |  |  |  | 9 | 10 | false |  | 2 boom lift 1 scissor lift | false |  |  |  |  | ACM
23071 | Nashville Yards 9A3 & 9B3 | 2024-11-16 | Saul chicas | Today we were s installing tube at level 34 also we were moving some material to the roof | Subcontractor | Dillon Bowman | [5 empty] | 4 | 3 |  |  | Ladder | [5 empty] | Tubing | [28 empty] | 270 | 10
24015 | New Pope School | 2024-11-16 | rafael gomez | we continued on elevation 313,314,315 | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 9 | false |  | 2 boom lift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 50 | 9
24018 | QTS-NAL1-DC1 | 2024-11-16 | Saul chicas | Today we were working on west elevation | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Subgirt Zee | [22 empty] | 40 | 10 | [6 empty] | 800 | 10
23039 | Vantage VA22 | 2024-11-15 | Saul chicas | Today we were working on East elevation | Subcontractor | Joe Hoyle | [5 empty] | 2 | 10 |  |  | Boom lift | [5 empty] | Coping | [40 empty] | 110 | 10
23071 | Nashville Yards 9A3 & 9B3 | 2024-11-15 | Saul chicas | We were installing tube at north and east elevation at level 34 | Subcontractor | Dillon Bowman | [5 empty] | 3 | 10 |  |  | Ladders | [5 empty] | Tubing | [28 empty] | 300 | 10
24015 | New Pope School | 2024-11-15 | rafael gomez | we continued on elevation 313,314,315 | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 9 | false |  | 2 boom lift | false |  |  |  |  | Flashing | [32 empty] | 300 | 9
24018 | QTS-NAL1-DC1 | 2024-11-15 | Saul chicas | Today we were working on south and west elevation | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Scaffold / boom lift | [5 empty] | Corrugated / Screen wall Flashing Other Subgirt Zee | [22 empty] | 25 | 10 | [6 empty] | 90 | 10 | 100 | 10 | [8 empty] | We installed 160 foot of wood blocking on soy to elevation | 10
23039 | Vantage VA22 | 2024-11-14 | Saul chicas | Today we were working on east elevation installing coping | Subcontractor | Joe Hoyle | true | Bad weather raining |  |  | Bad weather raining | 3 | 10 |  |  | Scaffold / boom lift | [5 empty] | Coping Subgirt Zee | [30 empty] | 110 | 10 | [8 empty] | 40 | 10
24015 | New Pope School | 2024-11-14 | rafael gomez | the crew din't work on Wednesday do to the rain ! we continue working on elevation 313,314 and 315 | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 9 | false |  | 2 2boom lift | false |  |  |  |  | Flashing Insulation Subgirt Zee | [26 empty] | 100 | 9 |  |  | 100 | 9 | 150 | 9
22061 | 19th and Church | 2024-11-13 | JC Panels | Panel installation | Subcontractor | Josh McPherson | false |  |  |  |  | 9 | 10 | false |  | 2 boom lifts 1 scissor lift | false |  |  |  |  | ACM | 19
23033 | Iron Mountain VA6 | 2024-11-13 | Marvin Blanco | Remaking panels for the stairs 4 and also reinstalling panels in the bottom of the stairs the one's we had to take down for the framing to be fix in the stairs five there ir a scaffolding on our way to install panels | Subcontractor | Joe Hoyle | false |  |  |  |  | 6 | 12 | false |  | Boomlift | false |  |  |  |  | ACM | 14 | 72
23039 | Vantage VA22 | 2024-11-13 | Saul chicas | Today we were working on east yard | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | Coping Corrugated / Screen wall Subgirt Zee | [22 empty] | 12 | 10 | [6 empty] | 100 | 10 | [8 empty] | 340 | 10
23071 | Nashville Yards 9A3 & 9B3 | 2024-11-13 | Saul chicas | Today we start installing tubes on south and west elevation | Subcontractor | Dillon Bowman | true | Bad wether start raining from 12:00 pm |  |  | Bad weather | 3 | 10 |  |  | Ladder | [5 empty] | Tubing | [28 empty] | 130 | 10
24001 | McEwen Northside | 2024-11-13 | Marvin Blanco | Today was raining and we couldn't work really well but we install a couple of ACM panels and metal panels un the roof screenwall yesterday we have to move all the materials from one side to the other we spend 5 hours moving material after that we have enough materials to be working | Subcontractor | Josh McPherson | false |  |  |  |  | 8 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Corrugated / Screen wall | 6 | 40 | [20 empty] | 28 | 40
24018 | QTS-NAL1-DC1 | 2024-11-13 | Saul chicas | Today we were working on north and east elavation | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift / scaffold | [5 empty] | Corrugated / Screen wall Other Subgirt Zee | [22 empty] | 58 | 10 | [6 empty] | 300 | 10 | [10 empty] | We were installing 140' foot of wood blocking on north elevation ( extra work ) | 10
23039 | Vantage VA22 | 2024-11-12 | Saul chicas | Today we were working on east wall | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 24 | 10
24015 | New Pope School | 2024-11-12 | rafael gome | we are still working on elevation 314,315,316 | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 9 | false |  | 2 boom lift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 300 | 9 |  |  | 200 | 9
24018 | QTS-NAL1-DC1 | 2024-11-12 | Saul chicas | Today we were working on east elevation installing wood blocking flashing and corrugated panels | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift / scaffold | [5 empty] | Corrugated / Screen wall Flashing Other | [22 empty] | 36 | 10 | [8 empty] | 80 | 10 | [8 empty] | We installed wood blocking 100 foot | 10
23033 | Iron Mountain VA6 | 2024-11-11 | Marvin Blanco | Remaking panels for the stairs 4 and taking down panels from the wall because those are shorts and reinstalling the new panels with the good dimensions also reinstalling the bottom panels because those panels hitt tell us to take out because they need to cut their framing in the bottom of all the stairs 2,3,4,5 | Subcontractor | Joe Hoyle | false |  |  |  |  | 5 | 12 | false |  | Boomlift | false |  |  |  |  | ACM | 12 | 60
23039 | Vantage VA22 | 2024-11-11 | Saul chicas | Today we were working on east elevation and also on blade wall fixing the ACM panels | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift /scaffold | [5 empty] | Coping Corrugated / Screen wall Flashing | [22 empty] | 27 | 10 | [8 empty] | 80 | 10 | [6 empty] | 80 | 10
23071 | Nashville Yards 9A3 & 9B3 | 2024-11-11 | Saul chicas | Today we were unloading material and also we were moving material to the roof | Subcontractor | Dillon Bowman | [5 empty] | 3 | 10 | true | Tubes, hardware and panels | Ladders | [5 empty] | ACM | 0 | 10
24001 | McEwen Northside | 2024-11-11 | Marvin Blanco | Installing ACM panels in north elevation and also installing metal panels in the screenwall penthouse for today everything was good no issues we have enough material to be working just one thing we need 3" screws take 3 | Subcontractor | Josh McPherson | false |  |  |  |  | 8 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Corrugated / Screen wall | 7 | 40 | [20 empty] | 30 | 40
24015 | New Pope School | 2024-11-11 | rafael gomez | we are working on elevation 314,315,316 | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 9 | false |  | 2 boom lift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 200 | 9 |  |  | 250 | 9
24018 | QTS-NAL1-DC1 | 2024-11-11 | Saul chicas | Today we were working on north wall | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift/ scaffold | [5 empty] | Corrugated / Screen wall Flashing Other | [22 empty] | 45 | 10 | [8 empty] | 30 | 10 | [8 empty] | We installed 50 foot of wood blocking | 10
22061 | 19th and Church | 2024-11-09 | JC Panels | Fins and panels installation | Subcontractor | Josh McPherson | false |  |  |  |  | 9 | 10 | false |  | 2 boom lifts and 1 scissor lift | false |  |  |  |  | ACM Other | 8 | [41 empty] | Fins 196
22061 | 19th and Church | 2024-11-08 | JC Panels | Fins installation | Subcontractor | Josh McPherson | false |  |  |  |  | 9 | 10 | false |  | 2 boom lift and 1 scissor lift | false |  |  |  |  | ACM
23039 | Vantage VA22 | 2024-11-08 | Saul chicas | Today we were working on east elevation also we were installing double face tape | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 46 | 10
23039 | Vantage VA22 | 2024-11-08 | Saul chicas | Today we were working on north and east elevation | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift/ scaffold | [5 empty] | Corrugated / Screen wall Other | [22 empty] | 30 | 10 | [18 empty] | We installed 200' of wood blocking | 10
24015 | New Pope School | 2024-11-08 | rafael gomez | we continue in elevation 409 whith the fascia and its almost completed | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 9 | false |  | 2 boom lift | false |  |  |  |  | Corrugated / Screen wall Subgirt Zee | [22 empty] | 20 | 9 | [6 empty] | 200 | 9
24018 | QTS-NAL1-DC1 | 2024-11-08 | Saul chicas | Today we were working on north and east elevation | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift / scaffold | [5 empty] | Corrugated / Screen wall Other | [22 empty] | 30 | 10 | [18 empty] | We installed 200' foot of wood blocking | 10
22061 | 19th and Church | 2024-11-07 | JC Panels | Panel and fins plates installation | Subcontractor | Josh McPherson | false |  |  |  |  | 9 | 10 | false |  | 2 boom lifts and 1 scissor lift | false |  |  |  |  | ACM | 6
23033 | Iron Mountain VA6 | 2024-11-07 | Marvin Blanco | Remaking ACM panels, and taking panels from the wall the panels are shorts we are replacing for the good dimensions panels we are done in the stairs 2 and we jumped out to the stairs 4 and started Remaking panels also and changing panels | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 12 | false |  | Boomlift | false |  |  |  |  | ACM | 8 | 48
23039 | Vantage VA22 | 2024-11-07 | Saul chicas | Today we were working on blade wall installing ACM metal panels | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift and ladders | [5 empty] | ACM | 6 | 10
24001 | McEwen Northside | 2024-11-07 | Marvin Blanco | Installing ACM panels and also installing metal panels in the screenwall in the ACM panels we have a lot of issues the panels are to big everywhere it doesn't have the ½ inches in the side's of the brick and also top and bottom we have to cut all the panels to make it fit in the openings we need to resolve all this kind of problems because every job we have it's to many problems | Subcontractor | Josh McPherson | false |  |  |  |  | 8 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Corrugated / Screen wall | 8 | 40 | [20 empty] | 20 | 40
24015 | New Pope School | 2024-11-07 | rafael gomez | we star on elevation 409 to do fascia | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 9 | false |  | 2 boom lift | false |  |  |  |  | Corrugated / Screen wall Subgirt Zee | [22 empty] | 15 | 9 | [6 empty] | 200 | 9
24018 | QTS-NAL1-DC1 | 2024-11-07 | Saul chicas | Today we were working on north elevation and east elevation | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift and scaffold | [5 empty] | Corrugated / Screen wall Other Subgirt Zee | [22 empty] | 58 | 10 | [6 empty] | 1200 | 10 | [10 empty] | We were installing wood blocking on north elevation we installed 100 foot of wood blocking | 10
23039 | Vantage VA22 | 2024-11-06 | Saul chicas | One crew working installing double face tape on east yard another crew working on ACM panels | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | ACM Flashing | 3 | 10 | [30 empty] | 100 | 10
24033 | Cannon Nissan | 2024-11-06 | Chad mccoy | The rest of the caps were installed today. 6 end dam pieces were made and installed bc the acm caps needed to be sealed where the sign is suppose to go and where acm coping caps did not have a full end piece. Panels were peeled today and we started tripping in reveals and caulking. All panels are installed and 95 percent are peeled. | Subcontractor | Dillon Bowman | true | It rained all day. Making it hard to caulk in the rain |  |  | Rainy and 72 | 6 | 8 | true |  | 45 foot boom | false |  |  |  |  | ACM Caulking | 10 | 4 | [18 empty] | 35 | 1
22061 | 19th and Church | 2024-11-05 | JC Panels | Fin plates installation and caulking | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | true | Drill bits | 2 boom lifts 1 scissor lift | false |  |  |  |  | ACM
23033 | Iron Mountain VA6 | 2024-11-05 | Marvin Blanco | Today we were taking layout and checking how many more sheets we are going to need to finish this project because we had to many issues on this one because everywhere was shorts panels not because John W. McDougall it's because the Hitt team and framing guys and that's why we are talking a little bit longer because this guys don't have anything correct also they cut the bottom framing and now the panels are hanging 2 " down of the wall there nothing to attach the stared clip we have to take down 13 panels front the stairs 2 to replace the remake panels | Subcontractor | Joe Hoyle | false |  |  |  |  | 6 | 12 | false |  | Boomlift | false |  |  |  |  | ACM | 12 | 72
23039 | Vantage VA22 | 2024-11-05 | Saul chicas | One crew working on east yard installing J trump around windows another crew working on ACM panels balde wall | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | Flashing | [32 empty] | 270 | 10
24001 | McEwen Northside | 2024-11-05 | Marvin Blanco | Today we were trying to install ACM panels but there is a lot of issues in the weatherproofing and also to many screws from the windows guys there is nothing safe for anybody the building is going to be getting weather inside because the windows moullions are attached up not up down | Subcontractor | Josh McPherson | false |  |  |  |  | 8 | 10 | true | 4 creates of ACM panels | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Hat Channel | 3 | 30 | [32 empty] | 600 | 50
24015 | New Pope School | 2024-11-05 | rafael garcia | we completed elevation 408 ! the crew didn't work Wednesday 11/6/2024 because it wast raining all day | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 9 | false |  | 2 boomlift | false |  |  |  |  | Corrugated / Screen wall Flashing | [22 empty] | 15 | 9 | [8 empty] | 70 | 9
24018 | QTS-NAL1-DC1 | 2024-11-05 | Saul chicas | Today we were working on north side installation base flashing and corrugated metal panels | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift scaffold | [5 empty] | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 30 | 10 | [6 empty] | 600 | 10 | 310 | 10
24033 | Cannon Nissan | 2024-11-05 | Chad McCoy | Acm was continued and L metal was installed for caps | Subcontractor | Dillon Bowman | false |  |  |  |  | 6 | 10 | true |  | 45 foot boom | false |  |  |  |  | ACM Flashing | 31 | 9 | [30 empty] | 65 | 1
23033 | Iron Mountain VA6 | 2024-11-04 | Marvin Blanco | Remaking panels in the front canopy because the panels we had in the job site are to shorter it doesn't cover the coping also We have a lot of issues there because to many shorts panels everywhere and the concrete guys damaged the bottom panels and matt ask us to cut 2 panels and now the panels are with a big hole and he wants us to remake that panel and that's not our fault | Subcontractor | Joe Hoyle | false |  |  |  |  | 5 | 12 | false |  | Boomlift | false |  |  |  |  | Other | [42 empty] | Remaking panels | 60
23039 | Vantage VA22 | 2024-11-04 | Saul chicas | Today we were working on east yard installing J trimps around the windows | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Ladder | [5 empty] | Corrugated / Screen wall Flashing | [22 empty] | 3 | 10 | [8 empty] | 100 | 10
24001 | McEwen Northside | 2024-11-04 | Marvin Blanco | Installing Zs" insulation the roof at the screenwall and also taking layout for start installing ACM panels in northwest corner of the building and there is a lot of issues because the windows guys have a lot of screws attached to the steel up and that's not safe for anyone also there is panels to big McDougall needs to remake | Subcontractor | Josh McPherson | false |  |  |  |  | 8 | 11 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Hat Channel | 2 | 22 | [32 empty] | 600 | 66
24015 | New Pope School | 2024-11-04 | rafael gomez | we are working on elevation 408 that its almost complete | Subcontractor | Wylie McDougall | false |  |  |  |  | 5 | 9 | false |  | 2 boom lift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 20 | 9
24018 | QTS-NAL1-DC1 | 2024-11-04 | Saul chicas | Today we were working on north elevation | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Subgirt Zee | [22 empty] | 31 | 10 | [6 empty] | 150 | 10
24033 | Cannon Nissan | 2024-11-04 | Chad mccoy | Acm was continued. It was to dark to take pics. So they were taken this morning | Subcontractor | Dillon Bowman | true | 2 caps were cut to fit |  |  | Partly cloudy windy | 7 | 9.5 | false |  | 45 foot boom | false |  |  |  |  | ACM Flashing | 30 | 9 | [30 empty] | 100 | 1.5
24033 | Cannon Nissan | 2024-11-03 | Chad McCoy | I made the last two panels for underneath the canopy today one went above the door, and the other one filled the 2 1/4 void in between the curved mall and the vertical canopy facia. Another team was going around, continuing to put on coping caps and the L shape metal that is supposed to hold it up for attachment in the back. And then the third team was putting the facial panels on the high-rise section above the curtain wall that wraps to the sides. When we were putting the panels on that went over the windows that were supposed to line up with the joint lines we noticed that the panels are 4 foot nine and the eighth and the windows are 4 foot seven and some change so we had to get a hold of Dylan to get approval to cut Ralph these panels When we cut these panels with no longer work because we use the 4 foot panels to cut down so I had to make a 4 foot seven and 3 /4 To fill the last void. | Subcontractor | Dillon Bowman | true | The amount of remakes and modifications on this job are getting out of hand. I don’t remember it ever saying in the contract that we’re supposed to make 30+ percent of a job work. Window joint lines do not line up elevations are wrong. There are signs that had to be cut out that were not talked about the 2 inch legs that go back into the entryways. A lot of them came as 4 inch legs so they all had to be cut and modified the corners on the upper structure have to be remade because the plywood and build out of the framing is so out of square and out of plum that, they impact on the plywood prior to even reach the other Panels and their short left right. All the caps will have to be modified in some manner due to the ad square upper corners or an improper build on the panel that does not match structure. There’s a panel that goes into a gutter. The gutter Protrudes into where face of ACM is going to land, so these have to be modified so that they can go on without impacting the gutter plus the panels also have to be filled on the void where the water if it overflows in the gutter does not go behind the panel |  |  | Partly cloudy | 6 | 10 | true |  | 45 foot boom | false |  |  |  |  | ACM Flashing | 24 | 8 | [30 empty] | 60 | 2
24033 | Cannon Nissan | 2024-11-02 | Chad mccoy | Acm was continued on the face of the building, on the under belly of the canopy walls and the coping acm caps. The panels where the signs go had to be cut and routed to lower the top down bc the sign needed to sit on the structure. All the bolts had to be hole sawed out and one pig tail. Underneath the canopy the wall with the two doors all have to be made but 3 panels. We were going to make these panels like the prints. But there is a better way. I talked to Ross and Dillion and then I proceeded to make these panels my way. 8 panels were completely made. 4 panels were cut and routed. | Subcontractor | Dillon Bowman | true | Making panels is taking a lot of time. |  |  | Partly cloudy. 81 | 3 | 11.5 | true |  | 45 foot boom | false |  |  |  |  | ACM Flashing | 21 | 11.5 | [30 empty] | 60 | 1
22061 | 19th and Church | 2024-11-01 | JC Panels | Fin plate installation.. we need to find a way to cover those holes that doesn’t cover the z with the panel | Subcontractor | Josh McPherson | false |  |  |  |  | 3 | 10 | true |  | 2 boom lift 1 scissor lift | false |  |  |  |  | ACM
23039 | Vantage VA22 | 2024-11-01 | Saul chicas | Today we don't work because they were installing asphalt on the street | Subcontractor | Joe Hoyle | true | Working on asphalt |  |  |  | 1 | 0 |  |  | Boom lift | [5 empty] | ACM | 0 | 0
24015 | New Pope School | 2024-11-01 | rafael gomez | we are still working on elevation 409 and we start to put some panels on 411 | Subcontractor | Wylie McDougall | true | we are unable to keep installing because the windows are not ready |  |  |  | 5 | 9 | false |  | 2 boom lift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 50 | 9
24018 | QTS-NAL1-DC1 | 2024-11-01 | Saul chicas | Today we were working on south and north elevation | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift scaffold | [5 empty] | Corrugated / Screen wall Flashing Other | [22 empty] | 30 | 10 | [8 empty] | 200 | 10 | [8 empty] | Wood blocking on south elevation | 10
23033 | Iron Mountain VA6 | 2024-10-31 | Marvin Blanco | Today was a good day installing coping and also taking some dimensions for the panels that we need to remake because there is some panels short and also installing 2 panels inside the building | Subcontractor | Joe Hoyle | false |  |  |  |  | 6 | 12 | false |  | Boomlift | false |  |  |  |  | Coping Plate |  |  | 2 | 24 | [36 empty] | 100 | 48
24001 | McEwen Northside | 2024-10-31 | Marvin Blanco | Installing Zs" insulation and metal panels in the screenwall today was a great day we have everything we need plywood scaffolding screws and material | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 11 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 20 | 33 |  |  | 192 | 7 |  |  | 100 | 26
24015 | New Pope School | 2024-10-31 | rafael gomez | we start on elevation 409 | Subcontractor | Wylie McDougall | true | we are behind because the windows are not ready and the framing still not inspected |  |  |  | 5 | 9 | false |  | 2 boomlift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 20 | 9
22061 | 19th and Church | 2024-10-30 | JC Panels | Fin plates installation on 2nd floor | Subcontractor | Josh McPherson | false |  |  |  |  | 10 | 10 | false |  | 2 boom lift and 1 scissor lift | false |  |  |  |  | ACM
23039 | Vantage VA22 | 2024-10-30 | Saul chicas | Today we were working on east yard | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Flashing | [22 empty] | 5 | 10 | [8 empty] | 80 | 10
24015 | New Pope School | 2024-10-30 | rafael gomez | we complete elevation 408 ceiling | Subcontractor | Wylie McDougall | false |  |  |  |  | 6 | 9 | false |  | 1 boom lift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 20 | 9
24018 | QTS-NAL1-DC1 | 2024-10-30 | Saul chicas | Today we were working on north elevation installing wood blocking and installing corrugated panels | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift scaffold | [5 empty] | Corrugated / Screen wall Other | [22 empty] | 15 | 10 | [18 empty] | Wood blocking 272 foot installed | 10
22061 | 19th and Church | 2024-10-29 | JC Panels | Panels installation, fin clips installation | Subcontractor | Josh McPherson | false |  |  |  |  | 9 | 10 | false |  | 2 boom lifts 1 scissor lift | false |  |  |  |  | ACM | 3
23039 | Vantage VA22 | 2024-10-29 | Saul chicas | Today we keep working on east yard installing panels | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 | true | ACM panels | Boom lift | [5 empty] | Coping Corrugated / Screen wall Flashing | [22 empty] | 5 | 10 | [8 empty] | 140 | 10 | [6 empty] | 30 | 10
24015 | New Pope School | 2024-10-29 | rafael gomez | we continued working on the installation on elevation 313 and it's almost done | Subcontractor | Wylie McDougall | false |  |  |  |  | 5 | 9 | false |  | 1 boom lift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 60 | 9
24018 | QTS-NAL1-DC1 | 2024-10-29 | Saul chicas | We were installing panels on north elevation also installing wood block on south elevation | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Other | [22 empty] | 49 | 10 | [18 empty] | Wood blocking 180 foot | 10
22061 | 19th and Church | 2024-10-28 | JC Panels | Caulk the interior , concrete guys are working outside so they doesn’t allow us to keel installing outside | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 10 | true | Fins plates | 2 boom lifts and 1 scissor lift. | false |  |  |  |  | ACM Caulking | 5
23039 | Vantage VA22 | 2024-10-28 | Saul chicas | We keep installing corrugated panels on east yard | Subcontractor | Joe Hoyle | [5 empty] | 5 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 14 | 10
24015 | New Pope School | 2024-10-28 | rafael gomez | we continued working on elevation 313 installing corrugated | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 8 | false |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 30 | 8
24018 | QTS-NAL1-DC1 | 2024-10-28 | Saul chicas | Today we were installing blocking on east office and also installing panels on north elevation we install 250foot on blocking | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Scaffold boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 50 | 10
22061 | 19th and Church | 2024-10-25 | JC Panels | Coping installation | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | true |  | 2 boom lifts 1 scissor lift | false |  |  |  |  | Coping
24015 | New Pope School | 2024-10-25 | rafael gomez | we continued working on elevation 408 installing corrugated panes | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 8 | false |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 50 | 8
22061 | 19th and Church | 2024-10-24 | JC Panels | Copping installation | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | false |  | 2 boom lifts 1 scissor lift | false |  |  |  |  | Coping | [40 empty] | 176
24015 | New Pope School | 2024-10-24 | rafael gomez | we start working on elevation 408 on the ceiling panels | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 8 | false |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall Flashing | [22 empty] | 50 | 8 | [8 empty] | 130 | 8
22061 | 19th and Church | 2024-10-23 | JC Panels | Panel preparation and installation | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | false |  | 2 boom lifts and 1 scissor lift | false |  |  |  |  | ACM | 12
23054 | QTS MAN1 DC2 | 2024-10-23 | Ever Mendoza | Install Fabral | Subcontractor | Josh McPherson | [5 empty] | 4 | 10 |  |  | Scaffold | [5 empty] | Corrugated / Screen wall | [22 empty] | 13 | 40
24015 | New Pope School | 2024-10-23 | rafael gomez | working on elevation 313 installing insulation and zee | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 8 | false |  | 1boomlift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 300 | 8 |  |  | 300 | 8
22061 | 19th and Church | 2024-10-22 | JC Panels | Panel preparation and installation | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | false |  | 2 boom lifts and 1 scissor lifts | false |  |  |  |  | ACM | 15
23033 | Iron Mountain VA6 | 2024-10-22 | Marvin Blanco | Taking panels out of the wall because the framing was wrong in the bottom of all the stairs there is a big issue because it's going to take a lot of time putting those panels back up in the wall and I have to charge a change order Taking those panels down | Subcontractor | Joe Hoyle | false |  |  |  |  | 8 | 12 | false |  | Boomlift | false |  |  |  |  | Other | [42 empty] | We have 3 day taking panels out of the wall in the all the stairs 2,3,4,5 and the landscape guys damaged and panel with the star clip | 192
23039 | Vantage VA22 | 2024-10-22 | Saul chicas | Crew 1 working on east yard installing panels crew 2 working on north elevation installing ACM panels | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Boom lift | [5 empty] | ACM Corrugated / Screen wall | 5 | 10 | [20 empty] | 34 | 10
23054 | QTS MAN1 DC2 | 2024-10-22 | Ever Mendoza | installed of Corrugado fabral | Subcontractor | Josh McPherson | [5 empty] | 4 | 10 |  |  | Scaffold and boom lift | [5 empty] | ACM Corrugated / Screen wall | [22 empty] | 13 | 40
24015 | New Pope School | 2024-10-22 | rafael gomez | we continued working on elevation 313 | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 10 | false |  | 1 boom lift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 70 | 8 |  |  | 80 | 8
24018 | QTS-NAL1-DC1 | 2024-10-22 | Saul chicas | Today we were working on East office also on south west corner | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Scaffold boom lift | [5 empty] | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 46 | 10 | [6 empty] | 400 | 10 | 70 | 10
24033 | Cannon Nissan | 2024-10-22 | Chad McCoy | My daily’s have not been going thru. I requested a new link today. But we finished up our wall on the back west elevation that has 19 panels for the install but 9 had to be cut and routed. We then moved up one wall and ran the top row bc a decision was made and we can install coping caps soon. | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 10 | false |  | 40 foot boom | false |  |  |  |  | ACM | 20 | 9
22061 | 19th and Church | 2024-10-21 | JC Panels | Panels installation, insolation, z’s and angles installation | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 10 | false |  | 2 boom lifts 1 scissor lift | false |  |  |  |  | ACM | 8
23039 | Vantage VA22 | 2024-10-21 | Saul chicas | Crew 1 were working on north elevation installing ACM panels crew 2 were working on east yard installing corrugated panels | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Boom lift | [5 empty] | ACM Corrugated / Screen wall Insulation | 6 | 10 | [20 empty] | 10 | 10 |  |  | 390 | 10
23054 | QTS MAN1 DC2 | 2024-10-21 | Ever Mendoza | Continuamos con las instalaciones Zee para los ACM | Subcontractor | Josh McPherson | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | ACM |  | 40
24015 | New Pope School | 2024-10-21 | rafael gomez | we start to install zee and insulation on elevation 313 | Subcontractor | Wylie McDougall | false |  |  |  |  | 3 | 10 | false |  | 1 boomlift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 80 | 10 |  |  | 90 | 10
24018 | QTS-NAL1-DC1 | 2024-10-21 | Saul chicas | Crew 1 East office 4 guys 15 panels installed 15 panels cut working with the scaffold Crew 2 south elevation installing base flashing on the screen wall 300' zgarts installed 3 guys Crew3. 2guys we moved all the material to another area request by WT we also fly to the roof followings items 4 crates of panels 2 pallets of zgarts 1 panel of coping | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Scaffold / boom lift | [5 empty] | Corrugated / Screen wall Subgirt Zee | [22 empty] | 15 | 10 | [6 empty] | 300 | 10
24033 | Cannon Nissan | 2024-10-21 | Chad McCoy | We got the approval to cut and route the front panels by the curtain wall once that was done We started installing on the back additional wall. On the west elevation. This wall has a lot of issues as well. Panels that are suppose to have a 2 inch leg have 4 inch legs and panel widths are off. There are a lot of modifications on ever wall so far | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 10 | false |  | 40 foot boom | false |  |  |  |  | ACM | 9 | 5
24033 | Cannon Nissan | 2024-10-20 | Chad mccoy | 16 panels were installed. And 4 kick plates. We are only running the bottom 2 rows of panels still bc we are waiting on the GC to make a decision on the coping cap. | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 10 | false |  | 40 foot boom | false |  |  |  |  | ACM | 16 | 9
24033 | Cannon Nissan | 2024-10-19 | Chad McCoy | 18 panels were installed. The top row wasn’t installed bc decisions have to be made on how to install the coping cap due to the panels going past the top of the parapet | Subcontractor | Dillon Bowman | true | Acm cap has. Nothing to attach to. |  |  | Clear 79 | 3 | 10.5 | false |  | 40 foot boom | false |  |  |  |  | ACM | 18 | 9
22061 | 19th and Church | 2024-10-18 | JC panels | Insolación and z’s installation . Some of the Guys had to go back to Virginia we will be back on Monday . | Subcontractor | Josh McPherson | false |  |  |  |  | 3 | 9 | false |  | 2 boom lifts and 1 scissor lift | false |  |  |  |  | ACM
23060 | Clarendale | 2024-10-18 | Chad mccoy | 27 ft of z, 15 ft of flashing and 13 panels installed 8hrs 3 men | Subcontractor | Laura Forero | true | Install details are trash. Panels are not lined up with brick. They are proud of surrounding system. We are also installing insulation where it’s suppose to be installed already |  |  | Clear 75 | 3 | 8 | false |  | 65 foot boom | false |  |  |  |  | ACM Flashing Subgirt Zee | 13 | 6 | [28 empty] | 27 | 2 | 15 | 2
24015 | New Pope School | 2024-10-18 | rafael gomez | we continued on elevation 413 | Subcontractor | Wylie McDougall | false |  |  |  |  | 2 | 8 | false |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 12 | 8
24033 | Cannon Nissan | 2024-10-18 | Chad mccoy | We continued installation on the canopy and additional wall we battled the same problems as yesterday. We just knew better how do install with it faster. 2 panels cut and 2 panels routed. At the end of the day we cleaned up and moved are install side to the west elevation and we started layout for tomorrows install | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 11 | false |  | 40 foot boom | false |  |  |  |  | ACM | 30 | 10
22061 | 19th and Church | 2024-10-17 | JC Panels | Panel installation, insolation and framing | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 10 | true | Panels and angles |  | false |  |  |  |  | ACM | 8
23033 | Iron Mountain VA6 | 2024-10-17 | Marvin Blanco | Installing the louver at the from entry also installing acm panels in the stairs 5 | Subcontractor | Joe Hoyle | false |  |  |  |  | 10 | 12 | false |  | Scaffolding , boomlift | false |  |  |  |  | ACM Louvre | 10 | 36 | [22 empty] | 2 | 84
23039 | Vantage VA22 | 2024-10-17 | Saúl chicas | Today we were installing on east wall | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 20 | 10
23054 | QTS MAN1 DC2 | 2024-10-17 | Ever Mendoza | Install Zee | Subcontractor | Josh McPherson | [5 empty] | 3 | 8 | [8 empty] | ACM
23060 | Clarendale | 2024-10-17 | Chad mccoy | 13 panels installed today. We finished the panels on the canopy. It kicked our ass but we made it look good. 32 ft of z | Subcontractor | Laura Forero | true | We should not have to make panels work. The details on these panels are no good and we are installing them other ways we know that meet mcdougals standards but it should not be that way |  |  |  | 3 | 8 | false |  | 65 foot boom | false |  |  |  |  | ACM Subgirt Zee | 13 | 7 | [28 empty] | 32 | 2
24015 | New Pope School | 2024-10-17 | rafael. gomez | we start to install on elevation 413 those are the small entrances | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 20 | 10
24018 | QTS-NAL1-DC1 | 2024-10-17 | Saúl chicas | Today we were installing on south elevation and east elavation also we move material to the roof to start installing panels on the east wall | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Scaffold boom lift | [5 empty] | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 15 | 10 | [6 empty] | 500 | 10 | 200 | 10
24033 | Cannon Nissan | 2024-10-17 | Chad McCoy | The boom didn’t arrive till this morning. We installed 8 panels yesterday. But they all had to come done due to having to move up for an elevation bust. So we literally started over today on install. Every panel that has a AR2 so far has had the excursions in the wrong positions. We are having to more excursion around for proper installation. The eye brow panel that turns u see and going to the drop ceiling also had to be modified due to the inside dimension of the panel is the same or smaller than the build out on the building. So there is no plumbing anything with out modifications. There are no 5-6 inch kick plates. So we were instructed to kill panels to make them. | Subcontractor | Dillon Bowman | true | 8 panels were removed to restart |  |  | Clear 71 | 3 | 11 | false |  | 40 foot boom | false |  |  |  |  | ACM | 15 | 9
22061 | 19th and Church | 2024-10-16 | JC panels | Panel installation, insolation and frame | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | true | Screws | 2 boom lifts 1 scissor lift | false |  |  |  |  | ACM | 9
23039 | Vantage VA22 | 2024-10-16 | Saúl chicas | Today we change the panel on north side also we were installing coping at the roof | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Ladder boom lift | [5 empty] | Coping | [40 empty] | 60 | 8
23054 | QTS MAN1 DC2 | 2024-10-16 | Ever Mendoza | Install horizontal Zee and área for ACM | Subcontractor | Josh McPherson | true | The areas are not completely ready |  |  |  | 4 |  |  |  | Boom lift and scaffold | [5 empty] | ACM
24015 | New Pope School | 2024-10-16 | rafael gomez | we continued whith corrugated and we finished the window flashing | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 1 boomlift | false |  |  |  |  | Corrugated / Screen wall Flashing | [22 empty] | 10 | 10 | [8 empty] | 40 | 10
24018 | QTS-NAL1-DC1 | 2024-10-16 | Saúl chicas | Today we were working on south elevation also on east elevation installing z garts | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift / scaffold | [5 empty] | Corrugated / Screen wall Subgirt Zee | [22 empty] | 48 | 10 | [6 empty] | 1110 | 10
22061 | 19th and Church | 2024-10-15 | JC Panels | Panel installation, insolation, z’s angles | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 10 | false |  | 2 boom lifts 1 scissor lift | false |  |  |  |  | ACM | 8
23033 | Iron Mountain VA6 | 2024-10-15 | Marvin Blanco | Installing coping in the roof screenwall everything is working really well and also installing ACM panels all the ACM coping in the front entry it's short those panels doesn't work | Subcontractor | Joe Hoyle | false |  |  |  |  | 10 | 12 | true | Screws and backroll | Scaffolding , boomlift | false |  |  |  |  | ACM Coping | 9 | 36 | [38 empty] | 1500 | 108
23039 | Vantage VA22 | 2024-10-15 | Saul chicas | Today we were working installing corrugated panels on the east wall | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 16 | 10
23054 | QTS MAN1 DC2 | 2024-10-15 | Ever Mendoza | Se empezó a instalar Z e insolación para los paneles corrugados | Subcontractor | Josh McPherson | true |  |  |  | started rain, we left early because of the rain | 5 | 7 |  |  | Two boom lift | [5 empty] | ACM
24015 | New Pope School | 2024-10-15 | rafael gomez | continued whith corrugated panels | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 1boomlift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 40 | 10
24018 | QTS-NAL1-DC1 | 2024-10-15 | Saul chicas | Today we. It work beacuse of the rain | Subcontractor | Joe Hoyle | true | Bad weather |  |  | Bad weather | 8 | 0 |  |  | Boom lift scaffold | [5 empty] | ACM | 0 | 0
22061 | 19th and Church | 2024-10-14 | JC Panels | Panel installation, framing, insolation | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | false |  | 2 boom lifts 1 scissors lift | false |  |  |  |  | ACM | 15
23039 | Vantage VA22 | 2024-10-14 | Saul chicas | Today we start working on está elevation installion corrugated panels | Subcontractor | Joe Hoyle | [5 empty] | 7 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 27 | 10
24015 | New Pope School | 2024-10-14 | rafael gomez | we star to install the corrugated on elevation 317 | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 1 boom lift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 40 | 40
23033 | Iron Mountain VA6 | 2024-10-13 | Marvin Blanco | Today we were installing coping in the screenwall and also installing panels in the from entrance and all the coping panels not working because they are shorts we try to install the louver but the tools are not working we need silicone and also 2" screws 2 boxes and 1½ screws 1 boxe to finish all the acm panels but this is not included the others panels that we have shorts in the job site just what we have in the contract we have to manufacturing almost all the entrance canopy panels | Subcontractor | Joe Hoyle | false |  |  |  |  | 10 | 10 | false |  | Scaffolding , boomlift | false |  |  |  |  | ACM Coping | 5 | 30 | [38 empty] | 1500 | 70
24018 | QTS-NAL1-DC1 | 2024-10-12 | Saul chicas | Today we keep working on south elevation installing corrugated panels | Subcontractor | Joe Hoyle | [5 empty] | 6 | 8 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 33 | 8
22061 | 19th and Church | 2024-10-11 | JC Panels | Panel installation, insolation and framing | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | false |  | 2 boom lifts 1 scissor lift | false |  |  |  |  | ACM | 12
23033 | Iron Mountain VA6 | 2024-10-11 | Marvin Blanco | We are done with the stairs 3 we remake all the panels around the door and manufacture 1 line of panels in the corner of the tower also taking all the materials to the roof for start installing the coping | Subcontractor | Joe Hoyle | false |  |  |  |  | 10 | 12 | false |  | Scaffolding , boomlift | false |  |  |  |  | ACM | 20 | 120
24018 | QTS-NAL1-DC1 | 2024-10-11 | Saul chicas | Today we keep installing corrugated panels on south elevation wall | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 50 | 10
24032 | Sonoco | 2024-10-11 | Chad mccoy | 22 panels were installed and 2 kick plates. Plus layout. the panels that are glued up are horrible builds. Pics and videos have been sent to Josh and Colton. In these dark blue panels. There is a chrome line at ever horizontal joint on each panel. A lot of the glue ups are breaking apart. We had had 3 of the starter panels a101 a103 and a102 all had a ar2 where a fr2 was suppose to go? | Subcontractor | Colton Van Meter | true | Panel glue up ends, panels built wrong for installation, |  |  | Clear 80 | 3 | 10 | false |  | 45 foot boom | false |  |  | 1 |  | ACM Layout | 22 | 7
22061 | 19th and Church | 2024-10-10 | JC Panels | Panel installation, framing, insolation | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | true |  | 2 boom lifts and 1 scissor lift | false |  |  |  |  | ACM | 26
23039 | Vantage VA22 | 2024-10-10 | Saúl chicas | Today we were working installing ACM on north elevation | Subcontractor | Joe Hoyle | [5 empty] | 7 | 10 |  |  | Boom lift | [5 empty] | ACM Insulation | 17 | 10 | [24 empty] | 715 | 10
24018 | QTS-NAL1-DC1 | 2024-10-10 | Saúl chicas | Today we keep installing corrugated panel on south wall also we were moving the scaffold to start working on east wall | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 48 | 10
22061 | 19th and Church | 2024-10-09 | JC Panels | Panels installation on the inside and the west side of the building. Z’s and insolation installation on the inside | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | false |  | 1 scissor lift and 2 boom lifts | false |  |  |  |  | ACM | 22
23033 | Iron Mountain VA6 | 2024-10-09 | Marvin Blanco | Today we try to make some panels work in the stairs five but there is a lot of panels shorts big panels also We was peeling all the panels off and installing the last Panels at the stairs 3, we need silicone other things we did is took some dimensions for the coping there is a lot of areas the top wood is passing the face of the panels Hitt needs to cut that wood to make it fit all the coping | Subcontractor | Joe Hoyle | false |  |  |  |  | 12 | 12 | false |  | Scaffolding , boomlift | false |  |  |  |  | ACM | 15 | 144
23067 | Boeing PAC 3 | 2024-10-09 | Kevin Morris | Cut and installed 2 imp's and trim electrical panel boxes and conduit made it difficult to install and place scaffolding also started to install window trim | Subcontractor | Chris Buttrey | false |  |  |  |  | 4 | 10 | false |  | Boom 60' | false |  |  |  |  | Flashing IMP Trim | [8 empty] | 2 | 6 | [22 empty] | 40 | 2 |  |  | 40 | 2
22061 | 19th and Church | 2024-10-08 | JC Panels | Panel installation, we prepared the interior with insolation zs and adjustable angles installation | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | true | ACM ,flashing , insolation | 2 boom lifts 1 scissor lifts | false |  |  |  |  | ACM | 8
23033 | Iron Mountain VA6 | 2024-10-08 | Marvin Blanco | Installing ACM panels taking layout for the last stairs number 5 and it looks like we have some shorts panels also today Wednesday we will know which panels are going to work we need anadis silicone to put silicone panels to panel and silicone for the precast and panel | Subcontractor | Joe Hoyle | false |  |  |  |  | 12 | 12 | false |  | Scaffolding , boomlift | false |  |  |  |  | ACM | 28 | 144
23039 | Vantage VA22 | 2024-10-08 | Saúl chicas | Today we were working doing some caulking on the rod also installing ACM panel on the blade wall | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Ladder boom lift | [5 empty] | ACM Insulation Subgirt Zee | 8 | 10 | [24 empty] | 120 | 10 |  |  | 70 | 10
23067 | Boeing PAC 3 | 2024-10-08 | Kevin Morris | Installed 7 imp's electrical panel boxes and conduit in the way made it more difficult | Subcontractor | Chris Buttrey | false |  |  |  |  | 4 | 10 | false |  | Boom 60' | false |  |  |  |  | IMP | [8 empty] | 7 | 10
24017 | Wyler Nissan | 2024-10-08 | David placzkowski | put in trim around bay door and man door. caulked all skyward joints and caulked screw heads on the back of the cap panels. | Subcontractor | Chris Buttrey | false |  |  |  |  | 2 | 8 | false |  | 40ft boom lift | false |  |  |  |  | Caulking Flashing | [20 empty] | 150 | 8 | [10 empty] | 75 | 8
24018 | QTS-NAL1-DC1 | 2024-10-08 | Saúl chicas | Today we keep working on the screen wall south elavtion | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 |  |  | 2 boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 27 | 10
22061 | 19th and Church | 2024-10-07 | JC Panels | Panel installation, installation of z’s and insolation inside. Panel preparation | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 9 | false |  | 1 scissor lift 2 boom lifts | false |  |  |  |  | ACM | 7
23033 | Iron Mountain VA6 | 2024-10-07 | Marvin Blanco | Installing panels in the stairs 3 and also moving material we were installing 4" revils in the stairs 4 because the panels are the wrong dimensions and we supposed to put that trim there but matt the Hitt guy said to not installed and yesterday he said that he wants that revils there and we took all day fixing that stuff. | Subcontractor | Joe Hoyle | false |  |  |  |  | 9 | 12 | false |  | Scaffolding , boomlift | false |  |  |  |  | Trim | [36 empty] | 128 | 24
23039 | Vantage VA22 | 2024-10-07 | Saúl chicas | Today we were working on blade wall installing panels and we were doing some caulking on roof also | Subcontractor | Joe Hoyle | [5 empty] | 7 | 10 |  |  | Boom lift ladder | [5 empty] | ACM Caulking Subgirt Zee | 11 | 10 | [18 empty] | 60 | 10 | [8 empty] | 360 | 10
23067 | Boeing PAC 3 | 2024-10-07 | Kevin Morris | Installed imp and finished staging panels on roof to be installed | Subcontractor | Chris Buttrey | false |  |  |  |  | 3 | 10 | false |  | Boom 60' | false |  |  |  |  | IMP | [8 empty] | 6 | 10
24015 | New Pope School | 2024-10-07 | rafael gomez | we completed elevation 317 the zee and insulation | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 1 boomlift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 200 | 5 |  |  | 150 | 5
24017 | Wyler Nissan | 2024-10-07 | David placzkowski | installed acm panels. cut and routed 6 top panels over service bay. peeled poly | Subcontractor | Chris Buttrey | false |  |  |  |  | 2 | 8 | false |  | 40ft boom lift | false |  |  |  |  | ACM | 18 | 16
24018 | QTS-NAL1-DC1 | 2024-10-07 | Saúl chicas | Today we start installing screen wall on south elevation | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 30 | 10
22061 | 19th and Church | 2024-10-05 | JC Panels | Panel installation, panel preparation, z’s angles | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 7 | false |  | 2 boom lifts 1 scissor | false |  |  |  |  | ACM | 11 | 7
23067 | Boeing PAC 3 | 2024-10-04 | Kevin Morris | Had to tear down part of scaffolding to change broken wheel. Installed imp | Subcontractor | Chris Buttrey | false |  |  |  |  | 4 | 8 | false |  | Boom 60' | false |  |  |  |  | IMP | [8 empty] | 5 | 5
24015 | New Pope School | 2024-10-04 | rafael gomez | we continued whith installation of insulation and zee on elevation 317 | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 1 boomlift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 300 | 10 |  |  | 400 | 10
22061 | 19th and Church | 2024-10-03 | JC Panels | Panel installation, z’s , angles and flashing .. today United brought us the right boom lift . We had to fix 4 panels | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10 | false |  | 2 boom lifts and 1 scissor | false |  |  |  |  | ACM | 14
23067 | Boeing PAC 3 | 2024-10-03 | Kevin Morris | Installed window trim and flashing on east and trim on south | Subcontractor | Chris Buttrey | false |  |  |  |  | 4 | 10 | false |  | Boom 60' | false |  |  |  |  | Flashing Trim | [32 empty] | 80 | 5 |  |  | 110 | 5
23067 | Boeing PAC 3 | 2024-10-03 | Kevin Morris | Installed panels and trim ...trim protective plastic is baked on | Subcontractor | Chris Buttrey | false |  |  |  |  | 4 | 10 | true |  | Boom 60' | false |  |  |  |  | Flashing IMP | [8 empty] | 4 | 8 | [22 empty] | 70 | 2
24015 | New Pope School | 2024-10-03 | rafael gomez | we continued whith the zee and insulation and we are waiting for the flashing | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 1 bunklift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 500 | 20 |  |  | 400 | 20
24017 | Wyler Nissan | 2024-10-03 | David Placzkowski | pulled panels. prepped panels, installed acm panels | Subcontractor | Chris Buttrey | false |  |  |  |  | 2 | 6.5 | false |  | 40ft boom lift | false |  |  |  |  | ACM | 15 | 13
22061 | 19th and Church | 2024-10-02 | JC Panels | Today we install panels, z’s , J’s, prepared panels , install adjustable angles. Today United went with the wrong boom to site and they said that they were coming back with the right one but they didn’t | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 10.5 | false |  | 2 boom lifts 1 scissor lift | false |  |  |  |  | ACM | 19
23033 | Iron Mountain VA6 | 2024-10-02 | Marvin Blanco | We are remaking panels and glueing panels also manufacturing panels because there is a lot of short panels and some panels that they make it wrong everywhere | Subcontractor | Joe Hoyle | false |  |  |  |  | 9 | 13 | false |  | Scaffolding , boomlift | false |  |  |  |  | ACM | 35 | 117
23039 | Vantage VA22 | 2024-10-02 | Saul chicas | Today we were working on west yard installing pup rivets also on north side installing ACM panels we move material to the roof to start installing ACM also | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | ACM Insulation | 22 | 10 | [24 empty] | 780 | 10
23067 | Boeing PAC 3 | 2024-10-02 | Kevin | Preped trim staged panels and equipment on south side | Subcontractor | Chris Buttrey | false |  |  |  |  | 2 | 8 | false |  | Boom 60' | false |  |  |  |  | Flashing IMP
24015 | New Pope School | 2024-10-02 | rafael gomez | we completed elevation 302 but we need the corner !we start elevation 317 but we need a bigger boom to reach one side because there a lower floor that we don't reach ! | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 1bunklift | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 20 | 10 |  |  | 100 | 10 |  |  | 100 | 10
24015 | New Pope School | 2024-10-02 | rafael gomez | we continued withthe installation on 302 and its almost completed ! we are resolving the problems whith the flashing too ,but everything its good so far | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 1 bunk lift | false |  |  |  |  | Corrugated / Screen wall Flashing | [22 empty] | 40 | 10 | [8 empty] | 50 | 10
24017 | Wyler Nissan | 2024-10-02 | David placzkowski | pulled panels. prepped panels including grinding down returns to allow for a reveal to be able to fit. installed acm panels. peeled poly off panels as well | Subcontractor | Chris Buttrey | false |  |  |  |  | 2 | 8 | false |  | 40ft boom lift | false |  |  |  |  | ACM | 19 | 16
24018 | QTS-NAL1-DC1 | 2024-10-02 | Saul chicas | Today we keep installing subgarts on the south elevation wall | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | 2 boom lift | [5 empty] | Subgirt Zee | [30 empty] | 800 | 10
24020 | QTS ATL2 DC2 Osgood | 2024-10-02 | Marvin Blanco | This morning the guys took the orientation for the roof and they're ready to take the material to the roof and stared working but the problem is they don't have the scaffolding so tomorrow Thursday is the last day in the job site for what we have ready | Subcontractor | Dillon Bowman | true | Scaffolding |  |  | Good condition | 3 | 12 | false |  | 1 Boomlift and 1 forklift | false |  |  |  |  | Louvre | [24 empty] | 44 | 36
22061 | 19th and Church | 2024-10-01 | JC Panels | We install panels, prepare panels, install z’s and J’s and adjustable z’s . Flashing | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 56 | false |  | 2 boom lifts and 1 scissor lifts | false |  |  |  |  | ACM | 10
23033 | Iron Mountain VA6 | 2024-10-01 | Marvin Blanco | Installing ACM panels and also remaking panels and modifications of the panels in the stairs number 3 | Subcontractor | Joe Hoyle | false |  |  |  |  | 9 | 12 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM | 18 | 108
23039 | Vantage VA22 | 2024-10-01 | Saul chicas | Today we were working in west yard installing pup rivers and also installing on east elevation part A also we make a extra work on VA21 change order work | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Subgirt Zee | [22 empty] | 5 | 10 | [6 empty] | 780 | 10
23067 | Boeing PAC 3 | 2024-10-01 | Kevin Morris | Wheel on scaffolding broke | Subcontractor | Chris Buttrey | false |  |  |  |  | 4 | 10 | false |  | Boom 60' | false |  |  |  |  | IMP | [8 empty] | 11 | 10
24017 | Wyler Nissan | 2024-10-01 | David placzkowski | pulled acm panels. had to grind down reveal pockets on every panels to allow the reveal to be able to fit. prepped panels. installed acm panels. also pulled poly and front of building panels. | Subcontractor | Chris Buttrey | false |  |  |  |  | 2 | 8 | false |  | 40ft boom lift | false |  |  |  |  | ACM | 18 | 16
24018 | QTS-NAL1-DC1 | 2024-10-01 | Saul chicas | Today we keep working on south side installing zgarts | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | 2 boom lifts | [5 empty] | Subgirt Zee | [30 empty] | 800 | 10
24018 | QTS-NAL1-DC1 | 2024-10-01 | Saul chicas | Today we keep installing zgarts on east wall | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 | true | ZGarts | Boom lift and fork lift | [5 empty] | Subgirt Zee | [30 empty] | 800 | 10
24020 | QTS ATL2 DC2 Osgood | 2024-10-01 | Marvin Blanco | Installing louvers blades and also angles for the support for the louvers blades also We have to cut 24 louvers blades because they're to longer | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 12 | false |  | 1 Boomlift and 1 forklift | false |  |  |  |  | Louvre | [24 empty] | 24 | 36
22061 | 19th and Church | 2024-09-30 | JC Panels | We start installing flashing , z’s we prepare panels and install panels | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 48 | false |  | 2 boom lifts and 1 scissor lift | false |  |  |  |  | ACM | 5 | 16
23067 | Boeing PAC 3 | 2024-09-30 | Kevin Morris | Cut out window openings | Subcontractor | Chris Buttrey | false |  |  |  |  | 4 | 10 | false |  | Boom 60' | false |  |  |  |  | IMP Trim | [8 empty] | 6 | 9 | [26 empty] | 30 | 1
24015 | New Pope School | 2024-09-30 | Rafael gomez | We continued the corrugated panel installation on elevation 302 ,and we are putting the side j’s on the windows openings | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 1 bunk lift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 25 | 10
24017 | Wyler Nissan | 2024-09-30 | David placzkowski | prepped acm panels, installed acm panels | Subcontractor | Chris Buttrey | false |  |  |  |  | 2 | 6.5 | false |  | 40ft boom | false |  |  |  |  | ACM | 15 | 13
23033 | Iron Mountain VA6 | 2024-09-28 | Marvin Blanco | Taking 6 panels out of the wall because we have to move over the joint to make work other panels | Subcontractor | Joe Hoyle | true | Weatherproofing from the job site |  |  | Good condition | 4 | 12 | false |  | Scaffolding , boomlift | false |  |  |  |  | ACM | 8 | 48
24007 | DLR DL4 Guard Shack | 2024-09-28 | Israel | Superintendent of the job close at 2:00 pm | Subcontractor | Joe Hoyle | true | Trimming down the 1” legs |  |  | Sunny Day | 2 | 7 | false |  | Boom lift | false |  |  |  |  | ACM | 9 | 14
24020 | QTS ATL2 DC2 Osgood | 2024-09-28 | Marvin Blanco | We haven't done anything because the job site is been closed for the hurricane the last day they work it was Thursday half of the day they just installing a couple of angles Friday closed and Saturday closed | Subcontractor | Dillon Bowman | false |  |  |  |  | 1 |  | false |  | 1 Boomlift 1 forklift | false |  |  |  |  | Other | [42 empty] | Nothing because the job site is closed
23039 | Vantage VA22 | 2024-09-27 | Saul chicas | Today we are not able to work because of the rain | Subcontractor | Joe Hoyle | true | Bad weather |  |  | Bad weather | 7 | 0 |  |  | Boom lift swigstage | [5 empty] | ACM | 0 | 0
24018 | QTS-NAL1-DC1 | 2024-09-27 | Saul chicas | Today we are not able to work due to the bad weather | Subcontractor | Joe Hoyle | true | Bad weather |  |  | Bad weather | 4 | 0 |  |  | Boom lift | [5 empty] | Subgirt Zee | [30 empty] | 0 | 0
22061 | 19th and Church | 2024-09-26 | JC Panels | Today we start framing inside and we prepared panels to be ready to install on Monday. 4 of our guys travel back home because they have been staying in Nashville 3 weeks in a row.. we left 3 guys on site preparing panels also we left everything clean and ordered . On Tuesday a member of our crew had an injury . Report have been sent to mcdougall | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 56 | true | Flashing and angles | 2 boom lifts | true | Tarit Arangure | Arm laseration with z’s |  |  | ACM
23039 | Vantage VA22 | 2024-09-26 | Saul chicas | Today we were working on East and north wall installing ACM metal panels also on west yard working were Swigstage is located | Subcontractor | Joe Hoyle | [5 empty] | 7 | 10 |  |  | Boom lift swingstage | [5 empty] | ACM Corrugated / Screen wall Insulation Subgirt Zee | 24 | 10 | [20 empty] | 20 | 10 |  |  | 715 | 10 |  |  | 140 | 10
24007 | DLR DL4 Guard Shack | 2024-09-26 | Israel | Rain in the morning | Subcontractor | Joe Hoyle | true | Trimming down the 1” legs,modified panel caps and rain during the morning hours |  |  | Rain stop at 9:00 am | 2 | 7 | false |  | Boom lift | false |  |  |  |  | ACM | 9 | 14
24015 | New Pope School | 2024-09-26 | rafael gomez | we continued with insulation and we fix the details on the door and we start the installation of panels | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 9 | false |  |  | false |  |  |  |  | Flashing Insulation | [26 empty] | 90 | 9 |  |  |  |  | 90 | 9
24018 | QTS-NAL1-DC1 | 2024-09-26 | Saul chicas | Today we keep installing z garts on screen wall part elevation L | Subcontractor | Joe Hoyle | true | Bad weather raining |  |  | Bad weather raining | 4 | 8 |  |  | Boom lift | [5 empty] | Subgirt Zee | [30 empty] | 810 | 10
23033 | Iron Mountain VA6 | 2024-09-25 | Marvin Blanco | Installing ACM panels not a good day because the rain but everything else is working well we have to manufacturing panels | Subcontractor | Joe Hoyle | true | Weatherproofing guy is holding me for everything |  |  | Rain | 4 | 12 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM | 10 | 48
23039 | Vantage VA22 | 2024-09-25 | Saul chicas | Today we were working on east elevation part C also on west and east elevation | Subcontractor | Joe Hoyle | [5 empty] | 7 | 10 |  |  | Swig stage boom lift | [5 empty] | ACM Insulation Subgirt Zee | 22 | 10 | [24 empty] | 195 | 10 |  |  | 160 | 10
23060 | Clarendale | 2024-09-25 | Chad mccoy | 35ft various trim installed, 27 panels installed. | Subcontractor | Laura Forero | true | So far on this job we have been delayed 8 hrs. That’s 3 guys at 8 hrs each, and it’s bc of other trades, the GC and trying to figure out to make the structure work where framing is missing and where the walls are not straight. The upper wall we worked on today is not straight and if you push the starter trim to the wall where the wall falls in will be a inch gap |  |  | Partly cloudy 82 | 3 | 8 | true |  | 65 foot boom | false |  |  |  |  | Single Skin | [6 empty] | 27 | 6
24015 | New Pope School | 2024-09-25 | rafael gomez | we completed the zee and almost completed the insulation and flashing on elevation on 302 | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 9 | false |  | 1 bunklift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 300 | 9 |  |  | 450 | 182
24017 | Wyler Nissan | 2024-09-25 | David Placzkowski | pulled and prepped panels. the returns have had to be ground down on almost every panels as they are between 1/16th and an 8th above the reveal pocket so they would have been able to receive a reveal. some returns have also been to short as well. installed acm. | Subcontractor | Chris Buttrey | false |  |  |  |  | 3 | 10 | false |  | 5k lull. 40ft boom lift | false |  |  |  |  | ACM | 23 | 30
24018 | QTS-NAL1-DC1 | 2024-09-25 | Saul chicas | Today we were working installing zGarts on south wall screen part M | Subcontractor | Joe Hoyle | true | Bad weather raining |  |  | Bad weather raining | 4 | 10 |  |  | 2 boom lift | [5 empty] | Subgirt Zee | [30 empty] | 880 | 8
24020 | QTS ATL2 DC2 Osgood | 2024-09-25 | Marvin Blanco | The guy couldn't work because the rain they left the job site at lunch time they just install a few of angles for the louvers blades | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 11 | false |  | 1 Boomlift 1 forklift | false |  |  |  |  | Other | [42 empty] | Angles for the louvers blades | 33
23033 | Iron Mountain VA6 | 2024-09-24 | Marvin Blanco | I have 4 guys in the job site but today they stop working because we are missing a flashing and we are not able to work in the others areas because they're not ready | Subcontractor | Joe Hoyle | true | Weatherproofing from the job site |  |  | Good condition | 4 | 11 | false |  | 2 Boomlift and a forklift and scaffolding | false |  |  |  |  | ACM | 6 | 44
23039 | Vantage VA22 | 2024-09-24 | Saul chicas | Today we were working on the swingstage area on west yard also working on east elevation part c | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Swigstage/ boom lift | [5 empty] | ACM Corrugated / Screen wall Insulation | 14 | 10 | [20 empty] | 10 | 10 |  |  | 390 | 10
24007 | DLR DL4 Guard Shack | 2024-09-24 | Israel | Braking down wood crates | Subcontractor | Joe Hoyle | true | Trimming down the 1” legs of every single panel |  |  | Rain | 2 | 8 | false |  | Boom lift | false |  |  |  |  | ACM | 16 | 16
24015 | New Pope School | 2024-09-24 | rafael gomez | we continued with elevation 302 | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 8 | false |  | 1 bnklift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 200 | 8 |  |  | 240 | 8
24017 | Wyler Nissan | 2024-09-24 | David Placzkowski | pulled and prepped acm panels. had to grind down almost every single reveal pocket just to be able to insert reveal as there is to much material in it. installed acm panels | Subcontractor | Chris Buttrey | false |  |  |  |  | 3 | 8 | false |  | 5k lull and 40ft boom lift | false |  |  |  |  | ACM | 20 | 24
24018 | QTS-NAL1-DC1 | 2024-09-24 | Saul chicas | Today we were moving material to the west elevation part z and start installing zgarts | Subcontractor | Joe Hoyle | true | Bad weather raining |  |  | Bad weather raining | 4 | 5 |  |  | Boom lift | [5 empty] | Subgirt Zee | [30 empty] | 210 | 10
24020 | QTS ATL2 DC2 Osgood | 2024-09-24 | Marvin Blanco | Installing clips for the louvers blades and also unloading materials | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 11 | true | Fabral panels for the screenwall in the roof | 1 Boomlift and 1 forklift | false |  |  |  |  | Other | [42 empty] | Clips for the louvers blades | 33
22061 | 19th and Church | 2024-09-23 | JC Panels | Prepare panels, install panels, install frame .. we need some angles and flashing to finish the face of the building. | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 70 | false |  | 2 boom lift 1 scissor lift | false |  |  |  |  | ACM
23039 | Vantage VA22 | 2024-09-23 | Saul chicas | Today we were working on west elevation where the Swigstage is located also on east elevation par c installing ACM panels | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift / swingstage | [5 empty] | ACM Corrugated / Screen wall Insulation | 10 | 10 | [20 empty] | 10 | 10 |  |  | 390 | 10
23060 | Clarendale | 2024-09-23 | Chad McCoy | 8 panels installed, 30ft of strapping cut and installed,27 ft of termination clip and receiver installed and 25 ft caulked | Subcontractor | Laura Forero | true | Strapping is cut down and made in field due to studs going wrong direction |  |  | Partly cloudy | 3 | 8 | true | Ropes rope grabs | 65 foot boom | false |  |  |  |  | Single Skin | [6 empty] | 8 | 7
24007 | DLR DL4 Guard Shack | 2024-09-23 | Israel | Installing acm panels | Subcontractor | Joe Hoyle | true | Shaving off the 1” legs |  |  | Rain | 2 | 5 | false |  | Boom lift | false |  |  |  |  | ACM | 10 | 10
24015 | New Pope School | 2024-09-23 | rafael gomez | we start 302 elevation | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 1 bunklift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 150 | 40 |  |  | 150 | 40
24017 | Wyler Nissan | 2024-09-23 | David placzkowski | unloaded crates from truck. broke open crates. prepped panels, installed acm panels | Subcontractor | Chris Buttrey | false |  |  |  |  | 3 | 8 | true | 4 crates of acm panels. one pallet of reveals, 2 miscellaneous clip crates | 5k lull and 40 ft boom lift. | false |  |  |  |  | ACM | 14 | 24
24018 | QTS-NAL1-DC1 | 2024-09-23 | Saul chicas | Today we unloaded 2 deliveries trucks | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 | true | Foam panels , zGarts, tool box , screws, play wood, foam, 2x6 woods | Boom lift ,fork lift | [5 empty] | ACM | 0 | 10
24020 | QTS ATL2 DC2 Osgood | 2024-09-23 | Marvin Blanco | Installing louvers blades and angles for the louvers blades we started installing angles in the other little screen for the louvers everything is working really well for now we need ACM panels or the screenwall panels in the roof that way we are not slow | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 12 | false |  | 1 Boomlift and 1 forklift | false |  |  |  |  | Other | [42 empty] | Clips for the louvers blades | 36
24016 | Genesis of Montgomery | 2024-09-21 | rafael gomez | we are finishing all the job we are in the details | Subcontractor | Chris Buttrey | false |  |  |  |  | 6 | 8 | false |  | 2 bunklift 1scissorlift 1 forklift | false |  |  |  |  | Other | [42 empty] | cleaning the area and finishing peeling the panels | 48
24007 | DLR DL4 Guard Shack | 2024-09-20 | Israel | Installing acm panels | Subcontractor | Joe Hoyle | false |  |  |  |  | 2 | 9 | false |  | Boom lift | false |  |  |  |  | ACM | 20 | 18
24007 | DLR DL4 Guard Shack | 2024-09-20 | Israel | Trimming down the 1” legs,also face panels at the canopy are not big enough to fit | Subcontractor | Joe Hoyle | true | Concrete guys working around the guard shack. |  |  | Sunny | 2 | 8 | false |  | Boom lift | false |  |  |  |  | ACM | 18 | 16
24015 | New Pope School | 2024-09-20 | rafael gomez | we completed 318, 301 and 303 those areas are completed | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 8 | false |  | 1 bunklift | false |  |  |  |  | Corrugated / Screen wall Flashing Insulation Subgirt Zee | [22 empty] | 20 | 8 |  |  | 100 | 8 |  |  | 50 | 8 | 40 | 8
24020 | QTS ATL2 DC2 Osgood | 2024-09-20 | Marvin Blanco | Installing louvers blades and also angles to the steel | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 14 | false |  | 1 Boomlift and 1 forklift | false |  |  |  |  | Louvre | [24 empty] | 15 | 42
22061 | 19th and Church | 2024-09-19 | JC Panels | Prepare panels. Install panels, install angles | Subcontractor | Josh McPherson | false |  |  |  |  | 5 | 50 | true | Acm | 2 boom lifts | false |  |  |  |  | ACM
23039 | Vantage VA22 | 2024-09-19 | Saul chicas | Today we were working on east elevation part c also on west yard south elevation finishing screwing the corrugated panels | Subcontractor | Joe Hoyle | [5 empty] | 8 | 10 |  |  | Boom lift scaffold | [5 empty] | ACM Insulation Subgirt Zee | 8 | 10 | [24 empty] | 260 | 10 |  |  | 180 | 10
23060 | Clarendale | 2024-09-19 | Chad mccoy | Moved material this morning. Installed 22 ft of trim. Caulked 25 ft along brick. At 240 had to go get the screws to continue work for tmrw | Subcontractor | Laura Forero | true | The upper level had dense glass installed on it and the screws provided won’t reach to attach thru the dense glass and secure the panels. Work was stopped bc we had to go find some kind of screws. Carlos drove to 3 different locations looking. |  |  | 91 partly cloudy | 3 | 8 | false |  | 65 foot boom | false |  |  |  |  | Caulking Trim | [20 empty] | 30 | 2 | [14 empty] | 22 | 2
24007 | DLR DL4 Guard Shack | 2024-09-19 | Israel | Rainy day | Subcontractor | Joe Hoyle | true | No work today due to the rain |  |  | Rainy day | 1 | 0 | false |  | Boom lift | false |  |  |  |  | ACM | 0 | 0
24015 | New Pope School | 2024-09-19 | rafael gomez | we just did installation of corrugated today | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 1 bunklift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 50
22061 | 19th and Church | 2024-09-18 | JC Panels | We install corner panels. Front panels receive delivery | Subcontractor | Josh McPherson | false |  |  |  |  | 5 | 50 | true | ACM | 2 boom lifts | false |  |  |  |  | ACM
23039 | Vantage VA22 | 2024-09-18 | Saúl chicas | Today we are not able to work because of the rain | Subcontractor | Joe Hoyle | true | Rain |  |  | Rain | 1 | 0 |  |  | Boom lift / scaffold | [5 empty] | ACM | 0 | 0
23060 | Clarendale | 2024-09-18 | Chad McCoy | 23 panels, 21 ft of termination receiver, 6 ft of j trim. We had an hr delay because of cement trucks and curb being poured | Subcontractor | Laura Forero | true | . We had an hr delay because of cement trucks and curb being poured |  |  | 86 partly cloudy | 3 | 8 | false |  | 65 foot boom | false |  |  |  |  | Flashing Single Skin | [6 empty] | 21 | 4 | [24 empty] | 30 | 1
24007 | DLR DL4 Guard Shack | 2024-09-18 | Israel | We remake the panel the panel built damaged and replaced it | Subcontractor | Joe Hoyle | true | Panel building used the boom lift for 3 hrs to set up the brackets for the lights, the superintendent asked for us to move away while the grading company spread gravel around the guard shack before the rain started |  |  | Cloudy and rainy after 3:00 pm | 2 | 8 | false |  | Boom lift | false |  |  |  |  | ACM | 10 | 16
24015 | New Pope School | 2024-09-18 | rafael gomez | continued with installation | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 10 | false |  | 1 bunklift | false |  |  |  |  | Corrugated / Screen wall Flashing Insulation Subgirt Zee
24016 | Genesis of Montgomery | 2024-09-18 | rafel gomez | continued with the acm installation | Subcontractor | Chris Buttrey | false |  |  |  |  | 6 | 10 | false |  | 2 bunklift 1 scissorlift | false |  |  |  |  | ACM | 8 | 60
24020 | QTS ATL2 DC2 Osgood | 2024-09-18 | Marvin Blanco | Installing angles in the steel for the lovers blades with out any problems everything is working really well | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 11 | false |  | 1 Boomlift and a forklift | false |  |  |  |  | Other | [42 empty] | Angles for the lovers blades | 33
22061 | 19th and Church | 2024-09-17 | JC Panels | We start installing panels, prepared panels, install frame.. doing space for more crates. We went to pick up some covers for the lull because Yates required that to go inside and step on the new concrete | Subcontractor | Josh McPherson | false |  |  |  |  | 5 | 50 | false |  | 2 boom lifts | false |  |  |  |  | ACM
23039 | Vantage VA22 | 2024-09-17 | Saúl chicas | Today we complete installing the corrugated panels on south elevation west yard | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Scaffold / boom lift | [5 empty] | Corrugated / Screen wall Flashing | [22 empty] | 20 | 10 | [8 empty] | 120 | 10
23060 | Clarendale | 2024-09-17 | Chad mccoy | 20 panels, 30 ft flashing 3 lights cut out | Subcontractor | Laura Forero | false |  |  |  |  | 3 | 8 | false |  | 65 foot boom | false |  |  | 1.5 |  | Flashing Layout Single Skin | [6 empty] | 20 | 4 | [24 empty] | 30 | 1.5
24015 | New Pope School | 2024-09-17 | rafael gomez | we start the installation of corrugated ,flashing, zee and insulation ! | Subcontractor | Wylie McDougall | false |  |  |  |  | 4 | 11 | false |  | 1 bunklift | false |  |  |  |  | Corrugated / Screen wall Flashing Insulation Subgirt Zee | [22 empty] | 20 | 10 |  |  | 90 | 10 |  |  | 72 | 10 | 72 | 10
24016 | Genesis of Montgomery | 2024-09-17 | rafael gomez | continued with acm installation and peeling the panels as well | Subcontractor | Chris Buttrey | false |  |  |  |  | 6 | 10 | false |  | 2 bunklift 1 scissorlift | false |  |  |  |  | ACM | 8 | 60
22061 | 19th and Church | 2024-09-16 | JC Panels | Moving material for concrete guy, we got a lot of space for new material. We installed frame, panels | Subcontractor | Josh McPherson | false |  |  |  |  | 5 | 50 | false |  | 2 boom lifts | false |  |  |  |  | ACM
23039 | Vantage VA22 | 2024-09-16 | Saúl chicas | We were working on the west yard south elevation where the big scaffold is | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Scaffold / boom lift | [5 empty] | Coping Corrugated / Screen wall Flashing | [22 empty] | 32 | 10 | [8 empty] | 170 | 10 | [6 empty] | 130 | 10
24007 | DLR DL4 Guard Shack | 2024-09-16 | Israel Garduno | Panel built send 2 guys to set up the light brackets to support the lights, while they were working damage one of our panels which now we need to plan to remove 7 panels due to the installation process also trimming down the 1” legs and all the panels | Subcontractor | Joe Hoyle | false |  |  |  |  | 2 | 9 | false |  | Boom lift and fork lift | false |  |  |  |  | ACM | 10 | 7
24015 | New Pope School | 2024-09-16 | rafael gomez | we only unload the truck the first day because the material and bunklift where late! | Subcontractor | Wylie McDougall | true | the material wast late and bunklift as well |  |  |  | 4 | 4 | true | woodgrain soffit panels,flashing/breack metal ,screws,insulation ,stick pins for insulation ,gray caulk | 1 bunklift | false |  |  |  |  | ACM | 0 | 4
24016 | Genesis of Montgomery | 2024-09-16 | rafael gomez | continued with coping installation | Subcontractor | Chris Buttrey | false |  |  |  |  | 6 | 5 | false |  | 2 bunklift 1scissorlift | false |  |  |  |  | ACM Coping | 5 | 30
23054 | QTS MAN1 DC2 | 2024-09-15 | Ever Mendoza | Some material was moved near the work area | Subcontractor | Josh McPherson | [5 empty] | 5 | 6 |  |  | 2 boom lift | [5 empty] | ACM Corrugated / Screen wall
24016 | Genesis of Montgomery | 2024-09-15 | rafael gomez | we start with coping installation | Subcontractor | Chris Buttrey | false |  |  |  |  | 6 | 9 | false |  | 2bunklift 1scissorlift | false |  |  |  |  | ACM Coping | 3 | 54 | [38 empty] | 6 | 54
23006 | DLR Gold Sterling IAD54 | 2024-09-14 | Chad McCoy | 8 panels removed. 37 panels installed. 3 cut and routes. 4 lights installed. | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 12 | false |  | 46 foot boom. Warehouse forklift | false |  |  |  |  | ACM | 37 | 12
24020 | QTS ATL2 DC2 Osgood | 2024-09-14 | Marvin Blanco | Installing louvers blades and angles in the steel thank God everything is working really well we don't have any issues. | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 11 | false |  | 1 Boomlift and 1 forklift | false |  |  |  |  | Louvre | [24 empty] | 10 | 33
23039 | Vantage VA22 | 2024-09-13 | Saúl chicas | Today we were working on west yard part b and c and also at south elevation | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 | true | Yoyós | Scaffold boom lift | [5 empty] | Coping Corrugated / Screen wall | [22 empty] | 60 | 10 | [16 empty] | 100 | 10
24007 | DLR DL4 Guard Shack | 2024-09-13 | Israel Garduno | line up bolt pattern on the wing wall and secure it with bolts | Subcontractor | Joe Hoyle | false |  |  |  |  | 2 | 10 | false |  | Boom lift and fork lift | false |  |  |  |  | Insulation Other Subgirt Zee | [26 empty] | 800 | 16 |  |  | 600 | 16 | [10 empty] | Securing the wing walls | 2
24016 | Genesis of Montgomery | 2024-09-13 | rafael gomez | continued with acm panel installation | Subcontractor | Chris Buttrey | false |  |  |  |  | 6 | 8 | false |  | 2 bunklift 1scissorlift | false |  |  |  |  | ACM | 4 | 48
22061 | 19th and Church | 2024-09-12 | JC Panels | We install frame, insolation and panels. | Subcontractor | Josh McPherson | false |  |  |  |  | 5 | 50 | false |  | 2 boom lifts | false |  |  |  |  | ACM
23039 | Vantage VA22 | 2024-09-12 | Saúl chicas | Today we were working on east elevation also another crew were working on south yard where the big scaffold is set up | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Scaffold / boom lift | [5 empty] | Coping Flashing Insulation Subgirt Zee | [26 empty] | 130 | 10 |  |  | 100 | 10 | 230 | 10 | [6 empty] | 70 | 10
24007 | DLR DL4 Guard Shack | 2024-09-12 | Israel Garduno | Trying to line up bolt pattern on the wing wall and then setup | Subcontractor | Joe Hoyle | true | Not been able to work due to grading and curb forming |  |  | Sunny and pleasant | 2 | 8 | true | Acm panel,z metal and insulation | Boom lift and fork lift | false |  |  |  |  | Other | [42 empty] | Fail to set up the wing wall due to grading around the guard shack. No bolts on site to secure the wing walls for the guard shack.Dump truck ran over our chops saw | 16
24016 | Genesis of Montgomery | 2024-09-12 | rafael gomez | continued with acm installation | Subcontractor | Chris Buttrey | false |  |  |  |  | 6 | 9 | false |  | 2 bunklift 1 scissorlift | false |  |  |  |  | ACM | 6 | 54
22061 | 19th and Church | 2024-09-11 | JC Panels | We installed frame, insolation and panels. | Subcontractor | Josh McPherson | false |  |  |  |  | 5 | 50 | false |  | 2 boom lifts | false |  |  |  |  | ACM
23033 | Iron Mountain VA6 | 2024-09-11 | Marvin Blanco | My guys need areas to work because they're done already with the stairs 2 and 4 today they were manufacturing panels in the front entrance the weatherproofing guys don't have anything ready for us in the stairs 3 and 5 I think we will have to take the guys out of the Project till they get something ready | Subcontractor | Joe Hoyle | true | Coping for the screenwall and for the ACM panels |  |  | Good condition | 12 | 12 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM | 25 | 144
23039 | Vantage VA22 | 2024-09-11 | Saúl chicas | Today we were sprinting on east elevation part c also on west yard part b and c | Subcontractor | Joe Hoyle | [5 empty] | 5 | 10 |  |  | Boom lift / scaffold | [5 empty] | ACM Corrugated / Screen wall Subgirt Zee | 8 | 10 | [20 empty] | 8 | 10 | [6 empty] | 120 | 10
23052 | Land Rover Knoxville | 2024-09-11 | Chad McCoy | We did lay out on the trash section. And we started installing hat trim and panels on trash area . We tripped in reveals. We are still caulking windows. We are installing trim as we circle the building. | Subcontractor | Colton Van Meter | true | Still no coping to finish areas. |  |  | Partly sunny 88 | 5 | 8 | false |  | 2 85 foot booms | false |  |  |  |  | Caulking Corrugated / Screen wall Flashing Hat Channel | [20 empty] | 130 | 5 | 8 | 3 | [8 empty] | 60 | 1.5 | 40 | 2
24016 | Genesis of Montgomery | 2024-09-11 | rafael gomez | continued with the acm installation | Subcontractor | Chris Buttrey | false |  |  |  |  | 6 | 11 | false |  | 2 bunklift 1forklift | false |  |  |  |  | ACM | 6 | 66
24020 | QTS ATL2 DC2 Osgood | 2024-09-11 | Marvin Blanco | We were installing taking layout for the lovers blades and it's working really well everything fits good tomorrow we are going to be working installing angles | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 11 | false |  | Boomlift and forklift | false |  |  |  |  | Other | [42 empty] | Installing angles for the louvers blades | 33
22061 | 19th and Church | 2024-09-10 | JC Panels | Installe z’s insolation and panels. We also prepare panels for installations | Subcontractor | Josh McPherson | false |  |  |  |  | 5 | 50 | false |  | 2 boom lifts | false |  |  |  |  | ACM
23033 | Iron Mountain VA6 | 2024-09-10 | Marvin Blanco | Installing ACM panels in the front entrance and also stairs 2 and 4 we are waiting for the coping for the screenwall and also in the coping of the ACM panels my guys are manufactured a lot of ACM panels in the front entrance in the side and also in the front the weatherproofing guys doesn't have the stairs 3 ready for us so I think tomorrow we will be waiting on this guys | Subcontractor | Joe Hoyle | true | Coping for the screenwall in the roof |  |  | Good condition | 12 | 12 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM | 30 | 144
23039 | Vantage VA22 | 2024-09-10 | Saul chicas | Today we were working on west yard also we removed 3 panels at le house beacuse they for got to put water proof on the wall | Subcontractor | Joe Hoyle | [5 empty] | 5 | 10 |  |  | Boom lift / scaffold | [5 empty] | ACM Corrugated / Screen wall Subgirt Zee | 3 | 10 | [20 empty] | 10 | 10 | [6 empty] | 80 | 10
23052 | Land Rover Knoxville | 2024-09-10 | Chad McCoy | We finished installing the acm and corrugated panels on the building today. The trash section is all that’s left for panels. One guy caulked all day. One crew did corrugated and trim. And one crew did acm. The last panel was two inches to tall it had to be cut and routed. | Subcontractor | Colton Van Meter | true | Acm was wrong on the last panel height. It was a glue up so it had to be cut and routed |  |  | Sunny 88 | 5 | 8.5 | false |  | 2 85 foot booms | false |  |  |  |  | ACM Caulking Corrugated / Screen wall Flashing Insulation Subgirt Zee | 16 | 8 | [18 empty] | 150 | 6 | 3 | 1 |  |  | 75 | 1 |  |  | 20 | 0.5 | 300 | 4
24016 | Genesis of Montgomery | 2024-09-10 | rafael gomez | continued with the acm installation | Subcontractor | Chris Buttrey | false |  |  |  |  | 6 | 10 | false |  | 2 bunklift 1 scissorlift | false |  |  |  |  | ACM | 6 | 60
24020 | QTS ATL2 DC2 Osgood | 2024-09-10 | Marvin Blanco | We were installing clips for the louvers blades all day today and this afternoon we noticed that we have 27 pieces of clips 5x4 - x5 those clips are going in the vertical tube and we have 5 vertical tubes every each tube takes 7 clips and we just have 13 in the job site | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 12 | false |  | Boomlift and forklift | false |  |  |  |  | Other | [42 empty] | Clips for louvers blades | 36
22061 | 19th and Church | 2024-09-09 | JC Panels | We install framing and panels | Subcontractor | Josh McPherson | false |  |  |  |  | 5 | 50 | false |  |  | false |  |  |  |  | ACM
23033 | Iron Mountain VA6 | 2024-09-09 | Marvin Blanco | Installing ACM panels but we have a lot of short panels everywhere and also we are manufacturing panels because the canopy. | Subcontractor | Joe Hoyle | false |  |  |  |  | 12 | 12 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM | 25 | 144
23039 | Vantage VA22 | 2024-09-09 | Saul chicas | Today we were moving material on north elevation and another crew where working on west yard part b and c | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Subgirt Zee | [22 empty] | 12 | 10 | [6 empty] | 70 | 10
24016 | Genesis of Montgomery | 2024-09-09 | rafel gomez | we continue with the acm installation ! | Subcontractor | Chris Buttrey | false |  |  |  |  | 4 | 9 | false |  | 2 bunklift 1scissorlift | false |  |  |  |  | ACM | 5 | 9
22061 | 19th and Church | 2024-09-06 | JC Panels | We install frame, install panels, prepared panels, fix panels | Subcontractor | Josh McPherson | false |  |  |  |  | 4 | 40 | false |  |  | false |  |  |  |  | ACM
22061 | 19th and Church | 2024-09-05 | JC Panels | We frame all the elevation | Subcontractor | Josh McPherson | false |  |  |  |  | 4 | 40 | true | Angles | 2 boom lifts | false |  |  |  |  | ACM
23033 | Iron Mountain VA6 | 2024-09-05 | Marvin Blanco | We were installing ACM panels all day because the screenwall metal panels we are waiting for the coping to finish everything in the roof window guys are always in our way in the stairs 2 we have a lot of short panels we will have to change a lot of panels because the framing it's not good anywhere. | Subcontractor | Joe Hoyle | false |  |  |  |  | 12 | 12 | true | ACM panels | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM | 35 | 144
24016 | Genesis of Montgomery | 2024-09-05 | rafael gomez | we continued whith the acm installation !but we have to do routing in some panels for the front part and its taking a bit longer to continue | Subcontractor | Chris Buttrey | true | panels are bigger than expected, an we are waiting on the j channel |  |  |  | 6 | 8 | false |  | 2bunklift 1forklift 1scissorlift | false |  |  |  |  | ACM | 3 | 8
24020 | QTS ATL2 DC2 Osgood | 2024-09-05 | Marvin Blanco | Today was a waste day also on this job because the paperwork wasn't done the safety guy are asking for so many things that we don't even know and we don't need but it's what it's just to keep working I hope one day we can start installing the louvers.. | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 10 | false |  | 1 Boomlift 1 forklift | false |  |  |  |  | Other | [42 empty] | Nothing because this guy's ask for to many things | 30
23033 | Iron Mountain VA6 | 2024-09-04 | Marvin Blanco | Modification panels in the entry because the panels they made wrong | Subcontractor | Joe Hoyle | false |  |  |  |  | 12 | 12 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM | 37 | 144
23039 | Vantage VA22 | 2024-09-04 | Saul chicas | Today we were working on a east elevation part c also on east elevation | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Boom lift | [5 empty] | ACM Insulation Subgirt Zee | 26 | 10 | [24 empty] | 325 | 10 |  |  | 200 | 10
24016 | Genesis of Montgomery | 2024-09-04 | rafael gomez | we stard to do the layout, and then we start with the acm installation ,everything looks but we have a confusion with the drawings the elevations where mark wrong but we resolve the problem ,both of the bunklift have problems but christ are already notify | Subcontractor | Chris Buttrey | false |  |  |  |  | 6 | 12 | true | crates | 2 bunklift 1 forklift 1 scissor lift | false |  |  | 12 |  | ACM Layout | 7 | 12
24020 | QTS ATL2 DC2 Osgood | 2024-09-04 | Marvin Blanco | Bad day we couldn't work because we don't have double tipe 3M and Also my guys need the osha 30 | Subcontractor | Dillon Bowman | true | Double tipe 3M |  |  | Good condition | 3 | 12 | false |  | Boomlift and a forklift | false |  |  |  |  | Other | [42 empty] | Nothing because we need tipe 3M double to start installing the louvers | 36
22061 | 19th and Church | 2024-09-03 | JC Panels | We install z’s and panels. We had problems with the boom lift, in the morning it break down a mechanic went to site to fix it and after 15 minutes it broke down again .. | Subcontractor | Josh McPherson | false |  |  |  |  | 4 | 40 | false |  |  | false |  |  |  |  | ACM
23033 | Iron Mountain VA6 | 2024-09-03 | Marvin blanco | Installing ACM panels with a little difficult because the windows guys are in our way everybody wants to work in the same area weatherproofing guy is to slow we were installing flashing around the openings for the window moullions | Subcontractor | Joe Hoyle | false |  |  |  |  | 12 | 12 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Corrugated / Screen wall Flashing | 18 | 48 | [20 empty] | 15 | 48 | [8 empty] | 240 | 48
23039 | Vantage VA22 | 2024-09-03 | Saul chicas | Today we were working on east elevation installing z garts also we start on the east elevation part c installation panels | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Boom lift | [5 empty] | ACM Flashing Insulation Subgirt Zee | 10 | 10 | [24 empty] | 650 | 10 |  |  | 240 | 10 | 80 | 10
24020 | QTS ATL2 DC2 Osgood | 2024-09-03 | Marvin Blanco | Today was the first day in the job site thanks God everything works really good we received the material in the job site and we started taking layout for the louvers and it's looking forward the only thing we need to start working is 3M Doble time and more take 5 screws for drilling steel | Subcontractor | Dillon Bowman | false |  |  |  |  | 4 | 10 | true | Louvers | boomlift and forklift | false |  |  | 40 |  | Layout
22061 | 19th and Church | 2024-08-30 | JC Panels | Install panels , install z’s , caulk around the windows and the louvers | Subcontractor | Josh McPherson | false |  |  |  |  | 4 | 40 | false |  | 2 boom lifts | false |  |  |  |  | ACM
24016 | Genesis of Montgomery | 2024-08-30 | rafael gomez | they finish the caulking on the granite panels ,and clean the panels | Subcontractor | Chris Buttrey | false |  |  |  |  | 6 | 9 | false |  |  | false |  |  |  |  | Caulking | [20 empty] | 500 | 9
22061 | 19th and Church | 2024-08-29 | JC Panels | We fix some panels and all the problems we had on the job. Install some new panels and z’s | Subcontractor | Josh McPherson | false |  |  |  |  | 4 | 40 | false |  | 2 boom lifts | false |  |  |  |  | ACM
23033 | Iron Mountain VA6 | 2024-08-29 | Marvin Blanco | We were working on the ACM panels and corrugated panels in the ACM panels we have to manufacturers because they're to big we have to manufacture 29 more panels in 1 elevation and 15 more in the other elevation total panels 44 also in the corrugated panels we have a little problems because the panels are not the same size, today we have to leave early because the rain | Subcontractor | Joe Hoyle | false |  |  |  |  | 13 | 10 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Corrugated / Screen wall | 20 | 65 | [20 empty] | 18 | 65
23039 | Vantage VA22 | 2024-08-29 | Saul chicas | Today one crew were working on north elevation installing ACM panels also another crew move material to the roof and install on equipment screen wall west elevation | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Boom lift and ladder | [5 empty] | ACM Corrugated / Screen wall Subgirt Zee | 9 | 10 | [20 empty] | 8 | 10 | [6 empty] | 150 | 10
24016 | Genesis of Montgomery | 2024-08-29 | rafael gomez | we continued with the granite panels coping installations ,and we also start to do the caulking ! and we have a missing coping and chris its already notify | Subcontractor | Chris Buttrey | true | the gravel guys take out our equipment and It wast a delay to put them back until they said that we can star to for again |  |  |  | 6 | 10 | true | acm panels | 3 bunklift 1 forklift | false |  |  |  |  | Other | [42 empty] | granite panels coping installation | 10
24016 | Genesis of Montgomery | 2024-08-28 | rafael gomez | continuing installing the granites panels ,we see that some of the granite panels have some little cracks but its a factory defects ! we see it at the fist day , mr christ and mr Nate are awere of the situation . | Subcontractor | Chris Buttrey | false |  |  |  |  | 6 | 9 | false |  | 3 bunklift 1 forklift | false |  |  |  |  | Other | [42 empty] | granite panels | 9
22061 | 19th and Church | 2024-08-27 | JC Panels | We install z’s and panels, fix panels for the reveals | Subcontractor | Josh McPherson | false |  |  |  |  | 4 | 40 | false |  | 2 boom lifts | false |  |  |  |  | ACM
23033 | Iron Mountain VA6 | 2024-08-27 | Marvin Blanco | Manufacturer panels because they are to big we have to cut a lot of ACM panels, also installing panels acm ang corrugated panels in the screenwall for now we are making work the corrugated panels because they send this panels with different dimensions | Subcontractor | Joe Hoyle | false |  |  |  |  | 12 | 12 | false |  | Boomlift scaffolding forklift | false |  |  |  |  | ACM Corrugated / Screen wall | 12 | 72 | [20 empty] | 19 | 72
23039 | Vantage VA22 | 2024-08-27 | Saul chicas | Today we work on east elevation installing ACM and corrugated panes | Subcontractor | Joe Hoyle | [5 empty] | 5 | 10 |  |  | Boom lift | [5 empty] | ACM Corrugated / Screen wall Flashing Insulation Subgirt Zee | 13 | 10 | [20 empty] | 40 | 10 |  |  | 260 | 10 |  |  | 250 | 10 | 60 | 10
24007 | DLR DL4 Guard Shack | 2024-08-27 | Israel Garduno | We need to stay one more day,due to the deliveries been delayed | Subcontractor | Joe Hoyle | true | The guard shack came at 4:00 pm while the canopy and blade wall came at 6:00 pm |  |  | Hot and humid | 2 | 23 | false |  | Boom lift and forklift | false |  |  |  |  | Other | [42 empty] | Helping to install the guard shack | 48
24016 | Genesis of Montgomery | 2024-08-27 | rafael gomez | installing | Subcontractor | Chris Buttrey | false |  |  |  |  | 6 | 11 | false |  | 3 bunklift 1forklift | false |  |  |  |  | Other | [42 empty] | granite panels | 11
22061 | 19th and Church | 2024-08-26 | JC Panels | We install z’s and panels | Subcontractor | Josh McPherson | false |  |  |  |  | 3 | 30 | true | ACM | 2 boom lifts | false |  |  |  |  | ACM
23039 | Vantage VA22 | 2024-08-26 | Saul chicas | Today we were working on east elevation and also at east yard south elevation | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Boom lift | [5 empty] | ACM Corrugated / Screen wall Insulation Subgirt Zee | 9 | 10 | [20 empty] | 19 | 10 |  |  | 390 | 10 |  |  | 220 | 10
24016 | Genesis of Montgomery | 2024-08-26 | rafael gomez | first day of work and everything wast well explained | Subcontractor | Chris Buttrey | false |  |  |  |  | 6 | 8 | false |  | 3 bunklift 1 forlift | false |  |  |  |  | Other | [42 empty] | granite panels | 8
22061 | 19th and Church | 2024-08-24 | JC Panels | Install panels, prepare panels, Z’s , insolation | Subcontractor | Josh McPherson | false |  |  |  |  | 4 | 40 | false |  | 2 Boom lift | false |  |  |  |  | ACM
22061 | 19th and Church | 2024-08-23 | JC Panels | Panels installation, preparation, install z’s and insolation | Subcontractor | Josh McPherson | false |  |  |  |  | 3 | 30 | true | Boom lift | 2 boom lifts | false |  |  |  |  | ACM
23033 | Iron Mountain VA6 | 2024-08-23 | Marvin Blanco | We were installing ACM panels but every where is a short panels we are not able to finish anything because every where is a problem with the layout and also with the corrugated panels the same problem some panels 13" inches and others 13 ½" | Subcontractor | Joe Hoyle | false |  |  |  |  | 12 | 12 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Corrugated / Screen wall | 8 | 44 | [20 empty] | 25 | 100
22061 | 19th and Church | 2024-08-22 | JC Panels | Finish the entrance, installing more panels, insolation and z’s | Subcontractor | Josh McPherson | false |  |  |  |  | 3 | 30 | false |  | Boom lift | false |  |  |  |  | ACM
23033 | Iron Mountain VA6 | 2024-08-22 | Marvin Blanco | Today we try to make some panels work because almost every where it's not firing the panels some panels short and others panels to big in the openings around the windows it's short we were installing panels in screenwall also and some panels are big and others small we are not able to lap the panels really good we were moving material and scaffolding from the roof because matt ask us to move everything from the west side to put it in the north side. | Subcontractor | Joe Hoyle | false |  |  |  |  | 12 | 12 | false |  | Scaffolding, boomlift and forklift | false |  |  |  |  | ACM Corrugated / Screen wall | 8 | 44 | [20 empty] | 25 | 100
23039 | Vantage VA22 | 2024-08-22 | Saul chicas | Today we complete installation at the penthouse and we start installing tape on the east yard | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Boom lift / scaffold | [5 empty] | Other | [42 empty] | Installing tape on metal stud | 10
23052 | Land Rover Knoxville | 2024-08-22 | Chad mccoy | We had a slow start this morning, due to trying to figure out the hypotenuse Panels with the GC and the window guy we really didn’t start installing ACM until 1030 on the main face of the building. A direction has been picked for the hypotenuse panels to be re-made in the field or at least one of them so that we can get approval for the other five. | Subcontractor | Colton Van Meter | true | Same situation as yesterday on the hypotenuse Panels , but a decision has been made, and we will attack that at the beginning of next week when material gets on site |  |  | 91 partly cloudy | 7 | 10 | false |  | 2 65 foot booms. 1 we took from gc | false |  |  |  |  | ACM Insulation | 37 | 5 | [24 empty] | 120 | 1
22061 | 19th and Church | 2024-08-21 | JC Panels | We just install and prepare panels | Subcontractor | Josh McPherson | false |  |  |  |  | 3 | 30 | false |  | Boom lift | false |  |  |  |  | ACM
23033 | Iron Mountain VA6 | 2024-08-21 | Marvin Blanco | We start doing layout with the ACM panels and we have a lot of short panels and Aldo a lot of bigger panels that doesn't fit in the wall we have to cut a lot of panels and remake a lot of panels around the openings of the windows and the ends of the walls also the metal panels they are not the same size all the panels are different sizes | Subcontractor | Joe Hoyle | false |  |  |  |  | 12 | 12 | false |  | Scaffolding, boomlift and forklift | false |  |  |  |  | ACM Corrugated / Screen wall | 3 | 44 | [20 empty] | 40 | 100
23039 | Vantage VA22 | 2024-08-21 | Saul chicas | Today we were working on west yard and also at north roof stair penthouse we modified 6 panels | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 | true | ACM panels | Boom lift / scaffold | [5 empty] | ACM Coping Insulation Subgirt Zee | 8 | 10 | [24 empty] | 260 | 10 |  |  | 120 | 10 | [8 empty] | 50 | 10
23052 | Land Rover Knoxville | 2024-08-21 | Chad McCoy | Acm was continued to be installed around the building. 1 tram continued the bump out and another team set corners and another team filled in so corners could go all the way up. | Subcontractor | Colton Van Meter | true | The hypotenuse Panels are an issue, no matter which way you install them no matter which panel you put where there is a gap between the panels and the curtain wall and the soffit horizontal panels proceed into window glass. |  |  | 91 sunny | 7 | 9.5 | false |  | 2 65 foot booms and we took the gc boom to get the third crew rolling | false |  |  | 1 |  | ACM Insulation Layout Subgirt Zee | 24 | 7 | [24 empty] | 400 | 2 |  |  | 60 | 1
21062 | BNA MNAA Garage B | 2024-08-20 | Zarur Nazario Padron Jr | Working on canopy | Subcontractor | Marc Ribar | [5 empty] | 12 | 120 |  |  | 2 scissor lifts | [5 empty] | ACM Other | 50 | 100 | [40 empty] | 60 ft of flat metal | 20 | 2024-08-20 |  | 1d
22061 | 19th and Church | 2024-08-20 | JC Panels | We install z’s insolation and panels on the entrance | Subcontractor | Josh McPherson | false |  |  |  |  | 3 | 30 | false |  | Boom lift | false |  |  |  |  | ACM
23033 | Iron Mountain VA6 | 2024-08-20 | Marvin Blanco | Installing ACM panels we couldn't finish the wall because we have missed 3 pieces of base flashing because the window guys take out from the wall and start installing the L angles in the openings for the windows and panels also installing metal panels in the screenwall | Subcontractor | Joe Hoyle | false |  |  |  |  | 12 | 12 | false |  | Scaffolding, boomlift and forklift | false |  |  |  |  | ACM Corrugated / Screen wall Flashing | 7 | 14 | [20 empty] | 30 | 100 | [8 empty] | 80 | 30
23039 | Vantage VA22 | 2024-08-20 | Saul chicas | Today we modified 9 panels and installed 2 panels on the north roof stair penthouse | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 | true | Insulation and hardware | Scaffold | [5 empty] | ACM Insulation Subgirt Zee | 2 | 10 | [24 empty] | 195 | 10 |  |  | 50 | 10
21062 | BNA MNAA Garage B | 2024-08-19 | Zarur Nazario Padron Jr | Installing panels after waiting 3 days on waterproofing and also installing the rest of the the hook bars on the bridge | Subcontractor | Marc Ribar | [5 empty] | 12 | 120 |  |  | 2 scissor lifts | [5 empty] | ACM Other | 13 | 60 | [40 empty] | 70 ft worth of flat metal and 9 hood bars on the bridge | 60 | 2024-08-19 |  | 1d
22061 | 19th and Church | 2024-08-19 | JC Panels | This was our first day back in Nashville. We start our day unloading the material. Then we start laying out the ACM walls, we install some z, insolation and a panel. | Subcontractor | Josh McPherson | false |  |  |  |  | 4 | 40 | true | ACM panels |  | false |  |  |  |  | ACM
23033 | Iron Mountain VA6 | 2024-08-19 | Marvin Blanco | downloading material 6 creates of ACM panels also installing panels in the screenwall and also north elevation ACM remanufacturing ACM panels because the windows moullions they're not in the right spot, I think in the screenwall they need to add more blocking wood | Subcontractor | Joe Hoyle | false |  |  |  |  | 12 | 12 | true | 6 creates of ACM panels | Scaffolding , boomlift and forklift | false |  |  |  |  | ACM Corrugated / Screen wall | 10 | 44 | [20 empty] | 35 | 100
23039 | Vantage VA22 | 2024-08-19 | Saul chicas | Today we are working on penthouse | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Scaffold | [5 empty] | ACM Insulation Subgirt Zee | 14 | 10 | [24 empty] | 360 | 10 |  |  | 30 | 10
23052 | Land Rover Knoxville | 2024-08-19 | Chad mccoy | Panels were laid out so the window perimeter panels could be installed. But when further inspection was done the store front windows on 3 sides were installed in the wrong spot. They are 1 1/2 - 2 inches set inside the opening. We decidied to change the install direction of the panels so we can optimize installation | Subcontractor | Colton Van Meter | true | None of the windows are correct and a answer must be made bc we have been delayed long enough on the acm |  |  | 88 sunny | 6 | 8 | false |  | 2 65 foot booms | false |  |  | 2 |  | ACM Insulation Layout Trim | 7 | 7 | [24 empty] | 110 | 1 | [8 empty] | 45 | 1
21062 | BNA MNAA Garage B | 2024-08-18 | Zarur Nazario Padron Jr | Working on finishing pieces and caulking around them. Also putting up hook bars on bridge for ceiling panels | Subcontractor | Marc Ribar | [5 empty] | 7 | 70 |  |  | 2 scissor lifts and 1-85ft boom lift | [5 empty] | ACM Other | 8 | 42 | [40 empty] | Installed 9 of hook bars for the ceiling panels and caulked the tiny pieces of panel together | 28 | 2024-08-18 |  | 1d
23033 | Iron Mountain VA6 | 2024-08-18 | Marvin blanco | We start installing metal panels in the screenwall and also taking metal panels to the roof with the fork lift it take all day taking panels to the roof because we was waiting for the Crane and never showed up. | Subcontractor | Joe Hoyle | false |  |  |  |  | 12 | 12 | false |  | Scaffolding , boomlift and forklift | false |  |  |  |  | Corrugated / Screen wall Other | [22 empty] | 25 | 84 | [18 empty] | Taking material to the roof with the fork lift | 60
23033 | Iron Mountain VA6 | 2024-08-15 | Marvin Blanco | Installing flashing around the openings for the windows we only complete 2 openings because we don't have no more flashing after the those angles we went to install panels acm and metal panels corrugated panels in the screenwall we're going to need flashing for the openings around the windows | Subcontractor | Joe Hoyle | false |  |  |  |  | 12 | 12 | false |  | Boomlift scaffolding forklift | false |  |  |  |  | ACM Corrugated / Screen wall Flashing | 4 | 12 | [20 empty] | 30 | 96 | [8 empty] | 100 | 12
23039 | Vantage VA22 | 2024-08-15 | Saul chicas | Today we were working south east roof stair penthouse also we take the scaffold Down from the roof sunbelt pick it up yesterday also we modified 4 panels | Subcontractor | Joe Hoyle | [5 empty] | 3 | 10 |  |  | Scaffold | [5 empty] | ACM Insulation Subgirt Zee | 4 | 10 | [24 empty] | 360 | 10 |  |  | 120 | 10
24027 | Bailey Robbins Building | 2024-08-15 | JC Panels | We have finish the job 100% we left everything clean | Subcontractor | Chris Buttrey | false |  |  |  |  | 3 | 6 | false |  | Forklift | false |  |  |  |  | ACM
23039 | Vantage VA22 | 2024-08-14 | Saul chicas | Today we were working at penthouse modified panels and installing ACM | Subcontractor | Joe Hoyle | [5 empty] | 3 | 10 | true | ACM, insulation | Scaffold | [5 empty] | ACM Insulation Subgirt Zee | 4 | 10 | [24 empty] | 195 | 10 |  |  | 50 | 10
23052 | Land Rover Knoxville | 2024-08-14 | Chad McCoy | We continued the acm today, There was a lot of start and go due to window guys. The isn’t one area of windows or door that have a primary or a secondary caulk joint. Nothing i sealed. There is also a section of a curb that’s missing under the long windows on the acm bump out. We reversed installed the acm next to the curb that’s missing. And we had 4 talks over the windows with the gc and the window guy. | Subcontractor | Colton Van Meter | true | We have about 20 panels so far that are built with the wrong acm fab screws. The curtain wall isn’t caulked nor are the doors. We also have acm that’s built out of square. They taper from bottom to top on the sides in a 1/4. |  |  | Hot 93 | 5 | 10 | true |  | 2 65?foot booms | false |  |  | 1.5 |  | ACM Insulation Layout | 17 | 8 | [24 empty] | 200 | 1
24027 | Bailey Robbins Building | 2024-08-14 | JC Panels | We got to the site 7am the installation of the panels have been pretty good. Maybe we will be done by tomorrow. | Subcontractor | Chris Buttrey | false |  |  |  |  | 3 | 30 | false |  | Forklift | false |  |  |  |  | ACM
23033 | Iron Mountain VA6 | 2024-08-13 | Marvin Blanco | We have to reinstall flashing in the top of the windows that flashing was installing already and window guys take out just to put another piece of steel they were missing we have to clean up the flashing Aldo we have to cut some panels because they were a little bit longer in the corner it's going to be 8 panels for now and 6 pieces of the flashing reinstalling it took 3 to 4 hours fixing the flashing | Subcontractor | Joe Hoyle | false |  |  |  |  | 12 | 12 | false |  | Scaffolding and boomlift | false |  |  |  |  | ACM Corrugated / Screen wall Flashing Hat Channel Insulation | 4 | 5 | [20 empty] | 40 | 96 |  |  | 160 | 2 |  |  |  |  | 60 | 4 | 90 | 2
23039 | Vantage VA22 | 2024-08-13 | Saul chicas | Today we worked at the penthouse we modified 4 panels | Subcontractor | Joe Hoyle | [5 empty] | 3 | 10 | true | Parapet clamps | Scaffold | [5 empty] | ACM | 4 | 10
23052 | Land Rover Knoxville | 2024-08-13 | Chad mccoy | Acm was continued on cmu wall. It’s topped out and finished. While this was being topped out we pulled panels to start the slant panels in the window areas. But due to the windows not being installed we do not have anything to go off of. So I talked it over with the window guys and the gc. And my team moved to the other side of the building to start installing. Panel joint line was transferred around the building by laser and starter track and kick plates were installed. We had to do some layout but once it was completed we started installing. | Subcontractor | Colton Van Meter | true | Curtain wall instant complete for panels to finish tob |  |  | 89 partly cloudy | 5 | 10 | false |  | 2 65 foot booms | false |  |  | 1 |  | ACM Hat Channel Insulation Layout Subgirt Zee | 27 | 10 | [24 empty] | 150 | 1.5 |  |  | 25 | 0.5 |  |  | 10 | 0.5
24027 | Bailey Robbins Building | 2024-08-13 | JC panels | We arrive to site 12pm. The delivery arrived 3:30 that’s why we couldn’t do much . We just install flashing and J’s also we prepared some panels for tomorrow. | Subcontractor | Chris Buttrey | true | Acm panels |  |  |  | 3 | 2 | true | ACM panels | Forklift | false |  |  |  |  | Flashing
23033 | Iron Mountain VA6 | 2024-08-12 | Marvin Blanco | We're installing metal panels in the roof screenwall with the scaffolding We're missing the wood in the top of the steel I hope for tomorrow we will have something for the ACM panels also we're talking panels to the roof with the forklift.. | Subcontractor | Joe Hoyle | false |  |  |  |  | 6 | 12 | false |  | Scaffolding and boomlift forklift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 34 | 50
23039 | Vantage VA22 | 2024-08-12 | Saul chicas | Today we were working on penthouse installing ACM panels | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | Scaffold | [5 empty] | ACM | 11 | 10
23052 | Land Rover Knoxville | 2024-08-12 | Chad McCoy | Acm was installed on the cmu wall and transferred to the dens glass wall. Insulation was installed | Subcontractor | Colton Van Meter | true | Boom blew a main hydraulic hose. |  |  | Partly cloudy 88 | 5 | 12 | false |  | 2 65 foot booms | false |  |  | 1 |  | ACM Insulation Layout | 25 | 10 | [24 empty] | 820 | 2
23039 | Vantage VA22 | 2024-08-09 | Saul chicas | No working today beacuse of the raining | Subcontractor | Joe Hoyle | [5 empty] | 1 | 0 |  |  | Boom lift | [5 empty] | Other | [42 empty] | No working today due to the rain | 0
23052 | Land Rover Knoxville | 2024-08-09 | Chad McCoy | Acm was continued on cmu wall and coping was installed till we ran out | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | true |  | 2 65 foot booms | false |  |  |  |  | ACM Coping | 12 | 8 | [38 empty] | 170 | 6
23033 | Iron Mountain VA6 | 2024-08-08 | Marvin Blanco | Today we was installing jtrim for the metal panels under the rain everything works really good the only thing we need is the panels in the roof the Crane supposedly it's going to be in the job site on Tuesday and we don't have no more areas to work only in the metal panels tomorrow Friday we're going to finish installing the jtrim and that's all we have also I was checking the layout for the ACM panels in the corner and I think we will have to cut some panels in the corner to be lined up with the window moullions | Subcontractor | Joe Hoyle | false |  |  |  |  | 6 | 10 | false |  | Scaffolding and boomlift | false |  |  |  |  | Flashing | [32 empty] | 500 | 60
23039 | Vantage VA22 | 2024-08-08 | Saul chicas | No working raining | Subcontractor | Joe Hoyle | [5 empty] | 1 | 0 |  |  | Boom lift | [5 empty] | Other | [42 empty] | No work raining all day | 0
23052 | Land Rover Knoxville | 2024-08-08 | Chad McCoy | Storms Almost all day | Subcontractor | Colton Van Meter | true | Storms |  |  | Storms | 5 | 0.5 | false |  | 2 85 foot booms | false |  |  |  |  | ACM | 0 | 0
24010 | Thompson Tractor | 2024-08-08 | David placzkowski | installed hanger bar j. had to cut down stiffeners for being close to the extrusion like all the other panels that go on the hanger bar. installed very last 4 panels for the job. staterted to peel poly. also broke down crates | Subcontractor | Wylie McDougall | false |  |  |  |  | 2 | 8 | false |  | 80ft boom | false |  |  |  |  | ACM | 4 | 16
23033 | Iron Mountain VA6 | 2024-08-07 | Marvin Blanco | This morning we finished putting the scaffolding at the roof and also We get our first load with the metal panels we finished unloading after lunch and after that we went to the roof and started installing the Jtrim with the scaffolding and around 3 pm we get our second load of metal panels with stanley steel clips after we finish we continue working in the roof with the jtrim for 25 minutes because after that start raining there is one more thing we have 12 panels short because the window is not in the right place the move the window to the corners to make it fit so we need to replace 12 panels for now | Subcontractor | Joe Hoyle | false |  |  |  |  | 6 | 11 | true | Metal panels for the screenwall | 1 Boomlift and a scaffolding | false |  |  |  |  | Flashing | [32 empty] | 80 | 66
23039 | Vantage VA22 | 2024-08-07 | Saul chicas | Today we were working on west elevation west yard uninstalling and re installing panels at knee wall load bank | Subcontractor | Joe Hoyle | [5 empty] | 5 | 10 |  |  | 2 boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 5 | 10
23052 | Land Rover Knoxville | 2024-08-07 | Chad mccoy | Coping clear and acm was installed | Subcontractor | Colton Van Meter | true | Coping was wrong again. We are installing per mcdougals instructions |  |  | Partly cloudy 85 | 5 | 8 | false |  | 2 65 foot booms | false |  |  | 1.5 |  | ACM Coping Layout | 5 | 5 | [38 empty] | 150 | 4
23052 | Land Rover Knoxville | 2024-08-07 | Chad mccoy | 2 trucks came today with all the starter supply’s we needed to start acm. We recieved the coping today as well, not all of it but some. During inspection of the coping we have found more coping that is pressed wrong. We talked it over with mcdougal and a resolution was agreed upon. My second team installed acm on the front and layed out for continuation of acm. | Subcontractor | Colton Van Meter | true | Coping was made wrong, |  |  | Hot and sunny | 5 | 8 | true | 2 trucks. Acm zs and coping | 2 65 feet boom | false |  |  | 2 |  | ACM Coping Layout Trim | 5 | 5 | [34 empty] | 50 | 2 |  |  | 220 | 3
23033 | Iron Mountain VA6 | 2024-08-06 | Marvin Blanco | In the morning waiting for scaffolding because the only are to work is with scaffolding in the roof, in the ACM area window guys are working the scaffolding arrives at 1 pm and we start putting the scaffolding in the roof to start doing the jtrims around the screwball we only have a little delay waiting for scaffolding also window guys take of our base flashing 6 pieces and damaged | Subcontractor | Joe Hoyle | true | Scaffolding |  |  | Good condition 🔥 hot | 6 | 11 | true | Scaffolding | 1 Boomlift | false |  |  |  |  | Other | [42 empty] | We don't install anything because we're waiting for scaffolding | 66
23039 | Vantage VA22 | 2024-08-06 | Saul chicas | Today we were working on west yard uninstalling and re installing panels at knee load bank | Subcontractor | Joe Hoyle | [5 empty] | 4 | 10 |  |  | 2 boom lift | [5 empty] | Other | [42 empty] | Uninstalling and re installing panels at west elevation west yard part b and c ( extra work) | 10
23052 | Land Rover Knoxville | 2024-08-06 | Chad McCoy | We started our day prepping for a truck that didn’t bring everything to start installing, No coping, no color match kick plates, so shims or screws. But while waiting to be disappointed again we installed insulation and some trim on the corrugated and we started prepping the dumpster area for panels | Subcontractor | Colton Van Meter | false |  |  |  |  | 4 | 8 | true | Acm. | 2 65 foot booms | false |  |  | 2 |  | Flashing Hat Channel Insulation Layout | [26 empty] | 2000 | 7 |  |  |  |  | 80 | 2 | 80 | 1
24010 | Thompson Tractor | 2024-08-06 | David placzkowski | installed acm panels. put smaller panels on under bump out, put on 3/4 angle for bottom of panels first. then installed bump out panels. | Subcontractor | Wylie McDougall | false |  |  |  |  | 2 | 8 | false |  | 80ft boom | false |  |  |  |  | ACM | 5 | 16
23039 | Vantage VA22 | 2024-08-05 | Saul chicas | Today we were working on west yard doing some extra work on west yard at knee wall above the load bank also we were moving material at penthouse | Subcontractor | Joe Hoyle | true | WT was moving out material and also we don't have space to put or boom lift to keep working on west legation doing the extra work |  |  | Good | 5 | 10 |  |  | Boom lift | [5 empty] | Other | [42 empty] | Today we were doing extra work uninstalling and reinstalling corrugated panel above the load bank on west yard west elevation part b and c also we were moving some panels at penthouse | 10
24010 | Thompson Tractor | 2024-08-05 | David placzkowski | installed acm panel, bottom angle for 6 inch leg. we have and to trim back all the stiffners on all the panels so far because they are to high up amd we would never be able to engage it into the j | Subcontractor | Wylie McDougall | false |  |  |  |  | 2 | 8 | false |  | 80ft boom | false |  |  |  |  | ACM | 5 | 16
23039 | Vantage VA22 | 2024-08-02 | Saul chicas | Today we were working on north elevation also we was moving material on the penthouse (ACM ) | Subcontractor | Joe Hoyle | [5 empty] | 5 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 29 | 10
23039 | Vantage VA22 | 2024-08-01 | Saul chicas | Today we were working on north side also we were at the penthouse installing ACM panels | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Boom lift / scaffold | [5 empty] | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 20 | 10 |  |  | 455 | 10 |  |  | 230 | 10
23039 | Vantage VA22 | 2024-07-31 | Saul chicas | Today we were working on penthouse and west yard west elevation part b and c also WT was moving our corrugated panels these morning | Subcontractor | Joe Hoyle | [5 empty] | 6 | 10 |  |  | Boom lift / scaffold | [5 empty] | ACM Corrugated / Screen wall Flashing Insulation Subgirt Zee | 7 | 10 | [20 empty] | 14 | 10 |  |  | 390 | 10 |  |  | 190 | 10 | 180 | 10
24010 | Thompson Tractor | 2024-07-31 | David placzkowski | Installed acm panels on canopy. Installed 2 remade panels on front upper wall. caulked out both to finish both areas. also broke down crates and did a good clean up | Subcontractor | Wylie McDougall | false |  |  |  |  | 2 | 8 | false |  | 80ft boom lift | false |  |  |  |  | ACM | 4 | 10
23039 | Vantage VA22 | 2024-07-30 | Saul chicas | Today we were working on west yard west election part b and c also installing ACM panels at the penthouse | Subcontractor | Joe Hoyle | [5 empty] | 5 | 10 |  |  | 2 boom lift 1 scaffold | [5 empty] | ACM Corrugated / Screen wall Flashing Insulation Subgirt Zee | 7 | 10 | [20 empty] | 14 | 10 |  |  | 455 | 10 |  |  | 170 | 10 | 50 | 10
24010 | Thompson Tractor | 2024-07-30 | David placzkowski | installed j and angle. installed acm panels and caulked brick joint. caulked every screw hole and head of screws as requested. done that the whole job now | Subcontractor | Wylie McDougall | false |  |  |  |  | 2 | 8 | false |  | 80ft boom | false |  |  |  |  | ACM Caulking | 4 | 14 | [18 empty] | 10 | 0.5
23039 | Vantage VA22 | 2024-07-29 | Saul chicas | Today we start working installing ACM metal panels at le house also we were working on west yard west elevation part b and c installing corrugated metal panels | Subcontractor | Joe Hoyle | [5 empty] | 5 | 10 | true | Scaffold | 2 Boom lift / Scaffold | [5 empty] | ACM Corrugated / Screen wall | 6 | 10 | [20 empty] | 24 | 10
24010 | Thompson Tractor | 2024-07-29 | David placzkowski | installed acm panels. caulked out panels and flashing. very hard logistics to work around for install of acm. had to maneuver through 2 trees for install | Subcontractor | Wylie McDougall | false |  |  |  |  | 2 | 7 | false |  | 80ft boom | false |  |  |  |  | ACM | 2 | 10
24010 | Thompson Tractor | 2024-07-27 | David placzkowski | installed flashing and caulked | Subcontractor | Wylie McDougall | false |  |  |  |  | 5 | 7 | false |  | 80ft boom | false |  |  |  |  | Caulking Flashing | [20 empty] | 100 | 14 | [10 empty] | 60 | 4
23039 | Vantage VA22 | 2024-07-26 | Saul chicas | Today we were working on west yard west elevation part B and C | Subcontractor | Joe Hoyle | [5 empty] | 5 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 25 | 10
24010 | Thompson Tractor | 2024-07-26 | David placzkowski | installed flashing and acm panels and j | Subcontractor | Wylie McDougall | false |  |  |  |  | 2 | 8 | false |  |  | false |  |  |  |  | ACM Flashing | 7 | 12 | [30 empty] | 65 | 2
23039 | Vantage VA22 | 2024-07-25 | Saul chicas | We were working installing corrugated metal panels at west yard west elevation part b and c | Subcontractor | Joe Hoyle | [5 empty] | 5 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 28 | 10
24010 | Thompson Tractor | 2024-07-25 | David placzkowski | Installed panels, j and flashing | Subcontractor | Wylie McDougall | true |  |  |  | had a 1 hour rain delay after lunch and another 1 hour before end of day | 2 | 7 | false |  | 80ft boom | false |  |  |  |  | ACM Flashing | 2 | 10 | [30 empty] | 24 | 2
23039 | Vantage VA22 | 2024-07-24 | Saul chicas | Today we were working installing corrugated panels on west yard west elevation part B and C also we have to cut the double face tape to 1 inc | Subcontractor | Joe Hoyle | [5 empty] | 5 | 10 | true | Screws for corrugated panels | Boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 19 | 10
24010 | Thompson Tractor | 2024-07-24 | David placzkowski | installed acm panels | Subcontractor | Wylie McDougall | false |  |  |  |  | 2 | 8 | false |  | 80ft boom | false |  |  |  |  | ACM | 10 | 16
23039 | Vantage VA22 | 2024-07-23 | Saul chicas | Today we keep working on west yard | Subcontractor | Joe Hoyle | [5 empty] | 5 | 8 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Flashing | [22 empty] | 10 | 8 | [8 empty] | 220 | 8
24010 | Thompson Tractor | 2024-07-23 | David placzkowski | caulked and installed j. | Subcontractor | Wylie McDougall | false |  |  |  |  | 2 | 8 | false |  | 80ft boom | false |  |  |  |  | Caulking Other | [20 empty] | 85 | 8 | [20 empty] | installed j and did layout | 8
23039 | Vantage VA22 | 2024-07-22 | Saul chicas | Today we keep working on west yard also we finish moving all the ACM panels on the penthouse | Subcontractor | Joe Hoyle | [5 empty] | 5 | 8 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall Flashing | [22 empty] | 13 | 8 | [8 empty] | 60 | 8
23052 | Land Rover Knoxville | 2024-07-22 | Chad McCoy | Rain is hot or miss all week. | Subcontractor | Colton Van Meter | true | Storms. |  |  | 88 | 5 | 8 | false |  | 2 65 foot booms | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 32 | 7 |  |  | 450 | 3 |  |  | 120 | 2
24010 | Thompson Tractor | 2024-07-22 | David Placzkowski | took down 2 panels. caulked out all screws abs replaced the 2 panels again. also installed 5 more panels and began caulking | Subcontractor | Wylie McDougall | false |  |  |  |  | 2 | 8 | false |  | 45ft boom | false |  |  |  |  | ACM | 7 | 14
23039 | Vantage VA22 | 2024-07-20 | Saul chicas | Today we work on west yard installing corrugated panels | Subcontractor | Joe Hoyle | [5 empty] | 3 | 6 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 15 | 6
23039 | Vantage VA22 | 2024-07-19 | Saul chicas | Today we were installing corrugate panel on west yard also we were moving ACM to the penthouse | Subcontractor | Joe Hoyle | [5 empty] | 5 | 10 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 12 | 8
24010 | Thompson Tractor | 2024-07-19 | David placzkowski | installed acm and j. | Subcontractor | Wylie McDougall | false |  |  |  |  | 2 | 8 | false |  | 45ft boom | false |  |  |  |  | ACM | 9 | 16
23039 | Vantage VA22 | 2024-07-18 | Saúl chicas | Today we were downloading material and took us all day doing that and start moving some panels to the roof also also we're were cutting the first line of corrugate panel | Subcontractor | Joe Hoyle | [5 empty] | 5 | 10 | true | ACM, insulation, hardware, flashing, clicks | Boom lift | [5 empty] | ACM Corrugated / Screen wall | 0 | 10 | [20 empty] | 0 | 10
24010 | Thompson Tractor | 2024-07-18 | David placzkowski | installed j. had multiple delays and shut downs. 6 hrs worth of shut downs | Subcontractor | Wylie McDougall | true | had delays due to the contractor having issues with details and system depth as well as waterproofing that exceeds what print calls for |  |  |  | 2 | 2 | false |  | 45ft boom | false |  |  |  |  | ACM | 1 | 2
23039 | Vantage VA22 | 2024-07-17 | Saúl chicas | Today we don't work because we still waiting for material to start installing the corrugated panel | Subcontractor | Joe Hoyle | [5 empty] | 5 | 0 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 0 | 0
23052 | Land Rover Knoxville | 2024-07-17 | Chad McCoy | We finished the bottom section on the Long elevation today and then we turned the corner and started going around the building so that we can go up and then go across the top. We had storms today. The storm were coming and we were trying to pre-stage material in certain places easier access. | Subcontractor | Colton Van Meter | true | Storms |  |  | Storms on and off all day. Lightning within 3 miles | 4 | 9 | true |  | 2 65 foot booms | false |  |  | 2 |  | Corrugated / Screen wall Insulation Layout Subgirt Zee | [22 empty] | 15 | 3 |  |  | 400 | 1 |  |  | 430 | 2
24010 | Thompson Tractor | 2024-07-17 | David placzkowski | installed acm panels, installed j, moved materials to working location for tomorrow | Subcontractor | Wylie McDougall | false |  |  |  |  | 2 | 8 | false |  | 45ft boom | false |  |  |  |  | ACM | 5 | 12
23039 | Vantage VA22 | 2024-07-16 | Saúl chicas | Today we are not able to work because we are missing material (double face tape )also we have to start with the second sheet on west yard because they have to add a small frame to lower out flashing so we don't have a big gap between our flashing and the concrete | Subcontractor | Joe Hoyle | true | Double face tape |  |  | Good | 5 | 0 |  |  | Boom lifts | [5 empty] | Corrugated / Screen wall | [22 empty] | 0 | 0
23052 | Land Rover Knoxville | 2024-07-16 | Chad McCoy | We continued with the corrugated on the back Longbottom wall. There are a lot of touch in this section. We’re both full panel span over multiple cuts and then the lab all the are as well so there will be one panel with 2 to 5 cut and then the one above, it will also have the same 5+ and on top of each other. | Subcontractor | Colton Van Meter | true | The cuts and layout take a minute to make sure everything is correct. |  |  | Lightning and storms off and on all day | 4 | 8 | false |  | 2 65 foot booms | false |  |  | 2 |  | Corrugated / Screen wall Insulation Layout Subgirt Zee | [22 empty] | 15 | 5 |  |  | 400 | 2 |  |  | 100 | 1
24010 | Thompson Tractor | 2024-07-16 | David placzkowski | moved materials, did layout and started installed | Subcontractor | Wylie McDougall | false |  |  |  |  | 2 | 8 | false |  | 45ft boom lift | false |  |  |  |  | ACM | 3 | 12
23039 | Vantage VA22 | 2024-07-15 | Saúl chicas | Today we are not working because of the missing material ( double face tape ) | Subcontractor | Joe Hoyle | true | Double face tape |  |  | Good | 5 | 0 |  |  | Boom lifts | [5 empty] | Corrugated / Screen wall | [22 empty] | 0 | 0
23052 | Land Rover Knoxville | 2024-07-15 | Chad McCoy | Corrugated and insulation was continued around the area of the building we are working on. The back of the building where the scuppers are has a lot of layout. It’s a very busy wall. | Subcontractor | Colton Van Meter | true | There was a lot of higher ups on site today looking at the panel joints. |  |  | Sun and hot. 99 | 5 | 8 | true |  | 2 65 foot booms | false |  |  |  |  | Corrugated / Screen wall Insulation | [22 empty] | 10 | 6 |  |  | 450 | 5
24010 | Thompson Tractor | 2024-07-15 | David placzkowski | waited on truck, opened up crates and moved materials | Subcontractor | Wylie McDougall | false |  |  |  |  | 2 | 6 | true | 6 crates of materials and a crates of baker scaffolding | 45ft boom lift | false |  |  |  |  | Other | [42 empty] | opened up crates amd moved materials | 6
23033 | Iron Mountain VA6 | 2024-07-12 | Marvin Noel Blanco | Installing 13 panels we're not able to continue Installing panels because they're not ready they don't have any window install and we need to be lining up with the window moullons also they need to frame in the side of the window wall | Subcontractor | Joe Hoyle | false |  |  |  |  | 5 | 11 | true | ACM panels and insulation | 1 Boomlift | false |  |  |  |  | ACM | 13 | 55
23039 | Vantage VA22 | 2024-07-12 | Saúl chicas | Today we are not able to work because of the weather also we miss a double face tape between panel and metal stud | Subcontractor | Joe Hoyle | true | We are missing double face tape to start installing the corrugated panels |  |  | Raining | 5 | 2 |  |  | Boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 0 | 2
23052 | Land Rover Knoxville | 2024-07-12 | Chad mccou | Z insulation and panels were continued. We are stacking the 3 and 4 row that takes us to the to of the back elevevation. Minus the rip. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 8 | true |  | 2 65 foot booms | false |  |  |  |  | Corrugated / Screen wall Insulation | [22 empty] | 11 | 5 |  |  | 600 | 5
23056 | Eagleville Fire Hall | 2024-07-12 | Saúl chicas | Today we complete the installation of ACM and caulking 100% | Subcontractor | Chris Buttrey | [5 empty] | 1 | 2 |  |  | Ladder scaffold | [5 empty] | Caulking | [20 empty] | 70 | 2
23033 | Iron Mountain VA6 | 2024-07-11 | Marvin Noel Blanco | Installing Zs and insulation, but I don't think we have areas ready for the panels because there is no window install we're thinking to leave the job about a week and come back after. We need the corrugated panels for work in the roof but we don't have those, also we unload 6 create of panels | Subcontractor | Joe Hoyle | false |  |  |  |  | 5 | 11 | true | 6 creates of ACM panels and flats straps and Jtrim for the corrugated panels | 1 Boomlift | false |  |  |  |  | Hat Channel Insulation | [26 empty] | 1024 | 24 | [6 empty] | 20 | 20
23039 | Vantage VA22 | 2024-07-11 | Saúl chicas | Today we have a delivery of single skin panel also we start doing some layouts to start installation | Subcontractor | Joe Hoyle | [5 empty] | 5 | 10 | true | Single skins panels | 2 Boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 0 | 10
23052 | Land Rover Knoxville | 2024-07-11 | Chad mccoy | Z insulation and panels were continued. There is a layout that must be matched to meet the upper elevation to the Bottom. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 8 | false |  | 2 65 foot books | false |  |  |  |  | Corrugated / Screen wall Insulation | [22 empty] | 23 | 7 |  |  | 1750 | 7
23056 | Eagleville Fire Hall | 2024-07-11 | Saúl chicas | Today I was doing some caulking on the partial east and west elevation and also at east elevation west entry | Subcontractor | Chris Buttrey | [5 empty] | 1 | 6 |  |  | Ladders, scaffolding | [5 empty] | Caulking | [20 empty] | 130 | 6
23033 | Iron Mountain VA6 | 2024-07-10 | Marvin Noel Blanco | Waiting for silicone, installing Zs" and flashing moving material because we're making space for more delivery tomorrow morning Thursday we borrowed 2 cases of silicone because we never get our silicone, Putting barricade around the boomlift making everything 100 💯 PPE | Subcontractor | Joe Hoyle | true | Silicone |  |  | Good condition 🔥 hot | 5 | 11 | false |  | 1 boomlift | false |  |  |  |  | Flashing Hat Channel | [32 empty] | 90 | 15 | 300 | 40
23039 | Vantage VA22 | 2024-07-10 | Saúl chicas | Today we do the safety orientation also we onload the 2 boom lift but the delivery dont t show up | Subcontractor | Joe Hoyle | true | Material don't show up |  |  |  | 5 | 0 |  |  | Boom lift | [5 empty] | ACM | 0 | 0
23056 | Eagleville Fire Hall | 2024-07-10 | Saúl chicas | Today we were doing some caulking at esgleville TN we complete 100% the installation of ACM and 97% of caulking tomorrow we will complete everything 100% | Subcontractor | Chris Buttrey | [5 empty] | 1 | 10 |  |  | Ladder scaffold | [5 empty] | ACM Caulking | [21 empty] | 10
23061 | Baldwin Subaru | 2024-07-10 | David placzkowski | installed metal silver strip on tower | Subcontractor | Colton Tomlin | true | had to wait for the contractor to have the tower framed out amd raised. |  |  |  | 2 | 3 | false |  | 5k lull 46ft boom | false |  |  |  |  | Other | [42 empty] | Installed metal air on tower | 6
23033 | Iron Mountain VA6 | 2024-07-09 | Marvin Noel Blanco | Installing Zs in the north west corner of the building with silicone in the screws taking layout b | Subcontractor | Joe Hoyle | false |  |  |  |  | 5 | 11 | true | Screws shins 795 silicone | 1 Boomlift | false |  |  |  |  | Hat Channel | [34 empty] | 300 | 55
23052 | Land Rover Knoxville | 2024-07-09 | Chad mccoy | We continued installing Z and flashing. I filled in all the cut pieces that need to be filled in on the back wall. Another crew went down the right side face starting elevation with trim and the first Z and then a second crew way down the left face doing the same thing | Subcontractor | Colton Van Meter | true | Upon arrival this morning, we have noticed that everywhere that the doors open they do not have any kind of stoppers and the doors are destroying our bottom trim that the panel set in. I have talked to the GC about this and his response is there are wedges that are supposed to hold the door, but upon inspection, the wedges are not in the door themselves. They are just laying around. |  |  | Hot 92 | 5 | 8 | false |  | 65 foot boom | false |  |  | 1 |  | Flashing Layout Subgirt Zee | [30 empty] | 1120 | 6 | 310 | 2
23033 | Iron Mountain VA6 | 2024-07-08 | Marvin Blanco | waiting for material because john w McDougall didn't send screws and silicone for start doing the Zs" metal we lost all day work | Subcontractor | Joe Hoyle | true | Screws silicone |  |  | Good condition 🔥 hot | 5 | 10 | false |  | Boomlift | false |  |  |  |  | Other | [42 empty] | Nothing because we don't have what we need in the job site screws silicone | 50
23052 | Land Rover Knoxville | 2024-07-08 | Chad mccoy | No shipment came today we received the boom lift. We did any extensive layout on the corrugated we installed z and flashing | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 8 | false |  | 65 ft boom | false |  |  | 1 |  | Flashing Layout Subgirt Zee | [30 empty] | 820 | 6 | 200 | 2
23056 | Eagleville Fire Hall | 2024-07-08 | Saúl chicas | Today we complete all the installation of the ACM metal panels at Eagleville TN | Subcontractor | Chris Buttrey | [5 empty] | 3 | 10 |  |  | Scaffold | [5 empty] | ACM | 63 | 150
23061 | Baldwin Subaru | 2024-06-26 | David placzkowski | waited on truck until 10:05am. the off loaded truck and started to make the missing panels that was left out of the details. | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8 | false |  | 5k lull and 46ft boom | false |  |  |  |  | Other | [42 empty] | made all the panels necessary to fill the missing square foot of panels over the roof line. | 14
23061 | Baldwin Subaru | 2024-06-24 | David placzkowski | installed jam and head trim on man door, caulked, popped in reveals | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 5 | false |  | 5k lull and 46ft boom | false |  |  |  |  | Other Trim | [36 empty] | 40 | 4 |  |  |  |  | caulked, popped in reveals | 6
23061 | Baldwin Subaru | 2024-06-23 | David placzkowski | finish work. caulk joints. and end damns due to bad terminations | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 6 | false |  | 5k lull and 46ft | false |  |  |  |  | Caulking Other | [20 empty] | 85 | 8 | [20 empty] | had to field fabrication our own end damns and pop in trim for all heads and jam joints. caulking of trim and jams | 4
23061 | Baldwin Subaru | 2024-06-22 | David placzkowski | installed metal era blue strip | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8 | false |  | 5k lull and 46ft boom | false |  |  |  |  | Other | [42 empty] | blue metal sugary strip | 16
23061 | Baldwin Subaru | 2024-06-21 | David placzkowski | started install of blue metal stripping and also finish trim work. had to shut day down early due to having to go get caulk | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 3.5 | false |  | 5k lull and 46ft boom | false |  |  |  |  | Other | [42 empty] | metal arrow blue strip | 3.5
23061 | Baldwin Subaru | 2024-06-20 | David placzkowski | installed acm panels. re made3 panels in the field that was incorrect to begin with. caulked and popped in trim | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8 | false |  | 46ft boom and 5k lull | false |  |  |  |  | ACM | 9 | 8
23061 | Baldwin Subaru | 2024-06-19 | David placzkowski | installed acm panels, caulked and finish work. cut and routed 1 panel and had to make end damn for bad termination detal | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8 | false |  | 5k lull and 46ft boom | false |  |  |  |  | ACM | 8 | 6
23061 | Baldwin Subaru | 2024-06-18 | David placzkowski | installed acm panels. cut and routed 4 panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8 | false |  | 5k lull and 46ft boom | false |  |  |  |  | ACM | 21 | 16
23061 | Baldwin Subaru | 2024-06-17 | David placzkowski | installed acm panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 4 | false |  | 5k lull and 46ft boom | false |  |  |  |  | ACM | 10 | 8
23061 | Baldwin Subaru | 2024-06-16 | David placzkowski | installed acm panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 3 | false |  | 5k lull and 46ft boom | false |  |  |  |  | ACM | 4 | 8
23061 | Baldwin Subaru | 2024-06-14 | David placzkowski | installed acm panels amd caulked, peeled poly | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 7 | false |  | 5k lull and 46ft boom | false |  |  |  |  | ACM | 13 | 10
23061 | Baldwin Subaru | 2024-06-13 | David placzkowski | Installed acm panels. cut and routed 3 panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8 | false |  | 5k lull and 46ft boom | false |  |  |  |  | ACM | 13 | 16
23061 | Baldwin Subaru | 2024-06-12 | David placzkowski | installed acm panels. cut and routed 2 panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 6 | false |  | 5k lull and 46ft boom | false |  |  |  |  | ACM | 10 | 12
23061 | Baldwin Subaru | 2024-06-11 | David placzkowski | installed acm panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 5 | false |  | 5k lull and 46ft boom | false |  |  |  |  | ACM | 16 | 10
23009 | Yondr Allegro South | 2024-06-10 | Chad mccoy | 5 acm panels. 250 feet of trim | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 11 | false |  | 85 foot boom | false |  |  | 2 |  | ACM Layout Trim | 5 | 5 | [34 empty] | 250 | 9
23061 | Baldwin Subaru | 2024-06-10 | David placzkowski | installed acm panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 7 | false |  | lull and 46ft boom | false |  |  |  |  | ACM | 20 | 14
23061 | Baldwin Subaru | 2024-06-08 | David Placzkowski | Installed acm panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 6.5 | false |  | lull and 46ft boom | false |  |  |  |  | ACM | 17 | 13
24013 | VA 14.2 | 2024-06-08 | Chad McCoy | 22 access doors installed. 22 access doors trimmed out. 180 feet of clear installed. 180!feet of coping installed. 120 feet of corner installed | Subcontractor | Chris Buttrey | true | Hitt has key areas that they are in no rush to get finished. I will be leaving Virginia this weekend from all 3 jobs |  |  | Partly cloudy 82 | 5 | 8 | true |  |  | false |  |  |  |  | Coping Trim | [36 empty] | 120 | 4 |  |  | 130 | 4
23061 | Baldwin Subaru | 2024-06-07 | David placzkowski | installed acm panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 7.5 | false |  | lull and 46ft boom | false |  |  |  |  | ACM | 20 | 15
23061 | Baldwin Subaru | 2024-06-06 | David placzkowski | installed panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8.5 | false |  | 46ft boom, lull | false |  |  |  |  | ACM | 21 | 17
23061 | Baldwin Subaru | 2024-06-05 | David placzkowski | installed acm panels and unloaded truck | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8 | true | 5 crates of acm | lull and 45 foot boom lift | false |  |  |  |  | ACM | 10 | 14
23009 | Yondr Allegro South | 2024-06-04 | Chad mccoy | 11 acm panels were installed. 2 outlets cut out and 5 panels cut to fit due to wood blocking or precast, We also insulated z and insulation behind the upper panels that connect to the corrugated. I recieved the go ahead to cut panels to fit the wood blocking on the canopy entrance way. | Subcontractor | Colton Van Meter | true | Wood blocking on the top of the entrance way is 1 1/4 lower on the left side of the entry way than it is on the right. From the window hoping in between the panels the left side has 98 1/8 to bottom of wood blocking. In the right. It has around 99 5/16 on average to bottom of wood blocking. Acm joints are 1/16 off left to right with laser ran as a control line for elevation check. |  |  | Partly cloudy 92 | 4 | 9.5 | false |  | 85 foot boom | false |  |  | 1 |  | ACM Insulation Layout Subgirt Zee Trim | 11 | 5 | [24 empty] | 128 | 1 |  |  | 140 | 1.5 |  |  |  |  | 30 | 1
23072 | Hubler Nissan | 2024-05-30 | David placzkowski | caulked skyward joints, installed jam trim and head flashing | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 10 | false |  | 6k lull and 60ft boom | false |  |  |  |  | Caulking Flashing | [20 empty] | 100 | 15 | [10 empty] | 70 | 5
23072 | Hubler Nissan | 2024-05-29 | David placzkowski | installed panels and installed trim | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 9.5 | false |  | 6k lull and 60ft boom | false |  |  |  |  | ACM | 23 | 19
23072 | Hubler Nissan | 2024-05-28 | David placzkowski | installed acm panels, cut amd routed 2 panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 9.5 | false |  | 6k lull and 60ft boom | false |  |  |  |  | ACM | 35 | 19
23072 | Hubler Nissan | 2024-05-23 | David placzkowski | installed acm panels. grinder cleared the reveal pockets on every panel. | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 9 | false |  | 6k lull and 60ft boom | false |  |  |  |  | ACM | 17 | 18
23072 | Hubler Nissan | 2024-05-22 | David placzkowski | installed acm panels and peeled poly | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 9.5 | false |  | 6k lull and 60ft boom | false |  |  |  |  | ACM | 24 | 16
23072 | Hubler Nissan | 2024-05-21 | David placzkowski | installed acm panels. cut and routed 7 panels as well. peeled poly as well | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 9 | false |  | 6k lull and 60ft boom lift | false |  |  |  |  | ACM | 14 | 15
24013 | VA 14.2 | 2024-05-21 | Chad mccoy | 60 panels installed, The orange boom broke hitt had it on a fix list. We stopped installing at 1. We moved material to the front to finish. | Subcontractor | Chris Buttrey | true | Wood blocked isn’t down. The ground work hasn’t been completed. The access doors haven’t arrived. |  |  | Sunny 86 | 4 | 7 | true |  |  | false |  |  |  |  | Corrugated / Screen wall Flashing | [22 empty] | 60 | 6 | [8 empty] | 30 | 1
23006 | DLR Gold Sterling IAD54 | 2024-05-20 | Chad McCoy | 7 light holes cut, 7 upper vertical panels cut and routed, 12 zs installed. 3 bundles of insulation. | Subcontractor | Colton Van Meter | false |  |  |  |  | 4 | 10 | false |  | 85 foot boom | false |  |  |  |  | ACM Insulation Subgirt Zee Trim | 29 | 7 | [24 empty] | 100 | 1 |  |  | 130 | 1 |  |  |  |  | 40 | 1
23006 | DLR Gold Sterling IAD54 | 2024-05-20 | Chad McCoy | 7 light holes cut, 7 upper vertical panels cut and routed, 12 zs installed. 3 bundles of insulation. | Subcontractor | Colton Van Meter | false |  |  |  |  | 4 | 10 | false |  | 85 foot boom | false |  |  |  |  | ACM Insulation Subgirt Zee Trim | 29 | 7 | [24 empty] | 100 | 1 |  |  | 130 | 1 |  |  |  |  | 40 | 1
23009 | Yondr Allegro South | 2024-05-20 | Chad McCoy | 720 LF Zee, 117 panels, 20 bundles insulation, 40 LF J trim, 11 splice plates | Subcontractor | Colton Van Meter | true | The sign guys still haven’t installed there needed hardware for the sign. |  |  | Cloudy 85 | 3 | 14 | false |  | 85 foot boom | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee Trim | [22 empty] | 117 | 6 |  |  | 1280 | 4 |  |  | 720 | 4 |  |  |  |  | 40 | 1
23072 | Hubler Nissan | 2024-05-20 | David placzkowski | installed acm panels. had to take a grinder and grind down every reveal pocket due to the extrusion being to deep amd returns being to long | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8 | false |  | 6k lull and 60 ft boom lift | false |  |  |  |  | ACM | 20 | 16
23072 | Hubler Nissan | 2024-05-19 | David placzkowski | installed acm panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 7 | false |  | 60 ft boom. 6k lull | false |  |  |  |  | ACM | 20 | 14
23072 | Hubler Nissan | 2024-05-18 | David placzkowski | installed acm panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8.5 | false |  | 60 ft boom | false |  |  |  |  | ACM | 23 | 17
23072 | Hubler Nissan | 2024-05-17 | David placzkowski | waited on truck and started installing acm | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8 | true | truck of acm showed up at 11ish | 60 ft boom | false |  |  |  |  | ACM | 9 | 8
24013 | VA 14.2 | 2024-05-16 | Chad McCoy | 35 panels. 35 cuts. 100 feet of flashing Material moved to trailer for install. Area cleaned up. 5 panels and flashing removed for power solutions on south side gen yard | Subcontractor | Chris Buttrey | false |  |  |  |  | 4 | 8 | false |  |  | false |  |  |  |  | Corrugated / Screen wall Flashing | [22 empty] | 35 | 5 | [8 empty] | 100 | 1
23023 | Subaru LR | 2024-05-15 | David placzkowski | caulked panels and shadow stripping | Subcontractor | Colton Tomlin | false |  |  |  |  | 3 | 3 | false |  | 60 ft boom | false |  |  |  |  | Caulking | [20 empty] | 70 | 9
23023 | Subaru LR | 2024-05-14 | David placzkowski | installed blue shadow strip and cleat. installed acm panels. 1 remake panel as well. cut and routed 5 panels due to Effus being and inch lower than when measured | Subcontractor | Colton Tomlin | false |  |  |  |  | 3 | 8 | false |  | 60 ft boom | false |  |  |  |  | ACM Coping Other | 5 | 8 | [38 empty] | 80 | 8 | installed cleat and metal blue shadow stripping | 8
23023 | Subaru LR | 2024-05-13 | David placzkowski | installed coping and shadow strip | Subcontractor | Colton Tomlin | false |  |  |  |  | 3 | 8 | false |  | 60ft boom | false |  |  |  |  | Coping Other | [40 empty] | 60 | 8 | installed cleat, flashing and blue metal shadow strip. | 16
24013 | VA 14.2 | 2024-05-13 | Chad McCoy | 90 panels installed, 37 panels cut to fit. 75 leet of j. 75 feet of inside corner. 75 feet of outside corner 70 feet of caulking. | Subcontractor | Chris Buttrey | true | Door frames are not in. Scaffolding isn’t removed from north book end. There is a temporary electrical box that needs to be removed |  |  | Partly cloudy 81 | 5 | 10 | false |  | 19 foot scissor | false |  |  | 1.5 |  | Caulking Corrugated / Screen wall Flashing Layout | [20 empty] | 75 | 1.5 | 90 | 7 | [8 empty] | 225 | 1.5
23023 | Subaru LR | 2024-05-12 | David placzkowski | replaced remake panel and started shadow strip | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8 | false |  | 60 ft boom lift | false |  |  |  |  | Coping | [40 empty] | 30 | 10
23009 | Yondr Allegro South | 2024-05-10 | Chad McCoy | 19 panels, 27 sticks of J, 2 corner trims Concrete still has started being chipped. And pavement is starting Monday and Tuesday. | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 10 | false |  | 85 foot boom | false |  |  |  |  | Corrugated / Screen wall Trim | [22 empty] | 19 | 4 | [12 empty] | 300 | 4
24013 | VA 14.2 | 2024-05-10 | Chad McCoy | 25 corrugated panels were installed and 60 feet of flashing. We did as much as we could on the scissor lift. We are are awaiting the time on the 135. The electricians finished so we started installing those panels and as many rips and trim as we go down the wall | Subcontractor | Chris Buttrey | true | Door frames are not in. Wood blocking on south side isn’t removed for that install. |  |  | Raining 68 | 4 | 5.5 | true |  | 19 foot scissor | false |  |  |  |  | Corrugated / Screen wall Flashing | [22 empty] | 25 | 2 | [8 empty] | 60 | 1
23009 | Yondr Allegro South | 2024-05-09 | Chad McCoy | 30 panels 36 of of z. 1 bundle of insulation and 2 corners were installed today. Nothing has advanced with the concrete chipping nor the sign install. All the material has moved from the pavement areas to the dirt or sidewalks or lay down area. | Subcontractor | Colton Van Meter | false |  |  |  |  | 4 | 10 | true |  | 36 foot boom | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee Trim | [22 empty] | 30 | 4 |  |  | 110 | 1 |  |  | 36 | 1.5 |  |  |  |  | 20 | 0.5
24013 | VA 14.2 | 2024-05-09 | Chad McCoy | 40 panels installed. 35 cut to fit. The electrical started on the wrong side with his light lay out and install of conduit and pipes so they will have to finish today. The upper louver header corrugated on the prints calls for 13’ 2” but bc they opened it it’s now 13’5 1/4”. So these have to be cut out of 25 foot pieces of material. | Subcontractor | Chris Buttrey | false |  |  |  |  | 4 | 8 | false |  | Scissor lift | false |  |  | 1 |  | Corrugated / Screen wall Layout | [22 empty] | 40 | 6
23009 | Yondr Allegro South | 2024-05-08 | Chad McCoy | 60 panels 4 bundles of insulation and 72 of of z was installed. The concrete for the acm has not been chipped away. And nothing has been fixed. There is a large area of corrugated that has been left off for the sign studs to be installed but still no studs and on top of all this the pavement is happening soon so that will shut us down 2-3 days | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 8 | false |  | 85 foot boom | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 60 | 5 |  |  | 512 | 1.5 |  |  | 72 | 1.5
24013 | VA 14.2 | 2024-05-08 | Chad mccoy | 30 panels installed. 1.5 hr stand down and we left early so the electrician could start his boxes and conduit | Subcontractor | Chris Buttrey | true | Stand down |  |  | Cloudy and some rain | 4 | 7 | false |  |  | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 30 | 4.5
24013 | VA 14.2 | 2024-05-07 | Chad mccoy | We didn’t start installing till 945. We had to get stuff moved for booms. Load the trailer with panels and 2 guys had orientation. 68 panels. One cut for walk way install and 140 feet of trim. | Subcontractor | Chris Buttrey | true | Safety stand down for 45 minutes. 2 guys in orientation. Other trades material in our way. Scissor lift that was rented are wrong. They won’t fit in the walk path. |  |  | Partly cloudy 78 | 5 | 11 | false |  |  | false |  |  |  |  | Corrugated / Screen wall Flashing | [22 empty] | 68 | 6 | [8 empty] | 140 | 1.5
23009 | Yondr Allegro South | 2024-05-06 | Chad mccoy | 50 panels were installed and 50 feet of splice plates, the concrete for acm has not been chipped down and there was a 2 hr safety stand down that’s killing install | Subcontractor | Colton Van Meter | true | Safety stand down is pointless |  |  | Partly cloudy 73 | 4 | 10 | false |  | 85 foot boom 5k lull | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 50 | 6
23009 | Yondr Allegro South | 2024-05-01 | Chad McCoy | 48 panels, 5 J's, 8 bundles insulation | Subcontractor | Colton Van Meter | true | We are still awaiting j to install more corrugated and the acm areas are not fixed for install |  |  | Clear 86 | 4 | 8 | false |  | 85 foot boom | false |  |  |  |  | Corrugated / Screen wall Flashing Insulation | [22 empty] | 48 | 5 |  |  | 400 | 2 |  |  |  |  | 5 | 1
23009 | Yondr Allegro South | 2024-04-30 | Chad McCoy | 42 panels, 5 J's, 15 bundles insulation, 14 LF of Zee | Subcontractor | Colton Van Meter | true | We are still waiting on j metal to cap in the corrugated panels |  |  | 88 sunny | 4 | 8 | false |  | 85 foot boom | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 42 | 5 |  |  | 400 | 2 |  |  | 140 | 2
24013 | VA 14.2 | 2024-04-24 | Chad McCoy | 48 panels. These panels all had to be cut to fit a certain area. | Subcontractor | Chris Buttrey | false |  |  |  |  | 5 | 8 | false |  | Swing stage | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 48 | 6
24013 | VA 14.2 | 2024-04-24 | Chad McCoy | 35 panels cut down and installed. 50 feet of trim. | Subcontractor | Chris Buttrey | false |  |  |  |  | 5 | 8 | false |  | Swing stage | false |  |  |  |  | Corrugated / Screen wall Trim | [22 empty] | 35 | 6 | [12 empty] | 50 | 1
23009 | Yondr Allegro South | 2024-04-23 | Chad McCoy | 134 panels, 6 J's, 20 bundles insulation , 32 Zee's, 3 J's | Subcontractor | Colton Van Meter | true | We are out of j flashing |  |  | Windy clear | 2 | 10 | false |  | 85 foot boom | false |  |  |  |  | Corrugated / Screen wall Flashing Insulation Subgirt Zee | [22 empty] | 134 | 6 |  |  | 1350 | 3 |  |  | 32 | 1 | 30 | 1
24013 | VA 14.2 | 2024-04-23 | Chad McCoy | Trim was installed along the base of the north gen We trimmed and cut the drip flashing to go around the concrete steps for the fuel pumps. We then cut the panels and installed the bottom. We also replaced the panels that was took off for the electrical boxes and pipe. Two of the upper louver openings were adjusted after we installed the metal. So now nothing lines up. If the louver is installed the solid corrugated above the louver will we offset to the louver. | Subcontractor | Chris Buttrey | true | Foreman’s meeting. Which is pointless. And the scaffolding is still up that’s blocking the swing stage |  |  | Windy and clearc | 3 | 10 | true |  | Swingstage | false |  |  |  |  | Corrugated / Screen wall Flashing | [22 empty] | 40 | 6 | [8 empty] | 280 | 4
23006 | DLR Gold Sterling IAD54 | 2024-04-18 | Chad McCoy | We removed all the louvers that were cut and spliced in to fill the voids. And we replaced them with the new full length louvers. We cleaned out the red lift for pick up and we started the trim around the louver doors. But Marco asked us to wait till the architect approved the trim for the louver doors. | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 5 | false |  | 80 foot boom 60 foot boom | false |  |  |  |  | Louvre | [24 empty] | 30 | 3
23006 | DLR Gold Sterling IAD54 | 2024-04-16 | Chad McCoy | We cut and routed 11 panels for the coping. We installed these coping acm panels and caulked everything in. The coping tops had an additional 4 1/2 inch’s on the length bc system depth and z depth was added after we already gave the over all dimension. | Subcontractor | Colton Van Meter | true | Acm was drafted wrong and built wrong. |  |  | Clear 84 | 3 | 8 | false |  | 80 foot boom 60 foot boom | false |  |  |  |  | ACM | 11 | 8
23023 | Subaru LR | 2024-04-16 | David placzkowski | installed acm and did finishing caulking | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8.5 | false |  | 40ft boom. 6k lull | false |  |  |  |  | ACM | 10 | 8
23006 | DLR Gold Sterling IAD54 | 2024-04-15 | Chad McCoy | The sheer amount of material that is came to this job that is wrong, or needs to be modified is getting out of hand. The coping caps for the ACM were 4 inches too big on the top link that it’s stuck off the back of the wall so everything has to be cut a routed to fit the pair a pet cat so they can attach properly.. during conversations with Mcdougal and additional system depth plus the insulation depth was added to the overall dimension that I gave Colton for this additional work. And what this additional work has now turned into is additional work on top of additional work. | Subcontractor | Colton Van Meter | true | Cutting and railing. These panels is taking a little bit of time, especially the glue ups. Storms came through today and shut us down 4 to 5 times because of lightning. On top of everything else, the gutters I were installed on the ACM panels on the roof. We’re screwed in with Philip screws and some kind of clear sealant like they were not supposed to be done per conversations with Hitt. |  |  | Storms 83 | 3 | 8 | false |  | 85 foot boom 65 foot boom | false |  |  |  |  | ACM | 2 | 4
23009 | Yondr Allegro South | 2024-04-15 | Chad mccoy | 12 bundles of insulation and 43 panels. Storm came thru this after noon and lightning shut down outside work 3 times | Subcontractor | Colton Van Meter | true | Storms |  |  | Storms 83 | 2 | 8 | false |  | 85 foot boom. 5k lull | false |  |  |  |  | Corrugated / Screen wall Insulation | [22 empty] | 65 | 5 |  |  | 768 | 3
23023 | Subaru LR | 2024-04-15 | David placzkowski | installed acm and threw away crates | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 9 | false |  | 40ft boom. 6k lull | false |  |  |  |  | ACM | 40 | 18
23023 | Subaru LR | 2024-04-14 | David placzkowski | installed acm panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 6 | false |  | 40ft boom. 6k lull | false |  |  |  |  | ACM | 15 | 12
23006 | DLR Gold Sterling IAD54 | 2024-04-13 | Chad McCoy | We win in this morning and started getting everything ready for the guard shack. Patriot was on one side of the road and we were on the other. We both had our lane shut down and hit put out a message telling everybody not to drive through there due to work going on.. We pulled about 15 panels, and we laid them in our pathway between the fences, because there’s no other place to lay them. We could not stack them up due to the wind being so high that they were shaking, if not attempting to fall over. We pulled the reveals we needed to and the kick plates, but when I went to put the cake plates on, we found that the kick plates were white. so out of curiosity, I checked every other reveal that came with the crates and every other reveal was white. Every trim pieces were white there was two sections of trim that was not wait. It was blue so I cut that up to make reveals so that we could install for Panels. We installed a Z and insulation and we cut out two holes for outlets like we’ve done everywhere else we installed 15 petals and I think I have three reviews left that I can install. | Subcontractor | Colton Van Meter | true | We had wind gusts up to 50 miles an hour today so we had to be careful on panel placement and insulation that was free and could be blown around.. on the very last panel we were going to install it was laying where we had laid all the panels all day long in patriot the ones we had a conversation with that morning about stay the hell away from our side decided to drive down our side and they drove over the panel my guys watched it and then they try to find us and say oh that was a nice. A email was sent with pictures of the panel the people that did it and the tire tread Mark that |  |  |  | 5 | 8 | false |  | 80 foot boom 65 foot boom | false |  |  |  |  | ACM Insulation Subgirt Zee Trim | 15 | 5 | [24 empty] | 150 | 1 |  |  | 35 | 1 |  |  |  |  | 40 | 1
23023 | Subaru LR | 2024-04-13 | David placzkowski | installed acm paneling | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8.5 | false |  | 40 ft boom. 6k lull | false |  |  |  |  | ACM | 33 | 17
23023 | Subaru LR | 2024-04-12 | David placzkowski | installed acm panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 9.5 | false |  | 45ft boom. 6k lull | false |  |  |  |  | ACM | 26 | 19
24013 | VA 14.2 | 2024-04-12 | Chad mccoy | I had a 1.5 meeting this morning over louver and what is needed for there install. We cut back 8 sections on the upper part of the corrugated to make the louver opening match what was requested. We took down 8 sheets for the electricians to run their conduit for their lights. | Subcontractor | Chris Buttrey | true | We had to take Panels off for the electricians. We also had to cut back openings for the louvers due to improper description of louver openings and lay out. I had a meeting this morning that took forever took about an hour and a half. |  |  | Partly cloudy and windy | 3 | 8 | false |  | Swing stage | false |  |  |  |  | Corrugated / Screen wall Flashing | [22 empty] | 28 | 3 | [8 empty] | 40 | 1
23009 | Yondr Allegro South | 2024-04-11 | Chad McCoy | 80 Panels, 3 1/2 pallets of insulation and 34 sticks of Jay trim were installed today | Subcontractor | Colton Van Meter | false |  |  |  |  | 2 | 10 | false |  | 85 foot boom 5k lull | false |  |  |  |  | Corrugated / Screen wall Flashing Insulation | [22 empty] | 80 | 5 |  |  | 1500 | 4 |  |  |  |  | 320 | 2
23023 | Subaru LR | 2024-04-11 | David placzkowski | unloaded truck of 3 crates. received no clips. | Subcontractor | Colton Tomlin | true | we was delayed due to lack of waterproofing on building and lack of receiving clips |  |  |  | 2 | 2 | true | acm panels. | 45ft boom. 6k lull | false |  |  |  |  | Other | [42 empty] | just received truck only | 4
24013 | VA 14.2 | 2024-04-11 | Chad mccoy | 38 corrugated sheets installed. 15 cut to fit. | Subcontractor | Chris Buttrey | false |  |  |  |  | 2 | 7 | true |  | Swingstage | false |  |  | 1 |  | Corrugated / Screen wall Layout | [22 empty] | 38 | 6
23023 | Subaru LR | 2024-04-10 | David placzkowski | demo | Subcontractor | Colton Tomlin | true |  |  |  | 2 hr rain delay in morning | 2 | 6 | false |  | 45 ft boom. 6k lull | false |  |  |  |  | Other | [42 empty] | demolition of rest of existing panels on building | 12
24013 | VA 14.2 | 2024-04-10 | Chad McCoy | 45 corrugated sheets were installed. 8 pipe holes were cut. We skipped the generator small cuts so we can get to the damaged material for cuts and bc hitt said the top row of panels need to come down for electrical. LIKE I SAID A MONTH AGO | Subcontractor | Chris Buttrey | true | The electrical isn’t installed like on 13 and they say they can’t do it from the inside. |  |  | Partly cloudy | 3 | 10 | false |  | Swing stage | false |  |  | 1 |  | Corrugated / Screen wall Layout | [22 empty] | 45 | 6
23023 | Subaru LR | 2024-04-09 | David placzkowski | demo | Subcontractor | Colton Tomlin | true |  |  |  | 2 hrs in am for rain | 2 | 6 | false |  | 45ft boom lift | false |  |  |  |  | Other | [42 empty] | demolition of existing panels | 12
23009 | Yondr Allegro South | 2024-04-08 | Chad McCoy | Material was moved to the install lay down area to start the day. And insulation and j flashing and corrugated was installed to start multiple elevations. | Subcontractor | Colton Van Meter | false |  |  |  |  | 2 | 8 | false |  | 5klull 85 foot boom | false |  |  |  |  | Corrugated / Screen wall Flashing Insulation | [22 empty] | 35 | 3 |  |  | 384 | 2 |  |  |  |  | 180 | 2
23023 | Subaru LR | 2024-04-08 | David placzkowski | waited on lift | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 7 | false |  |  | false |  |  |  |  | Other | [42 empty] | waited on a lift all day but never arrived due to solar eclipse | 14
23006 | DLR Gold Sterling IAD54 | 2024-04-05 | Chad mccoy | Acm was continued on the main canopy and columns. 2 lights were cut out and one column was cut to fit. The columns were installed and lined up with the joints I put in the new soffit panels. The floating panel was installed on the precast. And we installed 200 feet of z on the visitors center. We had to move all equipment and crates away from the main building for codes inspection Monday thru Wednesday. | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 8 | false |  | 85 foot boom. 60 foot boom | false |  |  | 2 |  | ACM Layout Subgirt Zee | 19 | 6 | [28 empty] | 200 | 1.5
24013 | VA 14.2 | 2024-04-05 | Chad McCoy | 50 corrugated sheets were installed 3 pipe holes were cut out. 3 rip panels were cut for the inside door upper panels. And the elevation to the solid metal was established | Subcontractor | Chris Buttrey | true | Cold for framing is still missing in spots. Piping is not tested or inspected. Scaffolding was being taken down. |  |  | Partly cloudy | 2 | 8 | false |  | Swing stage | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 50 | 6
23006 | DLR Gold Sterling IAD54 | 2024-04-04 | Chad McCoy | The canopy soffit was continued. 2 panels were installed. Both panels needed to be cut for the light and altered for the precast. We also started setting the columns bottom panels. But during this install lightning was starting up and shutting us down for around a hr | Subcontractor | Colton Van Meter | true | The visitor center still has no windows or flashing or ceiling drywall or water proofing. No one was working on it |  |  | Storms windy and partly sunny at the end | 4 | 5 | false |  | 80 foot boom 60 foot boom | false |  |  | 1.5 |  | ACM Layout | 5 | 3
23009 | Yondr Allegro South | 2024-04-04 | Chad McCoy | Z and insulation pins were continued . We have almost completed all the z and push pins. I haven’t heard anything on the acm. So as of right now it’s still a no go. The push pins are caulked on and we are about to start running flashing and panels | Subcontractor | Colton Van Meter | false |  |  |  |  | 2 | 8 | false |  | 65 foot boom and a broken lull still | false |  |  |  |  | Subgirt Zee | [30 empty] | 400 | 5
24013 | VA 14.2 | 2024-04-04 | Chad McCoy | 40 corrugated sheets. We removed the swing stage basket from the walk way and secured it out side on sidewalk. Black piping is still going on. And this is holding up forming on those sections. The scaffolding is still sticking out of the gen yard structure. This is holding up framing. | Subcontractor | Chris Buttrey | true | Framing. Black pipe and inspections. Scaffolding is in the way of swing stage. Other trades are messing up finished panels in the walls |  |  | Partly sunny after the rain and 52 | 2 | 6 | false |  | Swing stage | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 40 | 4.5
23006 | DLR Gold Sterling IAD54 | 2024-04-03 | Chad McCoy | We are making the main entrance canopy panels and installing the rest of the perimeter fascia panels. It has stormed on us for2 days now. After we installed the big corner we started laying out for the new middle panels that will make a joint in the middle of the columns. We also have to cut for the columns and cut for the light lay out. With the lights we have one set that will be in the middle of a joint and with this the returns have to be cut off around 16 inches due to the light fixture laying flat with the acm. There is no way to install a reveal here and it will be open to seeing the fixture on both sides of the light hole. | Subcontractor | Colton Van Meter | true | The layout for the lights and the columns are takin a little while. I did lay out a panel wrong today and I requested a piece of acm to fix this |  |  | Storms and rain and 53 | 3 | 11 | true | Flashing arrived for the windows at the guard shack | 80 foot boom. 60 foot boom | false |  |  | 4 |  | ACM Layout | 9 | 4
23009 | Yondr Allegro South | 2024-03-26 | Chad McCoy | Z was continued today. Acm was stopped yesterday due to unfinished trades before us. So this morning we stole a third boom and 3 teams of 2 installed z on the walls. Stick pins and caulking on screw heads were also done today | Subcontractor | Colton Van Meter | false |  |  |  |  | 7 | 8 | false |  | 85 foot boom 5k lull | false |  |  |  |  | Subgirt Zee | [30 empty] | 1600 | 6
23009 | Yondr Allegro South | 2024-03-25 | Chad mccoy | One guy had orientation this morning. 4 guys installed z and push pins and caulking 3 guys layed out acm and installed acm. | Subcontractor | Colton Van Meter | true | ACM was started today, but due to improper foundation of other trades prior to us there is metal trim that’s messing around multiple elevations of the Acm install that needs to go on prior so Mike from Hitt it’s supposed to be getting an email sent out of us stopping on ATM install until |  |  | Clear 53 | 7 | 8 | false |  | 1 boom from Mcdougal 85 feet | false |  |  |  |  | ACM Caulking Subgirt Zee | 4 | 3 | [18 empty] | 150 | 1 | [8 empty] | 1150 | 5
23006 | DLR Gold Sterling IAD54 | 2024-03-20 | Chad mccoy | There was a lot going on today dominion is putting up their fence. Power solutions are doing a lot of work and genyard and everybody’s getting ready for the payment coming this week. we finished the last side of the GEN yard next to the electrical station. We were going to leave a section out until the 19th at 10 louvers came in but I had all the extra louvers from the left or the right hand side of the doors so instead of it looking in complete, we went ahead and install these fans to make the complete wall look finish. on the other side, we are also wrapping up the mirrored side of this wall with the very last section besides where the steel is moving we also in stalled the third door header section. We appreciate everything because they’re prepping the payment tomorrow for the upper elevation of the louvers next to the ACM on the roof. | Subcontractor | Colton Van Meter | false |  |  |  |  | 7 | 9 | false |  | 80 foot boom 60 foot boom | false |  |  |  |  | Louvre | [24 empty] | 90 | 5
23006 | DLR Gold Sterling IAD54 | 2024-03-19 | Chad mccoy | Louvers were continued. I had a formans meeting that was pointless. We are finishing up on the gen yard. 2 guys started the header install and 2 guys went to the roof to button up sc1 install with cross members and bolts. 2 other guys finished the corner fins on the gen yard. This section had to be reworked do to the steel placement and how out of level this area was. We also had to pre stage lifts and trailers to block off where we will be working in the morning due to the abundance of vehicles parking around the gen yard louvers. We had to move all of our insulation and crates of panels so concrete could be filled into the perimeter fence post holes. | Subcontractor | Colton Van Meter | true | The fence at the end of the genyard closest to SC1 had to be cut down because they stuck, pass the steel they also had to be cut down in the door section because they stuck into the door section |  |  | 48 sunny | 7 | 8 | true |  | 80 foot boom 60 foot boom | false |  |  |  |  | Louvre | [24 empty] | 150 | 6
23006 | DLR Gold Sterling IAD54 | 2024-03-18 | Chad McCoy | We are still trying to button up all the ins and outs of the gen yard louvers. We had two crews on it today. we should be pretty close to completed on these louvers by the end of the day Wednesday that includes the headers and all the little miscellaneous stuff inside they put the steel in on the left-hand side of the big wall so we framed it out and crossed my bird with bolts and everything today. we also had to 56 louvers today due to louvers either extending past the end of the steel or extending into the door where the door frames are going to be | Subcontractor | Colton Van Meter | true | They are working on the lights on the canopy and the entryway to the building but it is still taking forever. They cut the drywall out and they’re reframing the lights up and they’re moving them inward. |  |  | Sunny 48 | 5 | 8 | false |  | 80 foot boom 60 foot boom | false |  |  |  |  | Louvre | [24 empty] | 61 | 3
24013 | VA 14.2 | 2024-03-18 | Chad McCoy | This daily is for delays only. This morning upon arrival, no framing was done in a complete section where we could run a decent amount of Panels. I could only run 38 Panels in the section that was somewhat completed. The swing stateside was red roped off due to manholes being open and cables being pulled of links of 250 feet drawn out across the ground. All of the sub framers were on the north side of the building instead of being in two different spots and having one group finishing the book in by the turn spindles at the south side of the building. So at this time I had talked to Tony B and I told him that we would be back around 2 o’clock to set up and do these 38 panels. so when we returned at 2 o’clock they were still working on the small section on the southside so we decided to start gathering all the material that we needed for that wall and we were gonna put it on the lull in stack order, so we can offload it and put it directly on the wall. in the middle of this I got a phone call from Alex talking about installation and speed. After that conversation we continued to load the forks shortly after I got a phone call from Mcdougal saying to leave and not come back until 25th of March so we did not stage any material because I did not want it damaged we tied everything down I took pictures and | Subcontractor | Chris Buttrey | true | The framing is taking forever the black pipes it supposed to be coming through the walls. It goes to the fuel pump. Assemblies are not completed two out of 10 are sticking out where Panels can go on the wall. The framing guys are only working till 2 o’clock and then they stop working. |  |  | Sunny 48 | 2 | 5 | false |  | 2 80 foot booms | false |  |  |  |  | Corrugated / Screen wall | 0 | 0
23006 | DLR Gold Sterling IAD54 | 2024-03-16 | Chad McCoy | We are filling in the trash shoot today. And filling in cross members and bolts. 150 crossmembers 40 L brackets were installed and 20 verticals. And then 150 fins. 1 team went around the bottom of the gen yard filling in bolts and screws. | Subcontractor | Colton Van Meter | true | The last section on sc2 louvers had to have 14 inches cut off. Bc they are impacting into the precast wall. |  |  | Clear 70 | 4 | 10 | false |  | 80 foot boom and 60 foot boom. | false |  |  |  |  | Louvre | [24 empty] | 120 | 2.5
24013 | VA 14.2 | 2024-03-15 | Chad McCoy | 57 panels installed. 38 cut to size | Subcontractor | Chris Buttrey | true | We had to wait for the stairs to be closed to start that install, no framing was done today and none will be done Saturday |  |  | Clear sunny | 2 | 9 | false |  | 2 80 foot boom from hitt | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 57 | 7
24013 | VA 14.2 | 2024-03-14 | Chad McCoy | Layout was continued. 30 sheets of corrugated installed. | Subcontractor | Chris Buttrey | true | Perforated metal in bundles are 2 different colors and not all are 25 feet. Some are 4 inches short in the middle of the stack. |  |  | Sunny and hot all day | 2 | 9 | false |  | This daily doesn’t explain the day Colton | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 30 | 7
23006 | DLR Gold Sterling IAD54 | 2024-03-12 | Chad McCoy | I had a formans meeting today. In this meeting I got no answers on acm for visitors center and canopy light penetrations. The roof steel is being installed today where the 3 feet of steel is missing and I was told the header metal was going into. I cut down 45 louvers bc they are sticking over the 45 degree angle 9 inches. We also had to install individual fins to line up the elevations from side to side. | Subcontractor | Colton Van Meter | true | Cutting louvers again. And foreman’s meeting |  |  | Clear and 76 | 4 | 11 | false |  | 80 foot boom. 60 foot boom | false |  |  |  |  | Louvre | [24 empty] | 7 | 9
24013 | VA 14.2 | 2024-03-12 | Chad mccoy | Inventory was completed today. I also met with the scaffolding guy and showed him where a swing stage would be needed for this install of corrugated. We walked the area the guys that was doing the framing in this area had a boom with the knuckle running into vantage 13 corrugated | Subcontractor | Chris Buttrey | false |  |  |  |  | 1 | 0.5 | false |  | Nothing | false |  |  | 0.5 |  | Layout
23006 | DLR Gold Sterling IAD54 | 2024-03-11 | Chad McCoy | We continued the louver layout on the verticals and the brackets. We are still running into out of plum steel and out of level steel that is causing havoc on the fins and verticals. We have to line up with the fins on the long wall but the steel is so far out of level that the bottom of the verticals is 1 1/2 half off the steel and the top is slammed. We also are making trips back and forth to the lay down area at rhe airport so we can get all the material to the site on my trailers. We made three trips today | Subcontractor | Colton Van Meter | true | None of the header steel is installed. The missing stell on the roof is also not installed. And there has been no progression on the lights for the visitors center and canopy. |  |  | Cloudy. Super windy. And 48 | 4 | 8 | true | I delivered 3 trailer loads from lay down area | 60 foot boom. 80 foot boom | false |  |  | . |  | Layout
24013 | VA 14.2 | 2024-03-11 | Chad McCoy | Today we had orientation and badging. I also had to get a badge from vantage 11 so I could come and go thru the gates. Upon arrival, we noticed that the framing had barely been touched in all sections. None of the other penetrations for piping up the generators have been finished, and they pulled the crates down: do they didn’t finish the stacks. When I talk to Tony B he told me that he didn’t even realize that that I needed booms when he was in the walk with Alex and everybody for the pre-game installation plan | Subcontractor | Chris Buttrey | true | No equipment. And mention and badging took for ever |  |  | Clear and 48 | 4 | 2 | false |  | Nothing | false |  |  | 0.5 |  | Layout
23006 | DLR Gold Sterling IAD54 | 2024-03-07 | Chad McCoy | 50 cross braces, 20 brackets screwed off, 10 brackets bolted, 80 LF caulking, peeled panels on long wall. | Subcontractor | Colton Van Meter | true | Concrete was being poured where we have to install louvers. So we had to button up other things to do |  |  | Partly cloudy 55 | 2 | 10 | false |  | 60 and 80 feet booms | false |  |  |  |  | Caulking | [20 empty] | 80 | 1.5
22071 | GCDC Building 1 | 2024-03-04 | Oscar Hernandez | General clean up on the roof and moving material | Subcontractor | Colton Tomlin | false |  |  |  |  | 4 | 8 | false |  |  | false |  |  |  |  | ACM |  | 32
23006 | DLR Gold Sterling IAD54 | 2024-03-04 | Chad mccoy | We started our day continuing on the louvers. The blue boom is acting up but we are trying to use our two and hits 125. We had to install 14 more verticals today and 126 crossmembers and 12 L brackets. Hitt is also trying to fill the gens with def fluid and for about 45 minutes today we had to move out of the way for the 18 wheeler. But once we got all of our pierces installed we started installing fins. We installed 215 fins. At the end of the day I had a short phone call with Colton over the acm areas we installed. And we strapped some panels and we left | Subcontractor | Colton Van Meter | true | Def truck for about 45 minutes caused a delay |  |  | Partly cloudy 62 | 5 | 10 | false |  | Crappy 60 foot boom, 80 foot boom | false |  |  |  |  | Louvre | [24 empty] | 210 | 4
23006 | DLR Gold Sterling IAD54 | 2024-03-03 | Chad mccoy | We started this morning taken down all the lower panels on the eyebrow and making the first corner panel move over the amount needed to make the panels work across the front of the lower eye brow. By doing this we are where we need to be for every panel to work left to right like it should. Kevin and I finished installing the upper panels and then when to the lower column wrap. Once Kevin and I was down we took the lull with the trash dumpster on it and went around cleaning up and organizing all of our areas of work. We set up for the louvers and we moved all material for louvers to its area of install that was on site .. | Subcontractor | Colton Van Meter | true | The bust in the lower eye brow panels.took some time to fix but we fixed it and installed to the point where Hitt is holding us up on installation due to drywall and lights |  |  | Partly cloudy and 60s | 5 | 9 | false |  | 80 foot boom and 60 foot boom | false |  |  |  |  | ACM | 21 | 9
23061 | Baldwin Subaru | 2024-03-03 | David placzkowski | Installed shadow. caulked doors and column | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8 | false |  | 46 ft boom. 5k lull | false |  |  |  |  | Caulking Other | [20 empty] | 70 | 5 | [20 empty] | shadow strip | 8
23006 | DLR Gold Sterling IAD54 | 2024-03-02 | Chad mccoy | The acm arrived the other day for the front eyebrow and canopy. So we are starting on that today. Two teams. One doing the upper eyebrow column and wrap and the other doing the lower canopy. Kevin and I laid out our upper canopy column and then we started installing from the lower canopy roof up. Upon turning the corner there is a big hole above the curtain wall. Where our details tell us there will be a reveal. But the reveals fall out. The other team started installing from the furthest corner inward due to the acm needing to be installed from the 10x10 corner to the left. But the drywall and the lights are not finished so the extrusions are swapped and these panels are reversed installed. On this run of panels we only line up with one window mullion. But when we got to this area with the eye brow panels the eye brow panel was 1 3/4 “ off of the mullion. So I called Colton and then we cleaned up and called it a day | Subcontractor | Colton Van Meter | true | Panels are not lining up with where we need them on mullions |  |  | Raining cold and 42 | 5 | 9 | false |  | 1 80 foot boom, 1 60 foot boom | false |  |  |  |  | ACM | 14 | 9
23061 | Baldwin Subaru | 2024-03-02 | David Placzkowski | installed acm panel, peeled poly off panels, started install on shadow strip | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 7.5 | false |  | 46ft boom, 5k lull | false |  |  |  |  | ACM | 8 | 4
22071 | GCDC Building 1 | 2024-03-01 | Oscar Hernandez | General clean up on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 4 | 8 | false |  |  | false |  |  |  |  | ACM |  | 32
22071 | GCDC Building 1 | 2024-02-29 | Oscar Hernandez | Installing panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 4 | 8 | false |  |  | false |  |  |  |  | ACM |  | 32
23006 | DLR Gold Sterling IAD54 | 2024-02-29 | CHad mccoy | We started this morning getting everything ready two of us went to the crates that were dropped off yesterday and tried to find the prints that Tony said was in Crete number 4. We found the prince, and then we went back to the louvers. One team was hanging verticals one of the other team installed L brackets. 70 L brackets were installed today. 35 verticals. 60 crossmembers. 140 bolts assembly’s. 60 fins and about an 3 hrs worth of lay out | Subcontractor | Colton Van Meter | false |  |  |  |  | 4 | 10 | false |  | 80 foot boom. 60 foot boom | false |  |  | 3 |  | Layout
23061 | Baldwin Subaru | 2024-02-29 | David placzkowski | installed panels. peeled poly off panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8.5 | false |  | 46ft boom lift. 5k lull | false |  |  |  |  | ACM | 30 | 14
22071 | GCDC Building 1 | 2024-02-28 | Oscar Hernandez | Installing panels on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 4 | 8 | false |  |  | false |  |  |  |  | ACM |  | 32
23061 | Baldwin Subaru | 2024-02-28 | David placzkowski | installed acm panels. cut and routed 10 panels. peeled poly off panels as well | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8 | false |  | 46ft boom. 5k lull | false |  |  |  |  | ACM | 12 | 10
22071 | GCDC Building 1 | 2024-02-27 | Oscar Hernandez | On the roof Installing panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 4 | 8 | false |  |  | false |  |  |  |  | ACM |  | 32
23006 | DLR Gold Sterling IAD54 | 2024-02-27 | Chad McCoy | We started our morning getting the second trailer into the job site. I brought my 24 foot trailer bc I needed a place to store a lot of louver fins and that way it’s mobile. I had a foreman’s meeting that lasted almost a hr today and the guys went to the roof to finish the acm. The acm was finished on the roof on both walls today. After everything was installed clean up started and tomorrow afternoon we will get everything down. There is no need to leave any scaffolding on the roof so it will be coming down. Tomorrow we will all be on louvers. The other boom arrived today and I spent all the time I could today installing L brackets and doing lay out so I can stay ahead of the guys. I had to go around and get any boxes of material laying around so I could store them on the smaller trailer so it’s mobile. I also picked up all the louver parts at hurts office and the screws. At the end of the day we all went to the lay down yard to load the trailer and then we took it back to the job to place it for tomorrow install | Subcontractor | Colton Van Meter | true | Foreman’s meeting and I had to go talk to hitt about framing on 2 columns that is going to impact into the window and into one of there can lights. No steel install where it’s missing has been done. |  |  | 55 partly cloudy | 4 | 10 | false |  | 80 foot boom and 60 foot boom | false |  |  |  |  | ACM Caulking Insulation Subgirt Zee | 11 | 6 | [18 empty] | 100 | 1.5 |  |  |  |  | 320 | 1.5 |  |  | 80 | 2
23061 | Baldwin Subaru | 2024-02-27 | David placzkowski | installed acm | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 6.5 | false |  | 46 ft boom. 5k lull | false |  |  |  |  | ACM | 12 | 13
22071 | GCDC Building 1 | 2024-02-26 | Oscar Hernandez | Installing panels south East on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 4 | 8 | false |  |  | false |  |  |  |  | ACM |  | 32
23061 | Baldwin Subaru | 2024-02-26 | David placzkowski | installer acm panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8 | false |  | 46 ft boom. 5k lull | false |  |  |  |  | ACM | 34 | 16
23061 | Baldwin Subaru | 2024-02-25 | David placzkowski | installed acm panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 7 | false |  | 45ft boom. 5k lull | false |  |  |  |  | ACM | 34 | 14
23061 | Baldwin Subaru | 2024-02-24 | David placzkowski | installed acm panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 4 | false |  | 45 ft boom and 5k lull | false |  |  |  |  | ACM | 22 | 8
22071 | GCDC Building 1 | 2024-02-23 | Oscar Hernandez | Installing brackets and mullion and carrying material to the roof , punch list on screen wall | Subcontractor | Colton Tomlin | false |  |  |  |  | 4 | 8 | false |  |  | false |  |  |  |  | ACM |  | 32
23061 | Baldwin Subaru | 2024-02-23 | David placzkowski | installed acm panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8.5 | false |  | 45 ft boom | false |  |  |  |  | ACM | 30 | 17
22071 | GCDC Building 1 | 2024-02-22 | Oscar Hernandez | Installing mullion and panel on the roof (east) | Subcontractor | Colton Tomlin | false |  |  |  |  | 4 | 8 | false |  |  | false |  |  |  |  | ACM |  | 32
23006 | DLR Gold Sterling IAD54 | 2024-02-22 | Chad McCoy | We used a boom to set the corner acm and then the roof crew continued installing panels while the louver crew did layout and installed brackets on the louvers. | Subcontractor | Colton Van Meter | false |  |  |  |  | 6 | 10 | true |  | 80 foot boom | false |  |  |  |  | ACM Insulation | 7 | 5 | [24 empty] | 200 | 1
23061 | Baldwin Subaru | 2024-02-22 | David placzkowski | installed acm panels. Cut and routed 1 panel | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8.5 | false |  | 45ft boom | false |  |  |  |  | ACM | 39 | 17
22071 | GCDC Building 1 | 2024-02-21 | Oscar Hernandez | Installing brackets and mullion on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 4 | 8 | false |  |  | false |  |  |  |  | ACM |  | 32
23006 | DLR Gold Sterling IAD54 | 2024-02-21 | Chad McCoy | We started our morning with everybody doing acm. I had to be in a boom installing the corner panels that hang over a ledge. We had two guys on scaffolding and 1 on the roof. The other team was on the small wall fixing what Carlos guys installed out of level and out of plum. After I helped install two panels out of the boom I moved everything back to the front of the gen yard louver sand I continued installed the louvers. Cat is setting up 5 generators for the load test. And they started fueling the generators today. They are using 18 wheeler tankers for this. So it takes a lot of space. The guys on the roof stopped on the tall wall and went and installed a lot of panels on the small wall so we could set up another trade for penetrations. Once these certain panels were complete. Everybody went back to the tall wall. I cut down louver like Colton and I discussed and we installed them. But upon talking to him I have to take 8 louvers off in the am and cut them the same as the lower ones and install the new louvers that are coming Monday. | Subcontractor | Colton Van Meter | false |  |  |  |  | 7 | 10 | false |  | 80 foot boom | false |  |  |  |  | ACM Insulation Louvre Subgirt Zee Trim | 13 | 3 | [22 empty] | 58 | 2 | 320 | 2 |  |  | 100 | 2 |  |  |  |  | 20 | 1.5
23061 | Baldwin Subaru | 2024-02-21 | David placzkowski | installed acm panels. cut and routed 2 panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8 | false |  | 45 boom | false |  |  |  |  | ACM | 40 | 16
22071 | GCDC Building 1 | 2024-02-20 | Oscar Hernandez | Carrying panels to the roof and installing mullions on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 4 | 8 | false |  |  | false |  |  |  |  | ACM |  | 32
23006 | DLR Gold Sterling IAD54 | 2024-02-20 | Chad McCoy | We started our day getting the teams ready for the acm install on the roof. Carlos guys showed up late today. I had my guys on the tall acm wall and the second team on the smaller wall. I went up and showed them how I wanted everything after the foreman’s meeting. They had started but it was wrong. I corrected what they had done and showed the process and then I headed to the louver install. I have to get a certain distance on the louvers each day to meet the requirements for the fuel trucks and the generator load banks. At the end of the day. The team on the high wall installed 6 panels and 80 feet of z and 300 sqft of insulation. The other team installed 11 panels and 90 z and 250 sqft of insulation. I installed 75 louver fins and 30 crossmemebers. | Subcontractor | Colton Van Meter | true | Foreman’s meeting |  |  | Clear 43 | 10 | 10 | false |  | 80 foot boom | false |  |  | 2 |  | ACM Insulation Layout Louvre Subgirt Zee Trim | 17 | 4 | [22 empty] | 75 | 5 | 550 | 2 |  |  | 170 | 2 |  |  |  |  | 40 | 2
23061 | Baldwin Subaru | 2024-02-20 | David placzkowski | Installed acm panel. cut and routed 4 panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 9 | false |  | 45ft boom | false |  |  |  |  | ACM | 20 | 18
23006 | DLR Gold Sterling IAD54 | 2024-02-19 | Chad mccoy | We started our morning meeting everybody at the gas station next to the hotel. This way the guys from IAD 53 could follow us to our job site. Once we got to the job site, I showed them where to park and I took everybody that needed orientation to the Hitt office. Once everybody was orientated, I then split everybody up and where they were going to be working. One crew was on ACM one crew was on prep and clean up on louvers on the roof. Two crews were on louvers on the Genyard Matt and I got the law from Hitt with the trash container and we filled it with insulation Z and strapping for the roof and we got that to the roof for the guys. I also had one crew bring in every other panel that was on the ground to the roof. So now every ACM panel is on the roof ready for install .Kevin and them had to do some rework around the double doors on some panels to make them lineup. Nice and neat from left to right and equal to where it should be at the door elevation.. 78 crossmembers were installed on the roof and 65 were installed on the generator yard on the generator yard. We also installed 88 louver fans. We also continued filling in bolts and screws so that we could get to the first opening tomorrow. | Subcontractor | Colton Van Meter | true | Orentation, Flying material up. |  |  | Clear 47 | 10 | 10 | false |  | 80 foot boom | false |  |  | 2 |  | ACM Layout Louvre | 3 | 3 | [22 empty] | 88 | 2
23061 | Baldwin Subaru | 2024-02-19 | David placzkowski | installed acm panels. also had to cut and routed A15 and A19 | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8 | false |  | 45ft boom | false |  |  |  |  | ACM | 14 | 16
23061 | Baldwin Subaru | 2024-02-18 | David placzkowski | installed acm panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8.5 | false |  | 45 ft boom | false |  |  |  |  | ACM | 17 | 17
23061 | Baldwin Subaru | 2024-02-17 | David placzkowski | installed acm panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8 | false |  | 45ft boom | false |  |  |  |  | ACM | 13 | 16
23006 | DLR Gold Sterling IAD54 | 2024-02-16 | Chad McCoy | Panels on the roof were continued. 7 panels, 70 LF zee, 5 bundles insulation, 4 cut outs for electrical boxes, 20 LF caulk, and peeled panels lovers were continued and ran to the first big opening. | Subcontractor | Colton Van Meter | false |  |  |  |  | 6 | 10 | true |  | 80 foot boom | false |  |  |  |  | ACM Insulation Louvre Subgirt Zee | 7 | 3 | [22 empty] | 135 | 2 | 320 | 2 |  |  | 70 | 1.5
23006 | DLR Gold Sterling IAD54 | 2024-02-16 | Chad mccoy | I continued this morning installing verticals. And splice verticals. After I installed all the verticals left I started laying out the rest of the long side of the gen yard. I ran string lines so all the brackets will be in line. The steel goes in and out. I had to go to the visitor center for dementions a couple of times today. For the end of my day I built L brackets The peel and stick has to be cut to size and stuck to the bottom of these brackets. Each on gets this. | Subcontractor | Colton Van Meter | false |  |  |  |  | 1 | 11 | false |  | 80 foot boom | false |  |  | 7 |  | Layout
23061 | Baldwin Subaru | 2024-02-16 | David placzkowski | received truck of 7 crates and started installing panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8 | true | 7 crates of panels and shadow strip | 45ft boom | false |  |  |  |  | ACM | 6 | 16
23061 | Baldwin Subaru | 2024-02-15 | David placzkowski | waited on truck that didn't show and did layout | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 4 | false |  | 45ft boom | false |  |  |  |  | Other | [42 empty] | just did layout because we didn't get a truck. | 8
23006 | DLR Gold Sterling IAD54 | 2024-02-14 | Chad mccoy | Today I continued installing verticals. I installed 50 verticals today which is tricky with one person to make this happen. I had to run multiple string lines so I didn’t have to use the level on the very first one that starts the elevation. Once I got up all the verticals that I could, I went back and I started installing bolts on as many of them as I could until I ran out of bolts that were premade after that I had to install for fence on the right hand side of the street wall that lined up with the curve in the louvers and what I had to do was match the points to each other going up the vertical and what is gives me is a nice, clean, looking joint where I do not have to compensate or just as I go up with the rest of the louvers. Around 130 I went to Premier neck store and I met with Sam and we went over the water leak and the shutters in the back. I took pictures and also talked to Colton and Drake about this. The fuel trucks are going to start filling up the generators tomorrow and there’s going to be two fuel trucks per day For the next three days | Subcontractor | Colton Van Meter | true | I would count having to go to the other job as a delay for or towards my job that I’m on |  |  | Partly cloudy and 42 | 1 | 12 | false |  | 80 foot boom | false |  |  |  |  | Louvre | [24 empty] | 1 | 12
23006 | DLR Gold Sterling IAD54 | 2024-02-12 | Chad mccoy | I started my morning string lining from where we left off with fins all the way down to the first steel that was removed. I put a string on on every horizontal steel beam and what this does is it gives me the ins and outs of all the brackets that way I do not have to hold a level by myself.. Installed 165L brackets and laid everything out. I also started installing verticals. Once all the brackets were done I got 22 verticals installed and then it started storming and pouring down rain. | Subcontractor | Colton Van Meter | true | My guys did not return when they were supposed to so this is delaying me, but I just means I have to work harder |  |  | Cloudy rain in pm | 1 | 12 | false |  | 80 foot boom | false |  |  |  |  | Louvre | [24 empty] | 1 | 12
23006 | DLR Gold Sterling IAD54 | 2024-02-09 | Chad McCoy | We got to the site this morning and we started getting ready to install the fins on the verticals. So we had two sections that was ready but a couple of the spice plates needed crossmembers so those had to be cut and then we could the fins. Once that section was complete, we started prepping the top section of verticals for install. These have to be saving a quarter inch off the next section and then plum to the section below it. In the middle of reinstall, we noticed that we were missing some bundles of 19 foot 10 louver fins. So we had to pack up unload the trailer so that we could go to the yard and get six more bundles so that we can finish the sections we were working on. what’s the sections we were working on were completed we set everything up for the next day. We cleaned up our area and we put fuel in our boom. There is a lot of work that goes in to prepping the areas for louver install first you have to lay out where you think the fins are gonna lineup.. this is difficult in areas due to the steel being off kilter with the concrete points and even if you go to a later point where you think is right, the Steal is either wrong or your start points are wider than supposed to be. so to make everything fit just on the layout you have to pick a corner you have to pick a spot where you want them to go and then see where it goes left and right. Once that meets standards when you lay out each individual section of brackets, because each Finn is different, and nothing is the same unless that size of louver is repeated in your system. Once you get your first and second brackets where they need to go, you can string line for a good distance and then with that gives you is a nice level line from one point to the other on the steel to push brackets to to make your install a lot easier on the beginning. Then you level straight up and down from that point of your layout to each other bracket steel and then you can continue with installation on levels 1,2,3 &4. What’s your vertical is the one you have to drill every hole. we are coming across sections of the steel that at some point serve an inch and a half stick in the middle of the beam. It makes no sense. So you’re talking about six holes drilled per bracket on one set of verticals you have eight brackets. So I’m one set of verticals with eight brackets you have 48 holes you have to drill. Once you put your verticals up in each vertical, you have four more additional holes, you have to drill per vertical. Then you have to put your crossmembers on which is for more additional holes connect each vertical to each other. And then when everything is bolted and screwed off, then you can put your fins on. | Subcontractor | Colton Van Meter | false |  |  |  |  | 2 | 10 | false |  | 80 foot boom | false |  |  |  |  | Louvre | [24 empty] | 90 | 3
21062 | BNA MNAA Garage B | 2024-02-08 | Zarur Nazario Padron Jr | Working on ACM and caulking the rest of screw holes | Subcontractor | Marc Ribar | [5 empty] | 9 | 90 |  |  | 2-scissor lifts | [5 empty] | ACM Other | 15 | 60 | [40 empty] | Caulking screw holes that have been left over | 30
23006 | DLR Gold Sterling IAD54 | 2024-02-08 | Chad McCoy | We started installing fins this morning. The smaller sections 1 boom can do but the 19’10” takes two booms. We hung every where the spots were complete. We could not go all the way up in sections due to not having the splice plates for that section. We will go to the yard in the am and get it. We also filled in screws and X cross members to prepare other areas for install. | Subcontractor | Colton Van Meter | false |  |  |  |  | 2 | 11.5 | false |  | 80 foot boom | false |  |  |  |  | Louvre | [24 empty] | 195 | 4
23006 | DLR Gold Sterling IAD54 | 2024-02-07 | Chad mccoy | Today we just continued installing and finishing sections on the louvers. The louver section is all about the verticals. You’ve got to do the L brackets, the crossmembers and the vertical themselves. One complete section of verticals Includes 6L brackets, 34 screws in those brackets alone. 6X crossmembers. 12 bolt assemblies three vertical louver brackets.. and depending on the location, it could need a modified L bracket, which means it needs to be cut to go round steel or I-beams. And so far we have done this 148 times.. but once the assembly process is put together from the L brackets to the verticals to the crossmembers, the fins can be installed to make up a lot of time. At the end of the day we went through all the fins that we had and we separated up into sections to be installed on the wall so directly under wear those fins go, we put the entire pile of those fins that way we don’t have to walk back-and-forth they’re already placed. I also included two pictures of steel that’s being left out for access to garage doors in the building. These louvers in these areas will not be able to be installed and from what I heard today it’ll be a year. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 11 | false |  | 80 foot boom | false |  |  |  |  | Louvre | [24 empty] | 1 | 8
21062 | BNA MNAA Garage B | 2024-02-06 | Zarur Nazario Padron Jr | Working on finishing up ACM and caulking screw holes | Subcontractor | Marc Ribar | [5 empty] | 9 | 90 |  |  | 2 scissor lifts and 1-85ft boomlift | [5 empty] | ACM Other | 8 | 50 | [40 empty] | Caulking screw holes | 40
23040 | DRG Spring Hill | 2024-02-06 | Saul chicas | We start installing single sling on building 3 and also caulking building 1 | Subcontractor | Nick Akins | [5 empty] | 6 | 10 | true | ACM | Boom lift | [5 empty] | Single Skin | [6 empty] | 60 | 10
21062 | BNA MNAA Garage B | 2024-02-05 | Zarur Nazario Padron Jr | Working on finishing up on Canopy Level 5 | Subcontractor | Marc Ribar | [5 empty] | 8 | 80 |  |  | 2 scissor lifts | [5 empty] | ACM Other | 4 | 30 | [40 empty] | Caulking on top of canopy all of the cracks where it wasn't caulked | 50
23006 | DLR Gold Sterling IAD54 | 2024-02-05 | Chad mccoy | Oh, I had one guy that had to go through orientation this morning. So while we had him go to orientation, we went to where we are working and we started getting everything ready and laid everything out for install for today.. I continued laying out the verticals in the fins so that we could try our best lineup with either the steel or the concrete or somewhere in between, where it would look the best. we do have so far one section of louvers that to be cut due to the leaks, but all of the angles so far have worked out. When we started our install of our louvers, we started one edge off of the first section of concrete. The gaps between the bottom leave her in the concrete is very from a half an inch to 2 inch is due to the ups and downs of the concrete build prior to steel install. When we did our overall height of the steel we found that it’s roughly 24‘,1“ and then spots it goes to 24‘1“ and a quarter. So giving this our louvers are 2 3/8 shy of reaching the top of steel. If I move everything up to get top steel, we will be 4 inches or better off of concrete in certain places. We have installed 240 L brackets, 55 verticals, eight Fins. And probably five hours of layout. So on my way out what I’m doing is the second steel beam up we are setting the first and second L bracket 4 1/2 inches out and then we are string lighting from these two brackets from either angle to angle on the steel or end of steel to first angle.. then we are installing all the bottom row of brackets. After the first row of brackets are on, we’re installing all the verticals except for splice plates. What is gives me is the opportunity to install the fins and take them out without messing up the spice plates. It also allows me to use the verticals as my lay out so that I can line up with either concrete or steel or figure out what looks best on the wall. This also helps us with our ins and outs of the verticals. We are coming across some verticals that are built in properly and by built in properly. I mean they are not built the exact same as their sisters or brothers to the left or the right of them. on these build outs of these verticals, we have have found that the pre-installed angle that holds the fins on sometimes is at a quarter or 3/8 off of their original build. Once the layout is complete, and the L brackets and the verticals are installed it’s a wrap all you have to do is put the bolts in and the crossmembers in the back and the fins go on faster than anything else. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | 80 foot boom | false |  |  | 5 |  | Layout Louvre | [24 empty] | 1 | 9
23040 | DRG Spring Hill | 2024-02-05 | Saul chicas | Today we start working on building 3 installing hat Chanel and also unloading a truck with ACM panel | Subcontractor | Nick Akins | [5 empty] | 6 | 10 | true | ACM | Boom lift | [5 empty] | Caulking Hat Channel | [20 empty] | 100 | 10 | [12 empty] | 400 | 10
21062 | BNA MNAA Garage B | 2024-02-03 | Zarur Nazario Padron Jr | Caulking panels on top of Level 5 Canopy and finishing up the ceiling panels | Subcontractor | Marc Ribar | [5 empty] | 10 | 100 |  |  | 2-scissor lifts and 1-85ft boomlift | [5 empty] | ACM Other | 2 | 30 | [40 empty] | Caulking panels on top of Level 5 Canopy and finishing up on (22)ceiling panels | 70
21062 | BNA MNAA Garage B | 2024-02-02 | Zarur Nazario Padron Jr | Working on Garage B level 5 bridge and Canopy | Subcontractor | Marc Ribar | true | Painters that were painting the columns between the bridge and the canopy on level 5 delayed us for 3 days |  |  | Sunny/cloudy | 9 | 90 |  |  | 1-85ft boomlift and 2-scissor lifts | [5 empty] | ACM Other | 7 | 40 | [40 empty] | Installed 40ft LF of flashing and installed 2 full columns= 4 column panels and caulked them | 50
21062 | BNA MNAA Garage B | 2024-02-01 | Zarur Nazario Padron Jr | Working on ACM panels/caulking them and also working on Columns | Subcontractor | Marc Ribar | [5 empty] | 11 | 110 |  |  | 2 scissor lifts and 1-85ft boomlift | [5 empty] | ACM Other | 42 | 70 | [40 empty] | Installed 3 full columns and caulked them | 40
22071 | GCDC Building 1 | 2024-02-01 | Oscar Hernandez | Carrying materials for mcdougall | Subcontractor | Colton Tomlin | true | The truck for pickup the material have delay |  |  |  | 3 | 10 | false |  | Forklift | false |  |  |  |  | ACM |  | 30
23006 | DLR Gold Sterling IAD54 | 2024-02-01 | Chad McCoy | With the setback that came with yesterday on the small louver section I wanted to be done yesterday. But today we had to go in and one crew had to continue on the little louver section while the other crew flew panels to the roof so that we had more to install on the roof. So I was one of the individuals working on the small louver section what we did today which we ran as many brackets and verticals as we could, and what it was doing was giving the other crew when they got their time to just hang and go with no layout. Once all the panels were on the roof, we switch spots I took the 125 with one of my guys and we went to the front louver steel and we started the layout which included four string lines.. and 75 brackets is what we installed today. With these brackets, we did not install the spice plate brackets due to not being fully sure without fence being up where the spices are going to fall, but these can be installed at any point once I get the bases installed with the verticals and the bottom fin. So as we went and continue today, the other crew like I said, install the louvers as the day got closer to the end, I did not see them finishing it 100% so I pulled off of my louvers and we went and help them knock it out completely. So sC4 is completely finished completely modified everything is cut. Everything is installed, a hundred percent. On the rest of that build out 21 fence needed to be cut down and all the verticals again. Collectively between yesterday and today with all the modifications it took two guys 12 hours to properly lay out properly, cut out and properly install the louver system that was too big to long and cut from the factory at the wrong angles. First thing in the morning, we have to go to the roof and drill a 3 inch hole. For penetration, and then both crews will be on louvers. we will have two booms, but I’m hoping to steal a third so that I can do layout of head of everybody else and install the first row of L brackets | Subcontractor | Colton Van Meter | true | The only delay was like today, where we had to modify the louver system to meet the structure. Hopefully tomorrow I will know the full extent of the huge louver structure around the generators and whether or not the angled fans will work. When we pull the string lines and we started installing the L brackets on the crooked and wavy steel, we have found that majority of the brackets so far with steel pan out to be structurally sound with enough L bracket to attach to each horizontal steel beam. |  |  | 55 clear | 5 | 10 | false |  | 80 foot boom | false |  |  | 6 |  | Layout Louvre | [24 empty] | 42 | 5
21062 | BNA MNAA Garage B | 2024-01-31 | Zarur Nazario Padron Jr | Working on columns and ACM panels | Subcontractor | Marc Ribar | [5 empty] | 8 | 80 |  |  | 2 scissor lifts | [5 empty] | ACM Other | 43 | 40 | [40 empty] | 3 complete columns= 6 column panels | 40
22071 | GCDC Building 1 | 2024-01-31 | Oscar Hernandez | Setting up scaffolding on south East, and installing mullions on the roof south east | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  |  | false |  |  |  |  | ACM |  | 56
23006 | DLR Gold Sterling IAD54 | 2024-01-31 | Chad McCoy | We started our morning with one crew, going to the roof and the other crew going to sC4 louvers. The crew on the roof was trying to do as much aCM I could off the scaffolding to get ahead of the ductwork guys. They installed nine ACM panels plus Z and insulation, and flashing around one of the duck work holes. The scaffolding had to be broke down and moved four times due to the ductwork that protrude down the wall and then runs across the TPO. On the SC4 louvers every vertical in almost every fin Has to be cut to a certain dimension. The verticals have to have at least 2 feet cut off of them. The bottom is 7 inches and the top is 17 inches to make it equal with top of steel. on the louver fence them self the first row of fence have to have the angled section re-cut due to improper angle of the 45 areas it’s not a 45 but just the angle areas. Because when you put this area together, the top will be at a quarter in the bottom slants will be at an 1 3/8” The next role of fins has to have the same thing done to the left hand side as the first row fins. On the third role of fence nothing Has to be cut on it, due to I need the cut to be next to the precast. The factory cuts on these louver fans are not straight and we are coming across multiple louvers that are.1/4 - 3/8 longer than there sister louvers. to add to the situation of this louver section, the louvers cannot be plum going vertically. if you level out the verticals on the louver system and then you install the louvers, as you go up, you will see either the left or the right side slants in. so what we had to do was install all of the louvers and then take the bolts out and pull the verticals to where they needed to sit to look proper on the install and then we put the bolts back in. So yesterday we started this install, but this morning I took all of it down and restarted.. we got two sections up which included 40 L brackets 20 vertical brackets that had to be cut at 7 and 17 and 43 fins that had to be cut. When you’re cutting the slants in the fins. You have to start your cut straight dance slant and then finish straight. if you do not do this and you just cut it at a direct angle, then the top and the bottom will look pigeon toed to each other instead of a uniform joint going up, so during this with a chopsaw or a Skil saw is tricky, but it can be done. You just have to do it over and over and over until you get a process down. At the end of the day after we cleaned up, we had to move all of our crates all of our insulation so that they can do groundwork in that area. This is also tricky due to the limited placement that is allowed on this job we still do not have room to bring our louvers from the laydown area to the job to make installation faster and easier. They are still 15 miles away. | Subcontractor | Colton Van Meter | true | Modifying the louvers pretty much from scratch to fit a structure that is neither plum or level on the concrete cost us a pretty good amount of the day |  |  | Clear 49 | 5 | 10 | false |  | 80 foot boom | false |  |  | 4 |  | ACM Caulking Flashing Insulation Layout Louvre Subgirt Zee | 9 | 5 | [18 empty] | 50 | 1 |  |  | 43 | 1.5 | 100 | 0.5 |  |  | 100 | 1 | 19 | 1
21062 | BNA MNAA Garage B | 2024-01-30 | Zarur Nazario Padron Jr | Working on ceiling panels and 3 full columns=6 column panels, also worked on Garage B 1st floor | Subcontractor | Marc Ribar | [5 empty] | 11 | 105 |  |  | 2 scissor lifts and 1-85ft boomlift | [5 empty] | ACM Other | 4 | 40 | [40 empty] | Installed 4 ceiling panels, installed 3 complete columns=6 column panels and caulking panels | 65
22006 | UTC Football Athletic Facility | 2024-01-30 | Marvin blanco | installing ACM panels at the UTC football and it was a good day | Subcontractor | Nick Akins | false |  |  |  |  | 6 | 11 | false |  | 2 boomlift | false |  |  |  |  | ACM | 40 | 66
22071 | GCDC Building 1 | 2024-01-30 | Oscar Hernandez | Punch list and installing mullions on the roof south east | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  |  | false |  |  |  |  | ACM |  | 56
23006 | DLR Gold Sterling IAD54 | 2024-01-30 | Chad mccoy | We had to stop what we were doing today and start louvers because we’re trying to get ahead of other aspects going again in front of us that pertain to the generators that the louvers are going to be incasing. So one SC for the small generator louver section I let Dalton play this out and start installing everything. He called me down there, because during his layout, he found that the height of the louvers we’re going to stick to feet, pass the top of the steel. So, on this note, we started measuring everything and we found that louvers were too long for the sections so they’re going to have to be cut and both verticals had to be cut to make it where it’s stuck 1 inch past the top of steel. The angles in the louvers also do not match with a quarter inch reveal slot in between them. the top if you do a quarter inch it leaves the bottom if you follow the wall at an inch and three eights. So what we started doing was trying to flare out one side of the louver verticals and suck in one side of the louver verticals to offset this notion. But what we came across while talking to Colton was that the lineup of the points of the angle parts of the louver does not line up with the angled parts of the concrete or steel welds. So we took everything back down, and we realigned the first section and re-cut an angle to make the louvers line up with the same points that was discussed with Colton on the concrete and the steel welds. So the first section and half of the second section is done I’ve got to go in the morning and lay out the third section to make the corners match so I will have templates on all of the louver fins. Tomorrow I’m gonna have the guys go to the roof and I and one guy am going to stay on the ground working on a sC4 to get it correct. | Subcontractor | Colton Van Meter | true | The louvers for SC4 are too big when it comes to height, and when it comes to length. we are having to pretty much do this one from scratch. We are using the material that we were gave but everything has to be modified in the sense to make the corners line up with each other and the corners line up with the structure. |  |  | Clear 48 | 5 | 10 | false |  | 80 foot boom | false |  |  |  |  | Louvre | [24 empty] | 1 | 1
23023 | Subaru LR | 2024-01-30 | David placzkowski | installed acm panels, flashing and caulked | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 9.5 | false |  | 40ft boom lift | false |  |  |  |  | ACM Caulking Flashing | 12 | 10 | [18 empty] | 95 | 6 | [10 empty] | 40 | 2
21062 | BNA MNAA Garage B | 2024-01-29 | Zarur Nazario Padron Jr | Working on columns and Ceiling panels | Subcontractor | Marc Ribar | [5 empty] | 7 | 67 |  |  | 2 scissor lifts | [5 empty] | Other | [42 empty] | 25 ceiling panels and completed 2 columns= 4 column panels | 67
22071 | GCDC Building 1 | 2024-01-29 | Oscar Hernandez | installing mullions on the roof South East and completing end caps | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | 1 boom lift and 1 forklift | false |  |  |  |  | ACM |  | 56
23023 | Subaru LR | 2024-01-29 | David placzkowski | installed acm panels and peeled poly | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8 | false |  | 40ft boom | false |  |  |  |  | ACM | 32 | 14
23023 | Subaru LR | 2024-01-28 | David placzkowski | installed acm panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8 | false |  | 40ft boom | false |  |  |  |  | ACM | 36 | 16
21062 | BNA MNAA Garage B | 2024-01-26 | Zarur Nazario Padron Jr | Working on ACM panels on Level 5 Canopy | Subcontractor | Marc Ribar | [5 empty] | 9 | 90 |  |  | 2 scissor lifts | [5 empty] | ACM | 35 | 90
22071 | GCDC Building 1 | 2024-01-26 | Oscar Hernandez | Completing end caps and installing mullions on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | Boom lift and forklift, and 2 scaffolds | false |  |  |  |  | ACM |  | 56
23023 | Subaru LR | 2024-01-26 | David placzkowski | Installed acm panels and caulked | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 9.5 | false |  | 40ft | false |  |  |  |  | ACM Caulking | 14 | 6 | [18 empty] | 70 | 5.5
21062 | BNA MNAA Garage B | 2024-01-25 | Zarur Nazario Padron Jr | Working on Canopy Level 5 | Subcontractor | Marc Ribar | [5 empty] | 9 | 90 |  |  | 2 scissor lifts | [5 empty] | ACM Other | 4 | 45 | [40 empty] | 42 Ceiling panels | 45
23023 | Subaru LR | 2024-01-25 | David placzkowski | 26 panels installed today | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 9.5 | false |  | 60ft boom lift | false |  |  |  |  | ACM | 26 | 19
21062 | BNA MNAA Garage B | 2024-01-24 | Zarur Nazario Padron Jr | Working on Ceiling panels on Level 5 Canopy and installing ACM panels | Subcontractor | Marc Ribar | [5 empty] | 9 | 90 |  |  | 2 scissor lifts and 1 boom lift | [5 empty] | ACM Other | 8 | 90 | [40 empty] | 32 Ceiling panels | 90
22071 | GCDC Building 1 | 2024-01-24 | Oscar Hernandez | Completing panels on the doors and installing anchor and mullion on the roof South east | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | Forklift and 1 boom lift | false |  |  |  |  | ACM |  | 56
21062 | BNA MNAA Garage B | 2024-01-23 | Zarur Nazario Padron Jr | Working on ACM panels on Level 5 Canopy | Subcontractor | Marc Ribar | [5 empty] | 9 | 90 |  |  | 1 scissor lift and 2-85ft boom lifts | [5 empty] | ACM | 32 | 90
22071 | GCDC Building 1 | 2024-01-23 | Oscar Hernandez | 3 guys was installing anchor and mullion on the Roof ( south east) and 3 installing panels for door and gate on north east | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | Forklift and 1 boom lift | false |  |  |  |  | ACM |  | 56
23006 | DLR Gold Sterling IAD54 | 2024-01-23 | Chad McCoy | We started our morning laying the plywood down so we could have the scaffolding on the tall west elevation of the roof. We ran the bottom panels that starts the elevation off the drip and then we continued staking till I needed my scaffolding taller. So we had to stop what we were doing and go to the other side of the west elevation and top the acm out. The panels have to be taken to the higher roof and handed down to the guys on the scaffolding. We will have to trip on two reveals due to the tight fit with the concrete. This will be down when peeled. But know I can take both scaffoldings to the duct work part of the west elevation | Subcontractor | Colton Van Meter | true | Roof is covered with snow still |  |  | 47 clear | 3 | 9 | false |  | 65 foot boom | false |  |  |  |  | ACM Insulation Subgirt Zee | 15 | 6 | [24 empty] | 100 | 1 |  |  | 150 | 1
21062 | BNA MNAA Garage B | 2024-01-22 | Zarur Nazario Padron Jr | Working on ACM panels on Level 5 Canopy | Subcontractor | Marc Ribar | [5 empty] | 9 | 90 |  |  | 1 scissor lift and 2-85ft boomlifts | [5 empty] | ACM | 36 | 90
22071 | GCDC Building 1 | 2024-01-22 | Oscar Hernandez | 3 guys installing panels (doors) south west, 3 guys installing anchors and mullion on the roof south east | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | 1 forklift and 1 boom lift | false |  |  |  |  | ACM |  | 56
22006 | UTC Football Athletic Facility | 2024-01-20 | Marvin Blanco | installing ACM panels and also insulation with cold water we couldn't work like the way we need to but it's what it's. | Subcontractor | Nick Akins | false |  |  |  |  | 6 | 10 | false |  | 2 boomlift | false |  |  |  |  | ACM Insulation | 15 | 30 | [24 empty] | 500 | 30
22071 | GCDC Building 1 | 2024-01-18 | Oscar Hernandez | Installing panels south East (doors ) and carrying material to the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | Forklift and 1boom lift | false |  |  |  |  | ACM |  | 56
22071 | GCDC Building 1 | 2024-01-17 | Oscar Hernandez | Installing panels on south East | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | Forklift | false |  |  |  |  | ACM |  | 64
23006 | DLR Gold Sterling IAD54 | 2024-01-17 | Chad mccoy | We started our morning getting our pup signed, Then we headed to the roof to prep our areas that’s covered in ice and snow. We shoveled and cleared our paths and then we went and got 15 pieces of plywood and we made an area that was not slick or snowy. Once that was done we we flew up all the backers scaffolding and 8 panels and we started setting up our scaffolding so the was a third level. I installed 3 butterfly’s so that we could tie off and then we installed the safety ropes. We continued installing the z and insulation and then we started installing panels. The panels next to the concrete have to be cut due to the concrete holding the panel off the wall and pushing it into the vertical joint. This was consulted with Colton. | Subcontractor | Colton Van Meter | true | The roof is covered in ice and snow, Hitt has been telling us no to being on the roof but they are not getting other areas ready for installation so we don’t have to be. So today I said F that and we took mattered into our own hand and we prepped the roof and we made an area to work. Today power solutions went up to the double door area and started taken panels off the wall so they could put a code reader on the wall. I did yell at this guy and told him that he owns that panel and they have no authorization to take my panels off the wall. We discussed this with there foreman and we came up with a plan for everything. |  |  | 21 clear | 3 | 8 | false |  | 65 foot boom | false |  |  |  |  | ACM Caulking Insulation Subgirt Zee | 3 | 1 | [18 empty] | 40 | 1 |  |  |  |  | 259 | 1 |  |  | 10 | 1
23006 | DLR Gold Sterling IAD54 | 2024-01-13 | Chad mccoy | Prior to leaving for the holidays we took 60 panels to the roof. But when we got back we had to take more panels to the roof due to Hitt wanting us to start in another location due to penetrations. So we loaded the trailer with another 40 panels and then we took up the starter panels we needed. We installed 10 panels off of the scaffolding we had. But Togo higher I need safety ropes and the rest of the scaffolding g we brought. So we left at 130 bc Hitt was closing the site at 2. And we went and bought all we needed | Subcontractor | Colton Van Meter | true | On the roof we have to start late each day due to ice on the tpo. Hitt safety doesn’t allow anybody on the tpo when it’s icy or until the sun is high enough |  |  | Partly cloudy and 52 | 3 | 5 | false |  | 65 foot boom | false |  |  |  |  | ACM | 10 | 2.5
21040 | 801 Church | 2024-01-12 | Marvin blanco | moving material from. level 3 to level 8 in the forklift 24 creates of panels. | Subcontractor | Nick Akins | false |  |  |  |  | 2 | 10 | false |  | forklift | false |  |  |  |  | Other | [42 empty] | moving material in the forklift | 20
22071 | GCDC Building 1 | 2024-01-12 | Oscar Hernandez | Installing panels on screen wall south East | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 64
23006 | DLR Gold Sterling IAD54 | 2024-01-12 | Chad McCoy | We started our morning walking all of the site where our material is staged. On the ground, 2 of our crates are moved. One is in the road and one is on a hill slant. The visitor center and eye brow for future acm is slowly getting dense glass installed. On the roof our panels were moved and the starter panel was placed face down on the boards with 8 panels on top of it. Our panels were also unstrapped and one panel was loose. After we accessed everything we started installing base flashing and the z and then insulation and then panels. The flashing screws and the z screws were caulked after installation. After insulation was installed we installed strapping to hold it in place. | Subcontractor | Colton Van Meter | true | Penetrations coming thru the walls with solid pipes had to be stopped and removed so panels can be installed first. The duct work installed in one of the opening is also in the wrong placement in the hole. So the panels and the flashing will not line up correctly |  |  | Partly cloudy 44 | 3 | 9 | false |  | 65 foot boom | false |  |  |  |  | ACM Caulking Flashing Hat Channel Insulation Trim | 4 | 1 | [18 empty] | 30 | 1 |  |  |  |  | 700 | 2 |  |  |  |  | 110 | 1 | 500 | 3 | 20 | 1
21062 | BNA MNAA Garage B | 2024-01-11 | Zarur Nazario Padron Jr | Working on ACM panels and tracks for ceiling panels on Canopy level 5 | Subcontractor | Marc Ribar | [5 empty] | 9 | 90 |  |  | 1 85ft boomlift and 2 scissor lifts | [5 empty] | ACM Other | 10 | 50 | [40 empty] | 26 tracks and 15 c's | 40
22071 | GCDC Building 1 | 2024-01-11 | Oscar Hernandez | Installing panels on screen wall south East | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 56
21062 | BNA MNAA Garage B | 2024-01-10 | Zarur Nazario Padron Jr | Working on ACM and installing tracks for ceiling panels | Subcontractor | Marc Ribar | [5 empty] | 8 | 80 |  |  | 2 scissor lifts and 1-85ft boom lift | [5 empty] | ACM Other | 9 | 50 | [40 empty] | Installed 27 pieces of tracks for ceiling panels | 40
22006 | UTC Football Athletic Facility | 2024-01-10 | Marvin blanco | installing ACM panels and also Zs" | Subcontractor | Nick Akins | false |  |  |  |  | 6 | 10 | false |  | 2 boomlift | false |  |  |  |  | ACM Hat Channel | 17 | 30 | [32 empty] | 500 | 30
22071 | GCDC Building 1 | 2024-01-10 | Oscar Hernandez | Installing panels on screen wall South East | Subcontractor | Colton Tomlin | false |  |  |  |  | 8 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 64
23005 | DLR Gold Manassas IAD53 | 2024-01-10 | JC Panels | Today we start installing the ACM for the entrances. We receive a delivery of some fasteners and also we went to pick up some more to the Fastenal store to attach the clip to the panel. We have receive panels and insolation . Looking forward to receive the verticals to finish the louvers section that they make us remove. | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 | 40 | true | Fasteners | Boom lifts | false |  |  |  |  | ACM |  | 40
22006 | UTC Football Athletic Facility | 2024-01-09 | Marvin Blanco | installing ACM panels and Zs" insulation but we couldn't work to much because rain it was a bad day | Subcontractor | Nick Akins | false |  |  |  |  | 6 | 60 | false |  | 2 boomlift | false |  |  |  |  | ACM Hat Channel Insulation | 10 | 20 | [24 empty] | 600 | 20 | [6 empty] | 30 | 20
21062 | BNA MNAA Garage B | 2024-01-08 | Zarur Nazario Padron Jr | Working on Canopy Level 5 | Subcontractor | Marc Ribar | [5 empty] | 8 | 80 |  |  | 2-85ft boomlifts | [5 empty] | ACM | 42 | 80
22071 | GCDC Building 1 | 2024-01-08 | Oscar Hernandez | Installing panels on screen wall south East | Subcontractor | Colton Tomlin | false |  |  |  |  | 8 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 64
21062 | BNA MNAA Garage B | 2024-01-06 | Zarur Nazario Padron Jr | Working on West and North side of Canopy | Subcontractor | Marc Ribar | [5 empty] | 12 | 120 |  |  | 2-85ft boomlifts and 1 scissor lift | [5 empty] | ACM | 90 | 120
21062 | BNA MNAA Garage B | 2024-01-05 | Zarur Nazario Padron Jr | Working on West side of Canopy | Subcontractor | Marc Ribar | [5 empty] | 12 | 120 |  |  | 2-85ft boomlifts and 1 scissor lift | [5 empty] | ACM | 49 | 120
22006 | UTC Football Athletic Facility | 2024-01-05 | Marvin blanco | installing panels and insulation. checking all the panels making sure that we have everything. | Subcontractor | Nick Akins | false |  |  |  |  | 3 | 10 | false |  | boomlift | false |  |  |  |  | ACM | 5 | 10
22006 | UTC Football Athletic Facility | 2024-01-05 | Marvin blanco | installing Z"s and unloading material panels and insulation | Subcontractor | Nick Akins | false |  |  |  |  | 3 | 10 | false |  | boomlift | false |  |  |  |  | Hat Channel Insulation | [26 empty] | 1000 | 8 | [6 empty] | 1500 | 2
22019 | QTS ASH2 DC2 Lockridge | 2024-01-05 | Marvin blanco | fixing stuff from punch list and cleaning panels | Subcontractor | Josh McPherson | false |  |  |  |  | 2 | 10 | false |  | boomlift | false |  |  |  |  | Other | [42 empty] | doing a punch list for the job QTS DC2 cleaning panels | 20
22071 | GCDC Building 1 | 2024-01-05 | Oscar Hernández | Cutting and installing panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 6 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 48
22071 | GCDC Building 1 | 2024-01-05 | Oscar Hernandez | Cutting and installing panels South East | Subcontractor | Colton Tomlin | false |  |  |  |  | 8 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 64
21062 | BNA MNAA Garage B | 2024-01-04 | Zarur Nazario Padron Jr | Working on West side of Canopy | Subcontractor | Marc Ribar | [5 empty] | 12 | 120 |  |  | 2-85ft boom lifts | [5 empty] | ACM Other | 42 | 80 | [40 empty] | 50 ft of flat metal | 40
21062 | BNA MNAA Garage B | 2024-01-03 | Zarur Nazario Padron Jr | Working on Canopy | Subcontractor | Marc Ribar | [5 empty] | 12 | 120 |  |  | 2-85ft boom lifts and 2 scissor lifts | [5 empty] | ACM Other | 5 | 40 | [40 empty] | Installed 360ft of flat metal for ACM panels | 80
22071 | GCDC Building 1 | 2024-01-03 | Oscar Hernandez | Cutting and installing panels on South west and east | Subcontractor | Colton Tomlin | false |  |  |  |  | 5 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 40
22071 | GCDC Building 1 | 2024-01-02 | Oscar Hernandez | Cutting and installing panels on screen wall south East and north east | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | 1 fork lift and 4 boom lift | false |  |  |  |  | ACM |  | 56
22071 | GCDC Building 1 | 2023-12-29 | Oscar Hernandez | Cutting and installing panels | Subcontractor | Colton Tomlin | true |  |  |  |  | 8 | 8 | false |  | Boom lift and forklift | false |  |  |  |  | ACM |  | 64
21062 | BNA MNAA Garage B | 2023-12-28 | Zarur Nazario Padron Jr | Working on ACM panels on Level 5 Garage Canopy and cleaning/caulking panels on Level 2 Bridge | Subcontractor | Marc Ribar | [5 empty] | 8 | 80 |  |  | 2 scissor lifts | [5 empty] | ACM Other | 30 | 60 | [40 empty] | Caulking and making adjustments to coping panels to fit nicer onto roof | 20
22071 | GCDC Building 1 | 2023-12-28 | Oscar Hernandez | Cutting and installing panels on screen wall South East | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
21062 | BNA MNAA Garage B | 2023-12-27 | Zarur Nazario Padron Jr | Working on ACM panels on Level 5 Garage Canopy | Subcontractor | Marc Ribar | [5 empty] | 8 | 80 |  |  | 2 scissor lifts | [5 empty] | ACM | 32 | 80
21062 | BNA MNAA Garage B | 2023-12-26 | Zarur Nazario Padron Jr | Working on installing ACM panels and installed 1 complete Column | Subcontractor | Marc Ribar | [5 empty] | 8 | 80 |  |  | 2 scissor lifts | [5 empty] | ACM | 38 | 80
21062 | BNA MNAA Garage B | 2023-12-25 | Zarur Nazario Padron Jr | Working on installing ACM panels on West side of Level 5 Canopy Garage | Subcontractor | Marc Ribar | [5 empty] | 8 | 80 |  |  | 2 scissor lifts | [5 empty] | ACM | 40 | 80
22071 | GCDC Building 1 | 2023-12-22 | Oscar Hernandez | Cutting and installing panels on screen wall South East | Subcontractor | Colton Tomlin | false |  |  |  |  | 6 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 48
21062 | BNA MNAA Garage B | 2023-12-21 | Zarur Nazario Padron Jr | Working ACM panel on East side of Canopy Garage | Subcontractor | Marc Ribar | [5 empty] | 12 | 120 |  |  | 2 scissor lifts | [5 empty] | ACM | 45 | 120
22071 | GCDC Building 1 | 2023-12-21 | Oscar Hernandez | Cutting and installing panels on screen wall South East | Subcontractor | Colton Tomlin | false |  |  |  |  | 8 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 64
22071 | GCDC Building 1 | 2023-12-20 | Oscar Hernandez | Cutting and installing panels on screen wall South East | Subcontractor | Colton Tomlin | false |  |  |  |  | 8 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 64
21040 | 801 Church | 2023-12-19 | Marvin Blanco | installing panels in the south east wall in the corner having a little difficult time but we make it. | Subcontractor | Nick Akins | false |  |  |  |  | 5 | 10 | false |  | boomlift and swing stage | false |  |  |  |  | ACM | 6 | 50
22071 | GCDC Building 1 | 2023-12-19 | Oscar Hernandez | cutting and installing panels on screen wall SE and making layout on the roof SE | Subcontractor | Colton Tomlin | false |  |  |  |  | 8 | 8 | false |  | 1 forklift and 4 boom lift | false |  |  |  |  | ACM |  | 64
23006 | DLR Gold Sterling IAD54 | 2023-12-19 | Chad McCoy | We started our day going thru all the crates and loading the trailer with all of our starter panels for our tall wall of acm. And we loaded all the panels for the long wall. We are fighting the wind like we did yesterday. We brought all the panels up today that we had on the trailer. We started off taken 8 panels at a time but we had to drop it down to 4 don’t weight and we needed to be able to hold on to the panels once we got all the panels to the roof. One team broke off and started putting bolts and screws into the long side of the louver bottom section. Another team started laying out and prepping the tall wall for the acm. During this lay out we found that the door is set to far in beyond the edge of the drywall and the top is at the wrong elevation on the termination bar install. I had a meeting with hitt and they said they were going to fix it. So because of the door and the tpo and the steel missing for louvers. There is only a 3 panels area that can actually be installed. So we checked the other door and it to is recessed So both doors are installed wrong. | Subcontractor | Colton Van Meter | true | Doors are wrong and too elevation is as wrong. |  |  | Wind around 40 mph gust and cloudy and cold 38 | 4 | 6 | false |  | 65 foot boom | false |  |  | 1 |  | Layout
23006 | DLR Gold Sterling IAD54 | 2023-12-16 | Chad McCoy | We started our morning installing z and insulation and another team layer out the next section of panels. We installed drip flashing and z and insulation so we could run all the panels on the roof. The doors are still not in so on the long wall we can’t complete it due to the lack of hustle with Hitt. The double door is in the hole but it’s simple wired in place. Friday was a bust due to Hitt needing us to get all of our material and equipment moved due to generators being prepped for install and the road getting rock laid down. We got all of our panels up to the roof and 30 bundles of insulation. We also took up 60 sticks of z. | Subcontractor | Colton Van Meter | true | Every day it’s something else that we have to stop for and move or go to another area and work |  |  | Partly cloudy and 62 | 4 | 10 | false |  | 65 foot boom | false |  |  | 1.5 |  | ACM Flashing Insulation Layout Subgirt Zee | 28 | 7 | [24 empty] | 650 | 2 |  |  | 620 | 3 | 60 | 1.5
21062 | BNA MNAA Garage B | 2023-12-15 | Zarur Nazario Padron Jr | Working on the little pieces of ACM in between beams on Canopy Level 5 bridge | Subcontractor | Marc Ribar | [5 empty] | 6 | 60 |  |  | Scissor lift and 85 ft boom lift | [5 empty] | Other | [42 empty] | Installing little pieces of ACM in between beams and letting them sit in place so they can dry up. Total of 12 pieces ACM were put up | 60
22071 | GCDC Building 1 | 2023-12-15 | Oscar Hernandez | Cutting and installing panels on screen wall SE | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift 4 boom lift | false |  |  |  |  | ACM |  | 72
21062 | BNA MNAA Garage B | 2023-12-14 | Zarur Nazario Padron Jr | Working on rest of ACM panels on top side of Level 5 Bridge | Subcontractor | Marc Ribar | [5 empty] | 6 | 60 |  |  | 85ft boomlift | [5 empty] | ACM | 5 | 60
21062 | BNA MNAA Garage B | 2023-12-14 | Zarur Nazario Padron Jr | Putting up last ACM panel and cutting out little pieces for in between beams | Subcontractor | Marc Ribar | [5 empty] | 6 | 48 |  |  | Boom lift 85ft and scissor lift | [5 empty] | ACM Other | 1 | 12 | [40 empty] | Cutting out little pieces of ACM Panel to make it fit in empty spaces in between beams | 36
22071 | GCDC Building 1 | 2023-12-14 | Oscar Hernandez | Cutting and installing panels on screen wall SE | Subcontractor | Colton Tomlin | false |  |  |  |  | 8 | 8 | false |  | 1 forklift and 4 boom lift | false |  |  |  |  | ACM |  | 64
23006 | DLR Gold Sterling IAD54 | 2023-12-14 | Chad mccoy | We started our day booming panels up to the roof. Once the panels to start were on the roof. We ran a string line for our flashing and then we started installing the drip flashing where the base of our panels will be. once the flashing was ran to our stopping point we started filling in the z that we needed at the base for the bottom attachments. We are caulking the screw heads for any penetration on our install and we are caulking the z to the wall. We also caulked the flashing penetrations. After this was finished we started hanging insulation where the panels will be installed. As we hung the insulation we installed a vertical strapping to help hold the insulation in place in case the wind picks up. Once the insulation was installed we started hanging the panels. We hung half of the long wall bottom panels and then we started putting reveals in. But the reveal pockets are to small due to improper builds of the panels that made it thru QC. Pictures and videos of these areas were sent to Mcdougal. We had to fly more panels up to do our second run but we got them to the roof and installed before the end of the day | Subcontractor | Colton Van Meter | true | The reveal pockets on the panels are to small for reveals |  |  | Partly cloudy 43 | 4 | 9.5 | false |  | 65 foot boom | false |  |  |  |  | ACM Caulking Flashing Insulation Subgirt Zee | 22 | 7 | [18 empty] | 350 | 1.5 |  |  |  |  | 880 | 1.5 |  |  | 130 | 1 | 90 | 1.5
21062 | BNA MNAA Garage B | 2023-12-13 | Zarur Nazario Padron Jr | Working on panels on Garage B level 5 bridge | Subcontractor | Marc Ribar | true | We have been delayed by the waterproofers to start work on Canopy side |  |  | Sunny | 6 | 60 |  |  | 1-85ft boomlift and 1 scissor lift | [5 empty] | ACM | 5 | 60
21062 | BNA MNAA Garage B | 2023-12-13 | Zarur Nazario Padron Jr | Working on West side of Level 5 Canopy | Subcontractor | Marc Ribar | [5 empty] | 6 | 60 |  |  | Boom lift 85 ft | [5 empty] | ACM Trim | 6 | 57 | [34 empty] | 40 | 3
22071 | GCDC Building 1 | 2023-12-13 | Oscar Hernandez | Cutting and installing panels on screen wall South East | Subcontractor | Colton Tomlin | false |  |  |  |  | 8 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 64
23006 | DLR Gold Sterling IAD54 | 2023-12-13 | Chad McCoy | I started my day attending the foreman’s meeting at 7. We were not allowed to get on the roof till the sun was up and out. So after my meeting I went and got the guys and we started at830. The delivery truck came early so we told him he had to wait. We started taken material to the roof. We took z and insulation and flashing to the roof. I started at the north west corner and started laying out. We laid out 22 rolls of panels. And there joints left to right. We also caulked the joint lines top to bottom spanning three joints. We then started hanging Z up And then at 3 we started unloading the truck. N | Subcontractor | Colton Van Meter | true | Tpo was icy |  |  | Partly cloudy and cold | 4 | 8 | true | 7 crates of acm | 65 foot boom | false |  |  | 2.5 |  | Layout Subgirt Zee | [30 empty] | 570 | 4
21062 | BNA MNAA Garage B | 2023-12-12 | Zarur Nazario Padron Jr | Working on installing panels on Garage B level 5 Bridge | Subcontractor | Marc Ribar | true | Waterproofers have not allowed us to advance onto the canopy part of level 5 |  |  | Sunny | 6 | 60 |  |  | 1-85ft boomlift and 1 scissor lift | [5 empty] | ACM | 5 | 60
21062 | BNA MNAA Garage B | 2023-12-12 | Zarur Nazario Padron Jr | Working East side top of Level 5 Garage canopy | Subcontractor | Marc Ribar | [5 empty] | 6 | 60 |  |  | Boom lift 85 ft | [5 empty] | ACM Other | 4 | 24 | [40 empty] | Preparing panels and measuring out the layout to make sure the cuts come out precise so we don't mess up on a panel | 36
22071 | GCDC Building 1 | 2023-12-12 | Oscar Hernandez | Cutting and installing panels on screen wall SE. and replacing anchor on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
21062 | BNA MNAA Garage B | 2023-12-11 | Zarur Nazario Padron Jr | Working on installing top half of panels on Garage B level 5 bridge and measuring out how the panels will fit and how much of the panel will have to be removed to fit on pillars perfectly | Subcontractor | Marc Ribar | true | 3 people got delayed 2 hours each because they had to bring 2 scissor lifts up to Level 5 canopy (6 hours total) |  |  | Sunny | 6 | 60 |  |  | 85ft boomlift | [5 empty] | ACM | 2 | 60
21062 | BNA MNAA Garage B | 2023-12-11 | Zarur Nazario Padron Jr | Working on the part of East side of Level 5 Bridge on garage | Subcontractor | Marc Ribar | [5 empty] | 5 | 50 |  |  | 85ft boom lift | [5 empty] | ACM Other | 2 | 29 | [40 empty] | 3 people took 6 hours of time cause of 2 delivered scissor lifts and 15 hours were used to measure out the beams and the cuts for the panels | 21
22071 | GCDC Building 1 | 2023-12-11 | Oscar Hernandez | Replacing anchor on the roof and cutting and installing panels on screen wall SE | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-12-09 | fredy Rodriguez | This day plastic was removed from the panels and caulking was placed between the panel and membrane in the canopy area. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | bomlif | false |  |  |  |  | ACM Caulking | 4 | 5 | [18 empty] | 168 | 5
21062 | BNA MNAA Garage B | 2023-12-08 | Zarur Nazario Padron Jr | Working on West side of Level 5 Garage bridge | Subcontractor | Marc Ribar | [5 empty] | 7 | 56 |  |  | Boom lift 85 ft | [5 empty] | ACM Other | 3 | 49 | [40 empty] | Installing 16 ft of trim in between of panels and getting the panels ready | 7
22071 | GCDC Building 1 | 2023-12-08 | Oscar Hernandez | Cutting and installing panels on screen wall South East, replacing anchor on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
22071 | GCDC Building 1 | 2023-12-08 | Oscar Hernandez | Cutting panels on screen wall and installing steels on SE | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-12-08 | fredy Rodriguez | This day 2 panels were fabricated | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | bomlif | true |  |  |  |  | ACM | 42 | 5
21062 | BNA MNAA Garage B | 2023-12-07 | Zarur Nazario Padron Jr | Working on the East and bottom part of Level 5 Garage canopy | Subcontractor | Marc Ribar | [5 empty] | 6 | 60 |  |  | 2 x 85ft boom lifts | [5 empty] | ACM Other | 5 | 54 | [40 empty] | Getting panels ready and Installing the trim in between the panels - 16ft of trim | 6
23002 | QTS MAN1 DC3 | 2023-12-07 | fredy Rodriguez | This day 3 panels were fabricated | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | bomlif | false |  |  |  |  | ACM | 37 | 5
21062 | BNA MNAA Garage B | 2023-12-06 | Zarur Nazario Padron Jr | Working on Garage Level 5 East side of bridge | Subcontractor | Marc Ribar | true | We got delayed because they were pouring down concrete and the waterproofing guys were borrowing the boom |  |  | Sunny | 5 | 9 |  |  | 85ft boomlift | [5 empty] | ACM Other | 3 | 20 | [40 empty] | Laying out the panels and we were delayed 4-1/2 hours because of concrete workers and waterproofing guys | 25
22071 | GCDC Building 1 | 2023-12-06 | Oscar Hernandez | Cutting panels on screen wall south East, installing steels on the beams screen wall south East, drilling holes on beams screen wall south East | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-12-06 | fredy Rodriguez | This day 4 panels were fabricated | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | bomlif | false |  |  |  |  | ACM | 26 | 5
23005 | DLR Gold Manassas IAD53 | 2023-12-06 | JC Panels | We start installing clips in section 1, 3 and 4 | Subcontractor | Dillon Bowman | true | Clips for section 1, 3 And 4 |  |  |  | 5 | 40 | false |  | 2 boom lifts | false |  |  |  |  | Louvre | [25 empty] | 40
21062 | BNA MNAA Garage B | 2023-12-05 | Zarur Nazario Padron Jr | Working on the East side of the walkway canopy Garage B | Subcontractor | Marc Ribar | [5 empty] | 5 | 50 |  |  | 85ft boom lift | [5 empty] | ACM Other | 4 | 34 | [40 empty] | Fabricated end panels, measuring layout of Level 5 bridge, screwing in coping | 16
22071 | GCDC Building 1 | 2023-12-05 | Oscar Hernandez | Cutting panels on screen wall SE, drilling holes on beams screen wall south East, installing steels on the beams south East | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
21062 | BNA MNAA Garage B | 2023-12-04 | Zarur Nazario Padron Jr | First day at job site | Subcontractor | Marc Ribar | true | We had to wait for a boom lift for 3 hours/ 5 guys = 15 hours total |  |  | Sunny | 5 | 50 |  |  | 85 ft boom lift | [5 empty] | ACM Other | 4 | 42 | [40 empty] | Fabricating 2 end panels and moving material by hand | 8
22071 | GCDC Building 1 | 2023-12-04 | Oscar Hernandez | Cutting panels on screen wall south, drilling holes on beams screen wall south East | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | true | 3 boxes of mullions and 1 box of anchors | 1 forklift, 4 boom lift | false |  |  |  |  | ACM |  | 56
23005 | DLR Gold Manassas IAD53 | 2023-12-04 | JC panels | We finish with the Louvers on section 2 .. waiting for the clips to go to the section 1,3,4 | Subcontractor | Dillon Bowman | false |  |  |  |  | 6 | 48 | true |  | 2 boom lifts | false |  |  |  |  | Louvre | [25 empty] | 48
23006 | DLR Gold Sterling IAD54 | 2023-12-04 | Chad mccoy | We started. Are they doing our PTP and going by the Hitt office and picking up our crate of vertical spice plates. I went to the roof to finish layout to the end of the cat walk and installing the brackets on the bottom piece of steel. Josh and Dalton were in the basket doing the other brackets. Once all the brackets were done, I got in the basket and Dalton and I started hanging verticals Josh went behind us and put all the bolts in. Once all the boats read, we start at hang fins. we continue doing this for two sections so 20 verticals were installed 40 horizontal and 68 fins. | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 7 | false |  | 65 foot boom | false |  |  | 5 |  | Layout
23002 | QTS MAN1 DC3 | 2023-12-02 | fredy Rodriguez | I have a bad panel that will need to be replaced, the panel number is in the photos | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | bomlif | false |  |  |  |  | ACM | 36 | 5
22058 | Amazon IAD 179 | 2023-12-01 | Fredy veliz | Job done | Subcontractor | Colton Van Meter | [5 empty] | 8 | 10 |  |  | 3 boom lifts one forklift | [5 empty] | Other | [42 empty] | Installing blades and cleaning | 80
22071 | GCDC Building 1 | 2023-12-01 | Oscar Hernandez | Cutting panels on screen wall SE, drilling holes on beams SE, installing panels on screen wall north East and SE | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-12-01 | fredy Rodriguez | This day 7 panels were fabricated | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | boom lif | false |  |  |  |  | ACM | 13 | 5
23005 | DLR Gold Manassas IAD53 | 2023-12-01 | JC Panels | louvers | Subcontractor | Dillon Bowman | false |  |  |  |  | 4 | 8 | true |  | Boomlift 65 and boomlift 85 | false |  |  |  |  | Louvre | [25 empty] | 32
23006 | DLR Gold Sterling IAD54 | 2023-12-01 | Chad mccoy | We started our day going to the yard and getting the trailer we loaded yesterday. We then went to the job. I did my ptp and then Josh went to the roof and we started hanging fins. As we went we adjusted verticals and put bolts in. As dalton and I traveled to get more fins Josh filled in screws. We installed 136 fins When we had the section installed up to the portapottys. We had to stop and let Hitt move all of them. When they finished we reset up our caz and then it started pouring so we called it for the day . | Subcontractor | Colton Van Meter | true | Portapottys were in our way. |  |  | Rain at the end of the day | 3 | 8 | false |  | 65 foot boom | false |  |  |  |  | Louvre | [24 empty] | 136 | 6
23025 | Paseo Tower 1 - Garage Screen | 2023-12-01 | Jean negron | We continue installing the south side, the pole and the new light beam were installed and we continue the south side installing panels, we finished installing all the panels...for more information look at the photos... | Subcontractor | Colton Van Meter | false |  |  |  |  | 7 | 84 | false |  | 2 boom lift | false |  |  |  |  | Other | [42 empty] | Panels | 84
22058 | Amazon IAD 179 | 2023-11-30 | Fredy veliz | Was good day all the channels and corner angles are installed working just in the blades | Subcontractor | Colton Van Meter | [5 empty] | 8 | 11 |  |  | 3 boom lifts and one forklift | [5 empty] | Other | [42 empty] | Installing blades | 88
22071 | GCDC Building 1 | 2023-11-30 | Oscar Hernandez | Installing panels on screen wall north East,Cutting panels on screen wall South East drilling holes on beams SE | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23006 | DLR Gold Sterling IAD54 | 2023-11-30 | Chad mccoy | We started our day with setting up our controlled access zone. Dalton and Josh wouldn’t put the boom and they started setting verticals to the brackets that were installed. I went up and started laying out for new brackets. I laid out new brackets all the way to the end of the cat walk and then I started installing. Hitt had a safety walk today so for 45 minutes we were doing nothing due to the presence of certain safety individuals on the site. After they were done, we continued working. We installed 30 verticals today 46 brackets we drilled out and installed 168 bolts. I laid out for 46 additional brackets and we had a truck that was delivered today with Z flashing and insulation. Once the truck was unloaded, we’re headed to the yard with the trailer so that we could load up all the fans for SC1 section and that was the end of our day. | Subcontractor | Colton Van Meter | true | The safety walk caused us to waste 45 minutes today but the main problem is where the porter potties are located plus the amount of traveling vehicles and people in the area they were trying to work so it’s hard to stage anything close. Dominion also has half the road taken up where nobody can utilize it so that minimizes are traveling with the berm. |  |  | Partly cloudy 53 | 3 | 9 | true | Z flashing insulation in a crate of hardware | 65 foot boom | false |  |  | 1.5 |  | Layout
23025 | Paseo Tower 1 - Garage Screen | 2023-11-30 | Jean negro | Today we continue installing panels on the south side, 63 panels were installed and we received delivery of 7 boxes of panels...for more information see the photos | Subcontractor | Colton Van Meter | false |  |  |  |  | 7 | 84 | true | 7 crate panels | 2 boom lift | false |  |  |  |  | Other | [42 empty] | Panels | 84
22058 | Amazon IAD 179 | 2023-11-29 | Fredy veliz | Everything going good | Subcontractor | Colton Van Meter | [5 empty] | 8 | 11 |  |  | 3 boom lifts one forklift | [5 empty] | Other | [42 empty] | Installing channels | 88
22071 | GCDC Building 1 | 2023-11-29 | Oscar Hernandez | Cutting panels on screen wall SE, DRILLING holes on the beams SE, installing panels on screen wall north East | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-11-29 | fredy Rodriguez | This day we lend a forklift to move the material that would be used in the work area. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | boom lif | false |  |  | 5 |  | ACM Layout | 6 | 5
23025 | Paseo Tower 1 - Garage Screen | 2023-11-29 | Jean negro | Today 8 boxes of panels were delivered, they began to install, 33 panels were installed...for more information, look at the photos... | Subcontractor | Colton Van Meter | false |  |  |  |  | 6 | 60 | true | 8 crate the panels | 2 boom lift | false |  |  |  |  | Other | [42 empty] | Panels | 60
22058 | Amazon IAD 179 | 2023-11-28 | Fredy veliz | Good progress no issues today | Subcontractor | Colton Van Meter | [5 empty] | 8 | 11 |  |  | 3 boom lifts one forklift | [5 empty] | Other | [42 empty] | Installing channels | 88
22071 | GCDC Building 1 | 2023-11-28 | Oscar Hernandez | Cutting panels for screen wall south East, installing panels on screen wall north East | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | 1 forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
22058 | Amazon IAD 179 | 2023-11-27 | Fredy veliz | We had some issues with the 86' lifting the channel need I bigger lift I already talked to the PM about that and the wind was 15 m/h today | Subcontractor | Colton Van Meter | [5 empty] | 8 | 10 |  |  | 3 boom lift 86' one forklift | [5 empty] | Other | [42 empty] | Installing clips and channels finished the repair on building 169 | 80
22071 | GCDC Building 1 | 2023-11-27 | Oscar Hernandez | cutting and installing panels on screen wall north East , installing steels on the beams NE Moving scaffolds from the roof to the parking lot | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
22058 | Amazon IAD 179 | 2023-11-22 | Fredy veliz | Today we did not have very good progress crane working on the area and the Farral material is damaged | Subcontractor | Colton Van Meter | [5 empty] | 8 | 7 |  |  | 3 boom lifts one forklift | [5 empty] | Other | [42 empty] | Working on the Farrall wall | 56
22071 | GCDC Building 1 | 2023-11-22 | Oscar Hernandez | Cutting and installing panels on north East and installing panels general clean up on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM
22058 | Amazon IAD 179 | 2023-11-21 | Fredy veliz | Today we stop for the rain | Subcontractor | Colton Van Meter | true | Weather |  |  | Raining | 8 | 4 |  |  | 3 boom lifts and one forklift | [5 empty] | Other | [42 empty] | Installing blades | 32
23006 | DLR Gold Sterling IAD54 | 2023-11-21 | Chad mccoy | We started our morning getting more material for our louver wall. We are taken vertical splices from SC1 to finish our wall all the way to where the steel is missing. We installed 96 fins. We also installed 36 cross members. I had a foreman’s meeting that lasted 30 minutes. We also had to clean up the top with the shavings and make sure all of our work areas are clean bc we are leaving tonight | Subcontractor | Colton Van Meter | false |  |  |  |  | 4 | 5 | false |  | 86 foot boom | false |  |  |  |  | Louvre | [24 empty] | 5 | 5
22026 | CSCC - Arts & Technology | 2023-11-20 | Kevin Morris | Replaced panels G01 X01 and D08.. Removed 6 panels and installed 6 | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 | 8 | false |  | Boom 60', 32' scissor | false |  |  |  |  | ACM | 6
22058 | Amazon IAD 179 | 2023-11-20 | Fredy veliz | Having some delays cause by ducts guys the been having issues with the equipment slows us down | Subcontractor | Colton Van Meter | [5 empty] | 8 | 10 |  |  | 3 boom lifts and one forklift | [5 empty] | Other | [42 empty] | Installing channels and blades | 80
22071 | GCDC Building 1 | 2023-11-20 | Oscar Hernandez | Cutting and installing panels on screen wall north East and installing panels on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23006 | DLR Gold Sterling IAD54 | 2023-11-20 | Chad mccoy | We started this morning finishing installation on 10 brackets And then we installed 14 verticals. We then installed cross members to the verticals till we ran out. Once all this was done we started installing fins. We installed 144 fins. We will have to get more material from the lay down yard in the am. That way we can finish the wall | Subcontractor | Colton Van Meter | false |  |  |  |  | 4 | 8 | false |  | 86 foot boom | false |  |  |  |  | Louvre | [24 empty] | 6 | 8
22071 | GCDC Building 1 | 2023-11-18 | Oscar Hernandez | Cutting and installing panels on screen wall north East and installing panels on the roof north East and general clean up on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 8 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 64
22058 | Amazon IAD 179 | 2023-11-17 | Fredy veliz | Today with little tension with the ducts guys the Had a machine down make us a posible delay I decide to swap boom lifts with them and work in i different area with the condition to have the area de we need ready for Monday at the end of the day they did some progress and we did progress in other areas | Subcontractor | Colton Van Meter | [5 empty] | 8 | 10 |  |  | 3 boom lifts and forklift | [5 empty] | Other | [42 empty] | Installing blades | 80
22071 | GCDC Building 1 | 2023-11-17 | Oscar Hernandez | Cutting and installing panels on screen wall north East and installing panels on the roof north East | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23006 | DLR Gold Sterling IAD54 | 2023-11-17 | Chad mccoy | We started our morning early, One team started installing the bottom L brackets on the lower section and the other team started installing the upper L brackets and verticals. We installed 60;L brackets and 43 veritcal. After the bottom section team got to the end they fell back and started installing bolts and all screw to completely secure the brackets and verticals. The upper team installed till we were about over the painters then we fell back and also started screwing everything off and installing bolts. At the end of the day we cleaned up and took the trailer to the lay down area so in the morning we can load cross brackets and fins. | Subcontractor | Colton Van Meter | false |  |  |  |  | 4 | 9 | false |  | 86 foot boom | false |  |  | 2 |  | Layout
22058 | Amazon IAD 179 | 2023-11-16 | Fredy Veliz | Everything going good 50% blades done 95% clips done 70% Channel done | Subcontractor | Colton Van Meter | [5 empty] | 8 | 10 |  |  | 3 boom lift one forklift | [5 empty] | Other | [42 empty] | Installing supports on the channels and blades | 80
22071 | GCDC Building 1 | 2023-11-16 | Oscar | Cutting and installing panels on screen wall north East and installing panels on the roof north East | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | 1 forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23025 | Paseo Tower 1 - Garage Screen | 2023-11-16 | Jean negron | 22panels were installed | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 55 | true | Panels art | 2 boom lift | false |  |  |  |  | ACM | 22 | 30
22026 | CSCC - Arts & Technology | 2023-11-15 | Kevin Morris |  | JWMCD Crew | Drake De Tomasi | true |  |  |  |  | 2 | 10 | false |  | Boom 60', 32' scissor | false |  |  |  |  | Caulking | [20 empty] | 120
22058 | Amazon IAD 179 | 2023-11-15 | Fredy Veliz | Everything going good | Subcontractor | Colton Van Meter | [5 empty] | 8 | 10 |  |  | 3 boom lifts and one forklift | [5 empty] | Other | [42 empty] | Installing channels and blades | 80
22071 | GCDC Building 1 | 2023-11-15 | Oscar Hernandez | Cutting and installing panels on screen wall north East, installing panels on the roof north East | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23006 | DLR Gold Sterling IAD54 | 2023-11-15 | Chad mccoy | .We started our morning at the laydown area, prepping all the plates with the thermal barrier and loading the trailer and And we had to unload all of SC one, due to the crane being in the way. What’s everything was loaded we went back to the job site. I turned in my PTP. We moved our berm and we went to work. We started on SC two and we started laying out the bottom and then we ran the string line so we can have a nice straight line of louvers and then Josh and I filled in one section at the bottom and then we started going vertically well Dalton and Dante with left or right filling in the bottom section so we could just go from bottom to the top and start over and then start putting verticals on. Upon putting the verticals on where he found that the distance between both vertical stacked is not the same as the steel so he had to get involved, and we had to wait for permission to switch the tops and the bottoms, so that it would lay out and look decent. We installed 62 horizontal brackets and 11 verticals before we had to stop | Subcontractor | Colton Van Meter | true | Crane moving this morning, And the distance between the bottom of louver and top doesn’t match the distance between bottom and top of steel |  |  | Chilly partly cloudy. | 4 | 8 | false |  | 85 foot boom | false |  |  | 2 |  | Layout
23040 | DRG Spring Hill | 2023-11-15 | Saul chicas | Today we were putting caulking on building 1 and 2 | Subcontractor | Nick Akins | [5 empty] | 2 | 8 |  |  | Boom lift | [5 empty] | ACM | 0 | 8
22026 | CSCC - Arts & Technology | 2023-11-14 | Kevin Morris | Southwest stairwell closed couldn't install last 2 panels, G01 panel is 9" to short | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 | 10 | false |  | Boom 60', 32' scissor | false |  |  |  |  | ACM Caulking | 4 | [19 empty] | 80
22058 | Amazon IAD 179 | 2023-11-14 | Fredy veliz | Good progress | Subcontractor | Colton Van Meter | [5 empty] | 8 | 10 |  |  | 3 boom lift and one forklift | [5 empty] | Other | [42 empty] | Installing Channels and blades | 80
22071 | GCDC Building 1 | 2023-11-14 | Oscar Hernandez | 2 guys was cutting panels , 3 installing panels on screen wall north East, 3 installing panels on the roof north East | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23006 | DLR Gold Sterling IAD54 | 2023-11-14 | Chad mccoy | We started our day going to the lay down area and getting all the supply’s for SC1. We went back to the job and started running our first clips and our string lines. Then dalton and dontae went to the roof and filled in the bottoms as josh and I installed up and down. We had to go to Home Depot and get more drill bits and drills and a impact. We also had to get a vacuum bc o the shavings. This way we can try and manage the shaving on the top. We insisted installing the first section completely amd dalton amd donta layed out an installed Half way down,. We were told today that the crane will be moving to our side in the am. So we had o reload everything and take everything back to the lay down so we could reload all of sc2 for the rest of the week install. We installed 55 brackets and 12. Verticals | Subcontractor | Colton Van Meter | true | The cranes and there future placement are causing us to have to stop and go and change course mid stream |  |  | Windy/partly cloudy chilly | 4 | 8 | false |  | 85 foot boom | false |  |  | 2 |  | Layout
22026 | CSCC - Arts & Technology | 2023-11-13 | Kevin Morris | Boom lift was repaired, had to replace flashing and rewaterproof | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 | 10 | false |  | Boom 60', 32' scissor | false |  |  |  |  | ACM Flashing | 13 | [31 empty] | 15
22026 | CSCC - Arts & Technology | 2023-11-13 | Kevin Morris | boom lift was repaired today | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 | 10 | false |  | Boom 60', 32' scissor | false |  |  |  |  | ACM Flashing | 13 | [31 empty] | 15
22058 | Amazon IAD 179 | 2023-11-13 | Fredy veliz | Waiting on any updates from the ducts guys they going slow I hope the get done by thanksgiving so I can fin my the week after if not they gonna cause me a delay | Subcontractor | Colton Van Meter | [5 empty] | 8 | 11 |  |  | 3 boom lifts and one forklift | [5 empty] | Other | [42 empty] | Installing channels and blades | 88
22071 | GCDC Building 1 | 2023-11-13 | Oscar Hernandez | 2 guys cutting panels on screen wall north East, 3 guys installing panels on screen wall north East,3 guys installing panels on the roof north East | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23006 | DLR Gold Sterling IAD54 | 2023-11-13 | Chad mccoy | We started our morning getting to the job so that we can do orientation and roof orientation. We were told at this point that we cannot go onto the TPO on the roof until the ice has melted completely so that puts us starting if we have to be on the roof at a later time. Once we left, we went to Home Depot and we bought a bunch of safety stuff that we need to meet the requirements of Hitt. And then we drove to the laydown area and started assessing all the material at Dlr 44. Once we got there within your phone call saying that the boom was gonna be delivered so we had to turn around and go back to stage the boom. Once the boom was in place, we went back to the staging area and set up tables so that we could start installing the thermal barrier on the brackets for section SC1. While one crew did this, Myself, and another went back to the job site and started laying out the steel for SC1 and SC2. SC3 and SC4 are not going to be ready anytime soon. During the layout of SC, one, we found that the louver links are way longer than the opening from precast of precast so the last set of louvers will have to be cut down. During the layout of SC to the steel length is way shorter than it supposed to be by 40 inches. I’m meeting with Hitt must be done to figure out what is gonna be done to fill this void. The screws are going to be delivered at some point tomorrow and the staging area is 5.5 miles away from our job | Subcontractor | Colton Van Meter | false |  |  |  |  | 4 | 8 | false |  | 85 foot boom | false |  |  | 3 |  | Layout
23025 | Paseo Tower 1 - Garage Screen | 2023-11-13 | Jean negron | Today we continue on the south side, posts, plates, clips were installed...for more information look at the photos… | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | false |  | 2 boom lift | false |  |  |  |  | Other | [42 empty] | Posted plates | 50
23040 | DRG Spring Hill | 2023-11-13 | Saul chicas | Today we clean up on building 1 and 2 and start doing some caulking | Subcontractor | Nick Akins | [5 empty] | 3 | 10 |  |  | Boom lift | [5 empty] | ACM | 0 | 10
23002 | QTS MAN1 DC3 | 2023-11-12 | fredy Rodriguez | Waiting for a response regarding the installation in this area that is marked in red. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 8 | false |  | boom lif | false |  |  |  |  | ACM | 15 | 5
22026 | CSCC - Arts & Technology | 2023-11-11 | Kevin Morris |  | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 | 8 | false |  | Boom 60', 32' scissor | false |  |  |  |  | ACM | 7
22071 | GCDC Building 1 | 2023-11-11 | Oscar Hernandez | Cutting and installing panels on north East | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 56
23002 | QTS MAN1 DC3 | 2023-11-11 | fredy Rodriguez | This day the installation was being verified in this area marked in red. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 9 | false |  | boom lif | false |  |  |  |  | ACM | 12 | 5
23025 | Paseo Tower 1 - Garage Screen | 2023-11-11 | Jean negro | Today poles and plates were installed on the south side...for more information look at the photos... | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | false |  | 2 boom lift | false |  |  |  |  | Other | [42 empty] | Posted ,plates | 50
23040 | DRG Spring Hill | 2023-11-11 | Saul chucas | Today we keep installing panels on building 2 and we complete 100% the installing of ACM metal panels | Subcontractor | Nick Akins | [5 empty] | 4 | 5 | [8 empty] | ACM | 5 | 5
22026 | CSCC - Arts & Technology | 2023-11-10 | Kevin Morris | boom lift broke down at 330, clean up areas before we could start working finished at 9:00 | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 5 | 10 | false |  | Boom 60', 32' scissor | false |  |  |  |  | ACM | 15
22058 | Amazon IAD 179 | 2023-11-10 | Fredy veliz | We hade some rain today | Subcontractor | Colton Van Meter | [5 empty] | 8 | 8 |  |  | 3 boom lifts one forklift | [5 empty] | Other | [42 empty] | Installing clips | 64
23002 | QTS MAN1 DC3 | 2023-11-10 | fredy Rodriguez | The roof was cleaned and extra material was lowered with the crane. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 8 | false |  | bomlif | false |  |  |  |  | ACM | 9 | 5
23025 | Paseo Tower 1 - Garage Screen | 2023-11-10 | Jean negron | Today poles on the north side and plates on the north side were installed...for more information look at the photos... | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | false |  | 1 hanging scaffolding | false |  |  |  |  | Other | [42 empty] | Posted, plates | 50
23040 | DRG Spring Hill | 2023-11-10 | Saul chias | Today we keep installing panels on building 2 | Subcontractor | Nick Akins | [5 empty] | 6 | 10 |  |  | Boom lift | [5 empty] | ACM | 9 | 10
22026 | CSCC - Arts & Technology | 2023-11-09 | Kevin Morris | southwest stairwell still closed on inside, stopped at 3:45 to clean up areas we are working in do to email for mass clean up. | JWMCD Crew | Drake De Tomasi | true |  |  |  |  | 5 | 10 | false |  | Boom 60', 32' scissor | false |  |  |  |  | ACM | 24
22058 | Amazon IAD 179 | 2023-11-09 | Fredy veliz | Trying to finish by thanks given but the ducts guys not doing very good progress | Subcontractor | Colton Van Meter | [5 empty] | 8 | 10 |  |  | 3 boom lift and one forklift | [5 empty] | Other | [42 empty] | Installing clip and channels | 80
22071 | GCDC Building 1 | 2023-11-09 | Oscar Hernandez | Cutting and installing panels on screen wall north East | Subcontractor | Colton Tomlin | false |  |  |  |  | 6 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 56
23002 | QTS MAN1 DC3 | 2023-11-09 | fredy Rodriguez | This day we received material to continue working in the canopy area | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 8 | true | Acm paneles | boom lif | false |  |  |  |  | ACM Flashing | 6 | 5 | [30 empty] | 40 | 5
22026 | CSCC - Arts & Technology | 2023-11-08 | Kevin Morris |  | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 5 | 10 | false |  | Boom 60' x 2... 32' scissor | false |  |  |  |  | ACM Layout | 19
22058 | Amazon IAD 179 | 2023-11-08 | Fredy veliz | Everything going good | Subcontractor | Colton Van Meter | [5 empty] | 8 | 10 |  |  | 3 boom lifts and 1 forklift | [5 empty] | Other | [42 empty] | Installing clips and channels | 80
22071 | GCDC Building 1 | 2023-11-08 | Oscar Hernandez | Cutting and installing panels on screen wall NE | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | true |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23025 | Paseo Tower 1 - Garage Screen | 2023-11-08 | Jean negron | Today we continue installing posts on the south side and plaques were installed...for more information look at the photos.. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | false |  | 2 boom lift | false |  |  |  |  | Other | [42 empty] | Posted | 50
22026 | CSCC - Arts & Technology | 2023-11-07 | Kevin Morris | Waterproofing on west entrance done today. Staged scissor lift on east side entrance peeled and caulked panels west side fis | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 5 | 10 | false |  | Boom 60' x 2 32' scissor | false |  |  |  |  | ACM Caulking | 13 | [19 empty] | 80
22058 | Amazon IAD 179 | 2023-11-07 | Fredy veliz | Everything is going good for now no issues | Subcontractor | Colton Van Meter | [5 empty] | 8 | 10 |  |  | 3 boom lifts and one forklift | [5 empty] | Other | [42 empty] | Installing clips Chanel and blades | 80
22071 | GCDC Building 1 | 2023-11-07 | Oscar Hernandez | Cutting and installing panels on screen wall NE | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23040 | DRG Spring Hill | 2023-11-07 | Saul chicas | Today we installed panels on building 2 | Subcontractor | Nick Akins | [5 empty] | 7 | 10 |  |  | Boom lift | [5 empty] | ACM | 25 | 10
22026 | CSCC - Arts & Technology | 2023-11-06 | Kevin Morris | west side entrance still not water proofed | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 5 | 10 | true | cleat and copping for roofers. 32' scissor lift | Boom 60' x 2. 32' scissor lift | false |  |  |  |  | ACM Caulking | 31 | [19 empty] | 120
22058 | Amazon IAD 179 | 2023-11-06 | Fredy veliz | Everything Good | Subcontractor | Colton Van Meter | [5 empty] | 8 | 10 |  |  | 3 boom lifts and a 1 forklift | [5 empty] | Other | [42 empty] | Installing clips and prep Channels | 80
22071 | GCDC Building 1 | 2023-11-06 | Oscar Hernandez | Cutting and installing panels on screen wall NE | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23025 | Paseo Tower 1 - Garage Screen | 2023-11-06 | Jean negron | Today we continue installing T on the south side...for more information look at the photos...we frequently move them due to the traffic conditions there at the entrance of the building... | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | false |  | 2 boom lift | false |  |  |  |  | Other | [42 empty] | Clip T | 50
23040 | DRG Spring Hill | 2023-11-06 | Saul chicas | Today we installed panels on building 2 | Subcontractor | Nick Akins | [5 empty] | 7 | 10 |  |  | Boom Lift | [5 empty] | ACM | 16 | 10
23002 | QTS MAN1 DC3 | 2023-11-05 | fredy Rodriguez | We installed 50 feet of clips for coping | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 8 | false |  | Esqueford and bomlif | false |  |  | 3 |  | Coping Corrugated / Screen wall Layout | [22 empty] | 10 | 5 | [16 empty] | 50 | 5
22026 | CSCC - Arts & Technology | 2023-11-04 | Kevin Morris | had rework soffit panels on entrance of FIS | JWMCD Crew | Drake De Tomasi | true |  |  |  |  | 5 | 8 | false |  | Boom 60' x 2 | false |  |  |  |  | ACM Caulking Layout | 10 | [19 empty] | 80
22058 | Amazon IAD 179 | 2023-11-04 | Fredy veliz | Today we only worked have of the day just to do do some progress on the clips | Subcontractor | Colton Van Meter | [5 empty] | 7 | 6 |  |  | 3 boom lifts and one forklift | [5 empty] | Other | [42 empty] | Installing clips | 42
23002 | QTS MAN1 DC3 | 2023-11-04 | fredy Rodriguez | We installed 60 feet of coping clips and started working on installing the problem that existed. in the stairs area #4 | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 9 | false |  | Esqueford and bomlif | false |  |  |  |  | Coping Corrugated / Screen wall | [22 empty] | 10 | 5 | [16 empty] | 80 | 5
23025 | Paseo Tower 1 - Garage Screen | 2023-11-04 | Jean negron | Today the south side poles began to be installed...for more information look at the photos... | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | false |  | 2 Boom lift | false |  |  |  |  | Other | [42 empty] | Posted | 50
23040 | DRG Spring Hill | 2023-11-04 | Saul chicas | We installed panels on building 2 | Subcontractor | Nick Akins | [5 empty] | 4 | 8 |  |  | Boom lift | [5 empty] | ACM | 7 | 8
22026 | CSCC - Arts & Technology | 2023-11-03 | Kevin Morris | Swapped out 4 panels on exterior FIS with remakes. had to fab top left column interior FIS. Cleaned up inside fis where we installed panels. staged panels on east | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 5 | 10 | true | remake panels for west and FIS entrance | Boom 60' x 2 | false |  |  |  |  | ACM | 17
22058 | Amazon IAD 179 | 2023-11-03 | Fredy veliz | I am hoping the duct guys get done so we can speed up if not they gonna cause a delay | Subcontractor | Colton Van Meter | [5 empty] | 6 | 10 |  |  | 3 boom lifts and 1 forklift | [5 empty] | Other | [42 empty] | Installing clips | 60
22071 | GCDC Building 1 | 2023-11-03 | Oscar Hernandez | Cutting and installing panels on screen wall NE | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-11-03 | Fredy Rodriguez | We installed 20 feet of Clip for coping and taking measurements in the number 3 stair areas. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | bomlif | false |  |  | 5 |  | Corrugated / Screen wall Layout | [22 empty] | 14 | 5
23025 | Paseo Tower 1 - Garage Screen | 2023-11-03 | Jean negron | Today we worked on the south side, T continued to be installed...for more information look at the photos... | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | false |  | 2 boom lift | false |  |  |  |  | Other | [42 empty] | Clip T | 50
23040 | DRG Spring Hill | 2023-11-03 | Saul chicas | Today we installed panels on building 2 | Subcontractor | Nick Akins | [5 empty] | 7 | 10 | true | Caulking | Boom lift | [5 empty] | ACM | 20 | 10
22026 | CSCC - Arts & Technology | 2023-11-02 | Kevin Morris | Can only do 10 pics | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 5 | 10 | false |  |  | false
22026 | CSCC - Arts & Technology | 2023-11-02 | Kevin Morris | Interior panels on FIS entry had to fab top column panel to tall, joint by window mullion to big had to rework | JWMCD Crew | Drake De Tomasi | true | Dirt work on west has lifts trapped |  |  |  | 5 | 10 | false |  | Boom 60' x 2 | false |  |  |  |  | ACM Layout | 6
22058 | Amazon IAD 179 | 2023-11-02 | Fredy veliz | Everything going good | Subcontractor | Colton Van Meter | [5 empty] | 7 | 10 |  |  | 3 boom lifts and one forklift | [5 empty] | Other | [42 empty] | Installing clips | 70
22071 | GCDC Building 1 | 2023-11-02 | Oscar Hernandez | Cutting and installing panels on screen wall NE | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-11-02 | fredy Rodriguez | This day we were cleaning the roof. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | true | coping, Acm paneles ,aluminum angle pieces | Esqueford and bomlif | false |  |  |  |  | Corrugated / Screen wall Insulation Subgirt Zee | [22 empty] | 20 | 5 |  |  | 190 | 5 |  |  | 15 | 5
23025 | Paseo Tower 1 - Garage Screen | 2023-11-02 | Jean negron | Today we continue installing the south side T-clip. We continue on the north side installing post the second phase of posted is installed ...for more information look at the photos | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | false |  | 2Boom lift,2 hanging scaffolding | false |  |  |  |  | Other | [42 empty] | Posted , clip | 50
23040 | DRG Spring Hill | 2023-11-02 | Saul chicas | Today we installed panels on building 2 | Subcontractor | Nick Akins | [5 empty] | 7 | 10 |  |  | Boom lift | [5 empty] | ACM | 19 | 10
22026 | CSCC - Arts & Technology | 2023-11-01 | Kevin Morris |  | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 5 | 10 | false |  | Boom 60' x 2 | false |  |  |  |  | ACM | 27
22058 | Amazon IAD 179 | 2023-11-01 | Fredy veliz | We are finishing every are that we doing so the ducts guys have chance to finish before we get to close | Subcontractor | Colton Van Meter | [5 empty] | 7 | 10 |  |  | 3 boom lifts and a forklift | [5 empty] | Other | [42 empty] | Installing blades on area A,B,C | 70
22071 | GCDC Building 1 | 2023-11-01 | Oscar Hernandez | 2 guys for cutting panels on north East, and 6 installing panels on screen wall NE | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-11-01 | fredy Rodriguez | This day we removed 20 metal panels in order to fix a poorly planned problem. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | boom lif | false |  |  |  |  | ACM | 6 | 5
23025 | Paseo Tower 1 - Garage Screen | 2023-11-01 | Jean negron | Today we continue installing the south side T clip, the north side we begin to install posts, all the posts from above were installed...for more information look at the photos... | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | true | Posted | 1Boom lift , 2 hanging scaffolding | false |  |  |  |  | Other | [42 empty] | Posted,clip T | 50
23040 | DRG Spring Hill | 2023-11-01 | Saul chicas | Today we installed panels on building 1 and building 2 | Subcontractor | Nick Akins | [5 empty] | 7 | 10 |  |  | Boom lift | [5 empty] | ACM | 18 | 10
22026 | CSCC - Arts & Technology | 2023-10-31 | Kevin Morris | Vestibule is bigger than prints show had to wait for GC to look and decide if it was ok to proceed, he said to install panels | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 5 | 10 | false |  | Boom 60' x 2 | false |  |  |  |  | ACM Layout Subgirt Zee | 28
22058 | Amazon IAD 179 | 2023-10-31 | Fredy veliz | No issues working behind the duct guys | Subcontractor | Colton Van Meter | [5 empty] | 7 | 10 |  |  | 2 boom lifts and a forklift | [5 empty] | Other | [42 empty] | Hanging channels section A,B,&C And supports | 70
22071 | GCDC Building 1 | 2023-10-31 | Oscar Hernandez | installing steels on the beams and installing panel’s on screen wall NE, cutting panel NE | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift, and 4 boom lift | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-10-31 | fredy Rodriguez | This day we continue to verify measurements so that the panels can be manufactured correctly in the warehouse.And modifications were also made to 10 panels. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | bomlif | false |  |  | 2 |  | Layout Subgirt Zee | [30 empty] | 160 | 5
23025 | Paseo Tower 1 - Garage Screen | 2023-10-31 | Jean negron | Today was a busy day, we had to keep moving because there were many deliveries at the entrance to the building and we had to move them. We had a person downstairs to direct the work and we continued installing clips on the south side...for more information, look at the photos... | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | true | Post | 2 boom lift | false |  |  |  |  | Other | [42 empty] | Clip | 50
23040 | DRG Spring Hill | 2023-10-31 | Saul chicas | Today we keep installing on building 1 and also after installing on building 2 | Subcontractor | Nick Akins | [5 empty] | 8 | 10 |  |  | Boom lift | [5 empty] | ACM | 16 | 10
22058 | Amazon IAD 179 | 2023-10-30 | Fredy veliz | Working good | Subcontractor | Colton Van Meter | [5 empty] | 8 | 10 |  |  | 2 boom lifts and a forklift | [5 empty] | Other | [42 empty] | Prep en installing clips | 80
22071 | GCDC Building 1 | 2023-10-30 | Oscar Hernandez | 2 cutting panels on screen wall NE , 6 installing steels and drilling holes on the beams screen wall NE | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-10-30 | fredy Rodriguez | This day we did measurement verifications. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | boom lif | false |  |  | 3 |  | ACM Layout | 8 | 5
23040 | DRG Spring Hill | 2023-10-30 | Saul chicas | No working today raining all day | Subcontractor | Nick Akins | [5 empty] | 1 | 0 |  |  | Boom lift | [5 empty] | ACM | 0 | 0
22026 | CSCC - Arts & Technology | 2023-10-28 | Kevin Morris |  | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 | 8 | false |  | Boom 60' x 2 | false |  |  |  |  | Caulking | [20 empty] | 150
23002 | QTS MAN1 DC3 | 2023-10-28 | fredy Rodriguez | We have been rectifying measurements to see if we can install panels. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 8 | false |  | bomlif | false |  |  |  |  | ACM Insulation Subgirt Zee | 1 | 5 | [24 empty] | 60 | 5 |  |  | 140 | 5
23040 | DRG Spring Hill | 2023-10-28 | Saul chicas | Today we keep going installing panels on building 1 | Subcontractor | Nick Akins | [5 empty] | 6 | 10 |  |  | Boom lift | [5 empty] | ACM | 9 | 10
22026 | CSCC - Arts & Technology | 2023-10-27 | Kevin Morris |  | JWMCD Crew | Drake De Tomasi | true | Door way on west wall was to narrow had to field fab 6 panels |  |  |  | 5 | 10 | false |  | Boom 60' x 2 | false |  |  |  |  | ACM
22058 | Amazon IAD 179 | 2023-10-27 | Fredy veliz | Everything good working on the ends until duct guys finish with the crane | Subcontractor | Colton Van Meter | [5 empty] | 7 | 8 |  |  | 2 boom lifts and 1 forklift | [5 empty] | Other | [42 empty] | Hanging Chanel's total 47 pcs | 56
22071 | GCDC Building 1 | 2023-10-27 | Oscar Hernandez | 3 guys installing panels on the roof north East and 3 installing steels on the beams screen wall NE | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | Forklift and 2 boom lift | false |  |  |  |  | ACM |  | 56
23002 | QTS MAN1 DC3 | 2023-10-27 | fredy Rodriguez | We have been rectifying measurements to see if we can install panels. | Subcontractor | Colton Van Meter | true | We have been rectifying measurements to see if we can install panels. |  |  |  | 5 | 10 | false |  | boom lif | false |  |  |  |  | ACM | 13 | 5
23040 | DRG Spring Hill | 2023-10-27 | Saul chicas | Today we keep installing panels on building 1 | Subcontractor | Nick Akins | [5 empty] | 6 | 10 |  |  | Boom lift | [5 empty] | ACM | 17 | 10
22026 | CSCC - Arts & Technology | 2023-10-26 | Kevin Morris | Had to modify 2 panels H01 & H04 | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 5 | 10 | false |  | Boom 60' x 2 | false |  |  |  |  | ACM | 41
22058 | Amazon IAD 179 | 2023-10-26 | Fredy veliz | Everything going good will need the 3rd boom lift on 11-06-23 | Subcontractor | Colton Van Meter | [5 empty] | 7 | 10 |  |  | 2 boom lifts one forklift | [5 empty] | Other | [42 empty] | Ree screw clips prep and install Chanel's | 70
22071 | GCDC Building 1 | 2023-10-26 | Oscar Hernandez | Installing panels on the roof north west and north East and materials handling | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  |  | false |  |  |  |  | ACM |  | 56
23002 | QTS MAN1 DC3 | 2023-10-26 | fredy Rodriguez | We are waiting for a response, what will happen with the installation of panels that are not aligned with the window. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | boom lif | false |  |  | 5 |  | ACM Insulation Layout | 7 | 5 | [24 empty] | 120 | 5
23025 | Paseo Tower 1 - Garage Screen | 2023-10-26 | Jean negro | Today we finished installing the north side clip, only one north side clip was left pending...we continue to the south side installing the clip, T... for more information look at the photos | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | false |  | 2 boom lift | false |  |  |  |  | Other | [42 empty] | Clip, T | 50
23040 | DRG Spring Hill | 2023-10-26 | Saul chicas | Today we keep installing panels on building 1 | Subcontractor | Nick Akins | [5 empty] | 7 | 10 | true | ACM | Boom lift | [5 empty] | ACM | 19 | 10
22026 | CSCC - Arts & Technology | 2023-10-25 | Kevin Morris |  | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 4 | 10 | false |  | Boom 60' x 2 | false |  |  |  |  | ACM Layout | 17
22058 | Amazon IAD 179 | 2023-10-25 | Fredy veliz | Everything is going good no issues | Subcontractor | Colton Van Meter | [5 empty] | 7 | 10 |  |  | 2 boom lift and forklift | [5 empty] | Other | [42 empty] | Prep laying and installing clips | 70
22071 | GCDC Building 1 | 2023-10-25 | Oscar Hernandez | Installing panels on the roof north East and carrying material from the parking lot to the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | Forklift and boom lift | false |  |  |  |  | ACM |  | 56
23002 | QTS MAN1 DC3 | 2023-10-25 | fredy Rodriguez | This day I made measurements for the panels, but the windows are an inch too big. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | boom lif | false |  |  | 5 |  | Insulation Layout | [26 empty] | 620 | 5
23025 | Paseo Tower 1 - Garage Screen | 2023-10-25 | Jean negron | We continue on the north side installing the top clip...south side we continue installing the clip...for more information look at the photos... | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | false |  | 1Boom lift 1 hanging scaffolding | false |  |  |  |  | Other | [42 empty] | Clip,T | 50
23040 | DRG Spring Hill | 2023-10-25 | Saul chicas | Today we keep working installing ACM on building 1 | Subcontractor | Nick Akins | [5 empty] | 7 | 10 |  |  | Boom lifts | [5 empty] | ACM | 17 | 10
22026 | CSCC - Arts & Technology | 2023-10-24 | Kevin Morris |  | JWMCD Crew | Drake De Tomasi | true | waterproofing and flashing on fizz wasn't ready |  |  |  | 4 | 10 | false |  | Boom 60' x 2 | false |  |  |  |  | ACM Flashing Hat Channel Layout | 17 | [31 empty] | 5 |  | 90
22058 | Amazon IAD 179 | 2023-10-24 | Fredy veliz | Everything going good no issues | Subcontractor | Colton Van Meter | [5 empty] | 7 | 10 |  |  | 2 boom lift 1 forklift | [5 empty] | Other | [42 empty] | Prep and install clips | 70
22071 | GCDC Building 1 | 2023-10-24 | Oscar Hernandez | Hanging steels on the beams screen wall NE and re installing anchors on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | Forklift and 2 boom lift | false |  |  |  |  | ACM |  | 56
23002 | QTS MAN1 DC3 | 2023-10-24 | fredy Rodriguez | This day we started working on the North West area canopy | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | boom lif | false |  |  |  |  | Subgirt Zee | [30 empty] | 910 | 5
23025 | Paseo Tower 1 - Garage Screen | 2023-10-24 | Jean negron | Today we continue the north side installing clip from above...and we continue installing clip on south side...for more information look at the photos... | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | false |  | 1 hanging scaffolding 1 boom lift | false |  |  |  |  | Other | [42 empty] | Clip | 50
23040 | DRG Spring Hill | 2023-10-24 | Saul chicas | Today we start installing panels on building 1 | Subcontractor | Nick Akins | [5 empty] | 7 | 10 | true | ACM | Boom lift | [5 empty] | ACM | 20 | 10
22026 | CSCC - Arts & Technology | 2023-10-23 | Naza | First day at Job site | Subcontractor | Drake De Tomasi | false |  |  |  |  | 3 | 7 | false |  | 60' boom lift | false |  |  |  |  | ACM Hat Channel Other | 3 | 14 | [32 empty] | 10 | 2 | [6 empty] | Aluminum starter 10' Moving material by hand | 5
22026 | CSCC - Arts & Technology | 2023-10-23 | Kevin Morris |  | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 5 | 10 | false |  | Boom 60' x 2 | false |  |  |  |  | ACM Flashing Hat Channel Layout | 14 | [31 empty] | 40 |  | 30
22058 | Amazon IAD 179 | 2023-10-23 | Fredy veliz | Was a good days started the layout and had meeting with the ducts guys to coordinate the project | Subcontractor | Colton Van Meter | [5 empty] | 7 | 10 | true | Corrugated panels, screws, thermal break | 2 boom lift and forklift |  |  |  | 16 |  | Layout Other | [42 empty] | Orientation for the new guys Drilling holes on the clips Moving material Inspecting tools | 54
22071 | GCDC Building 1 | 2023-10-23 | Oscar Hernandez | Drilling holes on the beams and hanging C profile on the beams NE | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | Forklift and 2 boom lift | false |  |  |  |  | ACM |  | 56
23013 | Carvana San Diego | 2023-10-23 | Chad mccoy | We had to start this morning by making Panels. They were panels that were sent long and they were panels that are central, and they have to be laid out to where we need them so that we can make them to the right links and then install them.. These are pretty much in the area where the horse shoes are. So today we pretty much made three panels and we did all the flashing for the panels we had already done and we tripped in almost all of the reveals that needed to be done at the bottom base and I cut one more scupper. At the end of the day we took two boards with Styrofoam on it from Mcdougal when cased the west canopy panel that is coming apart and we feel the crevice with 1199 and then we took all the clamps that I had, and sandwiched this section to get this panel to close, and we are going to leave it until this evening | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 9 | false |  | 80 foot boom | false |  |  | 2 |  | ACM Layout Trim | 3 | 3 | [34 empty] | 120 | 3
23025 | Paseo Tower 1 - Garage Screen | 2023-10-23 | Jean negron | Today we started the north side we continued installing the south side we started installing the clips above...for more information look at the photos... | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | true | Clip 8 palet | 1 boom lift 1 hanging scaffolding | false |  |  |  |  | Other | [42 empty] | Clip and T | 50
23040 | DRG Spring Hill | 2023-10-23 | Saul chicas | Today we start unloading material and equipment doing some layout | Subcontractor | Nick Akins | [5 empty] | 7 | 10 | true | Boom lift | Boom lift | [5 empty] | ACM | 0 | 10
23002 | QTS MAN1 DC3 | 2023-10-22 | fredy Rodriguez | This day we had new measures to do the coping of the service elevator area. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | boom lif and Esqueford | false |  |  |  |  | Corrugated / Screen wall Flashing Insulation Subgirt Zee | [22 empty] | 27 | 5 |  |  | 140 | 5 |  |  | 180 | 5 | 40 | 5
23013 | Carvana San Diego | 2023-10-22 | Chad mccoy | We went in this morning and we continued installing panels on the west elevation. As we got to the panel area, we would take the trim off, cut the drip edge off of it, and then reinstall it . We cut out to camera holes and a scupper today. We are waiting to trip in the reveals and put on the flashing until we are further along with the panel install. That’ll come tomorrow | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 7 | true | Flashing from Nashville arrived | 80 foot boom | false |  |  | 1.5 |  | ACM Layout Trim | 6 | 3 | [34 empty] | 75 | 1
23013 | Carvana San Diego | 2023-10-21 | Chad McCoy | We started our day, getting the boom in place and getting everything ready to start taking down the Panels. The cameras are still up today so we had to work around the cameras being up and there’s a window washer in an 80 foot boom. They were also having to work around. We started on the lower wraparound panels next to the canopy with the soffit and we went east to west as we took Panels down we took the trim down to and cut all the drip edges off so that the new trim can go right over it. We also had to cut about 35 feet of drywall off the drywall stuck below the original trim install so when we went to put the new trim on after the panels are on it will be wavy and not consistent and flat like it’s supposed to be so we had to cut the pieces off to make it higher than the bottom or base of our trim.. once we got the areas reworked with the trim and panels removed, we started laying out for the new panels after we laid out for the new panels. We started installing the new panels. We removed 20 Panels today and we reinstalled six new panels and we removed And cut about 140 feet of trim today | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 8.5 | false |  | 80 foot boom | false |  |  | 2 |  | ACM Layout Trim | 6 | 2.5 | [34 empty] | 140 | 1.5
23025 | Paseo Tower 1 - Garage Screen | 2023-10-21 | Jean negron | We continue installing the north side clip...for more information look at the photos... | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | false |  | 2 hanging scaffolding | false |  |  |  |  | Other | [42 empty] | Clip | 50
22026 | CSCC - Arts & Technology | 2023-10-20 | Kevin Morris | Cleaned trash, moved material, and equipment from East side | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 | 10 | false |  | Boom 60' | false |  |  |  |  | ACM | 12
22071 | GCDC Building 1 | 2023-10-20 | Oscar Hernandez | Drilling holes on the beams NE | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | Drilling holes on the beams NE | false |  |  |  |  | ACM |  | 56
23002 | QTS MAN1 DC3 | 2023-10-20 | fredy Rodriguez | This day cleaning was carried out on the roof. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | true | This day I received another 65 foot Boom lift. | boom lif and Esqueford | false |  |  |  |  | Corrugated / Screen wall Flashing Insulation Subgirt Zee | [22 empty] | 28 | 5 |  |  | 150 | 5 |  |  | 35 | 5 | 40 | 5
23025 | Paseo Tower 1 - Garage Screen | 2023-10-20 | Jean negron | We continue installing clip and T north side...for more information look at the photos... | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | true | Clip, steel tube connection | 2 hanging scaffolding | false |  |  |  |  | Other | [42 empty] | Clip and T | 50
22026 | CSCC - Arts & Technology | 2023-10-19 | Kevin Morris |  | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 | 10 | false |  | Boom 60' | false |  |  |  |  | Caulking | [20 empty] | 200
22071 | GCDC Building 1 | 2023-10-19 | Oscar Hernandez | Installing panels on the roof and drilling holes on beams NE | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | Forklift and 2 boom lift | false |  |  |  |  | ACM |  | 56
23025 | Paseo Tower 1 - Garage Screen | 2023-10-19 | Jean negron | We continue installing Clip T... for more information look at the photos... | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | false |  | 2 hanging scaffolding | false |  |  |  |  | Other | [42 empty] | Clip | 50
22026 | CSCC - Arts & Technology | 2023-10-18 | Kevin Morris | Found panel 205-D10 damaged on wall | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 | 10 | true | Fs03 and 8 boxes of champagne caulk | Boom 60' | false |  |  |  |  | ACM Caulking | 1 | [19 empty] | 190
22071 | GCDC Building 1 | 2023-10-18 | Oscar Hernandez | Installing panels on the roof north and south side | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  |  | false |  |  |  |  | ACM |  | 56
23002 | QTS MAN1 DC3 | 2023-10-18 | fredy Rodriguez | This day we started working on the area of ​​stairs number 4, which was not ready before. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | boom lif and Esqueford | false |  |  |  |  | Corrugated / Screen wall Flashing Insulation Subgirt Zee | [22 empty] | 17 | 5 |  |  | 120 | 5 |  |  | 32 | 5 | 9 | 5
23025 | Paseo Tower 1 - Garage Screen | 2023-10-18 | Jean negron | Today we continue installing the north side 10clip and 13 the T clips were installed on the north side... for more information look at the photos... | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | false |  | 2 hanging scaffolding | false |  |  |  |  | Other | [42 empty] | Clip | 50
22026 | CSCC - Arts & Technology | 2023-10-17 | Kevin Morris |  | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 | 8 | false |  |  | false |  |  |  |  | Caulking | [20 empty] | 170
22071 | GCDC Building 1 | 2023-10-17 | Oscar Hernandez | Installing panels on the roof north and south and installing scaffold on the stairs on north side | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  |  | false |  |  |  |  | ACM |  | 56
23025 | Paseo Tower 1 - Garage Screen | 2023-10-17 | Jean negron | Today we started installing the north side clip...for more information look at the photos... | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | true | Screws,drill bit | 2 hanging scaffold | false |  |  |  |  | Other | [42 empty] | Clip | 50
22026 | CSCC - Arts & Technology | 2023-10-16 | Kevin Morris |  | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 | 8 | false |  |  | false |  |  |  |  | Caulking | [20 empty] | 140
22071 | GCDC Building 1 | 2023-10-16 | Oscar Hernandez | Installing panels on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | true | Steel for screen wall NE and SE |  | false |  |  |  |  | ACM
23025 | Paseo Tower 1 - Garage Screen | 2023-10-16 | Jean negron | Screws,clip | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | true | Clips,screws | 2 hanging scaffold | false |  |  |  |  | Other
22026 | CSCC - Arts & Technology | 2023-10-13 | Kevin Morris | Had to go to shop to pick up remake panel and caulking tips | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 | 9 | false |  | Boom 60' | false |  |  |  |  | Caulking | [20 empty] | 120
22026 | CSCC - Arts & Technology | 2023-10-13 | Kevin Morris |  | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 | 7 | false |  | Boom 60' | false |  |  |  |  | ACM Flashing Subgirt Zee | 14 | [29 empty] | 40 |  | 30
22071 | GCDC Building 1 | 2023-10-13 | Oscar Hernandez | Installing panels on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  |  | false |  |  |  |  | ACM |  | 56
22071 | GCDC Building 1 | 2023-10-12 | Oscar Hernandez | Installing panels on the roof south and north west | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  |  | false |  |  |  |  | ACM |  | 56
22026 | CSCC - Arts & Technology | 2023-10-11 | Kevin Morris |  | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 | 8 | true | Baker scaffolding |  | false |  |  |  |  | ACM Subgirt Zee | 18 | [29 empty] | 120
22050 | LaFontaine Lansing Ford | 2023-10-11 | Chad mccoy | We started our day laying out for the upper corrugated on the roof. We then installed these drip flashing along the hole way. After that we install 6 sheets of corrugated. The last two had to be cut down. After these were installed we laid out for the arched corrugated. In the arch is two ac ducts and a vent. After we installed the drip edge we laid out and cut the first panel. This area took 5 pieces and all had to be. It with a arch. Once we finished we trimmed out all we could and then we cleaned up and moved to the access doors. I had Trevor lay out the main door and the electrion did the other. Hat channel behind the panels had to be cut out and then the panels needed to be cut and then I routed the returns. On the panels and then I built the doors them self. I installed the excrusions and installed the doors. While I was building these donta installed the enclosure pieces for the doors and corners. | Subcontractor | Colton Van Meter | false |  |  |  |  | 2 | 16 | false |  |  | false |  |  | 4 |  | ACM Corrugated / Screen wall Layout Trim | 2 | 3 | [20 empty] | 8 | 3 | [12 empty] | 30 | 1
22071 | GCDC Building 1 | 2023-10-11 | Oscar Hernandez | 3 was installing panels on screen wall Sw, 3 was installing panels on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | Boom lift and forklift | false |  |  |  |  | ACM |  | 56
23025 | Paseo Tower 1 - Garage Screen | 2023-10-11 | Jean negron | We worked on the north side, we continued taking measurements and the north side was finished. For more information, look at the photos... | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | false |  |  | false |  |  |  |  | Other | [42 empty] | Making measures | 50
22026 | CSCC - Arts & Technology | 2023-10-10 | Kevin Morris |  | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 | 8 | false |  |  | false |  |  |  |  | ACM Subgirt Zee | 17 | [29 empty] | 180
22071 | GCDC Building 1 | 2023-10-10 | Oscar Hernandez | Installing panels on screen wall Sw and installing panels on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift | false |  |  |  |  | ACM |  | 72
23025 | Paseo Tower 1 - Garage Screen | 2023-10-10 | Jean negron | Today we continued the south side putting the measurements, we almost finished making all the measurements on the south side...and the brick sent photos that had red chaulk stains for more information in the photos to see that the brick is not stained | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | false |  | 2 boom lift | false |  |  |  |  | Other | [42 empty] | measures North side | 50
22026 | CSCC - Arts & Technology | 2023-10-09 | Kevin Morris |  | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 | 8 | false |  | Boom 60' | false |  |  |  |  | ACM Subgirt Zee | 17 | [29 empty] | 180
22071 | GCDC Building 1 | 2023-10-09 | Oscar Hernandez | 3 guys cutting and installing panels on screen wall Sw,3 installing panels on the roof and 2 carrying material and general clean up | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 1 boom lift | false |  |  |  |  | ACM |  | 72
23025 | Paseo Tower 1 - Garage Screen | 2023-10-09 | Jean negron | Today we started on the north side but we couldn't work because the paint wasn't ready we had to move them to the south side to work on the litf boom but we had a bad machine we had some bigicult to work on... | Subcontractor | Colton Van Meter | true | Today we started on the north side but we couldn't work because the paint wasn't ready we had to move them to the south side to work on the litf boom but we had a bad machine we had some bigicult to work on... |  |  |  | 5 | 50 | true |  | Boom lift | false |  |  |  |  | Other | [42 empty] | measures | 50
22071 | GCDC Building 1 | 2023-10-07 | Oscar Hernandez | Installing panels on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 8 | 8 | false |  |  | false |  |  |  |  | ACM |  | 64
22026 | CSCC - Arts & Technology | 2023-10-06 | Kevin Morris |  | JWMCD Crew | Drake De Tomasi | true |  |  |  |  | 2 | 6 | true | 4 crates of acm FS04 | Boom 60' | false |  |  |  |  | ACM | 12
22071 | GCDC Building 1 | 2023-10-06 | Oscar Hernandez | Installing panels on the roof and carrying material on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  |  | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-10-06 | fredy Rodriguez | Today we installed 100 galvanized angles.andThis day170 feet of Coping Clip were installed. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 11 | false |  | boom lif and Esqueford | false |  |  |  |  | Coping Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 2 | 5 | [6 empty] | 150 | 5 | 50 | 5 | [6 empty] | 280 | 5
23025 | Paseo Tower 1 - Garage Screen | 2023-10-06 | Jean negron | The north side was finished putting in all the light poles and the beams...for more information in the photos... | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | false |  | suspended scaffolding | false |  |  |  |  | Other | [42 empty] | light posts | 50
22026 | CSCC - Arts & Technology | 2023-10-05 | Kevin Morris | Right side of window set to far in causing fab screws to perturbed to far out | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 | 10 | false |  | Boom 60' | false |  |  |  |  | ACM Flashing Subgirt Zee | 26 | [29 empty] | 410 |  | 10
22071 | GCDC Building 1 | 2023-10-05 | Oscar Hernandez | Installing panels on the roof and carrying material | Subcontractor | Colton Tomlin | false |  |  |  |  | 5 | 8 | false |  |  | false |  |  |  |  | ACM |  | 40
23002 | QTS MAN1 DC3 | 2023-10-05 | fredy Rodriguez | This day160 feet of Coping Clip were installed. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 11 | false |  | boom lif and Esqueford | false |  |  |  |  | Coping | [40 empty] | 190 | 5
23025 | Paseo Tower 1 - Garage Screen | 2023-10-05 | Jean negron | The north side started, some posts were installed...more information in the photos... | Subcontractor | Colton Van Meter | true |  |  |  | rainy | 5 | 50 | false |  | Boom lift | false |  |  |  |  | Other | [42 empty] | light post | 50
22026 | CSCC - Arts & Technology | 2023-10-04 | Kevin Morris | Window set to far back leaving fab screws exposed | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 | 8 | false |  | Boom 60' | false |  |  |  |  | ACM Flashing Subgirt Zee | 19 | 7 | [28 empty] | 240 | 1 | 3
22071 | GCDC Building 1 | 2023-10-04 | Oscar Hernandez | General clean up, installing panels on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 5 | 8 | false |  |  | false |  |  |  |  | ACM |  | 40
23025 | Paseo Tower 1 - Garage Screen | 2023-10-04 | Jean negron | We continued on the south side, everything that could be done on the south side was finished, three remaining posts and two beams remained...for the information in the photos... | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | false |  | Boom lift | false |  |  |  |  | Other | [43 empty] | 50
22026 | CSCC - Arts & Technology | 2023-10-03 | Kevin Morris |  | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 | 8 | true | 3" zee | Boom 60' | false |  |  |  |  | ACM Flashing Subgirt Zee | 12 | [29 empty] | 30 |  | 10
22071 | GCDC Building 1 | 2023-10-03 | Oscar Hernandez | Installing panels on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  |  | false |  |  |  |  | ACM |  | 56
23002 | QTS MAN1 DC3 | 2023-10-03 | fredy Rodriguez | This day, material was lifted to the roof with the crane to have material in the area of ​​stairs number 4 and the elevator area. | Subcontractor | Colton Van Meter | false |  |  |  |  | 4 | 11 | false |  | boom lif and Esqueford | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 15 | 5
23025 | Paseo Tower 1 - Garage Screen | 2023-10-03 | Jean negron | 10 posts were installed on the south side, we started moving boom lift 2 and serco with teipe for the precaution of the rest of the area | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | false |  | Boom lift | false |  |  |  |  | Other | [42 empty] | light plates | 50
22026 | CSCC - Arts & Technology | 2023-10-02 | Kevin Morris | Took down 60' of 4" zee and 2 panels. Reinstalled 3" zee and 7 acm panels | JWMCD Crew | Drake De Tomasi | true | Rip down 4 inch zee to make 3 inch zee |  |  | Sunny / hot | 2 | 8 | false |  | Jlg boom | false |  |  |  |  | ACM Subgirt Zee Trim | 7 | [29 empty] | 200
22071 | GCDC Building 1 | 2023-10-02 | Oscar Hernandez | Installing panels on screen wall Sw and roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | Forklift and 2 boom lift | false |  |  |  |  | ACM |  | 64
23002 | QTS MAN1 DC3 | 2023-10-01 | fredy Rodriguez | At the moment I am waiting for answers so I can start in the area of ​​stairs number 4. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 8 | false |  | boom lif | false |  |  |  |  | Coping Corrugated / Screen wall Flashing | [22 empty] | 20 | 5 | [8 empty] | 30 | 5 | [6 empty] | 70 | 5
22071 | GCDC Building 1 | 2023-09-29 | Oscar Hernandez | Installing panels on screen wall Sw and roof , and carrying material on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and boom lift | false |  |  |  |  | ACM |  | 72
22026 | CSCC - Arts & Technology | 2023-09-28 | Kevin Morris |  | JWMCD Crew | Drake De Tomasi | true |  |  |  | Rain | 2 | 6.5 | true | Acm panels, zee, hat channel, reveal, job box, fasteners, shims, etc. | Boom 60' | false
22071 | GCDC Building 1 | 2023-09-28 | Oscar Hernandez | Installing panels on screen wall Sw,installing panels on the roof and carrying material for the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift, boom lift and boom truck | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-09-28 | fredy Rodriguez | At the moment I am waiting for answers so I can start in the area of ​​stairs number 4. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | boom lif | false |  |  |  |  | Coping Corrugated / Screen wall Flashing | [22 empty] | 11 | 5 | [8 empty] | 150 | 5 | [6 empty] | 140 | 5
22071 | GCDC Building 1 | 2023-09-27 | Oscar Hernandez | 2 cutting panels, 3 installing panels on screen wall Sw, 3 installing panels on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 |  | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-09-27 | fredy Rodriguez | This day 270 feet of copíng clips were installed. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 11 | false |  | bomlif | false |  |  |  |  | Coping Corrugated / Screen wall | [22 empty] | 11 | 5 | [16 empty] | 50 | 2
22073 | Pioneer Appalachia FCU | 2023-09-26 | Kevin Morris | Took down 5 corrugated panels replaced 4 new panels and 1 old. Took down 7 soffit panels and 2 lights to replace damaged panel reinstalled soffit panels and lights. Touched up trim and panels with touch up pen | JWMCD Crew | Eric Gutierrez | false |  |  |  |  | 2 | 10 | false |  | Boom | false |  |  |  |  | Corrugated / Screen wall Soffit
23002 | QTS MAN1 DC3 | 2023-09-26 | fredy Rodriguez | At the moment I am waiting for answers so I can start in the area of ​​stairs number 4. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 11 | false |  | boom lif | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 46 | 5
22071 | GCDC Building 1 | 2023-09-25 | Oscar Hernandez | Cutting and installing panels on screen wall Sw | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift 4 boom lift | false |  |  |  |  | ACM |  | 72
22073 | Pioneer Appalachia FCU | 2023-09-25 | Kevin Morris | Boom lift was delivered. Material didn't show up until 5:30 | JWMCD Crew | Eric Gutierrez | true | Material |  |  | Drizzle | 2 | 8 | true | Replacement soffit and corrugated panels | Boom lift delivered at 10:30 | false
23002 | QTS MAN1 DC3 | 2023-09-25 | fredy Rodriguez | 140 feet of angles were installed. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 11 | false |  | boom lif | false |  |  |  |  | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 16 | 5 | [6 empty] | 210 | 5 | 180 | 5
22071 | GCDC Building 1 | 2023-09-22 | Oscar Hernandez | Cutting and installing panels on screen wall Sw | Subcontractor | Colton Tomlin | false |  |  |  |  | 8 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 64
23002 | QTS MAN1 DC3 | 2023-09-22 | fredy Rodriguez | This day they moved the stairs that were the way to go up to the roof so I could install the panels in the North area | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 11 | false |  | boom lif and Esqueford | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 28 | 5
22071 | GCDC Building 1 | 2023-09-21 | Oscar Hernandez | 2 guys was cutting panels, 3 installing steel and 3 installing panels on screen wall Sw | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  |  | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-09-21 | fredy Rodriguez | This day I had to coordinate so that they have this area ready to install panels. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 11 | false |  | boom lif and Esqueford | false |  |  |  |  | Corrugated / Screen wall Flashing | [22 empty] | 25 | 5 | [8 empty] | 60 | 5
22071 | GCDC Building 1 | 2023-09-20 | Oscar Hernandez | Cutting and installing panels on screen wall Sw , installing panels on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | 1 forklift and 4 boom lift and big scaffold | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-09-20 | fredy Rodriguez | This day we had to move our material to give space to other people. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 11 | false |  | boom lif and Esqueford | false |  |  |  |  | Corrugated / Screen wall Flashing | [22 empty] | 24 | 5 | [8 empty] | 50 | 5
22071 | GCDC Building 1 | 2023-09-19 | Oscar Hernandez | Cutting and installing panels on screen wall Sw | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-09-19 | fredy Rodriguez | On this day, material was raised to the roof and a security fence was installed to be able to work on the south side. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 11 | false |  | bomlif and Esqueford | false |  |  |  |  | Coping | [40 empty] | 110 | 5
22071 | GCDC Building 1 | 2023-09-18 | Oscar Hernandez | Cutting and installing panels on screen wall Sw | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-09-18 | fredy Rodriguez | This day we fixed 360 feet of pieces that are closed to fit together so that everything fits well. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 11 | false |  | bomlif | false |  |  |  |  | Coping | [40 empty] | 360 | 5
23014 | Moses Lexus | 2023-09-18 | Saul chicas | Today we was doing some caulking are modified one panel we walk with GC around the building to make sure everything was ok we complete Moses Lexus 100% | Subcontractor | Drake De Tomasi | [5 empty] | 4 | 5 |  |  | 2 boom lift | [5 empty] | ACM | 1 | 20
23002 | QTS MAN1 DC3 | 2023-09-17 | fredy Rodriguez | This day 80 feet of Clip were installed to install coping also 90 feet of angles. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | boom lif | false |  |  |  |  | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 33 | 5 | [6 empty] | 120 | 5 | 40 | 5
23014 | Moses Lexus | 2023-09-17 | Saul Chicas | We keep working installing panels on walls | Subcontractor | Drake De Tomasi | [5 empty] | 4 | 10 |  |  | 2 boom lift | [5 empty] | ACM | 7 | 40
23002 | QTS MAN1 DC3 | 2023-09-16 | fredy Rodriguez | This day 120 feet of Clip were installed to install coping also 100 feet of angles. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 11 | false |  | boom lif and Esqueford | false |  |  |  |  | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 21 | 5 | [6 empty] | 170 | 5 | 50 | 5
23014 | Moses Lexus | 2023-09-16 | Saul Chicas | We keep working installing ACM metal panels also we made reveal for damage panel to keep installing | Subcontractor | Drake De Tomasi | [5 empty] | 4 | 10 |  |  | 2 boom lift | [5 empty] | ACM | 18 | 40
22071 | GCDC Building 1 | 2023-09-15 | Oscar Hernandez | Cutting and installing panels on screen wall Sw | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23014 | Moses Lexus | 2023-09-15 | Saul chicas | We installed 17 ACM panels 8 panels were removed and re installed 5 panels cut and modified 2 panels reveal was made from damaged panels to complete installation panels | Subcontractor | Drake De Tomasi | [5 empty] | 4 | 10 |  |  | 2 boom lift | [5 empty] | ACM | 17 | 40
22071 | GCDC Building 1 | 2023-09-14 | Oscar Hernandez | Cutting and installing panels on screen wall Sw | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-09-14 | fredy Rodriguez | This day 110 feet of Clip were installed to install coping | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 11 | false |  | boom lif and Esqueford | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 28 | 5
23002 | QTS MAN1 DC3 | 2023-09-14 | fredy Rodriguez | This day we were working in the East area and then they moved them to the South side | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | boom lif and Esqueford | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 33 | 5
23014 | Moses Lexus | 2023-09-14 | Saul Chicas | Today we unloaded material | Subcontractor | Drake De Tomasi | [5 empty] | 2 | 2 |  |  | Fork lift | [5 empty] | ACM | 0 | 4
22071 | GCDC Building 1 | 2023-09-13 | Oscar Hernandez | Cutting and installing panels on screen wall SW | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | true | Panels for roof | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-09-13 | fredy Rodriguez | This day 280 feet of angles were also installed in this same area. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 11 | false |  | 2 bomlif | false |  |  |  |  | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 24 | 5 | [6 empty] | 392 | 5 | 140 | 5
22044 | DLR IAD 44 | 2023-09-12 | Jean negron | 3 panels were removed...today and 8 panels were installed today...f14 it's time to cut tomorrow first thing it will be...if you had one of the photos you had to see the lines you have to see something different it will be marked more information in the photos | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 | 50 | false |  | Boom lift | false |  |  |  |  | ACM
22071 | GCDC Building 1 | 2023-09-12 | Oscar Hernandez | 1 foreman for supervision and 8 guys for cutting and installing panels on SW | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-09-12 | fredy Rodriguez | This day 200 feet of angles were also installed in this same area. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 11 | false |  | boom lif and Esqueford | false |  |  |  |  | Corrugated / Screen wall Flashing Subgirt Zee | [22 empty] | 2 | 5 | [6 empty] | 308 | 5 | 220 | 5
22044 | DLR IAD 44 | 2023-09-11 | Jean negron | We removed 7 panels and installed 1...more information in the photos... | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 | 50 | true | Delivery panels… | 1 boom lift | false |  |  |  |  | ACM
22071 | GCDC Building 1 | 2023-09-11 | Oscar Hernandez for cutting panels on SW 6 for installing panels on screen wall SW | 1 foreman for supervision, 2guys w | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-09-11 | fredy Rodriguez | This day 40 feet of Coping Clip were installed. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 11 | false |  | boom lif and Esqueford | false |  |  |  |  | Corrugated / Screen wall Flashing | [22 empty] | 21 | 5 | [8 empty] | 140 | 5
23002 | QTS MAN1 DC3 | 2023-09-10 | fredy Rodriguez | This day 320 feet of Clip were installed to install coping also 560 feet of angles. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 9 | false |  | boom lif and Esqueford | false |  |  |  |  | Coping Subgirt Zee | [30 empty] | 784 | 3 | [8 empty] | 60 | 3
23002 | QTS MAN1 DC3 | 2023-09-09 | fredy Rodriguez | Im having difficulties with the coping and I'm having delays with the installation because the pieces that are assembled in the main base, the bend that it was given it is too tight and there is no space for it to fit. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  |  | false |  |  |  |  | Hat Channel Subgirt Zee | [30 empty] | 672 | 5 |  |  | 100 | 5
22055 | UVA Wise Wyllie Library | 2023-09-08 | Chad mccoy | Yesterday I made that back Two corners but one of the corners was wrong, so I had to remake it. I remade it this morning and we made all of the back panels so on the skylight this morning we made nine panels. My two guys went to go install these panels, and I laid out and prepped the four panels around the entryway. These panels also had to be built two of them were a corner that wrapped the box to the front, and it had to be laid out per joint lines in the middle of the curtainwall verticals, and then one joint in the middle of the doorway. We had to leave around break go drop the truck off to get worked on and pick up a rental truck that took a little bit of time but we got everything installed today. Tomorrow we will peel cock, cleanup and trip in a couple of little reveals. | Subcontractor | Eric Gutierrez | false |  |  |  |  | 3 | 10 | false |  |  | false |  |  | 3 |  | ACM Insulation Layout | 13 | 5 | [24 empty] | 110 | 1
22071 | GCDC Building 1 | 2023-09-08 | Oscar Hernandez | 1 foreman for supervision, 2 guys for cutting panels on SW, 6 guys was installing panels on screen wall SW | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | 1 forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-09-08 | fredy Rodriguez | Im having difficulties with the coping and I'm having delays with the installation because the pieces that are assembled in the main base, the bend that it was given it is too tight and there is no space for it to fit. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | boom lif and Esqueford | false |  |  |  |  | Coping Corrugated / Screen wall Hat Channel Other Subgirt Zee | [22 empty] | 6 | 5 | [6 empty] | 280 | 5 |  |  | 40 | 5 |  |  |  |  | 30 | 5 | 20 galvanized angles were installed. | 5
22055 | UVA Wise Wyllie Library | 2023-09-07 | Chad McCoy | We started our day, making Panels. The guys got everything ready on the ground and I went up to the roof and laid out the two slant walls. Once I got the layout of the slant walls, I brought everything down and we started making the Panels. What’s up Panels were made they were loaded up on the lull with all the hardware that we needed and the insulation and I lifted it to the roof line with the lull. We installed all the panels and insulation, and then I laid out my corners. I went down and I built both corners and we came back and we installed one of them. The other one needed modifications so I waited till the next day and I built it for installation on the next day | Subcontractor | Eric Gutierrez | true | We had pop-up thunderstorms all day, and with this brought lightning and delays, where we had to be off the roof until it was past a certain mileage |  |  | Pop up storms | 3 | 11 | false |  | Suns out guns out | false |  |  | 2.5 |  | ACM Insulation Layout | 10 | 4 | [24 empty] | 110 | 1
22071 | GCDC Building 1 | 2023-09-07 | Oscar Hernandez | 1 foreman supervision, 2 guys cutting panels and 4 installing C profile on the beams and 3 installing panels on screen wall SW | Subcontractor | Colton Tomlin | false |  |  |  |  | 10 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 80
23002 | QTS MAN1 DC3 | 2023-09-07 | fredy Rodriguez | This day they were stopped at 2 in the afternoon because there was lightning nearby. | Subcontractor | Colton Van Meter | true | lightning alert |  |  |  | 5 | 8 | true | This day I received coping and metal z. | boom lif and Esqueford | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 13 | 5
23014 | Moses Lexus | 2023-09-07 | Saul Chicas | Today we where Installation panels panels on east elevation north elevation and southeast elevation also today we have to modified another pAnel because it was to long and also we need another panel because the high it was short too I will provide a picture to many modules panels and also scratch panels the way they put the panels on the crates was not correct to much scratches and wrong panel for this project I'm working to much extra on this job | Subcontractor | Drake De Tomasi | [5 empty] | 6 | 10 |  |  | 2 Boom lift | [5 empty] | ACM | 30 | 60
22055 | UVA Wise Wyllie Library | 2023-09-06 | Chad mccoy | We started our morning with two of us making panels. Josh went to the roof to finish all green girt and to fill in screws and to seal everything with caulking. We also took 10 bundles of insulation to the roof. We made 8 typical panels and then we took them to the roof and installed them. As we installed the panels we filled in the green girt opening with insulation. It has to be double stacked to make 4 inches.we installed the panels and then I took measurements for the corners panels. We built and installed one corner prior to wrapping up. | Subcontractor | Eric Gutierrez | false |  |  |  |  | 3 | 11 | false |  | Us | false |  |  |  |  | ACM Insulation Subgirt Zee | 9 | 6 | [24 empty] | 512 | 2 |  |  | 65 | 1.5
22071 | GCDC Building 1 | 2023-09-06 | Oscar Hernandez | 1 foreman for supervision, 2 guys cutting panels and 6 guys cutting panels on screen wall NW and SW | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-09-06 | fredy Rodriguez | This day I saw a talk to the boys about work safety. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | boom lif and Esqueford | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 20 | 5
23014 | Moses Lexus | 2023-09-06 | Saul chicas | We keep putting panels on wall | Subcontractor | Drake De Tomasi | [5 empty] | 6 | 10 |  |  | Boom lift | [5 empty] | ACM | 16 | 60
23037 | Toyota of Glen Burnie | 2023-09-06 | David Placzkowski | demoed 2 panels, field fabricated 2 panels. installed 2 panels. fixed 1 sagging panel | Subcontractor | Eric Gutierrez | false |  |  |  |  | 3 | 8 | false |  | 1-(19ft)scissor lift | false |  |  |  |  | ACM | 2 | 24
22055 | UVA Wise Wyllie Library | 2023-09-05 | Chad mccoy | We traveled this morning. And we got to the site and we had to find and take a place to leave the trailer so we could have a work area. I walked the site with randy and expressed so concerns about the lack of caulking on the flashing below our panel areas. And he had the roofers fix it. So while they were fixing this we organized the trailer and location of insulation and green girt. We installed as much of the full pieces of green girt prior to ending our day. | Subcontractor | Eric Gutierrez | false |  |  |  |  | 3 | 5 | false |  | Man power | false |  |  |  |  | Subgirt Zee | [30 empty] | 280 | 1.5
22071 | GCDC Building 1 | 2023-09-05 | Oscar Hernandez | Installing panels on screen wall NW and installing panels on screen wall SW and cutting panels for SW | Subcontractor | Colton Tomlin | false |  |  |  |  | 11 | 10 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 110
23002 | QTS MAN1 DC3 | 2023-09-05 | fredy Rodriguez | This day someone came to check the boom lift, because it is still very slow. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 11 | false |  | boom lif and Esqueford | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 24 | 5
23014 | Moses Lexus | 2023-09-05 | Saul chicas | Today we keep going installing metal panels on north and west well today we also modified cut 4 panels | Subcontractor | Drake De Tomasi | [5 empty] | 6 | 10 |  |  | 2 boom lift | [5 empty] | ACM | 46 | 60
23014 | Moses Lexus | 2023-09-04 | Saul Chicas | We keep installing the panels we modified on west elevation today we cut and modified on the west elevation 6 panels | Subcontractor | Drake De Tomasi | [5 empty] | 6 | 10 |  |  | Boom lift | [5 empty] | ACM | 34 | 60
23014 | Moses Lexus | 2023-09-03 | Saul Chicas | Today we installed panels on wall we have some big issues with the north and west elevation the panels on north elevation was short 3/4 from the side of west elevation so we decide to cut them to make those paneles works I will call you tomorrow morning to explain what was the issue modified 16 panels | Subcontractor | Drake De Tomasi | [5 empty] | 6 | 10 |  |  | Boom lift | [5 empty] | ACM | 22 | 60
23014 | Moses Lexus | 2023-09-02 | Saul Chicas | We keep working installing ACM panels on wall we installed 17 panels we uninstalled 5 panels are we modified (cut) 3 panels also | Subcontractor | Drake De Tomasi | [5 empty] | 6 | 10 |  |  | Boom lift | [5 empty] | ACM | 17 | 60
22050 | LaFontaine Lansing Ford | 2023-09-01 | Chad McCoy | We started our morning peeling and caulking the right side of the main arm structure. And we worked our way down passed the icon. Once we reached where we needed to install panels at we started installing panel caps all the way to the b17 that was the wrong size from mcdougal. I made b17 out of an extra A04 and we installed it and the we installed the last cap panel and then we continued peeling the face and the caps. It’s a tight fit between the main structure and the icon but Josh was peeling that. We set our self up to do that last of the corrugated we can do out of the material we have then all I have left is two icon panels. Trip in 14 reveals and caulk about 100 linear feet and we are done for 8 weeks | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 11 | false |  | Boom scissor | false |  |  |  |  | ACM Caulking | 8 | 7 | [18 empty] | 75 | 2
22050 | LaFontaine Lansing Ford | 2023-09-01 | Chad mccoy | We continued this morning wrapping up the corrugated that we could do. After we finished the bottom we finished the top roof line and the we trimmed everything out with corners, inside and out. We moved to the acme and we started installing caps. Once we got passed the icon we stopped and started peeling and sealing what we could to finish our day. During peeling the icon. There is a roller wrinkle in the face of the panel that can not be seen in any prior to peel pictures. This dent is 8 feet up and is very noticeable. A email was sent this morning to jwmcdougal about the panel so decisions can be made. This panel will be horrible to replace | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 11 | false |  | Boom scissor | false |  |  |  |  | ACM Corrugated / Screen wall Trim | 7 | 2 | [20 empty] | 10 | 3 | [12 empty] | 180 | 2
22071 | GCDC Building 1 | 2023-09-01 | Oscar Hernandez | 1 foreman for supervision, 2guysfor cutting panels, 8 panels on screen wall NW and completing the C profile Angles on the beam | Subcontractor | Colton Tomlin | false |  |  |  |  | 11 | 8 | false |  | 1 forklift and 4 boom lift | false |  |  |  |  | ACM |  | 88
23002 | QTS MAN1 DC3 | 2023-09-01 | fredy Rodriguez | This day the crane lifted 4 loads of material from us and we prepared the area to protect the roof. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 12 | false |  | squeford | false |  |  |  |  | ACM Corrugated / Screen wall Flashing Other Subgirt Zee | [22 empty] | 16 | 5 | [6 empty] | 49 | 5 | 170 | 5 | [8 empty] | Today we installed 36 galvanized angles. | 5
23014 | Moses Lexus | 2023-09-01 | Saúl chicas | Today we continue installing ACM metal panels on walls | Subcontractor | Drake De Tomasi | [5 empty] | 6 | 10 |  |  | Boom lift | [5 empty] | ACM | 34 | 60
23017 | Nissan Picayune | 2023-09-01 | David placzkowski | installed acm panels, cap panels, peeled poly. cut and routed 3 panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 10.5 | false |  | 2 scissor lifts, lull | false |  |  |  |  | ACM | 28 | 14
22071 | GCDC Building 1 | 2023-08-31 | Oscar Hernandez | 1 foreman supervision and materials handling, , 2 guys cutting panels, 1 guy for rivets end cap , 7 installing panels on screen wall | Subcontractor | Colton Tomlin | false |  |  |  |  | 11 | 8 | false |  | 1 forklift and 4 boom lift | false |  |  |  |  | ACM |  | 88
22072 | Crain Genesis | 2023-08-31 | Jean negton | We manufacture 300 feet of trim | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 75 | false |  | 2 boom lift | false |  |  |  |  | Coping Trim | [36 empty] | 300 | 30 |  |  | 250 | 45
23002 | QTS MAN1 DC3 | 2023-08-31 | fredy Rodriguez | This day the Ups gave me some screws to use on the roof. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 11 | true | This day the Ups gave me some screws to use on the roof. | bomlif | false |  |  |  |  | Corrugated / Screen wall Subgirt Zee | [22 empty] | 22 | 5 | [6 empty] | 336 | 5
23014 | Moses Lexus | 2023-08-31 | Saúl chicas | Today we keep going installing ACM metal panels on walls | Subcontractor | Drake De Tomasi | [5 empty] | 6 | 10 |  |  | 2 boom lift | [5 empty] | ACM | 25 | 60
23017 | Nissan Picayune | 2023-08-31 | David placzkowski | installed panels, installed door trim and caulked, installed new Grey kick plate | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 10.5 | false |  | 2 scissor lifts, lull | false |  |  |  |  | ACM | 42 | 16
22050 | LaFontaine Lansing Ford | 2023-08-30 | Chad mccoy | We started our day continuing the corrugated. We continued around the side and down the back. And we started the customer side of the corrugated on the roof. As we payed out and tried to take advantage of the material that was left length wise. We down stacked the last of the 20 footers and the last 3 had a huge rip in the middle of the where it looks like the forks at some point dig into the material and made the sheets where we can only get a 6 foot and 10 foot piece out of them due to dents and the hole. So this plus the storm damaged panels is making it where we can not install 2 different walls due to no material. | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 10 | false |  | Boom scissor | false |  |  |  |  | Corrugated / Screen wall Trim | [22 empty] | 14 | 7 | [12 empty] | 40 | 1
22071 | GCDC Building 1 | 2023-08-30 | Oscar Hernandez | 1 foreman supervision and material handling, 6 guys was installing panels on screen wall NW, 2 guys was cutting panels and 2 installing brackets for panel on roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 11 | 8 | false |  | 1 forklift , 4 boom lift and 1 big scaffold on the roof | false |  |  |  |  | ACM |  | 88
22072 | Crain Genesis | 2023-08-30 |  | 15panels were installed | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 75 | false |  | 2 boom lift | false |  |  |  |  | ACM | 15 | 70
23002 | QTS MAN1 DC3 | 2023-08-30 | fredy Rodriguez | In this area on the north side, work is being done but a little slowly, because there are also people working on installing paipas on the ground. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | boom lif | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 24 | 5
23014 | Moses Lexus | 2023-08-30 | Saúl chicas | We start installing panels on west elevation and also on north elevation panel number 208-1A32 is 1 inch short also | Subcontractor | Drake De Tomasi | [5 empty] | 4 | 10 |  |  | 2 boom lift | [5 empty] | ACM | 9 | 10
23017 | Nissan Picayune | 2023-08-30 | David Placzkowski | installed acm panels, finish caulking around window. field fabricated 15 panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 10 | true | flat stock panels, kick plate, 3 boxes of caulk, stiffners | 2 scissor lifts, lull | false |  |  |  |  | ACM | 16 | 20
22050 | LaFontaine Lansing Ford | 2023-08-29 | Chad mccoy | We continued this morning on corrugated. We installed down the side of the building with all the windows and we swapped out screws as we went. We did not do the bump out bc we wanted to continue with full sheets instead of cut sheets. So we skipped the bump out and we went to the back side of the building we swapped out all the screws on the back side and then we installed the missing trim over the roll up doors and then we installed the panels over the roll up doors all the way to the cmu wall. We also installed the last of the black closure trims around the door on the second story. And the last j up the cmu wall. | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 10 | true |  | Boom scissor lift | false |  |  |  |  | Corrugated / Screen wall Trim | [22 empty] | 18 | 8 | [12 empty] | 50 | 2
22071 | GCDC Building 1 | 2023-08-29 | Oscar Hernandez | 2 guys cutting panels on NW 6 installing panels on screen wall NW 2 guys installing brackets for panel on roof and 1 foreman for supervision | Subcontractor | Colton Tomlin | false |  |  |  |  | 11 | 8 | false |  | 1 forklift and 4 boom lift | false |  |  |  |  | ACM |  | 88
22072 | Crain Genesis | 2023-08-29 | Jean negton | It began to be the extra work of the piece that was manufactured more information in the photos. 11 panels are installed | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 85 | false |  | 2 boom lift | false |  |  |  |  | ACM | 11 | 75
23002 | QTS MAN1 DC3 | 2023-08-29 | fredy Rodriguez | This day the crane lifted two loads of material from us and we prepared the area to protect the roof. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 11 | false |  | boom lif | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 20 | 5
23014 | Moses Lexus | 2023-08-29 | Saúl chicas | Today we was downloading the material that we need start installing. Also we have some panels with some scratches on it below you can see the picture of panels | Subcontractor | Drake De Tomasi | true | Missing screws and straps |  |  |  | 4 | 10 | true | ACM panels | Boom lift and fork lift | [5 empty] | ACM | 0 | 40
23017 | Nissan Picayune | 2023-08-29 | David placzkowski | installed cap panels, caulked skyward joints, prepped rest of panels for south side of building | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 8.5 | false |  | 2 scissor lifts, 1 lull | false |  |  |  |  | ACM | 5 | 6
22050 | LaFontaine Lansing Ford | 2023-08-28 | Chad mccoy | We started our morning taken down all the storm damaged panels and all the trim that was damaged in the storm. The hole west elevation of corrugated at to come down and be we worked. All the way down to the base flashing. We also swapped out over 75 percent of screws that was installed prior to going home. There are 3 different sizes of corrugated. And with the storm it damaged multible of the same size. Do I have to reconfigure where to put seams bc they will no longer match up with what we need | Subcontractor | Colton Van Meter | true | Removing storm damage panels |  |  | Sunny | 3 | 11 | false |  | Boom. Scissor | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 26 | 7
22071 | GCDC Building 1 | 2023-08-28 | Oscar Hernandez | 1 foreman supervision and moving material ,2 cutting panels and 7 installing panels on screen wall NW and layout on the roof | Subcontractor | Colton Tomlin | false |  |  |  |  | 10 | 8 | true | Panels for roof | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 80
23002 | QTS MAN1 DC3 | 2023-08-28 | fredy Rodriguez | In this area on the north side, work is being done but a little slowly, because there are also people working on installing paipas on the ground. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 11 | false |  | boom lif | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 24 | 11
23017 | Nissan Picayune | 2023-08-28 | David placzkowski | installed cap panels, cut and routed 2 panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 7.5 | false |  | 2 scissor lifts, 1 lull | false |  |  |  |  | ACM | 19 | 15
23002 | QTS MAN1 DC3 | 2023-08-27 | fredy Rodriguez | I have a boom lift, which is very slow to go down and up. | Subcontractor | Colton Van Meter | true | I have a boom lift, which is very slow to go down and up. |  |  |  | 5 | 9 | false |  | 2 boom lif | false |  |  |  |  | Other | [42 empty] | We are installing metal panels | 5
23002 | QTS MAN1 DC3 | 2023-08-26 | fredy Rodriguez | This day I gave a talk to the guys about safety at work. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 9 | false |  | 2 boom lif | false |  |  |  |  | Flashing Subgirt Zee | [30 empty] | 420 | 2 | 230 | 2
23017 | Nissan Picayune | 2023-08-26 | David placzkowski | installed panels. cut and routed 5 panels, peeled poly | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 10 | false |  | 2 scissor lifts, 1 lull | false |  |  |  |  | ACM | 12 | 10
22071 | GCDC Building 1 | 2023-08-25 | Oscar Hernandez | 1 foreman supervision 2 guys cutting panels on NW and 6 installing panels on screen wall NW | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | =forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
23002 | QTS MAN1 DC3 | 2023-08-25 | fredy Rodriguez | This day I climbed the scaffolding to the roof. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | true | They brought me a scaffold. | boom lif | false |  |  |  |  | Subgirt Zee | [30 empty] | 480 | 7
23017 | Nissan Picayune | 2023-08-25 | David placzkowski | installed acm panels. cut and routed 15 panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 10 | false |  | 2 scissor lifts, 1 lull | false |  |  |  |  | ACM | 44 | 20
22061 | 19th and Church | 2023-08-24 | Carlos Cevallos | Today we listen to the safety meeting. Milwaukee did a demonstration about their tools. We couldn’t do something else. | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 0.5 | false |  | 2 all terrain scissor lifts | false |  |  |  |  | Other | [42 empty] | Listen to safety meeting | 3
22071 | GCDC Building 1 | 2023-08-24 | Oscar Hernandez | 1 foreman , 2 guys cutting panels , 6 installing panels on screen wall NW | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 |  | true | We put all material received on the roof with boom truck | 1 forklift , 4 boom lift and boom truck for put the material on the roof | false |  |  |  |  | ACM |  | 72
22072 | Crain Genesis | 2023-08-24 | Jean negton | 9 panels were installed | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 65 | false |  | 2 boom lift | false |  |  |  |  | ACM | 9 | 60
23017 | Nissan Picayune | 2023-08-24 | David placzkowski | installed panels. cut and routed 10 panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 10 | false |  | 2 scissor lifts, 1 lull | false |  |  |  |  | ACM | 31 | 20
23017 | Nissan Picayune | 2023-08-24 | David placzkowski | installed acm panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 10 | false |  | 2 scissor lifts | false |  |  |  |  | ACM | 31 | 20
22061 | 19th and Church | 2023-08-23 | Carlos Cevallos | Today we just came to the safety meeting.. dewalt make a demonstration of their new tools. Also we los the embeds, find and plates to the truck.. we couldn’t work the whole day because we haven’t received updates about the drilling | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 6 | false |  | 2 all terrain scissor lift | false |  |  |  |  | Other | [42 empty] | Safety meeting | 6
22071 | GCDC Building 1 | 2023-08-23 | Oscar Hernandez | 1 foreman for supervision 2 guys for cutting panels and 6 guys for installing panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | 1 forklift and 4 boom lift | false |  |  |  |  | ACM
22072 | Crain Genesis | 2023-08-23 | Jean negton | 9 panels were installed | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 70 | false |  | 2 boom lift | false |  |  |  |  | ACM | 9 | 65
23002 | QTS MAN1 DC3 | 2023-08-23 | Fredy Rodriguez | All good in this job I have no problem to start. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | 2 boom lift 1 forklift | false |  |  | 2 |  | Flashing Layout Other | [32 empty] | 100 | 5 | [8 empty] | metal Z and angles were installed | 3
23017 | Nissan Picayune | 2023-08-23 | David placzkowski | installed panels, cut and routed 4 panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 10 | false |  | 2 scissor lifts, 1 lull | false |  |  |  |  | ACM | 17 | 20
22061 | 19th and Church | 2023-08-22 | Carlos Cevallos | Today we start the day 6:15 for the safety week by Yates. We listen to the safety meeting and saw a fall protection.by guardian. After that we finish drilling the metal plates from the concrete knee wall. We only could work till 11:30 because we finish the work we can do right now. Concrete scanning was supposed to come today but they didn’t, so we couldn’t drill the ceiling from 2nd floor and the concrete slab. | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 30 | false |  | 2 all terrain scissor lifts | false |  |  |  |  | Other | [42 empty] | Drilling holes for eye bolts | 30
22071 | GCDC Building 1 | 2023-08-22 | Oscar Hernandez | 1 foreman for supervision, 2 people was cutting panels, 6 installing panels on screen wall NW | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | 1 forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
22072 | Crain Genesis | 2023-08-22 | Jean negton | 9 sky panels were installed | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | false |  | 2 boom lift | false |  |  |  |  | ACM | 9 | 45
23017 | Nissan Picayune | 2023-08-22 | David placzkowski | installed panels, cut and routed 13 panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 10 | false |  | 2 scissor lifts, 1 lull | false |  |  |  |  | ACM | 26 | 20
22071 | GCDC Building 1 | 2023-08-21 | Oscar Hernandez | 1 foreman for supervision, 2 people was cutting panels 5 installing panels on screen wall NW | Subcontractor | Colton Tomlin | false |  |  |  |  | 8 | 8 | true | Material for the roof and received scaffold | 1 forklift and 4 boom lift | false |  |  |  |  | ACM |  | 64
22072 | Crain Genesis | 2023-08-21 | Jean negton | 12 sky panels were installed | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 70 | false |  | 2 boom lift | false |  |  |  |  | ACM | 12 | 65
23017 | Nissan Picayune | 2023-08-21 | David placzkowski | installed panels. 4 panels cut and routed. waited on Nissan answer about mismatched joint lines before we could proceed | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 4 | false |  | 2 scissor lifts, 1 lull | false |  |  |  |  | ACM | 3 | 8
22050 | LaFontaine Lansing Ford | 2023-08-20 | Chad mccoy | We started this morning, laying out the icon metal for the panel install. And another crew started on Jay and laying out corrugated for the screw alignment. As we were doing the icon panels, we came across like glue up that didn’t match where we’re supposed to go. So we went and found it sister panel and he didn’t match her. It was supposed to go either. So upon further Digging We came across at the glue ups or miss labeled and built incorrectly. So I notified Colton and then we broke down the glue ups and rebuilt them on site. We gave one about 45 minutes to dry and we put some extra tape on it but then I had to hang it to keep going. But with these glue ups on the section that supposed to Blair back, they were supposed to be a taper with a panel of the vertical inside the vestibule entrance. It’s supposed to taper and go from bigger to smaller butt. They did not do it at the very top to match the soffit so the part of the glue up that goes vertically up is 1/4 wider than the soffit send it bumps up to. On the corrugated we have screws that are going into plywood with a cutter on them. They are fairly crappy. I do not think that it would be 100% secure as the time goes on. I really feel like the screws need to be changed out to a 1 inch screw with no cutter on it. | Subcontractor | Colton Van Meter | true | Panels are built wrong on the glue ups. We are rebuilding name on site in the field as we go |  |  | Hot sunny | 5 | 10 | false |  | Lull boom scissor | false |  |  |  |  | ACM Corrugated / Screen wall Trim | 16 | 7 | [20 empty] | 18 | 4 | [12 empty] | 175 | 4
23017 | Nissan Picayune | 2023-08-20 | David placzkowski | installed panels. cut and routed 2 panels. realized acm join lines did not match Mullens. | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 4 | false |  | 2 scissor lifts, 1 lull | false |  |  |  |  | ACM | 7 | 8
22050 | LaFontaine Lansing Ford | 2023-08-19 | Chad McCoy | We came in this morning and we set up for closure pieces to put around were corrugated supposed to go. Please continue ACM up the column in across the back leg. What we found is as you go up the column where are the Steelers sagging? It is actually pulling the vertical steel out of level head towards the middle of where the icon instead sitting. So when you run your call, I’m wrapped up the left side impacts the steel beam in the right side, flares off the steel beam and push it where you have to run these panels somewhat out of level and I had a plum on the right hand side just to get it to seats and run up the column. We also came across two panels that did not match the height of what they were supposed to the access door panel E05 is 1 inch smaller than the rest of the panels on height and b 17 Had excessive damage to the route to the point to where the route was broken at the top. I have plenty of panels to make this panel out of due to the over fabrication of multiple panels. But over 425 linear feet of trim was ran around the whole perimeter building. Tomorrow we will run the J and start the corrugated panels, but the trim had to be done prior due to nonexistent closure pieces to cover the wood an the framing after it was subframe by others. | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 10 | false |  | Lull boom scissor | false |  |  |  |  | ACM Trim | 13 | 6 | [34 empty] | 425 | 9
22072 | Crain Genesis | 2023-08-19 | Rony | We install extra Panels requested by the GC | Subcontractor | Colton Van Meter | false |  |  |  |  | 6 | 42 | false |  | 2 booms | false |  |  |  |  | ACM | 6
23017 | Nissan Picayune | 2023-08-19 | David placzkowski | installed panels. cutting and routed 11 panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 10 | false |  | 2 scissor lifts. 1 lull | false |  |  |  |  | ACM | 22 | 20
22050 | LaFontaine Lansing Ford | 2023-08-18 | Chad mccoy | And we started our morning, putting together the steel with the bolts that I bought from Home Depot that goes up for the icon. Once this was together, we took measurements, and we went and laid it out in front of the vestibule. Once it was laid out, we stood it up with the new straps that I bought and put it in the place. After we had it in the place, Trevor marked and drilled as Halls, but the bitch that he needed would not fit through the hole in the steel so what he had to do was we had to take down the steel and be safe I laid it back down he drilled holes and then we put it back. I did not like he’s holding method that he had done to hold the steel in place so as soon as his holes were drilled, I did my own thing we anchored into the concrete with red towels that I had. Plus I tied it back to the vestibule, with through bolts into the framing.. Once this was done, we continued with a CM on the top going across. We have been adding one and a half inch Z through the bottom soffit to help hold it in place. The problem with this across the span is that the steel drops from one into the middle, and then the middle to the other end almost 2 inches. There are parts in our panels where they have to be a little bit patched due to the structure and it seems to be sagging even more with the more panels we put on .it. I really think and I’ve already told Trevor that some kind of brace or crossmember needs to be added in the middle of the structure to help hold it up and down | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 9 | false |  | Lull boom scissor | false |  |  |  |  | ACM Other | 10 | 3 | [40 empty] | Icon steel | 5
22061 | 19th and Church | 2023-08-18 | Carlos Cevallos | Today we couldn’t do much because the drill bits for the metal plates wasn’t ready and that was the only thing that we had left to do..i got the bits 11:30 and I store them at 12:00.. the GC gave us permission to work only till 3:30pm so it was no productive to start working at that time. | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 30 | true | Drill bits for metal, I pick them up from the office | 2 all terrain scissor lift | false |  |  |  |  | Other | [42 empty] | We couldn’t do nothing | 30
22071 | GCDC Building 1 | 2023-08-18 | Oscar Hernandez | 6 people installing panels on screen wall NW., 2 cutting panels on NW 1 foreman for supervision | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | 1 forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
22072 | Crain Genesis | 2023-08-18 | Rony | We had a really good day today. No issues everything went smoothly. | Subcontractor | Colton Van Meter | false |  |  |  |  | 6 | 14 | false |  | To boom lift | false |  |  |  |  | ACM | 20
23017 | Nissan Picayune | 2023-08-18 | David placzkowski | unloaded truck. did layout. installed panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 2 | 10 | false |  | 2 scissor lifts | false |  |  |  |  | ACM | 13 | 20
22050 | LaFontaine Lansing Ford | 2023-08-17 | Chad mccoy | We start our morning, continuing on the aCM wrap around the main structure on the backside. We install three ACM panels and we went down to start building the next three when I started getting lightning and storm alerts. So we can move to the vestibule entrance on the Acm Install. We got two of these installed before the storm hit. Go to installing these two panels they’re supposed to be a closer place that’s at the bottom of it that our panel sent to you in the window guys CO2 but this was not install just like the rest of the building so we installed some of the motor middle that we had so that we can have something to fill that void. We had wind gusts of 35 to 50 miles an hour with lightning strikes for 3-4 hour. So while this was going on, we cannot work due to lightning within 10 miles towing at lunch. There’s a check for a while and then when the lightning got to 10.1 or greater miles we went back to work.. Reinstalled all of the vestibule panels yet about an inch and a quarter gap at the top for some reason. Outside edge to outside edge is a Prince William supposed to be 13 foot 1 1/8 we are 13 foot one and a quarter so Nice gaps at the skyward joints that will be his behind the icon. I’m going to stay because they will be sealed with caulk he and hidden with the icon. We ended our day talking to Trevor about setting the icon how there’s a possibility that we won’t install this new noisy, but we are putting it up first thing this morning to simply saying yes, the room in between the steel in the vestibule beams Are sufficient for Glazer’s to get their install in between | Subcontractor | Colton Van Meter | true | Storms |  |  | Storms | 3 | 5 | false |  | Lull boom. 26 foot scissor | false |  |  |  |  | ACM | 14 | 4
22061 | 19th and Church | 2023-08-17 | Carlos Cevallos | Today we finish drilling all the concrete from the knee wall an the second floor and made all the layout fro the top. We had to stop working at 11:30 because we run out of the drill bit for metal and we have to wait for updates to start drilling the holes from the concrete slab. | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 48 | false |  | 2 all terrain scissor | false |  |  |  |  | Other | [42 empty] | Eye bolts | 48
22071 | GCDC Building 1 | 2023-08-17 | Oscar Hernandez | 1 supervisión,2 people was cutting panels on screen wall NW, 6 installing panels on screen wall NW | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
22072 | Crain Genesis | 2023-08-17 | Rony | We had some delays due to pass by the GC to manufacture two extra openings on the doors. They were not on drawings.. so we need to doors extra. We install nine Panos we had a fabricate flashing for doors. | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 12 | false |  | One boom lift | false |  |  |  |  | ACM | 9 | 36
22050 | LaFontaine Lansing Ford | 2023-08-16 | Chad mccoy | We started our day, laying out our first panel because it had to be cut to wrap around the steel that holds the structure to the building. We cut out where the steel was gonna be and then I cut a seam to the edge of the panel and routed them and folded them down to that we could fold them back up once the panel is in place. We had to acquire a scissor lift today due to the painters taking the boom lift. I also talked to Colton about getting a scissor lift so that we can continue in the tight working conditions that we have to do down the inside section of the structure. These panels on the backside are very hard to install some of them take three of us due to the narrow places one of us has to be in the boom one of us has to be in the scissor lift, and one of us has to be in the structure to screw it off and help hold it to engage. There’s not much room to climb up and down Inside the structure but they had to be run on the soffit middle to help hold the soffit middle up and the soffit middle did not come with Weep holes in it. They are completely full of water. I talked to Trevor and we are installing we pose as we go | Subcontractor | Colton Van Meter | true | The difficulty hanging these panels on the backside with such a narrow area is extremely hard. To the point where a lot of these, you can’t even get the impact in place to screw them off so inventive ways with 90s and reversed install had to be done to secure this panel across-the-board |  |  | Sunny 84 | 3 | 9 | false |  | Boom and lull | false |  |  |  |  | ACM | 14 | 9
22061 | 19th and Church | 2023-08-16 | Carlos Cevallos | Today we keep drilling holes for the Hilti eye bolts on the bottom and top side of the second floor. We start also drilling the concrete slab on third floor but we had to stop because of some safety issues that Yates had. Nick and Steve went to have a meeting with them to talk about it. The time we stop working was at 3:00pm but we had to stay there till 4:30pl to explain them exactly what we were doing. Also I went to pick up drill bits for concrete and metal from the office. | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 45 | false |  | 2 All terrain scissor | false |  |  | 8 |  | Layout Other | [42 empty] | Drilling and installing eye bolts | 37
22071 | GCDC Building 1 | 2023-08-16 | Oscar Hernandez | 1 foreman supervision; 2 people cutting panels and 6 installing panels on screen wall NW | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | 1 forklift and 4 boom lift | false |  |  |  |  | ACM |  | 72
22072 | Crain Genesis | 2023-08-16 | Rony | We install a total of 10 panels has some issues the flashing they sent around the door. It was about 9 inches and we cut it to 8 inches to make it work. | Subcontractor | Colton Van Meter | true | Cutting flashing to make it fit around the doors |  |  |  | 5 | 12 | false |  | 1boom | false |  |  |  |  | ACM | 10
22050 | LaFontaine Lansing Ford | 2023-08-15 | Chad mccoy | We continued running up the big wall that we had started on yesterday. We had off and on storms all day long, so it was Hitt or miss, but we ran as many panels up As we could. We cannot can’t find Panels b05 The sixth panel. I called Colton and then we all started looking for it but I did stumble across a panel that was the exact same size, but I had an access door in it but in my prince, there’s no access doors on the big structure of ACM. The access doors were added later and was never updated in the install drawings that I had and I was never told about it so we read all the panels up and captive and caulked it and finished it and then we had to take Panels back off to get to the access panel so that we could install it | Subcontractor | Colton Van Meter | true | Storms on and off and no one Told me about the access panels being swapped out from original Panels |  |  | Storms | 3 | 10 | false |  | Boom and lull | false |  |  |  |  | ACM | 12 | 7
22061 | 19th and Church | 2023-08-15 | Carlos Cevallos | Today we start or day waiting till Steve Scan the building. Then we receive the storage box and the fins. After that we start taking about the wood we previously install for the building scanning. Also we start drilling some hole with the concrete but that works fine but the drills that we buy for the metal plates they got burned so fast and we couldn’t perforate them. | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 54 | true | Storage box,3 fins | Allterain scissor lifts | false |  |  | 27 |  | Layout Other | [42 empty] | Hilti eye bolts | 27
22071 | GCDC Building 1 | 2023-08-15 | Oscar Hernandez | 2 people was cutting the panels 6 people was installing panels on screen wall NW | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | true | Angles for the panels | Forklift and 4 boom lift | false |  |  |  |  | ACM |  | 56
22072 | Crain Genesis | 2023-08-15 | Rony | We had to do Layout what’s a good day we install a total of nine Panos | Subcontractor | Colton Van Meter | true |  |  |  |  | 3 | 11 | false |  | 1boom lift | false |  |  |  |  | ACM | 9
22050 | LaFontaine Lansing Ford | 2023-08-14 | Chad mccoy | We started our morning, locating everything, prints, screws, starter panels. We forgot our tables in California. So we had to go to Lowe’s an buy new ones. Once we got back we pulled the out side back corner panels from the crate we installed the bottom wrap and then we worked the outside corner. The metal going up the outside corner is twisted and tilts out. So first we ran the panels up as square as we could only to get to the top and the cap be a inch out of square to what was installed. I then took the wall back down to the perimeter band and we worked it to the cap. It was still off a little but due to impacting steel with inside of Acm there is nothing we can do besides make the wall look way out of square to go passed steel. | Subcontractor | Colton Van Meter | true | We have to install while looking at the future panel install due to in and out of steel while trying to maintain joints |  |  | Storms in the after noon | 3 | 10 | false |  | 45 foot boom. Lull | false |  |  |  |  | ACM | 12 | 5
22071 | GCDC Building 1 | 2023-08-14 | Oscar Hernandez | 2 people was installing C profile on the beams on SW , 2 people was cutting the panels on NW and 4 people was installing panels on NW | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | true | Material for the roof | Forklift and 3 boom lift | false |  |  |  |  | ACM |  | 72
22072 | Crain Genesis | 2023-08-14 | Rony | Had a late due to missing screws. Receiving material and organizing. | Subcontractor | Colton Van Meter | true | Missing screws |  |  |  | 3 | 30 | true | Hey acm and everything to start the job |  | false |  |  |  |  | ACM | 2
22071 | GCDC Building 1 | 2023-08-11 | Oscar Hernandez | Cutting panels and installing | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | Forklift and 3 boom lift | false |  |  |  |  | ACM |  | 56
22071 | GCDC Building 1 | 2023-08-10 | Oscar Hernandez | Receiving delivery panels and counting all the panels | Subcontractor | Colton Tomlin | true |  |  |  | Raining | 2 | 8 | true | Panels | Forklift | false |  |  |  |  | ACM |  | 16
22071 | GCDC Building 1 | 2023-08-09 | Oscar Hernandez | Cutting panels and installing panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  |  | false |  |  |  |  | ACM |  | 56
22071 | GCDC Building 1 | 2023-08-08 | Oscar Hernandez | Takes down the panels already installed and cutting panels | Subcontractor | Colton Tomlin | false |  |  |  |  | 5 | 8 | true | Panels | Forklift and boom lift | false |  |  |  |  | ACM
22071 | GCDC Building 1 | 2023-08-07 | Oscar Hernandez | Receiving panels delivery, hanging metals | Subcontractor | Colton Tomlin | true |  |  |  |  | 5 | 8 | true | Received panels delivery | Forklift and 3 boom lift | false |  |  |  |  | ACM |  | 40
22071 | GCDC Building 1 | 2023-08-04 | Oscar Hernandez | Drilling holes on the beams and hanging metal SW | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  |  | false |  |  |  |  | ACM |  | 56
23013 | Carvana San Diego | 2023-08-04 | Chad mccoy | Today we came in and started finishing trim under canopy’s. Even though the painter wasn’t finished. Then we peeled everything and we sealed the main buildings skyward joints Then we put all extra material in a crate and put it in a covered bay. The boom was cleaned out and filled up with gas. We kept the screws and caulking so it didn’t walk away. | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 5 | false |  | 86 foot boom | false |  |  |  |  | ACM | 1 | 1
22071 | GCDC Building 1 | 2023-08-03 | Oscar Hernandez | Drilling holes on the beams and hanging metals SW | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | 1 forklift and 3 boom lift | false |  |  |  |  | ACM |  | 48
23013 | Carvana San Diego | 2023-08-03 | Chad mccoy | We started our morning moving Acm and caps to the unfinished canopy so we could finish installing Acm today. We installed the perimeter panels and then we installed the caps. After all this was installed we ran some of the trim underneath. We could not finish due to the painter not being finished. So after we insrtalled as much as we could. We started peeling and caulking skyward joints and general clean up | Subcontractor | Colton Van Meter | true | Painter is not painting the structures ahead of usn |  |  | Lousy | 3 | 10 | false |  | 86 foot boom | false |  |  |  |  | ACM | 34 | 6
22071 | GCDC Building 1 | 2023-08-02 | Oscar Hernandez | Drilling holes on the beams and hanging metals | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 72 | true | Panels | Forklift and 3 booms lift | false |  |  |  |  | ACM |  | 72
23013 | Carvana San Diego | 2023-08-02 | Chad mccoy | We started our morning getting all the Acm caps for the left canopy. We laid all the caps out and made sure all were accounted for . Then we started installing. Once all the caps were in we started peeling. We peeled until josh was done sealing the tops of the canopy and finished putting the screws in them. Once josh was done. We moved to the one soffit panel that was left out. It was laid out and installed The flashing that was installed did not incorporate the stucko build out. So when panels are replace the trim must be replace to incorporate 4 inch voids. I put little cut pieces in there but I don’t not like them. Once the soffit was completed we made two more horse shoe panels for the top and peeled one inward section to see what it looks like finished . | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 12 | false |  | 86 foot boom and 19 foot scissor | false |  |  | 1.5 |  | ACM Layout | 23 | 9
22071 | GCDC Building 1 | 2023-08-01 | Oscar Hernandez | Drilling holes on the beams and hanging metals SW | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | 1 forklift and 3 boom lift | false |  |  |  |  | ACM |  | 72
23013 | Carvana San Diego | 2023-08-01 | Chad mccoy | We started our ,owning taken panels off so the framer could fix his canopy that is 1 inch or better out of plum, over 2.5 feet. Once that was done we continued installing on the tower. We wrapped the rest of the back and made 4 panels that installed in the.horse shoes. These panels are roughly 3.5 - 4.5 inches short on each side. Once the back was installed we moved around front and started installing the soffit panels. We did not get all three bc I have to figure out how to Ayacucho the last soffit with all the trim in place. The trim makes it where we can not do started track or screws thru the clips. I will figure it out this evening. | Subcontractor | Colton Van Meter | true | Panels had to be removed so that framing could be fixed on one canopy. |  |  | Partly cloudy. 85 | 3 | 10 | false |  | 86 foot boom and scissor lift | false |  |  | 2 |  | ACM Layout | 16 | 8
22071 | GCDC Building 1 | 2023-07-31 | Oscar Hernandez | Drilling holes on the beams and hanging metals SW | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 |  | false |  | Forklift and 3 boom lift | false |  |  |  |  | ACM
23013 | Carvana San Diego | 2023-07-31 | Chad mccoy | We started our morning Consolidating crates and cleaning up the yard. We put elevations of certain Panels in certain crates and we moved those crates to the areas we were working. The flat stock material was also moved where we were working due to us, having to have that material to make new panels. We were going to start on the last canopy with a 15 foot panels today so we brought the 215 foot panels around and we install the first panel off the boom lift and scissor lift. But there’s another side of the canopy that is an inch out of plum so absolutely nothing can be installed on this canopy until the structure is rebuilt. The reason nothing can be installed is because there is a piece of trim that goes on the back that the panels and the wood have to be perfectly in line or the trim will not work and there’s no point of us putting the panel on. This is also the canopy that is not painted yet, so no matter what the trim cannot go on until it’s painted and the substructure is fixed. So once we cleaned up this area after we figured out, we could do it. We move to the last panels on the bottom row. Wheezy and insulated the rest of the section and then we hung the first panel Off the corner. After this panel was hung, I had to lay out and cut out the scupper. What’s the scupper was laid out we had to build a little valley, so the water doesn’t leak in between the drywall insulation and waterproofing. This will keep the building dry. After this panel was done, we had to build and install three more panels. This took the last of our flat stock so now we just have older panels that are too tall and pieces of four sheets that we could possibly make new panels out of. Once we finished with this wall, we went to the high back part of the tower and we started running flashing. Once the flashing was completed we started running corner panels and the back perimeter panel, and we ended our day on the upper part of the Tower | Subcontractor | Colton Van Meter | true | The canopy with the areas that are at a plumber going to be a hindrance due to we do not know when they’re gonna be fixed and they cannot be painted until they are fixed |  |  | Partly cloudy | 3 | 12 | false |  | 86 foot boom scissor lift | false |  |  | 0.5 |  | ACM Insulation Layout Subgirt Zee Trim | 24 | 10 | [24 empty] | 75 | 0.5 |  |  | 60 | 0.5 |  |  |  |  | 90 | 1
22071 | GCDC Building 1 | 2023-07-28 | Oscar Hernandez | Drilling holes on the beams SW | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 |  | false |  |  | false |  |  |  |  | ACM |  | 72
23013 | Carvana San Diego | 2023-07-28 | Chad mccoy | We started our morning, Pulling the upper tower panels so that we can try and knock it out as much as we can today. We have concrete that’s gonna be poured next Monday or Tuesday so we have to get as much done on the face of the buildings as we can, where the concrete is not because we will not have access to those areas later on. So blue flashing has to go down of the curtain wall around the perimeter of the upper part of the tower so this is a little bit tricky due to curtain wall mounting brackets protruding through sealant areas from the curtain wall. These have to be snipped around so that the flashing sets proper. During layout of the upper sections, we have found that joint lines do not match up with curtainwall. This is pretty much running the same everywhere when it comes to a joint line matching up with a window, Molien or window joyed they have been equally 1 ½ to 2 inches Off the joints, and the panels are short, the panels protrude past the joints. So when we try to line up the first corner to make it match the joint and go down the wall, we discovered that the last corner panel that attaches to the face Panels is now short what we cheated that corner to make it lined up so there’s an inch and a half to 2 inch bust pretty much on all joints and have to line up with curtain wall joints. It doesn’t matter which side we start on when it comes to the corners if we do a proper quarter inch shim behind the panels and run the Panels down the way it supposed to nothing lines up one side of the corners Hass to be an inch to an inch and a half off the wall and then you have to cheat the joints to make it lineup and then you half to figure out how to make the last corner stretch to even work. Another bus that we found was the inside panel that looks like a horseshoe is 2 inches to 2 1/2 inches short from the corner panels that have to be slammed just to make the Panels go to the closest proximity of each other, all 8 of the horseshoe Panels Will have to be made | Subcontractor | Colton Van Meter | true | The sheer amount of panels that have to be made modified or tweaked in position on this job is ridiculous. There might be a fifth of panels that are supposed to line up with a certain spot that actually do the rest of them blow past the joint lines to the point where if you cut it back to make it work it’ll screw other panels up further down the wall. I don’t know if system depth was either Not taken in consideration, or was doubled and added in certain spots, but something needs to be looked at and went over with the field dimensions that were taken by the team that came out, compared to what was put into production |  |  | Overcast 89 | 3 | 10 | false |  | 19 foot scissor lift. 86 foot boom | false |  |  | 1 |  | ACM Flashing Layout | 26 | 7 | [30 empty] | 120 | 1
22071 | GCDC Building 1 | 2023-07-27 | Oscar Hernandez | Installing the angles 2x2 and we drilling holes on the beams on SW | Subcontractor | Colton Tomlin | false |  |  |  |  | 9 | 8 | false |  | Forklift and 3 booms lift | false |  |  |  |  | ACM |  | 72
23013 | Carvana San Diego | 2023-07-27 | Chad Mccoy | We started our morning, prepping Panels and getting everything ready to finish up one of the canopies on the ACm wrap. We had four ACM panels that need to be installed now. The only thing left on this canopy to do is the trim underneath and the coping around the top. After we did those four panels, we moved to the main structure and we started installing panels above the curtain wall to the sliding door. The corner panel, which is 12 foot long had to have a cut out in it that would protrude around a Steel support structure for assign. The smallest part of the structure is 4 inches in diameter. The biggest part is almost 9 inches. So to make this work, we cut the main part out for the inside beam but I routed another inch and a half and folded it outward so that everything could fold away put the panel on snip a little bit for the pieces back up and it would take over some of the hole that was left from the initial cut. We were going to continue around The building in this manner, but there was mini excavators, literally digging right next to the building and per safety/OSHA regulations. I’m not allowed to boom over the knuckle parts of a actuating excavator so we packed it up. We moved to the other side of the building and we started doing the canopy on the other side of build. We said our first panel and we started going down parallel with the building side, but on the third panel of this section, the substructure itself was out of plum 1 inch and an eighth We got a hold of the GC and we let him know what we were coming across. He got a hold of the subframe guys and they said they cannot come out and fix it until Monday. There’s another spot on the same canopy that is not waterproofed. This section was hit by a dump truck and con caved in, and the same individuals that need to fix the out of plum Subframing is the ones that fixed the dump truck damage. The problem with what they fixed is that it is not waterproofed, so we cannot continue with two sides of the canopy due to poor craftsmanship and missing waterproofing. So once we got as far as we can go on the canopy, we wrapped up for the day. On the same canopy on the underbelly of it none of it’s painted so we cannot put the trim around the inside perimeter due to lack of painting | Subcontractor | Colton Van Meter | true | The boom lift was switched out today because the United maintenance guy that checked it said that it had a engine harness failure code |  |  | 90 partly cloudy | 3 | 10 | false |  | A scissor lift, and a boom lift at 86 footer | false |  |  | 1 |  | ACM Insulation Layout Subgirt Zee | 18 | 7 | [24 empty] | 50 | 0.5 |  |  | 40 | 0.5
22071 | GCDC Building 1 | 2023-07-26 | Oscar Hernandez | Installing panels NW Material handling | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | Forklift and 3 boom lift | false |  |  |  |  | ACM |  | 56
23013 | Carvana San Diego | 2023-07-26 | Chadmccoy | We start our morning pick it up where we left off yesterday. We had to make one panel to replace the small panel that was installed for demonstration. This panel is a corner panel so not only do they have perimeter routes, it needs a route 16 inches in the panel that turns the corner. Once this was done, I heard from Colton and Colton gave me the news on a big portion of the Panels and he asked us to try and get dimensions to see what else was going to fit and work. So we cleaned up what we were doing and we started pulling panels for the upper top of the tower. But upon getting to the Tower, from where we could reach due to the other side of the concrete, not being cured enough and mounds of dirt around front and gravel not letting us get close enough to the building with a straight boom to reach where we need to go, we were limited to where we could set up to reach the upper part of the Tower. Upon arrival of the upper part of the tower, we noticed the upper part of the curtain walls were not sealeD.. So I let Colton know and then I went and talked to the curtainwall guys to figure out what was going on. Not only did they say they had to finish sealing it, but they had to put a ceramic beauty cap around the entire thing and if we did any flashing of any sorts in these areas, the flashing will impede the ceramic areas that needed to be installed. So, yet again, we pulled off another section to go to the lower canopy. To our surprise, the canopy actually fits on the dimensions that they were made to. The only hiccup on the canopy is that plywood was used in areas that did not need to be plywood. The plywood is also not even with the soffit piece of these canopies so when you put the panels and then you can put the trim piece on, But the trim piece follows what the plywood does. There is no variance in this area to make it nice and pretty and smooth the plywood in spots protrudes out way past what it supposed to and then another spot it sinks in. this is going to be a problem area, I do not feel like the trim that we are adding underneath the canopy will be excepted nor do I feel that the attachment screws that the GC said that we should do will be accepted either. But we did one side of the trim and then we continued hanging panels around the canopy. I left my boom in place in the front of the building to go ahead and tell everybody that that’s where we’re working tomorrow in the morning and I don’t care what they have to say | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 12 | false |  |  | false |  |  | 2 |  | ACM Layout Trim | 14 | 7 | [34 empty] | 60 | 1.5
22071 | GCDC Building 1 | 2023-07-25 | Oscar Hernandez | Hanging C profile, installing panels NW | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | Forklift and 3 boom lift | false |  |  |  |  | ACM |  | 56
23013 | Carvana San Diego | 2023-07-25 | Chad mccoy | We started our morning, going through the crates and pull it out Panels that we needed for the sections while we are waiting approval on the Rockwool. We got the approval on the Rockwall we OK to the GC and we started hanging Panels. We started in the A panels at the back of the building and walked away to the front of the building. With these panels Z Has to be installed top and bottom on the wall and then he also have to be installed in 2. 12 inch pieces at the vertical joint where the panels meet each other so that we can attach each panel in the joints as well. After this we have to insulate everything that is touching the section of the building that he’s got an AC unit go into it. What is Z and insulated The panels are laid out. The panels are built with the clips, the Panels install. At the back of the building where the rollup door is, the blue trim was installed to a certain point past the rollup door. This was superseded by the GC, and even more had to be cut off so by cutting this flashing off we now have to cut and route the two panels that come close to this section so that the curtain wall that’s going right upside the Eephus can I have a proper joint. Panels were swapped in two spots for 805 and 803 due to lining up with the window 805 lined up better than a 03 because I have three was 4 1/2 inches too long so this was confirmed with Colton and approved prior to doing it Once we got done with the a side section that we could reach off the scissor lift in the boom, we went to the F side section. We pulled all of these panels and started doing the exact same thing we did on the eighth but when we installed our first F size panel we came across a size difference in these panels of an inch and a half. All these panels on this backside of the building where the trim was installed previous to the panels being installed was all supposed to be the exact same size. So not only are the panels too short but now I have to make every single one of these panels out of the flat stock that I have. When it comes to other sections that can be worked, or needs to be worked as you go around the building, you find the access to these areas are limited or they have a certain date that we can get on them and work on them due to concrete The GC says that we can get on one side of the concrete tomorrow to start working as hard as we can with the boom lift. The next side will have to be either Friday or worst case scenario next Monday | Subcontractor | Colton Van Meter | true | This job is riddled with delays with issues with screwed up walls or panels, wrong size or complaints from the GC on the insulation plus areas that we need to work that we are limited on access due to the bill is not being able to be on certain areas plus there are mounds of dirt gravel rocks everywhere on the front of the building. And now we’re having to make Panels because they’re an inch and a half short. It’s just like every time we turn around. Somethings either screwed up her wrong or it needs to be justified on while we’re doing it. |  |  | Partly cloudy, 94 | 3 | 12 | true | Scissor lift | 86 ft straight boom. 19 foot scissor 5 k lull | false |  |  | 1.5 |  | ACM Insulation Layout Subgirt Zee | 10 | 5 | [24 empty] | 150 | 1.5 |  |  | 320 | 2
22071 | GCDC Building 1 | 2023-07-24 | Oscar Hernandez | Drilling holes and hanging C profile on NW | Subcontractor | Colton Tomlin | false |  |  |  |  | 7 | 8 | false |  | 1 forklift 3 boom lift | false |  |  |  |  | ACM |  | 56
22071 | GCDC Building 1 | 2023-07-21 | Oscar Hernandez | Drilling holes and hanging C profile NW | Subcontractor | Colton Tomlin | false |  |  |  |  | 6 | 8 | false |  |  | false |  |  |  |  | ACM |  | 48
22071 | GCDC Building 1 | 2023-07-20 | Oscar Hernandez | Drilling holes at NW and hanging C profile | Subcontractor | Colton Tomlin | false |  |  |  |  | 6 | 8 | false |  | Forklift and 2 boom lift | false |  |  |  |  | ACM
22071 | GCDC Building 1 | 2023-07-19 | Oscar Hernandez | Drilling holes on the beams and installi C profile | Subcontractor | Colton Tomlin | false |  |  |  |  | 6 | 8 | false |  | 2 boom lift and magnetic drill | false |  |  |  |  | Other | [43 empty] | 48
22026 | CSCC - Arts & Technology | 2023-07-18 | Keith Dukarm | Went to shop this morning to load up material then headed to cscc..got there got situated and started framing for panels once we got them on I caulked them and we headed to utc | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 | 9 | false |  |  | false
22071 | GCDC Building 1 | 2023-07-18 | Oscar Hernandez | Drilling holes on beam and receiving materials | Subcontractor | Colton Tomlin | false |  |  |  |  | 6 | 8 | false |  | Forklift and 2 boom lift | false |  |  |  |  | ACM |  | 48
20067 | BNA PROJECT 5 | 2023-07-17 | Zarur Nazario Padron Jr | Working on Airway and Large Wall | Subcontractor | Marc Ribar | [5 empty] | 3 | 30 |  |  | Boom lift | [5 empty] | Other | [42 empty] | Installed 80 ft of flashing and put in 2 caps on Airwave | 30
22071 | GCDC Building 1 | 2023-07-17 | Óscar Hernández | We drilled some hole on north West | Subcontractor | Colton Tomlin | [5 empty] | 6 | 8 |  |  | Forklift and boom lift |  |  |  | 48 |  | ACM Layout Perforated
22073 | Pioneer Appalachia FCU | 2023-07-17 | Keith Dukarm | Went this morning and finished up caulking and walked with GC he seemed pretty happy ..got done and cleaned up and left | JWMCD Crew | Eric Gutierrez | false |  |  |  |  | 2 | 2 | false |  |  | false
22073 | Pioneer Appalachia FCU | 2023-07-16 | Keith Dukarm | Installed panels that we glued up . Hanging something correct to somthing thats not close is difficult but I made it work looks pretty good compared to what was on there . GC was pleased . We put a trim piece in front where panels where different sizes. Looks good put trim flashing up on inside and also caulked the windows.. | JWMCD Crew | Eric Gutierrez | false |  |  |  |  | 2 | 10 | false |  | Boom lift | false
22073 | Pioneer Appalachia FCU | 2023-07-15 | Keith Dukarm | Got to work talked to GC then started a plan how to take panels down to fix. We had to come from top down to get them off..took bout an hour and half to get down they where so out of walk they just locked together. Once they where down we had to take trim off to get it prepared to move over some to split the difference. After that we started to cut and modify panels they are glue ups. That took us bout 2 to 3 hrs . Finally got them glued up and then we moved 2 panels that where on the corner moved them up bout 2 inches. Oh we fixed another panel in the drive through that did not line up with the one beside it . Tomorrow if glue is dry we will install and continue to fix other problems | JWMCD Crew | Eric Gutierrez | false |  |  |  |  | 2 | 10 | false |  | Boom lift | false |  |  |  |  | ACM
20067 | BNA PROJECT 5 | 2023-07-14 | Zarur Nazario Padron Jr | Working on South IAF and North IAF | Subcontractor | Marc Ribar | [5 empty] | 3 | 30 |  |  | N/A | [5 empty] | Other | [42 empty] | Installed flashing and also removed flashing | 30
20067 | BNA PROJECT 5 | 2023-07-14 | Zarur Nazario Padron Jr | Working on Airwave | Subcontractor | Marc Ribar | [5 empty] | 3 | 30 |  |  | Boom lift | [5 empty] | Other | [42 empty] | Put up some overly roof panels and caps on north and south side of Airwave | 30
21071 | Google NBY-HUB 1 | 2023-07-14 | Chad mccoy | We started our morning in our badges they were hooked up to the trailer they loaded everything. We need it on the trailer and then we pulled to the closest point to where we had to work. We put the plywood back on the plants. We put the scissor lift back on the plywood and we started installing panels over the vegetation. We installed five soffit panels and then I had to go to facia panels and trim to make sure all that was done prior to any more soffits due to the limited access once the soffits are in place We installed all the panels up to the wall over the vegetation and then we started doing the trim. With the limited supply of the cut down trim, we stopped what we were doing over the vegetation, and we moved to the door section and installed all those panels. We did this so that we could use the four pieces of trim over the door and if we have to I can use spiced pieces of trim over the Vegetation. A lot of the soffit panels when you bring the Panels down into the slope or pitch of the beam. You have to cut and trim the edge of the Panel. Where the theme is because you cannot go up far enough to engage the Panels on the clips. Once we put our panels in place, we do our joints and then we throw some old screws and we caulk a lot of the clips to the track. We installed all the soffits today so all we have to do tomorrow is trim them out. | Subcontractor | Steve Fudge | false |  |  |  |  | 3 | 12 | false |  | 2 scissor lifts | false |  |  | 2 |  | Flashing Layout Perforated Soffit Trim | [32 empty] | 50 | 1 |  |  | 100 | 1
22071 | GCDC Building 1 | 2023-07-14 | Oscar Hernandez | Safety orientation and receiving material and tools | Subcontractor | Colton Tomlin | false |  |  |  |  | 3 | 24 | true | Panels ,steel angles screws and drills | 1 forklift and 2 boom lift | false |  |  |  |  | ACM
20067 | BNA PROJECT 5 | 2023-07-13 | Zarur Nazario Padron Jr | Working on Airwave Area C | Subcontractor | Marc Ribar | [5 empty] | 3 | 30 |  |  | Boom lift | [5 empty] | Other | [42 empty] | Put up 40 ft of caps on Overly Roof panels and 30 ft of flashing | 30
21071 | Google NBY-HUB 1 | 2023-07-13 | Chad mccoy | We started our morning with a late start. I didn’t get back in from Nashville till 5:20 in the morning. So we didn’t get to google till around 9 am. We started by setting up the baker scaffolding and putting it in the foliage so that we could continue with what we were doing on removal of the soffit panels. But amongst removing soffit panels, google affiliates, watched us on the scaffolding, and they did not like what we were doing. What I was doing was I have to crawl into the ceiling to unscrew these panels these panels are screwed through the clips through the track on the backside of the panel on some of these panels or 3 feet wide so you have to get pretty far in there to make this work. After we did a couple panels and removed a couple of sprinkler systems caps, google came out with Walter and talk to us about our safety at this time Walter told us that we needed to do a updated action plan that needed to be approved through DPR and Google before we could proceed so we shut down until everything was approved. Nothing got approved until a little bit after 4 PM my time. So we literally sat there waiting and once we get the approval to put the plywood on the plants and that we were not liable for these plants, we removed all the soffit panels, so there was no need to get into the ceiling tomorrow besides with our hands to simply attach our panels in the same manner, the previous ones are attached | Subcontractor | Steve Fudge | false |  |  |  |  | 3 | 10 | false |  | 2 scissor lifts | false |  |  |  |  | ACM | 0 | 0
20067 | BNA PROJECT 5 | 2023-07-12 | Zarur Nazario Padron Jr | Working on Airwave Area C | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | Boom lift | [5 empty] | Other | [42 empty] | Put 90 ft of caps on Overly Roof panels | 40
20067 | BNA PROJECT 5 | 2023-07-11 | Zarur Nazario Padron Jr | Working on Airwave Area C | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | Boom lift | [5 empty] | Other | [42 empty] | Installed 100 ft of caps on overly roof panels | 40
20067 | BNA PROJECT 5 | 2023-07-10 | Zarur Nazario Padron Jr | Working on Airwave Area C | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | Boom lift | [5 empty] | Other | [42 empty] | Installed 90 ft of caps onto the Overly Roof Panels | 40
21071 | Google NBY-HUB 1 | 2023-07-10 | Chad mccoy | We start our morning getting our badges and getting through the gates so that we could start our day. We Hooked up to the trailer and we started loading all the material we needed to start Installing Z for furring down the ceiling and Panels to put on the ceiling after it’s adjusted and trim to put on the panels after their install. We continued installing the to the ceiling so that they would drop the ceiling down to the right elevation. Once we did multiple sections, we started laying out the Panels for cuts so that we could modify the Panels to go back. On the reason the Panels had to be cut was because when you drop the sealer down, eating crouched on the wood beams in the panel would not engage unless you cut an additional inch and a quarter off so you can go up and then in and then back down. As we were installing panels, we were going in the ceiling and securing the Panels with screws through the clips and we were caulking the clips that we could not get screws or fasteners in that way. There was multiple points on every soffit panel that has a hard attachment of some kind. So the soffit ended up having 45 screws and 4 to 5 clips with sealant on them attaching them to the Track systems. The Sprinkler guy was with us all day. Once we got Panels up, he was adjusting the sprinklers to the holes and putting the caps on. Once we got so many sections done on the little canopy soffit, we started trimming out around the perimeters to try an end or complete sections as we went instead of having a jump back-and-forth and back-and-forth. With each track system, there is multiple sections where the tracks have five or six screws, attaching it to the original soffit build out or structure. What we have came across is that the 5/16 screws that are screwed into the drop ceiling light duty track. Once you take them out and try to put them back in the hole is pretty much stripped. Multiple sections have to be reattached or there has to be another way that you could screw this off where it pulls through, Simply because of the weight we’re adding to the sections I do not feel comfortable with how everything is tied together, so we are trying to go above and beyond to make everything locked together and safe. We were at later tonight trying to get as much done as we can since I’m not gonna be here on Wednesday. We’re also going to work late tomorrow and we’re going to work late Thursday and Friday just to make sure everything is squared away except for the penetration mall and the soffits adjacent to it due to the penetrations not being removed and the order not being compliant with for the shut down of the door this is gonna have to happen after my California job and it’s gonna have to start Friday morning and end Sunday evening that way I have all weekend to block the store and I do not have to worry about people coming and going. | Subcontractor | Steve Fudge | true | Each time we got to a sprinkler panel and after it was secure, the sprinkler guy had to go up and do his work. This was 20 to 30 minutes per Sprinkler we got to for Sprinkler’s today. |  |  | Clear 88 | 3 | 13.5 | true | Z for the ceiling with higher slopes. | 2 scissor lifts | false |  |  | 3 |  | Layout Subgirt Zee Trim | [30 empty] | 180 | 3 |  |  |  |  | 65 | 2
21071 | Google NBY-HUB 1 | 2023-07-08 | Chad mccoy | We start our morning getting our badges and getting through the gates so that we could start our day. We Hooked up to the trailer and we started loading all the material we needed to start putting the trim in the facia all back. We do not have all new panels for the facia on the north canopy. So some panels have to be reused, but these panels that have to be reused have to be plug and played in the certain places due to the fact that previous installation has either damaged the face or the panels are too short. So we started At the corner from the vegetation and work their way to the door with the flashing and then once we got to the door with a perforated flashing and the L Metal, We started laying out from the previous soffit install so we can install and determine the links and specific placement for the facia panel joints to line up with the new/old soffit when it goes back. By installing the new L metal and the perforated metal and matching it with the top of curtain wall like we did on the previous canopy across the way that drops the opening of the facia panel down an inch and a half so the entire track system along the entire facia perimeter must be dropped to match all the way around. On the previous install, there were multiple panels that had multiple issues either. The panel is too short or the cuts were wrong or the faces were broke or scratched or there was some kind of issue with a lot of these panels. And again I know I already stated it but we did not get all of the facia panels on this order so there’s a lot of Panels that I have to make from previous facia panels to feel these voids where they meet somewhat under the beam. So we started installing and moving the tracks from the door to the corner. When we got to the corner, I turn the corner and put one more piece of perforated as we were riveting and fixing gaps with sealants, and making it like it is on the other canopy security came out and told us that lightning with 6 miles away with a severe thunderstorm coming our way and we needed to shut down. There is no easy shut down at Google once you shut down, you have to shut down so due to the time we went ahead and we ended our day. Again today we did not receive any Z they were supposed to be coming in a sprinter van and we did not have anybody working on the penetration wall | Subcontractor | Steve Fudge | true | We were shut down by weather today, due to lightning and a severe storm |  |  | Cloudy storms | 3 | 6.5 | false |  | 2 scissors lifts | false |  |  | 3 |  | Layout Perforated Trim | [36 empty] | 50 | 2
20067 | BNA PROJECT 5 | 2023-07-07 | Zarur Padron | Working on North | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | Boom lift | [5 empty] | IMP Other | [8 empty] | 6 | 32 | [32 empty] | Installed flashing on border of the panels and cleaned panels | 8
21071 | Google NBY-HUB 1 | 2023-07-07 | Chad mccoy | We start our morning getting our badges and getting through the gates so that we could start her day. Yesterday after work, we went and bought another section of bakers Kathleen, so that I can have to complete tears to reach the soffit to take it down. The soffit next to the wall that we are working on Hass to come down because this wall is being pushed out 3 inches so I need to take the soffit down because the wall Panels are going to protrude in the face of the panel of the soffit. So we continued building panels and cutting them down to go all the way up to the wall to the very top panel. Once we were at the top panel, we’ve been had to figure out how to take the soffit down. The soffit does not slide up and down like it’s supposed to. The previous installers went in to the crevice of the soffit and put screws in makeshift brackets into the holding brackets of each soffit panel, so that they are in a fixed position and screwed from the inside. At the time of installation, these were installed off boom lifts. It is very very difficult to reach the screws off a scaffolding. We got the soffit panels down and we finished hanging the wall all the way up and finish trimming it out. Once this was done, we moved to the scissor lift, and we started taking the soffits and the facia panels and the trim down from the corner to the door. As we continue taking Panels down, it was more and more difficult to reach the sections that had the screws it up due to the limited space in the amount of screws and the distance from where we could go into the soffit and reach without putting our complete body weight on the already stressed structure. We took 30 panels down +60 feet of flashing over the curtain wall. Then we cleaned up and we left for the day We still have not seen any activity on the wall next to the north entry with all the penetrations this is going to directly affect us when it comes down to the end of work, and when myself and my team needs to go to California | Subcontractor | Steve Fudge | false |  |  |  |  | 3 | 9 | false |  | 3 scissor lifts. 1 lull | false |  |  | 2 |  | Flashing Layout | [32 empty] | 25 | 1
20067 | BNA PROJECT 5 | 2023-07-06 | Zarur Padron Jr | Working on North side | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | Boom lift | [5 empty] | Other | [42 empty] | Removed the sheathing from the wall and cleaning panels | 40
21071 | Google NBY-HUB 1 | 2023-07-06 | Chad mccoy | We started our morning getting our badges so that we could get on to the site. Once we got on site, we had to figure out where we’re gonna park the truck in the trailer so that we didn’t have to walk a super long distance for tools and material. After that, we went to the back corner and realize that the scissor lift and the lull is still in the worksite. We pulled around and we set up the baker scaffolding, the vegetation underneath. It is a lot to work around, but we made it work. I took pictures and videos of the vegetation. There was some already down. The baker scaffolding set up on plywood to keep the wheels from digging in the dirt. Once this was erected, we started dismantling The wall by taking the white trim off, and then the panels and then the base metal. Once the whole wall is down, we started looking at the soffit to see if we could take it down right above us, but the soffit panels have yet to be determined what is holding them in place we attempted to move these panels by hand. We also tried prybars, dead, blows, and other means of leverage. Within ventured to other section of the soffit, so that we could see if there was multiple panels like this and each section has 2 to 4 panels that will not move. After that, I measured one of the beam gaps because it looked pretty big and it measured 4 inches. Disease that we brought is only 2 inches so after measuring multiple soffit panels to beam, we noticed that there is a variance that grew and shrink, depending on the way that you went from each triangle to each triangle. We got a hold of Steve and Steve wanted us to measure The distance from the original wood soffit to the track bottom that held the subframing in place. Subframing is out of level from each other from triangle to triangle. The furthest side next to the wall with vegetational has to be for Dan., 4 inches and a quarter. And then as you measure going around the canopy, the distance drops to 3 1/2 3 1/4 3 inches 2 3/4 and 2 ½. So this was told is Steve and Steve has made some Z that is specific for each section. After this was taken care of, we did further inspection on the wall we just took down we installed to Panels with a taper going up. This took the panels out of square, and it made it look like crap. So we took everything back down the west elevation has referred out almost 3 inches 3 1/4 on the right hand side the left-hand side next to the court mall is 2 1/2 2 3/4. This variance is determined by the outer edge of the Mullen cap furthest away from the wall. Before proceeding, I had to get this okayed through DPR due to it covering that cap. If they did not OK, it which they did, the only other option was to take the white panels down and cut them. In the midst of doing this wall and getting approval, we got shut down by lightning twice for about 2 1/2 hours. There is a lot more to this little wall and canopy then imaginable each independent triangle has its own depth that it must reach each wall Hass to be furred out, two-tone depth as well. One more even is going to have to include a taper that same wall with a slight taper, has all the penetrations in it, that no one has yet to start taking down. We still do not have approval for that wall, or to block the door. I am in no way excited about the days to come on this project. Every time I turn around there’s something else that has added that needs to be done to make it passable or look right so one simple section with two walls and soffits with facia builds, has turned into Each individual section being its own unique tear down and reinstall | Subcontractor | Steve Fudge | true | Lightning. Google shuts down everything |  |  | Storms | 3 | 8.5 | false |  | 3 scissor lifts 1 lull | false |  |  | 3 |  | Flashing Layout Perforated Subgirt Zee | [30 empty] | 30 | 1 | 30 | 1
22006 | UTC Football Athletic Facility | 2023-07-06 | Keith Dukarm | Got there at 6 unloaded material and tools then had to find parking ..started hanging Zs and insulation..once that was done started making panels ..its not a fast process making them in field we stopped on time for a quick lunch we even worked through rain showers we have 7 panels to do in the morning and caulk shouldn't be a full day but who knows im really trying to get this done as fast as possible and make it look good at the same time . Have more pics if u need them I can only send 10. | JWMCD Crew | Nick Akins | false |  |  |  |  | 2 | 10 | false |  |  | false
22006 | UTC Football Athletic Facility | 2023-07-05 | Keith Dukarm | Drove to job talked to gc sent pics to Eric got a game plan for tomorrow morning.. | JWMCD Crew | Nick Akins | false |  |  |  |  | 2 | 2 | false |  |  | false
20067 | BNA PROJECT 5 | 2023-06-30 | Zarur Padron Jr | Putting up flashing | Subcontractor | Marc Ribar | [5 empty] | 3 | 30 |  |  | Tied off to yo-yo | [5 empty] | Flashing | [32 empty] | 35 | 30
20067 | BNA PROJECT 5 | 2023-06-29 | Zarur Padron Jr | Putting up flashing | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | Boom lift | [5 empty] | Flashing | [32 empty] | 60 | 40
21071 | Google NBY-HUB 1 | 2023-06-29 | Chad mccoy | We started our morning getting our badges again. We hooked up to the trailer with the panels on it and we pulled to our spot. We setup all the area CAZs and we blocked off the doors and we went to work. Two guys installed the cut down night wall verticals and the horizontal tracks and the insulation. I made panels. And another guy gathered trim and flashing for the fascia. We have to make sure the trespa panels match the white panels up the wall so the joints line up. But the size of the white panels do not match up with what’s suppose to be on the wall. I had to make panels to match what was on the wall. The process to make these are aggravating. But we are making it happen. We ran up the wall with the wall panels and then we started removing and fixing the fascia panels and it’s trim underneath. Once we met up the corner where we had stopped on the east long face. We started installing the 8 inch trim and caulking and we finished flashing the bottom of the vertical wall and caulked it to the concrete. At the top of the curtain wall we also caulked the gap where the inconsistency was where our metal met the curtain wall | Subcontractor | Steve Fudge | false |  |  |  |  | 4 | 10 | false |  | 3 scissor lifts. 1 lull | false |  |  | 2 |  | Caulking Insulation Layout Trim | [20 empty] | 80 | 1.5 |  |  |  |  | 100 | 1 | [8 empty] | 140 | 2
22026 | CSCC - Arts & Technology | 2023-06-29 | Keith Dukarm | Walked with Eric seen what needed to be done ...they took Zs off wall and spray foamed it..so we had to scrap off what we could reach cause we had no lift to borrow...we also did the underneath slap on the side bellow the window...tomorrow I have a lift lined up that we can use and finish cutting spray foam and installing Zs | JWMCD Crew | Drake De Tomasi | true | They took our Zs down and sprayed without putting them back up |  |  | Nice in morning then a Tsunami came.. | 2 | 8 | false |  |  | false |  |  |  |  | Subgirt Zee
20067 | BNA PROJECT 5 | 2023-06-28 | Zarur Padron Jr | Installing flashing and putting in panels on North IAF | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | Harness connected to self retracting yo-yo | [5 empty] | Flashing IMP | [8 empty] | 4 | 20 | [22 empty] | 40 | 20
21071 | Google NBY-HUB 1 | 2023-06-28 | Chad mccoy | We started our morning getting our badges. We then hooked up to the trim trailer and set up to finish the right side of the east canopy. Two guys trimmed it out while I set up to remove all the insulation and track and nightwall framing from the wall. The camera guy showed up and removed the camera and we took the last panel down. And then we removed and cut back the framing for reinstallation. Once the bottom section was re layed out and reinstalled we installed one track so the elections had a depth to install there outlet. Once they were done we continued with the wall. I layed out and made cuts and two guys installed and layed out the track for each panel and installed the new black trim in the joints while the fourth guy knocked out punch list items and cleaned up to keep work areas taken care of. | Subcontractor | Steve Fudge | true | The camera removal and the electrician removing the out let and adjusting it took around 1.5 hrs all together. The white trim up the left east elevation is going to impact the trespa panels. My panels will be align and straight. The white trim will be cut to fit the gap. The white panels next to the trespa panels fall out of plum from bottom to top over 1 1/2 inches |  |  | Cloudy 72 | 4 | 10 | false |  | 3 scissor lifts. 1 lull | false |  |  | 4 |  | Caulking Flashing Insulation Layout Trim | [20 empty] | 30 | 1 |  |  |  |  | 100 | 0.5 |  |  |  |  | 80 | 1 |  |  | 45 | 1
20067 | BNA PROJECT 5 | 2023-06-27 | Zarur Padron Jr | Worked on South IAF and the overly roof panels | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | Boom lift | [5 empty] | IMP Overly Roof Panel | [8 empty] | 4 | 20 |  |  | 4 | 20
21071 | Google NBY-HUB 1 | 2023-06-27 | Chad mccoy | We started our morning going in early. We got our badges and then we started getting the trailer nick brought unloaded so he didn’t have to do anything but strap it down and hit the road. After everything was re arranged we started going thru panels and setting up to make new panels out of the flat stock. We had to make 5 new panels from scratch. This is more difficult than u think. We started cutting out the panels by size. Then we have to lay out ever clip. After the layout is done and the clips are marked, you have to drill the screw holes with out going all the way thru. The depth of the hole needs to be 5/16 deep. And deeper and u go thru the face of the panel. And smaller and the screw will not grab. If u cut these panel the wrong way you flack the face off of it. So the entire build is a process that needs to be handled delicately. We had to build 5 new panels today. But the old panels are not all the right elevation. Panels number e-32 needed to be 28 1/8 & e-33 needed to be 28 1/2. But the old panels were 27 7/16. We built the new panels to the panel e took of bc we were never told anything about the old trespa panels being the wrong height. So those two needed to be re built. Tomorrow I’m checking all the new trespa panels and comparing them to the white panels they line up with. These will tell me what I can install and what will have to be added to the build list. We installed the right side of the east canopy today. The white aluminum panels are out of level on the 4th panel up and the curtain wall falls in. But my panels are straight and lined up the best I can. After these were finished we cleaned up that area for tomorrow and we moved to the left side of the canopy to remove the one soffit for the sprinkler.(SEE DELAYS). Once this was removed the sprinkler guy adjusted his barrel and fixed his cap. We then took down all the wall panel’s except the one with the camera on it. And then we cleaned up for our day | Subcontractor | Steve Fudge | true | Upon taken the one soffit panel down for the sprinkler guy to reach his barrel. I went up in the lift. Dalton was harnessing up and about to come up. I put one hand on the bottom of the panel where my lift was and didn’t not pull of anything. And the panel came down off the soffit and landed on me. Upon further investigation of the soffit next to this one. The clips are not fully seated on the tracks. And with the slight angle of these panels I feel with a heavy wind the soffit panels will fall out of there place. I FaceTimed Steve and showed him. |  |  | Cloudy and cool | 4 | 13 | false |  | 3 scissor lifts and 1 lull | false |  |  | 3.5 |  | Flashing Layout | [32 empty] | 90 | 1.5
20067 | BNA PROJECT 5 | 2023-06-26 | Zarur Padron Jr | Finishing up on North IAF. | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | Scaffold | [5 empty] | IMP | [8 empty] | 14 | 40
21071 | Google NBY-HUB 1 | 2023-06-26 | Chad mccoy | We started our morning getting our badges and we picked up where we left off with the trim. Dalton and Kevin layed out and made the in side full length pieces of the triangle soffits that point away from the curtain wall. At the point in the triangle there is a unique u shaped piece that needed to be cut to fill the spots. These pieces had to be specifically made to fit in a specific spot. Each one had a different variation to the way it installed . Nick and Steve arrived this evening with the trailer of flat material and we met with dpr and the sprinkler guys over the soffit on the small canopy and the lowering of the system. We also talked about areas that need work and work finished. | Subcontractor | Steve Fudge | false |  |  |  |  | 4 | 8 | true | Trespa material so we can make panels | 3 scissors 1 lull | false |  |  | 2 |  | Layout Trim | [36 empty] | 180 | 5
21071 | Google NBY-HUB 1 | 2023-06-25 | Chad mccoy | We started our morning getting badges. Then I called in our work order number. And we went to work. We continued with the trim on the perimeter of the soffits on the east canopy. There are a lot of canopy panels that are barely in its tracks. N we did our best to secure this panels with out taken anything down. We can not remove or move any panels with sprinklers due to the sprinklers being live. Dpr has asked us not to even touch these panels till the system is in bypass. By simply looking at each canopy section you would think the angles are the same cut. But they are not. We started off cutting three canopy’s at once bc they looked typical but they were different so each one is its own layout. There are multiple sections that a panel has to be added to fill the void so we have something to stick the trim to. Thes panels have to be cut to size and clipped and installed. We ended our day taken down the rest of the facia panels on the left side of the canopy. | Subcontractor | Steve Fudge | true | Weather |  |  | Storms rolled thru mid day. | 3 | 8 | false |  | 3 scissor lifts | false |  |  | 3 |  | Flashing Layout Trim | [32 empty] | 5 | 0.5 |  |  | 150 | 5
21071 | Google NBY-HUB 1 | 2023-06-24 | Chad mccoy | We started our morning getting our badges. Then we met up with dpr to look over the soffit panels with the sprinklers in them. We set up two lifts and we took down soffit panels on the smaller canopy that gets lowered 2 inches. We looked over the sprinkler system. With dpr and they are as low as they can be set with out changing out the structure or barrel. We have a meeting Monday with mcdougall officals and dpr and the fire sprinkler guys. After we went thru and took pictures of this section we then reinstalled the soffit panels and cleaned up the area so we could move back to the big canopy. With the big canopy we started installing the trim again. The solid pieces take three lifts to do and the 2 piece sides take two lifts. In the areas where there is a void inbetween the soffit and the wood beams. This area must be filled prior to the finished trim to be installed on top. If we don’t then there will be nothing for the new trim to attach to. | Subcontractor | Steve Fudge | false |  |  |  |  | 3 | 8 | false |  | 3 single man lifts | false |  |  | 3 |  | Layout Trim | [36 empty] | 200 | 4
20067 | BNA PROJECT 5 | 2023-06-23 | Zarur Padron Jr | Wind was heavy so wasn't able to work on boom for too long | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | Boom lift | [5 empty] | Overly Roof Panel | [12 empty] | 5 | 40
20067 | BNA PROJECT 5 | 2023-06-23 | Zarur Padron Jr | Finishing up on North IAF | Subcontractor | Marc Ribar | [5 empty] | 5 | 50 |  |  | Scaffold | [5 empty] | IMP Other | [8 empty] | 22 | 45 | [32 empty] | 30 ft of flashing | 5
20067 | BNA PROJECT 5 | 2023-06-22 | Zarur Padron Jr | Putting up flashing | Subcontractor | Marc Ribar | [5 empty] | 3 | 30 |  |  | N/A | [5 empty] | Flashing | [32 empty] | 30 | 30
20067 | BNA PROJECT 5 | 2023-06-22 | Zarur Padron Jr | Finishing up on North IAF | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | Scaffold | [5 empty] | IMP | [8 empty] | 15 | 40
21071 | Google NBY-HUB 1 | 2023-06-22 | Chad mccoy | We started our morning getting our badges. Then we hooked to each trailer and we moved to our area where we all across the grass. We set up to do the fascia panels on the east canopy and the trim around the soffit. We took down and installed 6 fascia panels and then google reps came to us and said they were going to cook out on the concrete sidewalk. And they needed room to set up tents and tables. So we talked it over with the area they needed for there set up and we adjusted yet again for reasons we can’t control and we kept going. Penne kt comes to the fascia panels we have to remove the old panels and old flashing and move the tracks the panels are on. Some continued doing this down the walls plus we layed out each individual panel and each one has to have a cut the goes under the beams. As we continued down the wall we started running into birds nest with bird shit and baby’s in them. But okay was different bc under neath us was food and tables and people. So we had to shut down till the lunch was completed and all individuals and all food was put up. This shut us down around 2.5 hrs. Once everything was cleaned up. We continued with our removal and realignments and reinstall of panels and track system. | Subcontractor | Steve Fudge | true | The cook out took for ever. Every single day that we install or we attempt to install, we come across something on each individual section that delays or disrupts what we need to do. This job these panels the area of working the schedule from google compared us nothing is *NSYNC. Nothing is 100% here and absolutely nothing is going like it supposed to go. |  |  | Cloudy | 4 | 8 | false |  | 2 sucky single man lifts. | false |  |  | 3 |  | Flashing Layout Trim | [32 empty] | 100 | 2 |  |  | 40 | 1
20067 | BNA PROJECT 5 | 2023-06-21 | Zarur Padron Jr | Continuing work on North IAF | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | Scaffold and boom | [5 empty] | IMP | [8 empty] | 12 | 40
20067 | BNA PROJECT 5 | 2023-06-21 | Zarur Padron Jr | Putting up the rest of the panels | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | Boom 60 ft | [5 empty] | IMP Other | [8 empty] | 5 | 36 | [32 empty] | 4 ft of mending plate | 4
21071 | Google NBY-HUB 1 | 2023-06-21 | Chad mccoy | We started our morning at the front gate getting our badges. What is the Badgers were required we went through the gates and hooked up to the trailers and pulled the trailers to where we needed them. We had a quick safety talk so that we can get going on the wall that we took down yesterday. We took the panel that we installed yesterday off and we cut it back to where it would have a half inch joint up the curtain wall like DPR requested. Upon looking for the new wall panels To continue with the wall up matching the half inch joint up the curtain wall and touching the white trim that was installed into the white panels. We discovered that on the east elevation right side only four panels were replaced out of 8. On the left side of the east elevation, only three panels were replaced out of eight. We then checked the dimensions of the old panels to what the requirements are for where the new Panels needed to meet or match up to satisfy the design team and DPR’s request. The old panels are an inch and 3/4 to 2 1/2 inches shorter than the panel that we’ve already cut down to meet the requirements. So absolutely, none of the old panels on the east big canopy walls that need to be reused can be reused due to improper cuts, and the length of the Panels. To continue progress, which there has been a hiccup in every single stage of this reinstallation of these panels. We moved to the facia panels and the soffit trim on the big canopy. We started by taking down the old facia panels and removing the horrible trim that is along the bottom of these panels. We then finished running the vertical metal up the curtain wall so they could run into the perforated new flashing that goes at the base of the facia panels. Once the perforated flashing was installed with then started installing the facia panels back after we moved, the bottom track down to compensate for the length of the panel that was added to make up The distance or gap between the Panels and the top of curtainwall. Once the facia panels were done on the right side of the east elevation, we went to the trim that went around the perimeter of the soffit. This trim is 8 inches wide, and it has to be angle to match up along and with the requirements that DPR and the design team wanted us to do for the joints and where they don’t line up together. Once we went as far as we could with the east elevation, right side, soffit trim, we moved to the front panels on the facia and the perforated trim underneath it so that we can continue down the wall. The facia panels have to be done first, so that the trim can go up along the perimeter of the soffit next. On top of the curtain wall, there’s a lot of little pieces of metal that’s sticking up so these have to be taken care of prior to putting the new metal on or it’s gonna look as nasty as metal dead that we took down previous | Subcontractor | Steve Fudge | true | This job is riddled with delays. We have literally started and stopped 11 times on multiple sections due to not having all the material or not having the right material. We’re not having the proper equipment to do the sections. We also have to start and stop around other trades that are in no rush or hurry to simply move an electrical box or plumbing or cameras or fire boxes so that we can take the panels off and put the panels back on. Every time that we finish just a little bit I have to have a conversation with DPR to make sure that it meets the requirements or if it needs to be adjusted so that each section that we do finish or each piece can be crossed off the list instead of me having to return back to that section like every other section so that we can finish the work. The hat channel was wrong there a Panels that are wrong their panels that are missing the only thing that is actually work like it’s supposed to is the L-shaped black metal and the perforated metal. Everything else has had to have a bit of imagination or a well thought out plan to make it look or appear like it’s in the manner that is supposed to be. |  |  | Cloudy 82 | 4 | 10 | false |  | 2 crappy scissor lifts | false |  |  | 1 |  | Layout Perforated Trim | [36 empty] | 75 | 1.5
22073 | Pioneer Appalachia FCU | 2023-06-21 | Alexander Aguilar | Estructura de Z de 1 de y de 3 -insolación- 6 paneles ACM color grey | Subcontractor | Eric Gutierrez | [5 empty] | 5 | [9 empty] | ACM Flashing Insulation Other Trim
Rosa L Parks | #NO MATCH | 2023-06-21 | Marvin blanco | Installing ACM panels and installation | Subcontractor | #NO MATCH | false |  |  |  |  | 12 | 10 | false |  | swing stage and boomlift | false |  |  |  |  | ACM | 15 | 120
21071 | Google NBY-HUB 1 | 2023-06-20 | Chad mccoy | . we started our morning getting our badges at the gate. I met United Rentals In outside the gate this morning to pick up our cones and barriers for our CAZ. Then we go thru and we we have to have a tool box and safety talk each morning. We then started taken down the first wall of panels. Once the wall of panels were down we then found that the new hat channel and the already installed nightwall system was the exact same size. There was no difference so the hat channel could not be used. All the night wall clips had to be cut down. To do this everything came down but the clips. And each one needed to be laid out and cut. Then the wall framing and tracks had to be put back. But before that could be started we had to remove and fix the trim at the bottom of each panels. The bottom kick trim was never remade. So it is white and Steve said he was bring a the new trim Monday. New black trim was installed up the curtain wall side and the new white trim was installed up the white panel section. But before the panel at the bottom could be installed. The electrician had to fix his outlet and readjust the box, so it would not impede the panel after installation. This took hours of waiting for this to be done. Once this was done, we laid out the two penetrations we re-cut the holes and we installed the panel. I got with Martin over the new panel, installed to see if it met requirements that was specified in the email. Everything was done accordingly except up the curtain wall. It needs to be taken off and cut back to a 3/8 offset going up the curtain wall. So these panels will have that in the morning as we continue at the Wall | Subcontractor | Steve Fudge | true | The material from Mcdougal was the wrong size. It caused additional work to be done for the night wall system, because we cannot modify the hat channel. The electrician took forever, adjusting one outlet. |  |  | Rain almost all day | 4 | 10 | false |  | 2 one man scissor lifts | false |  |  | 1 |  | Layout Trim | [36 empty] | 45 | 0.5
22073 | Pioneer Appalachia FCU | 2023-06-20 | Alexander Aguilar | Se instaló estructura Z de 5 pulgadas - se instaló insolación- se instaló 9 paneles ACM1 color grey | Subcontractor | Eric Gutierrez | [5 empty] | 5 | [9 empty] | ACM Flashing Other Soffit Trim
20067 | BNA PROJECT 5 | 2023-06-19 | Zarur Padron Jr | Had a rain and lightning delay | Subcontractor | Marc Ribar | [5 empty] | 4 | 32 |  |  | Boom lift | [5 empty] | IMP Other | [8 empty] | 8 | 28 | [32 empty] | 16 ft of mending plate | 4
20067 | BNA PROJECT 5 | 2023-06-19 | Zarur Padron Jr | Working on North IAF | Subcontractor | Marc Ribar | true | Rain and lightning delay |  |  | Rain and lightning | 4 | 32 |  |  | N/A | [5 empty] | IMP Other | [8 empty] | 3 | 28 | [32 empty] | 30 ft of metal flashing | 4
20067 | BNA PROJECT 5 | 2023-06-19 | Zarur Padron Jr | Working on North IAF (rain delays) | Subcontractor | Marc Ribar | [5 empty] | 4 | 32 |  |  | Scaffold | [5 empty] | IMP Other | [8 empty] | 8 | 28 | [32 empty] | 16 ft of mending plate | 4
20067 | BNA PROJECT 5 | 2023-06-19 | Zarur Padron Jr | Working on Top Hat North | Subcontractor | Marc Ribar | [5 empty] | 4 | 32 |  |  | N/A | [5 empty] | Other | [42 empty] | 80 ft of metal flashing | 32
22073 | Pioneer Appalachia FCU | 2023-06-19 | Alexander Aguilar | Instalamos estructura Z Instalamos insolación se instalaron 10 paneles ACM1 color -grey | Subcontractor | Eric Gutierrez | [5 empty] | 5 | 10 | true | 0 | [6 empty] | ACM Flashing Trim
20067 | BNA PROJECT 5 | 2023-06-16 | Zarur Padron Jr | Working on South IAF | Subcontractor | Marc Ribar | [5 empty] | 4 | 32 |  |  | Scaffold | [5 empty] | IMP | [8 empty] | 8 | 32
20067 | BNA PROJECT 5 | 2023-06-16 | Zarur Padron Jr | Working on South IAF | Subcontractor | Marc Ribar | [5 empty] | 4 | 32 |  |  | N/A | [5 empty] | Other | [42 empty] | 53ft of stainless steel flashing, 30 ft of galvanized zee's | 32
20067 | BNA PROJECT 5 | 2023-06-15 | Zarur Padron Jr | Working on South IAF | Subcontractor | Marc Ribar | [5 empty] | 4 | 32 |  |  | N/A | [5 empty] | IMP Other | [8 empty] | 3 | 24 | [32 empty] | 30 ft of metal flashing, 6 ft of mending plate | 8
20067 | BNA PROJECT 5 | 2023-06-15 | Zarur Padron Jr | Working on South IAF | Subcontractor | Marc Ribar | [5 empty] | 4 | 32 |  |  | Scaffold | [5 empty] | IMP Other | [8 empty] | 8 | 30 | [32 empty] | 16 ft of mending plate | 2
22044 | DLR IAD 44 | 2023-06-15 | Jean negron | the entrance was finished it was coulkio the panels were cleaned with rags | Subcontractor | Dillon Bowman | false |  |  |  |  | 4 | 70 | false |  | 2 boom | false |  |  |  |  | ACM Caulking | 14 | 50 | [18 empty] | 50 | 15
22073 | Pioneer Appalachia FCU | 2023-06-15 | Alexander | Instalación de panel | Subcontractor | Eric Gutierrez | [5 empty] | 5 | 9 | [8 empty] | ACM | 6 | 9
20067 | BNA PROJECT 5 | 2023-06-14 | Zarur Padron Jr | Working on South IAF | Subcontractor | Marc Ribar | [5 empty] | 4 | 32 |  |  | N/A | [5 empty] | Other | [42 empty] | 40ft of stainless steel, 40 ft of zee's, 40 ft of starter flashing | 32
20067 | BNA PROJECT 5 | 2023-06-14 | Zarur Padron Jr | Working on South IAF | Subcontractor | Marc Ribar | [5 empty] | 4 | 32 |  |  | Scaffold | [5 empty] | IMP Other | [8 empty] | 8 | 26 | [32 empty] | 15 ft Starter flashing and 15 ft J-flashing and 16 ft of mending plate | 6
20067 | BNA PROJECT 5 | 2023-06-13 | Zarur Padron Jr | Working around the door on North IAF | Subcontractor | Marc Ribar | [5 empty] | 4 | 32 |  |  | Scaffold | [5 empty] | Other | [42 empty] | 10 ft of head flashing, 20 ft of angle trim, 50 ft of stainless flashing, 10 ft of starter flashing, 11 PCs of metal strap, 20 ft vertical J trim | 32
20067 | BNA PROJECT 5 | 2023-06-13 | Zarur Padron Jr | Working on North IAF | Subcontractor | Marc Ribar | [5 empty] | 4 | 32 |  |  | Scaffold | [5 empty] | IMP Other | [8 empty] | 8 | 28 | [32 empty] | 10 ft of mending plate | 4
20067 | BNA PROJECT 5 | 2023-06-12 | Zarur Padron Jr | Working on South IAF | Subcontractor | Marc Ribar | [5 empty] | 4 | 32 |  |  | Scaffold | [5 empty] | IMP Other | [8 empty] | 4 | 16 | [32 empty] | 20 ft of mending plate, 20 ft of J-trim, 10 ft of window flashing | 16
20067 | BNA PROJECT 5 | 2023-06-12 | Zarur Padron Jr | Continuing work on roof | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | Scaffold | [5 empty] | Other | [42 empty] | 20ft of J-flashing, 10ft of head flashing, 20 ft of angle flashing, 25 ft of starter J- flashing, 25 ft of starter flashing, 25 ft of stainless steel flushing | 40
20067 | BNA PROJECT 5 | 2023-06-09 | Zarur Padron Jr | Working on North IAF | Subcontractor | Marc Ribar | [5 empty] | 4 | 32 |  |  | Scaffold | [5 empty] | Other | [42 empty] | Taking film off, Cleaning panels, Installing vertical gaskets at joints | 32
20067 | BNA PROJECT 5 | 2023-06-09 | Zarur Padron Jr | Installing IMP | Subcontractor | Marc Ribar | [5 empty] | 4 | 32 |  |  | Scaffold | [5 empty] | Flashing IMP Other | [8 empty] | 9 | 18 | [22 empty] | 10 | 2 | [8 empty] | 20 ft mending plate, 20 ft of starter flashing, 20 ft starter J | 12
20067 | BNA PROJECT 5 | 2023-06-08 | Zarur Padron Jr | Continued working on IMP | Subcontractor | Marc Ribar | [5 empty] | 4 | 32 |  |  | Scaffold | [5 empty] | Flashing IMP Other | [8 empty] | 5 | 18 | [22 empty] | 10 | 2 | [8 empty] | 20 ft of J flashing at bottom and vertical end 10 ft mending plate | 12
20067 | BNA PROJECT 5 | 2023-06-08 | Zarur Padron Jr | South | Subcontractor | Marc Ribar | [5 empty] | 3 | 24 |  |  | Scaffold | [5 empty] | Flashing IMP Other | [8 empty] | 4 | 16 | [22 empty] | 10 | 2 | [8 empty] | 10 ft of J flashing and 10 ft of stainless steel flashing and 10 ft of mending plate | 6
20067 | BNA PROJECT 5 | 2023-06-06 | Zarur Padron Jr | Working on North IAF | Subcontractor | Marc Ribar | [5 empty] | 3 | 30 |  |  | Ladders | [5 empty] | ACM Flashing Other | 5 | 16 | [30 empty] | 10 | 2 | [8 empty] | 10 ft of mending plate and 10 ft j flashing | 4
22033 | 127 RLP Tempo Hotel | 2023-06-06 | Marvin blanco | installing Acm panels. | Subcontractor | Marc Ribar | false |  |  |  |  | 8 | 10 | false |  | swing stage | false |  |  |  |  | ACM | 10 | 80
20067 | BNA PROJECT 5 | 2023-06-05 | Zarur Padron Jr | Installing Overly Roof Panels on Northwest | Subcontractor | Marc Ribar | [5 empty] | 4 | 32 |  |  | Boom lift 80ft | [5 empty] | Overly Roof Panel | [12 empty] | 7 | 32
20067 | BNA PROJECT 5 | 2023-06-05 | Zarur Padron Jr | Continued working on IAF North | Subcontractor | Marc Ribar | [5 empty] | 4 | 32 |  |  | Scaffold | [5 empty] | ACM | 9 | 32
20067 | BNA PROJECT 5 | 2023-06-02 | Zarur Padron Jr | Working on IAF North | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | Scaffold | [5 empty] | ACM | 9 | 40
20067 | BNA PROJECT 5 | 2023-06-02 | Zarur Padron Jr | Working on the Northwest side of the roof and installing overly roof panels | Subcontractor | Marc Ribar | [5 empty] | 4 | 32 |  |  | Boom lifts | [5 empty] | Overly Roof Panel | [12 empty] | 9 | 32
20067 | BNA PROJECT 5 | 2023-06-02 | Zarur Padron Jr | The wind starting picking up around 11 | Subcontractor | Marc Ribar | [5 empty] | 2 | 16 |  |  | Boom 60 ft | [5 empty] | Flashing IMP Other | [8 empty] | 1 | 6 | [22 empty] | 20 | 2 | [8 empty] | 10 ft of mending plate and 10 ft of J flashing and 1 cupping cap | 8
20067 | BNA PROJECT 5 | 2023-06-01 | Zarur Padron Jr | They worked on North IAF | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | Scaffold | [5 empty] | ACM | 15 | 40
20067 | BNA PROJECT 5 | 2023-06-01 | Zarur Padron Jr | They installed panels on the west side | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | Boom lift | [5 empty] | ACM Other | 5 | 38 | [40 empty] | Mending plate | 2
20067 | BNA PROJECT 5 | 2023-06-01 | Zarur Padron Jr | Installed the rest of the panels on North IAF | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | Scaffold | [5 empty] | ACM | 7 | 40
22039 | Amazon IAD 606 | 2023-06-01 | Chad mccoy | We started our day continuing the trim around the doors. The doors got installed today. The double doors was ok beside the door installers dented up the drip edge above the door on both doors. There is no way to chang this out so we did our best to slap and skim over the original metal to make this pass. We finished the pclad up the walls and then we installed the coping to finish it off. While we were gone the electricians ran a scissor lift into the lower drip metal and messed it up in two spots. So we cut this area off and reinstalled and new base trim. At the end of the day we were instructed that we needed to install the pclad on the doors. But during the inventory of what was needed for these installs we came across that we do not have enough darker trim to finish the double doors. So decisions were made and the trim is in route and will be here in the morning to finish the job. | Subcontractor | Eric Gutierrez | false |  |  |  |  | 2 | 9 | false |  | Scissor lift | false |  |  |  |  | Coping Corrugated / Screen wall Flashing Trim | [22 empty] | 45 | 4 | [8 empty] | 50 | 2 |  |  | 50 | 2 |  |  | 15 | 1
22054 | Amazon IAD 169 | 2023-06-01 | Fredy veliz | Corrugated panels structure is bigger so we are 2 panels short | Subcontractor | Colton Van Meter | [5 empty] | 7 | 14 |  |  | 3 boom lifts and forklift | [5 empty] | Other | [42 empty] | Installing corrugated panels and blades | 98
20067 | BNA PROJECT 5 | 2023-05-31 | Zarur Padron Jr | Installed panels and J flashing on North side roof | Subcontractor | Marc Ribar | [5 empty] | 3 | 30 |  |  | Scaffold | [5 empty] | ACM Flashing | 8 | 24 | [30 empty] | 30 | 6
20067 | BNA PROJECT 5 | 2023-05-31 | Zarur Padron Jr | Fabricated panels and installed them | Subcontractor | Marc Ribar | [5 empty] | 3 | 30 |  |  | Scaffold | [5 empty] | ACM Other | 8 | 24 | [40 empty] | Mending plate 20 ft | 6
20067 | BNA PROJECT 5 | 2023-05-31 | Zarur Padron Jr | Sheet rock guys borrowed the boom lift so they could put sheet rock so we could install panels | Subcontractor | Marc Ribar | [5 empty] | 2 | 20 |  |  | Boom lift 60ft | [5 empty] | Other | [42 empty] | Cleaning panels and installing rubber gasket between joints | 20
20067 | BNA PROJECT 5 | 2023-05-31 | Zarur Padron Jr | They took down panels so they would be able to move the picture frame | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | Boom lift 60ft | [5 empty] | Other | [42 empty] | Panels moved | 40
22054 | Amazon IAD 169 | 2023-05-31 | Fredy veliz | Channel are 100 % complete all we have is install blades and the screen I will do that tomorrow | Subcontractor | Colton Van Meter | [5 empty] | 7 | 13 |  |  | 3 boom lifts and forklift | [5 empty] | Other | [42 empty] | Installing channels and blades | 91
20067 | BNA PROJECT 5 | 2023-05-30 | Zarur Padron Jr | A group 3 stopped the work at Inner Southside Canopy (safety issues) to work on a different elevation and to move a scaffold from south side to north side roof. | Subcontractor | Marc Ribar | [5 empty] | 3 | 60 |  |  | 80 ft boom | [5 empty] | ACM Flashing Other | 2 | 8 | [30 empty] | 80 | 22 | [8 empty] | Moving scaffold | 30
22054 | Amazon IAD 169 | 2023-05-30 | Fredy veliz | Todays we had the plan to work to 7 :00 pm but they stop us at 6:00 I was told we can work to 6 | Subcontractor | Colton Van Meter | [5 empty] | 7 | 12 |  |  | 3 boom lifts and forklift | [5 empty] | Other | [42 empty] | Installing Chanel's and blades | 84
22054 | Amazon IAD 169 | 2023-05-27 | Fredy veliz | We stopped working earlier because the Holliday | Subcontractor | Colton Van Meter | [5 empty] | 7 | 8 |  |  | 3 boom lifts and forklift | [5 empty] | Other | [42 empty] | Installing channels and blades | 56
20067 | BNA PROJECT 5 | 2023-05-26 | Zarur Padron Jr | East side airwave | Subcontractor | Marc Ribar | [5 empty] | 3 | 30 |  |  | N/A | [5 empty] | Flashing Other | [32 empty] | 70 | 15 | [8 empty] | Flashing Clit 70ft | 15
22044 | DLR IAD 44 | 2023-05-26 | Jean negron | Box G was finished and Box C was finished. More details in the photos. | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 | 50 | false |  |  | false |  |  |  |  | ACM Caulking Layout Plate
20067 | BNA PROJECT 5 | 2023-05-25 | Zarur Padron | 3 different crews | Subcontractor | Marc Ribar | [5 empty] | 15 | 10 |  |  | Boom | [5 empty] | ACM Caulking Flashing Soffit | 16 | 100 | [18 empty] | 15 | 25 | [10 empty] | 10 | 25
22033 | 127 RLP Tempo Hotel | 2023-05-25 | Marvin blanco | installing ACM panels and also plate panels | Subcontractor | Marc Ribar | false |  |  |  |  | 20 | 10 | true | ACM panels insulation and hats channels | boomlift swing stage and forklift | false |  |  |  |  | ACM Plate | 15 | 100 | 20 | 100
22044 | DLR IAD 44 | 2023-05-25 | Jean negron | Box C is finished. 2 remaining panels. 7 panels are installed in box G. ISO cleans more details in the photos | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 | 60 | false |  | Boom lift 2 | false |  |  |  |  | ACM Caulking Coping Flashing
22054 | Amazon IAD 169 | 2023-05-25 | Fredy veliz | Getting close to be on top of other trades at some point next week they have to move so we can finish | Subcontractor | Colton Van Meter | [5 empty] | 7 | 12 |  |  | 3 boom lifts and a forklift | [5 empty] | Other | [42 empty] | Installing Chanel's and blades | 84
20067 | BNA PROJECT 5 | 2023-05-24 | Zarur Padron Jr | Extra Precaution 100% guys tied off | Subcontractor | Marc Ribar | [5 empty] | 3 | 30 |  |  | N/A | [5 empty] | Flashing Other | [32 empty] | 70 | 15 | [8 empty] | Flashing Clit 70 ft | 15
22026 | CSCC - Arts & Technology | 2023-05-24 | Keith Dukarm | Started the day by continuing to install Zs Eric came out we walked the job and talked about it ..he did get the stair towers approved which we will do tomorrow and move a bottom row of Zs up for brick to fit ...bout 120 left went to Albion to finish J trim that was left off . It is now complete. The lift will be good to call of Friday at CSCC | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 | 8 | false |  | Boom lift | false |  |  |  |  | Subgirt Zee
22044 | DLR IAD 44 | 2023-05-24 | Jean negron | We weigh on the roof and continue box C. of the stairs. since yesterday they enlisted it. installed z. insolation. 6 panels. ... flashing... in the part of the box G... the last ceiling panels were installed, 2 were missing, one of them was cut and in the part of the door we weighed today since they had ready this morning 4 more sat in That aria would be 12 panels in total. Some parts of the conopy were collected, more details in the photos | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 |  | false |  |  | false |  |  |  |  | ACM Caulking Flashing Insulation Subgirt Zee
22054 | Amazon IAD 169 | 2023-05-24 | Fredy veliz | Everything going good no issues | Subcontractor | Colton Van Meter | [5 empty] | 7 | 12 |  |  | 3 boom lifts and forklift | [5 empty] | Other | [42 empty] | Installing channels braces and blades | 84
20067 | BNA PROJECT 5 | 2023-05-23 | Zarur Padron Jr | Extra safety cautions (little bit of wind) | Subcontractor | Marc Ribar | [5 empty] | 4 | 32 |  |  | 80 ft boom | [5 empty] | ACM Other | 6 | 24 | [40 empty] | 1 Fab panels | 8
22026 | CSCC - Arts & Technology | 2023-05-23 | Keith Dukarm | Started today off by going to meeting in morning job meeting then we got outr lift around back and started hanging Zs on the entrance way we got that complete end of day we move the lift back around to front so we can finish that tomorrow | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 3 | 8 | false |  | Boom lift | false
22044 | DLR IAD 44 | 2023-05-23 | Jean negron | We thought about installing the 2 remaining corners and then installing the small panels that I added to the box of 3 and a half. The panels were manufactured in 2 more hours per panel and the lower part of the roof floor was assembled. More details in the photos. | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 | 55 | false |  | Boom lift 2 | false |  |  |  |  | ACM Caulking | 6 | 30 | [18 empty] | 20 | 3
22054 | Amazon IAD 169 | 2023-05-23 | Frey veliz | We started setting blades section a,b,c complete | Subcontractor | Colton Van Meter | [5 empty] | 7 | 11 |  |  | 3 boom lifts and forklift | [5 empty] | Other | [42 empty] | Installing blaces and blades section a,b,c | 77
20067 | BNA PROJECT 5 | 2023-05-22 | Zarur Padron Jr | Panel that connects to the corner was fabricated | Subcontractor | Marc Ribar | [5 empty] | 4 | 32 |  |  | 80 ft boom lift | [5 empty] | ACM Other | 4 | 24 | [40 empty] | Panel Fab | 8
22026 | CSCC - Arts & Technology | 2023-05-22 | Keith Dukarm | Started day off by seeing what needed to be done and contacted Eric to go over things...then we started hanging Zs and getting measurements for cuts...waited for lift not sure when it actually showed up but didn't see it arrive tomorrow will continue to hang Zs and try and wrap up auditorium section and back entrance..the Wednesday Eric will be here to go over what esle needs to bebdone | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 3 | 8 | false |  | Boom lift | false |  |  |  |  | Subgirt Zee
22033 | 127 RLP Tempo Hotel | 2023-05-22 | Marvin blanco | installing panels plate panels and also ACM panels | Subcontractor | Marc Ribar | false |  |  |  |  | 16 | 10 | false |  | swing stage forklift and boomlift | false |  |  |  |  | ACM | 20 | 160
22044 | DLR IAD 44 | 2023-05-22 | Jean negron | 12 panels were installed of those 12 panels we cut one F02 cut the half inch that was required between the two panels vary throughout the box .. hitt contractor .. They already know about the subject | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 | 50 | false |  | Boom lift 2 | false |  |  | 5 |  | ACM Caulking Layout | 15 | 40 | [18 empty] | 10 | 3
22054 | Amazon IAD 169 | 2023-05-22 | Fredy veliz | Today we Started working one hours earlier , we did notch the 10 Channels in the section a,b,c | Subcontractor | Colton Van Meter | [5 empty] | 7 | 11 |  |  | 3 boom lifts | [5 empty] | Other | [42 empty] | Notching and installing Channel and braces section a,b,c | 84
20067 | BNA PROJECT 5 | 2023-05-19 | Zarur Padron Jr | Working together with framing guys (sharing boom lift) | Subcontractor | Marc Ribar | [5 empty] | 4 | 32 |  |  | 60 ft boom lift | [5 empty] | IMP Other | [8 empty] | 4 | 30 | [32 empty] | Mending plate 20ft | 2
22033 | 127 RLP Tempo Hotel | 2023-05-19 | Marvin blanco | installing panels | Subcontractor | Marc Ribar | false |  |  |  |  | 15 | 10 | false |  | boomlift forklift and swing stage | false |  |  |  |  | Plate |  |  | 60 | 150
22044 | DLR IAD 44 | 2023-05-19 | Jean negron | cutting of panels modification of the box due to bad measurements of the wall | Subcontractor | Dillon Bowman | true | cutting of panels modification of the box due to bad measurements of the wall |  |  |  | 5 | 50 | false |  | Boom lift 1 | false |  |  |  |  | ACM Caulking | 7 | 4 | [18 empty] | 10 | 5
22054 | Amazon IAD 169 | 2023-05-19 | Fredy veliz | Installation going good | Subcontractor | Colton Van Meter | [5 empty] | 7 | 9 |  |  | 3 boom lifts 1 forklift | [5 empty] | Other | [42 empty] | Installing Channel and braces | 63
20067 | BNA PROJECT 5 | 2023-05-18 | Zarur Padron Jr | We had a problem with the boom lift but the technician came and fixed it right away | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | 60 boom lift | [5 empty] | Flashing IMP | [8 empty] | 6 | 28 | [22 empty] | 40 | 12
22044 | DLR IAD 44 | 2023-05-18 | Jean negron | We weighed in the box g, measurements were taken, the panels were cut.. fo1,,f03,,F04,, were modified for reasons of the measurements of the wall, the entrance of the box F,, could not be finished due to reasons that it lacks rroof, they are missing some electricity lights... that we are still waiting for... for that reason we could not finish it | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 | 50 | false |  | Boom lift 1 | false |  |  |  |  | ACM Caulking Flashing | 9 | 40 | [18 empty] | 10 | 2 | [10 empty] | 30 | 5
22054 | Amazon IAD 169 | 2023-05-18 | Fredy veliz | We are coordinating with other trades to work on the same area , for now everything good but in the future we will need to move to finish the areas where they working | Subcontractor | Colton Van Meter | [5 empty] | 7 | 11 |  |  | 3 boom lifts and forklift | [5 empty] | Other | [42 empty] | Installing channels and braces | 77
20067 | BNA PROJECT 5 | 2023-05-17 | Zarur Padron Jr | Waiting for framing guys to have this area ready | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | 60 ft boom lift | [5 empty] | Flashing IMP Other | [8 empty] | 6 | 26 | [22 empty] | 40 | 10 | [8 empty] | Mending plate 20 ft | 4
21040 | 801 Church | 2023-05-17 | Marvin blanco | installing tubes | Subcontractor | Nick Akins | false |  |  |  |  | 7 | 9 | false |  | forklift | false |  |  |  |  | Tubing | [28 empty] | 80 | 70
22033 | 127 RLP Tempo Hotel | 2023-05-17 | Marvin blanco | installing panels and installation | Subcontractor | Marc Ribar | false |  |  |  |  | 13 | 10 | true | plate panels and acm panels | swing stage boomlift and forklift | false |  |  |  |  | Insulation Plate |  |  | 30 | 80 | [22 empty] | 200 | 50
22044 | DLR IAD 44 | 2023-05-17 | Jean negron | We weighed by cutting the DO1 panel... for reasons of the wall measurements... 4 panels were installed, measurements were taken on the wall. more details in the photos | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 | 50 | false |  | Boom lift 2 | false |  |  | 4 |  | ACM Caulking Layout | 4 | 40 | [18 empty] | 12 | 1
22054 | Amazon IAD 169 | 2023-05-17 | Fredy veliz | We need to work Saturdays to finish in time | Subcontractor | Colton Van Meter | [5 empty] | 7 | 11 |  |  | 3 boom lifts 1 forklift | [5 empty] | Other | [42 empty] | Installing Chanel's | 77
20067 | BNA PROJECT 5 | 2023-05-16 | Zarur Padron Jr | Reinstalled panels (have been removed) | Subcontractor | Marc Ribar | [5 empty] | 4 | 40 |  |  | Scaffold | [5 empty] | IMP Other | [8 empty] | 5 | 32 | [32 empty] | Mending plates | 8
22033 | 127 RLP Tempo Hotel | 2023-05-16 | Marvin blanco | installing panels and tubes. | Subcontractor | Marc Ribar | false |  |  |  |  | 13 | 10 | false |  | swing stage boomlift and forklift | false |  |  |  |  | Plate |  |  | 20 | 130
22044 | DLR IAD 44 | 2023-05-16 | Jean negron | We weighed the entrance to box D, 8 panels were installed and one was cut. Panel D01 was cut from the bottom for reasons of the wall measurements | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 | 60 | false |  | Scaffold | false |  |  | 2 |  | ACM Caulking Layout | 8 | 45 | [18 empty] | 15 | 3
22054 | Amazon IAD 169 | 2023-05-16 | Fredy veliz | Having issues with other trades material on our work areas | Subcontractor | Colton Van Meter | true | Other trades material in our way |  |  |  | 7 | 11 |  |  | 2 boom lifts and forklift | [5 empty] | Other | [42 empty] | Had 2 guys on one boom lift finishing screw they almost done and I started installing Chanels | 77
22054 | Amazon IAD 169 | 2023-05-16 | Fredy veliz | Today with Had some issues with other trades material on our working areas causing delays | Subcontractor | Colton Van Meter | true | Other trades material on our areas many traffic |  |  |  | 7 | 11 |  |  | 3 boom lifts and forklift | [5 empty] | Other | [42 empty] | Had 2 guys on one boom lift finishing screws they will finish tomorrow, started installing Chanels 36 total started late | 77
23017 | Nissan Picayune | 2023-05-16 | Chad mccoy | We went in early today to organize the trailer and get everything that was off thrown away bc the dumpster arrived. We didn’t touch the building till 745 pm. So we got everything off the trailer and then I started taken panels off around 740-745. The area where the louver was had clips screwed to the wall with 3/8 screws and these areas where difficult to remove. But I found a way and repeated it till I was done. I had to remove a make shift cap over the icon panels and then I removed the icon panels. These panels where installed from the bottom up on one side and the other was installed from the top down. These panels also had random screws holding everything together from panel face to panel return and a lot of these screws where hidden under caulking. Once the icon was down I turned the corner and started from the top down. The last panel was the panel with the water connection. This connection was live so when I removed the cover water spread everywhere till I got the panels off and the cover back on. This was a challenging task and it took two people We both were soaked. We got everything down and started clean up. The hole removal time from yesterday and today was about 10 for all panels. | Subcontractor | Colton Tomlin | false |  |  |  |  | 4 | 5 | false |  | Scissor lift | false |  |  |  |  | ACM | -110 | 5
22054 | Amazon IAD 169 | 2023-05-15 | Fredy veliz | I moved 179 material today , trying to work the fast and best we can. Other working in the same aranés | Subcontractor | Colton Van Meter | [5 empty] | 5 | 11 |  |  | 3 boom lifts one forklift | [5 empty] | Other | [42 empty] | Re screws the clips an move material | 55
23017 | Nissan Picayune | 2023-05-15 | Chad mccoy | We started our day driving to the site from mcdougal. Upon arrival to the site there was nothing removed from the building and there was no dumpster and no scissor lift. The louvers sign lights cameras and water attachment was all still there. The scissor lift was dropped off at the wrong dealer ship. So we had to go pick it up on my trailer and bring it back. I talked with the Hoyat guy and we came up with a plan. The panel with the light in it I cut around the light and left that Acm. The panels with the camera we cut around those and we left the cameras. We removed all the coping Acm and we removed 145 panels. We started at 730 pm and we left at 1153 pm the same day | Subcontractor | Colton Tomlin | true | Nothing was prepped and ready like it was suppose to be |  |  | Storms in the distance but other than that cloudy | 4 | 5 | false |  | Scissor | false |  |  |  |  | ACM | -145 | 5
22044 | DLR IAD 44 | 2023-05-13 | Jean negron | Rain | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 | 0 | false |  |  | false |  |  |  |  | ACM
22044 | DLR IAD 44 | 2023-05-12 | Jean negron | The coping of the box was installed,, A, they continued taking out garbage, all the material that we brought up to the roof had to be lowered again. For example, the z, that the insulation was not used. We had to take it down the stairs | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 | 50 | false |  | Scaffold | false |  |  |  |  | Caulking Coping Hat Channel | [20 empty] | 10 | 1 | [12 empty] | 120 | 20 |  |  |  |  | 12 | 120
22054 | Amazon IAD 169 | 2023-05-12 | Fredy veliz | Had to do extra work because the steel is not correct | Subcontractor | Colton Van Meter | true | Steel is not builder correct |  |  |  | 6 | 11 |  |  | 3 booms lift 1 forklift | [5 empty] | Other | [42 empty] | Installing clips | 66
21024 | Vanderbilt Graduate Housing | 2023-05-11 | Marvin blanco | installing flashing | Subcontractor | Drake De Tomasi | false |  |  |  |  | 2 | 6 | false |  | latter | false |  |  |  |  | Flashing | [32 empty] | 10 | 6
21040 | 801 Church | 2023-05-11 | Marvin blanco | drilling holes in the tubes because they are not in the right place | Subcontractor | Nick Akins | false |  |  |  |  | 7 | 10 | false |  | 2 forklift | false |  |  |  |  | Tubing | [28 empty] | 5 | 70
22033 | 127 RLP Tempo Hotel | 2023-05-11 | Marvin blanco | installing panels and insulation. | Subcontractor | Marc Ribar | false |  |  |  |  | 15 | 150 | false |  | 3 boomlift | false |  |  |  |  | Plate |  |  | 27 | 150
22044 | DLR IAD 44 | 2023-05-11 | Jean negron | download the delivery, we installed 10 today. The complete box could not be finished for the reason that the wall is not finished. More details in the Photos. We cleaned the roof of all the junk material. | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 | 50 | true | Paneles . Flashing, coping, | Scaffold | false |  |  |  |  | ACM Caulking Flashing Insulation Subgirt Zee | 10 | 30 | [18 empty] | 0 | 1 |  |  |  |  | 80 | 2 |  |  | 80 | 2 | 20 | 2
22054 | Amazon IAD 169 | 2023-05-11 | Fredy veliz | Section A,B and C steel structure is not builded correct 2 of the horizontal tube are 2" off the vertical tube we have to notch the Chanel's | Subcontractor | Colton Van Meter | [5 empty] | 6 | 11 |  |  | 3 boom lifts and forklift | [5 empty] | Other | [42 empty] | Installing clips | 66
21040 | 801 Church | 2023-05-10 | Marvin blanco | making holes on every tubes because they make it in wrong places | Subcontractor | Nick Akins | false |  |  |  |  | 9 | 11 | false |  | forklift | false |  |  |  |  | Tubing | [28 empty] | 1 | 110
22033 | 127 RLP Tempo Hotel | 2023-05-10 | Marvin blanco | installing tubes and also panels | Subcontractor | Marc Ribar | false |  |  |  |  | 16 | 10 | false |  | 3 boomlift and 1 forklift | false |  |  |  |  | Plate Tubing |  |  | 15 | 50 | [24 empty] | 110 | 80
22044 | DLR IAD 44 | 2023-05-10 | Jean negron | 3 modified panels were installed, they had to be cut .. ç16 ..c16 ..c16.. ç05 b.. ç08 .. ç08..ç08. all the ç08 were cut to 17 inches.. all the ç16 were cut to 20 inches more details in the Photos | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 | 50 | false |  | Scaffold | false |  |  | 5 |  | ACM Coping Flashing Insulation Layout Subgirt Zee | 4 | 20 | [24 empty] | 200 | 10 |  |  | 200 | 10 | 50 | 5 | [6 empty] | 40 | 5
22054 | Amazon IAD 169 | 2023-05-10 | Fredy veliz | Third boom lift show up today at 11 am | Subcontractor | Colton Van Meter | [5 empty] | 6 | 11 |  |  | 3 boom lifts and forklift | [5 empty] | Other | [42 empty] | Installing clips | 66
22054 | Amazon IAD 169 | 2023-05-09 | Fredy veliz | Raining today we had too stop for 3 hours | Subcontractor | Colton Van Meter | [5 empty] | 6 | 11 |  |  | 2 boom lifts one forklift | [5 empty] | Other | [42 empty] | Installing clips | 48
22054 | Amazon IAD 169 | 2023-05-09 | Jean neron | I watched all day | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 0 | false |  |  | false |  |  |  |  | ACM
22044 | DLR IAD 44 | 2023-05-08 | Jean negron | It was installed,, z,, insulation,, panels,, cleaning .. | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 | 50 | false |  | Scaffold | false |  |  |  |  | ACM
22054 | Amazon IAD 169 | 2023-05-08 | Fredy veliz | Other companies working under on the generator we have to work around the and skip some section until they finish | Subcontractor | Colton Van Meter | [5 empty] | 6 | 11 |  |  | 2 boom lifts and forklift | [5 empty] | Other | [42 empty] | Installing clips | 66
23010 | Morgan Building Repair | 2023-05-07 | Chad mccoy | We started our day making panels again and installing them as we went. There are a couple glue up panels that need to be built and so trim around the doors need to be re worked. We be did that as we went. We made panel and then installed it and then made the next and installed it. We did not make all the panels and then install bc we needed to do minor adjustments to each panels for looks and alignment due to the wood behind the panels being hit by the car and the water making it swell we installed all the panels and then we made and installed the trim around one of the doors. It was yet again to dark to work so we called it and we will do the finishing touches tomorrow morning. | Subcontractor | Dillon Bowman | true |  |  |  | We had severe storms come threw and it hindered about 1.5 hrs of work. But we pressed on after | 2 | 14 | false |  |  | false |  |  |  |  | ACM | 12 | 10
22044 | DLR IAD 44 | 2023-05-06 | Jean negron | the box number was weighed, ç, installed, z, insolation.. flashing | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 | 40 | false |  | Scaffold | false |  |  |  |  | ACM
23010 | Morgan Building Repair | 2023-05-06 | Chad mccoy | We started our morning driving to the job. We arrived around 145-2 pm. We met with josh over the dealership and then we started taken the panels down. Once all the panels were removed we started making panels and reinstalling them. We installed and made 4 panels and then it started getting dark. The canopy lights do not work so working till midnight wasn’t going to happen. So we cleaned up and headed to our hotel | Subcontractor | Dillon Bowman | false |  |  |  |  | 2 | 7 | false |  |  | false |  |  |  |  | ACM | 4 | 2.5
22044 | DLR IAD 44 | 2023-05-05 | Jean negron | it was installed the panels that were missing coping. coulking, more details in the photos. finished, moved all the remaining material, cleaning | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 | 50 | false |  | Scaffold | false |  |  |  |  | ACM |  | 30
22054 | Amazon IAD 169 | 2023-05-05 | Fredy veliz | Need one more boom lift to finish at the end of may | Subcontractor | Colton Van Meter | [5 empty] | 6 | 11 |  |  | 2 boom lifts and forklift | [5 empty] | Other | [42 empty] | Installing clips | 66
22044 | DLR IAD 44 | 2023-05-04 | Jean negron | 7 panels were installed .. 50 feet of coping. and all the coping was cut and modified to be cut to cut two .. and 4 manufactured b15 .. b16 .. b17 ..b18 .... flashing installation .. moving panels cleaning... | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 | 45 | false |  | Scaffold | false |  |  |  |  | ACM | 7 | 30
22054 | Amazon IAD 169 | 2023-05-04 | Fredy veliz | Cold weather | Subcontractor | Colton Van Meter | [5 empty] | 6 | 11 |  |  | 2 Boom lifts and forklift | [5 empty] | Other | [42 empty] | Installing clips | 66
22054 | Amazon IAD 169 | 2023-05-03 | Fredy veliz | Everything going good weather is not very good | Subcontractor | Colton Van Meter | [5 empty] | 6 | 11 |  |  | 2 boom lift 120 and forklift | [5 empty] | Other | [42 empty] | Installing clips | 66
22054 | Amazon IAD 169 | 2023-05-03 | Jean negron | 10 panels were installed, 7 were cut, material was moved on site | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | false |  | Scaffold | false |  |  | 1 |  | ACM Flashing Layout | 10 | 40 | [30 empty] | 2 | 5
22054 | Amazon IAD 169 | 2023-05-02 | Fredy veliz | rain for couple hours | Subcontractor | Colton Van Meter | true | Raining for couple hours |  |  | Raining | 6 | 11 |  |  | 2 boom lift and forklift | [5 empty] | Other | [42 empty] | Installing blades and installing clips on the next section | 66
22054 | Amazon IAD 169 | 2023-05-01 | Fredy veliz | Having a hart time finding material and steel company Is moving material on building 179 and they been parking trailers on front of our materials obstructing the road making spend more time carry material by hand | Subcontractor | Colton Van Meter | true | Trailers obstructing the material , hard to find material are mixed in the creates and no labels |  |  |  | 6 | 11 |  |  | 2 boom lift , forklift | [5 empty] | Other | [42 empty] | Installing channels on section f,g,k Installing the flange support in the Chanel's Getting the blades ready to install | 66
22054 | Amazon IAD 169 | 2023-04-27 | Fredy veliz | Section M blades are miter in the bottom section they need to be cut at 6' straight cut | Subcontractor | Colton Van Meter | [5 empty] | 6 | 11 |  |  | 2 boom lifts and forklift | [5 empty] | Other | [42 empty] | Installing clips and Chanel section K,L,G | 66
22054 | Amazon IAD 169 | 2023-04-26 | Fredy veliz | I found the blades I was looking for I had to open all the creates because the labels was gone because the rain | Subcontractor | Colton Van Meter | [5 empty] | 6 | 11 |  |  | 2 Boom lift and forklift | [5 empty] | Other | [42 empty] | Installing clips on the elevation k,L,G | 66
22039 | Amazon IAD 606 | 2023-04-25 | Chad mccoy | We started our morning installing cleat for the coping, front and back of wood blocking . The cleat is not the right dimension for the coping. SEE DELAYS. a new method had to be made for install. So the front is engaged in the cleat and the back is screwed with 2 inch screws. The front of the coping has a hymn but all the hymns are closed. So these all have to be opened. As we went with the coping we also installed panels and flashing that needed to be installed in the door sections. The splice plates are not normal splice plates. They are 10 feet sections. There is a lot of overage of material with certain colors and then there are a smaller amounts in other colors. At the nf of the day we started organizing and cleaning for tomorrow demobilization. | Subcontractor | Eric Gutierrez | false |  |  |  |  | 2 | 9 | false |  | 2 scissor lifts | false |  |  |  |  | Coping Corrugated / Screen wall Flashing | [22 empty] | 6 | 1 | [8 empty] | 75 | 1.5 | [6 empty] | 90 | 5
22054 | Amazon IAD 169 | 2023-04-25 | Fredy veliz | Can't find some blades Material labels are going cause rain | Subcontractor | Colton Van Meter | [5 empty] | 6 | 10 |  |  | 2 boom and forklift | [5 empty] | Other | [42 empty] | Installing blades on the section m,n,p,q | 66
22054 | Amazon IAD 169 | 2023-04-24 | Fredy veliz | Some dimensions are wrong in the elevevatio M | Subcontractor | Colton Van Meter | [5 empty] | 6 | 11 |  |  | 2 boom lifts and forklift | [5 empty] | Other | [42 empty] | Installing Chanel's on the section m,n,p,q | 66
22039 | Amazon IAD 606 | 2023-04-21 | Chad mccoy | We continued our day installing the louvers, We had to install the louver pan and then he louvers. The concrete guys were installing all day so we had to get them out of our area and then we set the louvers. After the louvers were set we started instaing flashing and trim around the louvers and we started in starting the panels inbetween the concrete guys were all over and there was fresh concrete under our areas of work. So we cleaned up and left. For the weekend | Subcontractor | Eric Gutierrez | false |  |  |  |  | 2 | 4 | false |  | 2 scissor lifts | false |  |  | 0.5 |  | Corrugated / Screen wall Flashing Layout Louvre | [22 empty] | 15 | 1 | 2 | 1 | [6 empty] | 70 | 1
22054 | Amazon IAD 169 | 2023-04-21 | Fredy veliz | Section m drawings do not match with structure | Subcontractor | Colton Van Meter | [5 empty] | 6 | 9 |  |  | 2 boom lifts and forklift | [5 empty] | Other | [42 empty] | Prep and install beams | 54
22039 | Amazon IAD 606 | 2023-04-20 | Chad mccoy | We started our day turning the corner and getting the areas ready for the louvers. We could not install the louver due to the concrete guys working behind the louver holes so instead we install the hole white tall wall and all of the bottom to the door opening. Once the concrete guys were out of the way we then installed two louvers over the door and we prepped the louver hole at the corner for tomorrow morning | Subcontractor | Eric Gutierrez | false |  |  |  |  | 2 | 8 | false |  | 2 scissor lifts | false |  |  | 1 |  | Corrugated / Screen wall Flashing Layout Louvre | [22 empty] | 45 | 5 | 2 | 1
22054 | Amazon IAD 169 | 2023-04-20 | Fredy veliz | Section M,N,P&Q part of the structure is no builded the correct size | Subcontractor | Colton Van Meter | [5 empty] | 6 | 11 |  |  | 2 boom lifts and forklift | [5 empty] | Other | [42 empty] | Prep and install clips | 66
22039 | Amazon IAD 606 | 2023-04-19 | Chad mccoy | We started our morning Transferring lines from one slight column to the next leg, so that we can keep the Panels inline. As soon as I was done, we then started to run it up the slide column with a slight Panels on the slate, J. What’s the slate Panels in the slight Jay was finished. We then went to the white louvers and filled in that area.. And then we started again with the slate, J and a slate. Panels. Drake and Eric came by today. We talked for about 1520 minutes and then I went back to work. Ended our day doing the last dark side of p clad panels on the wall. . it’s pretty much a reputational thing over and over and over. You do a section you set up for the next little section then you finish that section and then you said it for the next section and each one has its own color it’s only to be in its own install so technically there are 13 individual sets of install set up everything just on the P clad panels. | Subcontractor | Eric Gutierrez | false |  |  |  |  | 2 | 8 | false |  | 2 scissor lifts | false |  |  | 1 |  | Corrugated / Screen wall Flashing Layout | [22 empty] | 60 | 6 | [8 empty] | 60 | 1
22054 | Amazon IAD 169 | 2023-04-19 | Fredy veliz | The need articulating 120 boom lift I was not working I called the and the fixed at 3:30 pm | Subcontractor | Colton Van Meter | true | One of the boom lifts was not working |  |  | Good | 6 | 11 |  |  | 2 boom lifts and a forklift | [5 empty] | Other | [42 empty] | Prep and installing clips | 66
22039 | Amazon IAD 606 | 2023-04-18 | Chad mccoy | We started our morning continuing the slate color panels up the steel beams. The j has to be ran up both sides and the each individual piece has to be cut to fit and tripped in. This is because u can not slide these pieces from the top of the j and clear the pclad clips. So it has to be cut to barely fit and then slide in to the spot it needs to be installed and then moved into place with a bar and a pick. Then we have lay out lines that these pieces must meet. So our panels stay the same upon reaching the height of the structure. Once the slate is installed all the way up we then go below the louvers and install all the color match pclad panels and all the j for each individual section. There is a lot of layout and individual pieces for each individual section. The Z was suppose to be 1 1/4 that was made for the sections that the pclad needed to be ripped down and tripped in with out Any pclad clips. But the Z was all made at 1 1/2. So a different method has to be made to make these sections hold in place. Each individual section is its own entity, but each section can not be installed till the section before it is done. So there’s no working two sections at a time. We had a meeting with the door guys, Karen from hitt, and the framer today, The door guy says he might not have anything for 2 weeks on the doors. And the frame that were put up have to be redone. So once we are done if the doors aren’t in I can not do the panels in the sections of the doors. | Subcontractor | Eric Gutierrez | true | Meeting over doors 40 minutes |  |  | Clear 77 | 2 | 9 | false |  | 2 scissor lifts | false |  |  | 2 |  | Corrugated / Screen wall Flashing Layout | [22 empty] | 42 | 4 | [8 empty] | 150 | 2
22054 | Amazon IAD 169 | 2023-04-18 | Fredy veliz | Haven't issues with structure not line up properly and one of the boom lifts it only work with one person | Subcontractor | Colton Van Meter | true | One boom is not working properly |  |  | Wind little high | 6 | 11 |  |  | 2 boom lifts and 1 forklift |  |  |  | 10 |  | Layout Other | [42 empty] | Installing and prep clips | 56
22026 | CSCC - Arts & Technology | 2023-04-17 | Keith Dukarm | Did the concert spots today then moved to back bump out we keep the Zs done a inch cause they have not put there peel and stick on yet ..we got most of it done will finish tomorrow..there will be some drip flashing brought and we will put up what we can | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 3 | 8 | false |  | .boom lift | false
22039 | Amazon IAD 606 | 2023-04-17 | Chad mccoy | We started our day getting to the site and going thru to make sure nothing was moved or damaged. The scissor lifts had been moved and left on. I had the control boxes in the truck all week so someone else used there box and left them on. So we stopped what we were doing and we went and got extension cords. When we got back we plugged them up and started laying out. The door areas are still not done . Karen asked me to do those areas last. So after a extensive layout and material stage for each section we started cutting panels for our first wall. Once the panels were cut we installed the lower drip trim and starter track and then we ran the j channel up the precast wall and then we started running the panels. We ran that wall up and then went around the corner past the door. The framing around the door sticks out past the steel 1/2-5/8 of a inch. This will cause the pclad panels to not set right with the louver install. We waited on Karen and she said we will see what happens when the door is installed. So after looking at the rest of the framing we went to the next section and started running starter trim and track and j. The wind was high this after noon so we had to re crate and strap down all panels prior to leaving | Subcontractor | Eric Gutierrez | false |  |  |  |  | 2 | 8 | false |  | 2 dead scissor lift | false |  |  | 3 |  | Corrugated / Screen wall Flashing Layout | [22 empty] | 32 | 5 | [8 empty] | 100 | 2
22054 | Amazon IAD 169 | 2023-04-17 | Fredy veliz | Material mixed in the creates for diferent areas | Subcontractor | Colton Van Meter | [5 empty] | 6 | 11 | true | Corrugated panels , flashings , screws | 2 boom lifts and forklift | [5 empty] | Other | [42 empty] | Finding and moving materials | 66
22026 | CSCC - Arts & Technology | 2023-04-14 | Keith Dukarm | Worked on entrance way this morning ..got that done and did some of the places where the panels sit in...redid the mock up..and put the Zs back on the door they fixed | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 3 | 8 | false |  |  | false
22026 | CSCC - Arts & Technology | 2023-04-13 | Keith Dukarm | Had orientation this morning then started entrance way... | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 3 | 8 | false |  |  | false
22026 | CSCC - Arts & Technology | 2023-04-12 | Keith Dukarm | Showed up this morning for orientation and they couldn't do it agian said it would be tomorrow..we finished the wall we started on and moved lift around back to do the bump out we got it done but after talking with Eric we took the drip back down ..we had to remove Zs on the wall we did yesterday cause door is in wrong spot...any way tomorrow we will be starling on entries way.. | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 3 | 8 | false |  | Boom lift | false |  |  |  |  | Subgirt Zee
Memphis wellness center waterproofing | #NO MATCH | 2023-04-12 | Chad mccoy | We started our morning taking the gate apart and moving the boom in place to start our removal of ,teal, then caulk a little gap, then install peel and stick and then reinstall the metal and then caulk the seam that ranged from 1/4 to 1 inch. The first 2 pieces of metal already had peel and stick on it but we re covered it and sealed it with caulking so the was no question on that section. We continued this method all the way down the long side of the wall. Along the wall the things that changed was the metal that was installed. The gaps varied and the metal behind the metal removed was in most places cut horrible and wavy. The peel and stick along the sections failed and was falling down. So in 6 places the original peel and stick had to be removed and then replaced and sealed. We went all the way down and turned the corner. We could not reach the last 5 feet due to the reach of the boom. I did call drake and let him know. We also re sealed all the skyward joints on the coping. No old sealant was removed. A heavy wide bead was placed over these sections to make sure adequate area coverage of the seal. We cleaned up and moved the boom back to the parking lot. We rebuilt the gate and we went on our way. | Subcontractor | #NO MATCH | false |  |  |  |  | 2 | 8 | false |  | Electric boom. | false |  |  |  |  | Caulking | [20 empty] | 200 | 8
22026 | CSCC - Arts & Technology | 2023-04-11 | Keith Dukarm | Started the day we was supposed to go orientation but it was Spanish speaking so we will do outs tomorrow..but anyways me and John mark got the bench mark so we could start..waited for limestone guy to come to figure his lay out finally figured out the door is in wrong place we got the layout and hung the Zs the door will have to be moved tomorrow we will be moving to back bump out to do it they did get it water proofed... | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 3 | 8 | false |  | Boom lift | false |  |  |  |  | Subgirt Zee | [30 empty] | 420
22026 | CSCC - Arts & Technology | 2023-04-10 | Keith Dukarm | First day on the job getting stuff situated..seeing what all is ready and what can be done ...we worked on mock up...tomorrow they are supposed to get us some lines so we can start our layouts .. | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 3 | 8 | false |  | Boomlift | false
22039 | Amazon IAD 606 | 2023-04-06 | Chad mccoy | We started our day continuing the louvers. We had not received the drip flashing to do the 3 white louvers that was missing it’s flashing . So we did our three louvers we could do and then we started laying out for the place install, but upon looking at the structure. The buildout the framers did at the bottom of the structure. It’s short 5 inches. It’s suppose to be 1’4” from the bottom of the steel. But they pulled 1‘4” from the top of steel. This will move and mess up our plclad in the low spot of the face of each sheet. Hitt was told and hitt came out and verified that the framers messed up per the framers prints. So we sit around till a answer was made. But no one ever said anything. The drip flashing that was missing in the original shipment did not arrive till 315 this evening. So today was another wasted day. | Subcontractor | Eric Gutierrez | true | This hole job is a delay. The structure is framed wrong or not finished being framed. The wood blocking finally started going on at 1230 pm today. The louvers have being wrong on the color and the framers builds our wrong per there own prints. |  |  | Hot 82 Sunny | 2 | 10 | true | Drip flashing @315 | 2 scissor lifts | false |  |  |  |  | Flashing Louvre | [24 empty] | 3 | 1.5 | [6 empty] | 15 | 0.3
22039 | Amazon IAD 606 | 2023-04-05 | Chad mccoy | We started this morning on the upper louvers. We pulled our first louver and we pulled the drip pan. We installed the drip pan and we started our layout left to right and upon this layout I saw that the louvers over lapped each other. So we measured the louver next to it and rechecked the louver hole. After this we measured the hole for ml6. And upon this lay out we found that the louvers were 2 inches short of the louvers below that were installed. So calls were made and mistakes were found and plans were made to send the louvers off and repaint them to the right color. So re were instructed to crate the louvers all together and get them ready for pick up. But upon pick up the van they sent was to small so the crate had to be remodified to fit in the van. This hole situation took way longer than it should have. It was a waste of most of the day. We installed as many louvers as we could. No one else is working on the areas ahead of us. There are no doors or frames going in. And there are no wood blocking going in. And the framers stopped installing frames around the structure today to. | Subcontractor | Eric Gutierrez | true | Horrible day on install, louvers wrong size, Louvers wrong color and no other trades getting stuff done ahead of us |  |  | Sunny 82 | 2 | 10 | false |  | 2 scissor lifts | false |  |  | 1 |  | Layout Louvre Trim | [24 empty] | 7 | 4 | [10 empty] | 50 | 1
22039 | Amazon IAD 606 | 2023-04-04 | Chad mccoy | We started our morning, redoing the two louvers that we installed yesterday with the new install message instead of using the aluminum L pieces that was provided by ap Performance. Once we get it down to 100%, we started with all the louvers up that we could. We are missing seal pan for ml4. I let Eric know. He got with a P performance and they’re supposed to be another one in route by Monday. This is going to cause that section of louvers not to be installed until it arrives. But when it comes to delays, the generator people have a generator testing facility, set up with 60 or 70 cables running through that’s gonna keep us from getting over there to do pclad and louvers. The stud framing is not finished on both of the sides. The doors are not in and neither is the wood blocking for the coping. So, even when we get all the livers in, we can start part of the P cloud install, but we are going to be stopped due to the lack of install by other trades | Subcontractor | Eric Gutierrez | false |  |  |  |  | 2 | 10 | true | Pclad and 4 crates | 2 scissor lifts | false |  |  | 2 |  | Layout Louvre Trim | [24 empty] | 13 | 6 | [10 empty] | 75 | 1
22039 | Amazon IAD 606 | 2023-04-03 | Chad mccoy | We started our morning doing our rushed orientation that went over nothing, After our orientation we went and looked at our install are? The framing wasn’t ready. They slow played the install all day. We were expecting the louvers this morning but they didn’t make it till almost 1. Our hrs of install are from 530-6 to 330. And no saturdays. So today was a bust with a late delivery and the framing being a bust and hitt killing our install time. It was a crap day. We started installing the louvers and and laying out but the new install of the louvers are a bust. There is a section at the top of the louver and bottom that gets 2 L shaped angles tht have a thru bolt but when u do the offset of the angle the thru bolt will not have enough to hold the angles together. So a z will be used in the place of the angle at the bottom and the top for safety and proper installation | Subcontractor | Eric Gutierrez | true | Louvers ran late. And a grounds keeper on a lawn mower ran over our drip pans for our louvers. Hitt and his managers where called |  |  | Clear /75 | 2 | 8 | true | Louvers | 2 scissor lifts | false |  |  | 1 |  | Layout
21008 | 900 Church | 2023-03-31 | Marvin blanco | installing acm panels and also remaking panels because they make it too big | Subcontractor | Dillon Bowman | true | flashing |  |  |  | 6 | 11 | false |  | boomlift | false |  |  |  |  | ACM | 4 | 66
21040 | 801 Church | 2023-03-31 | Marvin blanco | installing tubes in the parking garage | Subcontractor | Nick Akins | false |  |  |  |  | 10 | 11 | false |  | forklift | false |  |  |  |  | Tubing | [28 empty] | 500 | 110
21008 | 900 Church | 2023-03-30 | Marvin blanco | installing acm panels | Subcontractor | Dillon Bowman | true | flashing |  |  | good condition | 4 | 11 | false |  | boomlift | false |  |  |  |  | ACM | 10 | 44
21040 | 801 Church | 2023-03-30 | Marvin blanco | We finally received the tubes to be able to continue working after 8 days waiting, thank God today we were able to download the material and now we are happy, hopefully the next load will not fail | Subcontractor | Nick Akins | false |  |  |  |  | 10 | 11 | true | tubes for parking garage | forklift | false |  |  |  |  | Other | [42 empty] | moving tubes | 110
22033 | 127 RLP Tempo Hotel | 2023-03-30 | Marvin blanco | installing clips for tubes in the east side | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 11 | true | washers for embeds | boomlift | false |  |  |  |  | Other | [42 empty] | clips for tubes | 44
21008 | 900 Church | 2023-03-28 | Marvin blanco | installing ACM panels and also insulation and z's | Subcontractor | Dillon Bowman | false |  |  |  |  | 7 | 11 | false |  | boomlift | false |  |  |  |  | ACM Hat Channel | 8 | 40 | [32 empty] | 200 | 37
21024 | Vanderbilt Graduate Housing | 2023-03-28 | Keith Dukarm | Started with tool box talk scissor and swingstage safety proper tie offs ...went to meeting they need to have area cleaned by end off week..they should finish swing stage by tomorrow...they started on columns.. | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 6 | 8 | false |  | Swing stage scissor lift | false
21024 | Vanderbilt Graduate Housing | 2023-03-28 | Marvin blanco | installing panels moving swing stage | Subcontractor | Drake De Tomasi | false |  |  |  |  | 7 | 11 | false |  | swing stage and scissors lift | false |  |  |  |  | ACM | 8 | 77
21040 | 801 Church | 2023-03-28 | Marvin blanco | waiting on tubes | Subcontractor | Nick Akins | true | tubes |  |  | good condition | 10 | 11 | false |  | forklift | false |  |  |  |  | Other | [42 empty] | nothing just waiting | 110
22033 | 127 RLP Tempo Hotel | 2023-03-28 | Marvin blanco | installing angles for tubes at north side and west side we have a couple of embeds missing | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 11 | false |  | boomlift | false |  |  |  |  | Other | [42 empty] | angles for tubes | 44
21024 | Vanderbilt Graduate Housing | 2023-03-27 | Keith Dukarm | Started the day off just by catching up with whats been going on...then had a tool box talk basically on swing stage safety..then went to the meeting had Omar go with me so he could hear what was said I did the talking ..they continued to install panels in the alley part ..they did get a shipment today I believe it was panels for the 2 columns out front | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 6 | 8 | true | Panels and metal | Swing stage | false
22039 | Amazon IAD 606 | 2023-03-25 | Chad mccoy | We started our day getting the scissor lift out of the building and prepping everything for dismantle. Once everything was in place we started removing panels. The sign electrical was in the way so we had to sit it in the icon for reinstallation. All the panels had to be removed and the new panels had to be built from the dimension of the left over opening. We started with the bottom on reinstallation and fab and once it was built and installed we then did the second and then the third. Once all panels were installed we installed a new trim in between the black soffit and the white soffit . The panels were caulked out and the we wiped down everything and cleaned up our work area and I took pictures to end our day. | Subcontractor | Eric Gutierrez | true | The electrical was not placed right for dismantle and the Acm we brought had scratches all in it. And there was long intentions in the Acm that made selection of each panel on the sheets of amc time consuming due to all three sheets having heavy imperfections. |  |  | Windy and sleeting. 31 degrees | 2 | 7 | false |  |  | false |  |  |  |  | ACM | 3 | 4
22007 | Albion in the Gulch | 2023-03-18 | Chad mccoy | We started our day at Mcdougal getting material and everything loaded and ready. I also picked up Kevin and we’re headed to the job site. Want to go to the job site we are moving everything out of the truck. I had everything to work area and then I went and parked the. Truck. I soon as I got back telling me to go see if you could find a J and we needed. Kevin walked down the garage where everything was staged but it wasn’t there. I then called Clark, and they said it might be moved to the bottom of the garage. Kevin 2 floors up and all the way down looking . We were told it was thrown away. I went to Mcdougal to see if I could get more material. There was no Jay at Mcdougal just Panels. So I made some phone calls and then I went back to pick up Kevin and all the tools. . Dropping Kevin off at the shop and we ended our day | Subcontractor | Dillon Bowman | true | Material was thrown away by Clark |  |  | Cold/clear | 2 | 4 | false |  |  | false |  |  |  |  | ACM | 0 | 0
22044 | DLR IAD 44 | 2023-03-17 | Rony | Having some issues installing the coping due to the northside, had to extra inches due to the insulation and disease, we were delayed by Hitta by asking cleaning, requesting us to maintain the area clean it. Here’s my proof, and I prove on the photos. | Subcontractor | Dillon Bowman | false |  |  |  |  | 6 | 60 | false |  |  | false |  |  |  |  | ACM
21024 | Vanderbilt Graduate Housing | 2023-03-16 | Keith Dukarm | Toolbox talk ..swing stage safety, properties offs, P.P.E is all in correct working order..then I did inspections on swing stage .. went to meeting same thing just making sure the guys are all on same page ...they got corner done Jesse got metal cut for the cross soffit is ready they drop stage for corner on bridge everything should be finished tomorrow... | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 6 | 8 | false |  | Swing stage | false
22044 | DLR IAD 44 | 2023-03-16 | Rony | we struggle today installing the top pieces on the penthouse due to that is very uncomfortable very delayed. Two guys passing another two guys passing on another floor and another two guys on the roof. Very slow process | Subcontractor | Dillon Bowman | false |  |  |  |  | 6 | 60 | false |  |  | false |  |  |  |  | ACM
21024 | Vanderbilt Graduate Housing | 2023-03-15 | Keith Dukarm | Helped marvin first thing this morning with crane work at 801 took bout 2 hrs then back to Vanderbilt had to do a safety walk through where Jesse's stressed on straightening are material out and making more space ...the guys finished bridge work and started put trim pieces on the roof ... | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 5 | 8 | false |  | Swing stage | false
22044 | DLR IAD 44 | 2023-03-15 | Rony | Unable to work due to too much weather, when was blowing 45 mph winds of gusts | Subcontractor | Dillon Bowman | true |  |  |  | 45 miles gust of winds | 6 | 0 | false |  |  | false |  |  |  |  | ACM
21024 | Vanderbilt Graduate Housing | 2023-03-14 | Keith Dukarm | Tool box talk swingstage safety..did inspections on swing stage after putting it together..filled out JSA then went to meeting ...after that I did a walk around on our punch for the south tower we had to things and it was just the 4 panels they told them to leave off so they could pour concrete...talked to Jesse he said he was going to fix the beam in that soffit and cut the tabs off on corner .. | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 6 | 8 | true | Some metal angle...some insulation...and a few panels | Swing stage | false
22044 | DLR IAD 44 | 2023-03-14 | Rony | Unable to work due to weather delays | Subcontractor | Dillon Bowman | true | The weather is having wind gusts up to 45 mph |  |  |  | 6 |  | false |  |  | false |  |  |  |  | ACM
21024 | Vanderbilt Graduate Housing | 2023-03-13 | Keith Dukarm | Toolbox talk ..did inspections and went to meeting..had to fix 2 panels at the Hyatt took a hr then back to Vanderbilt to keep an eye on the guys they had a decent day they want them to consolidate the crates ... | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 6 | 8 | false |  | Swing stage | false
22044 | DLR IAD 44 | 2023-03-13 | Rony | Finish installing the louvers and the coauking was also completed. We also install some panels on up in the house. They were a couple guys. They were moving material and scratch or Panos. I’m gonna post the pictures already notify it’s regarding the situation. | Subcontractor | Dillon Bowman | false |  |  |  |  | 6 | 60 | false |  | One boom lift | false |  |  |  |  | ACM
20067 | BNA PROJECT 5 | 2023-03-12 | Antonio | Installed paneling, galvanized braces, flashing, and cups | Subcontractor | Marc Ribar | [5 empty] | 8 | 8 |  |  | Boom lift, forklift | [5 empty] | ACM Coping Flashing Plate | 27 | 6 | 12 | 2 | [28 empty] | 190 | 4 | [6 empty] | 70 | 3
20067 | BNA PROJECT 5 | 2023-03-11 | Antonio | Installed panels, galvanized braces, and flashing | Subcontractor | Marc Ribar | [5 empty] | 10 | 10 |  |  | Boom lift, forklift | [5 empty] | ACM Flashing Plate | 30 | 6 | 10 | 3 | [28 empty] | 70 | 2
21024 | Vanderbilt Graduate Housing | 2023-03-10 | Keith Dukarm | Started with tool box talk ..then talked to the guys to see what the plan was for today then continued to do my daily and inspections..Omar went to meeting I had to run to another job just to find out it wasn't ready so I came back .. they guys to good today kept glasses on all day lol have to tell them once a day .. other then that it was a good day tomorrow they will be moving stage to set up on another run ... | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 6 | 8 | false |  |  | false
22044 | DLR IAD 44 | 2023-03-10 | Rony | We tried to install louvers, but we couldn’t continue due to the weather | Subcontractor | Dillon Bowman | false |  |  |  |  | 6 | 12 | false |  |  | false |  |  |  |  | ACM
21024 | Vanderbilt Graduate Housing | 2023-03-09 | Keith Dukarm | First thing tool box talk swing stage set up tie offs life lines and rope grabs safety glasses and gloves..then went to the meeting listen to how they have so many days to get done ...explained to guys what the meeting was about ..they got stages set up and material staged ... | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 6 | 8 | false |  | Swing stage | false
22044 | DLR IAD 44 | 2023-03-09 | Rony | Had issues in the morning we had our material in the roof and we had to move all material. We lost about six hours in the morning. | Subcontractor | Dillon Bowman | true | Due to their fixing the roof where we had our materials, we lost about six hours |  |  |  | 6 | 60 | false |  | One boom lift | false |  |  |  |  | ACM
20067 | BNA PROJECT 5 | 2023-03-08 | Antonio | Installed panel around light fixture, removed panel from interior,placed metal plates for panels on lower south side of terminal, continued running panels on top roof of BNA, chalked panels | Subcontractor | Marc Ribar | [5 empty] | 11 | 10 |  |  | Scissor lift and 60 foot lift | [5 empty] | ACM Caulking Plate | 6 | 3 | 5 | 2 | [16 empty] | 10 | 4
22007 | Albion in the Gulch | 2023-03-08 | Keith Dukarm | Went to Vanderbilt did my inspections and JSA. Went to the meeting made sure Omar was aware of what needs to be done ..they also had a site meeting after that I went to Albion and continued to help get everything done ...we are 100 percent done there as far as I know . | JWMCD Crew | Dillon Bowman | false |  |  |  |  | 3 | 8 | false |  |  | false
22044 | DLR IAD 44 | 2023-03-08 | Rony | Having issues installing dude to the weather. we also had a cut panels around the door. The measurement on the door on a dry, and did not match the door on the henhouse. Two guys moving material to the roof. | Subcontractor | Dillon Bowman | false |  |  |  |  | 6 | 60 | false |  | Boom lift 1 | false |  |  |  |  | ACM | 12 | 60
21024.2201 | Vanderbilt Graduate Housing | 2023-03-07 | Keith Dukarm | Tool box talk got with Omar to see what the plan was for today did inspections and filled out JSA. Went to meeting. Went to Albion went to shop then back to Albion hung other wall only thing left is some trim and caulking ..Vanderbilt will be moving stages tomorrow | JWMCD Crew | #NO MATCH | false |  |  |  |  | 6 | 8 | false |  | . | false
21046 | The Moore Building | 2023-03-07 | Chad mccoy | We started our day we started making and installing the back panels on the upper part of the big planter. The last panels besides the one panel that needs to be rolled have a pretty good layout prior to install and build. There are no square sides and 2 panel have a 3”-35 degree angle cut. I layed these out and cut and built these panels and installed them. Once these were done we started peeling the seams and caulking. The bad thing about caulking is that the wind was like a tornado and spun the shaving around and now I have to re do the caulking. So after this we didn’t caulk anymore. So I have one panel that is a kick panel and an angle pitch and it goes under the bar. This panel took a little while to imagine and layout. It had 6 cuts and 4 routes. But with a little modifying as we installed it’s up and secure. We got the go ahead to install the panels under the bar so we started the kick plates and then we started installing the panels under it. The first panel was a z shaped panel with 4 route . But I realize that we were out of the screws I was using to install these panels so we stopped and we went and bought screws and will finish in the morning | Subcontractor | Drake De Tomasi | false |  |  |  |  | 2 | 8 | false |  |  | false |  |  | 2.5 |  | ACM Caulking Layout | 7 | 3 | [18 empty] | 20 | 0.5
22044 | DLR IAD 44 | 2023-03-07 | Rony | We had a difficult day due to the weather the wind blowing very hard | Subcontractor | Dillon Bowman | false |  |  |  |  | 6 | 60 | false |  | One boom lift | false |  |  |  |  | ACM
21024 | Vanderbilt Graduate Housing | 2023-03-06 | Keith Dukarm | Tool box talk . Filled out JSA and inspection sheets went to meeting ..then made sure guys was aware of what the meeting was about ...then I went to Albion to start the install on the 9th floor single skin panels that wasn't installed at the time when we was there we actually finished one side with install of panels just have to put trim on it .the pictures im going to attach are from both jobs that I am on | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 6 | 2.5 | true | Looked like a skid of single skin.. |  | false
22044 | DLR IAD 44 | 2023-03-06 | Rony | You had a good day installing | Subcontractor | Dillon Bowman | false |  |  |  |  | 6 | 60 | false |  | One boom lift | false |  |  |  |  | ACM
20067 | BNA PROJECT 5 | 2023-03-04 | Antonio | Removed panel for light fixture and traced out cut out then removed cut out panel. | Subcontractor | Marc Ribar | [5 empty] | 10 | 10 |  |  | Man lift | [5 empty] | ACM Flashing | 24 | 10 | [30 empty] | 150 | 6
20067 | BNA PROJECT 5 | 2023-03-03 | Antonio | Storm prep | Subcontractor | Marc Ribar | [5 empty] | 10 | 8 | [8 empty] | Other | [42 empty] | Prep materials for storm | 8
21063 | LTW061 | 2023-03-03 | Dh | We did clean up and 30 panels were cut | Subcontractor | Josh McPherson | [5 empty] | 8 | 10 |  |  | 4 booms lifts | [5 empty] | Corrugated / Screen wall | [22 empty] | 34 | 68
21087 | Long Hollow Baptist Church | 2023-03-03 | Fredy veliz | Job 100 % complete included panel reinstall | Subcontractor | Colton Van Meter | [5 empty] | 3 | 8 |  |  | No equipment | [5 empty] | Plate |  |  | 12 | 24
22044 | DLR IAD 44 | 2023-03-03 | Rony | Unable to work due to weather too much rain | Subcontractor | Dillon Bowman | true |  |  |  | Rían | 5 | 0 | false |  |  | false |  |  |  |  | ACM
21024 | Vanderbilt Graduate Housing | 2023-03-02 | Keith Dukarm | Same as yesterday tool box in the morning inspection papers filled out went to meeting had they got the 2 panels made for bottom of window still need to install..finished caulking return panels on roof | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 6 | 8 | false |  | Swing stage scaffolding scissor lift | false
21046 | The Moore Building | 2023-03-02 | Chad mccoy | I started my day at mcdougal preparing material for install at moore building. I had to make the kick plates and all the panels that wrap the bottom. I made a lot bc the left over material will be the bottom kick plate for the upper section of the bench. I loaded everything up and a dolly cart and headed to the site. I unloaded everything and got it to level 8 and I started installing. The curved parts were tricky. But with wood clamps and screws I was able to shape the pieces to what I needed. I put all the A 112s on the panels and the on the bench and I lined the seams up and attached the panels to the bench. There is one panel that I was going to make it 2 pieces but I think I can make it all in one. So I have to grab material from mcdougal and then I will head to install Monday | Subcontractor | Drake De Tomasi | false |  |  |  |  | 1 | 5 | false |  |  | false |  |  | 2.5 |  | ACM Layout | 5 | 2.5
21046 | The Moore Building | 2023-03-02 | Chad mccoy | I started my morning, going to the Moore building and removing the panels that Brody installed and adjusting them to hoars specs. Oh, one panel has to go back with me to Mcdougal to be remade to it to be bigger to adjust for moving the other panel. Before I left, I went ahead and install the bottom to Panels and all the little trims. I took measurements on the access doors, and I turned them into Joe Hoyle. I came back to Mcdougal and I made my new panel and then I went back to the job site and I installed it. Before I left, I took four pages of measurements so that I could cut and make all the little trim pieces that I needed to start the other bench. | Subcontractor | Drake De Tomasi | false |  |  |  |  | 1 | 6 | true | 1 new panel and 3 panels that were already made |  | false |  |  |  |  | ACM | 4 | 3
21063 | LTW061 | 2023-03-02 | Dh | We were shaken out the louvers materials | Subcontractor | Josh McPherson | [5 empty] | 8 | 10 |  |  | 4 booms lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 25 | 68
22044 | DLR IAD 44 | 2023-03-02 | Rony | We were told by the GC to remove the insulation. We move the insulation. Remove the Panos already installed.. total of five people working moving material removing cleaning to make it work. | Subcontractor | Dillon Bowman | true | We had to remove the existing the previous day. We install the installation and disease we had to take it off. |  |  |  | 5 | 50 | false |  | Boom lift | false |  |  |  |  | ACM | 16 | 50
|  | 2023-03-02 | Antonio | Hour of housecleaning work area as well | Subcontractor | [6 empty] | 9 | 8 |  |  | Spider lift, scaffold | [5 empty] | ACM Other | 3 | 3 | [40 empty] | Removing film off panels and cleaning it with goo gone | 6
20067 | BNA PROJECT 5 | 2023-03-01 | Antonio | One group inside putting corner pieces on floor 3 and other group installing panels out on lower segment of roof | Subcontractor | Marc Ribar | true | Weather conditions, and faulty lift |  |  | Windy with light showers | 10 | 8 |  |  | Spider lift | [5 empty] | ACM Other | 10 | 6 | [40 empty] | Removing plastic wrap off panels and washing panels | 2
21024 | Vanderbilt Graduate Housing | 2023-03-01 | Keith Dukarm | Started with tool box talk.Then did inspection on swing stage filled out JSA.We had a stand down in plaza for entire work place after that me and others had to walk with 2 of Dunns guys around the building to see what has to be done they have 60 days left ...they guys worked finishing Broadway and put closure pieces on roof..the end of day I went to AMI to pick somthing up... | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 6 | 9 | true | Scissor lift | Swing stage scaffolding scissor lift | false
21063 | LTW061 | 2023-03-01 | Dh | 46 panels were cut and 40 lf of started extrusion | Subcontractor | Josh McPherson | [5 empty] | 8 | 10 |  |  | 4 booms lifts | [5 empty] | Corrugated / Screen wall | [22 empty] | 46 | 68
21087 | Long Hollow Baptist Church | 2023-03-01 | Fredy veliz | Job complete | Subcontractor | Colton Van Meter | [5 empty] | 2 | 4 |  |  | Boom lift | [5 empty] | Plate |  |  | 2 | 8
22044 | DLR IAD 44 | 2023-03-01 | Rony | A moving material to the roof. installing Z clips and installation | Subcontractor | Dillon Bowman | true | We measure the north elevation and came out to be the wall is bigger by 3 1/2 inches |  |  |  | 6 | 60 | false |  | One boom lift | false |  |  |  |  | ACM | 8 | 10
21024 | Vanderbilt Graduate Housing | 2023-02-28 | Keith Dukarm | Started the day off with tool box talk ..basically just having everything tied off and be aware of your surroundings..then I inspected swingstage so them guys could get to work...filled out jsa and inspection sheet then went to meeting ...didn't nothing really happen today as far as safety told couple guys to put there glasses on ...they finished corner of Broadway except the 2 bottom panels on each column do to they are pouring concrete..other then that was pretty good day | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 6 | 8 | false |  |  | false
21063 | LTW061 | 2023-02-28 | Dh | 44 panels were cut | Subcontractor | Josh McPherson | [5 empty] | 8 | 10 |  |  | 4 booms lifts | [5 empty] | Corrugated / Screen wall | [22 empty] | 55 | 68
22044 | DLR IAD 44 | 2023-02-28 | Rony | Oh, we had to move materials on boom lift to the roof to guys doing that moving scaffold to the roof assembling scaffold. We had to wait on materials the driver that arrive on the job site. we install save clips in insulation unpin house and move material to the | Subcontractor | Dillon Bowman | true | We had a delay. The truck driver arrived on job site. He was not waking up and he was holding traffic for four hours. |  |  |  | 6 | 60 | true | ACM insulation miscellaneous | One boom lift | false |  |  |  |  | Insulation Louvre Subgirt Zee | [24 empty] | 0 | 0 | 80 | 15 |  |  | 10 | 15
21024 | Vanderbilt Graduate Housing | 2023-02-27 | Keith Dukarm | Staryed with tool box talk..mostly jus be aware of surroundings keep eyes open..inspected stage that they didn't get to get on yesterday from there went to meeting talked about what we was doing and are plan to get done ...guys started working meet up with Joe later that day walked with him and Marvin.. | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 6 | 8 | false |  | Swing stage and scaffolding | false
21063 | LTW061 | 2023-02-27 | Dh | No | Subcontractor | Josh McPherson | [5 empty] | 8 | 10 |  |  | 4 booms lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 68 | 68
21087 | Long Hollow Baptist Church | 2023-02-27 | Fredy veliz | Removing panels on the screen walls | Subcontractor | Colton Van Meter | [5 empty] | 3 | 8 |  |  | Boom lift | [5 empty] | Other | [42 empty] | Removing 12 panels on the screen walls | 24
22044 | DLR IAD 44 | 2023-02-27 | Rony | We had to wait till the truck was delivered today we move material some panels came, scratched from the delivery or from the shop. You can see it in the images below. | Subcontractor | Dillon Bowman | true | Last two hours waiting for truck |  |  | Then it started raining | 5 | 40 | true | panels | One boom lift | false |  |  |  |  | ACM | 0 | 0
21024 | Vanderbilt Graduate Housing | 2023-02-24 | Keith Dukarm | Today started pretty good tool box talk .just making sure all the guys are on same page ..then I went to meeting while Omar got his guys going ..panels showed up for corner of Broadway got them off loaded ..Omar had to leave and go to another job while I stood and keep an eye on the guys ..towards the end of my work day I got a picture sent to me of one of the guys standing on the rail in swingstage..I was told I needed to address this right then ...Jesse was cool about it not really upset..so I had a conversation with the guys involved..I explained to them that this is a no no and this can't happen ...I did say if I got another message or I seen them they would be off the job..they understood..so I took care of the situation and will see how it goes from here | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 6 | 8 | true | Panels | Swing stage and scaffolding | false
21063 | LTW061 | 2023-02-24 | Dh | No | Subcontractor | Josh McPherson | [5 empty] | 6 | 10 |  |  | 3 booms lifts | [5 empty] | Corrugated / Screen wall | [22 empty] | 68 | 44
21024 | Vanderbilt Graduate Housing | 2023-02-23 | Keith Dukarm | Started the day by having tool box talk mostly safety ..after that me and Omar went up and inspected swing stage everything was fine ...come done and told the guys they where good ..filled out jsa and inspection sheets went to meeting ...they guys are moving a little slow just a bunch of kids ...hopefully tomorrow they will get the panels for Broadway..I did have a meeting at 3 me and Omar over the incident that happen last week ...everything went well they are happy how we have went above and beyond to make things better I had got them danger tape and signs they was happy bout that ...and just the way McDougalls JSA papers are and how I been writing what are plans are for the day...over things are good ... | JWMCD Crew | Drake De Tomasi | false | [5 empty] | 9 | false |  | Swing stage | false
21063 | LTW061 | 2023-02-23 | Dh | We requested materials with no luck | Subcontractor | Josh McPherson | [5 empty] | 6 | 10 |  |  | 3 booms lifts | [5 empty] | Corrugated / Screen wall Hat Channel | [22 empty] | 45 | 20 | [10 empty] | 1300 | 24
21024 | Vanderbilt Graduate Housing | 2023-02-22 | Keith Dukarm | Today was messed up day got shut down cause of wind the guys started a lay out .and green gurt install on Broadway waited on scaffolding it arrived took guys bout 30 mins to unload and 30 to put one together 6 guys ..my bad I thought I hit send on this yesterday | JWMCD Crew | Drake De Tomasi | false | [5 empty] | 8 | false |  | Scaffolding | false
21024 | Vanderbilt Graduate Housing | 2023-02-22 | Marvin blanco | waiting for scaffolding 7 hours from 6 am to 1 pm with nothing to do because the lantern is not ready and we need a machine to work because we cannot fly | Subcontractor | Drake De Tomasi | false |  |  |  |  | 6 | 11 | false |  | swing stage and scaffolding | false |  |  |  |  | Other | [42 empty] | nothing we lose all day waiting for scaffolding | 66
21063 | LTW061 | 2023-02-22 | Dh | N/o | Subcontractor | Josh McPherson | [5 empty] | 6 | 10 |  |  | 3 booms lift | [5 empty] | Corrugated / Screen wall Hat Channel | [22 empty] | 68 | 20 | [10 empty] | 1300 | 24
21086 | Nashville SC Training Facility | 2023-02-22 | Fredy veliz | Job almost complete waiting for 2 panels to arrive | Subcontractor | #NO MATCH | [5 empty] | 4 | 8 |  |  | Boom lift | [5 empty] | Flashing Other | [32 empty] | 50 | 12 | [8 empty] | Install clips on the panels at the water fountain | 20
22019 | QTS ASH2 DC2 Lockridge | 2023-02-22 | Marvin blanco | installing metal panels and also acm panels | Subcontractor | Josh McPherson | true | base flashing |  |  |  | 10 | 10 | false |  | 4 boomlift | false |  |  |  |  | ACM | 30 | 110
22040 | Moses Nissan | 2023-02-22 | Jean negron | Today we caulk all coping and caulk all around door ass well we made up 2 panel the are the one in the east elevation we take off the paper as well and we check on the panels around the building and there is some panels the have been damaged and they were normally not like this and other panels in the front side on top have been damaged too I will leave photos for u guys but this panels was not damaged | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 36 | false |  | 1Boom lift | false |  |  |  |  | ACM | 0 | 0
21024 | Vanderbilt Graduate Housing | 2023-02-21 | Keith Dukarm | I work 8 hrs not them...started this morning inspecting stage and just seeing what they got done . Then did the jsa and inspection sheet ..after that went to the meeting and listened to what was going on and what needs to be done ..they started the day off by peeling panels on remaining wall the got stage down and started dismantling it..2 guys jumped in smaller stage and started to prepare the wall for panels they finally got the metal up after lunch then power cable quit working so that stopped them there by that time my 8 hrs was up I called back an hr later and there was still no power so we will see tomorrow when I get there on what was done... | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 6 | 8 | false |  | Swing stage | false
21024 | Vanderbilt Graduate Housing | 2023-02-21 | Marvin blanco | moving materials moving swing stage and also JE DUNN cut the power from the swing stage so we lose all day moving materials and waiting for power 🔋 also we have to be waiting for the weather proof fix the lantern because they haven't ready | Subcontractor | Drake De Tomasi | false |  |  |  |  | 6 | 11 | false |  | swing stage | false |  |  |  |  | Other | [42 empty] | nothing because JE DUNN IS NOT READY | 66
21063 | LTW061 | 2023-02-21 | Dh | No | Subcontractor | Josh McPherson | [5 empty] | 6 | 10 | [8 empty] | Corrugated / Screen wall Hat Channel | [22 empty] | 70 | 20 | [10 empty] | 600 | 24
21024 | Vanderbilt Graduate Housing | 2023-02-20 | Keith Dukarm | First day on job sent there to keep things safe and keep it organized.. first thing was a meeting this morning this is Marvin's job Omar is Forman so I sat in meeting with omar..after that we went and inspected swingstage they would be working on ...everything to my knowledge was good everything was tight and all pins where in ...so from there had to fill out inspection sheet for it ..then they got to work ..they took a corner piece of stage off and started hanging panels while I was there they got 2 on I did my 8hrs and left so not sure what got done after I left I do know that there where not any stages moved .. | JWMCD Crew | Drake De Tomasi | true |  |  |  | Some rain most nice | 5 | 8 | true | Looked like a skid of single skin.. | Swing stage | false |  |  |  |  | ACM
21024 | Vanderbilt Graduate Housing | 2023-02-20 | Marvin blanco | installing acm panels and also moving swing stage | Subcontractor | Drake De Tomasi | false |  |  |  |  | 6 | 11 | false |  | swing stage | false |  |  |  |  | ACM | 8 | 66
21063 | LTW061 | 2023-02-20 | Dh | We have requested rivets couple time with no answer and also have requested shims with no luck | Subcontractor | Josh McPherson | [5 empty] | 6 | 10 | [8 empty] | Corrugated / Screen wall Hat Channel | [22 empty] | 46 | 20 | [10 empty] | 500 | 24
22019 | QTS ASH2 DC2 Lockridge | 2023-02-20 | Marvin blanco | installing metal panels and also acm panels | Subcontractor | Josh McPherson | true | flashing for columns |  |  | good | 11 | 10 | false |  | 4 boomlift | false |  |  |  |  | ACM Corrugated / Screen wall | 30 | 60 | [20 empty] | 50 | 50
jeep Detroit Michigan | #NO MATCH | 2023-02-20 | Marvin blanco | fixing panels the punch list | Subcontractor | #NO MATCH | false |  |  |  |  | 4 | 12 | false |  | scissors lift | false |  |  |  |  | ACM | 4 | 44
22040 | Moses Nissan | 2023-02-19 | Jean negron | Today we finish up everything ,everything was caulk alll the trash was thrown it away just one last panel the the leave is too short to make up the panel but we have make it work we finish installing all the panels on the west and nort elevations we cut and modify some panels 6 hrs extra on doing this crafting we also had issues on installing this panels Bcs the wall was not really In level | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 54 | false |  | 1 boom lift | false |  |  |  |  | ACM | 0 | 0
22040 | Moses Nissan | 2023-02-18 | Jean negron | Today we work on completely everything around the building we also crag panels we got issues Bcs the acm leave is to short it was 8 hrs extras on crafting this panels but I will leave information pictures | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 48 | false |  | 1 boom lift | false |  |  |  |  | ACM | 0 | 0
21063 | LTW061 | 2023-02-17 |  | No work due to rainy day | Subcontractor | Josh McPherson | [5 empty] | 6 | [9 empty] | ACM
21087 | Long Hollow Baptist Church | 2023-02-17 | Fredy veliz | Missing 2 panels on the fountain, the panels the we installed we nene to install some angle , because is not place to attach | Subcontractor | Colton Van Meter | [5 empty] | 4 | 9 |  |  | Boom lift | [5 empty] | Plate |  |  | 24 | 36
21024 | Vanderbilt Graduate Housing | 2023-02-16 | Marvin blanco | We had problems disassembling a swing stage and they kicked us out for 3 days and the guys will learn this time | Subcontractor | Drake De Tomasi | false |  |  |  |  | 6 | 11 | false |  | swing stage | false |  |  |  |  | ACM | 8 | 66
21063 | LTW061 | 2023-02-16 | Dh | We had a delivery and we had asked like multiple time for shims and rivets and we never got them please get us what we need to get the job done please you guys should whats needed to complete the work | Subcontractor | Josh McPherson | [5 empty] | 6 | 10 |  |  | 2/45 ft boom lifts | [5 empty] | Corrugated / Screen wall Hat Channel | [22 empty] | 50 | 20 | [10 empty] | 460 | 12
21087 | Long Hollow Baptist Church | 2023-02-16 | Fredy Véliz | The framing dimensions was made incorrect the horizontal tubing are 1-1/2" off from the center of the joint | Subcontractor | Colton Van Meter | [5 empty] | 4 | 4 |  |  | Boom lift |  |  |  | 14 |  | Layout
22019 | QTS ASH2 DC2 Lockridge | 2023-02-16 | Marvin blanco | installing ACM PANELS and also metal panels | Subcontractor | Josh McPherson | true | base flashing silicone and reveals |  |  | good | 11 | 10 | false |  | 4 boomlift | false |  |  |  |  | ACM Corrugated / Screen wall | 30 | 60 | [20 empty] | 30 | 50
22033 | 127 RLP Tempo Hotel | 2023-02-16 | Marvin blanco | checking embeds and layout with Nick and Mark | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 2 | false |  | walking | false |  |  |  |  | Other | [42 empty] | just checking embeds | 8
22040 | Moses Nissan | 2023-02-16 | Jean negron | We couldn’t be able to work reason of remaining all day | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 0 | false |  | 0 | false |  |  |  |  | ACM | 0 | 0
21046 | The Moore Building | 2023-02-15 | Chad mccoy | We started our morning, going to Mcdougal to meet with Joe and pick up a piece of a panel so that we can do a couple things at the site. Once we got to the site we went. to the eighth floor to do the motor enclosure on the left-hand side. This one was a little bit trickier due to the placement of the steel framing in the wall for the window that opens and closes. Once this was installed, we headed down to see if the ceiling has been removed for the L-shaped metal that was at the shop. The ceiling had not been removed so we Got everything ready so that we could go do the little panel by the louvers off the boom lift after this we had to just hang around until Joe brought us some more metal. Joe dropped off the kick plate metal and the L-shaped header metal over the big garage entrance of the main building. We laid out and measured for the placement of the kickplate. It had to be done in two pieces. Once I was laid out and cut out, we installed it. As we were installing the kickplate, the ceiling tiles were being removed so that the L-shaped metal could go on. We did not use the boom lift for this. We use the scissor lift due to lack of accessibility with other trades and material around the area. We pulled this as we went so as soon as the last piece was up with pulled it and we were done | Subcontractor | Drake De Tomasi | false |  |  |  |  | 2 | 8 | true | Joe dropped off kickplate metal and ACM pieces for the L-shaped header | 45 foot boom | false |  |  | 1.5 |  | ACM Layout | 8 | 4
21063 | LTW061 | 2023-02-15 | Dh | No notes | Subcontractor | Josh McPherson | [5 empty] | 6 | 10 | [8 empty] | Corrugated / Screen wall Hat Channel | [22 empty] | 64 | 32 | [10 empty] | 770 | 22
21087 | Long Hollow Baptist Church | 2023-02-15 | Fredy veliz | Checking the foundation whit the project manager and GC | Subcontractor | Colton Van Meter | [5 empty] | 1 | 4 |  |  | Boom lift | [5 empty] | Other | [42 empty] | Checking the foundation | 4
22040 | Moses Nissan | 2023-02-15 | Jean negron | Today was a good day we finish up the east elevation everything was perfectly done and in the was line up intead of a 2 panel and clónica the need to be craft ass week we mande many panels it was 24 extra in cuts I will leave photos of the Mabel the was made and otras the was craft | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 36 | false |  | Boom lift | false |  |  |  |  | ACM | 0 | 0
21063 | LTW061 | 2023-02-14 | Dh | No | Subcontractor | Josh McPherson | [5 empty] | 6 | 10 |  |  | 2-45 ft boom | [5 empty] | Corrugated / Screen wall | [22 empty] | 74 | 60
21087 | Long Hollow Baptist Church | 2023-02-14 | Fredy veliz | Concrete foundation and steel framing was made in reverse | Subcontractor | Colton Van Meter | [5 empty] | 4 |  |  |  | Boom lift | [5 empty] | Other | [42 empty] | Morning and checking panels | 16
22021 | VA-14 | 2023-02-14 | Joey laxton | installed coping | Subcontractor | Nick Akins | false |  |  |  |  | 4 | 10 | false |  |  | false |  |  |  |  | Coping | [40 empty] | 300 | 40
21046 | The Moore Building | 2023-02-13 | Chad mccoy | We started our day at mcdougal collecting everything for the Moore building that was ready. Once we got everything loaded we headed to the site. We started on the ground level with the door trim. We had to wait on joe to tell us how he wanted them installed. Once that was done we installed left right and upper trim. We need one more piece to make the door look finished. Once that was done we cleaned up. And started hauling material to the 8 floor. Once everything was on the 8 floor we started laying out for the s.clips that line up the new bottom panel with the upper that was already installed. We had to install the z panel in the back and then we installed the panel it’s self. To hold the panel in place we added little braces on the floor and on the top of the panel and up the side to help the panel set in the same plain as existing panel. Once these panel was signed off on, the boom arrived so we stopped what we were doing and moved to the ground level. I started by measuring for the panel that Installs by the louvers. Then we measured the louver slant gap, for joe to make a panel insert. Once that measurement was in to joe we moved to the 4 panel install around the edge of the building. The first and last panel had to be cut and routed to fit the window gaps. We installed the first 3 panels and then I capped off the edge of the louver. This had to be down before the last panel could be installed. Once that was done we cut and routed the last panel and we installed it. The louvers to the left of our panel are out of plumb. About 3/4 of a inch over 2 feet. After our last panel was installed I caulked and peeled the panels to finish. We cleaned up and moved the boom back to the other side of the building. | Subcontractor | Drake De Tomasi | true | We had a lot of work and then start on stopping and then I had to wait on the answers in certain places. On the ground level, we had to stop off at the door Because a lot of people open and shutting the doors and we had to wait on joe. There was multiple trades trying to work with the floor panels had to be installed |  |  | Clear. Sunny | 2 | 9 | false |  | 45 Boom | false |  |  | 1.5 |  | ACM Caulking Flashing Layout | 4 | 2 | [18 empty] | 30 | 1 | [10 empty] | 25 | 1
21063 | LTW061 | 2023-02-13 | Dh | 135 lf of trim was installed | Subcontractor | Josh McPherson | [5 empty] | 6 | 10 |  |  | 2-45ft boom | [5 empty] | Corrugated / Screen wall | [22 empty] | 48 | 60
22012 | QTS ASH2 DC1 Lockridge | 2023-02-13 | Marvin blanco | doing silicone | Subcontractor | Josh McPherson | true | base flashing for the columns |  |  |  | 11 | 11 | false |  | boomlift | false |  |  |  |  | Caulking | [20 empty] | 500 | 121
22012 | QTS ASH2 DC1 Lockridge | 2023-02-13 | Marvin blanco | doing silicone installing ACM panel's we don't have no more gray silicone and also no more backroll we have panels they to big for the wall south area | Subcontractor | Josh McPherson | true | base flashing |  |  | good | 11 | 11 | false |  | boomlift and scaffolding | false |  |  |  |  | ACM | 30 | 121
22021 | VA-14 | 2023-02-13 | Joey laxton | demoed 2 panels and installed 7 | Subcontractor | Nick Akins | false |  |  |  |  | 4 | 10 | false |  |  | false |  |  |  |  | ACM | 7 | 35
22040 | Moses Nissan | 2023-02-13 | Jean negron | Today we arrive to saint albans at 5 afternoon from charlotte nc but we starte working as soon we arrive and we try to work in the problem and craft all the panels in the west elevation we work on crafting this panels and it was 5 hrs extra on working in this panels by crafting | Subcontractor | Colton Van Meter | false |  |  |  |  | 3 | 18 | false |  | 1 boom lift | false |  |  |  |  | ACM | 0 | 0
22040 | Moses Nissan | 2023-02-11 | Jean negron | Today we work on the coping and by finishing the wall it was a really good day everything in the west elevation have been installed all joint was perfectly matching I will leave photo for u guys but it was a really good day we pretty much close up everything | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 40 | false |  | 2 boom lift at tu | false |  |  |  |  | ACM | 0 | 0
22044 | DLR IAD 44 | 2023-02-11 | Rony | We completed the caulking on the north elevation most of the caulking is completed. We are off site until 2/23. | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 | 50 | false |  | Two boom lift one forklift | false |  |  |  |  | Caulking | [20 empty] | 1200 | 50
21063 | LTW061 | 2023-02-10 | Dh | No notes | Subcontractor | Josh McPherson | [5 empty] | 7 | 10 |  |  | 2-45'ft boom lifts | [5 empty] | Corrugated / Screen wall | [22 empty] | 48 | 60
22040 | Moses Nissan | 2023-02-10 | Jean negron | Si today we work on covering all the south elevation we work pretty good it was a good day and we craft a few panel the had a return of 4 in bigger we work pretty good we also work kn the coping on top I will leave more information for you guys in photos we pretty much work on layout out and it was 4 extras in crafting this panels | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 12 | false |  | 2 boom lift | false |  |  |  |  | ACM | 0 | 0
22040 | Moses Nissan | 2023-02-10 | Jean negron | Today we start installing and doing layout in the whole south elevation wall we work pretty good and we work in the west elevation also we work on the coping and we craft 4 panels that tools 2 hrs working on it we work pretty good it was a good day I’ll leave more information in photos | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 75 | false |  | 2 boom lift | false |  |  |  |  | ACM | 0 | 0
22044 | DLR IAD 44 | 2023-02-10 | Rony | We installed two louvers today and did some caulking | Subcontractor | Dillon Bowman | true |  |  |  |  | 2 | 20 | false |  | Two boom lifts one forklift | false |  |  |  |  | Caulking Louvre | [20 empty] | 190 | 8 |  |  | 2 | 4
21063 | LTW061 | 2023-02-09 | Dh | The 4 guys only work 7.5 per day from 7-00 am to 3:00 pm | Subcontractor | Josh McPherson | [5 empty] | 7 | 10 |  |  | 45' ft booms | [5 empty] | Corrugated / Screen wall | [22 empty] | 40 | 60
22044 | DLR IAD 44 | 2023-02-09 | Rony | We had a good day no issues. The back and Rod arrive like around 11. Me and one guy he is in the front putting back and rod with the back a little bit of caulking in the back so the baccarat wouldn’t go through. I did that everything was good. | Subcontractor | Dillon Bowman | false |  |  |  |  | 2 | 20 | false |  | Two boom lifts one forklift | false |  |  |  |  | Caulking | [20 empty] | 250 | 20
21063 | LTW061 | 2023-02-08 | Dh | No | Subcontractor | Josh McPherson | [5 empty] | 7 | 10 |  |  | 2-45 ft boom and 65'ft | [5 empty] | Corrugated / Screen wall | [22 empty] | 41 | 62
22044 | DLR IAD 44 | 2023-02-08 | Rony | Today was a good day. The weather was good we mostly were doing the caulking. Wet side west side I missing five louvers to finish the caulking west side. The west side I missing five louvers to finish the caulking. | Subcontractor | Dillon Bowman | false |  |  |  |  | 2 | 10 | false |  | To boom lift One forklift | false |  |  |  |  | Caulking | [20 empty] | 369 | 2
21024 | Vanderbilt Graduate Housing | 2023-02-07 | Marvin blanco | installing hat channels and also ACM panels | Subcontractor | Drake De Tomasi | false |  |  |  |  | 6 | 11 | false |  | swing stage | false |  |  |  |  | ACM Hat Channel | 3 | 33 | [32 empty] | 100 | 33
21063 | LTW061 | 2023-02-07 | Dh | No | Subcontractor | Josh McPherson | [5 empty] | 7 | 10 |  |  | 2-45'ft boom lifts and 65'ft | [5 empty] | Corrugated / Screen wall | [22 empty] | 46 | 62
22019 | QTS ASH2 DC2 Lockridge | 2023-02-07 | Marvin blanco | installing metal panels and also acm replacing panels in the north wall 4 panels taking 10 hrs for 2 guys | Subcontractor | Josh McPherson | true | base flashing for columns |  |  |  | 11 | 11 | false |  | boomlift | false |  |  |  |  | ACM Corrugated / Screen wall | 20 | 60 | [20 empty] | 35 | 61
22021 | VA-14 | 2023-02-07 | Joey laxton | installed acm, peeled poly | Subcontractor | Nick Akins | false |  |  |  |  | 5 | 10 | false |  |  | false |  |  |  |  | ACM | 20 | 50
22040 | Moses Nissan | 2023-02-07 | Jean negron | So todays we modify a few panels and we work on the layout and. Making a new panels we had really big issues there on the east elevation with our measuring BCS the joint was not matching with the glass join we really lost time but we work on modifying panels and installing layout we also work 4 hrs extra on making this panel and modifying the other I’ll leave more information in photos | Subcontractor | Colton Van Meter | false |  |  |  |  | 4 | 48 | false |  | 1 boom lift | false |  |  |  |  | ACM | 0 | 0
22044 | DLR IAD 44 | 2023-02-07 | Rony | We started caulking the louvers on the west side. One person, Caulking, the other person cleaning, and installing back Bacharach. | Subcontractor | Dillon Bowman | true | Not having the right size back and rod. One guy I’m fun cleaning and put them back in rod. |  |  |  | 2 | 20 | true |  | Two boom lifts, one forklift | false |  |  |  |  | Caulking | [20 empty] | 120 | 2
21024 | Vanderbilt Graduate Housing | 2023-02-06 | Marvin blanco | cutting stell losing all day | Subcontractor | Drake De Tomasi | false |  |  |  |  | 6 | 11 | false |  | swing stage | false |  |  |  |  | Other | [42 empty] | nothing install just doing other stuff | 11
21063 | LTW061 | 2023-02-06 | DH | We really need the rivets and hat channel | Subcontractor | Josh McPherson | [5 empty] | 7 | 10 |  |  | 2-45' ft boom lift | [5 empty] | Corrugated / Screen wall | [22 empty] | 34 | 70
22012 | QTS ASH2 DC1 Lockridge | 2023-02-06 | Marvin blanco | installing ACM panel's metal panels we are been waiting for base flashing 2 weeks almost 3 I hope some day gets delivered | Subcontractor | Josh McPherson | true | base flashing for bottom panels and backroll |  |  |  | 11 | 11 | false |  | boomlift | false |  |  |  |  | ACM | 30 | 121
22022 | Szott M59 Jeep Dealership Renovation | 2023-02-06 | Marvin blanco | fixing panels replacing panels | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 10 | false |  | scissors lift | false |  |  |  |  | Other | [42 empty] | replacing panels | 40
22040 | Moses Nissan | 2023-02-06 | Jean negron | Hey so today today we work on the east elevations and north elevation on working all to the top we had. Big issues that I guess this panel will need to be fabricated bcs the are to short I’ll leave photos for you guys to check on. we couldn’t keep it going the wall bcs of this we also cut 4 panels of the bottom the delay of cutting this panels was 6 hrs l’ll leave the rest of information in photos | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 60 | false |  | 1 boom lift | false |  |  |  |  | ACM | 0 | 0
21024 | Vanderbilt Graduate Housing | 2023-02-05 | Marvin blanco | fixing panels in the lanterns and also moving swing stage. | Subcontractor | Drake De Tomasi | false |  |  |  |  | 6 | 11 | false |  | swing stage | false |  |  |  |  | Other | [42 empty] | moving swing stage and fixing panels at the lantern | 66
22012 | QTS ASH2 DC1 Lockridge | 2023-02-05 | Marvin blanco | installing panels in the screenwall and also Acm panels downloading material | Subcontractor | Josh McPherson | true | backroll |  |  | could | 11 | 11 | false |  | boomlift and scaffolding | false |  |  |  |  | ACM | 44 | 121
22033 | 127 RLP Tempo Hotel | 2023-02-05 | Marvin blanco | taking layout and also cleaning embeds | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 11 | false |  | boomlift | false |  |  | 33 |  | Layout
21087 | Long Hollow Baptist Church | 2023-02-03 | Fredy veliz | The 3 portal are complete | Subcontractor | Colton Van Meter | [5 empty] | 4 | 6 | true | 4 steel panels | Boom lift | [5 empty] | Plate |  |  | 4 | 24
22010 | Ports Petroleum Fuel | 2023-02-03 | Chad mccoy | We started this morning getting there early so that we can try and get the boom started each morning it’s been -17 to- 23, So getting the boom started, it warmed up is something that we have to make sure happens prior to work. Once we get everything up and running, we had to go on top of the canopy and flash across the bottom of the canopy on the inside perimeter. We use the old flashing that is getting covered, but nobody will see it. We set this flashing in sealant, then screwed it in and then sealed the screws and the top seam. What’s this was done we started laying out and running to Panels on the right side of the canopy. The easiest way to cut out around the three tiebacks for the canopy is to do a square. I talked to the GC today and he said and agreed that clear caulking needs to be in these three squares so that he doesn’t get everywhere and if they have to go in and adjust the canopy, they can see what they’re doing besides blindly going into a blue sealant. What’s the right so I was done? I had to start taking Down the single skin. Are drilled out all the rivets that were holding on the last piece and then we tripped it out and then we took down the next piece to use as a reference line. Behind the single skin is insulation so all that had to be installed vertically so that we can make it the same everywhere. What’s this area was prepped I laid out for the new panel that I wanted to be cut to go all the way up to the top of the parapet wall. Then we had to go dig out a 13 foot piece out of the mound of snow that was on top of all the material. The 13 foot piece was on the very bottom. Once I transferred my layout to this piece of single skin, we cut it and then installed it. Once everything fit next to the canopy after a few tweaks, I liked it so we attached it and then went on to the next piece. Where I had to trip out the little piece I damaged it so we replaced it with the second piece that we took out and all was great. Now that the single skin is on, I can run the left AC and Panels on top of the canopy. We started off doing the small panel. That’s 5 inches. It had to be cut around the canapé perimeter on the left-hand side and then trip to the Place. And they were just stacked and went including another cut for the third time back. Once those panels were all the way to the top, the prayer pit we’ve been laid out. And took dimensions for the new panel that had to be made to follow the full length of the canopy. So I started building these panels but the AC it was so cold that we actually broke two returns by simply folding them up one time. So we moved everything inside we let the AC and warm up and then we continue to cut route and fab this panel that needed to go in the bottom. There is no room for clips, so I set this panel and sealant top bottom left and right. Once this was done, we cleaned up the trailer and all of our area and we called it a day. I have to finish doing the trim work on the single skin tomorrow and I have to finish ceiling everything on top the canopy that was added plus I have to build a little panel to the bottom right because there is an additional void underneath the canopy to the bottom right where there’s no single skin or Panels | Subcontractor | Eric Gutierrez | true |  |  |  | The high today was nine, but the feel like was -21. With the wind gust of 25 to 30 all day long | 2 | 8 | false |  | Boom | false |  |  |  |  | ACM Caulking Corrugated / Screen wall Flashing | 13 | 5 | [18 empty] | 45 | 1.2 | 2 | 1.5 | [8 empty] | 13 | 0.5
22040 | Moses Nissan | 2023-02-03 | Jean negron | Today we work in the south elevation of the building today was a pretty good day we really work in installing all panel and also the coping we had to modify some panel Bc of some problems we had with the measuring so we work like 4 hrs extra on doing cuts and modifying this panels i will leave more information in photo | Subcontractor | Colton Van Meter | true | Working on cuts the plans measurement didn’t consice with the measuring in the building we cut like 4 panel and we also had to made a node panel the was not send it was 1A70 but we made this panel out of 1A49 the we also need to modify too |  |  |  | 4 | 56 | false |  | 1 boom lift | false |  |  |  |  | ACM | 0 | 0
21063 | LTW061 | 2023-02-02 | DH | No notes | Subcontractor | Josh McPherson | [5 empty] | 7 | 10 |  |  | 2-45'ft and a 65'ft booms lifts | [5 empty] | Corrugated / Screen wall Hat Channel | [22 empty] | 18 | 30 | [10 empty] | 1000 | 32
22002 | DLR Sterling Premier Building A | 2023-02-02 | Rony | We received the glass they were missing arrive today. We try to make it work but it was not fitting. I spoke to Steve regarding how to make it work. We had to cut the inside of the frame to make the glass fit. It took about four hours for two guys, but in the end we made it worked. | Subcontractor | Steve Fudge | true | The glass will not fit in the opening, so we made it work by ripping the inside of the frame pocket to make it work, but the glass install |  |  |  | 2 | 8 | true | Glass | No equipment | false |  |  |  |  | ACM | 1 | 8
22010 | Ports Petroleum Fuel | 2023-02-02 | Chad mccoy | We started this morning getting there early so that we can try and get the boom started each morning it’s been -17 to- 23, So getting the boom started, it warmed up is something that we have to make sure happens prior to work. An additional add to this morning the wind was gusting up to 33 miles an hour, which dropped the temperature down to -21 for most of the day. So because the wind was gusting, so bad, we went on the opposite side of the building where the wind would not hit it so we could build all the panels do all the cuts put all the clips on get every panel we needed ready so that when we pull back around, all we had to do was grab and go. Our first two panels, but around the outlet the last outlet. And then the rest of them stacked on top of that for that stack. The next row was the row that supposed to connect to the canopy or run a half inch off of it. But during layout and observation of this canopy, it is shifted to the right 5 1/2 inches. This is causing the face of the panels to go inside the canopy dimensions, and to go over the canopy, left side edge where it was supposed to land, flush and vertically in line with the left side of the canopy. So layout was done Eric was called and decisions had to be made. Upon looking at this with the GC. I found that the single scan installers had a layout that we are half inch off if they had continued they’re single scan to the right one more piece. So Eric the GC and I all talked this over and we are going to do a time and money to fix all the problem areas because this is going to extend my install by a half of a day to 3/4 of a day due to all the modifications and extra install in Fab, that I have to do to make everything look pretty like we’re supposed to. Once we got the OK, we cut around the right side of the canopy and ran another stack of panels up to the top. After this stack of panels, we cleaned up and we headed to the Airbnb. | Subcontractor | Eric Gutierrez | true | The canopy is in the wrong spot. The single skin is not finished to the left side of the canopy. There is no flashing or drippage of any kind inside the canopy, where the blue skin comes down to touch the canopy, and it is not caulked. |  |  | Morning. -10 feels like -17. High 5 feels like -9 | 2 | 10 | false |  | Boom | false |  |  |  |  | ACM Caulking Flashing | 12 | 6 | [18 empty] | 10 | 0.3 | [10 empty] | 1 | 0.1
22021 | VA-14 | 2023-02-02 | Joey laxton | Installed acm | Subcontractor | Nick Akins | false |  |  |  |  | 5 | 10 | false |  |  | false |  |  |  |  | ACM | 13 | 50
22044 | DLR IAD 44 | 2023-02-02 | Rony | We install the west louvers it was a good day no issues we made it happen. | Subcontractor | Dillon Bowman | false |  |  |  |  | 4 | 40 | true | To create caulking in one miscellaneous in the other | Two boom lift one forklift | false |  |  |  |  | Louvre | [24 empty] | 26 | 40
21063 | LTW061 | 2023-02-01 | DH | No notes | Subcontractor | Josh McPherson | [5 empty] | 7 | 10 |  |  | 45'ft boom lift 65'ft | [5 empty] | Corrugated / Screen wall Hat Channel | [22 empty] | 16 | 30 | [10 empty] | 1200 | 32
22010 | Ports Petroleum Fuel | 2023-02-01 | Chad mccoy | We went in early this morning to make sure that the boom lift started and we had enough time for the day. We continued on the small wall, We had to cut out for the outlets and then continue running up to wall. Once this wall was finished, we packed everything up and moved to the other side of the building. We ran our flashing and in the middle of the second piece, where the curtain wall sinks, and the plywood pushes out and it leaves a half of an inch gap in between the flashing of the wall. We ran three pieces of flashing, and then we started running Panels. The third and fourth panel on the big wall, had to have two cuts in both of them for the outlets. Wants to cut for me and Panels were installed. We continue to run it up the building and then I rebuild it and then we started the second row. Our panels are level up the face but if you look to the Panels compared to the corrugated, it looks like our panels fall out but if you put a level on the corrugated corner bead, you will see that over 4 feet the corrugated falls in 3/4 of an inch. I told the GC, my stuff will be level. I am not going to follow improper insulation from another trade | Subcontractor | Eric Gutierrez | true | We are continuing to battle, the structure, the plywood, the other trades that installed before us, the loose outlets, and the crappy waterproofing |  |  | Cold -17 in morning -9 in the afternoon | 2 | 9 | false |  | Boom lify | false |  |  |  |  | ACM Caulking Flashing | 22 | 6 | [18 empty] | 59 | 1 | [10 empty] | 30 | 0.5
22021 | VA-14 | 2023-02-01 | Joey laxton | installed acm | Subcontractor | Nick Akins | false |  |  |  |  | 5 | 10 | false |  |  | false |  |  |  |  | ACM | 32 | 50
22040 | Moses Nissan | 2023-02-01 | Jean negron | Today we work on doing the layout we also cut 5 paneles the goes on the bottom to make it fit with the wall bcs it was to big we also had big issues on installing the front panel where the sing will be installed big problems in the system and plans | Subcontractor | Colton Van Meter | true | We had big delays in installing panels on the south elevation bcs of the system problem |  |  |  | 4 | 48 | false |  | 1 forklift | false |  |  |  |  | ACM | 0 | 0
22044 | DLR IAD 44 | 2023-02-01 | Rony | Today was a good day. We install seal pants and louvers. We were waiting for the painters to paint the west side, but we finish everything we could. Deonte gave us the greenlight to install the sill pants on the west side. The only small issues we were having it some openings for little tight. The louvers bulging a little bit. | Subcontractor | Dillon Bowman | false |  |  |  |  | 4 | 40 | false |  | Two boom lifts one Forklift | false |  |  |  |  | Louvre | [24 empty] | 18 | 40
21024 | Vanderbilt Graduate Housing | 2023-01-31 | Marvin blanco | installing plate panels angles and insulation | Subcontractor | Drake De Tomasi | false |  |  |  |  | 6 | 12 | false |  | swing stage | false |  |  |  |  | Hat Channel Insulation Plate |  |  | 22 | 40 | [22 empty] | 80 | 2 | [6 empty] | 180 | 30
21040 | 801 Church | 2023-01-31 | Marvin blanco | cleaning embeds and also installing clips for tubes | Subcontractor | Nick Akins | false |  |  |  |  | 4 | 12 | false |  | nothing | false |  |  |  |  | Other | [42 empty] | installing clips for tubes | 48
21063 | LTW061 | 2023-01-31 | DH | The new crew only works 7:00-3:00 PM we only worked 4 hrs due to rain | Subcontractor | Josh McPherson | [5 empty] | 7 | 4 |  |  | 45,ft boom lift 65,ft boom | [5 empty] | Corrugated / Screen wall Hat Channel | [22 empty] | 12 | 4 | [10 empty] | 0 | 16
22010 | Ports Petroleum Fuel | 2023-01-31 | Chad mccoy | Pics/videos | Subcontractor | Eric Gutierrez | false |  |  |  |  | 2 | 10 | false |  | Boom | false |  |  |  |  | ACM | 16 | 4
22010 | Ports Petroleum Fuel | 2023-01-31 | Chad McCoy | Pics | Subcontractor | Eric Gutierrez | false |  |  |  |  | 2 | 10 | false |  | Boom | false |  |  |  |  | ACM | 16 | 4
22010 | Ports Petroleum Fuel | 2023-01-31 | Chad mccoy | Pics | Subcontractor | Eric Gutierrez | false |  |  |  |  | 2 | 10 | false |  | 45 foot boom | false |  |  |  |  | ACM | 16 | 4
22010 | Ports Petroleum Fuel | 2023-01-31 | Chad mccoy | We got to the job site this morning and nobody was there. The radio said -17 But the weather channel said that it felt like -31. So first thing off the bat, I took pictures of the canopy that’s on the bigger side to install where it is tied back to the structure with three red tiebacks. I talked this over with Nick. He wants to do a horizontal cut down the panel. That way they can be horse shoot in I’m going to see how close they are to the middle of the panel and see what the best option is, if Nick’s option does not pan out. We started on the shorter side today, and the problem with the shorter side today was that the wood blocking was not equal to the curtainwall. There was exposed wood everywhere, and the electrical outlets had a three-quarter inch cap on majority of the sides of both outlets that needed to be sealed. All through the blue skin, there is penetrations screws, holes couches that need to be sealed. The GC asked us to simply caulk them, so we are caulking as we go. Once we got an answer on the wood, blocking and all the penetrations, we started pulling the flashing and Panels out so that we can install. As we got to the flashing, we found that the flashing is not painted properly. Videos and pictures of all the flashing was sent to Eric and Nick to show the imperfections that will be seen on the flashing. I have we hung two pieces of flashing. We started hanging the pants. After eight panels were on and a little bit of layout, we saw that nothing was going to fit left to right. So Panels had to be taken down and shifted to a 3/8 joint. Even with a 3/8 joint, we still have to cut 3/4 off of one of the panels. I talked this over with Nick and that’s what we decided to do. After this decision was made, we went down for our last piece of flashing, but upon further inspection of the flashing, we found that the paint is flaking off all of the flashing. So another decision was made to cut the hymn off of the ones that were on the building already. And to install the rest of the flashing upside down so the ham is behind the panels and the bottom will have a cut off. Look to it to the drip edge to the new flashing that Eric is got going through the painter and engineering can slip right over it and be caulked in the Place.. There is a lot of issues with the building left and right up and down compared to what we’re supposed to do compared to the Architecturals and I felt like all day today we just kept finding more and more stuff. Out of the 26 Panels, we pulled out of the crate three of them had what looked like a screw head Mark through the peel and into the paint. Pictures of this was sent to Eric and Nick. Out of the 26 panels that we removed nine of these Panels had to have excursions adjusted and corner clips because the encroached on the reveal pocket and reveals could not be slid into these pockets due to the tightness and improper build of these Panels. All penetrations that we do with screws to hold our panel on they are being caulked. The reason for this is that the waterproofing that was put in behind these panels is simply a air and water barrier. It is not a self healing water system. Since it is the same Henry water barrier that is used on the data centers I am treating it like a data center install and caulking all the screwheads. We are working in about an inch of ice and everything is covered in snow. It took close to an hour to get the boom lift just to start this morning before we left we plugged it up so the glow plugs could be warming up all night and the battery and we orientated it in a manner where we can get the truck next to it to help jump it off if need be. Two panels on the wall had to be cut for an electrical outlet. The next two panels that go above those two will also have to be cut for those same outlets because they fall in a joint.. We did not start installing Panels until close to 1145. That’s when our first paneling on | Subcontractor | Eric Gutierrez | true | Just read through my daily you’ll see the delays |  |  | -17 low. 1 was the high. Clear | 2 | 10 | true | I brought a crate full of Panels from Tennessee | 45 foot boom | false |  |  |  |  | ACM Caulking Flashing | 16 | 4 | [18 empty] | 50 | 1 | [10 empty] | 23 | 1
22019 | QTS ASH2 DC2 Lockridge | 2023-01-31 | Marvin blanco | installing Acm panels and also metal panels | Subcontractor | Josh McPherson | true | backroll red panels for canopy |  |  | could | 11 | 110 | false |  | boomlift | false |  |  |  |  | ACM Corrugated / Screen wall Hat Channel | 20 | 30 | [20 empty] | 30 | 30 | [10 empty] | 300 | 50
22040 | Moses Nissan | 2023-01-31 | Jean negron | Today we counts for much bus of snowing and raining more information hotoo | Subcontractor | Colton Van Meter | false |  |  |  |  | 4 | 32 | false |  | 1 boom lift | false |  |  |  |  | ACM | 0 | 0
22044 | DLR IAD 44 | 2023-01-31 | Rony | Sally was a bad day to work, unable to work due to the weather we install one panel on the west side | Subcontractor | Dillon Bowman | true | Waiting on painters |  |  | Raining all day weather delay | 4 | 8 | true |  | Two boom lifts one Forklift | false |  |  |  |  | Louvre | [24 empty] | 1 | 8
21024 | Vanderbilt Graduate Housing | 2023-01-30 | Joey laxton | installed acm panels | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 10 | false |  |  | false |  |  |  |  | ACM | 34 | 50
21024 | Vanderbilt Graduate Housing | 2023-01-30 | Marvin blanco | moving swing stage cleaning installing angles insulation | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 12 | false |  | swing stage | false |  |  |  |  | Hat Channel Insulation Plate |  |  | 3 | 2 | [22 empty] | 220 | 4 | [6 empty] | 180 | 54
21040 | 801 Church | 2023-01-30 | Marvin blanco | Se pusieron 17 click grandes.y 23 chicos y se iso limpieza de canales.tambien,17 big clicks were put on, and 23 small ones, and channels were also cleaned. | Subcontractor | Nick Akins | false |  |  |  |  | 4 | 12 | false |  | nothing | false |  |  |  |  | Other | [42 empty] | clips | 48
21063 | LTW061 | 2023-01-30 | DH | Everything is going good so far | Subcontractor | Josh McPherson | [5 empty] | 7 | 10 |  |  | 65'ft boom lift | [5 empty] | Corrugated / Screen wall Hat Channel | [22 empty] | 10 | 30 | [10 empty] | 1100 | 32
22019 | QTS ASH2 DC2 Lockridge | 2023-01-30 | Marvin blanco | installing angles metal panels and ACM panels | Subcontractor | Josh McPherson | true | backroll, screws |  |  | good | 11 | 11 | true | silicone | 3 boomlift | false |  |  |  |  | ACM Corrugated / Screen wall Hat Channel | 20 | 36 | [20 empty] | 20 | 48 | [10 empty] | 300 | 37
22040 | Moses Nissan | 2023-01-30 | Jean negron | Today we pretty much work on checking matorial was here and also work on the layout we had to make a little cuts in some panels we work on installing panels on the east elevation | Subcontractor | Colton Van Meter | false |  |  |  |  | 5 | 50 | true | acm panle aclips caulk screw | 1 boom lift | false |  |  |  |  | ACM | 0 | 0
22044 | DLR IAD 44 | 2023-01-30 | Rony | We install clips on the west elevation | Subcontractor | Dillon Bowman | true | We were delay because we had to wait on painters to go front of us before we started installing seal pins |  |  |  | 4 | 40 | false |  | Two boom lifts, one forklift | false |  |  |  |  | Other | [42 empty] | Clips | 40
22044 | DLR IAD 44 | 2023-01-28 | Rony | Three guys installing louvers. Two guys in installing siiii pans in clips. | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 | 8 | false |  | forklifts two boom lift | false |  |  |  |  | Louvre | [24 empty] | 15 | 40
21024 | Vanderbilt Graduate Housing | 2023-01-27 | Marvin blanco | moving swing stage and Also installing angles. | Subcontractor | Drake De Tomasi | false |  |  |  |  | 6 | 11 | true | panels and swing stage | 2 swing stage | false |  |  |  |  | Other | [42 empty] | angles | 66
21040 | 801 Church | 2023-01-27 | Marvin blanco | installing clips for tubes in the parking garage 87 clips level 7 to 11 | Subcontractor | Nick Akins | false |  |  |  |  | 6 | 11 | false |  | nothing | false |  |  |  |  | Other | [42 empty] | clips for tubes | 66
21063 | LTW061 | 2023-01-27 | DH | Everything is going well so far | Subcontractor | Josh McPherson | [5 empty] | 7 | 10 |  |  | 65'ft boom lift | [5 empty] | Corrugated / Screen wall Hat Channel | [22 empty] | 26 | 30 | [10 empty] | 1070 | 32
22012 | QTS ASH2 DC1 Lockridge | 2023-01-27 | Marvin blanco | installing panels in the screenwall and also checking some panels I think we have shortly panels at the freedom wall and we need backroll for silicone it's taking forever to get to the job site | Subcontractor | Josh McPherson | true | backroll |  |  | could | 12 | 11 | false |  | 3 boomlift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 45 | 132
22033 | 127 RLP Tempo Hotel | 2023-01-27 | Marvin blanco | taking layout and there is some embed they're not in the right place | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 11 | false |  | boomlift | false |  |  | 33 |  | Layout
22044 | DLR IAD 44 | 2023-01-27 | Rony | Today was a good day. We did really well more than expected. Had a little bit of issues with six openings. Where does CO pan was a little tight on the corners a banded a little bit, but it went through | Subcontractor | Dillon Bowman | false |  |  |  |  | 7 | 70 | false |  | Two boom lifts one forklift | false |  |  |  |  | Louvre | [24 empty] | 29 | 70
21063 | LTW061 | 2023-01-26 | Dh | We started installing single skin already 4 men crew showed up and stared installed hat channel | Subcontractor | Josh McPherson | [5 empty] | 7 | 10 |  |  | 65 ft boom lift | [5 empty] | Corrugated / Screen wall Flashing Hat Channel | [22 empty] | 30 | 30 | [8 empty] | 120 | 10 | 800 | 40
21087 | Long Hollow Baptist Church | 2023-01-26 | Fredy veliz | Portal are completo except for 4 panels that we waiting on then to arribe | Subcontractor | Colton Van Meter | [5 empty] | 4 | 8 |  |  | Boom lift | [5 empty] | Plate |  |  | 14 | 42
22044 | DLR IAD 44 | 2023-01-26 | Rony | Are you what’s the good day? It was cold, but was a good Day openings were great no it was cold, troubles. | Subcontractor | Dillon Bowman | false |  |  |  |  | 5 | 60 | false |  | Two boom lifts one forklift | false |  |  |  |  | Louvre | [24 empty] | 15 | 60
21063 | LTW061 | 2023-01-25 | Dh | We only worked 3 hrs due to a rainy day | Subcontractor | Josh McPherson | [5 empty] | 3 | 3 |  |  | 65'ft boom lift | [5 empty] | Hat Channel | [34 empty] | 250 | 9
21087 | Long Hollow Baptist Church | 2023-01-25 | Fredy veliz | Bad weather | Subcontractor | Colton Van Meter | [5 empty] | 4 | 5 |  |  | Boom lift | [5 empty] | Plate |  |  | 5 | 20
22002 | DLR Sterling Premier Building A | 2023-01-25 | Jean negron | Today we work on finishing all corners of the coping and we had to make cuts on every corner of the panhouse we also build up the door and installed in front side of the premium building we caulk all the windows but the door was still need to be caulk and on the bottoms side of the door we had some screw that haven’t been send and the door of the panhouse up in the roof still need to be caulk we couldn’t caulk bcs reason it was raining and trash also need to be through it always everything around us was close and we did not had space to through it and that pretty much it more information in photo | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 25 | false |  | 1 boom lift | false |  |  |  |  | Caulking | [20 empty] | 0 | 0
22021 | VA-14 | 2023-01-25 | Chad mccoy | We went in this morning and we were gonna start hanging the top row of Panels, but there were deliveries that had to go in through the garage door where my blue boom was. So, instead of installing first thing this morning, we started peeling and tripping in reveals and doing some caulking. That way we don’t have to do as much in the next couple of days. As soon as they were done with the deliveries, we started installing again.. We installed everything but the two panels that I have to hand make the one panel that I have to hand make is a bottom right panel that goes over the door entry way that the right side leg is 8 inches to Nero, and then the top one is the one that turns from the face of the Panels. We are installing to the penthouse section that Joey is doing. These panels will be done made tomorrow and installed tomorrow. It rained a lot today, but we needed to finish | Subcontractor | Nick Akins | true | Rain and delivers Slowed us down on installation, but we made it up |  |  | Rain / 37 | 4 | 8 | false |  | 32 foot scissor. 85 foot boom | false |  |  |  |  | ACM | 11 | 4
22021 | VA-14 | 2023-01-25 | Joey laxton | installed acm and peeled polly | Subcontractor | Nick Akins | false |  |  |  |  | 5 | 10 | false |  |  | false |  |  |  |  | ACM | 10 | 50
22044 | DLR IAD 44 | 2023-01-25 | Rony | It was raining all morning and still continue raining, but we went to the job site and install some steel pans | Subcontractor | Dillon Bowman | true | Rain and lightning |  |  | Raining | 5 | 25 | false |  | 2 booms one forklift | false |  |  |  |  | Louvre | [24 empty] | 0 | 0
21024 | Vanderbilt Graduate Housing | 2023-01-24 | Marvin blanco | moving swing stage installing panels installation | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 11 | false |  | swing stage | false |  |  |  |  | Plate |  |  | 7 | 44
21040 | 801 Church | 2023-01-24 | Marvin blanco | installing clips for tubes cleaning and also taking a layout | Subcontractor | Nick Akins | false |  |  |  |  | 4 | 12 | false |  | nothing | false |  |  |  |  | Other | [42 empty] | clips for tubes | 48
21063 | LTW061 | 2023-01-24 | DH | We continue installing hat channels | Subcontractor | Josh McPherson | [5 empty] | 3 | 10 |  |  | 65'ft boom lift | [5 empty] | Hat Channel | [34 empty] | 700 | 30
21071 | Google NBY-HUB 1 | 2023-01-24 | Marvin blanco | fixing stuff flashing doing silicone | Subcontractor | Steve Fudge | false |  |  |  |  | 4 | 11 | false |  | boomlift | false |  |  |  |  | Other | [42 empty] | fixing stuff flashing and others things | 44
21087 | Long Hollow Baptist Church | 2023-01-24 | Fredy veliz | No coments | Subcontractor | Colton Van Meter | [5 empty] | 4 | 8 |  |  | Boom | [5 empty] | Plate |  |  | 7 | 32
22002 | DLR Sterling Premier Building A | 2023-01-24 | Jean negron | We work on finishing the coping the coping is fully done and we also work in the door in front of the building work by finishing we also installed glass all windows was caulked and we put some rovers as well pretty much is most of what we did we also work on small details everything around was caulk and the copi was done I’ll leave photos for more information | Subcontractor | Steve Fudge | false |  |  |  |  | 9 | 90 | false |  | Boom lift 1 | false |  |  |  |  | Caulking Coping | [20 empty] | 0 | 0 | [18 empty] | 80 | 30
22012 | QTS ASH2 DC1 Lockridge | 2023-01-24 | Marvin blanco | installing metal panels everything is going OK for now | Subcontractor | Josh McPherson | false |  |  |  |  | 12 | 11 | false |  | 3 boomlift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 60 | 132
22021 | VA-14 | 2023-01-24 | Chad mccoy | . We pretty much picked up this morning, where we left off yesterday. Where they continue running starter strip up the right side of expansion joint up the tall wall before we could continue with the routed panels. We finished installing the panels up the left-hand side of the garage doors and then across the top and then we started on the top. Everything at the left-hand side has to be cut down to a finish face value of 40 inches. So there was quite a few cuts in quite a few routes today we had to cut out for scuppers. The scuppers took a big chunk out of the panels so they were flimsy during installation. We also had to carry a horizontal joint line from the right side of the panels that are being left off to the left side so that we could match elevational lines from the existing VA 13 and the panels we already installed. Once we matched up all the horizontal joint lines we went to start putting the top row of Panels on but the top roller Panels is an inch and a half two tall due to wood blocking so all of the top row has to be cut down and inch and a half on the length. Then, towards the end of the day, we had to swap out, empty crates for crates with Panels in it, so that we could start fresh in the morning, without having to walk a very long distance | Subcontractor | Nick Akins | false |  |  |  |  | 4 | 8 | false |  | 85 foot boom, 32 foot scissor | false |  |  | 1.5 |  | ACM Layout | 13 | 5.5
22021 | VA-14 | 2023-01-24 | Joey laxton | installed acm and flashing | Subcontractor | Nick Akins | false |  |  |  |  | 9 | 10 | false |  |  | false |  |  |  |  | ACM Flashing | 25 | 80 | [30 empty] | 50 | 10
22033 | 127 RLP Tempo Hotel | 2023-01-24 | Marvin blanco | trying to make orientation but the said no. so we went to take some laying out and see if the embed is going to work and I think it's correct for now the one's we took 🤔 | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 10 | false |  | boomlift | false |  |  | 40 |  | Layout
22044 | DLR IAD 44 | 2023-01-24 | Jean negron | We recive 2 boom lift martirial and more we start on installing flashing in the west side of the building we installed 27 flashing | Subcontractor | Dillon Bowman | false |  |  |  |  | 4 | 40 | true | 2 boom lift louvers matorial flashing screws | 2 boom light | false |  |  |  |  | Flashing | [32 empty] | 108 | 20
21063 | LTW061 | 2023-01-23 | Dh | 500 LF of hat channel were installed we only worked half of day due to rain | Subcontractor | Josh McPherson | [5 empty] | 3 | 5 |  |  | 65' ft boom lift | [5 empty] | Hat Channel | [34 empty] | 500 | 15
21087 | Long Hollow Baptist Church | 2023-01-23 | Fredy veliz | No coments | Subcontractor | Colton Van Meter | [5 empty] | 4 | 8 |  |  | Boom lift | [5 empty] | Plate |  |  | 11 | 32
22002 | DLR Sterling Premier Building A | 2023-01-23 | Jean negron | Today we had to take the material through the stairs we installed the copping and we also covered every corner we also cut the splazer of the coping | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 80 | false |  |  | false |  |  |  |  | Louvre | [24 empty] | 0 | 0
22021 | VA-14 | 2023-01-23 | Chad mccoy | . We started our morning, moving panels from the back of the building to the front. The TPO is now complete over the garage doors so we are able to set the flashing and then the bottom row of Panels. The wind has been blowing pretty gusty today. So we started off setting the flashing and then the Z and insulation that was missing. Every panel that we installed today, except for one had to be cut and rounded one of them on two sides. Due to the amount of stiffeners on these panels, this does take a little while but it is possible. We also had to have holes in the walls patch today where the 2 x 4 covering the upper garage door with the plastic wrap, was being blown around in the wind, and went through the drywall like a sword. We took pieces of reveal and screws and we attached this plastic wrap with that 2 x 4 securely because I do not want it going into our Panels. | Subcontractor | Nick Akins | true | The wind was blowing to the point where the panels were very hard to handle, taking them up the building. We only have 26 panels left that we can install so we ended our day at 8 hour day. I was concerned about safety with the guys under me and carrying the panels in my lift so I made the decision to leave |  |  | Rain and windy | 4 | 8 | false |  | 85 foot boom. 32 foot scissor | false |  |  | 1 |  | ACM Flashing Insulation Layout Subgirt Zee | 10 | 6 | [24 empty] | 50 | 0.2 |  |  | 35 | 0.5 | 35 | 0.35
22021 | VA-14 | 2023-01-23 | Joey laxton | installed acm and flashing | Subcontractor | Nick Akins | false |  |  |  |  | 9 | 10 | false |  |  | false |  |  |  |  | ACM Flashing | 26 | 80 | [30 empty] | 500 | 10
21063 | LTW061 | 2023-01-20 | Dh | Nice day | Subcontractor | Josh McPherson | [5 empty] | 3 | 10 |  |  | 65'ft boom lift | [5 empty] | Hat Channel | [34 empty] | 550 | 24
21087 | Long Hollow Baptist Church | 2023-01-20 | Fredy veliz | Panels made incorrect on ele 203 | Subcontractor | Colton Van Meter | [5 empty] | 4 | 8 |  |  | Boom lift |  |  |  | 6 |  | Layout Plate |  |  | 5 | 26
22002 | DLR Sterling Premier Building A | 2023-01-20 | Jean Neg | Today we work on installing all louvers we can and we installed 16 today it took us hr per louver to cuy it by 6 people total.hrs per cut would be 96 | Subcontractor | Steve Fudge | false |  |  |  |  | 12 | 180 | false |  | 4 boom lift 2 cissorlift 1 forklift | false |  |  |  |  | Louvre | [24 empty] | 16 | 80
22002 | DLR Sterling Premier Building A | 2023-01-20 | Jean Negron | We finish the other side of the building to complete the louvers we also finish the penhouse so we just pretty much trying to get done with the louver penhouse and about the door it will be installed on Monday orders from the superintendent we also all small louvers was also installed an hr extra cuts on all little louvers more information photo | Subcontractor | Steve Fudge | false |  |  |  |  | 10 | 70 | false |  | 2 boom lift 1 forklift | false |  |  |  |  | Louvre | [24 empty] | 4 | 24
22002 | DLR Sterling Premier Building A | 2023-01-20 | Jean Negron | Today we work on installing louvers we installed 10 louvers today in cuts it was 42 hrs in total | Subcontractor | Steve Fudge | false |  |  |  |  | 12 | 84 | false |  | 2 boom lift 1 forklift | false |  |  |  |  | Louvre | [24 empty] | 10 | 42
22021 | VA-14 | 2023-01-20 | Chad mccoy | We started this morning, clearing everything out so we can get the booms side-by-side the 120 a the 8. We need both of these booms to work together to set these panels. To set the first panels I had to go get an entire crate of panels and bring them around and put them where we could get them. To do the first three panels on the tall wall. I had to take the 85 and snake in between the panels. We just hung yesterday and the steel around the generator yard and sit until the panels were brought to us to minimize the activity next to these panels, so nothing was damaged.. As soon as these three panels were hung, the 120 stayed in place and the 85 was the panel transport from ground to wall. The wind was extremely strong today to the point where they shut the crane down. On the high roof above the garage doors below us the roofers were working and we were not allowed to boom over the roofers. So we went up the one side, three panels wide until the panel started being more than we could handle with the wind and then being 15+ foot tall. So I called Nick and I called Steve and I told him I was going to hang three more panels and then we were calling it for the day for safety reasons. | Subcontractor | Nick Akins | true | The roofers are causing a safety issue with booms and panels going over them so that is delaying installation due to their positioning. Plus they do not have the roofing done so that I can run the flashing across to do my first row of tall panels. The wind is gusting, so hard that they shut the crane down today and panels were dancing or swing as we were taking them up in the |  |  | Cloudy and windy high in the 40s | 4 | 6 | false |  | 85 boom. 32 foot scissor. | false |  |  |  |  | ACM | 9 | 4
21063 | LTW061 | 2023-01-19 | Dh | No work due to rains | Subcontractor | Josh McPherson | [5 empty] | 3 | [9 empty] | ACM
21087 | Long Hollow Baptist Church | 2023-01-19 | Fredy veliz | Elevation 201 framing structure incorrect sizes in the back side | Subcontractor | Colton Van Meter | true | Panels made incorrect and framing too |  |  |  | 4 | 8 |  |  | Boom lift | [5 empty] | Plate |  |  | 8 | 32
22002 | DLR Sterling Premier Building A | 2023-01-19 | Jean negron | Today we started to installed louvers at around 1pm we had a big delay with the group ahead us we have to give them sum time to them to be done with the back fill but at the end we start installing louvers and we installed 7 louvres each louver took us on hr to cut total of 42 hrs in cut we also hold the my team on working On putting the union plate | Subcontractor | Steve Fudge | true | Big delay by waiting for the group ahead us be done with the back fill |  |  |  | 12 | 156 | false |  | 2 boom lift one forklift | false |  |  |  |  | Louvre | [24 empty] | 7 | 42
22012 | QTS ASH2 DC1 Lockridge | 2023-01-19 | Marvin blanco | finish installing ACM panels and also Ltrim at the roof cleaning north elevation and taking scaffolding down | Subcontractor | Josh McPherson | false |  |  |  |  | 12 | 14 | false |  | 2 boomlift 1 boomlift damaged | false |  |  |  |  | ACM | 20 | 80
22021 | VA-14 | 2023-01-19 | Chad mccoy | We went in this morning to find A blue substance all over the panel tops and on the new flashing we put down yesterday evening. This was done by the roofer when they were drawing in the rooftop. It took about 45 minutes to get it off the flashing because the flashing was already caulked down. Once we get it off the flashing we started hanging panels. We hung the panels all the way to the inside corner and turn the corner. While we were working today they were sealing the door jams with sealant and epoxy. We had a couple of bust in dimension so we had to figure out and lay out and make work. I had to cut in route today and six other cuts for red iron. I had to install some Z and insulation and a couple flashings but nothing major. Also pulled some coping measurements for Steve on the lower section | Subcontractor | Nick Akins | false |  |  |  |  | 4 | 9 | false |  | 85 foot boom, 32 foot scissor lift | false |  |  |  |  | ACM Insulation Subgirt Zee Trim | 21 | 6 | [24 empty] | 20 | 0.2 |  |  | 15 | 0.5 |  |  |  |  | 15 | 30
22021 | VA-14 | 2023-01-19 | Joey laxton | acm and flashing installed | Subcontractor | Nick Akins | false |  |  |  |  | 9 | 8 | false |  |  | false |  |  |  |  | ACM Flashing Insulation Subgirt Zee | 27 | 50 | [24 empty] | 192 | 7 |  |  | 180 | 10 | 900 | 5
21024 | Vanderbilt Graduate Housing | 2023-01-18 | Marvin blanco | installing plate panels and also moving the swing stage cleaning our area of work and doing some measuring | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 12 | false |  | swing stage | false |  |  |  |  | Plate |  |  | 8 | 48
21040 | 801 Church | 2023-01-18 | Marvin blanco | installing clips for tubes and also cleaning the concrete | Subcontractor | Nick Akins | false |  |  |  |  | 4 | 12 | false |  | nothing | false |  |  |  |  | Other | [42 empty] | clips for install tubes next | 48
21063 | LTW061 | 2023-01-18 | DH | Good day | Subcontractor | Josh McPherson | [5 empty] | 3 | 10 |  |  | 65'ft boom lift | [5 empty] | Hat Channel | [34 empty] | 110 | 30
21071 | Google NBY-HUB 1 | 2023-01-18 | Marvin blanco | putting silicone all around the windows | Subcontractor | Steve Fudge | false |  |  |  |  | 4 | 12 | false |  | ladders 🪜 | false |  |  |  |  | Caulking | [20 empty] | 300 | 48
21087 | Long Hollow Baptist Church | 2023-01-18 | Fredy veliz | 6 panels are notch in the wrong place | Subcontractor | Colton Van Meter | [5 empty] | 4 | 8 |  |  | Boom lift | [5 empty] | Plate |  |  | 11 | 32
22002 | DLR Sterling Premier Building A | 2023-01-18 | Jean negron | Today we work on installing louvers we installed 14 in total in cuts was one hrs per louver cut it by 6 people total hrs of 84 today it was a pretty good day | Subcontractor | Steve Fudge | false |  |  |  |  | 14 | 154 | false |  | 2 boom lift one forklift | false |  |  |  |  | Louvre | [24 empty] | 14 | 60
22002 | DLR Sterling Premier Building A | 2023-01-18 | Jean negron | Today we work on installing louvers we installed 15 we had Issues with 2 because of the opening again 90 hrs in cuts was today by 6 people | Subcontractor | Steve Fudge | false |  |  |  |  | 14 | 168 | false |  | 2 boom lift 1 forklift | false |  |  |  |  | Louvre | [24 empty] | 15 | 50
22012 | QTS ASH2 DC1 Lockridge | 2023-01-18 | Marvin blanco | installing ACM panels and moving materials from 1 side to the other side cleaning and also we have a damaged boomlift window cleaning jump on it and with a metal sign he He cut the boomlift cables and he hasn't been able to fix that, it's already been ruined damaged for 3 days tomorrow there will be 4 | Subcontractor | Josh McPherson | false |  |  |  |  | 12 | 14 | false |  | boomlift | false |  |  |  |  | ACM | 80 | 168
22021 | VA-14 | 2023-01-18 | Chad mccoy | We started our morning trying to locate Panels around the job site that are mixed matched in multiple crates. We are a very busy wall to finish there’s multiple cutting routes there’s multiple layouts there’s multiple items to be cut out of this wall. We also had to set another header flashing above the second garage door. We had to move out of the way so people could bring material in and take material out plus every time a big group of people walks underneath the boom through the door we have to stop over doing and let them walk through. But we continue the Panels where the canopy is going to be. We continue the top row of panels all the way over. And then we plug and play the bottom. The reason for this is the majority of the panels that are gonna be damaged are the bottoms they need to be their own entity and they need to be easily removed and put back. I had 11 Panels to install today and I have 10 panels that I had to have some kind of cut or a cut in Route. We also got a 32 foot scissor today we got it in place at the end of the day that way in the morning we can clip up some panels and rock ‘n’ roll. | Subcontractor | Nick Akins | true | I refuse to match my side to the previous side on VA 13. That being said I did my side per print with the elevation the left and right plum level square. There is a inch and a quarter to an inch and 3/8 difference in our horizontal joint and be a 13 towards our joint. All this has been relayed with pictures to Steve Fudge |  |  | Clear | 3 | 9 | false |  | 85 boom, 32 foot scissor | false |  |  |  |  | ACM | 11 | 6
22021 | VA-14 | 2023-01-18 | Joey laxton | acm panels and flashing installed | Subcontractor | Nick Akins | false |  |  |  |  | 9 | 8 | false |  |  | false |  |  |  |  | ACM Flashing Insulation Subgirt Zee | 34 | 50 | [24 empty] | 320 | 7 |  |  | 300 | 10 | 30 | 5
21063 | LTW061 | 2023-01-17 | Daniel hernandez | No work due to rain | Subcontractor | Josh McPherson | [5 empty] | 3 | [9 empty] | ACM
21087 | Long Hollow Baptist Church | 2023-01-17 | Fredy veliz | Elevation 201 botton panels has to be cut cause slope on the concrete | Subcontractor | Colton Van Meter | [5 empty] | 6 | 8 |  |  | Boom lift | [5 empty] | Other Plate |  |  | 8 | 32 | [38 empty] | Moving materials to the work area | 16
22002 | DLR Sterling Premier Building A | 2023-01-17 | Jean negaron | Today we work on installing louvers we installed 10 in total we had issues in the morning boca of not enough space and the concrete guy had to fill up 2 wholes of concrete it was 10 louvers cut that took us around 1 per louver we los 3 hrs measuring the coping in the penthouse and send it to the office it was 10 louvers installed total of 66 hrs in cut | Subcontractor | Steve Fudge | false |  |  |  |  | 12 | 132 | false |  | 2 boom lift and one forklift | false |  |  |  |  | Louvre | [24 empty] | 10 | 60
22021 | VA-14 | 2023-01-17 | Chad mccoy | We started our morning pretty early. But it’s hard to see so we’re going to push back our start times a little bit. First thing we had to do was get the off-road 4 x 4 scissor lift put it in place. Then we had to find and locate the two big corners so that we could start laying it out right to left instead of left or right. The two big corners were on the bottom of a crate at the back of the building the entire crate had to be uncrated our panels taken off and then the rest of the Panels put back in the crate. Our 85 not arrived yet, So we borrowed the 60 from the steel guys. The gaps left to right had to be one to five eights and horizontal gap had to be narrowed to three eights. Once the two corners are on we set four more bottoms all the way to the first garage door. One of these Panels had to have 2 - 12 inch holes cut out. Once we get to the upper panels where the scuppers were the first panel had to be light out on the left because the middle panel had to be laid out on the left and right to be cut and the third panel had to be cut out on the right it was a pretty easy layout. We had to do a piece of flashing over the door for the header detail but the panels that are over the garage doors or a two piece panel and these panels were also in the very back of the building under other Panels the red Aaron had to be laid out and cut so that the Panels could edge around these canopy braces. Apparently there are no color match screws and a lot of these panels are coming with no screw holes in them and we have to build it because it only has two excursions on a bunch of the sides.On the upper Panels to top panels have to be cut down a half an inch due to the elevation impacting into wood blocking. | Subcontractor | Nick Akins | true | One of the biggest delays we have are the way that the panels are in the crates the starter Panels are on the very bottom of each crate and none of the Panels they go to a single wall are in a single crate they are separated and on most of the Panels the panel number is in the very middle of the panel you have to take the Panels out to find out what panel goes where |  |  | Rain | 4 | 9 | false |  | Off-road scissor, 85 foot boom | false |  |  |  |  | ACM | 13 | 6
22021 | VA-14 | 2023-01-17 | Joey laxton | installed acm panels and flashing | Subcontractor | Nick Akins | false |  |  |  |  | 9 | 8 | false |  |  | false |  |  |  |  | ACM Flashing Insulation Subgirt Zee | 31 | 36 | [24 empty] | 128 | 10 |  |  | 120 | 10 | 70 | 16
21063 | LTW061 | 2023-01-16 | Daniel hernandez | 800 LF of hat channel were installed | Subcontractor | Josh McPherson | [5 empty] | 3 | 10 |  |  | 65' ft boom lift | [5 empty] | Hat Channel | [34 empty] | 800 | 30
21087 | Long Hollow Baptist Church | 2023-01-16 | Fredy veliz | Issues with slope on the concrete panels on the bottom has to be bout out | Subcontractor | Colton Van Meter | [5 empty] | 4 | 8 |  |  | Boom lift | [5 empty] | Other | [42 empty] | Moving panels to the work areas | 32
22021 | VA-14 | 2023-01-16 | Chad mccoy | Today was a lot of hurry up and wait. We are outside this morning they were to Lulls, And a boom lift and a crane or fighting for our area that we were working in. The crane had half of our area marked off of danger tape. Another part of our area was taken by our cratesA 5 foot section by the length of our area was taken by a walk path and porter shitters. During the area that the crane was flying material he told us that we were not allowed to be underneath that material which pretty much meant we cannot work. We also had to do orientation again due to a 60 day offsite turn around. The orientation took way longer than it was supposed to. Once orientation was done we went to the upper section of the garage and we scoped it out with Alex. The roofer has done no work up here this all has to be roofed TPoed and have insulation put down. We were asked to give him three days starting tomorrow. So after orientation and after we looked at the top area we then started trying to plan out our tag on where and how we were going to reclaim our working area. A scissor lift will work fine to do the lower section. During the time that the roof is being done on the upper part of the lower section he does not want us to boom over the roofers so we cannot do anything on the tall wall. They originally told us that we cannot put the crates in the Street. I told them I was putting the crates in the Street. So I put the crates in the street all but two we could not find our starter panels so we had to search the entire site and each individual create define eight panels what they were failed we brought them to our working area plus all our trim. The bottom J trim does not go all the way to the wall so it is being modified to fit. Per the layout the first panel and the panel on top of it or 4 inches too long iIt protrudes into expansion joint. So I had to get permission by Steve to cutting out these panels. We will hit it hard tomorrow and make up for today’s shenanigans. Upon looking at the job site I sent some pictures to Steve of damaged panels on the previous walls there are already been installed there are a lot of damage panels | Subcontractor | Nick Akins | true | See notes for a list of the delays |  |  | Sunny/cold | 4 | 8 | true | I brought a trailer load of panels for Joey on his blade wall for the northside | Nothing arrived today | false |  |  | 1 |  | Layout
22021 | VA-14 | 2023-01-16 | Joey laxton | installed acm panels | Subcontractor | Nick Akins | false |  |  |  |  | 9 | 10 | false |  |  | false |  |  |  |  | ACM | 12 | 90
21024 | Vanderbilt Graduate Housing | 2023-01-13 | Marvin blanco | installing plate panels in the swing stage | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 11 | false |  | swing stage | false |  |  |  |  | ACM | 8 | 40
21071 | Google NBY-HUB 1 | 2023-01-13 | Marvin blanco | fixing panels because they make it to big it's 8 panels corners and also on the end panels of the loading dock wall waiting Also for Dpr guys to install the last piece of framing in the top of loading dock wall | Subcontractor | Steve Fudge | true | coping for loading dock wall and also windows flashing |  |  | could | 4 | 11 | false |  |  | false |  |  |  |  | Other | [42 empty] | nothing because they are cutting panels to make it fit | 44
22002 | DLR Sterling Premier Building A | 2023-01-13 | Jean Negron | Today we work on installing louvers we installed 10 louvers and 1 hour per louvers to cut before starting to work we had a waiting bcs company Hitt was digging 2 wholes in the spot where we was gone work so my people and I had to wait 2 hrs so they start flattening the earth to get ready to work we also had big issus and loss 2 hrs in one of the opening bcs the louver didn't fit it was to tight | Subcontractor | Steve Fudge | false |  |  |  |  | 14 | 182 | false |  | 4 boom lift 2 cissorlift 1 forklift | false |  |  |  |  | Louvre | [24 empty] | 10 | 70
22012 | QTS ASH2 DC1 Lockridge | 2023-01-13 | Marvin blanco | installing acm panels z's and also insulation some body also a cleaner guys get our boomlift and damaged | Subcontractor | Josh McPherson | false |  |  |  |  | 11 | 11 | true | flashing and silicone | boomlift | false |  |  |  |  | ACM Hat Channel Insulation | 25 | 80 | [24 empty] | 100 | 10 | [6 empty] | 80 | 20
21063 | LTW061 | 2023-01-12 | Daniel hernandez | We had 2 deliveries in AM also there was panels damaged on the truck we also installed 30 hay channels | Subcontractor | Josh McPherson | [5 empty] | 3 | 10 |  |  | 65 boom lift | [5 empty] | Hat Channel | [34 empty] | 300 | 15
22021 | VA-14 | 2023-01-12 | Joey laxton | 6 panels installed | Subcontractor | Nick Akins | false |  |  |  |  | 5 | 10 | false |  |  | false |  |  |  |  | ACM | 6 | 50
21024 | Vanderbilt Graduate Housing | 2023-01-11 | Marvin blanco | installing the swing stage where we need it. and also installing panels angles with insulation | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 11 | false |  | swing stage | false |  |  |  |  | Plate |  |  | 7 | 40
21063 | LTW061 | 2023-01-11 | Daniel hernandez | We did receive 2 deliveries today we had to unload out of the gate and bring the crates inside the job due to the drivers not beignets badge also there is some pieces of panels that came damaged | Subcontractor | Josh McPherson | [5 empty] | 3 | 8 |  |  | 65 boom lift |  |  |  | 30 |  | Layout
21071 | Google NBY-HUB 1 | 2023-01-11 | Marvin blanco | installing panels in the loading dock wall and the corners panels don't work because they make it to big | Subcontractor | Steve Fudge | true | revels windows flashing and coping |  |  | could | 7 | 11 | false |  | ladders 🪜 | false |  |  |  |  | Plate |  |  | 4 | 70
22002 | DLR Sterling Premier Building A | 2023-01-11 | Jean Negron | We did not work today because the group working on our side didn't fill up no whole and didn't have no space | Subcontractor | Steve Fudge | false |  |  |  |  | 1 | 1 | false |  | 0 | false |  |  |  |  | Louvre | [24 empty] | 0 | 0
22002 | DLR Sterling Premier Building A | 2023-01-11 | Jean Negron | Today we layout all the button side of the opening and we also installed all clips 350 in totql | Subcontractor | Steve Fudge | false |  |  |  |  | 14 | 140 | false |  | 4 boom lift 2 cissorlift 1 forklift | false |  |  |  |  | Caulking | [20 empty] | 0 | 0
22007 | Albion in the Gulch | 2023-01-11 | Keith Dukarm | Went to shop first thing got material loaded and went to job unloaded material got it to the roof got tools up there ...got the the job done except the 2 sides where swing stage where | JWMCD Crew | Dillon Bowman | true |  |  |  |  | 2 | 8 | false |  |  | false |  |  |  |  | Coping
22012 | QTS ASH2 DC1 Lockridge | 2023-01-11 | Marvin blanco | installing ACM panels in the canopy the red panels and also installing panels in the north side around the windows | Subcontractor | Josh McPherson | false |  |  |  |  | 11 | 11 | false |  | boomlift | false |  |  |  |  | ACM | 15 | 110
22021 | VA-14 | 2023-01-11 | Joey laxton | installed acm panels on east wall | Subcontractor | Nick Akins | false |  |  |  |  | 5 | 10 | false |  |  | false |  |  |  |  | ACM | 12 | 50
21063 | LTW061 | 2023-01-10 | Daniel hernandnez | No work we had an issue with the site address i gave united rental a wrong address that is on the contract for this projec | Subcontractor | Josh McPherson | [5 empty] | 3 | 0 |  |  | No | [5 empty] | Other | [43 empty] | 0
22002 | DLR Sterling Premier Building A | 2023-01-10 | Jean Negron | Today we installed 10 louvers cut it by 6 people each louver took us 1 hrs to cut total of 60 hrs in cut we also had issus with the opening the be having like belly concrete in the opening | Subcontractor | Steve Fudge | false |  |  |  |  | 14 | 140 | false |  | 4 boom lift 2 cissorlift 1 forklift | false |  |  |  |  | Louvre | [24 empty] | 10 | 70
22007 | Albion in the Gulch | 2023-01-10 | Keith Dukarm | Finished up what little we had to do above door and fixing some caulk joints and cleaning panels...first thing this morning we had to get scissor lift down off 4 took some time seeing how they have walls up now ...but its finished | JWMCD Crew | Dillon Bowman | false |  |  |  |  | 2 | 8 | false |  | Swing stage | false |  |  |  |  | Insulation Single Skin Trim
22021 | VA-14 | 2023-01-10 | Joey laxton | 13 acm panels and 20 ft of flashing installed | Subcontractor | Nick Akins | false |  |  |  |  | 5 | 10 | false |  |  | false |  |  |  |  | ACM Flashing | 13 | 25 | [30 empty] | 20 | 25
21063 | LTW061 | 2023-01-09 | Daniel hernandez | We showed up to the site but we had an issue that boom lift was not delivered | Subcontractor | Josh McPherson | [5 empty] | 3 | 8 |  |  | No | [5 empty] | Other | [42 empty] | We were not able to do anything | 24
22007 | Albion in the Gulch | 2023-01-09 | Keith Dukarm | Started this morning by picking up J from shop..then we installed the j on 4th floor and caulked it 4th floor is finished..then we cleaned 4th ...made are way to 17th changes panel and installed J on top ..after that we started the walk way door will finish tomorrow | JWMCD Crew | Dillon Bowman | false |  |  |  |  | 4 | 8 | false |  | Swing stage | false |  |  |  |  | Caulking Single Skin Trim
21071 | Google NBY-HUB 1 | 2023-01-08 | Marvin blanco | windows flashing | Subcontractor | Steve Fudge | false |  |  |  |  | 7 | 70 | false |  |  | false |  |  |  |  | ACM
21071 | Google NBY-HUB 1 | 2023-01-08 | Marvin blanco | installing windows flashing | Subcontractor | Steve Fudge | false |  |  |  |  | 7 | 10 | true | aluminum panels but with out Strushon and reveals | nothing | false |  |  |  |  | Flashing | [32 empty] | 300 | 70
22002 | DLR Sterling Premier Building A | 2023-01-08 | Jean Negron | Today we installed 10 louvers cut it by 6 people today we had big issues with the opening by installing the louvers the opening have like belly in some side andand other doesn't so today we did a lot off cut we loose a lot of time with 7 of them but we made it at the end of the day 10 louvers in total cut it by 6 people 60 hrs in cuts | Subcontractor | Steve Fudge | false |  |  |  |  | 14 | 154 | false |  | 3 boom lift 2 cissorlift 1 forklift | false |  |  |  |  | Caulking Louvre | [20 empty] | 0 | 0 |  |  | 10 | 10
22002 | DLR Sterling Premier Building A | 2023-01-08 | Jean Negron | Today we work in the penhouse 10 person we had enough time to finish up but BCS of insufficient material we didn't finish the wall 2 person was also screwig the small louvers it was complicated to installed because it was an small opening | Subcontractor | Steve Fudge | false |  |  |  |  | 12 | 120 | false |  | 3 boom lift 2 cissorlift 1 forklift | false |  |  |  |  | Louvre | [24 empty] | 3 | 3
22012 | QTS ASH2 DC1 Lockridge | 2023-01-08 | Marvin blanco | installing acm panels and waiting for red panels to finish the front entre also waiting for answers for the weather proof at the stairs waiting on silicone | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 12 | false |  | boomlift | false |  |  |  |  | ACM | 40 | 70
22002 | DLR Sterling Premier Building A | 2023-01-07 | Jean Negron | Today we start by working in louver 6 people was cutting louver today each louver took one hr to cut total hrs 60 and 2 person moving material other thing we had big big issus with the opening bcs the opening it was to tight and.had to do to Natchez in boths side of the louver top and bottom we loose much time by installing it we loss time on cutting the louver and to maje it work with the opening | Subcontractor | Steve Fudge | true | W head big issus with the opening we loose a lot of time to find a way and make it work with the opening so we had to mat to Natchez in top and bottom of the louver the opening was to tight more information photo |  |  |  | 14 | 168 | false |  | 4 boom lift 2 cissorlift 1 forklift | false |  |  |  |  | Caulking Louvre | [20 empty] | 0 | 0 |  |  | 10 | 90
22021 | VA-14 | 2023-01-07 | Joey laxton | 3 acm panels took down and replaced | Subcontractor | Nick Akins | false |  |  |  |  | 5 | 8 | false |  |  | false |  |  |  |  | ACM | 3 | 45
20067 | BNA PROJECT 5 | 2023-01-06 | Naza | moving material inside walk bridge entrance and airwave, | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | 32' csissor lift, 80' boom | false |  |  |  |  | ACM Other | 19 | 100 | [40 empty] | moving material to inside walk bridge entrance and airwave, | 20
22007 | Albion in the Gulch | 2023-01-06 | Keith Dukarm | Finished install on 4 needs trimm around top.. | JWMCD Crew | Dillon Bowman | false |  |  |  |  | 4 | 8 | false |  | Scissor lift | false |  |  |  |  | Single Skin Trim | [6 empty] | 45 | [29 empty] | 90
22021 | VA-14 | 2023-01-06 | Joey laxton | took down and reinstalled acm panels | Subcontractor | Nick Akins | false |  |  |  |  | 5 | 10 | true | acm panels |  | false |  |  |  |  | ACM | 4 | 50
20067 | BNA PROJECT 5 | 2023-01-05 | Naza | moving material to stair tower and airwave, 4 panels refab at stair tower level 1by elevator door 2 guys 12hours | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | scaffold, 80' boom | false |  |  |  |  | ACM Other | 23 | 88 | [40 empty] | moving material to stair tower and airwave, 4 panels refab at stair tower level 1 by elevator door 2 guys 12hours | 32
22002 | DLR Sterling Premier Building A | 2023-01-05 | Jean Negron | Today there was five boom lift in the air installing all clips and all line up plate in the north side was done as well today was a excellent day we work over night | Subcontractor | Steve Fudge | false |  |  |  |  | 14 | 238 | false |  | 1forklift 2 cissorlift We use 5 but we was borrow 2 boom lift | false |  |  |  |  | Louvre | [24 empty] | 0 | 0
22007 | Albion in the Gulch | 2023-01-05 | Keith Dukarm | Today went pretty good really high wind made it little difficult but we managed..ran low on J but talked to denis and got it squared away..we finished 2 half walls on 4th floor..well installed still need J across the top... | JWMCD Crew | Dillon Bowman | false |  |  |  |  | 4 | 8 | false |  | Scissor lift | false |  |  |  |  | Single Skin Trim | [6 empty] | 40 | [29 empty] | 120 | 12
20067 | BNA PROJECT 5 | 2023-01-04 | Naza | moving material to stair tower and airwave, 4 panels refab at stair tower level 1 by elevator door 2 guys 12hours | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | scaffold, 80' boom | false |  |  |  |  | ACM Other | 21 | 88 | [40 empty] | moving material to stair tower and airwave, 4 panels refab at stair tower level 1 by elevator door 2 guys 12hours | 32
22007 | Albion in the Gulch | 2023-01-04 | Keith Dukarm | Started the day off by seeing what was left to do since I wasn't there last week...with that being said 17th still had some trim and caulking to do...the walk way on 20 still needs to be done but have been waiting on GC to give us the word if the door fram opening was right ...while waiting on answers me and Chad dropped to 4th and started layout and figuring issues there . While Kevin and starling continued to finish trim and caulkimg.. also cleaned area on 17 | JWMCD Crew | Dillon Bowman | false |  |  |  |  | 4 | 10 | false |  | Scissor lift | false |  |  |  |  | Single Skin Trim | [6 empty] | 5
22021 | VA-14 | 2023-01-04 | Joey laxton | 6 panels installed and 30 ft of flashing installed | Subcontractor | Nick Akins | false |  |  |  |  | 5 | 10 | false |  |  | false |  |  |  |  | ACM Flashing | 6 | 25 | [30 empty] | 30 | 25
20067 | BNA PROJECT 5 | 2023-01-03 | Naza | moving material to stair tower and airwave. | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | scaffold, 80'boom | false |  |  |  |  | ACM Other | 20 | 100 | [40 empty] | moving material to stair tower and airwave, | 20
22002 | DLR Sterling Premier Building A | 2023-01-03 | Jean Negron | Today we screw clips layout, and seal pan moving material and took the material up too the pen house today was a good day we installed 400 clips overnight | Subcontractor | Steve Fudge | true | We had an delay on cutting frame bcs the opening was 1m to tight and we also cut a seal pan |  |  | Sunny | 15 | 224 | false |  | 4 boom lift 2 cissorlift 1 forklift | false |  |  | 16 |  | Flashing Layout | [32 empty] | 12 | 1
22002 | DLR Sterling Premier Building A | 2023-01-02 | Jean Negron | Most of all sealpan was installed and 200 clips also we steal had sum missing flashing to covered up and and we set set the glass in front of the building we also screw line up plate many | Subcontractor | Steve Fudge | false |  |  |  |  | 14 | 182 | false |  | 4 boom lift 2 cissorlift 1 forklift | false |  |  | 8 |  | Caulking Flashing Layout | [20 empty] | 0 | 0 | [10 empty] | 500 | 100
22002 | DLR Sterling Premier Building A | 2023-01-01 | Chad mccoy | We started our morning moving the boom lifts and the law to be south side of the building. The upper sections have all the wood taken off but the lower sections still has all the wood. we can only reachA small part of the upper section so to maximize work we started removing the wood on the lower louver holes. We removed roughly 600 linear feet of two by fours and a lot of leftover plastic. We then had to clean and chip down eight sections so that the seal pans would lay flat and not be sticking up a plate to have dents. Once we got the areas we were working in nice and flat I started installing sill pans. Well Kevin continue to take down the rest of the wood. When Kevin was finished he started installing sill pans. Prior to installing these pans for the louvers we had to dig them out and get them out of the mud and get them to the second level on the mezzanine area so that we could stage an install. We had a layout for each of the louver clips or brackets. I did not have three eights SDS bits so I had to run to Home Depot so that we could start installing these brackets. I started on the right Kevin started on the far left and we met in the middle. We installed 130 brackets. This includes 130 layouts because each one is 1 foot apart 3 inches off the back. Once they were laid out we went back started on the left on the right and we started hammer drilling and installing the hardware to hold the brackets in place. Each bracket has caulking underneath it where we penetrated the bracket through the seal pan into the concrete. And then they were tightened down with a half inch drive impact 9/16 socket. I still have to go back and cut what little of the bolts are sticking out so the louver does not hit these when we install. Both big blue boom lift also ran out of diesel today I had to go get 10 gallons each. Tomorrow we’re going in and we should be able to set the upper clips for five sections of louvers which will equal 18 louvers we will try and get as many of these installed as well before we leave to head back to Tennessee | Subcontractor | Steve Fudge | true | The job site is extremely muddy I got a boom lift stuck on the northside we had to pull it out with lull. |  |  | Sunny. 68 | 3 | 10 | false |  | Booms | false |  |  | 1.5 |  | Caulking Flashing Layout | [20 empty] | 200 | 1.5 | [10 empty] | 110 | 1
22002 | DLR Sterling Premier Building A | 2022-12-31 | Chad mccoy | We started our morning getting to the site and finding where everything is. I took pictures of damaged and miss treated material, around the building. There are pent house panels just thrown on a dirt mound and louvers knocked over in the mud and sill pans destroyed from removal. I sent pics to Steve and nick. We then went up and checked louver holes to make sure that the louvers would fit. 4 louvers had to be adjusted to make room for the next louver to install. Once adjustments where made I had to cut screw tips off and sill with caulking the sill pan bolts. There are some concrete anchors that are barely drilled and they fell out. These had to be reset with a hammer drill. These louvers are heavy. We used a lull to get the louvers to the base of install. I went up and got the measurements for the modifications to the louvers. Kevin cut the spots out. And then two booms to install. I had the louver on my boom, And Kevin and Starlin where in the boom above me. We all lifted the louver in place. Then I would stabilize while Starlin went down and went in the building to attach the louver with screws. | Subcontractor | Steve Fudge | true | It rained half the day. And the work areas are 5 inches of mud. We tried to get the material that’s thrown in the mud but I sank over a foot and lost a boot in the mud that had to get removed. So we stopped cleaned up and left |  |  | Rain | 3 | 11 | false |  | Booms. I don’t know what else | false |  |  | 1 |  | Layout Louvre | [24 empty] | 5 | 5
22002 | DLR Sterling Premier Building A | 2022-12-29 | Jean Negron | 12 louvers was installed and cut it took 1 hr per louver to cut by 6 people total of 72 we also installed 50 clips and move material from inside the building | Subcontractor | Steve Fudge | false |  |  |  |  | 12 | 204 | false |  | 3 boom lift 2 cissorlift 1 forklift | false |  |  |  |  | Caulking Louvre | [20 empty] | 0 | 0 |  |  | 12 | 50
20067 | BNA PROJECT 5 | 2022-12-28 | Naza | moving material to stair tower and airwave, 5 panels refab at stair tower level 3 by elevator door 2 guys 16hours | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | scaffold, 80' boom | false |  |  |  |  | ACM Other | 30 | 84 | [40 empty] | moving material to stair tower and airwave, 5 panels refab at stair tower level 3 by elevator door 2 guys 16hours | 36
22002 | DLR Sterling Premier Building A | 2022-12-28 | Jean Negron | The morning we arrive we start moving our boom lift to a different spot to move one of the palette we was gone need we had a delay of 3 hrs bcs there wasn't enough space the road was all wholes around and the workers had to move the material by hand not enough space to work we loose much time there so much likely we start by installing louvers around 12 pm we installed 3 louvers in total it took us an hr per cut by 3 people total hr of 23 and we also installed 90 clips | Subcontractor | Steve Fudge | true | The company Hitt been working near us and its like not enough space I'm the road so we had to move material at the same time the road all full of whole we had to move all boom lift |  |  | Sunny | 12 | 144 | false |  | 3 boom lift 2 cissorlift 1 forklift | false |  |  |  |  | Louvre | [24 empty] | 3 | 20
22021 | VA-14 | 2022-12-28 | Joey laxton | 6 acm panels installed and 80ft of flashing installed | Subcontractor | Nick Akins | false |  |  |  |  | 5 | 10 | false |  |  | false |  |  |  |  | ACM Flashing | 6 | 25 | [30 empty] | 80 | 25
20067 | BNA PROJECT 5 | 2022-12-27 | Naza | moving material to stair tower and airwave, 5 panels refab at stair tower level 3by elevator door 2 guys 16hours | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | scaffold, 80'boom | false |  |  |  |  | ACM Other | 30 | 84 | [40 empty] | moving material to stair tower and airwave, 5 panels refab at stair tower level 2 by elevator door 2 guys 16hours | 36
22002 | DLR Sterling Premier Building A | 2022-12-27 | Jean Negron | We start by installing louvers and clips we installed 14 louvers and like normally it took 1 hr each louver to cut only it would be a total of 84 and it was 40 clips also , and 2 worker start from the back of line where we installing to screw the line up plate . | Subcontractor | Steve Fudge | false |  |  |  |  | 12 | 204 | false |  | 3 boom lift 2 cissorlift 1 forklift | false |  |  |  |  | Caulking Louvre | [20 empty] | 0 | 0 |  |  | 14 | 60
22021 | VA-14 | 2022-12-27 | Joey laxton | 16 acm panels installed | Subcontractor | Nick Akins | false |  |  |  |  | 5 | 8 | false |  |  | false |  |  |  |  | ACM | 16 | 48
20067 | BNA PROJECT 5 | 2022-12-26 | Naza | moving material to stair tower and airwave, 5 panels refab at stair tower level 3, 2 guys 12hours | Subcontractor | Marc Ribar | false |  |  |  |  | 12 |  | false |  | scaffold, 80'boom | false |  |  |  |  | ACM Other | 27 | 100 | [40 empty] | momoving material to stair tower and airwave, | 20
22007 | Albion in the Gulch | 2022-12-23 | Keith Dukarm | Finishing what we started on Wednesday..we installed panels and insulation moved and organized material also moved sunbelts stuff on the roof .. 104 panels and bout 25 bundles of insulation | JWMCD Crew | Dillon Bowman | false |  |  |  |  | 5 | 8 | false |  | Swing stage | false |  |  |  |  | Insulation Single Skin Trim | [6 empty] | 104 | [29 empty] | 300 | 30
22002 | DLR Sterling Premier Building A | 2022-12-22 | Jean negro | Ice water | Subcontractor | Steve Fudge | false |  |  |  |  | 1 | 0 | false |  | 0 | false |  |  |  |  | Louvre | [24 empty] | 0 | 0
20067 | BNA PROJECT 5 | 2022-12-21 | Naza | crews working at stair tower and airwave | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | scaffold, 80 boom | false |  |  |  |  | ACM Other | 7 | 40 | [40 empty] | ,moving material to stair tower, takeing the film off the overly panels, cap to overly anels. 3 panels refab at stair tower level 2 by elevator door 2 guys 12hoursp | 60
22002 | DLR Sterling Premier Building A | 2022-12-21 | Jean negron | We had issues since we arrived there wasn’t enough space bcs there was not enough space and there was another workers digging where we was working more information in foto we only had the opportunity to be able to work around 3 pm we installed clips 80 clips in total for got to mentioned the we also had to move matirial mostly all day 26 hrs in today by 2 people we took 3 hrs to make any plan of the work and the issues we had this morning | Subcontractor | Steve Fudge | true | We had to move of the area we was working at and move a lot of matirial |  |  |  | 9 | 96 | false |  | 3 boom lif 1 cissorlift 1 forklift | false |  |  |  |  | Louvre | [24 empty] | 0 | 0
22007 | Albion in the Gulch | 2022-12-21 | Keith Dukarm | Finished 9th floor area and started 17th floor...ran Zs insulation and panels | JWMCD Crew | Dillon Bowman | false |  |  |  |  | 5 | 8 | false |  | Swing stage | false |  |  |  |  | Insulation Single Skin Subgirt Zee Trim | [6 empty] | 49 | [23 empty] | 1200 | [5 empty] | 120
22007 | Albion in the Gulch | 2022-12-21 | Keith Dukarm | More pics. | JWMCD Crew | Dillon Bowman | false |  |  |  |  | 5 | 8 | false |  | Scaffolding | false |  |  |  |  | Single Skin Trim | [6 empty] | 39 | [30 empty] | 23
22007 | Albion in the Gulch | 2022-12-21 | Keith Dukarm | Started where we left off in monday..we had 5 panel rips and 34 panels to hang then caulking we got the Nashville side of 9th complete..interstate side got the top rows on.. | JWMCD Crew | Dillon Bowman | false |  |  |  |  | 5 | 8 | false |  | Scaffolding | false |  |  |  |  | Single Skin Trim | [6 empty] | 39 | [30 empty] | 23
20067 | BNA PROJECT 5 | 2022-12-20 | Naza | crews working at stair tower and airwave | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | scaffol, 80 boom | false |  |  |  |  | ACM Other Overly Roof Panel | 6 | 40 | [10 empty] | 32 | 60 | [28 empty] | moving material to stair tower and airwave | 20
22002 | DLR Sterling Premier Building A | 2022-12-20 | Jean negron | We started by building 3 stormfrom and we also installed … we also installed 9 louvers and took us 1 hour to cut every louver by 6 people we made 54 hrs doing cuts | Subcontractor | Steve Fudge | true | We lost a lot of time and had issues with some other guy around us we couldn’t move no material we didn’t had enough space more information photo |  |  |  | 12 | 192 | false |  | 3 boom lift 2 cissorlift 1 forklift | false |  |  | 2 |  | Layout Louvre | [24 empty] | 9 | 60
22021 | VA-14 | 2022-12-20 | Joey laxton | installed 10 acm panels and 60ft of base flashing | Subcontractor | Nick Akins | false |  |  |  |  | 5 | 8 | false |  |  | false |  |  |  |  | ACM Flashing | 10 | 23 | [30 empty] | 60 | 23
22074 | Arconic NFPA 285 Test | 2022-12-20 | Chad mccoy | We started our morning getting to the test site at 6 o’clock. We were not allowed to go in the building till 730. Once we got signed in and everything was going we started flashing out the wall we flashed out the window and then we flashed out the bottom part of the wall. Once the flash was on then we rolled the peel and stick out to the sides of the wall so that we could throw the pieces of the peel and stick on top to bottom. We use my roller to roll the air bubbles and the peel and stick down the wall. Once a peeling stick was on we started laying out for season insulation but we noticed that there was a bust in the wall from the bottom of the structure to the bottom of the window. This elevation bust May the bottom panels 7 inches too short and took that 7 inches and made it sticks 7 inches past the top of the structure. So everybody was called and decisions were made to move panels. So the rope panels of the is going at the bottom and the rope panels of FR going second from the top. There was a lot of hurry up and wait today. We also had to stop working at 3:30 and start cleaning up due to the fact that they were gonna shut the doors at 4 o’clock so starting light plus all the stops during the day plus stopping early made us have to turn this into a two day venture | Subcontractor | Joe Hoyle | true | The panel dimensions per the print had a 6 1/2 inch bust from bottom of structure to bottom of window |  |  |  | 2 | 7 | true | Panels, see, insulation, waterproofing |  | false |  |  |  |  | ACM AWB Flashing Insulation Subgirt Zee | 12 | 2.5 | [24 empty] | 230 | 1 |  |  | 135 | 1.5 | 35 | 1.5 |  |  |  |  | 230 | 1
20067 | BNA PROJECT 5 | 2022-12-19 | Naza | 6 panels refab at stair tower level 2 by elevator door, 2 guys 16 hours | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | scaffold, 80' boom | false |  |  |  |  | ACM Other Overly Roof Panel | 12 | 40 | [10 empty] | 28 | 44 | [28 empty] | moving material to stair tower and airwave, 7 panels refab at stair tower level 2 by elevator door 2 guys 16hours | 36
22002 | DLR Sterling Premier Building A | 2022-12-19 | Jean negron | We installed clips and seal pan today we screw 20 clips and 6 seal pan we build 5 frame and we installed 8 seal pan for stormform installation we also layout | Subcontractor | Steve Fudge | false |  |  |  |  | 12 | 144 | false |  | 3 boom lift 1 cissorlift 1 forklift | false |  |  | 12 |  | Caulking Flashing Layout | [20 empty] | 0 | 0 | [10 empty] | 60 | 8
22007 | Albion in the Gulch | 2022-12-19 | Keith Dukarm | More pics | JWMCD Crew | Dillon Bowman | false |  |  |  |  | 4 | 8 | false |  | Scaffolding | false |  |  |  |  | Single Skin Trim | [6 empty] | 65 | 8 | [28 empty] | 200 | 20
22007 | Albion in the Gulch | 2022-12-19 | Keith Dukarm | Started where we left off on Wednesday..me and starlin finished up the top row on one side and Kevin and David got the panels up on the other ..still have to caulk and put some ripped panels in and them 2 walls will be done ...tomorrow we will be finishing up what we can do on 9th floor.. | JWMCD Crew | Dillon Bowman | false |  |  |  |  | 4 | 8 | false |  | Scaffolding | false |  |  |  |  | Single Skin Trim | [6 empty] | 65 | 8 | [28 empty] | 200 | 20
22021 | VA-14 | 2022-12-19 | Joey laxton | installed Acm paneling and 11 pieces drip edge flashing installed | Subcontractor | Nick Akins | false |  |  |  |  | 5 | 8 | false |  |  | false |  |  |  |  | ACM | 13 | 23
22002 | DLR Sterling Premier Building A | 2022-12-18 | Jean negron | We start by installing louvers the 2 louvers took to hrs per 6 person to installed bcs of the opening to tight we installed 12 louvers and we took 1 hr to cut per 6 persons , total hrs of cuts 78 hrs we also installed 8 seal pan and 70 clips we also did some layout | Subcontractor | Steve Fudge | true | Cutting louvers ,small opening |  |  |  | 12 | 204 | false |  | 3 boom lift 2 cissorlift 1 forklift | false |  |  | 6 |  | Caulking Flashing Layout Louvre | [20 empty] | 0 | 0 |  |  | 12 | 80 | [6 empty] | 75 | 10
22002 | DLR Sterling Premier Building A | 2022-12-17 | Jean negron | Today we worked in screwing clips in the opening and doing the layout we also move material we worked 10 hrs each person | Subcontractor | Steve Fudge | true | Construcción hitt move a lot things around where we was working at and we did not had enough space |  |  | Mood | 12 | 120 | true | Hat channel coping | 3 Boom lift one forklift and 1 cissorlift | false |  |  | 6 |  | Layout
19028 | Kistler Rolled Panels | 2022-12-16 | Chad mccoy | We Started our day going to the roof to see if we could do those panels on the roof. The roof was too windy so instead we went down to level three balcony and we took off and reinstalled four panels. What’s this was done we waited for the boom lift to arrive in the other boom lift to get picked up. Once our track boom arrived we got it in a place and we removed 10 panels over the tracks. We installed one panel and then it was time to go to the roof to do those panels. We have a small window to do those panels so we then took those panels down and put those panels up. We cleaned up the level 34 section brought everything down except for the panels we were told to leave in the maintenance room and left for the day | Subcontractor | Chris Ball | true | The wind this morning the latest on 34 but we were able to knock it out at night |  |  | 50s clear | 3 | 15 | false |  | 65 foot track boom | false |  |  | 1 |  | ACM Layout | 7 | 3
20067 | BNA PROJECT 5 | 2022-12-16 | Naza | 6 panels refab at stair tower by elevator door, 2 guys 16 hours. | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | scaffold, 80' boom | false |  |  |  |  | ACM Other Overly Roof Panel | 12 | 42 | [10 empty] | 28 | 40 | [28 empty] | moving panels to stair tower and airwave.6 panels refab at stair tower by elevator door, 2 guys 16hours | 38
22002 | DLR Sterling Premier Building A | 2022-12-16 | Jean negron | we start by installing louvers we took an hour cutting the louver by 6 person took us one each 7 louvers for cutting and we also had issues on las 3 louvers took 2 hrs each on louvers BCS the opening was to small and we made a total of 96 hrs doing cuts | Subcontractor | Steve Fudge | false |  |  |  |  | 12 | 228 | false |  |  | false |  |  |  |  | Caulking Flashing Louvre | [20 empty] | 0 | 0 |  |  | 10 | 140 | [6 empty] | 15 | 4
20067 | BNA PROJECT 5 | 2022-12-15 | Naza | 7 panels refab at stair tower slope, 2 guys 18 hours. | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | scaffold, 80 boom | false |  |  |  |  | ACM Other Overly Roof Panel | 9 | 40 | [10 empty] | 24 | 42 | [28 empty] | moving material to stair tower and airwave. 7 panels refab at stair tower slope, 2 guys 18 hours | 38
21024 | Vanderbilt Graduate Housing | 2022-12-15 | Marvin blanco | checking panels don't fit because they make it short. | Subcontractor | Drake De Tomasi | false |  |  |  |  | 6 | 11 | false |  | boomlift | false |  |  |  |  | ACM | 6 | 66
21071 | Google NBY-HUB 1 | 2022-12-15 | Marvin blanco | waiting on silicone the guys finished everything they have we just need to put silicone between the base flashing and everything else is done | Subcontractor | Steve Fudge | true | silicone and 1 panels also windows flashing |  |  | good | 5 | 10 | false |  | scissors lift and boomlift | false |  |  |  |  | Other | [42 empty] | checking everything else for not forgetting something | 50
22002 | DLR Sterling Premier Building A | 2022-12-15 | Jean negron | Raining | Subcontractor | Steve Fudge | false |  |  |  |  | 1 | 0 | false |  | 0 | false |  |  |  |  | Louvre | [24 empty] | 0 | 0
19028 | Kistler Rolled Panels | 2022-12-14 | Chad mccoy | We started this morning making sure that the panels that needed to go on the terraced above level three was out of the crate. Storms came in today all day long we had 25+ mile an hour winds with up to 45 mile an hour gust. When the boom lift got on site we had to wait for the train guy to get there. The train company said that they forgot about us so they sent somebody as soon as They could. As soon as the train guy got there we started moving the boom lift in the place to start taking down the panels. In the middle of the railroad tracks they have installed another set of railroad tracks that come to find out will make moving a tired driven boom lift exceptionally difficult. We got to where we needed to jump over the tracks and the 6 inch concrete curb that separated the track system and the ground that at the time we did not know was a soft as it is. We did this exactly like the last times that we move the boom lift on to this same area the only difference is the ground was really saturated and that extra set of tracks in the middle of the train tracks. The boom lift and not make it we’ve got three tires up but the fourth tire would not go so if we weren’t battling the mud and the 6 inch concrete curve then we were battling the dual layered train tracks. So when we figured out that the boom lift would not go and then decided to try and get it out of the situation it was in. The boom lift was stuck as soon as we cannot get the boom lift stuck the train guy came and said you need to move this boom a train is on his way. I had no other choice but to try the best that I could to get this damn boom lift off the tracks. It took about an hour and 15 minutes start to finish but we got it off the tracks and away from the train. As soon as the train passed within straddled one track and drove two wheels up on another track and drove down the train tracks to simply put the panels and the ladder up on level three Terrace. What’s the Panels on the ladder we’re up there we set the ladder up and I started going up the ladder but as soon as I started going up the ladder 28 feet the wind started pushing the ladder over. I had to have two ground guys hold the ladder in place why I peel the panel 28 feet near. During this time we had got a lightning alert saying that the lightning was within 15 miles so we had to hurry up and get everything put up and stored in the building or on the terraced flat so that we could get in the vehicle due to the lightning alert. We were also under a dangerous severe storm alert a tornado watch which a tornado landed 2 miles from us later that day and lightning all around us. So we ended the day | Subcontractor | Chris Ball | true | Nothing on this job has went like it’s been planned |  |  | Severe storm warning, Lightning, Heavy rain an area flooding, Tornado watch which landed 2 miles from us | 3 | 5 | false |  | 86 foot boom that won’t work. We Put in an order for a boom lift with tracks | false |  |  |  |  | ACM | 0 | 0
20067 | BNA PROJECT 5 | 2022-12-14 | Naza | 7 panels had to be refab down the slope at stair tower 2 guys 18 hours | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | scaffold, 80' boom | false |  |  |  |  | ACM Other | 29 | 82 | [40 empty] | moving material stair tower, airwave. 7 panels had to be refab down the slope at stair tower | 38
22002 | DLR Sterling Premier Building A | 2022-12-14 | Jean negron | We started the day by installing clips and seal pan we installed 150 clips and 3 seal pan we also installed 11 louvers we took an hrs by cutting everything louvre and we also had issues with the opening it took us more time and it also took us 1 hr per louver every each person it would be a total of 66 hrs | Subcontractor | Steve Fudge | true | Louvers cuts |  |  |  | 12 | 180 | false |  | 3 boom lift 3 cissorlift and 1 forklift | false |  |  | 10 |  | Caulking Flashing Layout Louvre | [20 empty] | 0 | 0 |  |  | 11 | 90 | [6 empty] | 29 | 4
22007 | Albion in the Gulch | 2022-12-14 | Keith Dukarm | Let's try this agian ......started at 430 had the elevator from 5 to 7 moved insulation and J trim..once we got it moved we staged it in the hallway where I was told I could put it ...once we got that situated we took a little break ..after that we started organizing the 9th floor to start that ...we started 9th and got 2 rows on one wall Monday should finish one sid of 9th the other side we just have top rows..this is the second time I wrote this so if I forgot somthing just ask ...everything is tied down and secured for any weather we may have when im not there... | JWMCD Crew | Dillon Bowman | false |  |  |  |  | 2 | 8 | false |  | Swing stage | false |  |  |  |  | Single Skin Trim | [6 empty] | 34 | [29 empty] | 80
22007 | Albion in the Gulch | 2022-12-14 | Keith Dukarm | Let's try this agian ......started at 430 had the elevator from 5 to 7 moved insulation and J trim..once we got it moved we staged it in the hallway where I was told I could put it ...once we got that situated we took a little break ..after that we started organizing the 9th floor to start that ...we started 9th and got 2 rows on one wall Monday should finish one sid of 9th the other side we just have top rows..this is the second time I wrote this so if I forgot somthing just ask ...everything is tied down and secured for any weather we may have when im not there... | JWMCD Crew | Dillon Bowman | false |  |  |  |  | 2 | 8 | false |  | Swing stage | false |  |  |  |  | Single Skin Trim | [6 empty] | 34 | [29 empty] | 80
19028 | Kistler Rolled Panels | 2022-12-13 | Chad mccoy | We started our evening gathering tools to go to 34. The wind on the ground is pretty strong. When we got to the roof it was blowing around 25 with gust up to 30plus We started sitting up the scaffolding to take the upper panels off first but the wind was trying to knock over the scaffolding. So I made a call and we took half the scaffolding down and we only worked on the bottom two. When we got the bottom panels off I had to re secure the tracks on the wall bc they were lose. We located studs in the wall and we ran 3 inch 5/16 screws in the tracks till the drywall it’s self was pulling in. We then set up my lay out and the clip system I came up with so we could fully attaché the panels to the wall. Once the panels were installed we cleaned up and went back to the Airbnb | Subcontractor | Chris Ball | true | The wind was causing safety to be a issue. |  |  | Windy. Storms coming in | 3 | 4 | false |  |  | false |  |  |  |  | ACM | 2 | 1
20067 | BNA PROJECT 5 | 2022-12-13 | Naza | crews working at airwave and stair tower, 6 panels had to be refab down the slope at stair tower 2 guys 16 hours | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | scaffold, 80' boom | false |  |  |  |  | ACM Other | 27 | 84 | [40 empty] | 2 guys refabing ACM panels at stair tower slope, moving material to stair tower, airwave | 36
22002 | DLR Sterling Premier Building A | 2022-12-13 | Jean negron | 2 person moving material all day 20 hrs worked. -2 person caulking and installing seal pan all day 17 seal pan was installed. - we also installed 7 louvers took us 1 hrs to cut per louver 42 hrs worked | Subcontractor | Steve Fudge | false |  |  |  |  | 10 | 140 | false |  | 3 boom lift 2 cissorlift 1 forklift | false |  |  |  |  | Caulking Flashing Louvre | [20 empty] | 0 | 0 |  |  | 7 | 50 | [6 empty] | 175 | 24
22007 | Albion in the Gulch | 2022-12-13 | Keith Dukarm | Moved and sorted panels and j ...used swing stage made several trips to the 17th floor after we did that we took what panels we had for 9 and put them.there also took the j there to | JWMCD Crew | Dillon Bowman | false |  |  |  |  | 2 | 8 | false |  | Swing stage | false
22021 | VA-14 | 2022-12-13 | Joey laxton | punch list work | Subcontractor | Nick Akins | false |  |  |  |  | 5 | 8 | false |  |  | false |  |  |  |  | Perforated
20067 | BNA PROJECT 5 | 2022-12-12 | Naza | crews working at stair tower and airwave | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | scaffold , 80'boom | false |  |  |  |  | ACM Other | 30 | 100 | [40 empty] | moving material to areas stair tower and airwave | 20
21071 | Google NBY-HUB 1 | 2022-12-12 | Marvin blanco | fixing stuff flashing coping panels and also waiting for silicone | Subcontractor | Steve Fudge | true | silicone windows flashing and Also 1 panel |  |  | frio | 5 | 11 | false |  | boomlift | false |  |  |  |  | Other | [42 empty] | fixing stuff | 55
22002 | DLR Sterling Premier Building A | 2022-12-12 |  | We started the day by installing clips, seal pan and coulk we installed 180 clips we caulk around the clips and we installed 9 seal pen overnight we also work on installing the louvers 4 louvers we make some extra cut on it BCs the opening was smaller than the louver and in the 4th louver we had big issues by installing it bcs the opening was to tight and we had to take it out many time to measure the opening and the louver finding a way to make it work we took 1 hrs each each panel and The last one took us like 2 also in cute we made 30 hrs in total | Subcontractor | Steve Fudge | false |  |  |  |  | 9 | 144 | false |  | 3 boom lift 1 cissorlift | false |  |  |  |  | Caulking Flashing Louvre | [20 empty] | 0 | 0 |  |  | 4 | 80 | [6 empty] | 90 | 8
22012 | QTS ASH2 DC1 Lockridge | 2022-12-12 | Marvin blanco | installing panels and remaking panels waiting for the framing pass inspection | Subcontractor | Josh McPherson | true | flashing silicone backroll blue tape |  |  | frio | 15 | 12 | false |  | boomlift | false |  |  |  |  | ACM | 25 | 180
22021 | VA-14 | 2022-12-12 | Joey laxton | 20 perforated panels installed on lil screen wall | Subcontractor | Nick Akins | false |  |  |  |  | 5 | 8 | false |  |  | false |  |  |  |  | Perforated
22002 | DLR Sterling Premier Building A | 2022-12-11 | Jean negron | We started by cutting louver withc took us 2 hrs by cutting each louvre and we had some. Big issues by intalling the last 2 louvers BCS the opening was to small and we had to make some little more cuts more information in pictures we intalled 5 louvre in total cut it by 6 worked total 42 hrs | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 88 | false |  |  | false |  |  |  |  | Caulking Louvre | [20 empty] | 0 | 0 |  |  | 5 | 50
20067 | BNA PROJECT 5 | 2022-12-10 | Saul chicas | We were working on interiors wall | Subcontractor | Marc Ribar | [5 empty] | 6 | 6 |  |  | Boom lift and scissor lift | [5 empty] | Hat Channel Other | [42 empty] | Terracota | 36
22002 | DLR Sterling Premier Building A | 2022-12-10 | Jean negron | We start the day by installing 30 clips,6 flashing coulk we measure and we installed 4 louver 2 louvers took us 1 hrs each one and the other 2 louvers we had some issues delay bcs the opening was to small so we grind the clip around to make it work we had to make some cut as well | Subcontractor | Steve Fudge | false |  |  |  |  | 9 | 99 | false |  | 2 Boom lift 1 cissorlift | false |  |  |  |  | Caulking Flashing Louvre | [20 empty] | 0 | 0 |  |  | 4 | 60 | [6 empty] | 60 | 6
22002 | DLR Sterling Premier Building A | 2022-12-10 | Jean negron | We stated the day by installing clips, we installed 80 clips in total , 3 flashings, we had a delivery of 10 palete of louvers the 2 guys took around 2 hrs u unload it they also move material to have enough space for the rest of marerial we were getting , 5 louver was installed as well 6 people getting louvers ready moving it cutting it measures took us around 1 hrs per louver | Subcontractor | Steve Fudge | false |  |  |  |  | 6 | 144 | true | 1 truck we had 10 Palete of louvers only | 3 Boom lift 1 cissorlift 1 forklifts | false |  |  |  |  | Caulking Flashing Louvre | [20 empty] | 0 | 0 |  |  | 5 | 90 | [6 empty] | 30 | 2
20067 | BNA PROJECT 5 | 2022-12-09 | Naza | crews working at stair tower and air wevw | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | 80' boom, scaffold | false |  |  |  |  | ACM Other | 26 | 100 | [40 empty] | moving material to stair tower and air wave. | 20
20067 | BNA PROJECT 5 | 2022-12-09 | Saul chicas | Today we were working on the Interiors walls | Subcontractor | Marc Ribar | [5 empty] | 6 | 10 |  |  | Boom lift and scissor lift | [5 empty] | Hat Channel Other | [42 empty] | Terracotta | 60
22002 | DLR Sterling Premier Building A | 2022-12-09 | Jean negron | We started the day by installing clips flashing and coulk on,installed 80 clips 3 flashing and coulk all around the clips we had a delivery in the morning with 2 of my guy took like 2 hrs to unloaded we installed 5 louvers 6 guys es working on morning it cutting it and measuring all around whit h they took 1 hr per louver by cutting measuring and and picking it up we also cut the jam of the clips | Subcontractor | Steve Fudge | false |  |  |  |  | 9 | 144 | true | Truck with 10 pallet of louver s material only | Boom lift cissorlift and forklift | false |  |  |  |  | Caulking Flashing Louvre | [20 empty] | 0 | 0 |  |  | 5 | 90 | [6 empty] | 30 | 2
22002 | DLR Sterling Premier Building A | 2022-12-09 | Jean negron | Note 2 person working on unloading the material and had some issues to finding a parking to unload the truck took them over 2 hrs to wait the matachines and worked around move or give us some space ,the rest of the group was installing clips and other 2 person putting flashing on north side of the building after lunch we start installing louvers in the opening of 4 units in the ML1A we had some issues on installing the fourth louvers the issue was the we had to cut the clip 3/8 bcs the clip was hitting on the screen of the louver , second Isaí we had some delays on putting some of the big lights so we could be able to work at night, we cut 5 louvers the took usaround 1 hour per louver would be a total of 16 hrs ,installed 15 and 8 flashing unload 2 truck , we as well caul the the clips of the seal pan all around the clip and the screw | Subcontractor | Steve Fudge | true | We have delays in the morning tl find a parking lot in the construction area to unload all the martial and my 2 worked had a delay of 2 hrs to get a answers from the supervisors and we have 2 hrs of delay to get a scissor lift up to the second floor the we did not had away to bring it up to the second floor and had tl wait till night to get it up there |  |  | Solid | 6 | 16 | true | 2 trucks with louver matirial total of 16 pallets | Boom lift forklift | false |  |  |  |  | Caulking Flashing Louvre | [20 empty] | 0 | 0 |  |  | 5 | 10 | [6 empty] | 85 | 8
22007 | Albion in the Gulch | 2022-12-09 | Keith Dukarm |  | JWMCD Crew | Dillon Bowman | false | [6 empty] | false |  |  | false |  |  |  |  | Single Skin Trim
20067 | BNA PROJECT 5 | 2022-12-08 | Naza | 5 panels had to be manufactured down the slope at stair tower, airwave. | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | 80' boom, scaffold | false |  |  |  |  | ACM Other | 27 | 100 | [40 empty] | moving panels to stair and airwave | 20
20067 | BNA PROJECT 5 | 2022-12-08 | Saúl chicas | We keep working on the Interior wall vestibule | Subcontractor | Marc Ribar | [5 empty] | 6 | 10 |  |  | Boom lift and scissor lift | [5 empty] | Hat Channel Other | [42 empty] | Terracota | 60
22007 | Albion in the Gulch | 2022-12-08 | Keith Dukarm | Hung panels and trim | JWMCD Crew | Dillon Bowman | false |  |  |  |  | 5 | 8 | false |  | Swing stage | false |  |  |  |  | Single Skin Trim | [6 empty] | 45 | [29 empty] | 140 | 14
20067 | BNA PROJECT 5 | 2022-12-07 | Naza | 5 panels had to be refab down the slope at top and bottom stair tower, crew working at air wave | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | scaffol, 80' boom | false |  |  |  |  | ACM Other | 22 | 100 | [40 empty] | 4 guys moving material to airwave and stair tower areas | 20
20067 | BNA PROJECT 5 | 2022-12-07 | Saúl Alvarado | Today we were working on the interior vestibule elevation | Subcontractor | Marc Ribar | [5 empty] | 6 | 10 |  |  | Boom lift and scissor lift | [5 empty] | Hat Channel Other | [34 empty] | 80 | [7 empty] | Terra-cotta | 60
21060 | Vantage VA 13 | 2022-12-07 | Joey laxton | 33 panels of perforated metal installed | Subcontractor | Steve Fudge | false |  |  |  |  | 3 | 10 | false |  | 86 ft boom lift | false |  |  |  |  | Perforated
22002 | DLR Sterling Premier Building A | 2022-12-07 | Jean negron | We start by installing 4 Louvers first louvre took us about 2 hrs bcs we were trying to find a way to work with it in the next 3 louvers took use like 1 hrs each Uber to cut and installed and 6 people was working with it ,total de 30 hrs , 10 clips was installed and 3 seal pan .c we unloaded a delivery of eight pallets of louvre material | Subcontractor | Steve Fudge | false |  |  |  |  | 6 | 60 | true | Eight pallets of louvre material | Boom lift and forklift sea scissor lift | false |  |  |  |  | Caulking Flashing Louvre | [20 empty] | 0 | 0 |  |  | 4 | 60 | [6 empty] | 30 | 2
20067 | BNA PROJECT 5 | 2022-12-06 | Naza | crews working at stair tower and air wave | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | 80' boom & baker scaffold | false |  |  |  |  | ACM Other | 21 | 100 | [40 empty] | moving material up to the roof | 20
22002 | DLR Sterling Premier Building A | 2022-12-06 | Jean negron | 70 clips was installed ,6 seal pan was installed we caulk we stalled seal pen we remove some wood the it was screws around the windows we start installing the first louvre at 12 and we start having some issues with the louvre we lost 2 hrs by installing the louvres and trying to find out way to installed the louvre and much time was lost for a issue about the Union we had to meteré every Union and company from the hit came to check everything around measured everything around the company hitt had to come over to figure something out much time was lost raining all morning | Subcontractor | Steve Fudge | true | Issues in the union and and losing time by measured ever opening |  |  | Raining | 7 | 70 | false |  | 3 Boom lift 1 forklift | false |  |  |  |  | Caulking Flashing Other | [20 empty] | 0 | 0 | [10 empty] | 59 | 2 | [8 empty] | E
22007 | Albion in the Gulch | 2022-12-06 | Keith Dukarm | Ran insulation and panels...me and Chad ran 51 panels other crew ran 18 | JWMCD Crew | Dillon Bowman | false |  |  |  |  | 5 | 8 | false |  | Swing stage | false |  |  |  |  | Insulation Single Skin
22021 | VA-14 | 2022-12-06 | Joey laxton | installed zee metal and insulation. punch list work on va 13 | Subcontractor | Nick Akins | false |  |  |  |  | 3 | 10 | false |  | 86 ft boom lift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 384 | 10 |  |  | 264 | 10
20067 | BNA PROJECT 5 | 2022-12-05 | Naza | north airwave, north mezz | Subcontractor | Marc Ribar | false |  |  |  |  | 14 | 140 | false |  | scaffold | false |  |  |  |  | ACM IMP | 20 | 70 | [6 empty] | 15 | 70
20067 | BNA PROJECT 5 | 2022-12-05 | Saul chicas | We were installing terra-cotta on the east elevation sector 20 and also we start doing doing layouts and installation some tracks inside we Installed 27 terra-cotta on sector 20 | Subcontractor | Marc Ribar | [5 empty] | 6 | 10 | true | Boom lift | Scissor lift | [5 empty] | Hat Channel Insulation | [34 empty] | 52
21024 | Vanderbilt Graduate Housing | 2022-12-05 | Marvin blanco | waiting on insulation and also panels | Subcontractor | Drake De Tomasi | true | acm panels and insulation |  |  |  | 6 | 11 | false |  | boomlift | false |  |  |  |  | ACM | 6 | 72
22007 | Albion in the Gulch | 2022-12-05 | Jean negron | 2 person moving material form the East to north side all day and and 4 person working on putting 120clips and 10 seal pan everything worked was in the north side of the building | Subcontractor | Dillon Bowman | false |  |  |  |  | 6 | 60 | true | Caulking and screw | Forklift and boom lift | false |  |  |  |  | Caulking Flashing Louvre | [20 empty] | 0 | 0 |  |  | 0 | 0 | [6 empty] | 10 | 20
22007 | Albion in the Gulch | 2022-12-05 | Keith Dukarm |  | JWMCD Crew | Dillon Bowman | false |  |  |  |  | 4 | 8 | false |  | Swing stage | false |  |  |  |  | Layout Single Skin | [6 empty] | 34 | [23 empty] | 42
22012 | QTS ASH2 DC1 Lockridge | 2022-12-05 | Marvin blanco | installing acm panels | Subcontractor | Josh McPherson | false |  |  |  |  | 21 | 12 | false |  | boomlift | false |  |  |  |  | ACM | 60 | 252
20067 | BNA PROJECT 5 | 2022-12-03 | Saul chicas | Today we were installing terra-cotta on the east elevation sector 20 and also we were installing some flashing for the expansion joints | Subcontractor | Marc Ribar | true | We were waiting for the waterproof to put caulking on our flashing that we installed on the east elevation sector 20 |  |  |  | 4 | 6 |  |  | Scissor lift | [5 empty] | Flashing Hat Channel Insulation Subgirt Zee | [32 empty] | 80
22002 | DLR Sterling Premier Building A | 2022-12-03 | Jean negron | We did not work this day bcs it was raining mostly all day | Subcontractor | Steve Fudge | false |  |  |  |  | 5 | 0 | false |  | 0 | false |  |  |  |  | Louvre | [24 empty] | 0 | 0
20067 | BNA PROJECT 5 | 2022-12-02 | Naza | column covers, overly flashing | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | 60' boom, 32' csissor | false |  |  |  |  | Flashing Other | [32 empty] | 180 | 60 | [8 empty] | column covers | 60
21087 | Long Hollow Baptist Church | 2022-12-02 | Fredy Veliz | No issues the first the first and second face is complete pending to come back on 01-02-23 to finish the portals | Subcontractor | Colton Van Meter | [5 empty] | 5 | 8 |  |  | Boom lift | [5 empty] | Plate |  |  | 24 | 40
22002 | DLR Sterling Premier Building A | 2022-12-02 | Jean negron | Working in the north side putting sell pan and clips | Subcontractor | Steve Fudge | true | Waiting for screw for the concrete and waiting for the widows colors |  |  | Good | 5 | 10 | true | 2 boom lift and 1 forklift | Boom lift and forkclift | false |  |  |  |  | Louvre | [24 empty] | 0 | 50
22007 | Albion in the Gulch | 2022-12-02 | Keith Dukarm | Moved material | JWMCD Crew | Dillon Bowman | false |  |  |  |  | 8 | 8 | false |  | Swing stage | false
22021 | VA-14 | 2022-12-02 | Joey Laxton | moved materials to roof and installed 22 perforated panels | Subcontractor | Nick Akins | false |  |  |  |  | 3 | 8 | false |  | 86 ft boom | false |  |  |  |  | Perforated
22023 | LaFontaine Buick GMC | 2022-12-02 | Chad mccoy | We came in this morning and started peeling and caulking. We started on the front left side left of the icon. I peeled out of the boom and my helper peeled and caulked the doors. We peeled all the way around the building. And half of the icon. While we were peeling. I could see what looks like little ripples all through the job. These ripples are along all sides of each panel. White black and brushed aluminum. They all have these ripples next to each return around the perimeter of each panel. Some are more noticeable than other. It is only panels that were folded up in the shop. All panels that we folded in the field seem to not have these areas. I sent a lot of picture to Colton | Subcontractor | Colton Van Meter | false |  |  |  |  | 2 | 8 | false |  | Boom lift | false |  |  |  |  | Caulking | [20 empty] | 250 | 5
20067 | BNA PROJECT 5 | 2022-12-01 | Naza | column covers, overly flashing | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | 60' boom, 32' csissor lift | false |  |  |  |  | Other | [42 empty] | clolumn covers & overly flashing | 120
21071 | Google NBY-HUB 1 | 2022-12-01 | Marvin blanco | taking pictures | Subcontractor | Steve Fudge | false |  |  |  |  | 6 |  | false |  |  | false |  |  |  |  | ACM
21071 | Google NBY-HUB 1 | 2022-12-01 | Marvin blanco | taking pictures | Subcontractor | Steve Fudge | false |  |  |  |  | 6 |  | false |  |  | false |  |  |  |  | ACM
21087 | Long Hollow Baptist Church | 2022-12-01 | Fredy | No issues | Subcontractor | Colton Van Meter | [5 empty] | 5 | 8 |  |  | Boom lift | [5 empty] | Plate |  |  | 36 | 40
22002 | DLR Sterling Premier Building A | 2022-12-01 | Jean negron | we were moving material and sorting material all day installation of clip angles top and down | Subcontractor | Steve Fudge | true | Delay on knowing what color it was in each window and we had to reach out the architect |  |  | 3 | 5 | 50 | false |  | Bunl | false |  |  |  |  | Louvre | [24 empty] | 0 | 50
22021 | VA-14 | 2022-12-01 | Joey laxton | installed 14 perforated metal panels | Subcontractor | Nick Akins | false |  |  |  |  | 3 | 10 | false |  | 86 ft boom lift | false |  |  |  |  | Perforated
22022 | Szott M59 Jeep Dealership Renovation | 2022-12-01 | Marvin blanco | everything good just waiting on punch list | Subcontractor | Drake De Tomasi | false |  |  |  |  | 3 |  | false |  |  | false |  |  |  |  | ACM
22022 | Szott M59 Jeep Dealership Renovation | 2022-12-01 | Marvin blanco | everything good | Subcontractor | Drake De Tomasi | false |  |  |  |  | 3 |  | false |  |  | false |  |  |  |  | ACM
22023 | LaFontaine Buick GMC | 2022-12-01 | Chad mccoy | We started today picking up on the icon where we left off on the top eyebrow Panels. We work left to right once we set the U-shaped panels and we started doing the top skyward Panels. Once our last icon panel went on we started doing the framing for the access doors and installing access doors. It was really no big issues today. We have sold seven pieces of Z into the cap panels of the existing building in front of the icon. | Subcontractor | Colton Van Meter | false |  |  |  |  | 2 | 8 | false |  | Boom lift | false |  |  |  |  | ACM | 17 | 6.5
20067 | BNA PROJECT 5 | 2022-11-30 | Naza | column covers, flashing north road canopy. | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | 60' boom, 32' csissor lift | false |  |  |  |  | Flashing Other | [32 empty] | 180 | 60 | [8 empty] | column covers | 60
20067 | BNA PROJECT 5 | 2022-11-30 | Saul chicas | We start working on sector 20 east elavtion | Subcontractor | Marc Ribar | [5 empty] | 5 | 10 |  |  | Scissor | [5 empty] | Flashing Hat Channel Insulation Other Subgirt Zee
21024 | Vanderbilt Graduate Housing | 2022-11-30 | Marvin blanco | installing plate panels | Subcontractor | Drake De Tomasi | false |  |  |  |  | 3 | 12 | false |  | boomlift | false |  |  |  |  | Plate |  |  | 16 | 36
21071 | Google NBY-HUB 1 | 2022-11-30 | Marvin blanco | taking pictures | Subcontractor | Steve Fudge | false |  |  |  |  | 5 |  | false |  |  | false |  |  |  |  | ACM
21071 | Google NBY-HUB 1 | 2022-11-30 | Marvin blanco | cleaning and taking pictures | Subcontractor | Steve Fudge | true | panels and windows flashing |  |  |  | 6 | 4 | false |  | nothing | false |  |  |  |  | Other | [42 empty] | cleaning | 30
21087 | Long Hollow Baptist Church | 2022-11-30 | Fredy veliz | No issues | Subcontractor | Colton Van Meter | [5 empty] | 5 | 8 |  |  | Boom lift | [5 empty] | Plate |  |  | 24 | 40
22021 | VA-14 | 2022-11-30 | Joey Laxton | moved materials and installed 33 perforated metal panels | Subcontractor | Nick Akins | false |  |  |  |  | 3 | 10 | false |  | 86 ft boom lift | false |  |  |  |  | Perforated
22021 | VA-14 | 2022-11-30 | Joey laxton | installed perforated metal and moved materials. 20 panels installed | Subcontractor | Nick Akins | false |  |  |  |  | 3 | 10 | false |  | 86ft boom lift | false |  |  |  |  | Perforated
19006 | Kistler Rolled Panels | 2022-11-29 | Keith Dukarm | Flashing and weep holes | JWMCD Crew | Chris Ball | false |  |  |  |  | 3 | 8 | false |  | Boom lift 125 i think | false |  |  |  |  | Flashing | [32 empty] | 70
19006 | Kistler Rolled Panels | 2022-11-29 | Keith Dukarm | Flashing and weep holes | JWMCD Crew | Chris Ball | false |  |  |  |  | 3 | 8 | false |  | Boom lift 125 i think | false |  |  |  |  | Flashing | [32 empty] | 70
20067 | BNA PROJECT 5 | 2022-11-29 | Naza | cover columns, north road canopy | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | 85' boom, 32' csissor lift | false |  |  |  |  | Other Overly Roof Panel | [12 empty] | 12 | 40 | [28 empty] | overly caps, column covers | 80
20067 | BNA PROJECT 5 | 2022-11-29 | Saul chicas | We keep working on section 17 east Elavtion | Subcontractor | Marc Ribar | [5 empty] | 5 | 10 |  |  | Scissor lift | [5 empty] | Flashing Hat Channel Insulation Other Subgirt Zee
21087 | Long Hollow Baptist Church | 2022-11-29 | Fredy veliz | We having issues with the structure, is out of square and smaller couple inches according to the drawings | Subcontractor | Colton Van Meter | true | Inconsistent dimensions on the structure |  |  | Raining after lunch | 5 | 7 |  |  | Boom lift | [5 empty] | Other Plate |  |  | 4 | 8 | [38 empty] | Re alignment panels to match with the structure dimensions | 27
22002 | DLR Sterling Premier Building A | 2022-11-29 | Jean negron | We did not work BCS it was raining all day | Subcontractor | Steve Fudge | false |  |  |  |  | 4 | 0 | false |  | 0 | false |  |  |  |  | Louvre | [24 empty] | 0 | 0
19006 | Kistler Rolled Panels | 2022-11-28 | Keith Dukarm | Waiting on others and cleaning panel that was most of problem panel went right up | JWMCD Crew | Chris Ball | false |  |  |  |  | 3 | 9 | false |  | Boom lift 125 i think | false |  |  |  |  | ACM | 1 | 9 | [18 empty] | 5
20067 | BNA PROJECT 5 | 2022-11-28 | Naza | walk brige, north road canopy | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | 32' csissor lift, 60' boom | false |  |  |  |  | ACM Other Overly Roof Panel | 24 | 60 | [10 empty] | 12 | 46 | [28 empty] | overly caps | 14
20067 | BNA PROJECT 5 | 2022-11-28 | Saul chicas | Today we keep working installing terra-cotta on sector 17 east elevation | Subcontractor | Marc Ribar | [5 empty] | 5 | 10 |  |  | Scissor lift | [5 empty] | Flashing Hat Channel Insulation Other Subgirt Zee | [43 empty] | 50
21087 | Long Hollow Baptist Church | 2022-11-28 | Fredy veliz | The estructure in the balconies is not the correct dimensions the outside panels are over hanging 1.1/2" | Subcontractor | Colton Van Meter | [5 empty] | 5 | 8 |  |  | Boom lift | [5 empty] | Plate |  |  | 10 | 40
22002 | DLR Sterling Premier Building A | 2022-11-28 | Jean negron | Me and my group started by doing the orientation after that we had to wait for the material arrive the ended up arriving at 4 pm we unloaded 2 the 2 truck trailer and we Andes up finishing by 7 pm | Subcontractor | Steve Fudge | true | From 9am to 4pm my group and I had wait for the material to arrive |  |  | 7 | 4 | 40 | true | Material | Forklift | false |  |  |  |  | Louvre | [24 empty] | 0 | 10
22023 | LaFontaine Buick GMC | 2022-11-27 | Chad mccoy | We started our morning laying out a panels on the flat stock that we brought to Michigan with us. We had to build a panel that span across the entry way of the icon. There was 2 bust in the original panel and it didn’t fill the spots needed over the columns. We built this panel and then installed it. We then continued with the icon till 12 o’clock then we stopped and we payed out and built a 4 sided column wrap that was busted up a route. Once this was built we installed it and the rest of the panels that stacks on it. We also broke down and threw away 6 crates. | Subcontractor | Colton Van Meter | true | Laying out these panels took a little while bc they both had specific areas that it needed to meet |  |  | Rain all day | 2 | 8 | true |  | Boom lift | false |  |  |  |  | ACM | 8 | 4
22023 | LaFontaine Buick GMC | 2022-11-26 | Chad mccoy | We started our day continuing on the icon left column. We stacked them up till we got to the sign panels. The sign panels go on before the rest of the column. So we installed the sign panels and then we were going to install the transition panel from the icon to the existing building. But there are 2 voids where nothing covers this area. So I talked to Colton and we came up with a plan to make a panel on site that will fit this area. After this decision we installed the rest of the column all the way up. We then started the top icon panels. Hat channel needs to be laid down prior to this panels being installed. We broke our last drill bit and that ended our day | Subcontractor | Colton Van Meter | true | the bust in the transition panels from the icon to the existing building |  |  | Cloudy /39 | 2 | 8 | false |  | Boom lift | false |  |  |  |  | ACM | 15 | 6
20067 | BNA PROJECT 5 | 2022-11-25 | Naza | north road canopy, walk bridge | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | 32' csissor lift , 60' boom | false |  |  |  |  | ACM Other | 24 | 60 | [40 empty] | overly caps | 60
20067 | BNA PROJECT 5 | 2022-11-24 | Naza | walk bridge, overly caps | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | 32' csissor lift, 60' boom | false |  |  |  |  | ACM Other | 24 | 60 | [40 empty] | overly caps | 60
20067 | BNA PROJECT 5 | 2022-11-23 | Naza | top-hat & north road canopy | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | 30' boom lift towable, 32' csissor lift | false |  |  |  |  | Flashing Overly Roof Panel | [12 empty] | 28 | 60 | [18 empty] | 130 | 60
21087 | Long Hollow Baptist Church | 2022-11-23 | Fredy veliz | No issues | Subcontractor | Colton Van Meter | [5 empty] | 2 | 8 |  |  | Boom lift | [5 empty] | Plate |  |  | 9 | 16
22012 | QTS ASH2 DC1 Lockridge | 2022-11-23 | Marvin blanco | installing acm panels and checking materials | Subcontractor | Josh McPherson | true | flashing |  |  | cold | 8 | 12 | false |  | boomlift | false |  |  |  |  | ACM | 20 | 96
20067 | BNA PROJECT 5 | 2022-11-22 | Naza | north road canopy, top-hat | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | 32' csissor lift, 30' boom towable | false |  |  |  |  | ACM Flashing Other Overly Roof Panel | 2 | 6 | [10 empty] | 32 | 50 | [18 empty] | 70 | 40 | [8 empty] | remove film | 24
21024 | Vanderbilt Graduate Housing | 2022-11-22 | Marvin blanco | installing panels | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 12 | false |  | boomlift | false |  |  |  |  | Plate |  |  | 12 | 36
21071 | Google NBY-HUB 1 | 2022-11-22 | Marvin blanco | fixing stuff and installing flashing around the windows | Subcontractor | Steve Fudge | true | panels coping and windows flashing |  |  | could | 6 | 12 | false |  | boomlift | false |  |  |  |  | Flashing | [32 empty] | 200 | 72
21087 | Long Hollow Baptist Church | 2022-11-22 | Fredy veliz | Missing one panel for the one of the columns | Subcontractor | Colton Van Meter | [5 empty] | 4 | 7 |  |  | Boom lift | [5 empty] | Plate |  |  | 23 | 28
22012 | QTS ASH2 DC1 Lockridge | 2022-11-22 | Marvin blanco | installing Acm panels | Subcontractor | Josh McPherson | false |  |  |  |  | 8 | 12 | false |  | 96 | false |  |  |  |  | ACM | 20 | 12
22022 | Szott M59 Jeep Dealership Renovation | 2022-11-22 | Marvin blanco | fixing stuff and installing panels | Subcontractor | Drake De Tomasi | false |  |  |  |  | 3 | 12 | false |  | boomlift | false |  |  |  |  | ACM | 20 | 36
20067 | BNA PROJECT 5 | 2022-11-21 | nAZA | NORTH CANOPY & BEAM COVERS | Subcontractor | Marc Ribar | false |  |  |  |  | 12 | 120 | false |  | 32' csissor lift, 60',85' boom lift | false |  |  |  |  | Other Overly Roof Panel | [12 empty] | 34 | 60 | [28 empty] | stainless steel panels beam covers | 60
20067 | BNA PROJECT 5 | 2022-11-21 | Saúl chicas | Today we were working installing terra-cotta on east elevation sector 17 | Subcontractor | Marc Ribar | [5 empty] | 4 | 10 |  |  | Scissor lift | [5 empty] | Hat Channel Insulation Subgirt Zee | [26 empty] | 192 |  |  |  | 140 |  |  |  | 80
21087 | Long Hollow Baptist Church | 2022-11-21 | Fredy veliz | No issues | Subcontractor | Colton Van Meter | [5 empty] | 2 | 8 |  |  | Boom lift | [5 empty] | Other | [42 empty] | Re screws 3 columns and install 10" flat peace on 2 columns | 16
22023 | LaFontaine Buick GMC | 2022-11-21 | Chad mccoy | We started our day Getting ready to install the last column panel.We pulled the panel out and took it to the tables we folded up two ends and put the brackets the corner brackets in. We noticed a crack going on the inside of the route and we were really hoping that we could save it but it was about 4 inches and when you looked at the poly you could see it through the poly. I FaceTime Colton to let him see the panel. So we skipped that panel on the panels above it and we continue to hang in the wall until all that’s left on the building is the icon in the four column panel | Subcontractor | Colton Van Meter | true | The damage panel will have to be installed later and the panels above it once I get the material and remake it on site |  |  | Partly cloudy and 29 | 2 | 8 | false |  | Boom | false |  |  |  |  | ACM | 19 | 6
22023 | LaFontaine Buick GMC | 2022-11-20 | Chad mccoy | We started our day at 6 degrees. But we picked up again on the long wall. We finished off the long wall all the way to the corner panels. Then we reverse laid out the corner panels down to the pavement. We then started laying out the cuts around the bump out in the bottom two panels. We could only install two of the column panels bc it’s a 4 sided wrap and the scissor lift is locked in the building. So we will pick that up Monday. We then set up for the icon. We started setting up and lying out the icon. We found that the bolts in the ground are to far away from the wall. I FaceTimed Colton and we talked about this situation. I installed the bottom two panels so that the condition that will flow up the sides will we seen so a decision can be made. | Subcontractor | Colton Van Meter | true | The icon bolts are to far away from the building to give us a nice joint up the areas that are closed to the original building. It’s suppose to be 1/2 inch. But the gap is 3 5/8 inches |  |  | 22 snow | 2 | 8 | false |  | Lull and boom | false |  |  |  |  | ACM Hat Channel | 12 | 5 | [32 empty] | 80 | 1
22041 | Moses Nissan | 2022-11-20 | David Placzkowski | installed perforated metal | Subcontractor | #NO MATCH | false |  |  |  |  | 4 | 5 | false |  | 86 ft boom | false |  |  |  |  | Perforated
21046 | The Moore Building | 2022-11-19 | Naza | Soffit panels at level 8 east | Subcontractor | Drake De Tomasi | false |  |  |  |  | 9 | 90 | false |  | 2 32' csissor lifts | false |  |  |  |  | ACM | 16 | 90
22021 | VA-14 | 2022-11-19 | David placzkowski | moved perforated materials to the roof. started install on perforated materials on roof screen wall | Subcontractor | Nick Akins | false |  |  |  |  | 4 | 8 | false |  | 86 ft boom lift | false |  |  |  |  | Perforated
22023 | LaFontaine Buick GMC | 2022-11-19 | Chad mccoy | We picked up where we left off Friday, down the long side of the building. I had been snowing for 4 days now. All the excursions and reveal slots are full of ice and snow. This is taken more time to prep and get ready for each panel. But we installed 22 panels and laid out the last three to double check previous layouts to the last column. | Subcontractor | Colton Van Meter | true | Ice in the excursions and 5 inches of snow with ice u set the snow |  |  |  | 2 | 10 | false |  | Lull and boom | false |  |  |  |  | ACM | 22 | 7
20067 | BNA PROJECT 5 | 2022-11-18 | Naza | south road canopy | Subcontractor | Marc Ribar | false |  |  |  |  | 10 | 100 | false |  | 32' csissor lift, 60' boom lift | false |  |  |  |  | IMP Overly Roof Panel | [8 empty] | 5 | 50 |  |  | 38 | 50
20067 | BNA PROJECT 5 | 2022-11-18 | Saul chicas | We installed some terra-cotta in east elevation sector 12 insulation zGarts tracks and terra-cotta | Subcontractor | Marc Ribar | [5 empty] | 5 | 10 |  |  | Scissor lift |  |  |  | 10 |  | Hat Channel Insulation Layout Other Subgirt Zee
21046 | The Moore Building | 2022-11-18 | Naza | 10 ACM panels at first level north side, 4 ACM panels at east soffit on level 8 and galvanized Zees's 700' | Subcontractor | Drake De Tomasi | false |  |  |  |  | 9 | 90 | false |  | swingstage & 2 32' csissor lifts | false |  |  |  |  | ACM Subgirt Zee | 14 | 50 | [28 empty] | 700 | 40
21071 | Google NBY-HUB 1 | 2022-11-18 | Marvin blanco | installing soffit panels | Subcontractor | Steve Fudge | false |  |  |  |  | 13 | 12 | false |  | boomlift | false |  |  |  |  | Other | [42 empty] | phenolic panels | 156
21087 | Long Hollow Baptist Church | 2022-11-18 | Fredy veliz | No issues | Subcontractor | Colton Van Meter | [5 empty] | 4 | 8 |  |  | Boom lift | [5 empty] | Plate |  |  | 12 | 32
22012 | QTS ASH2 DC1 Lockridge | 2022-11-18 | Marvin blanco | installing metal panels | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 12 | false |  | boomlift and scaffolding | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 42 | 72
22021 | VA-14 | 2022-11-18 | David placzkowski | installed zee and insulation. | Subcontractor | Nick Akins | false |  |  |  |  | 4 | 10 | false |  | 86 ft boom lift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 2700 | 20 |  |  | 624 | 20
22023 | LaFontaine Buick GMC | 2022-11-18 | Chad mccoy | We got up this morning and there was 4 inches of snow on the ground with a half an inch of ice underneath that. When we got to the site the panels were buried in snow and ice. A lot of our time today was trying to get ice out of the extrusions that are on the Panels so that we could properly engage them in reveal them. We started on the big column to the right of the icon that was a five sided panel this first panel had two curbs and an elevated sidewalk curve that had to be cut out of all of it. It took me a little while to lay this out due to the different elevations of the curves. These panels also we’re supposed to have a curtain wall that they went back to but this curtain wall was behind the limestone so I made a decision to fill the void in the back of the panel with a reveal that was double sided sticky tape and made onto the panel with another reveal which I talked to Colton about and FaceTime him and showed him. This had to be done all the way up the column on both sides. We have been running into issues with Panels that barely have any screws in the excursions. But once we put some screws in and we finish the call and we started hanging the upper soffit panels in between icon and this column. We also went up and adjusted some cap panels and got them ready for attachments with two by fours. | Subcontractor | Colton Van Meter | true | Panels are full of ice and snow and the panels have to be cleaned out especially the extrusions before we can even install these panels. Some of the panels are so full and so heavy that we have to clean them out in the crate the best we can before we move them because we do not want to slip and fall on the ice on the ground and damage panel. |  |  | Snow/28 | 2 | 9 | false |  | Lull boomlift | false |  |  |  |  | ACM | 9 | 5
20067 | BNA PROJECT 5 | 2022-11-17 | Naza | south road canopy | Subcontractor | Marc Ribar | false |  |  |  |  | 10 | 100 | false |  | 32' csissor lift, 60' boom lift | false |  |  |  |  | Flashing IMP | [8 empty] | 10 | 60 | [22 empty] | 240 | 40
20067 | BNA PROJECT 5 | 2022-11-17 | Naza | intermittent rain | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 50 | false |  | Scissor lift 32, boom lift 60' | false |  |  |  |  | Flashing Other Overly Roof Panel | [12 empty] | 14 | 30 | [18 empty] | 60 | 10 | [8 empty] | Metal caps moving material | 10
21046 | The Moore Building | 2022-11-17 | Naza | ACM panels soffit level 8 north, 800' of Zee's soffit level8 east side. | Subcontractor | Drake De Tomasi | false |  |  |  |  | 6 |  | false |  | 2 32' csissor lift | false |  |  |  |  | ACM Subgirt Zee | 7 | 20 | [28 empty] | 800 | 40
21046 | The Moore Building | 2022-11-17 | Naza | first level north | Subcontractor | Drake De Tomasi | false |  |  |  |  | 6 | 60 | false |  | swingstage | false |  |  |  |  | Subgirt Zee | [30 empty] | 210 | 60
21087 | Long Hollow Baptist Church | 2022-11-17 | Fredy veliz | No issues | Subcontractor | Colton Van Meter | [5 empty] | 4 | 8 |  |  | 2 boom lifts | [5 empty] | Plate |  |  | 19 | 32
22012 | QTS ASH2 DC1 Lockridge | 2022-11-17 | Marvin blanco | installing metal panels at screenwall taking time because the boomlift couldn't make it | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 12 | false |  | scaffolding and boomlift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 60 | 72
22021 | VA-14 | 2022-11-17 | David placzkowski | installed zee metal and insulation | Subcontractor | Nick Akins | false |  |  |  |  | 4 | 10 | true | perforated metal | 86ft boom | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 512 | 20 |  |  | 480 | 20
22023 | LaFontaine Buick GMC | 2022-11-17 | Chad mccoy | We started our morning transferring joint lines to the two main columns behind the Icon so we can double check That are joints are lining up all the way across still. We hung six panels on the two big columns at the main entrance and then we had to go to Fastenal to pick up all the hardware to put this deal together. I did not have sockets for this steel so I also had to go to AutoZone and get sockets for my half inch drive impact so that we could torque All the nuts and bolts down as tight as we can get them. I was in the boom lift the GC was in the scissor lift in my helper was driving the lull when we set the steel. What’s the steel and everything was bolted down and put where we put it within continued hanging panels. It snowed on us all day | Subcontractor | Colton Van Meter | true | The weather has been cold and snowing and icy the last couple days. These column panels that we were putting up are huge and they wrap multiple sides so it takes a little while to get these panels shimmed up to where they need to be on the starter Panels at the bottom of the column |  |  | 29/snow | 2 | 9 | false |  | Lull and boom lift | false |  |  | 1 |  | ACM Layout | 18 | 7
20067 | BNA PROJECT 5 | 2022-11-16 | Naza | south road canopy | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 50 | false |  | 32' csissor lift | false |  |  |  |  | Flashing Other Overly Roof Panel | [12 empty] | 14 | 30 | [18 empty] | 30 | 12 | [8 empty] | metal caps for overly panels | 8
21046 | The Moore Building | 2022-11-16 | Naza | ACM pnels first level north | Subcontractor | Drake De Tomasi | false |  |  |  |  | 6 | 60 | false |  | swingstage | false |  |  |  |  | ACM | 14 | 60
22021 | VA-14 | 2022-11-16 | David placzkowski | installing zee and insulation | Subcontractor | Nick Akins | false |  |  |  |  | 5 | 10 | false |  | 86ft boom lift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 1024 | 10 |  |  | 1236 | 10
22023 | LaFontaine Buick GMC | 2022-11-16 | Chad mccoy | We started this morning picking up we left off yesterday. We did three panels from the soffit to the parapet cap. Then I had to transfer horizontal joint lines with the laser so that we could start the big column. This column has multiple sides with multiple angles with two tight fit joints. We had to dig out the rock and the mulch to get the panel to go down to where we could attach it at the bottom. This first panel also had to be cut twice and routed and then cut for the curves that it went over. Once this panel is set we set the panel adjacent to it and once these panels were where we wanted them to be we stacked the rest of the column. Once the column is finished we went back to the soffit/face panel and then continued up the wall. We set six more panels after this. While I set the last three panels my helper moved material for tomorrow’s install closer to where we’re gonna be installing and we cleaned up all the trash where the crates were | Subcontractor | Colton Van Meter | true | The big column had 135 routes that were hand routed after They were machined. These 135s are not capable of being done on the CNC so it has to be hand done but when they did the 135 routes in person they are not straight |  |  | cloudy and 31 | 2 | 11 | true | Backer rod and metal plates | Boom lift and scissor | false |  |  |  |  | ACM | 18 | 8.5
20067 | BNA PROJECT 5 | 2022-11-15 | Naza | location south road canopy | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 50 | false |  | 32'csissor lift | false |  |  |  |  | Flashing Other Overly Roof Panel | [12 empty] | 16 | 30 | [18 empty] | 30 | 12 | [8 empty] | metal caps | 8
21046 | The Moore Building | 2022-11-15 | Naza | firt level north | Subcontractor | Drake De Tomasi | false |  |  |  |  | 6 | 60 | false |  | swingstage | false |  |  |  |  | ACM | 14 | 60
22023 | LaFontaine Buick GMC | 2022-11-15 | Chad McCoy | We started the morning getting the delivery of the lull. And we picked up where we left off with the panels over the two garage doors. We had the layout for the two middle panels that attach to the A112. Once that was set we stacked all the panels on top of it. Everything seemed to be feeling really good and laying where it’s supposed to be. Once we wrap the top of the Para pit we started on the next column with the multilevel cut bottom and the drain pipe in the face. This panel had to be laid out in four different areas due to unlevel ground a curve a pipe and a window curve. What’s this panel was installed we stack the column all the way up. After we put the top pre-glue up panel on we then started doing the panels over the curtain wall and the ones about.. It snowed on us all day but we push through. There are absolutely no routed reveals so every reveal Hass to be custom-made to the Panels | Subcontractor | Colton Van Meter | true | It takes a while to lay out the reveals we need for a multi turn column wrap but we got it. Panels also or mislabeled they will have a sticker on one end that does not match the marker number in the middle. And then a lot of the panels don’t have stickers on the ends at all so we had to take multiple panels out of crates to figure out what panels are what |  |  | Snowing and 30s | 2 | 11 | false |  | Boom lift, lull | false |  |  |  |  | ACM | 19 | 8
21046 | The Moore Building | 2022-11-14 | Naza | ACM panels north elevation | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 50 | false |  | 120' | false |  |  |  |  | ACM | 4 | 50
21087 | Long Hollow Baptist Church | 2022-11-14 | Fredy veliz | No issues | Subcontractor | Colton Van Meter | [5 empty] | 4 | 8 |  |  | Boom lift | [5 empty] | Other Plate |  |  | 12 | 26 | [38 empty] | Move materials ,install 10" metal plates | 8
22012 | QTS ASH2 DC1 Lockridge | 2022-11-14 | Marvin blanco | installing metal panels with to much trouble on the scaffolding. | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 12 | false |  | scaffolding | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 47 | 72
22012 | QTS ASH2 DC1 Lockridge | 2022-11-14 | Marvin blanco | installing metal panels with to many problems | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 12 | false |  | boomlift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 24 | 72
22022 | Szott M59 Jeep Dealership Renovation | 2022-11-14 | Marvin blanco | waiting on material and also installing panels | Subcontractor | Drake De Tomasi | true | flashing for the lights |  |  | could | 3 | 12 | false |  | boomlift | false |  |  |  |  | ACM | 40 | 36
22023 | LaFontaine Buick GMC | 2022-11-14 | Chad mccoy | We started our morning getting to the site to try to figure out the best times to start with the sun and the light. We laser lined a level line across all columns. The first set of trucks to show up to be unloaded till about 850. They were three deliveries of material and there was one delivery of a boom lift. The forklift that we used to unload everything was small but eventually we got everything unloaded. Once everything was unloaded we went through the crates and we wrote down every single panel that was in those crates on that crate so we don’t have to worry about the paper when it starts raining and snowing later this week. We then started pulling panels for the interior two columns at the main entrance behind the icon that we have to put up. The bottom two panels had to be cut to fit around concrete curbs so that was a little bit of a layout. Once we did those six panels we moved to the far left-hand side and started laying out and running the A1 12 so that we can put the panels around the doors. The columns are a main must have to make sure that we fall in line with the horizontal joints in the top panels. We did not reach our goal for Panels per day today but it was a late start on the installation due to layout deliveries and equipment | Subcontractor | Colton Van Meter | true | The first panels that we needed for the bottom of the columns in come on the first truck of a Acm came on the second |  |  | Cold cloudy | 2 | 11 | true | Crates of ACM, The steel for the icon, One boob lift | Boom lift | false |  |  | 1 |  | ACM Layout | 14 | 5
21046 | The Moore Building | 2022-11-11 | Naza | ACM panels north elevation | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 50 | false |  | 120' | false |  |  |  |  | ACM | 5 | 50
21046 | The Moore Building | 2022-11-10 | Naza | ACM panels north elevation | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 50 | false |  | 120' boom | false |  |  |  |  | ACM | 5 | 50
21071 | Google NBY-HUB 1 | 2022-11-10 | Marvin blanco | many problems in each of the things we want to do checking material and also waiting for material | Subcontractor | Steve Fudge | true | panels and coping |  |  | good condition | 10 | 12 | false |  | boomlift scissors lift | false |  |  |  |  | Other | [42 empty] | nothing my guys are waiting for material | 120
21075 | 900 Church AECOM | 2022-11-10 | Chad mccoy | We started our day picking up the cleats at mcdougal. I took the cleat and off loaded it at 900 church. After I went back to mcdougal and grabbed the coping. I dropped it off and Keith and I went to Albion and moved everything. I left the key and scissor lift box with Micheal. We then went back to 900 church. Kevin and I started laying out and installing the cleats and. Opting. Keith trimmed out everything. Starlin started caulking. Not one piece of coping was the same size. The cleat was miss bent and not made for the coping to lock on. I had to but screws in the front and back for a solid attachment. At the end of the day we had to take the scaffolding down and all the trash. We left a lot of trim and corrugated in case we had the panel under the door needs to be installed. | Subcontractor | Denis Usatenko | true | The coping and cleat were miss bent and nothing was the same size so lining up anything was a plug and play situation. |  |  | Clear | 4 | 9 | true | Cleat and coping | Nothing | false |  |  |  |  | Caulking Coping | [20 empty] | 50 | 3 | [18 empty] | 65 | 5
21087 | Long Hollow Baptist Church | 2022-11-10 | Fredy veliz | No issues | Subcontractor | Colton Van Meter | [5 empty] | 4 | 8 |  |  | Boom lift | [5 empty] | Plate |  |  | 12 | 32
22012 | QTS ASH2 DC1 Lockridge | 2022-11-10 | Marvin blanco | installing coping and metal panels | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 12 | false |  | boomlift | false |  |  |  |  | Coping Corrugated / Screen wall | [22 empty] | 16 | 30 | [16 empty] | 32 | 42
22021 | VA-14 | 2022-11-10 | David placzkowski | installed zee and insulation | Subcontractor | Nick Akins | false |  |  |  |  | 3 | 10 | false |  | 86ft boom lift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 1280 | 15 |  |  | 336 | 5
22022 | Szott M59 Jeep Dealership Renovation | 2022-11-10 | Marvin blanco | installing panels | Subcontractor | Drake De Tomasi | false |  |  |  |  | 3 | 12 | false |  | boomlift | false |  |  |  |  | ACM | 30 | 36
22024 | The Joseph Hotel | 2022-11-10 | Marvin blanco | plate panels and angles | Subcontractor | Hannah Sadloski | false |  |  |  |  | 5 | 12 | false |  | swing stage | false |  |  |  |  | Plate |  |  | 24 | 60
20067 | BNA PROJECT 5 | 2022-11-09 | Naza | night crew pedestrian bridge | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  |  | false |  |  |  |  | ACM | 15 | 30
20067 | BNA PROJECT 5 | 2022-11-09 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 60 | false |  | 60', 86' boom | false |  |  |  |  | Other | [42 empty] | column covers, moving materiall | 60
21046 | The Moore Building | 2022-11-09 | Naza | galvanized Zee's north elevation | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 50 | false |  | 120' boom | false |  |  |  |  | Subgirt Zee | [30 empty] | 430 | 50
21075 | 900 Church AECOM | 2022-11-09 | Chad mccoy | We started our morning at the shop looking at the coping that was made NOT TO FIT. after talking to Dennis we met up with Dennis and went to Albion. We looked over everything and came up with a plan. Once we got back to mcdougal Keith and I checked out the coping again and then we headed to 900 church. To install flashing and two panels where the steel was installed. I had to lay out and cut 16 holes While this was going on other trades we’re doing finish install on the window wall. And pipes were being ran and installed in the panel holes that we cut out before we left last time. | Subcontractor | Denis Usatenko | true | Other trades working in our area of each wall |  |  | Clear | 2 | 8 | false |  | Nothing | false |  |  | 1.5 |  | Corrugated / Screen wall Layout | [22 empty] | 2 | 1
21087 | Long Hollow Baptist Church | 2022-11-09 | Fredy veliz | No issues | Subcontractor | Colton Van Meter | [5 empty] | 6 | 8 |  |  | Boom lift | [5 empty] | Plate |  |  | 10 | 48
22021 | VA-14 | 2022-11-09 | David Placzkowski | installed zee metal and insulation | Subcontractor | Nick Akins | false |  |  |  |  | 3 | 10 | false |  | 86ft boom lift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 960 | 6 |  |  | 756 | 14
20067 | BNA PROJECT 5 | 2022-11-08 | Naza | night crew pedestrian bridge | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  | 32' csissor lift | false |  |  |  |  | ACM | 18 | 30
20067 | BNA PROJECT 5 | 2022-11-08 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 7 | 70 | false |  | 60', 86' boom | false |  |  |  |  | Other | [42 empty] | column covers, moving materiall | 70
21046 | The Moore Building | 2022-11-08 | Naza | purlins east elevation | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 50 | false |  |  | false |  |  |  |  | Other | [42 empty] | purlins east elevatiom | 50
21087 | Long Hollow Baptist Church | 2022-11-08 | Fredy veliz | We found that some panels are made smaller then other ones | Subcontractor | Colton Van Meter | [5 empty] | 6 | 10 | true | Perforated Panels plates | Boom lift | [5 empty] | Other Plate |  |  | 12 | 40 | [38 empty] | Moving material to the work area and cuting angles clips for vertical joint | 20
22021 | VA-14 | 2022-11-08 | David Placzkowski | installed zee and insulation | Subcontractor | Nick Akins | false |  |  |  |  | 3 | 10 | true | 490 pieces of zee metal and 8 pallets of Insulation | 86ft boom lift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 1152 | 10 |  |  | 432 | 10
20067 | BNA PROJECT 5 | 2022-11-07 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  | 32' csissor lift | false |  |  |  |  | ACM | 17 | 30
20067 | BNA PROJECT 5 | 2022-11-07 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 7 | 70 | false |  | 86' 60' boom | false |  |  |  |  | Other | [42 empty] | co,umn covers and moving materiall | 70
21046 | The Moore Building | 2022-11-07 | Naza | tubes and purlins east elevation | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 50 | false |  | 80'boom | false |  |  |  |  | Other Tubing | [28 empty] | 30 | 12 | [12 empty] | 3 embeds 28 purlins | 38
21071 | Google NBY-HUB 1 | 2022-11-07 | Marvin blanco | installing panels coping and fixing panels | Subcontractor | Steve Fudge | true | panels coping |  |  | good condition | 10 | 12 | false |  | boomlift | false |  |  |  |  | Coping Plate |  |  | 18 | 50 | [36 empty] | 280 | 70
21087 | Long Hollow Baptist Church | 2022-11-07 | Fredy veliz | Have some issues with the vertical steel tube not welded in the right place | Subcontractor | Colton Van Meter | true | Steel tube builded incorrect |  |  |  | 4 | 10 |  |  | Boom. Lift |  |  |  | 2 |  | Layout Other Plate |  |  | 8 | 18 | [38 empty] | Removing panels from the creates and moving to the working areas | 20
22012 | QTS ASH2 DC1 Lockridge | 2022-11-06 | Marvin blanco | installing metal panels | Subcontractor | Josh McPherson | true | clips for metal panels |  |  | good condition | 6 | 12 | false |  | boomlift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 27 | 72
22022 | Szott M59 Jeep Dealership Renovation | 2022-11-06 | Marvin blanco | installing panels | Subcontractor | Drake De Tomasi | false |  |  |  |  | 3 | 12 | false |  | boomlift | false |  |  |  |  | ACM | 25 | 36
22053 | Fort Worth Carvana | 2022-11-06 | Marvin blanco | installing panels | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 12 | false |  | boomlift | false |  |  |  |  | ACM | 10 | 48
22017 | Paretti Mazda | 2022-11-05 | Chad mccoy | We went to this site the other day and the left was wrong. So Eric re ordered a bigger lift. So when we got on site the new scissor lift was locked in the building. So I called Marcus and we got in. Upon setting the lift up and going to the top of structure we noticed a gray coping panel installed instead of black. So I called Eric and a agreement was made and we made that one to. So we took off 3 panels 2 caps and one small panel to get the big scratched panel out. We made both panels and we re installed these panels and caulked everything back the way it was | Subcontractor | Eric Gutierrez | false |  |  |  |  | 2 | 4 | false |  | 26 foot scissor | false |  |  |  |  | ACM | 4 | 2
20067 | BNA PROJECT 5 | 2022-11-04 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  | 32' scissor lift | false |  |  |  |  | Overly Roof Panel | [12 empty] | 34 | 30
20067 | BNA PROJECT 5 | 2022-11-04 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 60 | false |  | 86' boom | false |  |  |  |  | Other | [42 empty] | column covers and moving materiall | 60
21024 | Vanderbilt Graduate Housing | 2022-11-04 | Marvin blanco | installing and remaking panels | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 13 | false |  | swing stage and boomlift | false |  |  |  |  | ACM Hat Channel | 8 | 20 | [32 empty] | 36 | 32
21046 | The Moore Building | 2022-11-04 | Naza | east elevation | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 50 | false |  | 80' boom | false |  |  |  |  | Other | [42 empty] | 98 purlins | 50
21071 | Google NBY-HUB 1 | 2022-11-04 | Marvin blanco | remaking panels and installing panels making for panels that John W McDougall made bigger and smaller I hope they get better on this | Subcontractor | Steve Fudge | true | panels base flashing silicone screws pop rivet |  |  | good | 9 | 12 | false |  | boomlift | false |  |  |  |  | Flashing Plate |  |  | 18 | [29 empty] | 160
22012 | QTS ASH2 DC1 Lockridge | 2022-11-04 | Marvin blanco | installing angles and z's at the screenwall on DC2 | Subcontractor | Josh McPherson | true | clips for metal panels |  |  | good | 6 | 12 | false |  | boomlift | false |  |  |  |  | Hat Channel | [34 empty] | 168 | 72
22022 | Szott M59 Jeep Dealership Renovation | 2022-11-04 | Marvin blanco | installing panels and remaking panels | Subcontractor | Drake De Tomasi | false |  |  |  |  | 3 | 12 | false |  | boomlift | false |  |  |  |  | ACM | 35 | 36
22053 | Fort Worth Carvana | 2022-11-04 | Marvin blanco | remaking panels and installing panels | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 12 | false |  | boomlift | false |  |  |  |  | ACM | 6 | 48
20067 | BNA PROJECT 5 | 2022-11-03 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  | 32' scissor lift | false |  |  |  |  | Overly Roof Panel | [12 empty] | 37 | 30
20067 | BNA PROJECT 5 | 2022-11-03 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 60 | false |  | 86' boom | false |  |  |  |  | Other | [42 empty] | columns install and moving materiall | 60
21082 | UTMC MOB | 2022-11-03 | Keith Dukarm |  | JWMCD Crew | Josh McPherson | false |  |  |  |  | 3 | 8 | false |  | Scissor lift | false |  |  |  |  | Flashing
22021 | VA-14 | 2022-11-03 | Naza | east elevation tubes and | Subcontractor | Nick Akins | false |  |  |  |  | 6 |  | false |  | 80' & 120' boom | false |  |  |  |  | Other Tubing | [28 empty] | 40 | 18 | [12 empty] | 4 embeds & 65 purlins | 22
22057 | Ochsner West Tower | 2022-11-03 | Chad mccoy | We started our day adjusting the swing stage to take the soffits off. But when we got it adjusted and then we went all the way to the soffits, we couldn’t reach back into the inter corner like we thought. So with the cable and stage as far right as we could go. I could not reach 2.6 feet of the panels. So around 6 square feet would not be able to be in attached from the building. So a decision was made by oscjner and the GC that 3 soffits wouldn’t be changed and the new panels will remain on site with oschner. So we went and we re adjusted the stage again to re install the two panels we took off. Once the stage was adjusted. We had to take apex up so he could see the structure and make sure all was good prior to us putting anything back. Once he was finished we took him down and pulled our panel. Prior to installing the panels. All excrusions had to be swapped to to the new panels not matching the ones we took down. Every stiffener had to have 12 inches cut off so it would lay in the original spots as the older panels. So prepping each panels is time consuming. To take these panels up in the stage we have to first lull them to the second roof. Then we had to walk them to the stage. Then we have to have 2 cradles ready on the stage to hold these panels. Walking up the building in the stage is a balancing act bc the panel is off weight from one side to the other. So and movement in the stage is a drastic deep in the stage front to back. . Once we got the panels installed. We cleaned up all of our mess from the old cut up panels. | Subcontractor | Eric Gutierrez | true | Panels were built wrong |  |  | Hot and partly cloudy | 2 | 11 | false |  | 30 foot stage | false |  |  |  |  | ACM | 2 | 2
20067 | BNA PROJECT 5 | 2022-11-02 | nAZA | NIGHT CREW south road canopy & column covers | Subcontractor | Marc Ribar | false |  |  |  |  | 10 | 100 | false |  | 86', 60' & 32' scissor | false |  |  |  |  | Other Overly Roof Panel | [12 empty] | 40 | 30 | [28 empty] | column covers 7 pcs | 70
21046 | The Moore Building | 2022-11-02 | Naza | guys installing tubes east elevation using boom lift. | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 40 | false |  | 80' & 120' boom | false |  |  |  |  | Other Tubing | [28 empty] | 70 | 24 | [12 empty] | moving materiall, install embeds | 16
21082 | UTMC MOB | 2022-11-02 | Keith Dukarm |  | JWMCD Crew | Josh McPherson | false |  |  |  |  | 3 | 8 | false |  | Scissor lift | false |  |  |  |  | Flashing
22021 | VA-14 | 2022-11-02 | David placzkowski | installed zee metal and insulation | Subcontractor | Nick Akins | false |  |  |  |  | 3 | 6 | false |  | 85 ft boom lift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 260 | 6 |  |  | 324 | 6
22057 | Ochsner West Tower | 2022-11-02 | Chad mccoy | We started our morning meeting up with John and Joe and them giving us the rundown of everything that needed to happen with the other trades. We went to the roof and we checked out all the swing stage builds before we went and got on the swing stage. And then we went down and prepped the ladders and got everything to the second floor so that we could start going up in the swing stage and take a material down. Upon getting to the top with the swing stage we found that the swing stage was in the wrong position. The swing stage needed to be moved further out on the I-beams and it needed to be moved 6 feet to the left to the inside corner. They also put two by fours and peel and stick over the Panels and this had to be removed prior to panels being removed. The swing stage didn’t get moved in finished until around 2 o’clock. The lights were done earlier that day with my yo-yo and a ladder going down over the ledge on the roof. We went ahead and we prepped one of the swing stage verticals but the other one had to be completely tore down and moved to the right 4 feet. Once the swing stage was done we went up and we started cutting the panels out of place and taking the wood blocking and the peel and stick down. Upon further inspection we found that rockwool is missing off the inside face of the Panels I do not have Rockwall to put it back. We successively cut out the two big panels and the inside upper corner. During this entire time when we were cutting Panels out we were getting swarmed by over 30 wasp from all directions. We did not remove the soffit panels because I have to move the swing stage back in to reach the inside section where the soffit panels are. The soffit panels will be moved first thing in the morning. We cleaned up all our cut pieces and took it down to the second high roof and stacked it so when we put the new panels on the second high roof we can load the lull with cut material to take to the dumpster. The swing stage per each section is going to take for individual adjustments To reach the outside an upper part of the panels and then to reach the soffit and then it has to be done in reverse for installation. | Subcontractor | Eric Gutierrez | true | The swing stage was set up in the wrong section and all the preventive measures with the two by fours and pillars dickhead to be removed prior to Panels being taken down |  |  | Partly cloudy | 2 | 11 | true | 2 crates / a skid of flat stock | 30 foot swing stage | false |  |  |  |  | Other | [42 empty] | Panels were cut out that were damaged in the hurricane | 2
20067 | BNA PROJECT 5 | 2022-11-01 | Naza | night crew working at south road canopy & column covers. | Subcontractor | Marc Ribar | false |  |  |  |  | 10 | 100 | false |  | 86', 60' boom and 32' scissor lift | false |  |  |  |  | Other Overly Roof Panel | [12 empty] | 39 | 30 | [28 empty] | column covers | 70
21046 | The Moore Building | 2022-11-01 | Naza | no delays today... | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 50 | false |  | 80' & 120' boom | false |  |  |  |  | ACM Caulking Other | 6 | 16 | [18 empty] | 10 | 4 | [20 empty] | 105 purlins, sealed all the screw heads of the Zee's | 20
21082 | UTMC MOB | 2022-11-01 | Keith Dukarm |  | JWMCD Crew | Josh McPherson | false |  |  |  |  | 3 | 8 | false |  | Scissor lift | false |  |  |  |  | Flashing
22021 | VA-14 | 2022-11-01 | David Placzkowski | Installed insulation and zee metal | Subcontractor | Nick Akins | false |  |  |  |  | 3 | 10 | false |  | 86ft boom lift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 1344 | 16 |  |  | 240 | 4
20067 | BNA PROJECT 5 | 2022-10-31 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 7 | 70 | false |  | 60' & 86' boom | false |  |  |  |  | Other | [42 empty] | column covers 8 pcs | 70
21046 | The Moore Building | 2022-10-31 | Naza | the crew working on the north elevation stopped working due to escabasions on the ground. | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 50 | false |  | 80' & 120' boom | false |  |  |  |  | Other Subgirt Zee | [30 empty] | 300 | 14 | [10 empty] | purlins 98 pcs 20 hrs, Embeds 6 hrs. | 26
21024 | Vanderbilt Graduate Housing | 2022-10-30 | Marvin blanco | installing z's and panels acm | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 12 | false |  | boomlift and swing stage | false |  |  |  |  | ACM Plate | 6 | 24 | 6 | 24
21071 | Google NBY-HUB 1 | 2022-10-30 | Marvin blanco | remaking flashing because they make it rough | Subcontractor | Steve Fudge | false |  |  |  |  | 7 | 12 | false |  | boomlift | false |  |  |  |  | Other | [42 empty] | making a flashing for the windows | 72
21071 | Google NBY-HUB 1 | 2022-10-30 | Marvin blanco | installing flashing around the windows and cleaning | Subcontractor | Steve Fudge | true | panels and coping |  |  | could | 7 | 12 | false |  | boomlift | false |  |  |  |  | Flashing | [32 empty] | 600 | 84
21082 | UTMC MOB | 2022-10-30 | Keith Dukarm |  | JWMCD Crew | Josh McPherson | false |  |  |  |  | 3 | 8 | false |  | Scissor lift | false |  |  |  |  | Flashing
22012 | QTS ASH2 DC1 Lockridge | 2022-10-30 | Marvin blanco | installing metal panels | Subcontractor | Josh McPherson | true | clips for panels |  |  | could | 6 | 12 | false |  | boomlift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 42 | 72
22022 | Szott M59 Jeep Dealership Renovation | 2022-10-30 | Marvin blanco | installing panels acm | Subcontractor | Drake De Tomasi | false |  |  |  |  | 3 | 12 | false |  | boomlift | false |  |  |  |  | ACM | 12 | 36
21046 | The Moore Building | 2022-10-29 | Naza | tube lay out doesn't align with the layuot of the ACM panels and windows above. | Subcontractor | Drake De Tomasi | false |  |  |  |  | 7 | 56 | false |  | 80' & 120' boom | false |  |  |  |  | ACM Other | 5 | 32 | [40 empty] | layouts for plates, aligning plates. | 24
22012 | QTS ASH2 DC1 Lockridge | 2022-10-29 | erwin hernandez | installing metal panels | Subcontractor | Josh McPherson | true | clips for metal panels |  |  | good condition | 5 | 12 | false |  | scaffolding and boomlift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 42 | 60
20067 | BNA PROJECT 5 | 2022-10-28 | Naza | night crew column covers and roof panels at south road canopy. | Subcontractor | Marc Ribar | false |  |  |  |  | 9 | 90 | false |  | 32' csissor, 60' & 86' boom. | false |  |  |  |  | Other Overly Roof Panel | [12 empty] | 20 | 20 | [28 empty] | column covers 7 pcs | 70
21046 | The Moore Building | 2022-10-28 | Naza | window above it is not sealed to the wall yet to continue with the installation of the panels | Subcontractor | Drake De Tomasi | false |  |  |  |  | 8 | 80 | false |  | 80' & 120' boom | false |  |  |  |  | ACM Other | 11 | 40 | [40 empty] | purlins 115 pcs | 40
20067 | BNA PROJECT 5 | 2022-10-27 | Naza | night crew columns | Subcontractor | Marc Ribar | false |  |  |  |  | 7 | 70 | false |  | 86' & 60' boom | false |  |  |  |  | Other | [42 empty] | columns covers 8 pcs | 70
20067 | BNA PROJECT 5 | 2022-10-27 | Naza | 5 panels fabricated to fit at south of top canopy | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  |  | false |  |  |  |  | ACM Other | 5 | 16 | [40 empty] | fabricating the 5 panela, carring panels up to the roof, take film off | 14
21046 | The Moore Building | 2022-10-27 | Naza | no delays | Subcontractor | Drake De Tomasi | false |  |  |  |  | 8 | 80 | false |  | 80' &120' boom | false |  |  |  |  | ACM Other | 8 | 40 | [40 empty] | purlins 130 pcs east elevation | 40
22007 | Albion in the Gulch | 2022-10-27 | Chad mccoy | We started our morning early. We fought the buck hoist all day. Keith and I starting bring our side insulation to level 9. The buck hoist was taken 20-30 minutes to pick us up. Kevin and starlin finished there z on there walls. Once we got our first wall of insulation on 9 we started installing. As we installed we caulked the screws to the wall. After our insulation was all in. We cut down strapping and installed 2 rolls on the out side insulation closes to the edges of the building. Once our side was done. We kept bring up insulation to help Kevin and his side. Once Kevin’s side was done. We cLeaned up a took the carts down. | Subcontractor | Dillon Bowman | true | Buck hoist had multiple delivers that hindered buck hoist trips |  |  | Partly cloudy / chilly | 4 | 6 | false |  | Scissor lift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 1600 | 4 |  |  | 60 | 1
22021 | VA-14 | 2022-10-27 | David placzkowski | installed zee metal | Subcontractor | Nick Akins | false |  |  |  |  | 3 | 10 | false |  | 86ft boom | false |  |  |  |  | Subgirt Zee | [30 empty] | 588 | 20
20067 | BNA PROJECT 5 | 2022-10-26 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 7 | 70 | false |  | 86' & 60' boom | false |  |  |  |  | Other | [42 empty] | column covers 8 pcs | 70
20067 | BNA PROJECT 5 | 2022-10-26 | Naza | 6 panela fabricated north top canopy | Subcontractor | Marc Ribar | true | Issues with the boom lift for 2 hours |  |  | sunny | 4 |  | false |  | 36' boom towable | false |  |  |  |  | ACM Other | 6 | 24 | [40 empty] | moving material up to the roof | 8
21046 | The Moore Building | 2022-10-26 | Naza | 2 guys 1/2 day cutting purlins at the shop after cutting they bring the purlins to moore building. ACM 5 corner panels install at north east cormer | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 50 | false |  | 80' & 120' boom | false |  |  |  |  | ACM Other | 5 | 30 | [40 empty] | cutting and installing purlins east elevation | 20
21071 | Google NBY-HUB 1 | 2022-10-26 | Marvin blanco | building scaffolding and taking down the scaffolding | Subcontractor | Steve Fudge | true | panels |  |  | could | 8 | 12 | false |  | scissors lift | false |  |  |  |  | Other | [42 empty] | they couldn't work because the safety guy don't letting work | 96
22007 | Albion in the Gulch | 2022-10-26 | Chad mccoy | We started our morning trying to find a new place to park. The parking lot where we did park before is now a towing zone. Once we got on site I updated our board. And we then moved our tools and all the z to level 9 on level 4 to level 9. We set up the laser and we laser lined all four walls to be the same. Keith and I installed two walls and Kevin and starlin did the other two. We ran out of z’s two times. And we had to get more from the ground. We had to end our day and go to 900 church. I had to secure to panels on Marvin’s guys panel install around the pool. A welder welded in two stainless steel brackets and I drilled holes and screwed the panels in to secure them. After this we went to mcdougal and I strapped the straps off of our pick of 900 church of material off of level 35. After that I dropped off the guys and I had to go to south hall for a quick look at where a sign should go | Subcontractor | Dillon Bowman | false |  |  |  |  | 4 | 11 | false |  | Scissor lift | false |  |  | 1 |  | Layout Subgirt Zee | [30 empty] | 860 | 6
22021 | VA-14 | 2022-10-26 | David placzkowski | installed zee metal and Insulation | Subcontractor | Nick Akins | false |  |  |  |  | 1 | 10 | false |  | 86ft boom lift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 384 | 4 |  |  | 588 | 16
20067 | BNA PROJECT 5 | 2022-10-25 | Naza | 5 panels fabricated bottom to fit north of top canopy RCP | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 40 | false |  | 36' bnoom towable | false |  |  |  |  | ACM Flashing Other | 5 | 15 | [30 empty] | 30 | 6 | [8 empty] | 5 panels were made to measure and carring panels up to the roof | 19
21024 | Vanderbilt Graduate Housing | 2022-10-25 | Marvin blanco | we couldn't install anything because they don't have the swing stage ready for us | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 12 | false |  | swing stage | false |  |  |  |  | Other | [42 empty] | nothing to install they couldn't setup the swing stage | 60
21071 | Google NBY-HUB 1 | 2022-10-25 | Marvin blanco | installing base flashing and panels cleaning | Subcontractor | Steve Fudge | true | panels |  |  | good condition | 7 | 13 | true | base flashing | scissors lift and scaffolding | false |  |  |  |  | Flashing Plate |  |  | 20 | 84 | [28 empty] | 80 | 18
21075 | 900 Church AECOM | 2022-10-25 | Chad mccoy | We started our day cutting z and installing z and insulation and flashing. Kevin and starlin then started laying out and cutting corrugated for our install. I drew up the cut outs and kevin then laid it out and cut it. As we finished a bump in. We then trimmed it out with inside and outside corners. As the day continued we did general clean up and prepped material for it to be flown down tomorrow | Subcontractor | Denis Usatenko | true | The wind was horrible. It cause handing down material hard and it took 3 guys |  |  | Windy | 4 | 8 | false |  | Nothing | false |  |  | 2 |  | Corrugated / Screen wall Insulation Layout Subgirt Zee Trim | [22 empty] | 6 | 2 |  |  | 130 | 1 |  |  | 60 | 1 |  |  |  |  | 160 | 1.5
22012 | QTS ASH2 DC1 Lockridge | 2022-10-25 | Marvin blanco | waiting on material because they took to much time for delivery we didn't install anything we don't have nothing to install | Subcontractor | Josh McPherson | true | insulation clips for metal panels angles for screen wall |  |  | good condition | 6 | 12 | false |  | boomlift | false |  |  |  |  | Other | [42 empty] | nothing because my guys they don't have material to install | 72
22021 | VA-14 | 2022-10-25 | David placzkowski | installed zee metal on insulation on east wall | Subcontractor | Nick Akins | false |  |  |  |  | 3 | 10 | false |  | 86 ft | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 448 | 8 |  |  | 852 | 12
22022 | Szott M59 Jeep Dealership Renovation | 2022-10-25 | Marvin blanco | installing panels and remaking panels | Subcontractor | Drake De Tomasi | false |  |  |  |  | 2 | 14 | false |  | boomlift | false |  |  |  |  | ACM | 20 | 28
22053 | Fort Worth Carvana | 2022-10-25 | Marvin blanco | remaking panels | Subcontractor | Joe Hoyle | true | delay on the job site because they are not ready for us to install panels |  |  | good condition | 3 | 12 | false |  | boomlift | false |  |  |  |  | ACM | 4 | 36
20067 | BNA PROJECT 5 | 2022-10-24 | Naza | moving material up to the airwave roof east side top canopy CPR north | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  | 36' boom tow | false |  |  |  |  | ACM Flashing Other | 8 | 22 | [30 empty] | 20 | 2 | [8 empty] | carring material up to the roof | 6
21024 | Vanderbilt Graduate Housing | 2022-10-24 | Marvin blanco | checking out on panels because all the panels are bad no one work | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 12 | true | panels and insulation angles 3x3 | swing stage and boomlift | false |  |  |  |  | Hat Channel Insulation | [26 empty] | 144 | 3 | [6 empty] | 90 | 6
21046 | The Moore Building | 2022-10-24 | Naza | making 9/16 holes in each tube 14 pcs east elevation | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 50 | false |  | 80' boom | false |  |  |  |  | Other Tubing | [28 empty] | 140 | 20 | [12 empty] | 1/16 holes on 14 tubes | 30
22012 | QTS ASH2 DC1 Lockridge | 2022-10-24 | Marvin blanco | installing z's and delays on material | Subcontractor | Josh McPherson | true | metal panels installation angles clips for panels silicone |  |  | good condition | 6 | 12 | false |  | boomlift | false |  |  |  |  | Hat Channel | [34 empty] | 680 | 72
22021 | VA-14 | 2022-10-24 | David placzkowski | installing zee metal and insulation | Subcontractor | Nick Akins | false |  |  |  |  | 3 | 10 | false |  | 86ft Boom Lift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 1152 | 16 |  |  | 168 | 4
22022 | Szott M59 Jeep Dealership Renovation | 2022-10-24 | Marvin blanco | redoing a panels checking the layout and installing panels | Subcontractor | Drake De Tomasi | false |  |  |  |  | 2 | 12 | false |  | boomlift | false |  |  |  |  | ACM | 20 | 24
20067 | BNA PROJECT 5 | 2022-10-21 | Naza | the guys have to carry ACM panels to the roof | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  | 36' boom towable | false |  |  |  |  | ACM Other | 8 | 24 | [40 empty] | carring ACM panels up to the roof | 6
21008 | 900 Church | 2022-10-21 | Marvin blanco | installing panels and fixing panels remaking panels | Subcontractor | Dillon Bowman | false |  |  |  |  | 4 | 12 | false |  |  | false |  |  |  |  | Other | [42 empty] | remaking 12 panels and cleaning | 48
21024 | Vanderbilt Graduate Housing | 2022-10-21 | Marvin blanco | fixing stuff in the panels because they're not right | Subcontractor | Drake De Tomasi | false |  |  |  |  | 7 | 12 | false |  | swing stage and boomlift | false |  |  |  |  | ACM Hat Channel Insulation Plate | 4 | 2 | 11 | 5 | [22 empty] | 100 | 3 | [6 empty] | 180 | 2
21046 | The Moore Building | 2022-10-21 | Naza | this is the date 21 I had a confusion | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 50 | false |  | 80' boom | false |  |  |  |  | Other | [42 empty] | purlin's | 50
21046 | The Moore Building | 2022-10-21 | Naza | 2 guys at the shopcutting purlin's | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 10 | false |  | 120' and 80' boom | false |  |  |  |  | Other | [42 empty] | purlin's 215 pcs | 50
21071 | Google NBY-HUB 1 | 2022-10-21 | Marvin blanco | fixing stuff and remaking panels | Subcontractor | Steve Fudge | true | panels base flashing |  |  | good condition | 8 | 12 | false |  | boomlift | false |  |  |  |  | Other | [42 empty] | fixing panels and coping | 96
21075 | 900 Church AECOM | 2022-10-21 | Chad mccoy | We started our day getting all our tools to the roof. I cut out 8 holes for the electricians. While Kevin and starling got the new flashing to the roof. We then put plywood down and we set up the scaffolding so we could install the concrete covers. The big box cover has tap one in it but the L shape covers are only caulked on. Once those were shimmed up to dry. We started filling in screws and I caulked one pipe and the big concrete cover. I also laid out and cut 2 scuppers out of the panels that was installed | Subcontractor | Denis Usatenko | true | The roofers are not done with the bump in areas. We can’t set the base flashing and we had to stop on the z and insulation bc they were working in these areas. This is the second day |  |  | Clear | 3 | 8 | false |  | Nothing | false |  |  |  |  | Flashing | [32 empty] | 30 | 2
22012 | QTS ASH2 DC1 Lockridge | 2022-10-21 | Marvin blanco | waiting on material and installing z's | Subcontractor | Josh McPherson | true | delay on metal panels angles for screenwall silicone coping and jtrim |  |  | good condition | 6 | 12 | false |  | boomlift | false |  |  |  |  | Hat Channel | [34 empty] | 800 | 72
22022 | Szott M59 Jeep Dealership Renovation | 2022-10-21 | Marvin blanco | taking measurements and doing layout and installing boffus and waiting to the machine get fixed | Subcontractor | Drake De Tomasi | false |  |  |  |  | 2 | 12 | false |  | boomlift | false |  |  |  |  | Other | [42 empty] | boffus | 24
22053 | Fort Worth Carvana | 2022-10-21 | Marvin blanco | installing panels and remaking panels they make it too bad | Subcontractor | Joe Hoyle | false |  |  |  |  | 4 | 12 | false |  | boomlift | false |  |  |  |  | ACM Hat Channel | 12 | 10 | [32 empty] | 200 | 2
20067 | BNA PROJECT 5 | 2022-10-20 | Naza | day crew | Subcontractor | Marc Ribar | false |  |  |  |  | 7 |  | false |  | 2 30' towable booms | false |  |  |  |  | ACM Flashing Other | 20 | 48 | [30 empty] | 60 | 8 | [8 empty] | moving material to the roof | 14
21008 | 900 Church | 2022-10-20 | Marvin blanco | installing panels and remaking panels | Subcontractor | Dillon Bowman | false |  |  |  |  | 4 | 13 | false |  |  | false |  |  |  |  | ACM | 13 | 52
21046 | The Moore Building | 2022-10-20 | Naza | 3 guys cutting blades at the shop | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 50 | false |  | 80'& 120' boom | false |  |  |  |  | Other | [42 empty] | 60 blades and 3 guys cutting blades at the shop | 50
21071 | Google NBY-HUB 1 | 2022-10-20 | Marvin blanco | installing panels and waiting on the scaffolding | Subcontractor | Steve Fudge | true | panels |  |  | could | 8 | 12 | false |  | scissors | false |  |  |  |  | Plate |  |  | 20 | 96
21075 | 900 Church AECOM | 2022-10-20 | Chad mccoy | We started this morning laser lining a line for the drip flashing. The tpo and the insulation is crazy wavy but we set everything and then ran it. There are spots where the insulation and drip are sitting on each other. So after that we started running panels. We established our first panel and the the next 8 had penetrations in them. The penetrations went from 1 inch to 13 inch circumference. A couple panels needed to be cut completely in half due to the penetration being dead center in the panels. We finished that penetration wall on a cut down panel. We turned the corner and the next 9 had to be cut either on height or the door or bc of concrete. We trimmed out the door and added z and insulation to finish out the door way. We finished the big wall with a full sheet. | Subcontractor | Denis Usatenko | true | The roofers have not finished the top in the bump in sections. We have to wait to establish the corrugated metal bc of this. One side is there trash area storing area. the penetrations really slowed us down with the continued layout and multiple penetrations and more than one in one panel. |  |  | Clear/ cold | 4 | 12 | false |  | Nothing | false |  |  | 4 |  | Corrugated / Screen wall Insulation Layout Subgirt Zee Trim | [22 empty] | 21 | 4 |  |  | 100 | 0.5 |  |  | 20 | 0.5 |  |  |  |  | 140 | 3
22012 | QTS ASH2 DC1 Lockridge | 2022-10-20 | Marvin blanco | nothing to do because we don't have material to work I hope we can get something this week | Subcontractor | Josh McPherson | true | clips panels angles z's insulation |  |  | could | 8 | 12 | false |  | boomlift | false |  |  |  |  | Other | [42 empty] | nothing to install we don't have metal panels to install no jtrim no angles no z's | 96
22021 | VA-14 | 2022-10-20 | David placzkowski | Installed zee and insulation | Subcontractor | Nick Akins | false |  |  |  |  | 3 | 10 | false |  | 86ft boom lift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 576 | 6 |  |  | 696 | 10
22053 | Fort Worth Carvana | 2022-10-20 | Marvin blanco | installing panels and taking down some panels also because they haven't ready | Subcontractor | Joe Hoyle | false |  |  |  |  | 3 | 12 | false |  | boomlift | false |  |  |  |  | ACM | 9 | 36
20067 | BNA PROJECT 5 | 2022-10-19 | Naza | day crew | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 40 | false |  | 2 30' towables booms | false |  |  |  |  | ACM Other | 16 | 28 | [40 empty] | moving materiall to the roof | 12
21008 | 900 Church | 2022-10-19 | Marvin blanco | remaking panels because they make it too tall bigger remaking 12 panels | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 11 | false |  | nothing | false |  |  |  |  | ACM | 9 | 33
21046 | The Moore Building | 2022-10-19 | Naza | the plates had to be drilled new holes in the concrete and screw anchored into all the plates on top of floor 7 | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 50 | false |  | 80' & 120' boom | false |  |  |  |  | Other Plate Tubing |  |  | 5 | 10 | [24 empty] | 50 | 20 | [12 empty] | 60 blades | 20
21061 | ATT Building Facade Rehab | 2022-10-19 | Fredy Rodriguez | this day we did a safety talk and respect the work rules and inspection of our team | Subcontractor | Josh McPherson | false |  |  |  |  | 8 | 80 | false |  | Swing stage and forklift | false |  |  |  |  | ACM Other Tubing | 11 | 10 | [26 empty] | 4 | 2 | [12 empty] | 12 clips were installed | 3
22012 | QTS ASH2 DC1 Lockridge | 2022-10-19 | Marvin blanco | installing metal panels in the screenwall taking more time because they don't have the clips for the metal panels | Subcontractor | Josh McPherson | true | clips for metal panels |  |  | good condition | 6 | 12 | false |  | boomlift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 39 | 72
22021 | VA-14 | 2022-10-19 | David placzkowski | installed zee metal and insulation | Subcontractor | Nick Akins | false |  |  |  |  | 3 | 10 | true | caulk and screws | 86ft Ariel Boom lift | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 1152 | 14 |  |  | 168 | 6
22053 | Fort Worth Carvana | 2022-10-19 | Marvin blanco | installing acm panels and hats channels | Subcontractor | Joe Hoyle | false |  |  |  |  | 3 | 12 | false |  | boomlift | false |  |  |  |  | ACM | 9 | 36
20067 | BNA PROJECT 5 | 2022-10-18 | Naza | day crew | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  | 2 30' towable booms | false |  |  |  |  | ACM | 24 | 30
20067 | BNA PROJECT 5 | 2022-10-18 | Naza | day crew | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 40 | false |  | 86' b00m 32' scissor | false |  |  |  |  | IMP | [8 empty] | 32 | 40
21008 | 900 Church | 2022-10-18 | Marvin blanco | installing panels and remaking panels | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 11 | false |  |  | false |  |  |  |  | ACM | 8 | 11
21024 | Vanderbilt Graduate Housing | 2022-10-18 | Marvin blanco | installing panels at the bridge in the swing stage | Subcontractor | Drake De Tomasi | false |  |  |  |  | 3 | 11 | true | 12 panels for the bridge | boomlift and swing stage | false |  |  |  |  | ACM | 12 | 33
21046 | The Moore Building | 2022-10-18 | Naza | no delays | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 50 | false |  | 80' & 120' booms | false |  |  |  |  | Other Tubing | [28 empty] | 80 | 20 | [12 empty] | 10 clips plates, 80 blades | 30
21075 | 900 Church AECOM | 2022-10-18 | Chad mccoy | We started this morning, getting to the roof and finding that the roofers thru all there trash amongst our material. All of this needed to be moved and cleaned up prior to us being able to get to the z that was at the bottom of the crate. Once we got the z we started running the z. We left the bottom section off so the roofer could establish his elevation of the insulation and decking. As Keith and I completed a section of z and caulking the screws we then installed the insulation as well. Tomorrow when we fly up more z and the corrugated material we will fly down the crates that will be empty. We finished close to two big walls before running out of z 39 z’s had to be cut to fit in areas and limit the over lap | Subcontractor | Denis Usatenko | true | We had to clean the area of operation bc of the roofers. Prior to starting |  |  | Cold and windy | 4 | 8 | false |  | Nothing | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 920 | 3 |  |  | 72 | 4
22012 | QTS ASH2 DC1 Lockridge | 2022-10-18 | Marvin blanco | installing metal panels and doing scaffolding | Subcontractor | Josh McPherson | true | clips for metal panels |  |  | good condition | 6 | 12 | false |  | scaffolding and boomlift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 22 | 72
22021 | VA-14 | 2022-10-18 | David Placzkowski | Installed Zee metal and caulked the screw heads | Subcontractor | Nick Akins | false |  |  |  |  | 3 | 10 | false |  | 86ft Ariel Boom Lify | false |  |  |  |  | Subgirt Zee | [30 empty] | 864 | 20
22053 | Fort Worth Carvana | 2022-10-18 | Marvin blanco | installing panels flashing and hats channels | Subcontractor | Joe Hoyle | false |  |  |  |  | 3 | 12 | false |  | boomlift | false |  |  |  |  | ACM Flashing Hat Channel | 7 | 5 | [30 empty] | 90 | 4 | 100 | 3
20067 | BNA PROJECT 5 | 2022-10-17 | Naza | day crew | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  | 2 towable 32' boom | false |  |  |  |  | ACM | 16 | 30
20067 | BNA PROJECT 5 | 2022-10-17 | Naza | day crew | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 40 | false |  | 86' boom 32' scissor lift | false |  |  |  |  | Other | [42 empty] | 130' mending plate, 60' J starter, 20' starter flashing | 40
21008 | 900 Church | 2022-10-17 | Marvin blanco | installing ACM panels | Subcontractor | Dillon Bowman | true | reveals and angles A112 |  |  | good condition | 3 | 11 | false |  | nothing | false |  |  |  |  | ACM Insulation | 4 | 8 | [24 empty] | 70 | 3
21024 | Vanderbilt Graduate Housing | 2022-10-17 | Marvin blanco | installing angles insulation and panels | Subcontractor | Drake De Tomasi | true |  |  |  | good condition | 6 | 11 | true | panels and angles 3x3 | swing stage | false |  |  |  |  | ACM Hat Channel Insulation | 6 | 3 | [24 empty] | 70 | 3 | [6 empty] | 160 | 5
21046 | The Moore Building | 2022-10-17 | Nza | brick guys let us use they 60' boom | Subcontractor | Drake De Tomasi | false |  |  |  |  | 10 | 60 | false |  | 80' boom | false |  |  |  |  | Other Tubing | [28 empty] | 2100 | 60 | [12 empty] | 210 blades | 40
21071 | Google NBY-HUB 1 | 2022-10-17 | Marvin blanco | installing panels and flashing but we don't have any more white reveals and also base flashing for the canopies I hope we can get something tomorrow | Subcontractor | Steve Fudge | true | base flashing white reveals panels |  |  | could | 9 | 12 | false |  | scissors lift and boomlift | false |  |  |  |  | Flashing Plate |  |  | 20 | 80 | [28 empty] | 160 | 28
21075 | 900 Church AECOM | 2022-10-17 | Chad mccoy | We started our morning getting all the guys and heading to concentra. We all had to do drug teat for orientation at 900 church. Once that was done we went to try and find whistles. But we were running out of time so we called nick and Dennis and they brought the whistles. We headed to the job and went thru our orientation. Once that was finished we got radios from AE COM and we awaited arrival of nick and Dennis and the shipment. Once they all arrived kevin and I went to the roof and the rest stayed on the ground. We flew 2 skids of material and 3 skids of insulation. We are limited on the area of operation and lay down. There are 5 other trades working where we are working and around us. The starting elevation was a big topic of discussion. While we waited on the pm, we layered lined a level line around the area of install. And we moved around insulation for better area of operation, due to the limited walking room. AECOMS pm came to the roof and we talked about this area. A answer was decided and the roofer is going to cut back the area so our drip flashing will work. | Subcontractor | Denis Usatenko | true | The roofer is installing insulation all the way up against us, The walls are being repainted with water proofing, The left and right trim work is against the curtain walls are being worked on. |  |  | Clear/windy | 8 | 8 | true | Insulation, scaffolding, and flashing | Nothing | false |  |  | 0.5 |  | Layout
22012 | QTS ASH2 DC1 Lockridge | 2022-10-17 | Marvin blanco | installing metal panels in the screenwall taking much time because we don't have the clips for the panels and we have to be notching all the panels | Subcontractor | Josh McPherson | true | clips for the panels |  |  | good condition | 8 | 12 | false |  | boomlift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 30 | 96
22012 | QTS ASH2 DC1 Lockridge | 2022-10-17 | Marvin blanco Erwin hernandez | installing metal panels in the screenwall with out clips taking more time a lot of irresponsibility | Subcontractor | Josh McPherson | true | clips for metal panels |  |  | could | 6 | 12 | false |  | boomlift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 42 | 96
22021 | VA-14 | 2022-10-17 | David placzkowski | Unloaded the truck as soon as we started our shift. Then proceeded to get prepared to install zee metal. Spent the rest of the night installing said zee metal | Subcontractor | Nick Akins | false |  |  |  |  | 3 | 10 | true | Zee metal and insulation | 86ft Ariel boom ligt | false |  |  |  |  | Subgirt Zee | [30 empty] | 588 | 20
22053 | Fort Worth Carvana | 2022-10-17 | Marvin blanco | installing flashing and waiting for clips all weekend | Subcontractor | Joe Hoyle | true | clips and started clips |  |  | good condition | 3 | 12 | false |  | boomlift | false |  |  |  |  | Flashing Hat Channel | [32 empty] | 80 | 4 | 200 | 8
21071 | Google NBY-HUB 1 | 2022-10-16 | Marvin blanco | installing flashing and panels | Subcontractor | Steve Fudge | true | panels |  |  | good condition | 10 | 12 | false |  | scissors lift and boomlift | false |  |  |  |  | Flashing Plate |  |  | 20 | 60 | [28 empty] | 20 | 60
22012 | QTS ASH2 DC1 Lockridge | 2022-10-15 | Marvin blanco | installing metal panels with out clip taking more time to installing | Subcontractor | Josh McPherson | true | clips for metal panels |  |  | good condition | 8 | 12 | false |  | scaffolding and boomlift | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 45 | 96
22053 | Fort Worth Carvana | 2022-10-15 | Marvin blanco | we suppose to install panels but they clips for the panels never show up so we install a couple of flashing I hope tomorrow we will get the clips for ACM panels | Subcontractor | Joe Hoyle | true | clips for ACM panels 2 day delay |  |  | good condition | 3 | 12 | false |  | boomlift | false |  |  |  |  | Flashing | [32 empty] | 100 | 36
20067 | BNA PROJECT 5 | 2022-10-14 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 60 | false |  | 86' boom 32' csissor lift | false |  |  |  |  | ACM Flashing | 30 | 50 | [30 empty] | 40 | 10
21046 | The Moore Building | 2022-10-14 | Naza | no daleya | Subcontractor | Drake De Tomasi | false |  |  |  |  | 7 | 70 | false |  | 80' boom | false |  |  |  |  | Other | [42 empty] | 140 blades 15 clips | 70
20067 | BNA PROJECT 5 | 2022-10-13 | Naza | nigt crew | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 60 | false |  | 86' boom 32 csissor lift | false |  |  |  |  | ACM Flashing | 30 | 52 | [30 empty] | 30 | 8
21046 | The Moore Building | 2022-10-13 | Naza | no delays | Subcontractor | Drake De Tomasi | false |  |  |  |  | 7 | 70 | false |  | 80' boom | false |  |  |  |  | Other | [42 empty] | 80 blades 20 clips | 70
21071 | Google NBY-HUB 1 | 2022-10-13 | Marvin blanco | waiting on panels | Subcontractor | Steve Fudge | true | panels and base flashing |  |  | good condition | 10 | 12 | false |  | boomlift forklift | false |  |  |  |  | Other | [42 empty] | fixing stuff | 120
21071 | Google NBY-HUB 1 | 2022-10-13 | Marvin blanco | installing flashing because we don't have panels to install | Subcontractor | Steve Fudge | true | panels and reveals |  |  | could | 10 | 12 | false |  | 2 boomlift | false |  |  |  |  | Flashing | [32 empty] | 150 | 120
21071 | Google NBY-HUB 1 | 2022-10-13 |  | waiting for material | Subcontractor | Steve Fudge | false |  |  |  |  | 10 |  | false |  |  | false |  |  |  |  | ACM
22007 | Albion in the Gulch | 2022-10-13 | Chad mccoy | We started our day double checking the layout of the ceiling guys and laying out our top z to finish out our wall? We also had to add strapping to 4 sections of the wall bc the insulation was loose with the high winds. Kevin and starlin also finished bringing the insulation to level 4. The swing stage guy mike also came and we walked the areas of operation for swing stages | Subcontractor | Dillon Bowman | false |  |  |  |  | 4 | 7 | true |  | Scissor | false |  |  | 1 |  | Insulation Layout Subgirt Zee | [26 empty] | 160 | 1.5 |  |  | 80 | 1.5
22012 | QTS ASH2 DC1 Lockridge | 2022-10-13 | Marvin blanco | taking to much time installing metal panes because we don't have the clips | Subcontractor | Josh McPherson | true | clips for metal panels |  |  | raining 🌧 | 8 | 12 | true | acm panels | boomlift and forklift | false |  |  |  |  | Overly Roof Panel | [12 empty] | 50 | 96
20067 | BNA PROJECT 5 | 2022-10-12 | Naza | nigt crew | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 60 | false |  | 86' boon 32' csisor lift | false |  |  |  |  | ACM Flashing | 42 | 54 | [30 empty] | 30 | 6
21046 | The Moore Building | 2022-10-12 | Naza | delivery stop us for 1 1/2 hours at 19 south gate | Subcontractor | Drake De Tomasi | true | delivery stop us for 1 1/2 hours at 19 south gate |  |  | sunny | 6 | 60 | false |  | 80' boom | false |  |  |  |  | Other | [42 empty] | 90 blades | 60
22007 | Albion in the Gulch | 2022-10-12 | Chad mccoy | We started our day doing our tool box talk. And I had to do my sap. Then we grabbed our tools and went to level 4. We continued installing z and caulking the screws. Then we moved to installing insulation and the strapping to hold the insulation in. Prior to installing the strapping. Kevin used the double cuts and cut the strapping in half. They way we had twice as much. | Subcontractor | Dillon Bowman | true | The ceiling guys are in sure where there ceiling finishes. They are suppose to pop a line on both sides so we can stay 1/2 inch off there mark |  |  | Cloudy and windy | 4 | 8 | false |  | Scissor lift. | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 960 | 2 |  |  | 220 | 2
20067 | BNA PROJECT 5 | 2022-10-11 | Naza | nigt crew | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 60 | false |  | 86' boom 32' csissor lift | false |  |  |  |  | ACM Flashing | 34 | 52 | [30 empty] | 40 | 8
21046 | The Moore Building | 2022-10-11 | Naza | no delays | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 40 | false |  | 80' boom | false |  |  |  |  | Other | [42 empty] | 90 blades | 40
22007 | Albion in the Gulch | 2022-10-11 | Chad mccoy | We started our morning moving some material to the 4 floor. Nick and Dennis came today and I had a safe plan meeting with Clark. After that we continued moving material and laying out the level 4 area for install. Clark had to come and show us the layout they wanted off the slab of concrete bc the slab was out of level. Once that was established we started layout off a laser line so we could install the z. Clark also approved they method that we were caulking the z to the wall after it was screwed off. At the same time Roswell was laying out and installing the ceiling. We also moved insulation and z to level 4 The insulation was stacked and strapped down to keep it from blowing away. After work I went to mcdougal and tried to find something to lock in the insulation tomorrow. | Subcontractor | Dillon Bowman | true | Prior to starting. We had to find our scissor lift. Another trade was using it. We chained and locked everything together at the end of the day |  |  | Clear and windy | 4 | 8 | false |  | Scissor lift | false |  |  |  |  | Subgirt Zee | [30 empty] | 360 | 3
20067 | BNA PROJECT 5 | 2022-10-10 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 60 | false |  | 86' boom 32' csissor lift | false |  |  |  |  | ACM Flashing | 38 | 54 | [30 empty] | 20 | 6
21046 | The Moore Building | 2022-10-10 | Naza | no delays | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 40 | false |  | 80' | false |  |  |  |  | Other | [42 empty] | 115 blades | 40
22007 | Albion in the Gulch | 2022-10-10 | Chad mccoy | We started our day in orientation. Once orientation was over we prepped for the delivery. When the delivery arrived we unloaded and staged everything, so it could be taken to the upper lever. At 10 o’clock I had to be at 805 so we left and I wrapped up what was needed at 805. And then I dropped everybody off and headed to mcdougal to pick up carts and a chain and locks and screws | Subcontractor | Dillon Bowman | true | Orientation- and awaiting safe start intro |  |  | Clear | 4 | 5 | true | A pallet of z and insulation | Scissor lift was delivered today | false |  |  |  |  | ACM | 0 | 0
21071 | Google NBY-HUB 1 | 2022-10-08 | Marvin blanco | installing panels and cleaning. also we have problems with the reveals the pain not strong enough | Subcontractor | Steve Fudge | true | panels and reveals coping |  |  | could | 10 | 12 | false |  | scissors lift boomlift and a forklift | false |  |  |  |  | Plate |  |  | 20 | 120
22012 | QTS ASH2 DC1 Lockridge | 2022-10-08 | Marvin blanco | taking materials to the roof | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 12 | false |  | 2 boomlift and 1 forklift | false |  |  |  |  | Other | [42 empty] | taking materials to the roof | 72
20067 | BNA PROJECT 5 | 2022-10-07 | nAZA | DAY CREW | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 60 | false |  | 86' BOOM | false |  |  |  |  | Flashing IMP | [8 empty] | 9 | 18 | [22 empty] | 110 | 32
20067 | BNA PROJECT 5 | 2022-10-07 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 7 | 70 | false |  | 86' boom, 32' scissor lift | false |  |  |  |  | ACM Flashing | 70 | 52 | [30 empty] | 130 | 18
21046 | The Moore Building | 2022-10-07 | Naza | no delays | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 40 | false |  | 80' boom | false |  |  |  |  | Other | [42 empty] | 110 blades | 40
20067 | BNA PROJECT 5 | 2022-10-06 | Naza | day crew | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 50 | false |  | 86' boom | false |  |  |  |  | IMP | [8 empty] | 19 | 50
20067 | BNA PROJECT 5 | 2022-10-06 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 40 | false |  | 2 30' towable lifts | false |  |  |  |  | ACM Caulking | 11 | 26 | [18 empty] | 160 | 14
20067 | BNA PROJECT 5 | 2022-10-06 | Nza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 40 | false |  | 86' boom 32' scissor lift | false |  |  |  |  | ACM Flashing | 38 | 32 | [30 empty] | 40 | 8
21046 | The Moore Building | 2022-10-06 | Naza | no delays | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 50 | false |  | 80' boom | false |  |  |  |  | Other Subgirt Zee | [30 empty] | 200 | 20 | [10 empty] | blades 70 | 30
21061 | ATT Building Facade Rehab | 2022-10-06 | Fredy Rodriguez | I am sending you the photo of the south side we will have to cut the brick to put it even and install the clips | Subcontractor | Josh McPherson | false |  |  |  |  | 5 | 50 | false |  | Swing stage and forklift | false |  |  |  |  | Tubing | [28 empty] | 288 | 10
20067 | BNA PROJECT 5 | 2022-10-05 | Naza | day crew | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 40 | false |  |  | false |  |  |  |  | Flashing IMP Other | [8 empty] | 8 | 20 | [22 empty] | 40 | 8 | [8 empty] | 40' starter "J " 50' mending plate | 12
20067 | BNA PROJECT 5 | 2022-10-05 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 40 | false |  | 86' boom, 32' csissor lift | false |  |  |  |  | ACM Flashing | 33 | 32 | [30 empty] | 30 | 8
20067 | BNA PROJECT 5 | 2022-10-05 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 40 | false |  | 2 30' towable lifts | false |  |  |  |  | ACM Hat Channel | 10 | 28 | [32 empty] | 80 | 12
21046 | The Moore Building | 2022-10-05 | Naza | the guys doing Zee's they were installing on and off cuz the deliveries | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 40 | false |  | 80' and 120' booms | false |  |  |  |  | Other Subgirt Zee | [30 empty] | 180 | 20 | [10 empty] | 70 blades | 20
20067 | BNA PROJECT 5 | 2022-10-04 | Naza | day crew airwave | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 50 | false |  | 2 86' booms | false |  |  |  |  | Flashing Other | [32 empty] | 260 | 36 | [8 empty] | caps 26 | 14
21046 | The Moore Building | 2022-10-04 | Naza | hey stopped us from continuing to install blades and tubes from 7am to 9:30am because the crane was flying glass | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 10 | false |  | 80' and 120' booms | false |  |  |  |  | Other Subgirt Zee | [30 empty] | 300 | 30 | [10 empty] | 46 blades | 20
21061 | ATT Building Facade Rehab | 2022-10-04 | Fredy Rodriguez | work is being done in the southern area but there are special clips that I need to install can you send them as soon as possible so as not to have delays please | Subcontractor | Josh McPherson | false |  |  |  |  | 4 | 44 | false |  | Swing stage and forklift | false |  |  |  |  | Other Tubing | [28 empty] | 90 | 11 | [12 empty] | Clip | 11
21071 | Google NBY-HUB 1 | 2022-10-04 | Marvin blanco | delays on material trim and panels they are not responsible at all | Subcontractor | Steve Fudge | true | delays on everything |  |  | very good condition | 10 | 12 | false |  | 3 boomlift and 1 forklift | false |  |  |  |  | Other | [42 empty] | nothing installed because we don't have nothing of material I don't know how they want us to install panels with out material | 120
22012 | QTS ASH2 DC1 Lockridge | 2022-10-04 | Marvin blanco | delays on material and scaffolding waiting on the scaffolding because they said they're going to bring it today but nothing 😑 😒 | Subcontractor | Josh McPherson | true | metal panels and scaffolding |  |  | good condition | 7 | 12 | false |  | 2 boomlift and 1 forklift | false |  |  |  |  | Other | [42 empty] | waiting all day | 84
20067 | BNA PROJECT 5 | 2022-10-03 | Naza | day crew | Subcontractor | Marc Ribar | false |  |  |  |  | 9 | 10 | false |  | 2 86' booms | false |  |  |  |  | Flashing IMP Other Overly Roof Panel | [8 empty] | 21 | 30 |  |  | 22 | 30 | [18 empty] | 80 | 20 | [8 empty] | mending plates 45' | 10
21046 | The Moore Building | 2022-10-03 | Naza | they stopped us from continuing to install blades and tubes from 1pm to 3pm because the crane was flying glass and lowering garbage from the glaziers | Subcontractor | Drake De Tomasi | false |  |  |  |  | 6 | 10 | false |  | 80'boom | false |  |  |  |  | Other Tubing | [28 empty] | 130 | 20 | [12 empty] | 53 blades, 9 clips | 28
21071 | Google NBY-HUB 1 | 2022-10-03 | Marvin blanco | waiting on trim taking some panels out to the wall | Subcontractor | Steve Fudge | true | panels and trim |  |  | good condition | 9 | 12 | false |  | 3 boomlift and 1 forklift | false |  |  |  |  | Other | [42 empty] | nothing we don't have any revils trim | 12
22012 | QTS ASH2 DC1 Lockridge | 2022-10-03 | Marvin blanco | waiting on scaffolding but never arrived and we don't have anything for install | Subcontractor | Josh McPherson | true | metal panels and scaffolding |  |  | good condition | 8 | 12 | false |  | 2 boomlift and 1 forklift | false |  |  |  |  | Other | [42 empty] | nothing for install because the material it's delay | 96
20067 | BNA PROJECT 5 | 2022-09-30 | Naza | day crew | Subcontractor | Marc Ribar | false |  |  |  |  | 7 | 70 | false |  | 2 86' booms | false |  |  |  |  | Flashing IMP Other | [8 empty] | 30 | 40 | [22 empty] | 60 | 15 | [8 empty] | mending plates 80' | 15
20067 | BNA PROJECT 5 | 2022-09-30 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 50 | false |  |  | false |  |  |  |  | ACM | 10 | 50
21046 | The Moore Building | 2022-09-30 | Naza | 12 drilled tubes, 2 drills per hour 2 guys | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 10 | false |  | 80' boom | false |  |  | 14 |  | Layout Plate Tubing |  |  | 12 | 16 | [24 empty] | 120 | 20
20067 | BNA PROJECT 5 | 2022-09-29 | Naza | sunny day | Subcontractor | Marc Ribar | false |  |  |  |  | 7 | 70 | false |  | 2 86' b00ms | false |  |  |  |  | Flashing IMP Other | [8 empty] | 14 | 30 | [22 empty] | 200 | 20 | [8 empty] | mending plates 110' | 20
21046 | The Moore Building | 2022-09-29 | Naza | 2 drilled tubes per hour plus drill bits | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 50 | false |  | 80' boom | false |  |  | 8 |  | Layout Other Plate Tubing |  |  | 8 | 8 | [24 empty] | 80 | 14 | [12 empty] | blades 2 guys | 20
20067 | BNA PROJECT 5 | 2022-09-28 | Naza | no delays | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 10 | false |  | 2 86' booms | false |  |  |  |  | Other Overly Roof Panel | [12 empty] | 18 | 24 | [28 empty] | moving materiall by hand | 26
20067 | BNA PROJECT 5 | 2022-09-28 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 50 | false |  | 2 36' towable booms | false |  |  |  |  | ACM | 13 | 50
20067 | BNA PROJECT 5 | 2022-09-28 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 50 | false |  | 2 36' towable booms | false |  |  |  |  | ACM | 14 | 50
21046 | The Moore Building | 2022-09-28 | Naza | 2 drilled tubes per hour | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 50 | false |  | 80' boom | false |  |  | 8 |  | Layout Other Plate Tubing |  |  | 8 | 8 | [24 empty] | 80 | 14 | [12 empty] | blades 2 guys | 20
21071 | Google NBY-HUB 1 | 2022-09-28 | Marvin blanco | remanufacturing panels cleaning installing panels | Subcontractor | Steve Fudge | true | panels and trim |  |  | good condition | 15 | 12 | true | aluminum panels | 3 boomlift | false |  |  |  |  | Plate |  |  | 20 | 12
19028 | Kistler Rolled Panels | 2022-09-27 | Chad mccoy | We started today meeting with mr cheated about our plans for areas of work. Then Kevin went to the 31st floor with him and got the metal that already arrived. Kevin and I then started prepping the wall for installation of the new material. We had to remove all the 3 feet pieces and clean all the areas where the 3m tape was going. And we cut all the splice plates faces off. Once all this was done we started prepping the new material. There is two rows of matieral that needed to be cut down to 4 inches instead of 8 inches, like it was shipped. This is due to metal brackets holding the louvers in place. | Subcontractor | Chris Ball | false |  |  |  |  | 2 | 10 | false |  | 45 z boom | false |  |  |  |  | Flashing Trim | [32 empty] | 250 | 4 |  |  | 100 | 4
20067 | BNA PROJECT 5 | 2022-09-27 | Naz | no fdelays | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 10 | false |  | 2 86' booms | false |  |  |  |  | Overly Roof Panel | [12 empty] | 32 | 30
20067 | BNA PROJECT 5 | 2022-09-27 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 50 | false |  | 2 86's and 120' booms | false |  |  |  |  | ACM | 13 | 50
21046 | The Moore Building | 2022-09-27 | Naza | the guys on standby because the crane was flying material from 9am to 10:30am | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 50 | false |  | 80' | false |  |  | 6 |  | Layout Other Plate Tubing |  |  | 16 | 14 | [24 empty] | 40 | 10 | [12 empty] | blades 2 guys | 20
20067 | BNA PROJECT 5 | 2022-09-26 | Naza | day crew | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 10 | false |  | 2 86' booms | false |  |  |  |  | Flashing Overly Roof Panel | [12 empty] | 24 | 27 | [18 empty] | 30 | 3
20067 | BNA PROJECT 5 | 2022-09-26 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 50 | false |  | 2 86's and 120' boom | false |  |  |  |  | ACM | 11 | 50
21046 | The Moore Building | 2022-09-26 | Naza | moving materiall up to the levels, 2 guys 7 hrs driling holes plus $50 for drill bits | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 40 | false |  | 80' boom | false |  |  |  |  | Other Tubing | [28 empty] | 150 | 26 | [12 empty] | moving materiall (TUBES) and driling holes to tubes | 14
20067 | BNA PROJECT 5 | 2022-09-25 | Naza | day crew | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 10 | false |  | 2 86' booms | false |  |  |  |  | Flashing Overly Roof Panel | [12 empty] | 27 | 27 | [18 empty] | 30 | 3
21046 | The Moore Building | 2022-09-24 | Naza | south side 17 tubes installed, 2 guys 8 hrs drilling holes plus $50 for drill bits | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 32 | false |  | 80' boom | false |  |  |  |  | Tubing | [28 empty] | 170 | 40
20067 | BNA PROJECT 5 | 2022-09-23 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 7 | 70 | false |  | 2 86' and 120' boom lifts | false |  |  |  |  | ACM Flashing | 30 | 66 | [30 empty] | 20 | 4
21046 | The Moore Building | 2022-09-23 | Naza | leveling plates and instaling tubes, the tubes are being drilled with a hand drill to be installed 12 holes 2 guys x 6 hrs plus $50 of drill bits | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 40 | true | tubes | 80' boom | false |  |  | 12 |  | Layout Plate Tubing |  |  | 12 | 12 | [24 empty] | 120 | 16
21046 | The Moore Building | 2022-09-23 | naza | no delays | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 40 | true | tubes | 80' boom | false |  |  |  |  | Plate Tubing |  |  | 10 | 8 | [24 empty] | 120 | 32
20067 | BNA PROJECT 5 | 2022-09-22 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 10 | 100 | false |  | 2 86' and 120' boom lift | false |  |  |  |  | ACM Other | 61 | 75 | [40 empty] | stainless steel flashing | 25
21046 | The Moore Building | 2022-09-22 | naza | installing and leveling clip plates | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 40 | false |  | 80' boom | false |  |  |  |  | Plate |  |  | 40 | 40
21046 | The Moore Building | 2022-09-22 | naza | no delays | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 40 | false |  | 80' boom | false |  |  |  |  | Plate |  |  | 38 | 40
20067 | BNA PROJECT 5 | 2022-09-21 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 11 | 110 | false |  | 2 86' booms and 120' | false |  |  |  |  | ACM | 53 | 110
20067 | BNA PROJECT 5 | 2022-09-21 | Naza | back from night shift | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 60 | false |  | 2 86'booms 32' csissor lift | false |  |  |  |  | Flashing IMP Other | [8 empty] | 5 | 20 | [22 empty] | 60 | 10 | [8 empty] | 30' starter J, 30' mending plate' moving materiall | 30
21046 | The Moore Building | 2022-09-21 | naza | no delays | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 40 | false |  | 80' boom | false |  |  |  |  | ACM | 9 | 40
21071 | Google NBY-HUB 1 | 2022-09-21 | Marvin blanco | installing plate panels cleaning fixings panels | Subcontractor | Steve Fudge | false |  |  |  |  | 9 | 12 | false |  | 2 boomlift | false |  |  |  |  | Plate |  |  | 34 | 12
21007 | QTS Man 1 | 2022-09-20 | Keith Dukarm |  | JWMCD Crew | Josh McPherson | false |  |  |  |  | 2 | 5 | false |  | Boom lift | false |  |  |  |  | ACM | 2 | 5
21046 | The Moore Building | 2022-09-20 | Naza | no delays | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 40 | false |  | 80' boom | false |  |  |  |  | ACM Subgirt Zee | 10 | 26 | [28 empty] | 120 | 14
21071 | Google NBY-HUB 1 | 2022-09-20 | Marvin blanco | installing panels taking some measurements and fixing material cleaning | Subcontractor | Steve Fudge | false |  |  |  |  | 9 | 12 | true | panels | 2 boomlift | false |  |  | 2 |  | Flashing Layout Plate |  |  | 20 | 7 | [28 empty] | 10 | 3
21007 | QTS Man 1 | 2022-09-19 | Keith Dukarm | Took 10 down hung 8 2 has to come back down forgot vertical reveal | JWMCD Crew | Josh McPherson | false |  |  |  |  | 2 | 8.5 | false |  | Boom lift | false |  |  |  |  | ACM | 8 | 8.5
21046 | The Moore Building | 2022-09-19 | Naza | 80' of extra flashing | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 40 | true | tubes | 80' boom | false |  |  |  |  | Flashing Other | [32 empty] | 80 | 28 | [8 empty] | blades 82 pcs | 12
21046 | The Moore Building | 2022-09-16 | Naza | no delays | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 40 | false |  | 80' boom | false |  |  |  |  | ACM | 9 | 40
20067 | BNA PROJECT 5 | 2022-09-15 | Naza | night crew no delays | Subcontractor | Marc Ribar | false |  |  |  |  | 7 | 70 | false |  | 32' csissor 2 86' and 120' boom | false |  |  |  |  | ACM Flashing | 49 | 39 | [30 empty] | 50 | 10
21046 | The Moore Building | 2022-09-15 | Naza | no delays | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 40 | false |  | 8' boom | false |  |  |  |  | ACM | 8 | 40
21082 | UTMC MOB | 2022-09-15 | Chad mccoy | We started our morning picking up where we left off yesterday, Keith and Kevin removed five panels on the canopy. They then reinstalled the three new panels on the canopy and put it all back together. During this time I was caulking columns next to the smaller canopy. When Keith and Kevin got finished they moved to the one panel that we needed a Z boom for over the small canopy. It was removed and replaced and recaulked. Once all the panels have been replaced all three of us started caulking. I then pulled off of what I was doing and I made the little panels for the 2 1/8 inch void. I had to make three of these a soffit side face and a cap or a coping. Once this was finished we all spent the rest of the day caulking and cleaning up. | Subcontractor | Josh McPherson | false |  |  |  |  | 3 | 10 | false |  | Scissor lift. 60 z boom | false |  |  |  |  | ACM | 7 | 7
22012 | QTS ASH2 DC1 Lockridge | 2022-09-15 | Marvin blanco | installing jtrim | Subcontractor | Josh McPherson | true | metal panels |  |  | good condition | 6 | 12 | false |  | 2 boomlift | false |  |  |  |  | Trim | [36 empty] | 760 | 12
20067 | BNA PROJECT 5 | 2022-09-14 | Naza | no delays | Subcontractor | Marc Ribar | false |  |  |  |  | 7 | 70 | false |  | 32' csissor 2 86' and 120' boom | false |  |  |  |  | ACM Flashing | 58 | 60 | [30 empty] | 60 | 10
21046 | The Moore Building | 2022-09-14 | Naza | crew started late due to a traffic incident | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 40 | false |  | 80' | false |  |  |  |  | ACM | 8 | 48
21061 | ATT Building Facade Rehab | 2022-09-14 | Fredy Rodriguez | for the south side you can call so that the scaffolding can be further modified to be able to work on the installation of the tubes and panels | Subcontractor | Josh McPherson | false |  |  |  |  | 8 | 88 | true | insulation and screws and gunpowder and nails | Swing stage and forklift | false |  |  |  |  | ACM Insulation | 12 | 5 | [24 empty] | 900 | 3
21071 | Google NBY-HUB 1 | 2022-09-14 | Marvin blanco | installing panels and base flashing and star clip | Subcontractor | Steve Fudge | true | plate panels |  |  | good condition | 6 | 10 | false |  | 2 boomlift | false |  |  |  |  | Flashing Plate |  |  | 15 | 8 | [28 empty] | 13 | 2
21082 | UTMC MOB | 2022-09-14 | Chad mccoy | We started this morning continuing on the barrel removing Panels and putting the new ones back in. The one panel on the barrel we removed it and the coping above it. and when weRemoved the dented panel and then we tried to put the new panel into its place the new panel did not match the clip layout and it was not in the same radius as the rest of the panels on the rotunda. This calls us to try and install this panel at least 3 times before getting the shape of the panel where it was supposed to be. Without any damage. We then replace the coping that was above it and then we went and got the new coping that was in the crate but it had imperfections in it and it was too long. See delays. Once the panels were installed Chris the GC wanted me to look at the endcap on the right hand side of the rotunda so me and Keith went up and adjusted some pieces on it and then we started peeling the panels. See delays. Once the panels were peeled Keith move the scissor lift to the furthest side away from the rotunda of the big canopy so that he could start prepping the 3 panels for removal tomorrow when the boom lift arrives. At the end of the day today we also had to remove the trailer and everything that we had on site out into the parking lot due to ground work gonna be starting in the islands of the Drive area around the building | Subcontractor | Josh McPherson | true | The new panels that we are replacing the old panels with are just as dark as the panels that we are removing. The panels that simply had dance in them that were the right shade of anodized aluminum, Are now a dark shade because they were replaced with the new ACM. Two of the columns after we peeled it had wrinkles behind the pill like Josh saw in the shop. And the new coping cap also had wrinkles in it plus it was completely taped from end to end with brown tape this took a little while to remove. The new panels on the rotunda also have the same punctures in it that was on the previous rolled Panels pictures were taken and sent to Josh. |  |  | Cloudy 78 | 3 | 8 | false |  | Scissor lift | false |  |  |  |  | ACM | 4 | 4
22012 | QTS ASH2 DC1 Lockridge | 2022-09-14 | Marvin blanco | installing z's and jtrim | Subcontractor | Josh McPherson | true | metal panels |  |  | good condition | 6 | 12 | false |  | 2 boomlift | false |  |  |  |  | Flashing Hat Channel | [32 empty] | 60 | 2 | 820 | 10
20067 | BNA PROJECT 5 | 2022-09-13 | Naza | HP did not allow us to install ACM panels on the airwave because the waterproofing was not done well | Subcontractor | Marc Ribar | false |  |  |  |  | 7 | 70 | false |  | 86' 120' boom lifts | false |  |  |  |  | ACM Flashing IMP Other | 47 | 60 | [6 empty] | 1 | 2 | [22 empty] | 10 | 2 | [8 empty] | 10' of stater J, 40' of stainless steel flashing | 6
21046 | The Moore Building | 2022-09-13 | Naza | no delays | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 40 | false |  |  | false |  |  |  |  | ACM Other | 13 | 32 | [40 empty] | router was made to 4 panels of the first row | 8
21071 | Google NBY-HUB 1 | 2022-09-13 | Marvin blanco | installing panels flashing and star clips | Subcontractor | Steve Fudge | true | panels and flashing |  |  | good condition | 6 | 11 | false |  | 2 boomlift | false |  |  |  |  | Flashing Plate |  |  | 18 | 8 | [28 empty] | 240 | 3
21082 | UTMC MOB | 2022-09-13 | Chad mccoy | We started our day picking up from where we left off yesterday. Keith and Kevin installed two column panels to finish out three of the columns. I continue trying to makeThe window flashing work but no matter what idea there’s still a gap between the edge of window in the curve section of the ACM. So I stopped doing that and then we all started removing soffit panels. Once a soffit panels were removed we started reinstalling the soffit panels. Once the soffit panels were reinstalled I went and started removing the one column panel that was in between the column and the lower canopy. Keith and Kevin started on the barrel removing the two darker panels and the one dark coping. They reinstalled one of the panels and then I needed them to help me install my column panel that I had to cut and modify to go around the I-beam and the pipe. While they were on the ground we went ahead and we removed and replace the last lower canopy panel so that the lower canopy will only need to be caulked and peeled to be finished | Subcontractor | Josh McPherson | true | 10 panels had to be cut out and removed so that we could reinstall the new panels. There are a lot more stress cracks or lines in each Panels And each day it seems to look a little worse |  |  | Clear /78 | 3 | 10 | false |  | Scissor lift | false |  |  |  |  | ACM | 10 | 10
22012 | QTS ASH2 DC1 Lockridge | 2022-09-13 | Marvin blanco | we fall behind because we don't have ladders to do the work and we don't have to go looking for borrowed scaffolding either | Subcontractor | Josh McPherson | true | metal panels |  |  | good condition | 6 | 13 | false |  | boomlift | false |  |  |  |  | Hat Channel | [34 empty] | 164 | 13
20067 | BNA PROJECT 5 | 2022-09-12 | Naza | today I had to put all the crews on the night shift because the north side areas the frame didn't match the IMP joints HP has to give us a solution before we can install any panel and the mezz waterproofing have incomplete areas | Subcontractor | Marc Ribar | false |  |  |  |  | 12 |  | false |  | 2 36' towable, 86' and 120' | false |  |  |  |  | ACM Flashing | 94 | 105 | [30 empty] | 90 | 15
21046 | The Moore Building | 2022-09-12 | Naza | 4 panels were routered in the first row | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 40 | false |  | 80' boom | false |  |  |  |  | ACM Flashing | 8 | 34 | [30 empty] | 50 | 6
21046 | The Moore Building | 2022-09-12 | Naza | welders delayed us by an hour at north side elevation installing ACM panels | Subcontractor | Drake De Tomasi | true | welders delayed us by an hour 1pm to 2pm at north side elevation installing ACM panels |  |  | sunny | 4 | 40 | false |  | 80' boom | false |  |  |  |  | ACM Flashing Subgirt Zee | 8 | 20 | [28 empty] | 220 | 16 | 40 | 4
21061 | ATT Building Facade Rehab | 2022-09-12 | Fredy Rodriguez | this day we work 4 people in 2 swing stage and 3 on the ground and 1 person on the roof | Subcontractor | Josh McPherson | false |  |  |  |  | 8 | 88 | true | O3 acm panel | Swing stage and forklift | false |  |  |  |  | ACM | 20 | 4
21071 | Google NBY-HUB 1 | 2022-09-12 | Marvin blanco | installing panels and star clips and flashing cutting z's | Subcontractor | Steve Fudge | true | aluminum panels flashing and trims |  |  | good condition | 6 | 10 | false |  | 2 boomlift and 1 forklift | false |  |  |  |  | Plate |  |  | 19 | 10
21082 | UTMC MOB | 2022-09-12 | Chad mccoy | This morning Kevin and I met at Mcdougal and we loaded up the trailer with the crates of Panels and we headed to UTMC. Once we got the TMC I got with the GC and let him know that we were on site with the Panels from Mcdougal. Keith started cutting out caulking at columns and removing columns that had panels damaged or missed colors. Keith removed seven columns and reinstalled five today. I removed all of the bottom flashing pieces on the bottom of the panels and then clean the caulking off so that the flashing could go on. The builds on the flashing made the inside dimension of the flashings close to 3 7/8 so I removed all the caulking that I could on the build and got it up to 4 1/16. This still does not give me the dimensions on the inside that I needed to go underneath the window of 4 1/2 inside dimension. During the middle of all this the GC pointed out that every panel on the rotunda had lines or cracks up at some more worse than others. | Subcontractor | Josh McPherson | true | The flashing did not work so we are redoing the installation idea and I’m trying to get as much out of the inside dimension as I can |  |  | Clear/80 | 3 | 5..5 | true | 3 crates | Scissor lift | false |  |  |  |  | ACM | 5 | 5
22012 | QTS ASH2 DC1 Lockridge | 2022-09-12 | Marvin blanco | installing z's and angles in the screenwall | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 8 | false |  | 2 boomlift | false |  |  |  |  | Hat Channel | [34 empty] | 600 | 8
22012 | QTS ASH2 DC1 Lockridge | 2022-09-10 | Marvin blanco | installing z's and angles in the screenwall | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 12 | false |  | 2 boomlift | false |  |  |  |  | Hat Channel | [34 empty] | 930 | 12
20067 | BNA PROJECT 5 | 2022-09-09 | Naza | night crew road canopy | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 50 | false |  | 86' boom lift | false |  |  |  |  | ACM Flashing | 32 | 40 | [30 empty] | 80 | 10
20067 | BNA PROJECT 5 | 2022-09-09 | Naza | night crew airwave | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 50 | false |  | 2 36' boom towable | false |  |  |  |  | ACM Other | 10 | 30 | [40 empty] | caulking, taking film off and moving material from yard to garage B level 5 | 20
21046 | The Moore Building | 2022-09-09 | Naza | $80 for parking to set boom lift at parking lot | Subcontractor | Drake De Tomasi | false |  |  |  |  | 3 | 30 | false |  | 80' boom | false |  |  |  |  | Subgirt Zee | [30 empty] | 540 | 30
21071 | Google NBY-HUB 1 | 2022-09-09 | Marvin blanco | installing base flashing and clean up | Subcontractor | Steve Fudge | true | aluminum panels |  |  | good condition | 6 | 10 | false |  | 2 boomlift | false |  |  |  |  | Flashing | [32 empty] | 350 | 10
22012 | QTS ASH2 DC1 Lockridge | 2022-09-09 | Marvin blanco | installing z's and angles | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 12 | false |  | ladders 🪜 boomlift | false |  |  |  |  | Hat Channel | [34 empty] | 208 | 12
20067 | BNA PROJECT 5 | 2022-09-08 | naza | no delays | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 60 | false |  | 2 86' and 120' boom | false |  |  |  |  | Flashing IMP Other | [8 empty] | 1 | 4 | [22 empty] | 50 | 16 | [8 empty] | J starter for {MP panels 50' 4 panel colums | 40
21046 | The Moore Building | 2022-09-08 | Naza | $80 for parking to set boom lift at parking lot | Subcontractor | Drake De Tomasi | false |  |  |  |  | 3 | 30 | false |  | 80' | false |  |  |  |  | Subgirt Zee | [30 empty] | 570 | 30
21071 | Google NBY-HUB 1 | 2022-09-08 | Marvin blanco | installing flashing around the windows and cleaning | Subcontractor | Steve Fudge | true | aluminum panels |  |  | good condition | 6 | 10 | true | base flashing | 2 boomlift | false |  |  |  |  | Flashing | [32 empty] | 168 | 10
22012 | QTS ASH2 DC1 Lockridge | 2022-09-08 | Marvin blanco | installing z's and angles in the screenwall with ladders 🪜 | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 12 | false |  | 2 boomlift | false |  |  |  |  | Hat Channel | [34 empty] | 112 | 12
20067 | BNA PROJECT 5 | 2022-09-07 | naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 50 | false |  | 2 36' boom towable | false |  |  |  |  | ACM Flashing Other | 13 | 34 | [30 empty] | 30 | 8 | [8 empty] | moving materiall | 12
20067 | BNA PROJECT 5 | 2022-09-07 | Naza | sunny day | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 40 | true | colom covers | 2 86' and 120' booms | false |  |  |  |  | Flashing Other | [32 empty] | 140 | 20 | [8 empty] | muving material and take it to the roof (IMP) | 20
21046 | The Moore Building | 2022-09-07 | Naza | non-area to be able to seat the boom lift | Subcontractor | Drake De Tomasi | true | non-area to be able to seat the boom lift |  |  | sunny | 3 | 30 | false |  | 80' boom | false |  |  |  |  | Other Subgirt Zee | [30 empty] | 180 | 15 | [10 empty] | blades | 15
21061 | ATT Building Facade Rehab | 2022-09-07 | Fredy Rodríguez | Two damaged panels found. Fabricated two panels to installed around louvers. Send list of materials needed for 9/9/2022, see attached material list for additional details. | Subcontractor | Josh McPherson | false |  |  |  |  | 8 | 88 | false |  | Fork Lift and Swing Stages. | false |  |  |  |  | ACM Insulation | 7 | 55 | [24 empty] | 1140 | 33
20067 | BNA PROJECT 5 | 2022-09-06 | Naza | taking a boom lift to the 5th floor of garage B | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 50 | false |  | 2 36' boom towable | false |  |  |  |  | ACM Other | 12 | 38 | [40 empty] | taking a boom lift to the 5th floor of garage B | 12
21046 | The Moore Building | 2022-09-06 | Naza | delays to use the boom lift | Subcontractor | Drake De Tomasi | true | delays to use the boom lift, asphalt workers were working on the area we needed to lay our boom |  |  | foggy | 5 | 50 | false |  | 40' swingstage and 80' boom lift | false |  |  |  |  | Hat Channel Other Subgirt Zee | [30 empty] | 60 | 6 |  |  | 80 | 12 | [6 empty] | cutting blades at the shop, installing blades. | 32
21071 | Google NBY-HUB 1 | 2022-09-06 | Marvin blanco | installing flashing around the windows | Subcontractor | Steve Fudge | true | aluminum panels and flashing |  |  | good condition | 6 | 10 | false |  | 2 boomlift and forklift | false |  |  |  |  | Flashing | [32 empty] | 220 | 10
22012 | QTS ASH2 DC1 Lockridge | 2022-09-06 | Marvin blanco | installing z's and jtrim at the screenwall | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 12 | false |  | 2 boomlift | false |  |  |  |  | Flashing | [32 empty] | 620 | 12
22045 | Target Center Repair | 2022-09-03 | Chad mccoy | We started our day sectioning off the area where we needed to work. Today had a noise ordinance so we couldn’t start till eight. Keith and I were on the high section of the panels over the garage door and right next to the bridge that attaches to the target center. With this section you have to go from the bottom up if you try to go from the top down the boom at that extension likes to drop a foot and a half to 2 feet so you have to go up the wall and then retract back down and then start again once your repositioned. This took a while we have a little bit left to go we will finish it Monday. I was able to position the boom lift where one person in the 500 pound setting can’t go almost all the way to the camera like I wanted to in the beginning. I cannot go around the corner that’ll have to be a new setting on the boom on Monday but we’ll get it taken care of | Subcontractor | Nick Akins | true | There was a section of panels on the tire section that was completely disengaged you couldn’t tell until you got up there so we had to reset and re-engage close to seven Panels |  |  | Clear/77 | 3 | 6 | false |  |  | false |  |  |  |  | Other | [42 empty] | Rivets and washers and screws and washers | 6
20067 | BNA PROJECT 5 | 2022-09-02 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 40 | false |  | 2 86' and 120' | false |  |  |  |  | ACM | 12 | 40
20067 | BNA PROJECT 5 | 2022-09-01 | Naza | night crew They could only take a lift to the 5th floor of garage B, HP did not allow them to take the second | Subcontractor | Marc Ribar | true | night crew They could only take a lift to the 5th floor of garage B, HP did not allow them to take the second |  |  | night time | 4 | 40 | false |  | 2 32' lifts | false |  |  |  |  | ACM Other | 8 | 28 | [40 empty] | taking lift up to garage B level 5 | 12
22045 | Target Center Repair | 2022-09-01 | Chad mccoy | Keith and Kevin started their day on the high roof of the slant wall installing rivets and washers as high as they can reach and then they move to the scaffolding and then they move to the extension ladder doing the same thing. Eyes started on the furthest part of the slant wall away from the bridge and then went up the tall wall then came down and went around and finished the entire slant wall and then I started up on the big wall next to the slant ball and the bridges. When Keith and Kevin were done Kevin came off the roof and he started cleaning the ground Keith jumped in the basket with me and Keith and I started with Tall ball over the loading dock next to the sky bridge | Subcontractor | Nick Akins | false |  |  |  |  | 3 | 8 | false |  | 135 boon | false |  |  |  |  | Other | [42 empty] | Rivets and washers were installed | 8
20067 | BNA PROJECT 5 | 2022-08-31 | Naza | night crew could only use the 120' boom, HP did not allow us to take the 2 lifts to the garage | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 40 | false |  | 2 86' and 120' | false |  |  |  |  | ACM | 15 | 40
20067 | BNA PROJECT 5 | 2022-08-31 | Naza | day crew | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 40 | false |  | 2 86' boom lifts and 120' | false |  |  |  |  | Flashing Other | [32 empty] | 60 | 18 | [8 empty] | layout and control lines from west side over to north side | 22
22045 | Target Center Repair | 2022-08-31 | Chad mccoy | I started today working on the slant wall and then finishing the side where I had to move, due to the lack of signs. Then I started riveting on the tall wall. Keith and Kevin finished the flashing and then cleaned up and came around to where I was. I set them up on the roof and the started riveting on the upper roof of the slant wall. I also took the GC up to see the progress and my method of installation on the rivets and washers. | Subcontractor | Nick Akins | false |  |  |  |  | 3 | 8 | false |  | 135 boom | false |  |  |  |  | Other | [42 empty] | Reworked flashing and install a lot of screws and rivets | 8
20067 | BNA PROJECT 5 | 2022-08-30 | Naza | 4 guys muving material | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 40 | false |  | 2 86' and 120' booms | false |  |  |  |  | Other | [42 empty] | moving materials up to north side stainless steel,manding plates,plywood,scaffold | 40
22045 | Target Center Repair | 2022-08-30 | Chad mccoy | Pics | Subcontractor | Nick Akins | false |  |  |  |  | 3 |  | false |  |  | false |  |  |  |  | Flashing | [32 empty] | 10 | 8
22045 | Target Center Repair | 2022-08-30 | Chad mccoy | We started our morning setting up the scaffolding and waiting on the boom. Once the boom arrived I started on the slant wall. Each seam on the slant wall gets rivets and washers. I’m removing all the Phillip screws, to allow for movement on the panels . Keith is working on the trim on the other side. He is removing and modifying the trim to have a 1/4 gap in between flashings with a bottom lap that still gives the appearance of a continuous piece | Subcontractor | Nick Akins | true | I had a walk with everybody and they pointed out everything that they saw and there was a lot of stuff pointed out that was not on the original walk with me and Nick. So I told him that I am not doing anything until Nick tells me to do that |  |  | Clear | 3 | 8 | false |  | 135 boom | false |  |  |  |  | Flashing | [32 empty] | 10 | 8
20067 | BNA PROJECT 5 | 2022-08-29 | Naza | day crew preparing material for north side elevations | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  | 2 86' and 120' booms | false |  |  |  |  | Other | [42 empty] | IMP and flashing | 30
20067 | BNA PROJECT 5 | 2022-08-25 | Naza | cutting pavers for Mcdougall day crew | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  | 2 86' and 120' booms | false |  |  |  |  | Other | [42 empty] | pavers | 10
20067 | BNA PROJECT 5 | 2022-08-25 | Naza | night crew | Subcontractor | Marc Ribar | true | we had to wait for the waterproofing workers |  |  |  | 6 | 60 | false |  | 2 86' and 120' booms | false |  |  |  |  | ACM Flashing Other | 9 | 18 | [30 empty] | 40 | 12 | [8 empty] | columns frame 80' | 30
21007 | QTS Man 1 | 2022-08-25 | Keith Dukarm |  | JWMCD Crew | Josh McPherson | false |  |  |  |  | 2 | 5 | false |  | Boom lift | false |  |  |  |  | ACM | 3 | 5
20067 | BNA PROJECT 5 | 2022-08-24 | Naza | day crew removing terracotta and IMP panels north | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  | 2 86' and 120' booms | false |  |  |  |  | Other | [42 empty] | removing terracotta and IMP panels and moving material | 30
20067 | BNA PROJECT 5 | 2022-08-24 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 60 | false |  | 2 86 booms and 120' | false |  |  |  |  | ACM Other | 19 | 19 | [40 empty] | colums frame 70' LF, stainless still flashing 20' | 30
21007 | QTS Man 1 | 2022-08-24 | Keith Dukarm | Didn't have time to take pics left at 3 to go get caulk but got 5 panels on got 3 left ..and caulk ...reveals didn't get there till 11 .. | JWMCD Crew | Josh McPherson | true | Reveals |  |  | Hot | 2 | 8 | true | Reveals | Boom lift | false |  |  |  |  | ACM | 5 | 8
20067 | BNA PROJECT 5 | 2022-08-23 | Naza | removing terracotta and IMP panels day crew | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  | 2 86' and 120' booms | false |  |  |  |  | Other | [42 empty] | removing terracotta and IMP panels and changing head screws for flat head in the airwave | 30
20067 | BNA PROJECT 5 | 2022-08-23 | Naza | night crew | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 60 | false |  | 2 86' booms and 120' | false |  |  |  |  | ACM Other | 25 | 30 | [40 empty] | stainless steel at south canopy 30', and columns frame 110' LF | 30
21007 | QTS Man 1 | 2022-08-23 | Keith Dukarm | Yesterday and today's daily...10 total panels in 2 days today also peeled back of stairs and caulked a few things | JWMCD Crew | Josh McPherson | true | Short on reveals |  |  | Hot | 2 | 8 | false |  | Boom lift | false |  |  |  |  | ACM | 10 | 16
21060 | Vantage VA 13 | 2022-08-23 | Nathan Wall | 31 pcs. corrugated south gen. moved. coping to roof | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 10 | false |  | 2 80' booms | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 31 | 80
1658 | #NO MATCH | 2022-08-22 | Chad mccoy | I started laying out the plates in numeric order. But a lot of them didn’t go in that order. So I had to Lego it in to the right place. I placed 64 plates and bolted them down. 40 of them have the 3/8 screws installed in them. The extra material added under the plates are causing a issue with the holes lining up. After work I picked up the drill attachments and pry bar to help install the plates tomorrow used the sealant provided, | Subcontractor | Rod Grove | false |  |  |  |  | 1 | 9 | false |  | Nothing | false |  |  |  |  | Plate |  |  | 64 | 9
21060 | Vantage VA 13 | 2022-08-22 | Nathan Wall | installed 16 pcs. corrugated on south gen. 21 pcs. corrugated on north west gen. | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 10 | false |  | 2 80' boom lifts | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 37 | 80
21062 | BNA MNAA Garage B | 2022-08-22 | Naza | the panel #1 It gave them a lot of trouble to install the frame was off level and they had to make new holes | Subcontractor | Marc Ribar | true | the guys couldn't start work until 9am, concrete workers were cleaning the concrete pump in the area where we needed to work |  |  | sunny | 3 | 30 | false |  | 60' boom | false |  |  |  |  | Other | [42 empty] | flat perforated panels | 30
21071 | Google NBY-HUB 1 | 2022-08-22 | Marvin blanco | looking for material and installing flashing installing trim | Subcontractor | Steve Fudge | true | aluminum panels |  |  | good condition | 6 | 10 | true | 2 crates of panels | 2 boomlift | false |  |  |  |  | Flashing | [32 empty] | 56 | 10
21060 | Vantage VA 13 | 2022-08-21 | Nathan Wall | installed 18 pcs. corrugated on the south gen. | Subcontractor | Steve Fudge | false |  |  |  |  | 5 | 8 | false |  | 2 80' boom lifts | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 18 | 40
21060 | Vantage VA 13 | 2022-08-20 | Nathan Wall | installed 15 corrugated pcs. on south gen. | Subcontractor | Steve Fudge | false |  |  |  |  | 5 | 8 | false |  | 2 80' boom lifts | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 15 | 40
21071 | Google NBY-HUB 1 | 2022-08-20 | Marvin blanco | installing gnight wall and moving material | Subcontractor | Steve Fudge | true | aluminum panels |  |  | good condition | 6 | 8 | false |  | 2 boomlift | false |  |  |  |  | Hat Channel | [34 empty] | 1000 | 8
21060 | Vantage VA 13 | 2022-08-19 | Nathan Wall | installed 36 pcs. corrugated on the south gen. | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 10 | false |  | 2 80' boom lifts | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 36 | 80
21071 | Google NBY-HUB 1 | 2022-08-19 | Marvin blanco | waiting for material supposedly they were going to take it Thursday and nothing only insulation they brought us in the afternoon we went to bring the night walls because they took it to another place that was not | Subcontractor | Steve Fudge | true | aluminum plate panels and flashing |  |  | good condition | 6 | 10 | true | insulation | 2 boomlift | false |  |  |  |  | Other | [42 empty] | nothing we don't have the material | 8
21007 | QTS Man 1 | 2022-08-18 | Keith Dukarm | Started hanging back of stairs very difficult... | JWMCD Crew | Josh McPherson | false |  |  |  |  | 2 | 8 | false |  | Boom lift | false |  |  |  |  | ACM | 10 | 8
21024 | Vanderbilt Graduate Housing | 2022-08-18 | Marvin blanco | installing insulation and aluminum plate panels | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 10 | false |  | swing stage | false |  |  |  |  | Insulation Plate |  |  | 12 | 7 | [22 empty] | 240 | 4
21060 | Vantage VA 13 | 2022-08-18 | Nathan Wall | installed 16 pcs. northwest gen. 15 pcs. corrugated south gen. | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 10 | false |  | 2 80' boom lifts | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 31 | 80
21071 | Google NBY-HUB 1 | 2022-08-18 | Marvin blanco | driving yo the job site 5 horas and taking a delivery that we suppose to receive but it's not what we need. and waiting for 4 hours. | Subcontractor | Steve Fudge | true | aluminum panels reveal trims flashing and night wall |  |  | perfect condition | 6 | 10 | true | insulation, screws and silicone | 2 boomlift | false |  |  |  |  | Other | [42 empty] | nothing we don't have the material for install | 5
20067 | BNA PROJECT 5 | 2022-08-17 | Naza | night crew 3 guys south road canopy | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  | 2 booms 86' and 120' | false |  |  |  |  | ACM | 13 | 30
21007 | QTS Man 1 | 2022-08-17 | Keith Dukarm | Nothing much today | JWMCD Crew | Josh McPherson | false |  |  |  |  | 2 | 8 | false |  | Boom lift | false |  |  |  |  | ACM | 19 | 8
21024 | Vanderbilt Graduate Housing | 2022-08-17 | Marvin blanco | getting the delivery at 11:30 am and starting working at 1 pm | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 10 | true | plate panels, insulation, angles and screws | swing stage | false |  |  |  |  | Hat Channel | [34 empty] | 144 | 4
21060 | Vantage VA 13 | 2022-08-17 | Nathan Wall | installed 26 ACM panels on Blade Wall. 21 pcs. corrugated south gen. peel Poloymask loading dock | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 10 | false |  | 2 80' boom lifts | false |  |  |  |  | ACM Corrugated / Screen wall | 26 | 40 | [20 empty] | 21 | 40
20067 | BNA PROJECT 5 | 2022-08-16 | Naza | the day crew was moved to do night work inside sector 14, Utopia did us a favor by letting us use the spider lift | Subcontractor | Marc Ribar | true | the spider lift broke down at 11:30pm |  |  |  | 3 | 30 | false |  | 70' spider 2 booms 86' and 120' | false |  |  |  |  | ACM | 4 | 30
21007 | QTS Man 1 | 2022-08-16 | Keith Dukarm |  | JWMCD Crew | Josh McPherson | true | Modify panels |  |  | Hot | 2 | 8 | false |  | Boom lift | false |  |  |  |  | ACM | 15 | 8
21060 | Vantage VA 13 | 2022-08-16 | Nathan Wall | installed 10 ACM panels Blade Wall. peeled poloy | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 10 | false |  | 2 80' boom lifts | false |  |  |  |  | ACM | 10 | 80
21061 | ATT Building Facade Rehab | 2022-08-16 | Fredy Rodriguez | this day I received material and from 10 am to 5 pm we installed 9 panels with 2 people on the swing stage, 1 person on the roof and 2 people on the ground to pass material | Subcontractor | Josh McPherson | false |  |  |  |  | 5 | 50 | true | this day I received material Acm panels | Swing stage and forklift | false |  |  |  |  | ACM | 9 | 10
20067 | BNA PROJECT 5 | 2022-08-15 | Naza | not dilays | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 40 | false |  | 2 booms 86' and 120' | false |  |  |  |  | Other | [42 empty] | applying butyl to all the joints of IMP panels | 30
21060 | Vantage VA 13 | 2022-08-15 | Nathan Wall | 10 ACM panels Blade wall. installed trim around door. peeled poloy | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 10 | false |  | 2 80' boom lifts | false |  |  |  |  | ACM | 10 | 80
20067 | BNA PROJECT 5 | 2022-08-12 | Naza | not delays | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 40 | false |  | 2 booms 86' and 120' | false |  |  |  |  | Flashing IMP Other | [8 empty] | 12 | 28 | [22 empty] | 50 | 6 | [8 empty] | galvanized plates 40' | 6
21024 | Vanderbilt Graduate Housing | 2022-08-12 | Marvin blanco | installing panels , angles , insulation and waiting for the others guys setup the swing stage 4 hours waiting | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 11 | false |  | swing stage | false |  |  |  |  | Hat Channel Insulation Plate |  |  | 4 | 2 | [22 empty] | 16 | 1 | [6 empty] | 144 | 3
21062 | BNA MNAA Garage B | 2022-08-12 | Naza | this day was to completely screw all the plates | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  | 86' boom | false |  |  |  |  | Other | [42 empty] | this day was to completely screw all the plates | 30
20067 | BNA PROJECT 5 | 2022-08-11 | Naza | sunny day | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 50 | true | Crate ACM box of Clips | 2 booms 86' and 120' | false |  |  |  |  | Flashing IMP Other | [8 empty] | 22 | 30 | [22 empty] | 40 | 6 | [8 empty] | 2 guys 6am 1pm 40' flat metal and 80'LF of caulking at ground transportation south side they have to fix framing end wood | 14
21024 | Vanderbilt Graduate Housing | 2022-08-11 | Marvin blanco | installing insulation angles and panels cleaning area | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 11 | false |  | swing stage | false |  |  |  |  | Hat Channel Insulation Other Plate |  |  | 15 | 5 | [22 empty] | 224 | 3 | [6 empty] | 48 | 1 | [6 empty] | cleaning all area 2 hours | 2
21060 | Vantage VA 13 | 2022-08-11 | Nathan Wall | installed 17 pcs. corrugated northwest gen. 8 ACM panels south wall | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 10 | false |  | 2 80' boom lifts | false |  |  |  |  | ACM Corrugated / Screen wall | 8 | 40 | [20 empty] | 17 | 40
21062 | BNA MNAA Garage B | 2022-08-11 | Naza | very hot the guys stayed hydrated and taking breaks.... missing one plate still at the shop | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  | 86' boom | false |  |  |  |  | Plate |  |  | 13 | 30
21071 | Google NBY-HUB 1 | 2022-08-11 | Marvin blanco | cleaning installing insulation | Subcontractor | Steve Fudge | true | the panels never arrived and neither did the flashing and trims |  |  | good condition | 9 | 3 | false |  | 2 boomlift | false |  |  |  |  | Insulation | [26 empty] | 40 | 2
20067 | BNA PROJECT 5 | 2022-08-10 | Daniel | 1 ground guy (8 hours) - putting clips on panels/ keeping area clean and passing whatever material we needs | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 8 | false |  | 85FT BOOM, 120FT BOOM | false |  |  |  |  | ACM Caulking Trim | 8 | 8 | [18 empty] | 175 | 22 | [14 empty] | 80 | 2
20067 | BNA PROJECT 5 | 2022-08-10 | Naza | rain out at 2pm | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 40 | false |  | 2 booms 86' 120' | false |  |  |  |  | Flashing IMP Other | [8 empty] | 8 | 12 | [22 empty] | 22 | 6 | [8 empty] | galvanized plates 22' 3 guys 6 hours, 2 clean up at all areas 6am to 11:30am and intalling galvanized J 4 hours 11:30am 1:30pm | 22
21024 | Vanderbilt Graduate Housing | 2022-08-10 | Marvin blanco | installing angles insulation | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 8 | false |  | swing stage | false |  |  |  |  | Hat Channel Insulation | [26 empty] | 100 | 2 | [6 empty] | 192 | 6
21060 | Vantage VA 13 | 2022-08-10 | Nathan Wall | installed 10 ACM panels southwest ele. 4 ACM panels west wall 3rd floor | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 10 | false |  | 2 80' boom lifts | false |  |  |  |  | ACM | 14 | 80
21062 | BNA MNAA Garage B | 2022-08-10 | Naza | very hot the guys stayed hydrated | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  | 86' | false |  |  |  |  | Plate |  |  | 22 | 30
21071 | Google NBY-HUB 1 | 2022-08-10 | Marvin blanco | taking measurements checking the flashing around the windows but it's not completely we have missing parts installing night walls and installing insulation | Subcontractor | Steve Fudge | true | not trims reveos not panels not flashing not silicone not screws also nothing the nothing |  |  | good condition | 9 | 10 | false |  | 2 boomlift | false |  |  | 3 |  | Hat Channel Insulation Layout | [26 empty] | 400 | 3 | [6 empty] | 560 | 4
20067 | BNA PROJECT 5 | 2022-08-09 | Daniel | 2 ground guy(16 hours) putting clips on panels/ keeping area clean. | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 8 | false |  | 85FT BOOM, 120FT BOOM | false |  |  |  |  | ACM Caulking Trim | 33 | 14 | [18 empty] | 80 | 16 | [14 empty] | 160 | 2
20067 | BNA PROJECT 5 | 2022-08-09 | Daniel | 1 ground guy (8 hours)- putting clips on panels/ keeping area clean | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 8 | false |  | 85FT, 120FT | false |  |  |  |  | ACM Flashing Other Trim | 20 | 16 | [30 empty] | 50 | 2 |  |  | 110 | 4 |  |  |  |  | Extrusion that hold little panel in the middle, (60 FT) Drip edge flashing for roof panels,(50 FT)(8 hours) | 10
20067 | BNA PROJECT 5 | 2022-08-09 | Naza | 2 guys have to chenge head set screws at the airwave for flat head screws | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 50 | false |  | 2 boos 86' and 120' | false |  |  |  |  | IMP Other | [8 empty] | 30 | 30 | [32 empty] | 2 guys clean up losse foam from the IMP bundles tied up all the IMP bundles and chenge all the head screws at the airwave roof for flat head screws | 20
21024 | Vanderbilt Graduate Housing | 2022-08-09 | Marvin blanco | installing aluminum panels insulation and angles | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 11 | false |  | swing stage | false |  |  |  |  | Hat Channel Insulation Plate |  |  | 10 | 4 | [22 empty] | 200 | 2 | [6 empty] | 18 | 5
21062 | BNA MNAA Garage B | 2022-08-09 | Naza | rainy day after lunch | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 24 | false |  | 86' boom | false |  |  |  |  | Plate |  |  | 12 | 24
21062 | BNA MNAA Garage B | 2022-08-09 | Naza | a bit of trouble lining up the holes, some plates are not completely finished. | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  | 86' boom | false |  |  |  |  | Plate |  |  | 17 | 30
21071 | Google NBY-HUB 1 | 2022-08-09 | Marvin blanco | installing flashing and coping cutting clips taking measurements and cleaning | Subcontractor | Steve Fudge | true | aluminum panels |  |  | perfect condition | 9 | 10 | false |  | 2 boomlift | false |  |  | 2 |  | Coping Flashing Layout | [32 empty] | 100 | 6 | [6 empty] | 100 | 4
20067 | BNA PROJECT 5 | 2022-08-08 | Naza | the panels of the interior sector 14 south side were not finished because they took away the spider lift | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  | 2 booms 86' and 120' | false |  |  |  |  | ACM IMP | 3 | 15 | [6 empty] | 18 | 15
21024 | Vanderbilt Graduate Housing | 2022-08-08 | Marvin blanco | installing panels angles and insulation | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 11 | false |  | swing stage | false |  |  |  |  | Hat Channel Insulation Plate |  |  | 8 | 4 | [22 empty] | 200 | 2 | [6 empty] | 18 | 5
21060 | Vantage VA 13 | 2022-08-08 | Nathan Wall | installed 12 pcs. corrugated northwest gen. 5 panels west wall. Z and insulation | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 10 | false |  | 2 80' booms | false |  |  |  |  | ACM Corrugated / Screen wall Insulation Subgirt Zee | 5 | 20 | [20 empty] | 9 | 20 |  |  | 700 | 20 |  |  | 300 | 20
21062 | BNA MNAA Garage B | 2022-08-08 | Naza | first day of work in the project | Subcontractor | Marc Ribar | false |  |  |  |  | 3 | 30 | false |  | 86' boom | false |  |  |  |  | Plate |  |  | 12 | 30
21071 | Google NBY-HUB 1 | 2022-08-08 | Marvin blanco | installing flashing on the roof and fixing stuff | Subcontractor | Steve Fudge | true | aluminum panels |  |  | good condition | 9 | 10 | false |  | 2 boomlift | false |  |  |  |  | Coping | [40 empty] | 300 | 10
21060 | Vantage VA 13 | 2022-08-07 | Nathan Wall | installed 10 pcs. corrugated on roof | Subcontractor | Steve Fudge | false |  |  |  |  | 5 | 8 | false |  | 2 80' booms | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 10 | 40
20067 | BNA PROJECT 5 | 2022-08-06 | Naza | the rain reduced our production after 11am | Subcontractor | Marc Ribar | true | the rain reduced our production after 11am |  |  | raining after 11am | 6 | 48 | false |  | 2 bopoms 86' and 120' | false |  |  |  |  | IMP | [8 empty] | 36 | 48
21024 | Vanderbilt Graduate Housing | 2022-08-06 | Marvin blanco | installing aluminum panels and insulation | Subcontractor | Drake De Tomasi | false |  |  |  |  | 4 | 11 | false |  | swing stage | false |  |  |  |  | Insulation Plate |  |  | 6 | 3 | [22 empty] | 200 | 8
21060 | Vantage VA 13 | 2022-08-06 | Nathan Wall | installed 16 pcs. corrugated on roof | Subcontractor | Steve Fudge | false |  |  |  |  | 5 | 8 | false |  | 2 80' booms | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 16 | 40
21071 | Google NBY-HUB 1 | 2022-08-06 | Marvin blanco | working on the coping and fixing a wall 🧱 with the night wall and insulation | Subcontractor | Steve Fudge | true | aluminum panels and trim reviews |  |  | perfect condition | 9 | 8 | false |  | boomlift | false |  |  |  |  | Coping | [40 empty] | 10 | 8
21024 | Vanderbilt Graduate Housing | 2022-08-05 | Marvin blanco | installing panels hat channels and insulation | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 11 | false |  | swing stage | false |  |  |  |  | Hat Channel Plate |  |  | 5 | 3 | [30 empty] | 12 | 8
21060 | Vantage VA 13 | 2022-08-05 | Nathan Wall | installed 11 pcs. corrugated northwest gen. 10 pcs. corrugated on roof | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 10 | false |  | 2 80' booms | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 21 | 80
21024 | Vanderbilt Graduate Housing | 2022-08-04 | Marvin blanco | installing aluminum panels and putting angles also insulation | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 11 | false |  | swing stage | false |  |  |  |  | Hat Channel Insulation Plate |  |  | 6 | 4 | [22 empty] | 200 | 3 | [6 empty] | 24 | 4
21060 | Vantage VA 13 | 2022-08-04 | Nathan Wall | 8 pcs. corrugated northwest gen. 8 panels penthouse. rained | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 5 | false |  | 2 80' booms | false |  |  |  |  | ACM Corrugated / Screen wall | 8 | 20 | [20 empty] | 8 | 20
21071 | Google NBY-HUB 1 | 2022-08-04 | Marvin blanco | fixing stuff cleaning | Subcontractor | Steve Fudge | true | aluminum panels and flashing |  |  | perfect condition | 9 | 10 | false |  | 2 boomlift | false |  |  |  |  | Other | [42 empty] | fixing blue insulation | 10
20067 | BNA PROJECT 5 | 2022-08-03 | Naza | back on sector 14 interior spider lift ben repared | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 40 | false |  | 70'spider boom 86' 86' 120' | false |  |  |  |  | ACM | 10 | 40
21024 | Vanderbilt Graduate Housing | 2022-08-03 | Marvin blanco | installing installation metal angles and panels | Subcontractor | Drake De Tomasi | false |  |  |  |  | 5 | 11 | false |  | swing stage | false |  |  |  |  | Hat Channel Insulation Plate |  |  | 9 | 4 | [22 empty] | 240 | 3 | [6 empty] | 208 | 4
21046 | The Moore Building | 2022-08-03 | Naza | problems with the right swingstage motor gets heat up and stop working Joe Hoyle was notified at 4pm | Subcontractor | Drake De Tomasi | false |  |  |  |  | 3 | 30 | false |  | 30' swingstage | false |  |  |  |  | Flashing Hat Channel Other | [32 empty] | 30 | 6 | 120 | 15 | [6 empty] | moving material inspecting and geting the swingstage set up | 9
21060 | Vantage VA 13 | 2022-08-03 | Nathan Wall | installed 15 panels on penthouse. 22 pcs. corrugated northwest gen. | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 10 | false |  | 2 80' booms | false |  |  |  |  | ACM Corrugated / Screen wall | 15 | 40 | [20 empty] | 22 | 40
21061 | ATT Building Facade Rehab | 2022-08-03 | Fredy Rodriguez | this day of 11 amel Mr. Joshua told me to stop installing to verify the installation of panels and this day better prepare an area to be able to install the tubes that will be in the area of ​​​​blinds | Subcontractor | Josh McPherson | true | this day we stop for verification of installed panels |  |  |  | 10 | 10 | false |  | Swing stage and forklift | false |  |  |  |  | ACM | 6 | 100
21061 | ATT Building Facade Rehab | 2022-08-03 |  | 5 | Subcontractor | Josh McPherson | false |  |  |  |  | 3 |  | false |  |  | false |  |  |  |  | ACM
21071 | Google NBY-HUB 1 | 2022-08-03 | Marvin blanco | fixing things that are bad and taking measures of material that is needed | Subcontractor | Steve Fudge | true | aluminum panels are delay trim flashing star clips |  |  | perfect condition | 9 | 8 | false |  | 2 boomlift | false |  |  | 5 |  | Layout Other | [42 empty] | putting insulation on the wall we're fixing | 3
19006 | Kistler Rolled Panels | 2022-08-02 | Chad mccoy | Upon arrival the MOT was an hour late being set up. The boom lift had the wrong price amateur set for two men to go up in the basket so it had to be re-calibrated before two men can operate in the basket. Martin roofing was in Orlando it took them two hours to get on site to take the expansion joint out. Upon getting on the roof we found that there were multiple gaps in failed caulk joints from Martin roofing. There is also a slice in the rubber seal that goes at the base of the new building to old building. What’s Martin roof and had their system out then Keith and I started taking our panel off and in the middle of us taking our panel off a small storm here that showed us down for the airport for about 36 minutes. Once a Panels off we took pictures and everybody wanted to go up and see the condition of the area of operation under the panel. The only gap that was there is a little 6 x 4” hole that wasn’t even under our panel it was at the base of our panel hidden behind West Tampa glass trim. I have pictures of when our panel was installed in the entire section with waterproofed so at some point between then and when the expansion do it was finished somebody took all the waterproofing off the area that our silver panel covered on the side. | Subcontractor | Chris Ball | true | Between the weather and the boom and waiting on other trades we were down for a while because nobody was prepared |  |  | Pop-up storms 100 plus degrees | 2 | 10 | false |  | 80/60z boom | false |  |  |  |  | ACM | 1 | 1
20067 | BNA PROJECT 5 | 2022-08-02 | Daniel | 3 ground guys( 24 hours) putting clips on panels/ passing material and keeping area clean. | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 8 | false |  | 85FT BOOM, 120FT BOOM | false |  |  |  |  | ACM Trim | 15 | 14 | [34 empty] | 65 | 2
20067 | BNA PROJECT 5 | 2022-08-02 | Naza | problems with the spider boom lift we thought it was due to low battery charge and we put it on charge for 3 hours and it still did not work, Marc was immediately notified to request a technician from united rentals, the technician said it was due to a deprogramming the system and he reprogrammed it. for this reason we could not work inside sector 14 | Subcontractor | Marc Ribar | true | spider lift mechanical failures |  |  | sunny | 7 | 70 | false |  | 70', 86' 86' 120' boom lifts | false |  |  |  |  | ACM Other | 15 | 35 | [40 empty] | moving IMP bundles and 200' LF or galvanized starter J | 35
21060 | Vantage VA 13 | 2022-08-02 | Nathan Wall | 20 pcs. corrugated southwest gen. 5 panels on penthouse. | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 10 | false |  | 2 80' booms | false |  |  |  |  | ACM Corrugated / Screen wall | 5 | 40 | [20 empty] | 20 | 40
21061 | ATT Building Facade Rehab | 2022-08-02 | Fredy Rodriguez | from 6am to 4pm 2 people on the swing stage to install panels and from 6am to 4pm 2 people on the scaffolding to help hold the panels so that screws can be put in and from 6am to 4pm 2 people on the ground to help assemble the panels and from 6am to 4pm 4 people helping to pass material | Subcontractor | Josh McPherson | false |  |  |  |  | 10 | 10 | false |  | Swing stage and forklift | false |  |  |  |  | ACM | 25 | 10
21071 | Google NBY-HUB 1 | 2022-08-02 | Marvin blanco | fixing things left bad by the other company number sheet 204 on 7 | Subcontractor | Steve Fudge | true | panels are delay flashing trims |  |  | perfect | 10 | 10 | false |  | 2 boomlift | false |  |  |  |  | Other | [42 empty] | fixing a wall taking insulation out and z's | 10
20067 | BNA PROJECT 5 | 2022-08-01 | Daniel | 2 ground guys(16 hours) - putting clips on panels/ keeping area clean and passing material. | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 8 | false |  | 85FT BOOM, 120FT BOOM | false |  |  |  |  | ACM Trim | 15 | 14 | [34 empty] | 65 | 2
20067 | BNA PROJECT 5 | 2022-08-01 | Naza | 3 guys working at sector 14 interior ACM panels, 3 guys at airwave roof doing ice and water shield till 1pm after they did in all areas. | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 60 | false |  | 70' spider boom lift, 2 86's and 120' | false |  |  |  |  | ACM Other | 9 | 30 | [40 empty] | ice and water shield at airwave and after 1pm they were collecting trash all our areas. | 30
21024 | Vanderbilt Graduate Housing | 2022-08-01 | Marvin blanco | making orientation they was going to jump in the scaffolding swing stage and they don't have the live line so they went to the shop and brought it to the job site | Subcontractor | Drake De Tomasi | false |  |  |  |  | 3 | 11 | false |  | swing stage | false |  |  |  |  | Insulation Other | [26 empty] | 42 | 2 | [14 empty] | angle for attaching the panels | 4
21060 | Vantage VA 13 | 2022-08-01 | Nathan Wall | 15 panels on penthouse. 9 pcs. corrugated sw gen. 2 panels west wall | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 10 | false |  | 2 80' booms | false |  |  |  |  | ACM Corrugated / Screen wall | 17 | 40 | [20 empty] | 9 | 40
21061 | ATT Building Facade Rehab | 2022-08-01 | Fredy Rodriguez | this day from 6am to 8am we all start preparing to receive material and from 8am to 9am we unload material and from 9am to 4pm 2 people on the swing stage and 2 people on top of the skid and 2 people on the ground to install the panels and from 9am a 4pm 4 people on the ground to be able to pass the panels to be installed | Subcontractor | Josh McPherson | false |  |  |  |  | 10 | 10 | true | Acm panel ,screws and shim | Swing stage and forklift | false |  |  |  |  | ACM | 13 | 10
21071 | Google NBY-HUB 1 | 2022-08-01 | Marvin blanco | we drive to the job site and make the orientation for others guys we finish at 1 pm. and then waiting for material 4 hrs | Subcontractor | Steve Fudge | true | The material was supposed to arrive but it did not arrive |  |  | perfect | 10 | 10 | false |  | 2 boomlift | false |  |  |  |  | Other | [42 empty] | nothing | 4
21060 | Vantage VA 13 | 2022-07-31 | Nathan Wall | 7 panels west wall | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 5 | false |  | 2 80' booms | false |  |  |  |  | ACM | 7 | 10
21060 | Vantage VA 13 | 2022-07-30 | Nathan Wall | 7 panels west wall | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 5 | false |  | 2 80' booms | false |  |  |  |  | ACM | 7 | 10
21061 | ATT Building Facade Rehab | 2022-07-30 | Fredy Rodriguez | can you help me get bits for concrete and bits to break metal sometimes I find rebar when I drill the hole in the concrete please | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 60 | false |  | Swing stage and forklift | false |  |  |  |  | Insulation Other | [26 empty] | 1390 | 10 | [14 empty] | from 6am to 4pm 2 people installed insulation and from 6am to 4pm 2 people installed 24 clips and from 6am to 4pm 2 people buried to pass material and cleaning in the work area | 10
21061 | ATT Building Facade Rehab | 2022-07-30 | Fredy Rodriguez | This day we held a meeting to take safety measures at work and cleanliness in the work area | Subcontractor | Josh McPherson | true |  |  |  | this day we had the delay that the rain came and we could no longer work | 6 | 18 | false |  | Swing stage and forklift | false |  |  |  |  | Insulation Other | [26 empty] | 140 | 3 | [14 empty] | we installed 9 clips to hold pipes in the south area | 3
20067 | BNA PROJECT 5 | 2022-07-29 | Daniel | 2 ground guys(16hour) passing material/ putting clips on panels and keeping area clean. | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 8 | false |  | 85FT BOOM, 120FT BOOM | false |  |  |  |  | ACM Flashing Other Trim | 26 | 20 | [30 empty] | 60 | 4 |  |  | 122 | 4 |  |  |  |  | Back extrusion that holds little panel in the middle( 50 FT) | 4
20067 | BNA PROJECT 5 | 2022-07-29 | Naza | 3 workers who were working on elairwave were sent home by lightning and rain alert at 9am | Subcontractor | Marc Ribar | true | 3 guys working at airwave have to go home by lighting & rainy |  |  | rainy | 6 | 39 | true | 3 Crates FS14, 2 Crates FS16 4 boxes with clips | 86' boom | false |  |  |  |  | ACM Other | 12 | 30 | [40 empty] | galvanized metal flashing 110' | 9
20067 | BNA PROJECT 5 | 2022-07-28 | Daniel | 1 ground guy ( 8 hours ) - putting clips on panels/ making sure area is clean . | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 8 | false |  | 85FT BOOM, 120FT BOOM | false |  |  |  |  | ACM Caulking Other Trim | 24 | 12 | [18 empty] | 48 | 16 | [14 empty] | 70 | 2 |  |  |  |  | Back extrusion that holds little panel in the middle( 40 FT) | 2
20067 | BNA PROJECT 5 | 2022-07-28 | Naza | 5 guys working at airwave roof & 3 guys working at sector 14 interior ACM panels | Subcontractor | Marc Ribar | false |  |  |  |  | 8 | 80 | false |  | 86' boom | false |  |  |  |  | ACM Other | 12 | 30 | [40 empty] | watershield & metal panels caps | 50
21060 | Vantage VA 13 | 2022-07-28 | Nathan Wall | unloaded truck. 22 please. corrugated on southwest gen. 7 panels penthouse | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 10 | true | corrugated | 2 80' booms | false |  |  |  |  | ACM Corrugated / Screen wall | 7 | 40 | [20 empty] | 22 | 40
21061 | ATT Building Facade Rehab | 2022-07-28 | Fredy Rodriguez | in the southern area we are going to have a problem that when drilling the cement to anchor the clips we have enough metal angles can you help me get special bits to make the job easier please | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 60 | false |  | Swing stage and forklift | false |  |  |  |  | Insulation Other | [26 empty] | 1100 | 10 | [14 empty] | this day from 6am to 4pm 2 people installed insulation and 2 people from 6 to 4 installed 26 clips in the south area and from 6am to 4pm 2 people on the ground to pass material and cleaning in the work area | 10
20067 | BNA PROJECT 5 | 2022-07-27 | Daniel | 3 ground guy (24 hours )- putting clips on panels/ passing material and keeping area clean. | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 8 | false |  | 85FT BOOM, 120 FT BOOM | false |  |  |  |  | ACM Flashing Trim | 34 | 12 | [30 empty] | 30 | 2 |  |  | 138 | 2
20067 | BNA PROJECT 5 | 2022-07-27 | NAZA | 3 guys working at airwave roof & 3 guys working at sector 14 interior ACM panels | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 60 | false |  | 86' boom | false |  |  |  |  | ACM Other | 7 | 30 | [40 empty] | watershield 3 guys | 30
21060 | Vantage VA 13 | 2022-07-27 | Nathan Wall | installed 22 ocs. corrugated southwest gen. 20 panels Blade wall. 11 panels south wall. | Subcontractor | Steve Fudge | false |  |  |  |  | 10 | 10 | false |  | 2 80 booms | false |  |  |  |  | ACM Corrugated / Screen wall | 31 | 80 | [20 empty] | 22 | 20
21061 | ATT Building Facade Rehab | 2022-07-27 | Fredy Rodriguez | Can you help me check if we have more tubes in the store for the West area, because here we need a few tubes and if they are, can you make a plan to send them to me please? | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 60 | false |  | Swing stage and forklift | false |  |  |  |  | Insulation Other | [26 empty] | 2800 | 4 | [14 empty] | this day from 6am to 4pm 2 people installed insulation and from 6am to 2pm 2 people installed insulation and from 2pm to 4pm 2 people read measurements on walls in the southern area and from 6am to 4pm 2 people on the ground to pass material or cleaning in the work area | 12
20067 | BNA PROJECT 5 | 2022-07-26 | Naza | airwave roof 3 guys doing watershield & 2 guys doing metal caps. | Subcontractor | Marc Ribar | true | at 2pm the workers had to go down the airwave due to lightning alert |  |  | sunny in the morning and cloudy in the afternoon | 5 | 40 | false |  | 86' boom | false |  |  |  |  | Other | [42 empty] | watershield & filling the roof panels with screws and putting the metal caps 6am 2pm | 40
21060 | Vantage VA 13 | 2022-07-26 | Nathan Wall | installed 21 pcs. corrugated southwest gen. 14 panels west wall. 20 panels Blade wall. 12 panels south wall | Subcontractor | Steve Fudge | false |  |  |  |  | 10 | 10 | false |  | 2 80' booms | false |  |  |  |  | ACM Corrugated / Screen wall | 46 | 80 | [20 empty] | 21 | 20
21061 | ATT Building Facade Rehab | 2022-07-26 | Fredy Rodriguez | I have this question in the southern area there are bolt heads precisely in that area will be the clips that will hold the tube can you help me what plans were made to be able to work with the clips | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 60 | false |  | Swing stage and forklift | false |  |  |  |  | Insulation Other Tubing | [26 empty] | 1100 | 10 | 105 | 7 | [12 empty] | from 1 pm to 4 pm 2 people installed 35 feet of horizontal angles and from 6m to 4pm 2 people installed insulation and 2 people on the ground helping to pass material and from 6 am to 1 pm 2 people installed 6 tubes | 6
20067 | BNA PROJECT 5 | 2022-07-25 | Naza | 3 guys working at the airwave and 2 guys working at ground transportation north & south | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 50 | false |  | 86'boom | false |  |  |  |  | Caulking Flashing IMP Other | [8 empty] | 2 | 12 | [10 empty] | 20 | 4 | [10 empty] | 20 | 4 | [8 empty] | watershield at air wave 3 guys 6am 4pm | 30
21060 | Vantage VA 13 | 2022-07-25 | Nathan Wall | installed 21 pcs. corrugated south west gen. 13 panels west wall. 11 panels south wall 8 panels Blade wall | Subcontractor | Steve Fudge | false |  |  |  |  | 10 | 10 | false |  | 2 80' booms | false |  |  |  |  | ACM Corrugated / Screen wall | 33 | 80 | [20 empty] | 21 | 20
21061 | ATT Building Facade Rehab | 2022-07-25 | Fredy Rodriguez | this day from 6am to 4pm 2 people on the swing stage installed insulation also from 6am to 4pm 2 people on the ground passing material also from 6am to 11am 2 people put more screws in the shutters and from 11am to 12pm the inspector came to look at the bolts that are with the clips in the sement and joints of the tubes everything is very good and from 12pm to 4pm 2 people began to prepare and clean the swing stage to work on the installation of tubes and insulation | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 60 | true | Tubin | Swing stage and forklift | false |  |  |  |  | Insulation | [26 empty] | 1188 | 10
21071 | Google NBY-HUB 1 | 2022-07-25 | Marvin blanco | waiting on the boomlift 8 hrs and cleaning work area fixing others stuff | Subcontractor | Steve Fudge | true | flashing and panels |  |  | good | 3 | 10 | false |  | 2 boomlift | false |  |  |  |  | Insulation | [26 empty] | 600 | 10
21060 | Vantage VA 13 | 2022-07-24 | Nathan Wall | 6 panels south wall | Subcontractor | Steve Fudge | false |  |  |  |  | 5 | 5 | false |  | 2 80' booms | false |  |  |  |  | ACM | 6 | 25
21061 | ATT Building Facade Rehab | 2022-07-24 | Fredy Rodriguez | this day I had a problem to see if we can modify some larger plates to hold the tubes because I have no other option to be able to continue I will put the photo so that you can do your calculations we also installed the blinds that we had the problem yesterday to be able to assemble them well | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 70 | false |  | Swing stage and forklift | false |  |  |  |  | Insulation Louvre Tubing | [24 empty] | 13 | 10 | 1800 | 10 | 90 | 10
21060 | Vantage VA 13 | 2022-07-23 | Nathan Wall | installed 5 panels 11 pcs. Z , 370 square feet insulation | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 10 | false |  | 2 80' booms | false |  |  |  |  | ACM Insulation Subgirt Zee | 5 | 20 | [24 empty] | 370 | 20 |  |  | 110 | 40
21061 | ATT Building Facade Rehab | 2022-07-23 | Fredy Rodriguez | this day from 6am to 4pm we had to remove 9 blinds that were installed to be able to solve a problem that here in the plans did not have a Note of the installation form and we had to assemble it on the floor to be able to see that the shapes of the cuts were correct but that was a lot of wasted time | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 60 | false |  | Swing stage and forklift | false |  |  |  |  | Insulation Other | [26 empty] | 1400 | 10 | [14 empty] | this day 16 large plates were installed to hold the tubes 2 people from 6am to 4pm | 10
21071 | Google NBY-HUB 1 | 2022-07-23 | Marvin Blanco | installing insulation and checking z's | Subcontractor | Steve Fudge | false |  |  |  |  | 3 | 8 | false |  | boomlift | false |  |  |  |  | Insulation | [26 empty] | 400 | 8
20067 | BNA PROJECT 5 | 2022-07-22 | Daniel | 1 ground guy (8 hours) - putting clips on panels/ passing material and keeping area clean. | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 8 | false |  | 85FT BOOM, 120 FT BOOM | false |  |  |  |  | ACM Caulking Trim | 30 | 14 | [18 empty] | 188 | 16 | [14 empty] | 110 | 2
20067 | BNA PROJECT 5 | 2022-07-22 | Naza | 6 IMP panels were cut to size 9'-0" ground transportation north, 60' LF of trim | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 40 | false |  | 86' boom | false |  |  |  |  | Flashing IMP | [8 empty] | 6 | 32 | [22 empty] | 60 | 8
21060 | Vantage VA 13 | 2022-07-22 | Nathan Wall | installed 15 panels and 1520 square feet insulation | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 10 | false |  | 2 80' booms | false |  |  |  |  | ACM Insulation | 15 | 20 | [24 empty] | 1520 | 60
21061 | ATT Building Facade Rehab | 2022-07-22 | Fredy Rodriguez | this day from 6am to 4pm 2 people started installing insulation and from 6am to 4pm 2 people installing blinds and from 6am to 4pm 2 people on the ground helping to reach the material | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 60 | true | bands to hold the insulation and gun to be able to nail into the metal and large plates to hold tubes | Swing stage and forklift | false |  |  |  |  | Louvre | [24 empty] | 9 | 10
20067 | BNA PROJECT 5 | 2022-07-21 | Daniel | 1 ground ( 8 hour ) - passing material/ putting clips on panels z | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 8 | false |  | 85FT BOOM, 120 FT BOOM | false |  |  |  |  | ACM Caulking Flashing Other Trim | 30 | 18 | [18 empty] | 12 | 2 | [10 empty] | 60 | 4 |  |  | 120 | 4 |  |  |  |  | Back extrusion that hold little panel on the middle( 60 FT ) | 4
20067 | BNA PROJECT 5 | 2022-07-21 | Naza | 11 IMP panels at north transportation, unloading Crates 2 men hours | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 40 | true | 4 Crates ACM and Clips | 86' boom | false |  |  |  |  | IMP | [8 empty] | 11 | 38
21060 | Vantage VA 13 | 2022-07-21 | Nathan Wall | installed 11 panels, and 39 pcs Z south wall | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 10 | false |  | 2 80' booms | false |  |  |  |  | ACM Subgirt Zee | 11 | 40 | [28 empty] | 390 | 40
21061 | ATT Building Facade Rehab | 2022-07-21 | Fredy Rodriguez | this day from 6am to 10am 4 people were preparing angles to be able to hold the blinds this type of modification is being done here in project and from 10 am to 4pm 4 blinds were installed with 2 people on the swing stage and 2 people on the groun | Subcontractor | Josh McPherson | false |  |  |  |  | 4 | 40 | false |  | Swing stage and forklift | false |  |  |  |  | Louvre | [24 empty] | 4 | 6
20067 | BNA PROJECT 5 | 2022-07-20 | Daniel | 2 ground guys (16 hours) - putting clips on panels / passing material and keeping area clean . | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 8 | false |  | 85FT BOOM, 120FT BOOM | false |  |  |  |  | ACM Caulking Trim | 34 | 14 | [18 empty] | 140 | 16 | [14 empty] | 121 | 2
21008 | 900 Church | 2022-07-20 | Marvin blanco | second daily just for the pictures | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 |  | false |  |  | false |  |  |  |  | ACM
21008 | 900 Church | 2022-07-20 | Marvin blanco | cleaning and fixing little things | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 8 | false |  |  | false |  |  |  |  | ACM
21060 | Vantage VA 13 | 2022-07-20 | Nathan Wall | installed 54 pcs. Z 760 square feet insulation on the penthouse. crane shut down west side | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 10 | false |  | 2 80' booms | false |  |  |  |  | Insulation Subgirt Zee | [26 empty] | 760 | 40 |  |  | 540 | 40
21061 | ATT Building Facade Rehab | 2022-07-20 | Fredy Rodriguez | This day we had an inspection to verify the bolts to the concrete from 8 am to 10 am and at that time we weighed to prepare and modify angles to be able to put the screws in the blinds with 2 people on the swing stage and 2 on the ground | Subcontractor | Josh McPherson | false |  |  |  |  | 4 | 40 | true | isolation | Swing stage and forklift | false |  |  |  |  | Louvre | [24 empty] | 4 | 4
20067 | BNA PROJECT 5 | 2022-07-19 | Daniel | 2 ground guys (16 hours) - putting clips on panels/ handing material and making sure area is clean. | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 8 | false |  | 85FT BOOM, 120FT BOOM | false |  |  |  |  | ACM Caulking Trim | 28 | 22 | [18 empty] | 60 | 6 | [14 empty] | 210 | 4
20067 | BNA PROJECT 5 | 2022-07-19 | Naza | sunny day | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 60 | false |  | 86' boom | false |  |  |  |  | Flashing IMP Other | [8 empty] | 9 | 18 | [22 empty] | 70 | 3 | [8 empty] | airwave north and south galvanized flashing 470', flying IMP bundles to the roof for north elevation. | 39
21008 | 900 Church | 2022-07-19 | Jose pena | we have to make rout on the last panels in the corners because they didn't make right | Subcontractor | Dillon Bowman | false |  |  |  |  | 4 | 11 | false |  |  | false |  |  |  |  | ACM Other | 5 | 5 | [40 empty] | the others take time making rout In the corners panels and taking the film out the paper cleaning | 6
21008 | 900 Church | 2022-07-19 | Jose pena | we have to make rout on the last panels in the corners because they didn't make right | Subcontractor | Dillon Bowman | false |  |  |  |  | 4 | 11 | false |  |  | false |  |  |  |  | ACM Other | 5 | 5 | [40 empty] | the others take time making rout In the corners panels and taking the film out the paper cleaning | 6
21060 | Vantage VA 13 | 2022-07-19 | Nathan Wall | installed 14 panels on the west wall.. 370 square feet insulation and Z, 5 ACM panels south wall | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 10 | false |  | 2 80' booms | false |  |  |  |  | ACM Insulation Subgirt Zee | 19 | 20 | [24 empty] | 370 | 20 |  |  | 440 | 40
21061 | ATT Building Facade Rehab | 2022-07-19 | Fredy Rodriguez | this day I had a delay and maybe you can help me I have two groups ready to work but we are stopped because there is very little material we have to work with I hope they can send me the material I need to continue installing the tubes in the West zone | Subcontractor | Josh McPherson | true | No material could be installed due to waiting for someone to inspect the brick area in the area of ​​the shutters. |  |  |  | 6 | 48 | false |  | Swing stage and forklift | false |  |  |  |  | Other | [42 empty] | this day from 6 am to 2 pm 2 people took readings on the heights of the blinds and 4 people did general cleaning in all the available work areas and prepared angles to hold the blinds the time was from 6 am to 2 pm | 6
20067 | BNA PROJECT 5 | 2022-07-18 | Daniel | 1 ground guy (8 hours) putting clips on all the panels/ handing material and making sure area is clean. | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 8 | false |  | 85FT BOOM, 120 FT BOOM | false |  |  |  |  | ACM Flashing Other Trim | 38 | 20 | [30 empty] | 40 | 4 |  |  | 120 | 4 |  |  |  |  | Back extrusion that hold small panel( 50 FT) | 4
20067 | BNA PROJECT 5 | 2022-07-18 | Naza | rainy day | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 40 | true | 1/2 of palet with ice and watershield, palet with 12" flat galvanized. | 86' boom | false |  |  |  |  | Caulking Flashing Other | [20 empty] | 40 | 10 | [10 empty] | 20 | 2 | [8 empty] | looking for IMP panels for west elevation sout side, moving IMP panels to ground transportationnorth side 30pcs. | 28
21008 | 900 Church | 2022-07-18 | Marvin blanco | everything good | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 11 | false |  |  | false |  |  |  |  | ACM Insulation Plate | 7 | 4 | 17 | 6 | [22 empty] | 20 | 1
21060 | Vantage VA 13 | 2022-07-18 | Nathan Wall | Installed ACM and flashing west wall 3rd floor, and Z and insulation on the south wall | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 10 | true | ACM , corrugated | 85' boom | false |  |  |  |  | ACM Flashing Insulation Subgirt Zee | 14 | 16 | [24 empty] | 1150 | 20 |  |  | 1020 | 20 | 40 | 4
21061 | ATT Building Facade Rehab | 2022-07-18 | Fredy Rodriguez | this day we had many delays to install the blinds apart from the rain we had to make extra cuts to be able to modify the installation of the blinds | Subcontractor | Josh McPherson | true | Rain all morning |  |  |  | 6 | 60 | true | 21 persianas y 12 ángulos de aluminio | Swing stage and forklift | false |  |  |  |  | Louvre Other | [24 empty] | 1 | 2 | [16 empty] | this day from 6 am to 9 am we wait for the rain to pass and from 9 am to 10 am we receive the material and from 10 am to 12 pm we wait for the rain to pass and from 12 pm to 4 pm 4 people on the ground cut angles to be able to install the blinds and from 12 pm to 4pm 2 people installed 4 cut angles and a blind | 6
22017 | Paretti Mazda | 2022-07-17 | Rony | Fabricating Panels weather was extremely hot | Subcontractor | Eric Gutierrez | false |  |  |  |  | 4 | 14 | false |  | To boom lifts | false |  |  |  |  | ACM | 30 | 56
20067 | BNA PROJECT 5 | 2022-07-16 | Naza | 5 panels were cut and made to measure at ground transportation | Subcontractor | Marc Ribar | false |  |  |  |  | 10 | 10 | false |  | two 86' boom lifts | false |  |  |  |  | IMP Other | [8 empty] | 75 | 95 | [32 empty] | 5 panels were cut and made to measure at ground transportation 5 hours 5 guys. | 5
21060 | Vantage VA 13 | 2022-07-16 | Nathan Wall | Installed ACM and flashing west wall 3rd floor | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 6 | false |  | 85' boom | false |  |  |  |  | ACM Flashing | 7 | 8 | [30 empty] | 30 | 4
21071 | Google NBY-HUB 1 | 2022-07-16 | Rodney | Limpiesa | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 10 | false |  |  | false |  |  |  |  | ACM
22017 | Paretti Mazda | 2022-07-16 | Rony | Fabricating Panels to make fit weather was not that great | Subcontractor | Eric Gutierrez | false |  |  |  |  | 4 | 14 | false |  | Two Boom lifts | false |  |  |  |  | ACM | 18 | 56
20067 | BNA PROJECT 5 | 2022-07-15 | Daniel | 1 ground guy (8 hours) - putting clips on panels/ passing material | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 8 | false |  | 85 FT BOOM, 120 FT BOOM | false |  |  |  |  | ACM Flashing Other Trim | 34 | 20 | [30 empty] | 70 | 4 |  |  | 108 | 4 |  |  |  |  | Back extrusion that holds little panel(65FT) | 4
20067 | BNA PROJECT 5 | 2022-07-15 | Naza | Incidentally, the boom lift group dropped a panel, HP was notified, the guys analyzed that it was safer to put the panel inside the basket, and the perimeter was cordoned off with signs | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 10 | false |  | 86' boom | false |  |  |  |  | Flashing IMP Other | [8 empty] | 38 | 42 | [22 empty] | 70 | 20 | [8 empty] | galvanized J starter for IMP 110' | 8
21060 | Vantage VA 13 | 2022-07-15 | Nathan Wall | Installed ACM and flashing west wall 3rd floor | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 6 | false |  | 85' boom | false |  |  |  |  | ACM Flashing | 10 | 8 | [30 empty] | 40 | 4
21071 | Google NBY-HUB 1 | 2022-07-15 | Rodney | Demora por excavaciones | Subcontractor | Steve Fudge | false |  |  |  |  | 4 | 10 | false |  | Boom | false |  |  |  |  | ACM Tubing | [28 empty] | 40 | 10
22017 | Paretti Mazda | 2022-07-15 | Rony | How to fabricate couple panels to make them fit that took a while | Subcontractor | Eric Gutierrez | false |  |  |  |  | 4 | 14 | false |  | Two boom lift | false |  |  |  |  | ACM | 18 | 56
20067 | BNA PROJECT 5 | 2022-07-14 | Daniel | 3 ground guys (24 hours) - passing material/ putting clips on panels and keeping the area clean . | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 8 | false |  | 85FT BOOM, 120 FT BOOM | false |  |  |  |  | ACM Flashing Other Trim | 24 | 10 | [30 empty] | 20 | 2 |  |  | 70 | 2 |  |  |  |  | Extrusion that holds the back panel (40) | 2
20067 | BNA PROJECT 5 | 2022-07-14 | Daniel | 3 ground guys ( 24 hours) put clips on panels/ handed panels and whatever material they needed. Kept area clean | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 8 | false |  | 85FT BOOM, 120 FT BOOM | false |  |  |  |  | ACM Flashing Other Trim | 14 | 10 | [30 empty] | 20 | 2 |  |  | 50 | 2 |  |  |  |  | back extrusion that holds little panel( 10 FT) | 2
20067 | BNA PROJECT 5 | 2022-07-14 | Naza | We were supposed to fly IMP bundles to the roof but the crane operators didn't have time | Subcontractor | Marc Ribar | false |  |  |  |  | 8 | 80 | false |  | 86' boom | false |  |  |  |  | Flashing IMP Other | [8 empty] | 8 | 30 | [22 empty] | 20 | 10 | [8 empty] | 2 guys ice water shield at south airwave 70' galvanized flashing 6am 11am, 4 guys moving bundles of IMP 6am 10am, 2 guys west elev... south 120' flashing 50' of mending plate 6am 10am, 2 guys claning yard 10am 11am, 4 guys west elev... north 8 IMP panels install 80' galvanized J trim 11am 4pm. | 40
21060 | Vantage VA 13 | 2022-07-14 | Nathan Wall | Installed ACM and flashing west wall 3rd floor | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 10 | true | ACM | 85' boom | false |  |  |  |  | ACM Flashing | 14 | 16 | [30 empty] | 20 | 4
21071 | Google NBY-HUB 1 | 2022-07-14 | Rodney | Cambiar el boon no deja tener mejor producción | Subcontractor | Steve Fudge | false |  |  |  |  | 5 | 10 | false |  | Boom | false |  |  |  |  | ACM Insulation | [26 empty] | 3200 | 10
22017 | Paretti Mazda | 2022-07-14 | Rony | How to fabricate panels to make them fit took some time issues fabricating | Subcontractor | Eric Gutierrez | false |  |  |  |  | 4 | 14 | false |  | Two boom lifts | false |  |  |  |  | ACM | 18 | 56
20067 | BNA PROJECT 5 | 2022-07-13 | Naza | high temperatures the boys had to take constant breaks, 3 guys installing IMP panels at ground trasportation south side 10am 4pm | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 60 | false |  | 86' boom | false |  |  |  |  | Flashing IMP Other | [8 empty] | 7 | 12 | [22 empty] | 80 | 6 | [8 empty] | 3 guys at roof water shield and galvanized flashing 80' 6am to 11am, 3 guys loking for IMP bundles 6am to 10am, 3 guys west side elevation 180' mennding plate 100' flashing 11am 4pm | 42
21008 | 900 Church | 2022-07-13 | marvin | the guys put 8 panels and 10 big trim plates and then in the afternoon the supervisor went to tell them to remove 4 panels because they needed to put reinforcement in the framing | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 11 | false |  | no equipment | false |  |  |  |  | ACM Plate | 10 | 8 | 14 | 3
21060 | Vantage VA 13 | 2022-07-13 | Nathan Wall | Installed ACM and flashing west wall 3rd floor | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 10 | true | ACM | 85' boom | false |  |  |  |  | ACM Flashing | 15 | 16 | [30 empty] | 40 | 4
21071 | Google NBY-HUB 1 | 2022-07-13 | Rodney | Se pierde mucho tiempo con el boon no sirve | Subcontractor | Steve Fudge | false |  |  |  |  | 4 | 10 | false |  | Boon | false |  |  |  |  | ACM Insulation | [26 empty] | 2400 | 10
21082 | UTMC MOB | 2022-07-13 | Chad mccoy | Pics | Subcontractor | Josh McPherson | false |  |  |  |  | 3 | 10 | false |  |  | false |  |  |  |  | Caulking Flashing | [20 empty] | 350 | 8 | [10 empty] | 42 | 1
21082 | UTMC MOB | 2022-07-13 | Chad mccoy | We started our morning continuing caulking. Keith started the barrel and I jumped on the scissor lift and was caulking random places. And then Kevin was cutting the flashing so I caulked flash out the barrel upper window head detail. Once we cut them all. I installed 32 pieces. But this flash was narrow. So it had to be screwed into place unlike the bottom window. Once that was done Kevin continued caulking on the ground. And Keith and I continued in the air | Subcontractor | Josh McPherson | false |  |  |  |  | 3 | 10 | false |  | 1 boom 1 scissor lift | false |  |  |  |  | Caulking Flashing | [20 empty] | 350 | 8 | [10 empty] | 43 | 1.5
22017 | Paretti Mazda | 2022-07-13 | Rony | No issues | Subcontractor | Eric Gutierrez | false |  |  |  |  | 4 | 15 | false |  | 2 Boom lifts | false |  |  |  |  | ACM | 30 | 60
20067 | BNA PROJECT 5 | 2022-07-12 | Naza | delays at airwave for us to install ice and water shield, Delays at west elevation above the curtain wall waterpruf not ready. HP was notified for Kyle and Adam Lewis. | Subcontractor | Marc Ribar | true | at airwave and west side curtain wall. |  |  | sunny | 6 | 48 | true | metal trims, galvanized Zees | 86' boom | false |  |  |  |  | Flashing Other | [32 empty] | 120 | 12 | [8 empty] | 3 guys preparing roof panels for the night crew, 3 guys loking for IMP bundles to fly to the roof. | 36
21008 | 900 Church | 2022-07-12 | Marvin blanco | everything good | Subcontractor | Dillon Bowman | false |  |  |  |  | 4 | 11 | true | straps |  | false |  |  |  |  | Insulation Plate |  |  | 12 | 5 | [22 empty] | 300 | 6
21060 | Vantage VA 13 | 2022-07-12 | Nathan Wall | Unloaded truck got rained out | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 4 | true | ACM | 85' boom | false |  |  |  |  | Other | [42 empty] | Nothing, unloaded truck | 8
21071 | Google NBY-HUB 1 | 2022-07-12 | Rodney | Ninguna | Subcontractor | Steve Fudge | false |  |  |  |  | 5 | 10 | false |  | Boom | false |  |  |  |  | Insulation Tubing | [26 empty] | 50 | 10 | 112 | 10
22017 | Paretti Mazda | 2022-07-12 | Rony | No issues | Subcontractor | Eric Gutierrez | false |  |  |  |  | 4 | 12 | true |  | Two boom lift one forklift | false |  |  |  |  | ACM | 25 | 48
20067 | BNA PROJECT 5 | 2022-07-11 | Naza | sunny day, no delays. | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 60 | true | 3 Crates with ACM FS06, 1 Crate with Clips. | 86' boom | false |  |  |  |  | Flashing Other | [32 empty] | 120 | 15 | [8 empty] | ice and water shield, galvanized metal flashing 140', mending plate at west side elev...120' | 45
21060 | Vantage VA 13 | 2022-07-11 | Nathan Wall | Installed ACM and flashing on the west wall | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 8 | false |  | 85' boom | false |  |  |  |  | ACM Flashing | 11 | 12 | [30 empty] | 40 | 4
21061 | ATT Building Facade Rehab | 2022-07-11 | Fredy Rodriguez | This day we stop working because we cannot install the new blinds because first they are going to repair the area where they are going to be installed, we also no longer have material and we are waiting for plans to be able to continue | Subcontractor | Josh McPherson | true | we stopped because we have to wait for other people to repair brickwork and put water protection in the area where the new blinds are going to be installed |  |  |  | 4 | 24 | false |  | Swing stage and forklift | false |  |  |  |  | Other | [42 empty] | this day from 6am to 12pm the swing stage was cleaned and material that was removed from the blinds area was accommodated | 4
21071 | Google NBY-HUB 1 | 2022-07-11 | Rodney | Ninguna mujer | Subcontractor | Steve Fudge | false |  |  |  |  | 5 | 10 | true | Boon lift | Bomm | false |  |  |  |  | Tubing | [28 empty] | 112 | 10
21082 | UTMC MOB | 2022-07-11 | Chad mccoy | Pics | Subcontractor | Josh McPherson | false |  |  |  |  | 3 | 10 | false |  |  | false |  |  |  |  | Caulking | [20 empty] | 300 | 7
21082 | UTMC MOB | 2022-07-11 | Chad mccoy | We got to the site early this morning. When we arrived we noticed that some the panels have have clear plastic over it and is held in place with aggressive red tape. We waited to see if our equipment was going to arrive and when it didnt we started caulking all we could reach. The lift showed up after lunch. So we jumped on them and continued caulking. There are more missed color panels on the columns. Plus dents and waves in the panels that didn't seem to be there upon install | Subcontractor | Josh McPherson | true | Equipment showed up after 12 |  |  | Cloudy | 3 | 10 | false |  | 1 boom lift. 1 scissor lift | false |  |  |  |  | Caulking | [20 empty] | 300 | 7
21082 | UTMC MOB | 2022-07-11 | Chad mccoy | Pics | Subcontractor | Josh McPherson | false |  |  |  |  | 3 |  | false |  |  | false |  |  |  |  | Caulking | [20 empty] | 300 | 7
22017 | Paretti Mazda | 2022-07-11 | Rony | No issues I was a good day | Subcontractor | Eric Gutierrez | false |  |  |  |  | 4 | 13.5 | false |  |  | false |  |  |  |  | ACM
21060 | Vantage VA 13 | 2022-07-10 | Nathan Wall | Installed ACM and flashing on the west wall | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 8 | true |  | 85' boom | false |  |  |  |  | ACM Flashing | 11 | 12 | [30 empty] | 30 | 4
20067 | BNA PROJECT 5 | 2022-07-09 | Naza | rainy day. | Subcontractor | Marc Ribar | true | rain on and off |  |  | rainy | 4 | 20 | false |  | 86' boom lift, fork lift. | false |  |  |  |  | Flashing Other | [32 empty] | 110 | 10 | [8 empty] | melnding plate 150' | 10
21060 | Vantage VA 13 | 2022-07-09 | Nathan Wall | Installed acm on the west wall, got rained out | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 2 | false |  | 85' boom | false |  |  |  |  | ACM | 4 | 4
21061 | ATT Building Facade Rehab | 2022-07-09 | Fredy Rodriguez | It's ready, we've already removed the blinds, but it won't be ready to install the new blinds because they have to repair the brick first, and I don't know how long it's going to take. | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 48 | false |  | Swing stage and forklift | false |  |  |  |  | Other | [42 empty] | this day 6 people from 6 am to 2 pm we install 50 cut angles that hold the tubes from the bottom | 6
22017 | Paretti Mazda | 2022-07-09 | Rony | No issues | Subcontractor | Eric Gutierrez | false |  |  |  |  | 4 | 13.5 | false |  |  | false |  |  |  |  | ACM | 24 | 52
20067 | BNA PROJECT 5 | 2022-07-08 | Naza | high temperatures sunny day the crew stayed hydrated all day | Subcontractor | Marc Ribar | false |  |  |  |  | 4 | 40 | false |  | fork lift | false |  |  |  |  | Flashing Other | [32 empty] | 190 | 12 | [8 empty] | 20 man hours ice and watershield, 8 man hours moving material and flying bundles of insulated panels. | 28
21060 | Vantage VA 13 | 2022-07-08 | Nathan Wall | Installed ACM and flashing west wall 3rd floor | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 8 | false |  | 85' boom | false |  |  |  |  | ACM Flashing | 9 | 14 | [30 empty] | 40 | 4
21061 | ATT Building Facade Rehab | 2022-07-08 | Fredy Rodriguez | I am waiting if you can have the solution of the angles that are short to be able to install 3 lines of tubes that are missing in the areas of the brick columns | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 60 | true | this day they brought me 50 cut angles to hold the tubes from the bottom | Swing stage and forklift | false |  |  |  |  | Other | [42 empty] | this day from 6am to 4pm 8 blinds were removed 10 tubes 2 people were on the roof 2 on the swing stage and 2 on the ground | 6
22017 | Paretti Mazda | 2022-07-08 | Rony padilla | some issues today due to could not finish no locations due to they have an install a material and a selfie and that makes me not to install the coping Panel | Subcontractor | Eric Gutierrez | true |  |  |  |  | 4 | 14 | true | Papels | 2 boom lifts ,forklift | false |  |  |  |  | ACM | 27 | 56
20067 | BNA PROJECT 5 | 2022-07-07 | Daniel | 2 ground guys (16 hours) passing roof panels/ keeping the area clean. | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 8 | false |  | 85FT Boom, 120 FT Boom | false |  |  |  |  | Flashing Other Overly Roof Panel | [12 empty] | 28 | 12 | [18 empty] | 110 | 4 | [8 empty] | Installing galvanized metal on columns (100FT) Installed finish caps on roof panels (43)(4hours) | 12
20067 | BNA PROJECT 5 | 2022-07-07 | Naza | crew had to get off the airwave due to rain at 1pm to 3pm | Subcontractor | Marc Ribar | true | delay due to rain from 1pm to 3pm |  |  | sunny , raini after 1pm | 4 | 36 | false |  | fork lift | false |  |  |  |  | Flashing Other | [32 empty] | 80 | 9 | [8 empty] | ice and water shield 3 guys from 9am to 1pm, organizing bundles of IMP panels to fly to the roof on Friday one guy work on this all day from 6am to3pm the other 3 guys help to muve bundles from 1pm to 3pm | 27
21060 | Vantage VA 13 | 2022-07-07 | Nathan Wall | Installed base Flashing and panels | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 8 | false |  | 85' boom | false |  |  |  |  | ACM Flashing | 9 | 12 | [30 empty] | 40 | 4
21061 | ATT Building Facade Rehab | 2022-07-07 | Fredy Rodriguez | I want to see if they can help me if they will have the cut angles ready that are going to hold the tubes at the bottom | Subcontractor | Josh McPherson | false |  |  |  |  | 6 | 60 | false |  | Swing stage and forklift | false |  |  |  |  | Other | [42 empty] | from 6am to 11am the level of the installed pipes was rectified and was done by 2 people and from 6am to 4 pm 2 people on the roof to help level the pipes and help move material and from 6am to 4pm 2 people on the ground for security of work and cleaning and material storage and from 11 am to 4 pm 2 people began to remove the blinds that are going to be removed | 6
22017 | Paretti Mazda | 2022-07-07 | Rony padilla | Have issues installing the last two panels due to there’s nowhere to anchor also cannot install the coping due to they have not install the material where I can anchor my coping didn’t have all my panels All material on the job site due to delayed | Subcontractor | Eric Gutierrez | false |  |  |  |  | 4 | 14 | false |  |  | false |  |  |  |  | ACM | 22 | 56
20067 | BNA PROJECT 5 | 2022-07-06 | Daniel | 3 ground guys (24 hours) - cutting roof panels/ roof panel clips and just passing material | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 8 | false |  | 85FT Boom, 120 FT Boom | false |  |  |  |  | Flashing Other Overly Roof Panel | [12 empty] | 44 | 18 | [18 empty] | 22 | 3 | [8 empty] | long clip that hold roof panels, (44 clips) | 3
20067 | BNA PROJECT 5 | 2022-07-06 | Naza | the crew have to get off the airwave due to lightning from 2pm to 4pm, | Subcontractor | Marc Ribar | true | lightning airwave delay 2pm to 4pm |  |  | raining | 4 | 40 | false |  | 86 boom lift, fork lift. | false |  |  |  |  | Other | [42 empty] | 4 guys flat galvanized 6am to 10am, 4 guys airbarrier 10am to 2pm, 2pm to 4pm looking for bundles of INP panels for west side elevation. | 40
21060 | Vantage VA 13 | 2022-07-06 | Nathan Wall | Installed base Flashing and 2 panels | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 8 | true | ACM | 85' boom | false |  |  |  |  | ACM Flashing | 2 | 8 | [30 empty] | 40 | 8
21061 | ATT Building Facade Rehab | 2022-07-06 | Fredy Rodriguez | I need you to please solve the problem of being able to cut the angles that go in the lower part where you are going to hold the tubes and also modify the angles in the brick columns because they are short, thanks | Subcontractor | Josh McPherson | false |  |  |  |  | 4 | 40 | false |  | Swing stage and forklift | false |  |  |  |  | Other Tubing | [28 empty] | 20 | 2 | [12 empty] | from 6am to 7am 2 people prepared the platform to be able to work and from 7am to 10am 2 people installed 4 clips and 20 feet of pipe and from 10am to 4pm 2 people installed 75 feet of horizontal angles and also from 6 am to 4pm there were 2 people on the ground for work safety and moving tubes | 2
21071 | Google NBY-HUB 1 | 2022-07-06 | Chad mccoy | This morning we had stretch and flex. Then Rodney went back to night wall. The boom lift crew went back to install the panels. And I started doing base flashing so that we could start a new wall of installation tomorrow. I had a meeting today It took about an hour we also had lightning delay for about an hour as well. The boom lift crew installed panels while my crew Started layout an elevation on the night wall system because they have to be cut down because they’re hanging too low but prior to that we had to remove all the bottom layer of insulation. This is so I can trip in the flashing in the right manner, and then we installed flashing and then caulked that flashing then we ran Starter track and cut down night wall rail system For underneath the windows. And then we started the install and Panels | Subcontractor | Steve Fudge | true | Lightning was present today just like yesterday but it only shut us down today for about an hour. After that it rained but my crew kept working the other cruise got out of the rain |  |  | Storms | 6 | 10 | false |  | 2 booms | false |  |  | 1 |  | ACM Caulking Flashing Layout Other | 19 | 8 | [18 empty] | 125 | 1 | [10 empty] | 250 | 1 | [8 empty] | Underneath the windows the night wall was not installed so these had to be cut down and then installed we installed 55 of them today and we cut all 55 down to 27 inches | 1
21071 | Google NBY-HUB 1 | 2022-07-06 | Rodney | Tener cuidado cuando el material cuando lo enpaquen | Subcontractor | Steve Fudge | false |  |  |  |  | 5 | 10 | false |  | Boon | false |  |  |  |  | ACM Flashing | 18 | 10 | [30 empty] | 250 | 10
20067 | BNA PROJECT 5 | 2022-07-05 | Daniel | 2 ground guys( 16 hours ) putting clips on all panels/ passing material and keeping area clean . | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 8 | false |  | 85 FT Boom, 120 FT Boom | false |  |  |  |  | ACM Caulking Other Trim | 15 | 16 | [18 empty] | 12 | 8 | [14 empty] | 75 | 4 |  |  |  |  | peel poly off 102 panels. | 4
21071 | Google NBY-HUB 1 | 2022-07-05 | Rodney oliveros | Se demoro por el mal tiempo | Subcontractor | Steve Fudge | true | Mal tiempo lluvia |  |  |  | 5 | 10 | false |  | Boom lift | false |  |  |  |  | ACM Insulation |  | 10 | [25 empty] | 20
22017 | Paretti Mazda | 2022-07-05 | Rony padilla | Due to not having all the material have issues to start in a different location start installing but they’re not complete a section do it too and now my material was in the field | Subcontractor | Eric Gutierrez | false |  |  |  |  | 4 | 14 | false |  | 2 Boom lifts forklifts | false |  |  |  |  | ACM | 20 | 56
20067 | BNA PROJECT 5 | 2022-06-30 | Daniel | 2 ground guys( 16 hours ) putting clips on panels/ organizing panels and making sure area clean . | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 8 | false |  | 85FT BOOM- 120 FT BOOM | false |  |  |  |  | ACM Flashing Other Trim | 37 | 20 | [30 empty] | 20 | 4 |  |  | 450 | 4 |  |  |  |  | Back extrusion that holds inner panel(30FT) | 4
20067 | BNA PROJECT 5 | 2022-06-30 | Naza Padron | it started to rain from 11:00 am to 1 pm. 22 roof panels intalled 16 at the north 6 panels at south installed by 3 guys 6am to 11;00am 110' 0f flashing at north roof panels installed by 3 guys from 1;00pm to 4;00pm, one guy work from 6am to 11am and after the rain from 1pm to 4pm at roof south side cleaning roof panels | Subcontractor | Marc Ribar | true | the delay was caused by the rain from 11am to 1pm |  |  | sunny morning and rainy afternoon | 4 | 40 | false |  |  | false |  |  |  |  | Flashing Other Overly Roof Panel | [12 empty] | 22 | 15 | [18 empty] | 110 | 9 | [8 empty] | one guy cleans caulking and tape at south side roof panels 6am to 11am and after the rain 1pm to 4pm | 8
21061 | ATT Building Facade Rehab | 2022-06-30 | Fredy Rodriguez | sunny day from 6am to 3:30pm, rainy day from 3:20pm to 4pm | Subcontractor | Josh McPherson | false |  |  |  |  | 5 | 50 | false |  | swingstage | false |  |  |  |  | Other Tubing | [28 empty] | 165 | 20 | [12 empty] | from 6am to 3pm three guys preparing tubes and making new holes because the clips had to be moved from position, drilling could not be done because ribar was behind the concrete. from 3pm to 4pm three guys they prepared the swingstage on the south side to be used the next day. | 30
21071 | Google NBY-HUB 1 | 2022-06-30 | Chad mccoy | We started our morning doing stretch and flex. And then we are headed over to start working on the building. We split up into two crews today one of us worked out of the boom lift and the other crew was on the ground. The ground crew ran as many panels as they could all the way down the edge of the building plus any kind of flashing or night wall system or insulation that needed to be installed and the boom crew was going up and down the wall stacking panels vertically. Rodney was still on his side of the building doing night lol I didn’t see you till the end of the day. | JWMCD Crew | Steve Fudge | false |  |  |  |  | 6 | 10 | false |  | 2 booms | false |  |  |  |  | ACM Flashing Insulation | 34 | 8 | [24 empty] | 80 | 1 |  |  |  |  | 30 | 1
21071 | Google NBY-HUB 1 | 2022-06-30 | Rodney | Paneles unos mas grandes k otros | Subcontractor | Steve Fudge | false |  |  |  |  | 5 | 10 | false |  |  | false |  |  |  |  | ACM Flashing Overly Roof Panel | 34 | 10 | [10 empty] | 34 | 10 | [19 empty] | 10
20067 | BNA PROJECT 5 | 2022-06-29 | Daniel | 2 ground guys(16 hours) putting clips on panels/ passing material and making sure everything is clean . | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 8 | false |  | 85FT BOOM- 120 FT BOOM | false |  |  |  |  | ACM Flashing Trim | 32 | 24 | [30 empty] | 50 | 4 |  |  | 350 | 4
21009 | The Inn at Southhall | 2022-06-29 | Naza Padron | sunny day no delays | Subcontractor | Chris Ball | false |  |  |  |  | 3 | 11 | false |  | steep ladders | false |  |  |  |  | Coping Genesis | [14 empty] | 14 | 18 |  |  |  |  | 80 | 6 | [18 empty] | 21 | 9
21009 | The Inn at Southhall | 2022-06-29 | Naza Padron | sunny day no delays | Subcontractor | Chris Ball | false |  |  |  |  | 3 | 11 | false |  | steep ladders | false |  |  |  |  | Coping Genesis | [14 empty] | 14 | 18 |  |  |  |  | 80 | 6 | [18 empty] | 21 | 9
21060 | Vantage VA 13 | 2022-06-29 | Nathan Wall | 13 pcs. corrugated southwest gen. 6 panels loading dock | Subcontractor | Steve Fudge | false |  |  |  |  | 8 | 8 | false |  | 2 80' booms | false |  |  |  |  | ACM Corrugated / Screen wall | 6 | 32 | [20 empty] | 13 | 32
21071 | Google NBY-HUB 1 | 2022-06-29 | Chad mccoy | We started our morning doing stretch and flex. And then we are headed to the building to start installing, Either Panels or night wall material, Or trim and layout for a new panel install. I had a meeting today it lasted about an hour and 15 minutes. I installed about 280 feet of flashing. But to do this we had to take close to 75 pieces of insulation out because it goes behind it. Once a flashing was installed we caulked the top of the flashing to the building and all the screw heads and then we put the insulation back here. While we were doing this another team was installed and Panels. And another team was installing night wall on the other side of the building. | JWMCD Crew | Steve Fudge | true | I had a meeting today they delayed my trim install and layout. We are missing some panels and then I have some panels that are corner panels but they do not need to be corners and then I have one panel that doesn’t match any size panel on the print. There is a black membrane on the top of the blue Styrofoam that has to be cut back 5 inches around the entire perimeter of the buildings so the flashing will set where it needs to go. We cut about 110 feet off of the black membrane. The bottom flashing the termination detail has a two piece system that goes into each other so I built and put those together today So installation of the flashing would go smoother instead of trying to slide it in after the fact. After the flashing was in we had to caulk the top piece of the flashing to the building and every screw that was in the base |  |  | 92 | 6 | 10 | false |  | 2 booms | false |  |  |  |  | ACM Flashing Insulation | 15 | 9 | [24 empty] | 60 | 1 |  |  |  |  | 280 | 8
21071 | Google NBY-HUB 1 | 2022-06-29 | Rodney | Se puso 300fy de flashing | Subcontractor | Steve Fudge | false |  |  |  |  | 5 | 10 | false |  |  | false |  |  |  |  | ACM | 16 | 10
20067 | BNA PROJECT 5 | 2022-06-28 | Daniel | 2 ground guys(16 hours) putting clips on panels/ passing material and organizing everything . | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 8 | false |  | 85FT BOOM , 120 FT BOOM | false |  |  |  |  | ACM Flashing Other Trim | 28 | 20 | [30 empty] | 70 | 4 |  |  | 310 | 4 |  |  |  |  | back extrusion that holds inner panel, (80FT) | 4
21071 | Google NBY-HUB 1 | 2022-06-28 | Chad mccoy |  | JWMCD Crew | Steve Fudge | false | [6 empty] | false |  |  | false
21071 | Google NBY-HUB 1 | 2022-06-28 | Chad mccoy |  | JWMCD Crew | Steve Fudge | false | [6 empty] | false |  |  | false
21071 | Google NBY-HUB 1 | 2022-06-28 | Chad mccoy |  | JWMCD Crew | Steve Fudge | false | [6 empty] | false |  |  | false
21071 | Google NBY-HUB 1 | 2022-06-28 | Chad mccoy |  | JWMCD Crew | Steve Fudge | false | [6 empty] | false |  |  | false
21071 | Google NBY-HUB 1 | 2022-06-28 | Chad mccoy | We started our day doing stretch and flex and then I had orientation and badging so I can get on site. After stretch and flex the install crews Headed to the site. Once I was done with badging I went to the site and started walking around and seeing what I was done and taking pictures of everything for documentation. Rodney Installed The night wall framing while three other guys did the other Panels. The panel installation can go faster but the install crew needs to step it up. Rodney needs to be doing the night wall system in front of them so that they can continue to keep going instead of having to stop to do the night wall and the flashing their selves. | JWMCD Crew | Steve Fudge | true | The panels are Orientated in the crates where you cannot see any of the numbers unless you pull half the panels out and lay them somewhere where it’s safe. The painter painted over the stickers. A lot of the tight fit corners were welded on and ground down in the shop so these corners look like trash on the wall because they are not nice pretty factory returns with a factory fold. There are panels that are marked a certain number on the panel but when you go to measure that panel and match it to the prints It does not match up. I have one panel that doesn’t match any size at all on any of the prints that I have. I have other panels that are marked as a certain number but they go in a different spot and their corner panels. We are completely missing one panel 1a21. I feel like the lunch break needed to be brought up. Rodney left to go get all of his guys lunch but he was gone like 40 minutes when he came back he gave his guys lunch and then continued his lunch so he had like an hour and a half hour and 40 minute lunch. |  |  | Hot 82 | 6 | 9 | true | 4 inch Z and clips | 4 inch Z and clips2 booms | false |  |  |  |  | ACM | 16 | 8
20067 | BNA PROJECT 5 | 2022-06-27 | Daniel | 1 ground guy(8 hours) putting clips on panels/ handing us panels and material. | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 8 | false |  | 1- 85FT 1-120FT | false |  |  |  |  | ACM Trim | 21 | 28 | [34 empty] | 30 | 4
21060 | Vantage VA 13 | 2022-06-25 | Nathan Wall | Installed ACM and flashing | Subcontractor | Steve Fudge | false |  |  |  |  | 4 | 8 | true |  | 85' boom | false |  |  |  |  | ACM Flashing | 10 | 16 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 40 | 16
20067 | BNA PROJECT 5 | 2022-06-24 | Daniel | 4 installers ( 32 hours ) 1 ground guy(1 hour) - putting clips on panels/ handing panels and material. (2hour) all 5 of us went to go clean the roof on the south side, and take all the material that belonged on the roof that was on the south side . | JWMCD Crew | Marc Ribar | false |  |  |  |  | 5 | 10 | false |  | 85FT BOOM- 120 FT BOOM | false |  |  |  |  | ACM Flashing Trim | 23 | 6 | [30 empty] | 70 | 1 |  |  | 150 | 1
20067 | BNA PROJECT 5 | 2022-06-24 | Daniel | 2 installers( 20 hours) 1 ground guy (10 hours) passing roof panels/ material | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 10 | false |  |  | false |  |  |  |  | Flashing Overly Roof Panel | [12 empty] | 21 | 9 | [18 empty] | 100 | 1
21060 | Vantage VA 13 | 2022-06-24 | Nathan Wall | Installed ACM and flashing | Subcontractor | Steve Fudge | false |  |  |  |  | 4 | 10 | false |  | 85' boom | false |  |  |  |  | ACM Flashing | 10 | 20 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 40 | 20
20067 | BNA PROJECT 5 | 2022-06-23 | Daniel | 3 installers-( 24 hours) 3 ground guys(24 hours) setting up panels- passing material / panels. Some of the ground guys took turn cleaning up all the oil spill it took the whole 8 hours to clean everything up . | JWMCD Crew | Marc Ribar | true | Boom spilled oil everywhere, took a while too lay the litter all over the oil from north side to south side of airport. Then scoop it back up |  |  |  | 6 | 8 | false |  | 2-85FT BOOM | false |  |  |  |  | ACM Trim | 10 | 7 | [34 empty] | 60 | 1
20067 | BNA PROJECT 5 | 2022-06-23 | Daniel | 2 installers( 20 hours) 1 ground guy (10 hours) passing material/ panels | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 10 | false |  |  | false |  |  |  |  | Flashing Overly Roof Panel | [12 empty] | 21 | 9 | [18 empty] | 100 | 1
21060 | Vantage VA 13 | 2022-06-23 | Nathan Wall | Installed ACM, received missing panels. | Subcontractor | Steve Fudge | false |  |  |  |  | 4 | 10 | false |  | 85' boom | false |  |  |  |  | ACM | 15 | 40 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
21060 | Vantage VA 13 | 2022-06-22 | Nathan Wall | Installed Flashing, that wasn't on the truck yesterday had it overnighter. Installed ACM on the North Wall found that we was missing panels. | Subcontractor | Steve Fudge | false |  |  |  |  | 4 | 10 | true | Flashing | 85' boom | false |  |  |  |  | ACM Flashing | 3 | 20 | [18 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 40 | 20
20067 | BNA PROJECT 5 | 2022-06-21 | Daniel | 2 guys ( 16 hours) broke down 5 crates, flew all the wood, and 8 bags of trash down with crane. then grabbed forklift and threw them in the dumpster one by one . | JWMCD Crew | Marc Ribar | false |  |  |  |  | 2 | 8 | false |  | 2- 85FT BOOM | false
21060 | Vantage VA 13 | 2022-06-21 | Nathan Wall | Installed insulation, and Z on the penthouse, unloading a truck a the end of the day. | Subcontractor | Steve Fudge | false |  |  |  |  | 4 | 10 | true | ACM | 85' boom | false |  |  |  |  | Insulation Subgirt Zee | [20 empty] | 0 | 0 | 0 | 0 |  |  | 390 | 20 |  |  | 240 | 20
20067 | BNA PROJECT 5 | 2022-06-20 | Daniel | 2 installers (20 hours) 2 ground guys (20 hours) passing material/ getting panels ready. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 4 | 10 | false |  |  | false |  |  |  |  | ACM Flashing Trim | 17 | 8 | [30 empty] | 30 | 1 |  |  | 80 | 1
21069 | Broadwest HOAR | 2022-06-20 |  | Nathan Wall | Subcontractor | Denis Usatenko | false |  |  |  |  | 4 | 10 | true |  | 85' boom | false |  |  |  |  | Insulation Subgirt Zee | [20 empty] | 0 | 0 | 0 | 0 |  |  | 382 | 20 |  |  | 240 | 20
20067 | BNA PROJECT 5 | 2022-06-17 | Daniel | 3 guys (24 hours) loaded the truck with imp panels (13) bundles back and forth through the ramp to departures flew them up with crane . 2 bundles at a time | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 8 | false |  | 2- 85FT Boom | false
1658 | #NO MATCH | 2022-06-16 | marvin | 3 guys working putting panels and others 3 helping putting tubes on the screenwall moving scaffold installed z's | Subcontractor | Rod Grove | false |  |  |  |  | 6 | 12 | false |  |  | false |  |  |  |  | Overly Roof Panel | [12 empty] | 31 | 60 | [17 empty] | 60
21061 | ATT Building Facade Rehab | 2022-06-15 | Fredy Rodriguez |  | Subcontractor | Josh McPherson | false |  |  |  |  | 3 | 30 | false |  |  | false |  |  |  |  | Tubing | [28 empty] | 17 | 30
1658 | #NO MATCH | 2022-06-14 | marvin | 5 guys working on the roof and one helping the Naza guys because there were only two of them and they need one to pass material to the scaffold, a total of 6 guys. | Subcontractor | Rod Grove | false |  |  |  |  | 6 | 12 | true | I loaded 6 empty crates to Tommy |  | false |  |  |  |  | Overly Roof Panel | [12 empty] | 60 | 60
20067 | BNA PROJECT 5 | 2022-06-14 | Daniel | 1 ground guy ( 8 hours ) cutting metal / passing material, 2 guys installing galvanized metal on columns ( 125 FT ) (8 hours ) | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 8 | false |  | 2- 85FT BOOM | false
21061 | ATT Building Facade Rehab | 2022-06-14 | Fredy Rodriguez |  | Subcontractor | Josh McPherson | false |  |  |  |  | 3 | 30 | false |  | Swing stage and forklift | false |  |  |  |  | Tubing | [28 empty] | 16 | 30
21082 | UTMC MOB | 2022-06-14 | Chad mccoy | We started our morning continuing with the column install and the framing build out on the front two columns. We had to shoot on the Z put strapping around it to make it tight and then we installed the columns. The top two panels had to be cut because they were too long so each side had To have an inch and a quarter cut off of it. One of the columns is missing one of the panels at the top it is still at the shop and it will be picked up tomorrow and brought back here so that we can install it. I got a hold of Josh and I told Josh that we didn’t have a panel and they found it. We then moved to peeling the panels so that we can get a sense of the mix match colors around everything. Once the panels were peeled we installed the last to return to Panels and then peeled them as well. Altogether there are 30 mist colored panels a plethora of little dents throughout everything and one panel with a huge dent in it in the top middle. The panels also have what looks like stress cracks from when it was rolled. And in these panels you can see a distinct spot where they start rolling it at the end of the panel. We also started breaking down crates and trying to get everything organized or ready for tomorrow and we started caulking the skywards joints around everything to help the watershed while a decision is being made. | JWMCD Crew | Josh McPherson | true | The project manager over the GC told us to stop caulking everything until a decision was made. So I told him I am not officially supposed to stop until an email is sent to Josh or a message of some sort telling us to stop what we are doing and then I will stop. That was sent, the message was relayed to me and my guys and we will be waiting for further instructions and getting the site ready for a demobilization |  |  | Hot. Feels like said it was 110 today | 4 | 10 | false |  | 80 foot boom | false |  |  |  |  | ACM Caulking Insulation Subgirt Zee | 7 | 5 | [24 empty] | 30 | 0.3
1658 | #NO MATCH | 2022-06-13 | Naza | a sunny day 6 guys from 7am to 6pm. east side 7 panels install from 7am to 2pm. north 14 panels install from 7am to 6pm. moving panels from grown level to level 7, 2pm to 6pm | Subcontractor | Rod Grove | false |  |  |  |  | 6 | 11 | false |  | suspended scafold, boom lift | false |  |  |  |  | Corrugated / Screen wall Other | [22 empty] | 21 | 54 | [18 empty] | moving panels | 12
20067 | BNA PROJECT 5 | 2022-06-13 | Daniel | 1 ground guy ( 8 hours ) cutting metal / passing material, 2 guys installing galvanized metal on columns (200 FT) ( 8 hours) | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 8 | false |  | 2- 85 FT BOOM | false
21082 | UTMC MOB | 2022-06-13 | Chad mccoy | I started my morning early going to the shop to load up DCA 54 for Keith. I didn’t met the Alan Martin and Rainey At the hotel and they followed me to the Knoxville job. Once we got on site we started switching everything from my truck to Keith’s truck so that he could head to Virginia. Once I got him squared away and he got on the road we started getting the Bowman position moving the scaffolding where we need it broken down crates finding Panels that we need for elevations. I laser lined the back column to the front columns and then laid out from 6 inches off the concrete top to the top the canopy. This took a little while since there was no ground to pull off of and there was no way to easily line the front and back columns up left and right. We had to shoot on all the stud framing and then put strapping around it so that it would be sturdy and tight and not wobble when you land up against the Panels. | JWMCD Crew | Josh McPherson | true | The starter panels for both columns were different sizes one side was 2’ 2” the other side was 2’ 1”, This doesn’t make any sense because the distance from the concrete to the canopy is the same and the standoff from Concrete is the same. The Column Panels that we pulled out of the crate Were rolled out of square so to get these to engage we had to install it with termination clips and ratchet straps to hold it in place when we sprayed it off. I let alan and Martin install one column after I set the first two panels for elevAtion. I had to take there panels down bc the messed up the clips and it was all out of level. |  |  | Hot. 105 | 4 | 10 | false |  | 80 foot boom | false |  |  | 1 |  | ACM Layout Subgirt Zee | 10 | 8
1658 | #NO MATCH | 2022-06-12 | Naza padron | sunny day 10am to 5pm, incident occurred at 3:30pm a nut fell on the windshield of a parked car the installers were not using nuts on this day they think it may have fallen through the floor of the scaffold the scaffold was taken to level 1 to be cleaned completely. | Subcontractor | Rod Grove | false |  |  |  |  | 8 | 7 | false |  | 86' boom lift, suspended scaffold | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 58 | 56
1658 | #NO MATCH | 2022-06-11 | Naza | sunny day from 10am to 5pm | Subcontractor | Rod Grove | false |  |  |  |  | 8 | 7 | false |  | 86' boom lift, suspended scaffold | false |  |  |  |  | Other Tubing | [28 empty] | 96 | 35 | [12 empty] | moving material up to the roof using suspended scaffold | 21
20067 | BNA PROJECT 5 | 2022-06-10 | Daniel | 2 installing galvanized metal on columns 240 FT( 5 hours ) 1 ground guy ( 5 hours ) passing galvanized metal/ making cuts, then flew down our trash from the north side scaffold area for HP . ( 3 hours ) | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 8 | false |  | 2- 85FT BOOM | false
20067 | BNA PROJECT 5 | 2022-06-10 | Daniel | 1 ground guy(10 hours) putting clips on panels/ passing the panels . | JWMCD Crew | Marc Ribar | false |  |  |  |  | 4 | 10 | false |  | 2- 85FT BOOM | false |  |  |  |  | ACM Trim | 19 | 9 | [34 empty] | 90 | 1
20067 | BNA PROJECT 5 | 2022-06-09 | Daniel | Took the 85 FT BOOM to the north side parking lot. | JWMCD Crew | Marc Ribar | true | The delay was arrivals was open because of the CMA’s, they didn’t close it till after midnight because they didn’t want to back traffic up more. |  |  |  | 3 | 8 | false |  | 2- 85 FT BOOM | false
20067 | BNA PROJECT 5 | 2022-06-09 | Daniel | 3 guys (30 hours), did cleaning on the south side of the scaffolding, unloaded a truck of 5 crates, then took panels up to the north side scaffold . | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 10 | true | 5 crates of panels. | 2 - 85 FT BOOM, FORKLIFT | false
1658 | #NO MATCH | 2022-06-08 | Naza | sunny day 3 guys working on east side installing velly and missing panels | Subcontractor | Rod Grove | false |  |  |  |  | 3 | 10 | false |  |  | false |  |  |  |  | Genesis | [14 empty] | 9 | 30
20067 | BNA PROJECT 5 | 2022-06-08 | Daniel | 2 guys working on the columns (16 hours) installed 200FT, 1 ground guy (8 hours) cutting metal/ passing all the material . | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 8 | false |  | 2 -85FT BOOM | false
20067 | BNA PROJECT 5 | 2022-06-08 | Daniel | 3 guys caulking (30 hours) 39 joints so about 18 - 19 ft | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 10 | false |  | 85FT BOOM | false |  |  |  |  | Caulking
21082 | UTMC MOB | 2022-06-08 | Chad mccoy | We started today install Z’s on the upper rotunda and I started laying out z’s on the bottom canopy. Once Keith got all zs he could reach from the nearest side of the Canopy. He then started installing Panels. This role of Panels has been the worst set of panels to install with everything being out of level and out of square. | JWMCD Crew | Josh McPherson | true | The boom lift was down for over an hour because of A sensor that was on the basket Herc rentals came out And attempted to fix it but they could not fix it without genies 500 pound weights to recalibrate it. So only Keith And I can be in the basket and install because of the sensor saying that Kevin and Keith are overweight in the basket. The column panels that I put up and a lot of them still in the crates have dents in them from what looks like vise grips and then it has sporadic dents throughout the face of some of them that I do not know where they came from. But they are like this in the crate still crated Josh has videos |  |  | Partly cloudy | 3 | 11 | false |  | 80 foot boom | false |  |  |  |  | ACM Insulation Subgirt Zee | 14 | 9 | [24 empty] | 130 | 1
1658 | #NO MATCH | 2022-06-07 | Naza | istalling Zee's 80' to the concrete parapet wall and channels 40'east side level 29, delivery 4 Crates | Subcontractor | Rod Grove | false |  |  |  |  | 2 | 10 | true | 4 Crates stainless steel panels |  | false
20067 | BNA PROJECT 5 | 2022-06-07 | Daniel | worked on the north and south columns installed (400 FT galvanized metal) | JWMCD Crew | Marc Ribar | false |  |  |  |  | 4 | 8 | false |  | 85 FT BOOM | false
21082 | UTMC MOB | 2022-06-07 | Chad mccoy | We started our morning putting Zs on. So that we could continue installing panels and installation. Concrete was going on today Lois and underneath the canopy so access to certain parts of the rotunda was limited. | JWMCD Crew | Josh McPherson | true | In the morning we had storms that was off and on. We also had concrete going on below us and underneath the canopy so concrete trucks we’re all around the higher canopy. We battled the vertical joints on the panels today we could not figure out why one side the lineup and the other side would hangover so we started digging into the problem and we found that the top and the bottom part of the panels on a horizontal measurement or different links the bottom left-hand side and some of the top right hand side or out of square some of them are out of square 3/16 so we will close the joint at the top and still have a half inch joint at the bottom and still be overhanging |  |  | Storms in the am | 3 | 8 | false |  | 80 foot boom | false |  |  |  |  | ACM Insulation Subgirt Zee | 13 | 7 | [24 empty] | 195 | 1
1658 | #NO MATCH | 2022-06-06 | Naza | 7am to 5pm 2 guys moving panels to the roof | Subcontractor | Rod Grove | false |  |  |  |  | 2 | 10 | false |  | suspended scaffold | false |  |  |  |  | Other | [42 empty] | moving material to the roof | 20
20067 | BNA PROJECT 5 | 2022-06-06 | Daniel | 2 guys moved material around on the south side of the airport . | JWMCD Crew | Marc Ribar | true | It was around 12 when hp told all lifts to come down, because it storming and a lot of lighting and thunder in the area. Waited until 3 am it lasted all night so I just put the lift up . |  |  | thunder/ lightning | 2 | 8 | false |  | 2 -85FT BOOM, FORKLIFT | false
21071 | Google NBY-HUB 1 | 2022-06-06 | Naza | 7am to 3pm, work was not continued until 5pm due to rain. | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 8 | false |  | 40' boom | false |  |  |  |  | Insulation Other | [26 empty] | 1200 | 12 | [14 empty] | 10 channels and 50 clips were put it together | 4
21082 | UTMC MOB | 2022-06-06 | Chad mccoy | We started today installing insulation and striping where we need it for the panels to be attached to the wall. this is a continuation that Has to be done prior to the panels being hung. We are not hanging the insulation and leaving it open we are only installing it as the panels go in the wall that way it doesn’t blow out. | JWMCD Crew | Josh McPherson | true | The radius rotunda panels we are rolled in the shop. Some of these panels are over the road where the left and the right side of the panel will touch the wall in the middle of the panel will be close to 8 inches out from the wall. We are having to adjust these panels in the field to make it work |  |  | Partly cloudy | 3 | 10 | true | I brought strapping an Z the back from the shop | 80 foot boom | false |  |  |  |  | ACM Insulation | 22 | 9 | [24 empty] | 180 | 1
1658 | #NO MATCH | 2022-06-05 | Naza | starting at 10am and ending at 5pm. 14 hours doing Hat channels, 56 hours installing panels | Subcontractor | Rod Grove | false |  |  |  |  | 10 | 7 | false |  | suspended scaffold, baker scaffold | false |  |  |  |  | Corrugated / Screen wall Hat Channel | [22 empty] | 132 | 56 | [10 empty] | 160 | 14
21023 | Northgate Plaza - Phase 3 | 2022-06-05 | Fredy Rodriguez | this day the area was cleaned, the garbage was thrown away and the plastic was removed from the panels and silecon was put on areas I also have a delay because they did not send many clips I also do not have trim they sent me to change a panel but they did not tell me and I know you need to buy a ladder we are unemployed due to lack of trim and clip they sent very little | Subcontractor | Steve Fudge | false |  |  |  |  | 3 | 30 | false |  | Boom lif | false
1658 | #NO MATCH | 2022-06-04 | Naza | started working from 10am to 5pm | Subcontractor | Rod Grove | false |  |  |  |  | 10 | 7 | false |  | suspended scaffold, baker scaffold | false |  |  |  |  | Hat Channel Subgirt Zee | [30 empty] | 380 | 35 |  |  | 360 | 35
21023 | Northgate Plaza - Phase 3 | 2022-06-04 | Fredy Rodriguez | 230 feet of Z were also installed on this day | Subcontractor | Steve Fudge | false |  |  |  |  | 3 | 30 | false |  | Boom lif | false |  |  |  |  | ACM | 10 | 3
1658 | #NO MATCH | 2022-06-03 | Naza |  | Subcontractor | Rod Grove | false |  |  |  |  | 2 | 10 | false |  | suspended scaffold | false |  |  |  |  | Other | [42 empty] | moving material from level 7 to the roof from 7 am to 5pm | 20
20067 | BNA PROJECT 5 | 2022-06-03 | Daniel | 2 guys framing south columns (16 hours) 250 FT of galvanized metal | JWMCD Crew | Marc Ribar | false |  |  |  |  | 2 | 8 | false |  | 85FT BOOM | false
20067 | BNA PROJECT 5 | 2022-06-03 | Daniel |  | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 10 | false |  | 85FT BOOM | false |  |  |  |  | ACM Trim | 22 | 9 | [34 empty] | 45 | 1
21023 | Northgate Plaza - Phase 3 | 2022-06-03 | Fredy Rodriguez | 250 feet of Z were also installed on this day | Subcontractor | Steve Fudge | false |  |  |  |  | 3 | 30 | false |  | Boom lif | false |  |  |  |  | ACM | 12 | 3
21071 | Google NBY-HUB 1 | 2022-06-03 | Naza Padron | installing insulation from 7am to 5pm no delays. | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 10 | false |  | 40' boom | false |  |  |  |  | Insulation | [26 empty] | 1200 | 20
1658 | #NO MATCH | 2022-06-02 | Naza Padron | 2 guys moving up material to the roof from 7am to 5pm grown to level 7 | Subcontractor | Rod Grove | false |  |  |  |  | 2 | 10 | false |  | 86' boom | false |  |  |  |  | Other | [42 empty] | moving material up to level 7 | 10
20067 | BNA PROJECT 5 | 2022-06-02 | Daniel | 2 guys (16 hours) finished framing column all the way up on north side, started on the south side column ( 140 FT) | JWMCD Crew | Marc Ribar | false |  |  |  |  | 2 | 8 | false |  | 85 FT BOOM, | false
21009 | The Inn at Southhall | 2022-06-02 | Fredy Rodriguez | yesterday I was only able to install 5 panels I have spaces that lack material there is no control because there are no complete areas to be able to finish them I waste a lot of time waiting that is the list of panel numbers that I need | Subcontractor | Chris Ball | false |  |  |  |  | 3 | 21 | false |  | Boom lif | false |  |  |  |  | Genesis | [14 empty] | 5 | 3
21023 | Northgate Plaza - Phase 3 | 2022-06-02 | Fredy Rodriguez |  | Subcontractor | Steve Fudge | false |  |  |  |  | 3 | 36 | false |  | Boom lif | false |  |  |  |  | ACM | 11
21071 | Google NBY-HUB 1 | 2022-06-02 | Naza Padron | rainy day and problems with the lift, flat tire. the boom was out from 9am to 3:30pm | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 10 | false |  | 40' boom | false |  |  |  |  | Insulation Other | [26 empty] | 128 | 8 | [14 empty] | the workers were putting together clips and channels for 6 hours | 12
21023 | Northgate Plaza - Phase 3 | 2022-06-01 | Fredy Rodriguez |  | Subcontractor | Steve Fudge | false |  |  |  |  | 3 | 36 | false |  | Boom lif | false |  |  |  |  | ACM | 12 | 3
21061 | ATT Building Facade Rehab | 2022-06-01 | Fredy Rodriguez | this day 17 tubes were installed | Subcontractor | Josh McPherson | false |  |  |  |  | 3 | 10 | false |  | Swing stage and forklift | false
21071 | Google NBY-HUB 1 | 2022-06-01 | Naza Padron | sunny no delays installation from 7am to 5pm | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 10 | false |  |  | false |  |  |  |  | Insulation | [26 empty] | 1600 | 20
21082 | UTMC MOB | 2022-06-01 | Chad mccoy | We started today trying to figure out how to put the flashing on the wall with the wall being segmented. The studs are 12 inches apart so you can’t put a flat piece of flashing all the way around without modifying it to step and turn with the radius. So we cut down the flashing. And we left one side with a taper on it. I installed 70 of these 14 inch pieces. Four pieces at 53 inches. About 80 feet of peel and stick. 21 z’s at 28 inches, 4 Z’s at 40 inches, and 8Z’s at Full length | JWMCD Crew | Josh McPherson | true | It took us a little while to figure out how I wanted to install the flashing, The upper flashing cannot be installed due to the amount of upper cuts it’ll be but the lower flashing can be installed |  |  | Hot 90s | 3 | 10 | false |  | 80 foot zboom | false |  |  | 1.5 |  | Flashing Layout Subgirt Zee | [32 empty] | 110 | 6
20042 | JR GREEN | 2022-05-31 | Chad mccoy | We drove all the way to Covington Kentucky to install two panels for Jake. When we got there they were fiber cement and wood blocking that was already installed in its place so I made a phone call to figure out if that was supposed to stay in Jake’s said no so then we removed it. Upon measuring the panels panels or too big to even fit in the hole by 2 1/2 inches so one of the panels had to be cut around it down | JWMCD Crew | Chris Ball | true | The panels were too big to fit in the hole so I had to cut route one panel down but the panels were so scratched up on the peel face and there was a dent in one of the panels from the backside of the panel that we tried to rotate the panels to make it look the best on the wall but the scratches will probably be more likely Call Out |  |  | Hot. 91 | 2 | 4 | false |  |  | false |  |  |  |  | ACM | 2 | 3
21023 | Northgate Plaza - Phase 3 | 2022-05-31 | Fredy Rodriguez |  | Subcontractor | Steve Fudge | false |  |  |  |  | 3 | 30 | false |  | Boom lif | false |  |  |  |  | ACM | 8 | 3
21061 | ATT Building Facade Rehab | 2022-05-31 | Fredy Rodriguez | this day 12 tubes were installed | Subcontractor | Josh McPherson | false |  |  |  |  | 2 | 10 | true | this day I received a forklift | Swing stage and forklift | false
21071 | Google NBY-HUB 1 | 2022-05-31 | Naza Padron | good day to work, no delays installing insulation from 7am to 5pm | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 10 | false |  | 40' boom | false |  |  |  |  | Insulation | [26 empty] | 1280 | 20
21082 | UTMC MOB | 2022-05-31 | Chad mccoy | We got to the site this morning we met with Chris the GC, and then we started cleaning the lay down area. We started moving crates so that we can get to the trailer to clean up the groundwork and then when I talk to Josh Josh told me that we’d be back tomorrow to do the Z the flashing around the rotunda so then we cut some sections out for Josh then at the end of the day we packed everything up cleaned up the laydown area and headed to Cincinnati | JWMCD Crew | Josh McPherson | false |  |  |  |  | 4 | 3 | true | I brought flashing from mcdougal | 80 foot boom | false
21023 | Northgate Plaza - Phase 3 | 2022-05-30 | Fredy Rodriguez |  | Subcontractor | Steve Fudge | false |  |  |  |  | 3 | 36 | false |  |  | false |  |  |  |  | ACM | 10 | [20 empty] | 3
21029 | SCE Spine Center of Excellence | 2022-05-30 | Fredy Rodriguez |  | Subcontractor | Denis Usatenko | false |  |  |  |  | 3 | 30 | false |  |  | false |  |  |  |  | ACM | 24 | 3
1658 | #NO MATCH | 2022-05-29 | Naza Padron | Sunday we were allowed to work from 10am to 5pm | Subcontractor | Rod Grove | false |  |  |  |  | 8 | 7 | false |  | boom lift, suspended scaffold | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 44 | 35
21023 | Northgate Plaza - Phase 3 | 2022-05-29 | Fredy Rodriguez |  | Subcontractor | Steve Fudge | false |  |  |  |  | 3 | 36 | false |  | Boom lif | false |  |  |  |  | ACM | 12 | 3
21029 | SCE Spine Center of Excellence | 2022-05-29 | Fredy Rodriguez |  | Subcontractor | Denis Usatenko | false |  |  |  |  | 3 | 30 | false |  |  | false |  |  |  |  | ACM | 45 | 3
1658 | #NO MATCH | 2022-05-28 | Naza Padron | On Saturday we are only allowed to work from 10am to 5pm | Subcontractor | Rod Grove | false |  |  |  |  | 4 | 7 | false |  | boom lify & suspended scaffold | false |  |  |  |  | Corrugated / Screen wall | [22 empty] | 36 | 28
20067 | BNA PROJECT 5 | 2022-05-28 | Naza Padron | day shift air weve south side 7am to 3pm | Subcontractor | Marc Ribar | false |  |  |  |  | 5 | 8 | false |  |  | false |  |  |  |  | ACM | 22 | 40
21023 | Northgate Plaza - Phase 3 | 2022-05-28 | Fredy Rodriguez |  | Subcontractor | Steve Fudge | false |  |  |  |  | 3 | 36 | false |  | Boom lif | true |  |  |  |  | ACM | 12
21029 | SCE Spine Center of Excellence | 2022-05-28 | Fredy Rodriguez |  | Subcontractor | Denis Usatenko | false |  |  |  |  | 3 | 30 | false |  |  | false |  |  |  |  | ACM | 12 | 3
21061 | ATT Building Facade Rehab | 2022-05-28 | Fredy Rodriguez | this day we installed 12 tubes | Subcontractor | Josh McPherson | false |  |  |  |  | 4 | 40 | false |  |  | false
1658 | #NO MATCH | 2022-05-27 | Naza Padron | rainy day, the guys uploaded material to the roof every time it stopped raining | Subcontractor | Rod Grove | false |  |  |  |  | 4 | 12 | true | 9 crates of panels | boom lift & suspended scaffold | false |  |  |  |  | Corrugated / Screen wall Other | [22 empty] | 16 | 32 | [18 empty] | moving panels to the roof from grown level from 7am to 11am | 16
21029 | SCE Spine Center of Excellence | 2022-05-27 | Fredy Rodriguez |  | Subcontractor | Denis Usatenko | false |  |  |  |  | 3 | 36 | false |  |  | false |  |  |  |  | ACM | 38 | 3
1658 | #NO MATCH | 2022-05-26 | Naza Padron | sunny day noting to delay production | Subcontractor | Rod Grove | false |  |  |  |  | 7 | 10 | false |  | 86' boom & suspended scaffold | false |  |  |  |  | Corrugated / Screen wall Other | [42 empty] | 4 guys moving screen wall panels to the roof from grown level, 3 guys fixing panels joints at east side garage level 1 to 6 | 70
20067 | BNA PROJECT 5 | 2022-05-26 | Naza Padron | night shift air weve south side, from 8pm to 10pm all the guys move panels up to the scaffold, installing panels from 10pm to 4am | Subcontractor | Marc Ribar | false |  |  |  |  | 6 | 10 | false |  |  | false |  |  |  |  | ACM | 20 | 60
21082 | UTMC MOB | 2022-05-26 | Chad mccoy | We picked up today where we left off on the ACm. We continued running the perimeter panels until we got to the last corner and then we did the soffit panels and then we moved to the coping Panels. After those are done we install the last four panels on the back side of the tall canopy. I had 7 Panels that had to be modified for either cuts around columns or to fit the gutter or the coping cap that had to be modified for the extra build out on the decking. Once we installed our last panel we started caulking and peeling Panels. See delays | JWMCD Crew | Josh McPherson | true | It rained and stormed off and on all day. But the biggest delay today was once we were peeling the panels we noticed at the ACM was two different colors. As soon as this was noticed I got on the phone calling Josh so we are trying to figure out what happens tomorrow we are going in to pull all the panels to get a count on was installed and what’s the wrong color |  |  | Rain off and on all day | 3 | 8 | false |  | 60 foot boom | false |  |  | 1 |  | ACM Layout | 22 | 6
21082 | UTMC MOB | 2022-05-25 | Chad mccoy | I we started our morning starting the second canopy. First thing I had to do was line everything up so that I could lay out the first two panels to be cut around the beam. Once that was laid out we continue down the wall to the second beam. Once that beam cut out plus a conduit, We went to the wraparound quarter panel that wrapped into the gutter. This panel build was completely wrong so it had to be modified to fit the wall which also changed the coping at the top which also had to be modified at the end of the day. All the gather six panels had to be cut or modified to fit the structure | JWMCD Crew | Josh McPherson | true | The panel that wrap the back of the canopy that goes where the gutter goes had a leg that turned in that was 8 inches too long plus I had to cut 2 1/2 inches out for the wood blocking to protrude into facia panel because it stuck off the wall 2 1/2 inches and our panel is 2 1/4 depth |  |  | Partly cloudy | 3 | 8 | false |  | 60 foot boom | false |  |  | 1 |  | ACM Layout | 30 | 7
1658 | #NO MATCH | 2022-05-24 | Ivan fabela | material was received and the climb to the 7th floor began | Subcontractor | Rod Grove | false |  |  |  |  | 4 | 40 | true | Panels | Bum lift | false
20067 | BNA PROJECT 5 | 2022-05-24 | Naza Padron | Night Shift | Subcontractor | Marc Ribar | false |  |  |  |  | 2 | 7 | false |  | 86 boom lift | false |  |  |  |  | Hat Channel | [34 empty] | 370 | 14
21029 | SCE Spine Center of Excellence | 2022-05-24 | Fredy Rodriguez |  | Subcontractor | Denis Usatenko | false |  |  |  |  | 3 | 36 | false |  | Boom lif | false |  |  |  |  | ACM | 32 | 3
21071 | Google NBY-HUB 1 | 2022-05-24 | Naza Padron | Sunny day no delays. 86 Channels, 322 Thermal Clips. M2B | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 10 | false |  | 40' boom lift | false
21082 | UTMC MOB | 2022-05-24 | Chad mccoy | We started the day picking up where we left off yesterday and we finished the smaller canopy today. We had to install 27 panels, two of those panels head cuts for an I-beam and a drain pipe. Like I said and delays all day today we had to work around the groundwork. There is a 2 1/2 inch burst on one of the walls where the panels met up with the Eephus. Josh was informed about this in the GC called it out. Cajun got here at 4:40 this evening we had to unload four skids of panels one skid of flashing NZ’s and two pallets of Rockwool | JWMCD Crew | Josh McPherson | true | The ground crew was laying gravel today so we had to work around dump trucks skid steers and a compactor |  |  | Partly cloudy | 3 | 10 | true | 4 crates of panels. 1 crate of flashing and z 2 skids of rockwool | 64 boom | false |  |  | 1 |  | ACM Layout | 27 | 8
21009 | The Inn at Southhall | 2022-05-23 | Fredy Rodriguez | we continue waiting for more material to be able to start well | Subcontractor | Chris Ball | false |  |  |  |  | 3 | 18 | false |  | Boom lif | false |  |  |  |  | Genesis | [14 empty] | 9 | 3
21029 | SCE Spine Center of Excellence | 2022-05-23 | Fredy Rodriguez |  | Subcontractor | Denis Usatenko | false |  |  |  |  | 3 | 36 | false |  | Boom lif | false |  |  |  |  | ACM | 38 | 3
21061 | ATT Building Facade Rehab | 2022-05-23 | Fredy Rodriguez | 25 tubes were installed this day | Subcontractor | Josh McPherson | false |  |  |  |  | 5 | 50 | true | this day i received horizontal angles |  | false
21071 | Google NBY-HUB 1 | 2022-05-23 | Naza Padron | Sunny day no delays. 78 Channels, 282 Thermal Clips. | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 10 | false |  | 40' boom lift | false |  |  |  |  | Other | [43 empty] | 20
21082 | UTMC MOB | 2022-05-23 | Chad mccoy | We started this morning getting to the side and walking the site with the GC. He showed us how to get into the gate and where our laydown areas need to be due to gravel going in during the times that we’re working. Keith and I checked as many areas as we could and laid out as many areas as we could until the boom lift arrived. What’s a boom lift arrived we continued laying out all the rotunda until I realized it had to have 2 inch insulation and Z’s then we moved to the canopies. Cajun arrived and we got the lull And we started unloading the panels in the crates. We have a certain area that we had to put everything due to the gravel that’s going down. Then we started inventorying all the stuff that came and we realize that three-quarter inch screws for the crib tonight not arrive. Then we started pulling Panels for the lower canopy due to Z and insulation not coming till tomorrow. I am not installing a tight Fit corners the way that they’re supposed to do to the imperfections in the structure and how long it takes to get it right we are building these together on the ground and then installing them on the building | JWMCD Crew | Josh McPherson | true | The time that the panels and the boom lift arrived or later in the day, two panels had to be cut around an I-beam in a gutter and then the joint was in the middle of it. The way these panels are created in the crates we have to take 20 maybe even 25 panels out at some point to get to one panel these panels are all taped together and they are so tight in the crate that just to get a panel loose do you have to decrate half the crate |  |  | It rained all day | 3 | 10 | true | Four crates of Panels, two crates of accessory and a boom lift | 64 boom | false |  |  | 4.5 |  | ACM Layout | 4 | 3
1658 | #NO MATCH | 2022-05-22 | Fredy Rodriguez | 36 Chanel were also installed to be able to put screws to the panels | Subcontractor | Rod Grove | false |  |  |  |  | 6 | 48 | false |  | Swing stage and boom lif | false |  |  |  |  | Plate |  |  | 36 | 6
21029 | SCE Spine Center of Excellence | 2022-05-22 | Fredy Rodriguez | I need 9 panels in this area I'll send you the list here I can't find them | Subcontractor | Denis Usatenko | true | we waited 3 hours for the rain to pass |  |  |  | 3 | 21 | false |  | Boom lif | false |  |  |  |  | ACM | 15 | 3
1658 | #NO MATCH | 2022-05-21 | Iván fabela |  | Subcontractor | Rod Grove | false |  |  |  |  | 6 | 60 | false |  | Bum lift and swing stage | false |  |  |  |  | Hat Channel Overly Roof Panel | [12 empty] | 26 | 60 | [20 empty] | 20 | 60
1658 | #NO MATCH | 2022-05-21 | Iván Favela |  | Subcontractor | Rod Grove | false |  |  |  |  | 6 | 60 | false |  | Swing stage and bum lift | false |  |  |  |  | Hat Channel Overly Roof Panel | [12 empty] | 26 | 60 | [20 empty] | 20 | 60
21029 | SCE Spine Center of Excellence | 2022-05-21 | Fredy Rodriguez |  | Subcontractor | Denis Usatenko | false |  |  |  |  | 3 | 36 | false |  | Boom lif | false |  |  |  |  | ACM | 29 | 3
21029 | SCE Spine Center of Excellence | 2022-05-20 | Fredy Rodriguez |  | Subcontractor | Denis Usatenko | false |  |  |  |  | 3 | 36 | false |  | Boom lif | false |  |  |  |  | ACM | 21 | 3
21061 | ATT Building Facade Rehab | 2022-05-20 | Fredy Rodriguez | this day we installed 27 tubes in the AT&T | Subcontractor | Josh McPherson | false |  |  |  |  | 7 | 56 | false |  | Swing stage | false
21071 | Google NBY-HUB 1 | 2022-05-20 | Naza Padron | from 7am to 2pm we install panels at mocup,from 2pm to 5pm 130 thermal clips, 26 channels . | Subcontractor | Steve Fudge | false |  |  |  |  | 3 | 10 | false |  | 40' boom lift | false |  |  |  |  | Other | [42 empty] | 130 clips & 26 channels, mocup. | 30
21029 | SCE Spine Center of Excellence | 2022-05-19 | Fredy Rodriguez |  | Subcontractor | Denis Usatenko | false |  |  |  |  | 3 | 36 | false |  | Bom lif | false |  |  |  |  | ACM | 25 | 3
21060 | Vantage VA 13 | 2022-05-19 | Nathan Wall | We have caught the site. 2 weeks wait for ACM. Roof screen wall is complete minus top sheet, which is a cut in, we are waiting for decking so we can reach from inside. There is still some "Z" and insulation for the south side, but they are doing work to the loadeding dock and still have to finish framing the wall. We will have to come back to it no matter what. There is a 4 week outlook for the gen. yards, before we can start on them. we are going to be off site for two weeks, instead off staying and spinning our wheels. Nothing installed today just cleanup. | Subcontractor | Steve Fudge | false |  |  |  |  | 3 | 5 | false |  | 85' boom lift | false |  |  |  |  | Other | [42 empty] | Cleanup, nothing installed. | 15
21068 | Walt Massey Nissan | 2022-05-19 | marvin | changing damages panels | Subcontractor | Denis Usatenko | false |  |  |  |  | 3 | 10 | false |  | scissors lift | false |  |  |  |  | ACM | 26 | 30
21071 | Google NBY-HUB 1 | 2022-05-19 | Naza Padron | from 7am we install channels and k, thermal clips. from 10am to 5pm we did work doing the mocup. | Subcontractor | Steve Fudge | false |  |  |  |  | 3 | 10 | false |  | 40' boom lift | false |  |  |  |  | Other | [42 empty] | 175 clips & 35 channels, mocup. | 30
1639 | #NO MATCH | 2022-05-18 | Naza Padron | N/A | Subcontractor | Chris Ball | false |  |  |  |  | 3 | 5 | false |  | SCISSOR LIFT | false |  |  |  |  | Other | [42 empty] | Reinstall stainless steel panels back in the lobby area, Filling in trims of the lobby elevations. | 15
1639 | #NO MATCH | 2022-05-18 | Naza Padron | could not remove panels from vestibule need to remove light covers until the week of May 23. | Subcontractor | Chris Ball | false | [6 empty] | false |  |  | false |  |  |  |  | Other
1658 | #NO MATCH | 2022-05-18 | Ivan Favela | Backer rod and sealant and the rubber was removed from the panels | Subcontractor | Rod Grove | false |  |  |  |  | 4 | 40 | false |  | Swing stage and bumlift | false
21009 | The Inn at Southhall | 2022-05-18 | Fredy Rodriguez | 40 feet of Drip Trim were also installed. and 40 feet of Starter J installed | Subcontractor | Chris Ball | false |  |  |  |  | 3 | 30 | false |  |  | false |  |  |  |  | Genesis | [14 empty] | 11 | 3
21029 | SCE Spine Center of Excellence | 2022-05-18 | Fredy Rodriguez | 80 feet of J trim was installed | Subcontractor | Denis Usatenko | false |  |  |  |  | 3 | 30 | true | Acm panel ,screws and shim | Boom lif | false |  |  |  |  | ACM | 14 | 3
21060 | Vantage VA 13 | 2022-05-18 | Nathan Wall | Installed 7 sheets of perforated on roof screen wall. Cut back on man power, we are caught up on the site. Waiting on glass man to sit sills, probably going to be 2 weeks, before we need to start ACM. They are still doing concrete work on the south side, that stops us from working on the south wall. | Subcontractor | Steve Fudge | false |  |  |  |  | 3 | 10 | false |  | 85' boom lift | false |  |  |  |  | Perforated
1639 | #NO MATCH | 2022-05-17 | Naza Padron | N/A | Subcontractor | Chris Ball | false |  |  |  |  | 3 | 10 | false |  | SCISSOR LIFT | false |  |  |  |  | Other | [42 empty] | Review the panels with the Architect, Reinstall stainless steel panels back in the lobby area. | 30
1658 | #NO MATCH | 2022-05-17 | Fredy Rodriguez | the plastic was removed from the panels | Subcontractor | Rod Grove | false |  |  |  |  | 3 | 30 | false |  | Swing stage and boom lif | false
20067 | BNA PROJECT 5 | 2022-05-17 | Daniel | 3 guys laying waterproof 335 FT( 23 hours ) 2 guys laying waterproof/ smoothing it out, 1 guy rolling glue/ passing waterproof . | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 8 | false |  | 85 FT BOOM | false |  |  |  |  | Flashing | [32 empty] | 150 | 1
21029 | SCE Spine Center of Excellence | 2022-05-17 | Fredy Rodriguez | we were standing waiting for material and this day did not come | Subcontractor | Denis Usatenko | true | we were standing waiting for material and this day did not come |  |  |  | 3 |  | false |  | Boom lif | false
21060 | Vantage VA 13 | 2022-05-17 | Nathan Wall | Still not allowed in the building, but was able to get to the roof. Installed 17 sheets of perforated on the roof screen wall. Not able to work on the south side Still doing concrete work. Two guys went to QTS. | Subcontractor | Steve Fudge | false |  |  |  |  | 4 | 10 | false |  | 85' boom lift | false |  |  |  |  | Perforated
1639 | #NO MATCH | 2022-05-16 | Naza Padron | N/A | Subcontractor | Chris Ball | false |  |  |  |  | 3 | 10 | false |  | SCISSOR LIFT | false |  |  |  |  | Other | [42 empty] | Reinstall stainless steel panels back in the lobby area. | 30
1658 | #NO MATCH | 2022-05-16 | Fredy Rodriguez | Backer Rod and Sealant were installed bBacker Rod and Sealant were installed between the windows and panel and 23 tubes of 16 feet were cut | Subcontractor | Rod Grove | false |  |  |  |  | 7 | 70 | false |  | Swing stage and boom lif | false
20067 | BNA PROJECT 5 | 2022-05-16 | Daniel | 3 guys installing waterproof 275 FT(23 hours)2 guys laying waterproof/ smoothing it out, 1 guy rolling glue/ passing waterproof | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 8 | false |  | 85FT BOOM | false |  |  |  |  | Flashing | [32 empty] | 140 | 1
21009 | The Inn at Southhall | 2022-05-16 | Fredy Rodriguez | 50 feet of J finish and 50 feet of JAT corner trim and 25 feet of Corner trim and 40 feet of Drip Trim were also installed. | Subcontractor | Chris Ball | false |  |  |  |  | 3 | 30 | false |  | Bom lif | false |  |  |  |  | Genesis | [14 empty] | 20 | 3
21060 | Vantage VA 13 | 2022-05-16 | Nathan Wall | Today is a bad day, there is a odor in the building. Hitt is not letting anyone in or on the building. Can't be on the roof to work, can't go through the building to get access to the 2nd floor for the south side work. They are still doing concrete work on the south side so we can't use a boom lift. We are shut down. | Subcontractor | Steve Fudge | true | Odor in the building no one can access it. |  |  |  | 6 | 2 | false |  | 85' boom lift | false
1639 | #NO MATCH | 2022-05-15 | Naza Padron | N/A | Subcontractor | Chris Ball | false |  |  |  |  | 3 | 10 | false |  | SCISSOR LIFT | false |  |  |  |  | Other | [42 empty] | Reinstall stainless steel panels back. | 40
1658 | #NO MATCH | 2022-05-15 | Fredy Rodriguez | Backer Rod and Sealant were installed between the windows and panel and it was cleaned on the roof | Subcontractor | Rod Grove | false |  |  |  |  | 5 | 40 | false |  | Swing stage and boom lif | false
1658 | #NO MATCH | 2022-05-15 | Fredy Rodriguez | Backer Rod and Sealant were installed between the windows and panel and it was cleaned on the roof | Subcontractor | Rod Grove | false |  |  |  |  | 5 | 40 | false |  | Swing stage and boom lif | false
1639 | #NO MATCH | 2022-05-14 | Naza Padron | N/A | Subcontractor | Chris Ball | false |  |  |  |  | 4 | 10 | false |  | SCISSOR LIFT | false |  |  |  |  | Other | [42 empty] | Remuve damaged panels. | 40
1658 | #NO MATCH | 2022-05-14 | Fredy Rodriguez | Backer Rod and Sealant were installed between the windows and panel and more screws were put into the panels and 20 clips were installed | Subcontractor | Rod Grove | false |  |  |  |  | 7 | 56 | false |  | Swing stage and boom lif | false
1658 | #NO MATCH | 2022-05-14 | Fredy Rodriguez | Backer Rod and Sealant were installed between the windows and panel and more screws were put into the panels and 20 clips were installed | Subcontractor | Rod Grove | false |  |  |  |  | 7 | 56 | false |  | Swing stage and boom lif | false
1639 | #NO MATCH | 2022-05-13 | Naza Padron | N/A | Subcontractor | Chris Ball | true |  |  |  |  | 2 | 4 | false |  | N/A | false |  |  |  |  | Other | [42 empty] | removed stainless steel panels that were already instaled | 8
1639 | #NO MATCH | 2022-05-13 | Naza Padron | N/A | Subcontractor | Chris Ball | true |  |  |  |  | 2 | 6 | false |  | N/A | false |  |  |  |  | Other | [42 empty] | replacing panels with scratches | 12
1658 | #NO MATCH | 2022-05-13 | Fredy Rodriguez | Backer Rod and Sealant were installed between the windows and panel and 6 16-foot tubes and 14 clips were installed | Subcontractor | Rod Grove | false |  |  |  |  | 7 | 70 | true | 13 plate | Swing stage and boom lif | false
20067 | BNA PROJECT 5 | 2022-05-13 | Daniel | 3 guys waterproofing 260 FT( 23 hours) 2 laying waterproof/ smoothing it out, 1 rolling the glue/ keeping area clean . | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 8 | false |  | 85ft boom | false |  |  |  |  | Flashing | [32 empty] | 110 | 1
21010 | 17th & Grand | 2022-05-13 | Fredy veliz | Job is complete except for 2 panels on the north terrace hand rail,m for missing glass | Subcontractor | Denis Usatenko | [5 empty] | 6 | 8.5 |  |  | Swing stage boom lift , forklift | [5 empty] | ACM Other | 1 | 4 | [40 empty] | Caulking in the coping , punch items ,caulking hand rail panels | 47
21060 | Vantage VA 13 | 2022-05-13 | Nathan Wall | Hung 12 sheets of perforated, Hitt is concerned we are moving to quickly. Asked if we could take the week of the 23rd off, don't plan to. Talked with Fudge today so we can try and get a truck with Flashing that week on Monday. It rained on and off this morning. | Subcontractor | Steve Fudge | false |  |  |  |  | 6 | 8 | false |  | 85' boom lift | false |  |  |  |  | Perforated
21071 | Google NBY-HUB 1 | 2022-05-13 | Rodney Oliveros | N/A | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 8 | false |  | 40' boom lift | false |  |  |  |  | Other | [42 empty] | 86 Channels, 430 Clips | 16
1639 | #NO MATCH | 2022-05-12 | Naza Padron | N/A | Subcontractor | Chris Ball | true |  |  |  |  | 2 | 6 | true | 1 crate stainlesteel panels | N/A | false |  |  |  |  | Other | [42 empty] | removed stainless steel panels that were already instaled | 12
20067 | BNA PROJECT 5 | 2022-05-12 | Daniel | 3 guys (22 hours) laying waterproof 200 FT, 2 guys laying waterproof / smoothing it out, 1 guy passing waterproof/ rolling glue . | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 8 | false |  | 85FT BOOM | false |  |  |  |  | Flashing | [32 empty] | 250 | 2
21009 | The Inn at Southhall | 2022-05-12 | Fredy | This day, apart from Genesis, 40feet of StarterJ and 40 feet of Drip trim and 40 feet of J Corner trim were installed. | Subcontractor | Chris Ball | true | I don't have the complete material |  |  |  | 5 | 55 | true | ,screws and shim and flashing | Boom lif | false |  |  |  |  | Genesis | [14 empty] | 10 | 2
21010 | 17th & Grand | 2022-05-12 | Fredy veliz | South west & south east corner Alignment is complete | Subcontractor | Denis Usatenko | [5 empty] | 4 | 10 |  |  | Swing stage , boom lift , forklift | [5 empty] | Other | [42 empty] | Fixing corners in the south west and east ,Finish caulking at the elevator entry , caulking hand rail panels | 40
21060 | Vantage VA 13 | 2022-05-12 | Nathan Wall | Installed 14 sheets of perforated on the roof. Installed 832 square feet of insulation on the south side. | Subcontractor | Steve Fudge | false |  |  |  |  | 6 | 10 | false |  | 85' boom lift | false |  |  |  |  | Insulation Perforated | [26 empty] | 832 | 30
21071 | Google NBY-HUB 1 | 2022-05-12 | Rodney Oliveros | N/A | Subcontractor | Steve Fudge | false |  |  |  |  | 3 | 10 | false |  | 40' boom lift | false |  |  |  |  | Other | [42 empty] | 77 Vertical Channels and 385 Clips at 1A west & South | 30
20067 | BNA PROJECT 5 | 2022-05-11 | Daniel | 3 guys laying waterproof (20hours) 140FT, 2 guys laying waterproof/ smoothing it out, 1 guy passing waterproof/ rolling glue . 3 guys bringing material up (3 hours) | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 8 | false |  | 85FT BOOM | false |  |  |  |  | Flashing | [32 empty] | 80 | 1
21010 | 17th & Grand | 2022-05-11 | Fredy veliz | We complete with the west (leak fix) and moved the stage to the south west corner to fix the corner panel | Subcontractor | Denis Usatenko | [5 empty] | 7 | 12 |  |  | Swing stage ,boom lift,forklift | [5 empty] | ACM Other | 8 | 18 | [40 empty] | Installed panels back on the west side caulking interior panels caulking elevator entry | 102
21060 | Vantage VA 13 | 2022-05-11 | Nathan Wall | Installed 11 sheets of perforated on the roof. Installed 800 square feet of insulation on the Southside. Two guys went to QTS to demo panels. | Subcontractor | Steve Fudge | false |  |  |  |  | 4 | 10 | false |  | 85' boom lift | false |  |  |  |  | Insulation Perforated | [26 empty] | 800 | 20
21071 | Google NBY-HUB 1 | 2022-05-11 | Rodney Oliveros | N/A | Subcontractor | Steve Fudge | false |  |  |  |  | 3 | 10 | true | 40" boom lift | 40' boom lift | false |  |  |  |  | Other | [42 empty] | 48 Vertical Channels and 240 Clips at 1A north | 30
20067 | BNA PROJECT 5 | 2022-05-10 | Dillon Bowman |  | JWMCD Crew | Marc Ribar | true | IMP: IAF Substrate Not Ready - ACM: (Area B) Airwave Substrate Not Ready - RPS: (Area A) Waterproof Membrane Installation - Completed to Corner, Stopped per Adrian(HP) - RPS: (Area B) Waiting on Inspection - Roof Panels |  |  | Sunny: High80, Low 55 |  |  | false |  |  | false
21010 | 17th & Grand | 2022-05-10 | Fredy veliz | Today we removed the panels to Check for on the west side in the investigation was found the leak, after removing panels and insulation me and David found the that reason for the was a improper installation of their peeling stick flashing installed by alpha the water proof has been fixed we gonna procede to re install the panels tomorrow and make the change orders for jedunn. Roofers laying ladder on the panels elevator entry to work on the canopy | Subcontractor | Denis Usatenko | [5 empty] | 7 | 10 |  |  | Swing stage boom lift forklift | [5 empty] | ACM Other | 2 | 5 | [40 empty] | Caulking west hand rail outside Caulking interior panels caulking windows L9 East ,house keeping, punch items removing panels for leak investigation | 65
21060 | Vantage VA 13 | 2022-05-10 | Nathan Wall | There will be zero tolerance for the use of "platform " ladders. South loadeding dock is going to open up on the 19th. Installed 17 sheets of perforated. Installed "z" on Southside 41 sticks of it. | Subcontractor | Steve Fudge | false |  |  |  |  | 6 | 10 | false |  | 85' boom lift | false |  |  |  |  | Perforated Subgirt | [30 empty] | 410 | 30
21010 | 17th & Grand | 2022-05-09 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 7 | 10.5 |  |  | Swing stage,boom lift ,forklift | [5 empty] | ACM Other | 34 | 45 | [40 empty] | Caulking,house keeping,removing panels for hand rail glass replacement | 28
21060 | Vantage VA 13 | 2022-05-09 | Nathan Wall | losing house power for a week. Installed 14 sheets of perforated. Started installing "z" on Southside, can't put a boom lift there because of concrete, used a scissor lift. | Subcontractor | Steve Fudge | false |  |  |  |  | 6 | 10 | false |  | 85' boom lift | false |  |  |  |  | Perforated Subgirt | [30 empty] | 400 | 30
20042 | JR GREEN | 2022-05-06 | Chad mccoy | We picked up at the beginning of the day continuing to install panels in between the storms that were coming through. We installed all the panels and finished out the trim work and tried to do as much of the caulking as we could as the rain was hitting and missing us. One panel had to be cut and routed to fit because it was sent to the site raw. We went through about one case of caulking trying to finish up but with the rain it’s kinda hard to caulk in the rain you have to dry the section and then try and caulk it but if your caulk in the rain it could have a chance of failing so we had to stop and finish it the next morning | JWMCD Crew | Chris Ball | true | It rained off and on all day at points I was lightning. Besides the rain when we got to the site usually there is a box full of shims and screws and color match screws for the panel excursions it’s just a box of accessories that goes for the job. This job had no shims, had no panel screws, had no screws to put it on the wall, I had to rob screws out of each panel just to install the excursions that weren’t installed. I also ran out of termination clips and I was on the verge of running out of female clips but once I noticed that they were getting slim I started spreading them out further beyond the install recommendations or we never would’ve gotten it installed. The flashing was also wrong but we got with Jack. And he got us more flashing |  |  | Rain and storms off and in | 2 | 9 | false |  | 45 boom | false |  |  |  |  | ACM Flashing | 13 | 7 | [30 empty] | 50 | 1
20067 | BNA PROJECT 5 | 2022-05-06 | Dillon Bowman |  | JWMCD Crew | Marc Ribar | true | IMP: IAF Substrate Not Ready - ACM: (Area B) Airwave Substrate Not Ready - RPS: (Area A) Waterproof Membrane Installation - Completed to Corner, Stopped per Adrian(HP) - RPS: (Area B) Waiting on Inspection - Roof Panels |  |  | Over Cast High 73, Low 63 |  |  | false |  |  | false
21010 | 17th & Grand | 2022-05-06 | Fredy veliz | We not working this weekend | Subcontractor | Denis Usatenko | [5 empty] | 8 | 9 |  |  | Swing stage boom lift forklift | [5 empty] | ACM Flashing Other | 25 | 30 | [30 empty] | 8 | 4 | [8 empty] | Caulking,finish prep to install panels level 9 below windows, remove caulking from concrete wall, weeps on the north side,take trash down | 38
21060 | Vantage VA 13 | 2022-05-06 | Joey Laxton | Rain day | Subcontractor | Steve Fudge | false |  |  |  |  | 6 | 18 | false |  | 85 foot boom | false
21060 | Vantage VA 13 | 2022-05-06 | Nathan Wall | no work performed rain out | Subcontractor | Steve Fudge | false |  |  |  |  | 5 | 2 | false |  | 85' boom lift | false
20042 | JR GREEN | 2022-05-05 | Chad mccoy | We started our day laying out the upper section while we awaited the arrival of the trim from Nashville. We trimmed out the window headers and install the panels and then when Dylan got here we started doing the perimeter metal everywhere that we needed it and then we continued hanging panels. Two panels had to be cut and routed because they were sent out raw. We were trying to get as much as we could get done but then the storms came in at the end of the day and kinda ruined our plan. The headers over the windows had to have a trim piece to go over it and the caps had to be folded around to make little boxes. This took a little while to get these right but they are done. Once all the tram was on then we had to peel and stick to seal the top parts of it | JWMCD Crew | Chris Ball | true | The window headers are2x6. So the outside dimension is 5 1/2 inches tall. The trim was 5 inches tall inside diameter. So we had to trim 1/2 inch off of every square window header |  |  | Storms at the end of the day | 2 | 12 | true | Trim, caulking, and peel and stick | 45 foot boom | false |  |  | 30 |  | ACM Flashing Layout Trim | 20 | 7.5 | [30 empty] | 75 | 2 |  |  | 55 | 2
20067 | BNA PROJECT 5 | 2022-05-05 | Dillon Bowman | Moved Boom Lift in North Laydown for HP | JWMCD Crew | Marc Ribar | true | IMP: IAF Substrate Not Ready - ACM: (Area B) Airwave Substrate Not Ready - RPS: (Area A) Waterproof Membrane Installation - Completed to Corner, Stopped per Adrian(HP) - RPS: (Area B) Waiting on Inspection - Roof Panels |  |  | Thunderstorms: High 84, Low 55 |  |  | false |  |  | false
21008 | 900 Church | 2022-05-05 | Marvin Blanco | everything was delivered today | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 10 | false |  |  | false |  |  |  |  | ACM | 11 | 30
21010 | 17th & Grand | 2022-05-05 | Fredy veliz | North elevation 185 boom lift is completed the remaining work is caulking the windows on L6 but to do those we need glass boom lift we did not done today because the rain | Subcontractor | Denis Usatenko | true | The rain started at 2:45 and was going for couple minutes and comeback |  |  | Rain in the afternoon | 8 | 11.5 | true | Angles for the north west hand rail panels | Swing stages boom lift,forklift | [5 empty] | ACM Other | 26 | 40 | [40 empty] | Caulking on the north side , prep to install panels on level 9 below windows | 52
21060 | Vantage VA 13 | 2022-05-05 | Joey Laxton | We caught the framer at this point and we moved insulation from ground level to level 2 | Subcontractor | Steve Fudge | false |  |  |  |  | 5 | 50 | false |  | 85 foot boom lift | false |  |  |  |  | Perforated
21060 | Vantage VA 13 | 2022-05-05 | Nathan Wall | Safety stand down at 8:30. Installed 14 sheets of perforated, move 7 pallets of insulation to the 2nd floor, per Hitt. | Subcontractor | Steve Fudge | false |  |  |  |  | 5 | 10 | false |  | 85' boom lift | false |  |  |  |  | Perforated
20067 | BNA PROJECT 5 | 2022-05-04 | Dillon Bowman |  | JWMCD Crew | Marc Ribar | true | IMP: IAF Substrate Not Ready - ACM: (Area B) Airwave Substrate Not Ready - RPS: (Area A) Waterproof Membrane Installation - Completed to Corner, Stopped per Adrian(HP) - RPS: (Area B) Waiting on Inspection - Roof Panels |  |  | Cloudy: High 75, Low 61 |  |  | false |  |  | false
21008 | 900 Church | 2022-05-04 | Marvin Blanco | installing panels in the canopy of the 17th floor until 12 o'clock. Then I had to do pure little things because material was needed to continue installing panels. very irresponsible because they cannot carry what is needed. | Subcontractor | Dillon Bowman | true | ACM plate |  |  |  | 3 | 10 | false |  |  | false |  |  |  |  | ACM | 1 | 1
21010 | 17th & Grand | 2022-05-04 | Fredy veliz | We are done on the with the panels on the north except for the panels that was made wrong and some caulking that we need to use glass guys 135 boom lift | Subcontractor | Denis Usatenko | [5 empty] | 8 | 10.5 |  |  | Swuing stage boom lift forklift | [5 empty] | ACM Hat Channel Insulation Other | 10 | 12 | [24 empty] | 80 | 3 | [6 empty] | 72 | 12 | [6 empty] | Caulking prep for panels on L9 below windows prep for panels eyebrow north side | 57
21060 | Vantage VA 13 | 2022-05-04 | Joey Laxton | Thunderstorms all day long!! | Subcontractor | Steve Fudge | false |  |  |  |  | 6 | 18 | false |  | 85 foot boom | false
21060 | Vantage VA 13 | 2022-05-04 | Nathan Wall | no work performed. Rain out. | Subcontractor | Steve Fudge | false |  |  |  |  | 6 | 2 | false |  | 85' boom lift | false
21071 | Google NBY-HUB 1 | 2022-05-04 | Naza Padron | Google 2B north & West Elevation 1A west & North Elevation | Subcontractor | Steve Fudge | false |  |  |  |  | 4 | 8 | false |  | N/A | false |  |  |  |  | Other | [42 empty] | 390 clips and 78 channels | 32
21071 | Google NBY-HUB 1 | 2022-05-04 | Naza Padron | Google 2B north & West Elevation 1A west & North Elevation | Subcontractor | Steve Fudge | false |  |  |  |  | 4 | 8 | false |  | N/A | false |  |  |  |  | Other | [42 empty] | 390 clips and 78 channels | 32
20067 | BNA PROJECT 5 | 2022-05-03 | Dillon Bowman |  | JWMCD Crew | Marc Ribar | true | IMP: IAF Substrate Not Ready - ACM: (Area B) Airwave Substrate Not Ready - RPS: (Area A) Waterproof Membrane Installation - Completed to Corner, Stoped Per Adrian(HP) RPS: (Area B) Waiting on Inspection - Roof Panels |  |  | Scattered Showers, High 85, Low 67 |  |  | false |  |  | false
21008 | 900 Church | 2022-05-03 | Marvin blanco | making rout on the panels to make it fit | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 | 10 | false |  |  | false |  |  |  |  | ACM Soffit | 8 | 10
21010 | 17th & Grand | 2022-05-03 | Fredy veliz | North elevation not complete i slow process we spend i log time going up and down on the boom lift today we went down two times to move the boom lift the glass guys working on the same areas so sometimes we are on their way sometimes they are on our way | Subcontractor | Denis Usatenko | [5 empty] | 8 | 13 |  |  | Swing stage boom lift forklift | [5 empty] | ACM Hat Channel Insulation | 19 | 45 | [24 empty] | 160 | 5 | [6 empty] | 256 | 50
21060 | Vantage VA 13 | 2022-05-03 | Joey Laxton | We had a great day but we seen we was going to catch the framers | Subcontractor | Steve Fudge | false |  |  |  |  | 6 | 60 | false |  | 85 foot boom lift | false |  |  |  |  | Perforated
21060 | Vantage VA 13 | 2022-05-03 | Nathan Wall | Safety stand down at 8:30. Crane still in the way on Southside. Installed 12 sheets of perforated on the roof screen wall. | Subcontractor | Steve Fudge | false |  |  |  |  | 6 | 10 | false |  | 85' boom lift | false |  |  |  |  | Perforated
21071 | Google NBY-HUB 1 | 2022-05-03 | Naza Padron | Google 2B West and South Elevation work stopped due to rain | Subcontractor | Steve Fudge | true | we worked and stopped working because of the rain |  |  | raining day | 4 | 6 | false |  | N/A | false |  |  |  |  | Other | [42 empty] | 360 clips and 72 channels | 24
21010 | 17th & Grand | 2022-05-02 | Fredy veliz | The installation of the panels on the north side with the boom lift is slow process because we can't carry much materials and all out materials are located in level 5 | Subcontractor | Denis Usatenko | [5 empty] | 8 | 13 |  |  | Swing stage,boom lift forklift | [5 empty] | ACM Hat Channel Insulation Louvre | 21 | 52 | [22 empty] | 1 | 3 | 34 | 2 | [6 empty] | 230 | 47
21060 | Vantage VA 13 | 2022-05-02 | Nathan Wall | Every day this week is safety stand down. can not Install "z" on Southside crane in the way. Installed 17 sheets of perforated. | Subcontractor | Steve Fudge | false |  |  |  |  | 6 | 10 | false |  | 85' boom lift | false |  |  |  |  | Perforated
21071 | Google NBY-HUB 1 | 2022-05-02 | Naza Padron | Google 2B North Elevation | Subcontractor | Steve Fudge | false |  |  |  |  | 4 | 10 | true | Clips and Channels | N/A | false |  |  |  |  | Other | [42 empty] | 160 clips and 32 channels | 40
21010 | 17th & Grand | 2022-04-30 | Fredy veliz | I pick it up the hats at the shop | Subcontractor | Denis Usatenko | [5 empty] | 7 | 8 | [8 empty] | ACM Coping Hat Channel Other | 4 | 16 | [32 empty] | 20 | 8 |  |  |  |  | 40 | 24 | Caulking | 16
19006 | Kistler Rolled Panels | 2022-04-29 | Chad mccoy | We started our day in the yard loading up the rest of the material needed to finish out the install of the coping. Once we have everything loaded up we’ve ventured over to the job site and we started booming it up in the 180. Once everything was in place on the roof we then started installing coping and laying out outlets. Both of the corners for the last section were built backwards so one of the corners Hass to stay on because I do not have a replacement for it and the one corner we did install is a little bit bigger than the coping next to it due to the fact that I do not have that coping size to replace that coping with and we tried to put a different coping on it and it looked horrible. Once all the coping was installed we went and got mops and cleaner and we cleaned all of the coping. We used rollers on the side that had the sun to try and seat the. Sealant down. We are gonna be going back throughout the weekend and on Monday to hit all the joints one more time as the sun heats it up so that the sealant will lay down better and let the joints look better. Once we cleaned up the entire fifth level of everything that we had in the smoke room and on the deck and the coping we then went down and cleaned up our staging area where our trucks and the boom lift was parked and then we went to the yard and we threw everything away that was trash that needs to be thrown away we cleaned up the yard and we got everything ready for Monday’s departure. | JWMCD Crew | Chris Ball | true | The Koeppen did not want to engage in the cleats that were installed on the section. No matter what we did we could not keep some of the dents out due to the fact that we could not reach it in anyway. So we reworked cleats modified cleats moved cleats until we got the best possible outcome that we could get. |  |  |  | 3 | 8 | false |  | 180 boom | false |  |  | 1 |  | Coping Layout | [40 empty] | 60 | 4
20067 | BNA PROJECT 5 | 2022-04-29 | Daniel | 3 guys laying waterproof 264 FT(24 hours), 2 laying waterproof/ rolling glue, 1 guy passing water proof/ making cuts | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 8 | false |  | 85FT BOOM | false |  |  |  |  | Flashing | [32 empty] | 90 | 1
20067 | BNA PROJECT 5 | 2022-04-29 | Dillon Bowan |  | JWMCD Crew | Marc Ribar | true | IMP: IAF Substrate Not Ready - ACM: (Area B) Airwave Substrate Not Ready - RPS (Area A): Waterproof Membrane complete up to stopping point per Adrian of HP. - RPS (Area B): Waiting on Inspection for Roof Panels | [5 empty] | false |  |  | false
21010 | 17th & Grand | 2022-04-29 | Fredy veliz | We started to work on the boom lift at 10 am because David told me the they some people coming to work on asphalt then they call me at 9 am to let me know the rd work was push to next week and the the panel mm22 &mm23 was made wrong I add an other pcs to those panels | Subcontractor | Denis Usatenko | true | Misk communications form jedunn |  |  |  | 13 | 12 |  |  | Swing stage boom lifts forklift | [5 empty] | ACM Coping Hat Channel Insulation Other | 25 | 40 | [24 empty] | 180 | 6 | [6 empty] | 228 | 35 |  |  |  |  | 30 | 4 | Caulking, peel off panels south side | 68
21039 | Project Orion | 2022-04-29 | Javier Brito | The project is now completed caulking panels and everything please let us know if any punch list comes up | Subcontractor | Steve Fudge | [5 empty] | 3 | 10 |  |  | 60 ft boom lift | [5 empty] | Other | [42 empty] | Caulking | 30
21060 | Vantage VA 13 | 2022-04-29 | Joey Laxton | Moved material all day | Subcontractor | Steve Fudge | false |  |  |  |  | 2 | 20 | false |  | 85 foot boom | false
19006 | Kistler Rolled Panels | 2022-04-28 | Chad mccoy | We started today loading the trailer to take our material to the site. We placed the boom where we needed it and then we started transferring material from the ground to the roof. Yesterday we removed coping so we would be able to start by installing first thing. We installed all the coping from the boom from that corner all the way to the side of the bridge so we did not have to stand on it. Once all this coping was installed we Remove the entire side on the other side of the bridge and we started prepping for the next days install | JWMCD Crew | Chris Ball | true | Wind, For Alex had to be cut out and two pieces of coping how to be cut down to fit in the sections that did not require a 12 foot piece |  |  |  | 3 | 8 | false |  | 180 boom | false |  |  | 1 |  | Coping Layout | [40 empty] | 88 | 9
20067 | BNA PROJECT 5 | 2022-04-28 | Daniel | 3 guys (24 hours) 2 laying waterproof(330 FT)/ rolling glue, 1 guy cutting waterproof/ keeping area organized . | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 8 | false |  | 85FT BOOMLIFT | false
21010 | 17th & Grand | 2022-04-28 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 13 | 14 | true | Panels for north terrace and insulation louver | Swing stage ,boom lift,forklift | [5 empty] | ACM Hat Channel Insulation Other | 38 | 64 | [24 empty] | 180 | 4 | [6 empty] | 450 | 74 | [6 empty] | Moving the stage caulking | 36
21039 | Project Orion | 2022-04-28 | Javier Brito | Crew-1 3 men west elevation canopy 7 coping panels were installed all the panels are now installed 40 LF of caulking | Subcontractor | Steve Fudge | [5 empty] | 3 | 10 |  |  | 60 ft boom lift | [5 empty] | ACM | 7 | 30
19006 | Kistler Rolled Panels | 2022-04-27 | Chad mccoy | We started today where we left off. We continued in the area where we can’t reach with the boom. 5 outlet boxes were cut out We installed 9 pieces including the crazy corner. This included three cut coping and moving 7 cleats. We then had to move everything to the other side of the building and and cleaning up our area because lunch was soon and the office personnel come take there lunch on level 5. Once we finished moving everything and cleaning up we had to take down all of our old coping and go get sections D, E-2-1, and E-2-2. Once we loaded out trailer it was lunch time. After lunch we road marched the 180 around the building thru traffic to get to the other side. Once it was set we had to go get cones bc of traffic. We then started flying up material. We took off 11 more pieces. And then we started reinstalling and cutting the pieces needed to fit. | JWMCD Crew | Chris Ball | true | Moving the boom and clean up for office workers |  |  | Sunny. 91 | 3 | 10 | false |  | 180 foot boom | false |  |  | 1 |  | Coping Layout | [40 empty] | 140 | 9
20067 | BNA PROJECT 5 | 2022-04-27 | Daniel | 2 guys laying waterproof(132 FT) / rolling glue (14 hours) | JWMCD Crew | Marc Ribar | false |  |  |  |  | 2 | 8 | false |  | 85FT BOOMLIFT | false |  |  |  |  | Flashing | [32 empty] | 190 | 2
21010 | 17th & Grand | 2022-04-27 | Fredy veliz | Today we let Glass people use the stage on the east to install flashing above windows we shutdown the the 180 boom for 2 hour as for mechanical problems | Subcontractor | Denis Usatenko | [5 empty] | 13 | 14 | true | Coping | [6 empty] | ACM Coping Hat Channel Insulation Other | 27 | 62 | [24 empty] | 180 | 4 | [6 empty] | 450 | 77 |  |  |  |  | 30 | 4 | Caulking and peel of on the south side And moving the swing stage on the East side | 36
21039 | Project Orion | 2022-04-27 | Javier Brito | Crew-1 3 men northwest elevation 230 LF of caulking | Subcontractor | Steve Fudge | [5 empty] | 3 | 10 |  |  | 60 ft boom lift | [5 empty] | Other | [42 empty] | Caulking | 30
21060 | Vantage VA 13 | 2022-04-27 | Joey Laxton | we used a crane that the roofers had on sit to get the corrugated to the roof. After that we continued installing Z gurts and insulation on penthouse and west wall | Subcontractor | Steve Fudge | false |  |  |  |  | 6 | 8 | false |  | 85 ft boom lift | false |  |  |  |  | Insulation Subgirt | [26 empty] | 1000
19006 | Kistler Rolled Panels | 2022-04-26 | Chad mccoy | We started our day taken coping off. We took off 7 pieces and then we had to use the boom to get our material to the 5 floor. In most of the coping. Outlet covers have to be cut out. This takes layout time. We are being very careful to not dent anything. The problem with the coping is it had a oil canning effect. The coping covers have the oil canning in them when we take them out of the box. I took pictures of this on the trailer before they were even installed or taken to the roof. The boom can not reach half of one wall. So due to the hand rail we have to stand on one new coping to install the next piece. We are putting a moving blanket down on to of the coping to help with and scratches or dents. | JWMCD Crew | Chris Ball | true | It’s time consuming removing and prepping and reinstalling each piece of coping. We ended up taken 21 pieces off today. And installing 13 pieces back. We took of more than we needed so we could jump into installing tomorrow. The office workers take a hr lunch on the 5 floor where we are working so we have to take lunch at that time. |  |  | Partly cloudy 92 | 3 | 10 | false |  | 180 boom | false |  |  | 1 |  | Coping Layout | [40 empty] | 150 | 9
20067 | BNA PROJECT 5 | 2022-04-26 | Dillon Bowman | RPS: (Area A) Waterproof Membrane Installation - Inventory Management, Material Prepared for Night Work 04/27. RPS: (Area B) End-cap(top) Flashing Mock-up Installed | JWMCD Crew | Marc Ribar | true | IMP: IAF Substrate Not Ready ACM: (Area B) Airwave Substrate Not Ready |  |  | High 64, Low 52 - Overcast | 2 | 8 | false |  | Boom (85) | false
21010 | 17th & Grand | 2022-04-26 | Fredy veliz | This morning we had issues with access to the level 7&9 glass guys installed the glass in all the areas I called jedunn to make the complain and they pull the glass back out also we used their boom lift to install the panels on the north side | Subcontractor | Denis Usatenko | [5 empty] | 12 | 13.5 |  |  | Swing stage Boom list forklift | [5 empty] | ACM Hat Channel Other | 56 | 80 | [32 empty] | 490 | 68 | [6 empty] | Caulking and peel off panels | 24
21039 | Project Orion | 2022-04-26 | Javier Brito | Crew-1 south west canopy 238 LF of caulking this canopy is now completed | Subcontractor | Steve Fudge | [5 empty] | 3 | 10 |  |  | 60' ft boom lift | [5 empty] | Other | [42 empty] | 238 LF of caulking | 30
21010 | 17th & Grand | 2022-04-25 | Fredy veliz | Today we stop all the work outside at 9:30 am for the rain | Subcontractor | Denis Usatenko | [5 empty] | 13 | 13 | true | Hat Chanel's | [6 empty] | ACM Coping Hat Channel Insulation Other | 24 | 46 | [24 empty] | 180 | 8 | [6 empty] | 340 | 79 |  |  |  |  | 30 | 6 | Moving the swing stage | 30
21039 | Project Orion | 2022-04-25 | Javier Brito | Crew-1 3 men northwest and south west canopies 20 coping panels were installed | Subcontractor | Steve Fudge | [5 empty] | 3 | 12 |  |  | 60, ft boom lift | [5 empty] | ACM | 20 | 36
21010 | 17th & Grand | 2022-04-24 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 10 | 9 |  |  | Swing stage boom lifts forklift |  |  |  | 24 |  | ACM Hat Channel Layout | 20 | 42 | [32 empty] | 228 | 24
20067 | BNA PROJECT 5 | 2022-04-23 | Dillon Bowman | IMP: IAF Substrate Not Ready - ACM: (Area B) Airwave Substrate Not Ready - RPS: (Area A) Waterproof Membrane Installation - No Men on Site, Team Training Saturday AM - RPS: (Area B) Waiting on Inspection - Roof Panels | JWMCD Crew | Marc Ribar | false | [6 empty] | false |  |  | false
21010 | 17th & Grand | 2022-04-23 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 13 | 9 |  |  | Swing stage ,boom lift,forklift | [5 empty] | ACM Coping Hat Channel Insulation | 26 | 46 | [24 empty] | 480 | 28 | [6 empty] | 390 | 39 |  |  |  |  | 30 | 4
20067 | BNA PROJECT 5 | 2022-04-22 | Daniel | 3 guys (23 hours) 2 guys laying waterproof 66 FT, 1 guy rolling glue / cutting waterproof | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 8 | false |  | 85FT BOOM | false |  |  |  |  | Flashing | [32 empty] | 50 | 1
20067 | BNA PROJECT 5 | 2022-04-22 | Dillon Bowman | IMP: IAF Substrate Not Ready - ACM: (Area B) Airwave Substrate Not Ready - RPS: (Area A) Waterproof Membrane Installation - No Men on Site, Team Training Saturday AM - RPS: (Area B) Waiting on Inspection - Roof Panels | JWMCD Crew | Marc Ribar | false | [6 empty] | false |  |  | false
21010 | 17th & Grand | 2022-04-22 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 13 | 13.5 |  |  | Swing stage boom lift, forklift | [5 empty] | ACM Hat Channel Insulation Other | 48 | 64 | [24 empty] | 840 | 58 | [6 empty] | 340 | 30 | [6 empty] | Moving the swing stage | 24
21039 | Project Orion | 2022-04-22 | Javier Brito | Crew-1 3 men west elevation 12 panels installed | Subcontractor | Steve Fudge | [5 empty] | 3 | 11 |  |  | 60 ft boom lift | [5 empty] | ACM | 12 | 33
20067 | BNA PROJECT 5 | 2022-04-21 | Daniel | 3 guys (24 hours) 2 guys laying waterproof, (covering all the white/ covering part we did wrong . )155 FT / smoothing it out, 1 guy rolling glue/ cutting water and ice. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 8 | false |  | 85 FT BOOM | false
21010 | 17th & Grand | 2022-04-21 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 13 | 8 |  |  | Swing,boom lift,forklift | [5 empty] | ACM Hat Channel Insulation Other | 6 | 16 | [24 empty] | 180 | 4 | [6 empty] | 345 | 56 | [6 empty] | House keeping | 28
21010 | 17th & Grand | 2022-04-21 | Fredy veliz | That day we did not work on the boom lift on the north because jedunn request me to used to do the water proof on the south-east corner and that never happen because the boom lift I was too to fit in one lane so the move for nothin I agree to let then used because I had a lot things going on at an other areas | Subcontractor | Denis Usatenko
21039 | Project Orion | 2022-04-21 | Javier Brito | Crew-1 west elevation 10 panels installed the 2 canopies at north west and south west are missing the TPO | Subcontractor | Steve Fudge | [5 empty] | 3 | 11 |  |  | 60 ft boom lift | [5 empty] | ACM | 10 | 33
20067 | BNA PROJECT 5 | 2022-04-20 | Daniel | 3 guys laying waterproof for( 18 hours) 150 ft, 2 guys laying waterproof/ smoothing it out, 1 guy rolling glue/refilling glue . | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 8 | false |  | 85FT BOOM | false
21010 | 17th & Grand | 2022-04-20 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 13 | 10 |  |  | Swing stage boom lift forklift | [5 empty] | ACM Coping Hat Channel | 16 | 38 | [32 empty] | 58 | 24 |  |  |  |  | 120 | 68
21010 | 17th & Grand | 2022-04-20 | Fredy veliz | We leaved early for job site shutdown for owners event | Subcontractor | Denis Usatenko
21039 | Project Orion | 2022-04-20 | Javier Brito | Crew-1 southwest 2 panels installed and 10 panels installed at center canopy west elevation | Subcontractor | Steve Fudge | [5 empty] | 3 | 10 |  |  | 60 ft boom lift | [5 empty] | ACM | 12 | 30
19028 | Kistler Rolled Panels | 2022-04-19 | Chad mccoy | Keith and I started by getting a ladder to fix the door headers where the screws were coming thru. We cut off 9 screws and caulked the holes. I thin measured and laid out what I thought the garage door needed to be complete. I checked about 50 louvers for level. The issue is the louver builds. We also check louver size compared to concrete slab size. We walked and made decisions and what needed to happen on all punch list items. Then we ran them by scott and amy. Scott and I went to the roof and we discussed all the panels on 34 and where the roofer tried to clean some. Keith and I fixed two louvers to get them off the punch list. We also measured out all linear feet of the new metal needed | JWMCD Crew | Chris Ball | true | Waiting on scissor lift |  |  |  | 2 | 9 | false |  | Scissor lift | false
20067 | BNA PROJECT 5 | 2022-04-19 | Dillon Bowman | RPS: (Area A) Waterproof Membrane Installation - Material Handling, Installed 150ft of Waterproof Membrane. | JWMCD Crew | Marc Ribar | true | IMP: IAF Substrate Not Ready - ACM: (Area B) Airwave Substrate Not Ready - RPS: (Area B) Waiting on Inspection of Roof Panels |  |  | High 61, Low 37 - Overcast AM, Sunny Afternoon |  |  | false |  |  | false |  |  |  |  | Other | [42 empty] | 150 | 5
21010 | 17th & Grand | 2022-04-19 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 13 | 13 |  |  | Swing stage boom lifts, forklift | [5 empty] | ACM Hat Channel Insulation Other | 32 | 57 | [24 empty] | 500 | 26 | [6 empty] | 450 | 60 | [6 empty] | Caulking | 26
21039 | Project Orion | 2022-04-19 | Javier Brito | Crew-1 3 men south west canopy 7 panels installed 45 LF of caulking | Subcontractor | Steve Fudge | true | We lost half of the day bc we were waiting for materials to get delivered |  |  |  | 3 | 11 |  |  | 60 ft boom lift | [5 empty] | ACM | 7 | 33
20067 | BNA PROJECT 5 | 2022-04-18 | Dillon Bowman |  | JWMCD Crew | Marc Ribar | true | IMP: IAF Substrate Not Ready - ACM: (Area B) Airwave Substrate Not Ready - RPS: (Area A) Waterproof Membrane Installation [Substrate Wet From Rain] - RPS: (Area B) Waiting on Inspection - Roof Panels |  |  | Overcast - High 58, Low 45 |  |  | false |  |  | false
21010 | 17th & Grand | 2022-04-18 | Fredy veliz | We stop installing on the south for couple hours because somebody hit a gas pipe in the ground | Subcontractor | Denis Usatenko | [5 empty] | 10 | 13 |  |  | Swing stage boom lifts forklift | [5 empty] | ACM Coping Hat Channel Insulation Other | 22 | 40 | [24 empty] | 180 | 4 | [6 empty] | 550 | 60 |  |  |  |  | 30 | 4 | House keeping organizing material | 22
21010 | 17th & Grand | 2022-04-18 | Fredy veliz | We did not work on the boom lift on the north side because nes was removing that temporary power post at the north-West corner | Subcontractor | Denis Usatenko
21039 | Project Orion | 2022-04-18 | Javier Brito | We didn't work today due to a rainy day | Subcontractor | Steve Fudge | [5 empty] | 3 | 0
20067 | BNA PROJECT 5 | 2022-04-16 | Dillon Bowman |  | JWMCD Crew | Marc Ribar | true | Night Work Delay - HP was not permitting night work. |  |  | High 70, Low 54 |  |  | false |  |  | false
21010 | 17th & Grand | 2022-04-16 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 13 | 9 |  |  | Swing stage ,boom lift , forklift | [5 empty] | ACM Coping Other | 30 | 66 | [38 empty] | 20 | 2 | Caulking, moving panels to level 7, moving the swing stage on the east side | 49
20067 | BNA PROJECT 5 | 2022-04-15 | Dillon Bowman |  | JWMCD Crew | Marc Ribar | true | IMP: IAF Substrate Not Ready - ACM: (Area B) Airwave Substrate Not Ready - RPS: (Area A) Waterproof Membrane Installation [Substrate Wet From Rain] - RPS: (Area B) Waiting on Inspection - Roof Panels |  |  | High 73, Low 49 - Rainy |  |  | false |  |  | false
21010 | 17th & Grand | 2022-04-15 | Fredy veliz | We moved swing stage from the west to the south spent 4 hours 4 guys | Subcontractor | Denis Usatenko | [5 empty] | 13 | 12 | true | Coping | Swing stage boom lift ,forklift | [5 empty] | ACM Hat Channel Other | 34 | 60 | [32 empty] | 320 | 72 | [6 empty] | Moved swing stage Moving coping to the roof | 24
21039 | Project Orion | 2022-04-15 | Javier Brito | 4 panels were installed and then we went home bc we run out of clips and screws come back monday | Subcontractor | Steve Fudge | [5 empty] | 3 | 5 |  |  | 60 ft boom lift | [5 empty] | ACM | 4 | 15
20067 | BNA PROJECT 5 | 2022-04-14 | Dillon Bowman |  | JWMCD Crew | Marc Ribar | true | IMP: IAF Substrate Not Ready ACM: (Area B) Airwave Substrate Not Ready RPS: (Area A) Waterproof Membrane Installation [Rainout] RPS: (Area B) Waiting on Inspection - Roof Panels |  |  | High 67, Low 46 - Rainy |  |  | false |  |  | false
21010 | 17th & Grand | 2022-04-14 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 13 | 13.5 |  |  | Swing stage, boom lift ,forklift | [5 empty] | ACM Coping Hat Channel Insulation Other | 45 | 78 | [24 empty] | 180 | 4 | [6 empty] | 336 | 64 |  |  |  |  | 10 | 2 | Prep panels Caulking | 25
21039 | Project Orion | 2022-04-14 | Javier Brito | We only installed 2 panels bc we found an issue with the coping panels that were to short so we had to wait for a solution and GC was supposed to send you guys an email giving directions on how to proceed with those coping panels installation | Subcontractor | Steve Fudge | [5 empty] | 3 | 6 |  |  | 60 ft boom lift | [5 empty] | ACM | 2 | 18
20067 | BNA PROJECT 5 | 2022-04-13 | Dillon Bowman | No Work - Delays | JWMCD Crew | Marc Ribar | true | IMP: IAF Substrate Not Ready - ACM: (Area B) Airwave Substrate Not Ready - RPS: (Area A) Night-work Rain Out, Waterproof Membrane - RPS: (Area B) Waiting on Inspection for Roof Panels |  |  | High 79, Low 70. Thunderstorms |  |  | false |  |  | false |  |  |  |  | ACM IMP Other Overly Roof Panel | 0 | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0 | [28 empty] | 0 | 0
21010 | 17th & Grand | 2022-04-13 | Fredy veliz | We are moving the stages on the east side by our selves because the area the we doing it's complete in one day | Subcontractor | Denis Usatenko | true | Rain in the morning going back and forward and High wing |  |  |  | 13 | 12.5 | true | Screws and shims | Swing stages, boom lift, forklift |  |  |  | 8 |  | ACM Hat Channel Insulation Layout Other | 38 | 40 | [24 empty] | 240 | 8 | [6 empty] | 420 | 70 | [6 empty] | Re screw and peel off panel moving swing stage | 36
21039 | Project Orion | 2022-04-13 | Javier Brito | Crew-1 3 men north west elevation 5 panels installed | Subcontractor | Steve Fudge | [5 empty] | 3 | 10 |  |  | 60' boom lift | [5 empty] | ACM | 5 | 30
20067 | BNA PROJECT 5 | 2022-04-12 | Dillon Bowman | No Work - Delays | JWMCD Crew | Marc Ribar | true | IMP: IAF Substrate Not Ready - ACM: (Area B) Airwave Substrate Not Ready - RPS: (Area A) Night-work Rain Out,Waterproof Membrane - RPS: (Area B) Waiting on Inspection for Roof Panels |  |  | High 80, Low 60. Thunderstorms |  |  | false |  |  | false |  |  |  |  | ACM IMP Other Overly Roof Panel | 0 | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0 | [28 empty] | 0 | 0
21010 | 17th & Grand | 2022-04-12 | Fredy veliz | Swing stage on the west was installed too far from the building I spent 1 hours with 6 guys to moved and we this morning was raining we spent 5 hour prep panels | Subcontractor | Denis Usatenko | true | Raining |  |  |  | 14 | 13 |  |  | Swing stage boom lifts, forklift | [5 empty] | ACM Coping Hat Channel Other | 64 | 74 | [32 empty] | 664 | 32 |  |  |  |  | 41 | 6 | Prep panels | 70
21039 | Project Orion | 2022-04-12 | Javier Brito | Crew-1 3 men southwest canopy we did the layout and we installed 8 panels NOTE THAT THE DAILY REPORT FROM MONDAY THE ELEVATION WAS NORTHWEST I MADE A MISTAKE WITH WRITING SOUTH WEST | Subcontractor | Steve Fudge | [5 empty] | 3 | 12 |  |  | 60' ft boom lift | [5 empty] | ACM | 8 | 36
20067 | BNA PROJECT 5 | 2022-04-11 | Dillon Bowman | No work - Delays | JWMCD Crew | Marc Ribar | true | IMP: IAF Substrate Not Ready ACM: (Area B) Airwave Substrate Not Ready RPS: (Area A) Night-work Rain Out - Waterproof Membrane RPS: (Area B) Waiting on Inspection | [5 empty] | false |  | 2 Booms | false |  |  |  |  | ACM IMP Overly Roof Panel | 0 | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0
21009 | The Inn at Southhall | 2022-04-11 | Fredy | This day, apart from Genesis, 45 feet of StarterJ and 40 feet of Drip trim and 40 feet of J Corner trim were installed. | Subcontractor | Chris Ball | false |  |  |  |  | 5 | 50 | false |  | Bom lif | false |  |  |  |  | Genesis | [14 empty] | 9 | 5
21010 | 17th & Grand | 2022-04-11 | Fredy veliz | Shutdown for rain. And high wind | Subcontractor | Denis Usatenko | true | Moving stages ,weather, (rain ,wind) |  |  |  | 14 | 5 |  |  | Swing stage,boom lift ,forklift | [5 empty] | ACM Hat Channel | 12 | 22 | [32 empty] | 288 | 48
21039 | Project Orion | 2022-04-11 | Javier Brito | Crew-1 3 men south west canopy we did layout the canopy and everything was good we also installed 9 panels we have no issues as of right now | Subcontractor | Steve Fudge | [5 empty] | 3 | 12 |  |  | 60' ft boom lift | [5 empty] | ACM | 9 | 36
21010 | 17th & Grand | 2022-04-10 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 11 | 8 |  |  | Swing stage ,boom lift , forklift |  |  |  | 10 |  | ACM Hat Channel Layout | 29 | 54 | [32 empty] | 590 | 24
20067 | BNA PROJECT 5 | 2022-04-09 | Dillon Bowman | Per HP, not enough labor to warrant night work access | JWMCD Crew | Marc Ribar | true | Access to Site Denied |  |  | Rain Out |  |  | false |  |  | false
21010 | 17th & Grand | 2022-04-09 | Fredy veliz | Some panels are little bigger then other ones so the joing not gonna be perfect on the soffit areas on level 5 | Subcontractor | Denis Usatenko | [5 empty] | 12 | 9 |  |  | Swing stage ,boom lift ,forklift |  |  |  | 6 |  | ACM Hat Channel Layout | 18 | 34 | [32 empty] | 412 | 68
21060 | Vantage VA 13 | 2022-04-09 | Joey Laxton |  | Subcontractor | Steve Fudge | false |  |  |  |  | 6 | 60 | false |  | 85 foot boom | true |  |  |  |  | Single Skin | [6 empty] | 9 | 60
21069 | Broadwest HOAR | 2022-04-09 | Chad mccoy | Today I adjusted one column to better align the joint. And we caulked and peeled the columns. During this time. The tile was going in so we had to work together finish | JWMCD Crew | Denis Usatenko | true | Tile guys in the way, The columns do not match the soffit |  |  | Rain | 2 | 7 | false |  |  | false
21010 | 17th & Grand | 2022-04-08 | Fredy veliz | We shutdown for today for weather issues raining every 30 min also we fixing 13 panels on the east elev for improper fabrication | Subcontractor | Denis Usatenko | true | Raining |  |  |  | 12 | 5 |  |  | Swing stage,boom lift ,forklift | [5 empty] | ACM Other | 2 | 3 | [40 empty] | Moving materials up to level 9 for esta elevation house keeping | 57
21069 | Broadwest HOAR | 2022-04-08 | Chad | We started our day at the shop loading the panels in the back seats of mine and Keith’s work trucks. The were sitting on moving blankets. I got clips that were left over from 13th and D. I got shims out of the 900 church crate bc it was Dennis s job. We got to the site and we laser lined a level line on all 4 columns. Then I installed a column and Keith installed his own. We installed all columns today | JWMCD Crew | Denis Usatenko | true | The panels are not rolled the same. So we had to plug and play with each column to achieve the right matches for each. Then we had to try and hand roll these panels closer to what we needed |  |  | Clear | 2 | 9 | true | Screws |  | false |  |  | 2 |  | ACM Layout | 24 | 16
20067 | BNA PROJECT 5 | 2022-04-07 | Dillon Bowman | NDDA Guys - Night Work - Installed 300+ ft of Waterproof membrane, South Side, and 100ft of flashing at gutter. | JWMCD Crew | Marc Ribar |  |  |  |  | Rain Out | 3 | 8 | false |  |  | false |  |  |  |  | Other | [42 empty] | 300 | 8
21010 | 17th & Grand | 2022-04-07 | Fredy veliz | Mcinerney used one swing stage on the south e hours then used the one on the south east for 1 hours | Subcontractor | Denis Usatenko | [5 empty] | 13 | 12.5 | true | Hat Channel | Swing stage ,boom lifts , forklift | [5 empty] | ACM Hat Channel Insulation Other | 2 | 2 | [24 empty] | 1700 | 72 | [6 empty] | 270 | 40 | [6 empty] | Cuting material , moving swing stage ,installing z | 87
20067 | BNA PROJECT 5 | 2022-04-06 | Dillon Bowman | Night Work Rain Out | JWMCD Crew | Marc Ribar | true | Rain |  |  | Rain Out | 3 | 8 | false |  |  | false
21010 | 17th & Grand | 2022-04-06 | Fredy veliz | I having with the areas not been ready incomplete by other company's | Subcontractor | Denis Usatenko | true | Rain , incomplete caulking on the windows |  |  |  | 5 | 8 |  |  | Swing stage ,boom lift,forklift | [5 empty] | Hat Channel Other | [34 empty] | 190 | 20 | [6 empty] | Peel off panels on the west side Moving panels to the north side | 20
21069 | Broadwest HOAR | 2022-04-06 | Chad mccoy | We were dodging rain all day. We already had all the plates up but one. So we installed that one and then caulked them all out. We had a issue with one plate and the bolts. So I called Brian and he sent a Hoar guy down to grind the bolts down. I was not going to cut them off. So he cut them and then we finished. After we finished we cleaned up and went to the shop. The columns weren’t finished | JWMCD Crew | Denis Usatenko | true | Rain. And bolts |  |  | Rain | 2 | 4 | false |  |  | false
20067 | BNA PROJECT 5 | 2022-04-05 | Dillon Bowman | Night Work Rain Out | JWMCD Crew | Marc Ribar | true | Rain |  |  |  | 3 | 8 | false |  |  | false
21010 | 17th & Grand | 2022-04-05 | Fredy veliz |  | Subcontractor | Denis Usatenko | true | Rain |  |  |  | 14 | 7 |  |  | Swing stage , boom lift , forklift | [5 empty] | Other | [42 empty] | Removing panels from main entrance organizing material on level 5 | 35
21069 | Broadwest HOAR | 2022-04-05 | Chad mccoy | Today we started installing the Acm covers by the pool. On the third one Brian wanted us to move the bar panel 1 inch to the left. So we took it down and he had to cut insulation off of pipes and try and straighten the framing. We put it back and I made the upper panel and installed it. Keith caulked everything and we peeled it. We then went back to making the Acm plates. Keith laid each one out individually and I cut and routed them. We couldn’t caulk anything bc of the rain but we hung them to be finished tomorrow | JWMCD Crew | Denis Usatenko | true | The framing on the hair panel, and rain |  |  | Rainy | 2 | 8 | false |  |  | false |  |  | 2 |  | ACM Layout | 20 | 14
20067 | BNA PROJECT 5 | 2022-04-04 | Dillon Bowman | NDA Guys - Helped HP Move Roof Materials Across the Airwave Roof. | JWMCD Crew | Marc Ribar | true | HP Directed to Move Material |  |  |  | 3 | 8 | false |  |  | false
21010 | 17th & Grand | 2022-04-04 | Fredy veliz | Issues with power | Subcontractor | Denis Usatenko | true | Power was cut off for 2 hours in the morning |  |  |  | 14 | 10 |  |  | Swing stage,boom lift ,forklift | [5 empty] | Hat Channel Other Single Skin | 20 | [33 empty] | 840 | 72 | [6 empty] | Caulking,cuting material ,waiting for power | 44
21069 | Broadwest HOAR | 2022-04-04 | Chad McCoy | We started our day at mcdougal getting everything ready at mcdougal to take it to the job. We met up with Dennis and went to the site and went over everything that needed to be done. We talked to hoar and they told us what they wanted in each location. We also decided to have the 19 plates made in the shop. I’m getting them in the morning. After Dennis dropped us off at the shop we unloaded one sheet of Acm and headed to the job. We went and laid out the Acm for fabbing. We fabbed the panel in the parking lot and we took it up stairs to cut out the penetrations and the notches. We had to wait on hoar to finish moving the outlets before we could install the panel. They moved hem there selfs. Once they were done we installed the panel and cut the penetrations | JWMCD Crew | Denis Usatenko | true | The outlets had to be moved, it took for ever. |  |  | Cloudy | 2 | 9 | false |  |  | false |  |  |  |  | ACM | 2 | 10
21010 | 17th & Grand | 2022-04-02 | Fredy veliz | We did finish the west side because lost the power on the stages | Subcontractor | Denis Usatenko | true | Lost power on the stages |  |  |  | 11 | 8 |  |  | Swing stages , boom lift ,forklift | [5 empty] | Hat Channel Other Single Skin | 12 | 12 | [32 empty] | 580 | 36 | [6 empty] | 160' linear ft caulking and house keeping on level 7&9 | 40
20067 | BNA PROJECT 5 | 2022-04-01 | Dillon Bowman | NDA Guys - Murton's Hole TC inventory Management | JWMCD Crew | Marc Ribar |  |  |  |  | Rain Out | 3 | 8 | false |  |  | false
21010 | 17th & Grand | 2022-04-01 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 13 | 11 |  |  | Swing stages,boom lift,forklift | [5 empty] | Hat Channel Other Single Skin | 27 | 54 | [32 empty] | 120 | 12 | [6 empty] | 2 guays cuting material for south elevation 2 goys on the roof doin final check on the penthouse | 143
21011 | Beaumeade | 2022-04-01 | Marvin blanco | installed metal panels cutting metals panels putting diesel ⛽️ in the boomlift. | Subcontractor | Steve Fudge | false |  |  |  |  | 6 | 11 | false |  | 2 boomlift and 1 scissors lift. | false |  |  |  |  | Corrugated | [22 empty] | 48 | 66
21024 | Vanderbilt Graduate Housing | 2022-04-01 | Chad mccoy | He Dunn told us not to caulk anything till they figured out who owned it | JWMCD Crew | Drake De Tomasi | true | I forgot reveals at the shop. They had to be brought to me |  |  | Clear | 2 | 4 | false |  |  | false |  |  |  |  | ACM Insulation Subgirt | 1 | 0.5 | [24 empty] | 15 | 0.5 |  |  | 25 | 0.5
20067 | BNA PROJECT 5 | 2022-03-31 | Dillon Bowman | NIght Work Rain Out | JWMCD Crew | Marc Ribar | true |  |  |  | Rain Out |  |  | false |  |  | false
21010 | 17th & Grand | 2022-03-31 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 14 | 6 |  |  | Swing stage ,boom lift,forklift | [5 empty] | Hat Channel Single Skin | 31 | 60 | [32 empty] | 100 | 24
21011 | Beaumeade | 2022-03-31 | Marvin blanco | I'm driving to Virginia today. I have my 5 guys working on the screen wall building A | Subcontractor | Steve Fudge | false |  |  |  |  | 5 | 11 | false |  | boomlift and a scissors lift | false |  |  |  |  | Corrugated Other | [22 empty] | 17 | 20 | [18 empty] | my guys had to stop putting some panels up because Sccott from Hill called me for could tell them to stop because it's very windy at the moment they are finishing the framing studs | 11 a day
21024 | Vanderbilt Graduate Housing | 2022-03-31 | Chad mccoy | We started our day at the shop waiting to get loaded, We loaded our crate by hand. Then I talked to nick and then loaded the rest of the material. New got to site at 930 and we started laying out per panel size at 950. Ground work was going on right at our feet. So some access was limited. We only had one ladder that would reach. So that to limited us. We installed green girt and insulation and trim for windows and then panels. We left all material needed there at the end of the day. Then we went back to shop. We took no lunch today | JWMCD Crew | Drake De Tomasi | true | Excavators digging right next to us, we needed two extension ladders |  |  | Cloudy | 2 | 8.5 | false |  |  | false |  |  | 1 |  | ACM Flashing Insulation Layout Subgirt | 4 | 1.5 | [24 empty] | 40 | 1 |  |  | 50 | 1 | 36 | 1
20067 | BNA PROJECT 5 | 2022-03-30 | Dillon Bowman | High Winds, Rain Out | JWMCD Crew | Marc Ribar | true |  |  |  | Weather - High Winds, Rain Out |  |  | false |  |  | false
21010 | 17th & Grand | 2022-03-30 | Fredy veliz |  | Subcontractor | Denis Usatenko | true | High wind |  |  | Yes | 14 |  |  |  | Swing stage boom lift forklift | [5 empty] | Hat Channel Insulation Other Single Skin | 22 | 40 | [24 empty] | 80 | 4 | [6 empty] | 380 | 36 | [6 empty] | Re screen coping and caulking
20067 | BNA PROJECT 5 | 2022-03-29 | Dillon Bowman | NDA Guys - Inventory Management: Murton's Hole - Terracotta Material Management | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 6 | false |  | 2 Boom Lifts | false
20067 | BNA PROJECT 5 | 2022-03-29 | Dillon Bowman | Night Work: - NDA Guys - Waterproof Membrane Install Approx 300ft (Installed Backwords) | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 8 | false |  |  | false |  |  |  |  | Other | [42 empty] | 300 | 8
21010 | 17th & Grand | 2022-03-29 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 14 |  |  |  | Swing stage,boom lifts,forklift | [5 empty] | Hat Channel Single Skin | 54 | 80 | [32 empty] | 320 | 80
21011 | Beaumeade | 2022-03-29 | Marvin |  | Subcontractor | Steve Fudge | false |  |  |  |  | 6 |  | false |  | boomlift and scissors lift | false
|  | 2022-03-29 | Fredy | This day we worked 10 hours. We installed 42 panels, and we finished all the material. We took off the paper on the panel, now we're just waiting for the new material. | JWMCD Crew |  | false |  |  |  |  | 7 |  | false |  | Bom lif | false |  |  |  |  | ACM | 42 | 70
21008 | 900 Church | 2022-03-28 | Marvin Blanco | level 10 completed | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 |  | false |  |  | false |  |  |  |  | ACM Insulation Soffit Trim
21010 | 17th & Grand | 2022-03-28 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 14 |  |  |  | Swing stage ,boom lift,forklift | [5 empty] | Hat Channel Single Skin | 89 | 150 | [32 empty] | 180 | 10
21029 | SCE Spine Center of Excellence | 2022-03-28 | Fredy |  | JWMCD Crew | Denis Usatenko | false |  |  |  |  | 7 |  | false |  | Boom lif | false |  |  |  |  | ACM | 125 | 70
21029 | SCE Spine Center of Excellence | 2022-03-27 | Fredy |  | JWMCD Crew | Denis Usatenko | false |  |  |  |  | 7 |  | false |  | Bom lif | false |  |  |  |  | ACM | 63 | 70
21010 | 17th & Grand | 2022-03-26 | Fredy veliz | Shutdown the stages at 11 for high wind | Subcontractor | Denis Usatenko | [5 empty] | 8 |  |  |  | Swing stage boom lift,forklift | [5 empty] | Single Skin | 16 | 79
21029 | SCE Spine Center of Excellence | 2022-03-26 | Fredy | this day we cut here at work 700 clips because they did not send already cut | JWMCD Crew | Denis Usatenko | false |  |  |  |  | 7 |  | false |  | Boom lif | false |  |  |  |  | ACM Flashing | 61 | 56 | [30 empty] | 8 | 2
1639 | #NO MATCH | 2022-03-25 | Naza Padron | we do not recive all the stainless steel panels to replace the damaged ones we were able to replace 4 | Subcontractor | Chris Ball | false |  |  |  |  | 5 |  | false |  | SCISSOR LIFT | false |  |  |  |  | Other
1658 | #NO MATCH | 2022-03-25 | Daniel/Ivan | (1) ground guy (8) hours, holding ladder/ spotting. | JWMCD Crew | Rod Grove | false |  |  |  |  | 3 |  | false |  | 10K FORKLIFT, 85FT BOOM | false |  |  |  |  | Tubing | [28 empty] | 40 | 8
21010 | 17th & Grand | 2022-03-25 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 11 |  | true | Entry panels | Swing stage,boom lift,forklift |  |  |  | 4 |  | Hat Channel Layout Single Skin | 20 | 60 | [32 empty] | 338 | 70
21029 | SCE Spine Center of Excellence | 2022-03-25 | Fredy |  | JWMCD Crew | Denis Usatenko | false |  |  |  |  | 7 |  | false |  | Boom lif | false |  |  |  |  | ACM | 76 | 70
1639 | #NO MATCH | 2022-03-24 | Naza Padron |  | Subcontractor | Chris Ball | false |  |  |  |  | 5 |  | true | 1 crate stainlesteel | SCISSOR LIFT | false |  |  |  |  | Other | [42 empty] | 12 stainlesteel panels removed fom wall to replace 4 new
1658 | #NO MATCH | 2022-03-24 | Daniel/Ivan | (2) guys peeling tape from caulking (5) hours/ caulking big joints where they installed flashing(3) hours. (1) ground guy (8) hours, spotting swingstage/ passing material | JWMCD Crew | Rod Grove | false |  |  |  |  | 3 |  | false |  | 10K FORKLIFT, 85FT BOOM | false |  |  |  |  | Flashing | [32 empty] | 40 | 3
20067 | BNA PROJECT 5 | 2022-03-24 | Dillon Bowman / Manny Sandoval | Manny, Sterling, Chad, Keith, Dalton - Inventory Management: Completed IMP sorting, North Elevations Organized, lay down clean-up, made room for TC management. - JWMcD Walk: Manny and Dillon walk to review project outstanding elements in anticipation of Manny's transition. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 5 |  | true |  | 2 Boom Lifts | false
21008 | 900 Church | 2022-03-24 | Marvin blanco | waiting on material to finish | Subcontractor | Dillon Bowman | true | acm trim |  |  |  | 3 |  | false |  |  | false |  |  |  |  | ACM Insulation Soffit Trim
21010 | 17th & Grand | 2022-03-24 | Fredy veliz |  | Subcontractor | Denis Usatenko | true | Wind to high afternoon we stopped installing panels we continued installing hats only |  |  | Ye | 11 |  | true | Hats Chanel | Swing stage,boom lift, forklift |  |  |  | 8 |  | Coping Flashing Hat Channel Insulation Layout Other Single Skin | 11 | 20 | [24 empty] | 240 | 24 |  |  |  |  | 100 | 26 | 555 | 36 |  |  |  |  | 90 | 10 | Caulking
21011 | Beaumeade | 2022-03-24 | Marvin blanco | waiting on studs | Subcontractor | Steve Fudge | true | studs |  |  |  | 3 |  | false |  |  | false |  |  |  |  | Other | [42 empty] | louvers
21028 | Fieldhouse | 2022-03-24 | Buttrey |  | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 1 |  | false |  |  | false |  |  |  |  | Other | [42 empty] | Handrail endcaps
21029 | SCE Spine Center of Excellence | 2022-03-24 | Fredy |  | JWMCD Crew | Denis Usatenko | false |  |  |  |  | 7 |  | false |  | Boom lif | false |  |  |  |  | ACM Flashing | 23 | 56 | [30 empty] | 6 | 14
21029 | SCE Spine Center of Excellence | 2022-03-24 | Fredy |  | JWMCD Crew | Denis Usatenko | false |  |  |  |  | 7 |  | false |  | Boom lif | false |  |  |  |  | ACM Flashing | 23 | 56 | [30 empty] | 6 | 14
1639 | #NO MATCH | 2022-03-23 | Naza Padron |  | Subcontractor | Chris Ball | false |  |  |  |  | 5 |  | false |  | SCISSOR LIFT | false |  |  |  |  | Other | [42 empty] | 3 guys doing caulking 30 hours
1658 | #NO MATCH | 2022-03-23 | Daniel/Ivan | (2) guys calulking balcony’s(16) hours (8 floors),(1) ground guy (8) hours spotting swingstage/ passing caulk | JWMCD Crew | Rod Grove | false |  |  |  |  | 3 |  | true | Clips (300), (45) plates to hold tubes. | 10 Forklift, 85FT Boom | false
20067 | BNA PROJECT 5 | 2022-03-23 | Dillon Bowman / Manny Sandoval | Manny, Sterling, Chad, Keith - Day Work - Inventory Management: Sort North Materials, Isolate remaining south materials. - Airwave: Met with Brandon regarding RPS adjustments, - Night Work - Manny, Sterling - Ped Bridge: Template Work.. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 4 |  | false |  | 2 Boom Lifts | false
21010 | 17th & Grand | 2022-03-23 | Fredy veliz | We shutdown the swing stages at 11 because the wind | Subcontractor | Denis Usatenko | [5 empty] | 11 |  |  |  | Swing stage, boom lift,forklift | [5 empty] | Hat Channel Insulation Single Skin | 48 | 20 | [24 empty] | 560 | 24 | [6 empty] | 140 | 8
21029 | SCE Spine Center of Excellence | 2022-03-23 | Fredy |  | JWMCD Crew | Denis Usatenko | false |  |  |  |  | 7 |  | false |  | Bom lif | false |  |  |  |  | ACM | 69 | 10
1639 | #NO MATCH | 2022-03-22 | Naza Padron |  | Subcontractor | Chris Ball | false |  |  |  |  | 5 |  | false |  | SCISSOR LIFT | false |  |  |  |  | Other | [42 empty] | 3 guys doing caulking 30 hours
1658 | #NO MATCH | 2022-03-22 | Daniel/Ivan | (2) guys caulking bottom panels and balcony’s(16) hours, (1) ground guy (8) hours spotting swingstage/ passing caulking | JWMCD Crew | Rod Grove | false |  |  |  |  | 3 |  | false |  | 10K FORKLIFT, 85FT BOOM | false
20067 | BNA PROJECT 5 | 2022-03-22 | Dillon Bowman / Manny Sandoval | Manny, Sterling, Chad, Keith, Dalton - Inventory Management: Crane operations (4hrs Derr), start sorting north elevations. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 5 |  | false |  | 2 Boom Lifts | false
21010 | 17th & Grand | 2022-03-22 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 11 |  |  |  | Swing stage,boom lift,forklift | [5 empty] | Flashing Other | [32 empty] | 90 | 20 | [8 empty] | Caulking on the east hand rail panels Prep panels on level 9
21029 | SCE Spine Center of Excellence | 2022-03-22 | Fredy | today I received material we could not work all day because of the rain we only worked 4 hours | JWMCD Crew | Denis Usatenko | true |  |  |  |  | 7 |  | true | Acm panel ,screws and shim and Backer Rod and sealant | Boom lif | false
1639 | #NO MATCH | 2022-03-21 | Naza Padron |  | Subcontractor | Chris Ball | false |  |  |  |  | 5 |  | false |  | SCISSOR LIFT | false |  |  |  |  | ACM Other | 2 | 20 | [40 empty] | 2 guys doing caulking and fix end cap of incomplite panel 20 hours
1658 | #NO MATCH | 2022-03-21 | Daniel/Ivan | (2) guys caulking corner panels (16) hours (6) floors, (1) ground guy (8) hours spotting swingstage stage/ handing caulking | JWMCD Crew | Rod Grove | false |  |  |  |  | 3 |  | false |  | 10K FORKLIFT,85FT BOOM | false
20067 | BNA PROJECT 5 | 2022-03-21 | Dillon Bowman / Manny Sandoval | Manny, Sterling, Chad, Keith, Dalton - Inventory Management: Identify and Prepare South Elevations for Crane. - Airwave: Walk with HP(Brandon B, Bryce K) and Architect(David) - Met with HP(Kyle O.) to go over crane logistics. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 5 |  | false |  | 2 Boom Lifts | false
21010 | 17th & Grand | 2022-03-21 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 12 |  | true | 1-5/8 hay Chanel | Swing stage,boom lift,forklift | [5 empty] | Hat Channel Insulation Single Skin | 47 | 90 | [24 empty] | 680 | 20 | [6 empty] | 1024 | 40
21010 | 17th & Grand | 2022-03-20 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 6 |  |  |  | Swing stage,boom lift , forklift | [5 empty] | Hat Channel Single Skin | 28 | 36 | [32 empty] | 260 | 24
20067 | BNA PROJECT 5 | 2022-03-19 | Daniel | (3) guys laying waterproof (21 hours) 1 rolling the glue, 2 laying the waterproof. 1 guy moving boom lift/handing material, 2 guys spotting boom lift / receiving material (3 hours ) | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 | 8 | false |  | 85FT BOOM | false
21010 | 17th & Grand | 2022-03-19 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 8 |  |  |  | Swing stage,boom lift,forklift | [5 empty] | Hat Channel Louvre Single Skin | 20 | 32 | [22 empty] | 1 | 2 | [8 empty] | 280 | 34
1658 | #NO MATCH | 2022-03-18 | Daniel/Ivan | installed 2 clips | JWMCD Crew | Rod Grove | true | we worked for a hour and a half, then it rained so waited for the truck to come 9:30 |  |  | Rain | 6 |  | true | 795 silicone(48) | 10K FORKLIFT, 85 FT BOOM | false
20067 | BNA PROJECT 5 | 2022-03-18 | Dillon Bowman | No Crew - Rain Out | JWMCD Crew | Marc Ribar | true | Rain |  |  | Rain |  |  | false |  |  | false
1639 | #NO MATCH | 2022-03-17 | Naza Padron |  | Subcontractor | Chris Ball | false |  |  |  |  | 5 |  | false |  | SCISSOR LIFT | false |  |  |  |  | ACM Other | 10 | 30 | [40 empty] | 20 hours doing caulking
1658 | #NO MATCH | 2022-03-17 | Daniel/Ivan | (4) installers (32)hours, (2) installing clips that hold poles (31) clips, (2) installing clips on beams (9) clips, (2) caulking north side(8) floors . | JWMCD Crew | Rod Grove | false |  |  |  |  | 6 |  | false |  | 10K FORKLIFT, 85FT BOOM | false
20067 | BNA PROJECT 5 | 2022-03-17 | Dillon Bowman | No Crew - Rain Out | JWMCD Crew | Marc Ribar | true | Rain |  |  | Wet Substrate |  |  | false |  |  | false
21010 | 17th & Grand | 2022-03-17 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 12 |  |  |  | Swing stage, boom lift,forklift | [5 empty] | Hat Channel Single Skin | 32 | 80 | [32 empty] | 130 | 20
1639 | #NO MATCH | 2022-03-16 | Naza Padron | 13 panels were installed that cover the steel, and finished caulking the coping | Subcontractor | Chris Ball | false |  |  |  |  | 5 |  | false |  | SCISSOR LIFT | false |  |  |  |  | ACM Other | 13 | 40
1658 | #NO MATCH | 2022-03-16 | Daniel/Ivan | (2) guys (16) hours, pealing poly/ tape from caulking.(2) ground guys (16) hours, passing panels/ making cuts . | JWMCD Crew | Rod Grove | false |  |  |  |  | 6 |  | true | 12panels. | 10K FORKLIFT, 85FT BOOM | false |  |  |  |  | Plate |  |  | 12 | 16
20067 | BNA PROJECT 5 | 2022-03-16 | Dillon Bowman | No Crew - Rain Out | JWMCD Crew | Marc Ribar | true | Rain |  |  | Rain |  |  | false |  |  | false
21010 | 17th & Grand | 2022-03-16 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 12 |  | true | Singles skin, louver, reveals |  |  |  |  | 16 |  | Hat Channel Layout Other Single Skin | 39 | 48 | [32 empty] | 120 | 12 | [6 empty] | Removing panels on the north elevation 3 floor
1639 | #NO MATCH | 2022-03-15 | Naza Padron |  | Subcontractor | Chris Ball | false |  |  |  |  | 5 |  | false |  | SCISSOR LIFT | false |  |  |  |  | ACM Insulation Other | 14 | 40 | [24 empty] | 25 | 10 | [14 empty] | 8 panels were removed insulation wasplaced behind them,they were reinstalled and caulked
1658 | #NO MATCH | 2022-03-15 | Daniel/Ivan | (2) guys caulking (16) hours (7) floors. (1) ground guy (8) hours, handing material/ spotting swingstage. | JWMCD Crew | Rod Grove | false |  |  |  |  | 3 |  | true |  | 10K FORKLIFT, 85FT BOOM | false
20067 | BNA PROJECT 5 | 2022-03-15 | Dillon Bowman / Manny Sandoval | Night Work - Manny, Sterling - United Rental addressed boom issues. - Craned two crates. - Completed template exercise. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 2 |  | false |  |  | false
21008 | 900 Church | 2022-03-15 | marvin blanco | waiting for the job to be ready | Subcontractor | Dillon Bowman | false |  |  |  |  | 3 |  | false |  |  | false |  |  |  |  | ACM Insulation
21010 | 17th & Grand | 2022-03-15 | Fredy veliz | We are removing 8 panels on the north elev level 3 to fix windows caulking leak | Subcontractor | Denis Usatenko | [5 empty] | 12 |  |  |  | Swing stage,boom lift, forklift |  |  |  | 8 |  | Hat Channel Layout Other Single Skin | 12 | 20 | [32 empty] | 264 | 22 | [6 empty] | 1 guy doing punch items on the penthouse 288' caulking , peel and ree screws panels on the north west corner
1639 | #NO MATCH | 2022-03-14 | Naza Padron | 8 panels were removed and reinstalled with caulking to put foam insulation 2" on the back | Subcontractor | Chris Ball | false |  |  |  |  | 6 |  | true | 2 crates with ACM panels | SCISSOR LIFT | false |  |  |  |  | ACM Insulation | 12 | 40 | [24 empty] | 52 | 10
1658 | #NO MATCH | 2022-03-14 | Daniel/Ivan | (2) guys caulking 16 hours(8 floors), (1) ground guy spotting and handing material (8) hours . | JWMCD Crew | Rod Grove | false |  |  |  |  | 3 |  | true | 3/8 washers (500), 3/8 16x10 bolts (150), SOF back rod 1 1/8 (3,000 ft) | 10K FORKLIFT, 85FT BOOM | false
20067 | BNA PROJECT 5 | 2022-03-14 | Dillon Bowman / Manny Sandoval | Manny, Sterling - Troubleshooting with the boom lift. - Brought template to framers, could not complete template exercise. - Inventory Management: transported, lifted 9 crates. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 2 |  | false |  | 2 boom lifts | false
21010 | 17th & Grand | 2022-03-14 | Fredy veliz |  | Subcontractor | Denis Usatenko | true | Windows line is off 1-1/2" had to take 18 panels to make it work |  |  |  | 12 | [9 empty] | Coping Hat Channel Insulation Other Single Skin | 31 | 40 | [24 empty] | 640 | 36 | [6 empty] | 140 | 10 |  |  |  |  | 12 | 2 | Taken 18 panel out to fixed the windows are off the line 1-1/2" had couple guys doing punch list on the penthouse
21061 | ATT Building Facade Rehab | 2022-03-14 |  | we worked on the demolition of an area on the north side we removed angles and bricks we worked 11 people we worked 10 hours 2 people on the roof of the 11th floor holding the pieces to move 20 hours, also 3 people on the roof of the 7th floor accommodating and moving to the floor 1 the material 30 hrs, also 4 people on the platform doing the demolition, 40 hrs, also 2 people on the floor 1 receiving the material that is going to be voted on the trash | JWMCD Crew | Josh McPherson | false |  |  |  |  | 6 |  | false |  | Swing stage | false
21010 | 17th & Grand | 2022-03-13 | Fredy veliz | I am having issues with windows alignment | Subcontractor | Denis Usatenko | [5 empty] | 7 |  |  |  | Swing stage,boom lift ,forklift | [5 empty] | Coping Hat Channel Single Skin | 16 | 50 | [32 empty] | 100 | 5 |  |  |  |  | 60 | 15
1658 | #NO MATCH | 2022-03-11 | Daniel/Ivan | (2)guys caulking (16) hours (8) floors, (1) ground guy, spotting swingstage, handing caulk/ backer rod. | JWMCD Crew | Rod Grove | false |  |  |  |  | 3 |  | true | 2 boxes Hilti Anchor Bolts, 5/8 4inches long(180) | 10K FORKLIFT, 85Ft BOOM | false
20067 | BNA PROJECT 5 | 2022-03-11 | Dillon Bowman / Manny Sandoval | Manny, Sterling - Inventory Management: Jumped the Van - Airwave South: worked on HP concerns, riveting and caulking - GT Circulation: Fabricated and Installed 4 Columns, and moved extra materials to the lay-down. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 2 |  | false |  | 2 Booms | false |  |  |  |  | Other | [42 empty] | Stainless steel column covers - 4
21010 | 17th & Grand | 2022-03-11 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 11 |  |  |  | Swing stage,Boom lift, forklift | [5 empty] | Hat Channel Insulation Single Skin | 34 | 30 | [24 empty] | 1400 | 40 | [6 empty] | 278 | 40
21061 | ATT Building Facade Rehab | 2022-03-11 |  | we worked on the demolition of an area on the north side we removed angles and bricks we worked 11 people we worked 10 hours 2 people on the roof of the 11th floor holding the pieces to move 20 hours, also 3 people on the roof of the 7th floor accommodating and moving to the floor 1 the material 30 hrs, also 4 people on the platform doing the demolition, 40 hrs, also 2 people on the floor 1 receiving the material that is going to be voted on the trash | JWMCD Crew | Josh McPherson | false |  |  |  |  | 11 |  | false |  | Swing stage | false
21061 | ATT Building Facade Rehab | 2022-03-11 |  | we worked on the demolition of an area on the north side we removed angles and bricks we worked 11 people we worked 10 hours 2 people on the roof of the 11th floor holding the pieces to move 20 hours, also 3 people on the roof of the 7th floor accommodating and moving to the floor 1 the material 30 hrs, also 4 people on the platform doing the demolition, 40 hrs, also 2 people on the floor 1 receiving the material that is going to be voted on the trash | JWMCD Crew | Josh McPherson | false |  |  |  |  | 11 | 10 | false |  | Swing stage | false
1658 | #NO MATCH | 2022-03-10 | Daniel/ Fredy | (7) installers (56) hours, (2) installing panels / Chanel’s(2)installing clips/ tubes(2) installing clips/ tubes (18), (1) screwing in clips all day. (7) ground guys(56) hours,(2) passing panels/cutting,(2) holding ladders for installers on roof,(2) holding rope for tubes/ passing tubes,(1) ground guy spotting swing stage . | JWMCD Crew | Rod Grove | false |  |  |  |  | 14 | 8 | false |  | 10K FORKLIFT, 85FT BOOM | false |  |  |  |  | Hat Channel Plate Tubing |  |  | 22 | 5 | [24 empty] | 180 | 8 |  |  |  |  | 100 | 3
1658 | #NO MATCH | 2022-03-10 | Daniel/Fredy | (9)installers, (5) installing (4)hours clips(110)/ poles(5), (2) installing clips on south side for (5)hours(40clips), (2) installers(16) hours, making sure panels aren’t missing screws. (5) ground guys (40)hours, (1) ground guy spotting swing stage, (2) holding ladders for installers/ making sure area is clean, (2)handing material/ taking caulking up for panels . | JWMCD Crew | Rod Grove | false |  |  |  |  | 14 |  | false |  | 10K FORKLIFT, 85FT BOOM | false |  |  |  |  | Plate Tubing |  |  | 4 | 3 | [24 empty] | 50 | 4
20067 | BNA PROJECT 5 | 2022-03-10 | Dillon Bowman / Manny Sandoval | Manny, Sterling - Inventory Management: Worked on Boom lift, Received Break Metal for Columns - Airwave North: Rework areas of concern for HP, riveting and caulking. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 2 |  | true | Break Metal for Column | 2 Booms | false
21010 | 17th & Grand | 2022-03-10 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 11 |  |  |  | Swing stage,boom lift forklift | [5 empty] | Coping Hat Channel Single Skin | 39 | 50 | [32 empty] | 1200 | 50 |  |  |  |  | 30 | 2
20067 | BNA PROJECT 5 | 2022-03-09 | Dillon Bowman / Manny Sandoval | Manny, Sterling, Keith -Incident Reported: Our delivery driver had a near-miss event with a plane on the airstrip. Met with HP and DPS before escorting driver from premises. - Walked Roof to prep for work, roof not ready for night work. - Received shipment of caulking. - GT Circulation: Installed 50' of Caulking, Inspected column flashing, four are damaged, reordered more. - Inventory Management: Craning crates and moved trailer, clean-up and tied down roof materials. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 |  | false |  | 2 Booms, Forklift | false |  |  |  |  | Flashing | [32 empty] | 50 | 2
21010 | 17th & Grand | 2022-03-09 | Fredy Véliz |  | Subcontractor | Denis Usatenko | [5 empty] | 11 |  |  |  | Swing stage,boom lift,forklift | [5 empty] | Hat Channel Single Skin | 30 | 72 | [32 empty] | 200 | 34
1658 | #NO MATCH | 2022-03-08 | Daniel/Fredy | (8) installers (64) hours,(2) installing tubes(8)/ clips(97), (2) installing panels36/Chanel’s(6),(2) installing clips(97),(2) installing clips(97),(7) ground guys(56) hours, (1) spotting swingstage on ground,(3) handing panels/ cutting, (2) holding ladders for installers,(1) holding ropes for tubes . | JWMCD Crew | Rod Grove | false |  |  |  |  | 15 |  | true | 3/8 nuts galvanized (200), 3/8 16x10 bolts(300),3/8 washer (500) | 10K FORKLIFT, 85FT BOOM | false |  |  |  |  | Hat Channel Plate Tubing |  |  | 36 | 7 | [24 empty] | 80 | 8 |  |  |  |  | 60 | 1
20067 | BNA PROJECT 5 | 2022-03-08 | Dillon Bowman / Manny Sandoval | Manny, Sterling, Keith - GT Circulation: 40' Angle Flashing, 70" Caulking. Installed 12 2x2 angle in the column. Coordinated craning with Derr of material. Walked Roof with Marc and Dillon. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 |  | false |  | 2 Booms, Forklift | false |  |  |  |  | Flashing | [32 empty] | 40 | 2
1658 | #NO MATCH | 2022-03-07 | Daniel/Fredy |  | JWMCD Crew | Rod Grove | true |  |  |  | Rain |  |  | false |  | 85ft Boom,10K Forklift | false
20067 | BNA PROJECT 5 | 2022-03-07 | Dillon Bowman / Mannh Sandoval | Manny, Sterling, Tony Jr - Install 60’ of angle flashing with various cuts and miter work. - 77’ of finish caulking - Peeled Panels in Circulation - Column install prep. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 |  | false |  | 1 Scissor, 2 Booms | false |  |  |  |  | Flashing Other | [32 empty] | 60 | 3 | [8 empty] | Caulking - 77ft - 3 hrs
21010 | 17th & Grand | 2022-03-07 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 10 |  |  |  | Swing stage,boom lift,forklift | [5 empty] | Other Single Skin | 3 | 12 | [40 empty] | House keeping and prep panels
21010 | 17th & Grand | 2022-03-05 | Fredy veliz |  | Subcontractor | Denis Usatenko | [9 empty] | Swing stage,boom lift,forklift |  |  |  | 2 |  | Hat Channel Insulation Layout Other Single Skin | 33 | 30 | [24 empty] | 240 | 4 | [6 empty] | 260 | 20 | [6 empty] | Remove panels on the north Elevation 16 hours
1658 | #NO MATCH | 2022-03-04 | Daniel/Fredy | (9) ground guys(72) hours,(3) cutting tubes/ passing tubes,(3)cutting panels/ passing panels, (1) ground spotting swingstage, (2) holding ropes making sure poles didn’t fall.(6) installers (48) hours, (2)installing tubes/ clips(54),(2) installing clips(54)/drilling holes, (2) installing panels/ Chanel’s, Mitc (3) hours, PTP, Lining guys out, Inspecting swing stage. | JWMCD Crew | Rod Grove | false |  |  |  |  | 16 |  | false |  | 85FT BOOM, 10K FORKLIFT | false |  |  |  |  | Hat Channel Plate Tubing |  |  | 32 | 14 | [24 empty] | 336 | 8 |  |  |  |  | 70 | 2
20067 | BNA PROJECT 5 | 2022-03-04 | Dillon Bowman / Manny Sandoval | Night Work - Inventory Management: Gathered forklift from MH, prep and work with crane for lifts, staking materials on north roof. - Airwave: Installed 24 panels with tracks, prepared 5 additional tracks, clean up, secured materials for weather. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 |  | false |  | 1 scissor, 2 booms | false |  |  |  |  | Overly Roof Panel | [12 empty] | 24 | 4
21010 | 17th & Grand | 2022-03-04 | Fredy veilz |  | Subcontractor | Denis Usatenko | [5 empty] | 10 |  |  |  | Swing stage,boom lift,forklift | [5 empty] | Coping Hat Channel Single Skin | 30 | 87 | [32 empty] | 62 | 15 |  |  |  |  | 60 | 10
1658 | #NO MATCH | 2022-03-03 | Daniel/Fredy | (9) ground guys 72 hours, (2) ground guys holding ladder/grabbing rope for the tubes,(1) ground guy spotting swingstage (3)passing panels/making cuts,(3)passing tubes/cutting, (6) installers 48 hours, (2) installing panels,(2)installing poles, (2)making holes in beams and installing clips(33). Mitch(3) hours, inspecting swingstag, lining guys out, PTP | JWMCD Crew | Rod Grove | false |  |  |  |  | 16 |  | true | Mag Drill, 2 bottles of oil | 85 FT BOOM, 10K FORKLIFT | false |  |  |  |  | Hat Channel Plate Tubing |  |  | 36 | 15 | [24 empty] | 96 | 8 |  |  |  |  | 20 | 1
20067 | BNA PROJECT 5 | 2022-03-03 | Dillon Bowman / Manny Sandoval | NIght Work - Manny, Sterling, Tony - Airwave: Prepared 45 tracks with gasket, Installed 27 panels with tracks and 10 pieces of gutter flashing. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 |  | false |  | 1 scissor, 2 booms | false |  |  |  |  | Flashing Overly Roof Panel | [12 empty] | 24 | 4 | [18 empty] | 50 | 2
21010 | 17th & Grand | 2022-03-03 | Fredyveliz |  | Subcontractor | Denis Usatenko | [5 empty] | 10 | [7 empty] | 10 |  | Hat Channel Layout Single Skin | 30 | 70 | [32 empty] | 380 | 40
22014 | 5th & Broad CO14 | 2022-03-03 | Chad mccoy | I started my day picking up material from mcdougal this morning. I then headed to the site. We started over the skylights installing stiffeners and panels. But on the first panel the pieces of metal from mcdougal was not sturdy enough. So we reconfigured with what materials I had and we used the L shaped brackets to hold the panels in place. I used original hardware. It had flat head Phillips and I also used the long bolts provided by josh. I also used 5/16 screws. We also sealed the pvc pipes so I would be sealed. Once all the panels were installed we cleaned all the Acm of the eye brow below the panels we installed | JWMCD Crew | Josh McPherson | false |  |  |  |  | 3 |  | false |  | 45z boom | false |  |  |  |  | Other Perforated | [42 empty] | We installed 12 L shaped angle to hold the structure of the panels. And we installed 12 panels.
1658 | #NO MATCH | 2022-03-02 | Fredy | (6) ground guys 48 hours, (2) pulling swing stage,(2) handing panels,(2) handing tubes. (6) guys tubes 48 hours(2) handing tubes,(2) receiving tubes,(2) on swingstage taking tubes. (450 clips) Mitch (3) hours ptp, inspecting swingstage, lining guys out. | JWMCD Crew | Rod Grove | false |  |  |  |  | 15 |  | false |  | 85ft BOOM, 10K FORKLIFT | false |  |  |  |  | Hat Channel Plate |  |  | 40 | 15 | [30 empty] | 60 | 1
20067 | BNA PROJECT 5 | 2022-03-02 | Dillon Bowman / Manny Sandoval | Night Work - Manny, Sterling, Tony - Took measurements of south canopy over driveway, load and lift 3 crates, set-up and clean-up gang-boxes, met with framer for ped bridge, layout roof on column lines. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 |  | false |  | 1 scissor, 2 Boom | false
21010 | 17th & Grand | 2022-03-02 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 10 |  |  |  | Swing stages,boom lift ,forklift |  |  |  | 12 |  | Hat Channel Layout Single Skin | 32 | 58 | [32 empty] | 350 | 50
21028 | Fieldhouse | 2022-03-02 | Buttrey | Painted panels | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 2 |  | false |  | None | false |  |  |  |  | Other | [42 empty] | Painted. Will finish tomorrow as long as it looks good and don't have a catastrophic event
1658 | #NO MATCH | 2022-03-01 | Mitch chancey | MITCH ON SITE FOR 2 HOURS, DOING PTP, LIFT INSPECTION, AND LINING GUYS OUT. DUE TO NES POWER SHUT DOWN, WE HAD 9 GUYS FOR 3 HOURS SORTING AND MOVING TUBES ONCE POWER WAS BACK ON. | JWMCD Crew | Rod Grove | true | NES HAD POWER SHUT DOWN UNTIL 12. SO FREDY’S GUY COULD NOT USE STAGES. |  |  |  | 15 |  | true | 300’ cord from Sunbelt | 85’ BOOM, 10K FORKLIFT | false
20067 | BNA PROJECT 5 | 2022-03-01 | Dillon Bowman / Manny Sandoval | Night Work - Manny, Sterling, Tony - Airwaves RPS: craned 4 crates to roof, prep gasket inserts, installed 30 Panels. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 |  | false |  | 1 scissor, 2 Boom | false |  |  |  |  | Overly Roof Panel | [12 empty] | 30 | 8
21010 | 17th & Grand | 2022-03-01 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 10 | [7 empty] | 8 |  | Hat Channel Insulation Layout Single Skin | 19 | 48 | [24 empty] | 480 | 36 | [6 empty] | 220 | 28
22014 | 5th & Broad CO14 | 2022-03-01 | Chad mccoy | we started our day installing the flashing on top of the Acm panels. We went from the access panel, all the way down to the skylight and we wrapped the corner. The flashing is lapped 3 inches and we tripled the caulking underneath the flashing. Once we wrapped the corner we moved to the void inside the panels. We installed all the L shaped flashing and then we installed the flashing behind the column. The idea I had didn’t work so I re worked it to work. We then put peel and stick at the outer and upper edges of the flashing. And we caulked the seams. The flashing was placed in caulking and all edges caulked. We then moved to the void where the sunlight came thru the building. I sent pics to nick and he might want to rework that area tomorrow. | JWMCD Crew | Josh McPherson | false |  |  |  |  | 3 |  | false |  | 45z boom | false |  |  |  |  | Flashing | [32 empty] | 90 | 8
22014 | 5th & Broad CO14 | 2022-03-01 | Chad mccoy |  | JWMCD Crew | Josh McPherson | false |  |  |  |  | 3 |  | false |  |  | false
1658 | #NO MATCH | 2022-02-28 | MITCH CHANCEY | UNLOADED TRUCK FROM SHOP WITH 5 CRATES OF FS47 FOR NORTH WALL 7-29. I WAS ON SITE FOR 4 HOURS. DEALING WITH TRUCK, PTP, SAFETY INSPECTIONS, TURNER, AND GETTING GUYS LINED OUT FOR THE DAY. | JWMCD Crew | Rod Grove | true | TURNER HAD GUYS ON ROOF REMOVING TUBING FROM CATWALK BEHIND SCREEN WALL. WHILE THEY WERE CUTTING ON THE EAST WE HAD TO SWITCH GEARS AND SWAP OVER TO SORTING AND INSTALLING ON NORTH. WHILE THEY CUTTING THE NORTH HAD TO STOP INSTALL AND GO TO EAST GROUND LEVEL AND SORT AND PREP PANELS. AFTER ALL SAID AND DONE THEY FINISHED CUTTING AT 12:30. SO INSTALL CONTINUED ON NORTH WALL. |  |  |  | 5 |  | true | 5 CRATES OF FS47 | 85’ BOOM, 10K FORKLIFT. | false |  |  |  |  | Hat Channel Plate |  |  | 11 | 6 | [30 empty] | 40 | 1
20067 | BNA PROJECT 5 | 2022-02-28 | Dillon Bowman / Manny Sandoval | Manny, Sterling, Tony Jr. - All Hands HP Meeting - Measure Airwave Sections - HP Meeting: Ped Bridge - HP Meeting Overly RPS QC - GT Circulation: Installed 200ft of angle flashing, Final cleaning of work area in GT Circulation. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 |  | false |  | 1 scissor, 2 boom | false |  |  |  |  | Flashing | [32 empty] | 200 | 8
21010 | 17th & Grand | 2022-02-28 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 10 |  |  |  | Swing stage,boom lift, forklift |  |  |  | 8 |  | Hat Channel Insulation Layout Single Skin | 34 | 50 | [24 empty] | 1500 | 48 | [6 empty] | 160 | 12
22014 | 5th & Broad CO14 | 2022-02-28 | Chad mccoy | Today we went over the building with nick and John. John and I walked the job to look at the lay of the land and show the area that needed work. The boom got there at 930. We took the access panel off and climbed in the panels. I measured all the trim areas and told josh what would be needed. We then started taken panels down. But the panels seemed to be more of a challenge then we thought. Nick came down and we decided to cut them out. We cut the panels out and placed them in the maintenance room. We placed moving blankets in between each panels to keep them from getting damaged . | JWMCD Crew | Josh McPherson | true |  |  |  | Clear | 3 |  | false |  | 45z | false
22014 | 5th & Broad CO14 | 2022-02-28 | Chad mccoy | Pics | JWMCD Crew | Josh McPherson | false | [6 empty] | false |  |  | false
22014 | 5th & Broad CO14 | 2022-02-28 | Chad mccoy |  | JWMCD Crew | Josh McPherson | false | [6 empty] | false |  |  | false
21010 | 17th & Grand | 2022-02-27 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 7 |  |  |  | Swing stage,boom lift, forklift | [5 empty] | Hat Channel Single Skin | 9 | 15 | [32 empty] | 260 | 35
21010 | 17th & Grand | 2022-02-26 | Fredy veliz | 4 guys helping to get helping swing stage guys to get the material to the roof | Subcontractor | Denis Usatenko | [5 empty] | 10 |  |  |  | Swing stage, boom lift , forklift |  |  |  | 4 |  | Hat Channel Layout Single Skin | 17 | 36 | [32 empty] | 510 | 50
1658 | #NO MATCH | 2022-02-25 | MITCH CHANCEY | 2.5 HOURS UNLOADING TRUCK (5 GUYS FOR 30 MINUTES) TRAFFIC CONTROL. 37.5 HOURS SORTING AND TRANSPORTING PANELS TO THE 7TH FLOOR VIA 85’(1GUY LOADING, 1 OPERATOR, 2 GUYS CATCHING AND SORTING ON 7). TOOK 4 MORE OF THE 8’ TUBE TO THE ROOF VIA EAST SWING STAGE.HUNG NEW LIFE LINES FOR THE EAST STAGE. | JWMCD Crew | Rod Grove | false |  |  |  |  | 5 |  | true | 4 CRATES OF FS47 | 85’ BOOM, 10K FORKLIFT | false
20067 | BNA PROJECT 5 | 2022-02-25 | Dillon Bowman / Manny Sandoval | Manny, Sterling, Chad, Dalton - GT Circulation: Installed 200ft of Flashing, 20ft of Mending Plate, Field Fab and Install 8 Panels, 10ft of Caulking | JWMCD Crew | Marc Ribar | false |  |  |  |  | 4 |  | false |  | 1 scissor, 2 boom | false |  |  |  |  | Flashing IMP | [8 empty] | 7 | 5 | [22 empty] | 200 | 3
20067 | BNA PROJECT 5 | 2022-02-24 | Dillon Bowman / Manny Sandoval | Manny, Sterling, Chad, Dalton - GT Circulation: Field Fab and Install 8 Panels, Gathered Flashing for base and 2" Trim from lay down. Clean-up. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 4 |  | false |  | 1 scissor, 2 boom | false |  |  |  |  | IMP | [8 empty] | 8 | 8
1658 | #NO MATCH | 2022-02-23 | MITCH CHANCEY | 39.5 HOURS SPEND BETWEEN UNLOADING TRUCK, MOVING MATERIAL. BROUGHT STAGE DOWN AND TOOK (5) 8’ TUBES TO THE ROOF. SENT BACK A CRATE AND PALLET OF SWING STAGE PARTS BACK TO THE SHOP. CALLED AND GOT THE 35’ ELECTRIC BOOM PICKED UP. CLEANED UP THE EAST ALLEY. TOOK STAGE BACK TO ROOF, PULLED POWER CABLE UP, TIED ALL LIFE LINES AND LOAD CABLES DOWN ON GROUND IN PREPARATION FOR WEATHER TOMORROW. | JWMCD Crew | Rod Grove | false |  |  |  |  | 5 |  | true | 2 BUNDLES OF 20’ TUBES, 1 BUNDLE OF 8’ TUBES, 2 PALLETS OF “CLIPS”, 2 CRATES OF MISC CLIPS. | 85’ BOOM, 10K FORKLIFT | false |  |  |  |  | Plate |  |  | 1 | 0.5
20067 | BNA PROJECT 5 | 2022-02-23 | Dillon Bowman / Manny Sandoval | Manny, Sterling, Chad, Dalton, Keith - GT Circulation: Field Fan and installed 16 Panels, Installed 20ft of Mending Plate. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 5 |  | false |  | 1 Scissor, 2 Booms | false |  |  |  |  | IMP Other | [8 empty] | 16 | 6 | [32 empty] | Mending Plate: 20ft - 2hrs
21010 | 17th & Grand | 2022-02-23 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 8 |  |  |  | Swing stage,boom lift,forklift |  |  |  | 3 |  | Hat Channel Insulation Layout Single Skin | 6 | 12 | [24 empty] | 435 | 20 | [6 empty] | 280 | 39
22004 | Potawatomi Hotel Repair | 2022-02-23 | Buttrey | Repaired 2 panels that were coming apart at the glue up joint | JWMCD Crew | Josh McPherson | false |  |  |  |  | 2 |  | false |  | 135 strait boom | false |  |  |  |  | Other | [42 empty] | Repair of 2 panels
20067 | BNA PROJECT 5 | 2022-02-22 | Dillon Bowman / Manny Sandoval | Manny, Sterling, Keith, Dalton, Chad - GT Circulation: Field Fab 9 Corner Panels, Installed 3 Corner Panels, Installed 20 Ft of Mending Plate, Clean Work Zone (HP is calling this really tightly.) | JWMCD Crew | Marc Ribar | false |  |  |  |  | 5 |  | false |  | 1 Scissor, 2 Boom | false |  |  |  |  | IMP Other | [8 empty] | 3 | 8 | [32 empty] | Install 20 Ft of Mending Plate
22004 | Potawatomi Hotel Repair | 2022-02-22 | Buttrey | Straitened a panel and put it back on with insulation built up underneath it. | JWMCD Crew | Josh McPherson | true | Icy and slippery. Very high winds |  |  | Raining mixed with ice. | 2 |  | false |  | 135 strait boom | false |  |  |  |  | Other | [42 empty] | Repair panel fix
1658 | #NO MATCH | 2022-02-21 | MITCH CHANCEY | INSTALLING REMAINING PANELS, NORTH FACE 3RD HAD TO BE NOTCHED AROUND THE GARAGE SLAB. | JWMCD Crew | Rod Grove | false |  |  |  |  | 5 |  | false |  | 85’ BOOM, 35’ ELECTRIC BOOM, 10K FORKLIFT | false |  |  |  |  | Other Plate Subgirt |  |  | 22 | 23 | [26 empty] | 100 | 1 | [10 empty] | PREPPING AND SORTING PANELS 16 TOTAL MAN HOURS
20067 | BNA PROJECT 5 | 2022-02-21 | Dillon Bowman / Manny Sandoval | Manny, Sterling, Martin, Alan, Keith, Dalton, Tony Jr, Chad - GT Circulation: Mobilize to Work Area, Install 2 Panels, Install 20ft Flashing, Field Fab 3 Corners - Murton's Hole: Received Overly shipment, Recieve JWMcD Shipment (BM09) | JWMCD Crew | Marc Ribar | false |  |  |  |  | 8 |  | true | Overly (Roadway Canopies), BM09 from JWMcD | 1 Scissor, 2 Boom | false |  |  |  |  | Flashing IMP | [8 empty] | 2 | 2 | [22 empty] | 200 | 4
21010 | 17th & Grand | 2022-02-21 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 8 |  | true | Insulation | Swing stage,boom lift ,forklift | [5 empty] | Hat Channel Insulation | [26 empty] | 720 | 25 | [6 empty] | 160 | 38
21010 | 17th & Grand | 2022-02-20 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 7 |  |  |  | Swing stage,boom lift,forklift | [5 empty] | Coping Louvre Other Trim | [24 empty] | 140 | 2 | [10 empty] | 40 | 4 |  |  | 210 | 40 | Moving materials up to level 9 for east coast elevation and taking scaffolding down to the level 5
21010 | 17th & Grand | 2022-02-19 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 7 |  |  |  | Swing stage,boom lift , forklift | [5 empty] | Coping Corrugated Hat Channel Other | [22 empty] | 10 | 35 | [10 empty] | 120 | 12 |  |  |  |  | 20 | 2 | Take leftovers materials from the roof and installing the brake metal for coping on the penthouse
1658 | #NO MATCH | 2022-02-18 | MITCH CHANCEY | SUNBELT ON SITE FINISHING INSPECTION OF EAST SWING STAGE. 2 GUYS IN STAGE , 2 GUYS ON GROUND, 1 GUY ON THE ROOF. FOR 3 HOURS EACH (15 MH). AFTER SUNBELT FINISHED, WENT BACK TO INSTALLING PANELS ON THE NORTH FACE GROUND LEVEL. | JWMCD Crew | Rod Grove | false |  |  |  |  | 5 |  | true | LIFE SAFETY D-RINGS (2X). SENT BACK PANELS TO BE REWORKED, AND EMPTY SKIDS. | 85’ BOOM, 35’ ELECTRIC BOOM, 10K FORKLIFT | false |  |  |  |  | Plate Subgirt |  |  | 19 | 24 | [26 empty] | 140 | 1
20067 | BNA PROJECT 5 | 2022-02-18 | Dillon Bowman / Manny Sandoval | Manny, Sterling, Keith, Martin, Alan, Chad, Tony Jr, Dalton - Submittal Work: Terra Cotta Sample Work - Ground Transportation: Mobilize to Work Area - Installed 40 RPS Caps, and 60 RPS Gutter Finishes. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 8 |  | false |  | 1 Scissor, 2 Booms | false |  |  |  |  | Overly Roof Panel | [12 empty] | 100 | 8
21010 | 17th & Grand | 2022-02-18 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 7 |  | true | Louver and flashing | Swing stage ,boom lift ,forklift | [5 empty] | Corrugated Hat Channel | [22 empty] | 12 | 60 | [10 empty] | 280 | 24
1658 | #NO MATCH | 2022-02-17 | MITCH CHANCEY | ALL DAY WAITING ON BOOM LIFT TO BE PICKED AND NEW ONE DROPPED OFF. WHILE WAITING I TOOK PICTURES AND INVENTORY OF ALL PANELS ON-SITE. 6 HOURS ON SITE TOTAL. | JWMCD Crew | Rod Grove | true | LIFT WAS SUPPOSE TO BE DELIVERED @ 9 AM. CALLED ROY TO CHECK ON IT. DELIVERY WAS DELAYED TWICE, FINALLY ARRIVED @ 12:30PM |  |  | RAINING AND WINDY | 1 |  | false |  | 85’ BOOM, 35’ ELECTRIC BOOM, 10K FORKLIFT | false
20067 | BNA PROJECT 5 | 2022-02-17 | Chad McCoy/ Manny | The wind was strong tonight but we worked through it. We set everything up for us to finish the night before | JWMCD Crew | Marc Ribar | true | Wind |  |  | Partly cloudy | 3 |  | false |  |  | false |  |  |  |  | AWB Flashing | [32 empty] | 160 | 1 |  |  |  |  | 1105.5 | 4
20067 | BNA PROJECT 5 | 2022-02-17 | Dillon Bowman / Manny Sandoval | Manny, Sterling, Keith, Martin, Alan - Installed and Caulk 134 Pieces of Caps and Peeled Panels, Tie Down anticipating Storm. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 5 |  | false |  | 1 Scissor, 2 Booms | false |  |  |  |  | Overly Roof Panel | [12 empty] | 134 | 8
21010 | 17th & Grand | 2022-02-17 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 7 |  | true | Single skin | Swing stage ,forklift ,boom lift | [5 empty] | Other | [42 empty] | Cuting horizontals /verticals hay channel &organizing panels per elevation
20067 | BNA PROJECT 5 | 2022-02-16 | Dillon Bowman / Manny Sandoval | Night Work - Chad, Dalton, Tony Jr. - Airwave South - Install 1650ft Waterproof Membrane, 16 Pieces of Flashing | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 |  | false |  | 1 Scissor, 2 Boom | false |  |  |  |  | Flashing Other |  |  |  | Em | [28 empty] | 80 | 2 |  |  |  |  | 1650 | 3.5
21010 | 17th & Grand | 2022-02-16 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 7 |  | true | 5 crates of single skin | Swing stage | [5 empty] | Corrugated Hat Channel Other | [22 empty] | 3 | 10 | [10 empty] | 350 | 32 | [6 empty] | Curing vertical hat Cháchel
1658 | #NO MATCH | 2022-02-15 | MITCH CHANCEY | MORNING PTP MEETING. 4 GUYS TO THE NORTHEAST CORNER OF GARAGE. WENT TO THE ROOF TO DO MORE INVESTIGATING OF THE INCIDENT YESTERDAY WITH TURNER SAFETY. CALLED SUNBELT TO ARRANGE FOR THEM TO COME OUT AND “REDO” SWING STAGES ON THE EAST WALL. THAT WAY THEY ARE CORRECTLY SET UP AND SIGNED OFF ON BY THE MANUFACTURER REP. MEETING WITH OUR SAFETY TEAM TO DISCUSS FURTHER ACTION. RELAYED MESSAGE TO NAZA, ENDED UP SENDING 6 GUYS HOME WAITING ON PANELS / STAGE TO BE RESET. | JWMCD Crew | Rod Grove | true | HAVING TO WAIT ON DECISION ON NORTH WALL. WAITING ON SUNBELT TO RESET STAGES. |  |  |  | 4 |  | false |  | 85’ BOOM, 35’ ELECTRIC BOOM, 10K FORKLIFT | false |  |  |  |  | Plate Subgirt |  |  | 39 | 8 | [26 empty] | 200 | 8
20067 | BNA PROJECT 5 | 2022-02-15 | Dillon Bowman / Manny Sandoval | Manny, Sterling, Alan, Martin, Keith - Airwave: 50 RPS Panels, 70' Waterproof Membrance, Field Fab 50 Panels for Install, Stock Roof for Night Work. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 5 |  | false |  | 1 Scissor, 2 Booms | false |  |  |  |  | Other Overly Roof Panel | [12 empty] | 50 | 5 | [28 empty] | Waterproof Membrane: 70'
20067 | BNA PROJECT 5 | 2022-02-15 | Dillon Bowman / Manny Sandoval | Night Work - Chad, Dalton, Tony : 53 Panels Across North and South. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 |  | false |  | 1 Scissor, 2 Booms | false |  |  |  |  | Flashing Other | [32 empty] | 100 | 3 | [8 empty] | Waterproof Membrane: 1500'
20067 | BNA PROJECT 5 | 2022-02-15 | Manny sandavol | We were told prior to arriving that everything was gonna be ready for us when we got there the waterproofing that was on the roof was used the rollers and everything were down in the game box we had to fly all that up before we could even get started because there was only one roll of waterproofing on the roof. Once we get everything collected and everything flown to the roof we started installing at 9:45. The green operator didn’t get there till nine-ish a couple minutes before he flew our stuff roofers stuff and window stuff. | JWMCD Crew | Marc Ribar | true | Where the roofers are going ahead of us the TPO comes down into the valley and then up and over the top part of where we got to put a piece of metal and then waterproof over it we have to unstick their TPO so we can get the metal in place. This does make it a little bit of a challenge but we got it |  |  | Calm with a breeze at 5 to 10 | 3 |  | false |  |  | false |  |  |  |  | AWB Flashing | [32 empty] | 320 | 1.5 |  |  |  |  | 1306.5 | 4.5
21010 | 17th & Grand | 2022-02-15 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 7 |  |  |  | Swing stage | [5 empty] | Corrugated | [22 empty] | 15 | 70
21068 | Walt Massey Nissan | 2022-02-15 | Marvin blanco | Waiting on ACM panels | Subcontractor | Denis Usatenko | true | The driver don't show up |  |  |  | 5 |  | false |  |  | false
1658 | #NO MATCH | 2022-02-14 | MITCH CHANCEY |  | JWMCD Crew | Rod Grove | true | NEAR MISS. SAFETY STAND DOWN UNTILL 11:30. 85’ LIFT DOWN AGAIN FOR REPAIRS. |  |  |  | 9 |  | true | RM73 1 PANEL (3277) | 85’ BOOM, 35’ ELECTRIC BOOM, 10K FORKLIFT | false |  |  |  |  | Plate |  |  | 23 | 8
20067 | BNA PROJECT 5 | 2022-02-14 | Dillon Bowman / Manny Sandoval | All Roof Panel System Work _ 20 flashings, 60 Closure Caps, and some stocking roof with caps and panels. | JWMCD Crew | Marc Ribar | true |  |  |  |  | 8 |  | false |  | 1 Scissor, 2 Booms | false |  |  |  |  | Flashing Other Overly Roof Panel | [12 empty] | 53 | 5 | [18 empty] | 100 | 3 | [8 empty] | 60 Closure Caps for the RPS System
21066 | SLC 4 Project Trident | 2022-02-13 | Naza Padron |  | Subcontractor | Marc Ribar | false |  |  |  |  | 4 |  | false |  | 2 boom lifts 60' | [5 empty] | Perforated Tubing | [22 empty] | 31 | 24 |  |  |  |  | 180 | 16
21010 | 17th & Grand | 2022-02-12 | Fredy veliz | Single skin installation include vertical hats | Subcontractor | Denis Usatenko | [5 empty] | 4 |  |  |  | Swing stage |  |  |  | 6 |  | Flashing Insulation Layout Single Skin | 13 | [25 empty] | 60 | 3 |  |  |  |  | 10 | 1
21066 | SLC 4 Project Trident | 2022-02-12 | Naza Padron |  | Subcontractor | Marc Ribar | false |  |  |  |  | 4 |  | false |  | 2 boom lifts 60' | [5 empty] | Perforated Tubing | [22 empty] | 24 | 20 |  |  |  |  | 400 | 20
1658 | #NO MATCH | 2022-02-11 | MITCH CHANCEY |  | JWMCD Crew | Rod Grove | true | 85’ LIFT WAS DOWN FOR REPAIRS FOR 45 MINUTES. NORTH AND EAST STAGES WERE DOWN FOR +/- 1 HOUR, REPLACING MOTORS AND POWER YOKE ON THE EAST STAGE. |  |  | SUNNY/ WINDY | 10 |  | true | 2 BOXES OF 14-12X1 SCREWS, 2 BOXES OF 1/4X2 1/4 TAPCONS | 85’ BOOM, 35’ ELECTRIC BOOM, 10K FORKLIFT | false |  |  |  |  | Insulation Plate Subgirt |  |  | 34 | 8 | [22 empty] | 192 | 8 |  |  | 460 | 8
20067 | BNA PROJECT 5 | 2022-02-11 | Dillon Bowman / Manny Sandoval | Manny, Sterling, Martin, Alan, Chad, Dalton, Tony Jr, Keith - Inventory Management: Flew 4 Crates of RPS via crane to roof, loaded and carried 90 angle stainless for canopy, stocked the roof with around 80 panels [tops and bottoms] - Airwave: (RPS) 28 Pieces of Flashing, 17 Lower Panels, 60 Upper Panels, Assembled joinery [appling gasket to extrusion tracks]. . .. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 8 |  | false |  | 1 Scissor, 2 Boom | false |  |  |  |  | Other | [12 empty] | 77 | 64 | [18 empty] | 280 | [10 empty] | 64
21010 | 17th & Grand | 2022-02-11 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 8 |  |  |  | Swing stage |  |  |  | 4 |  | Insulation Layout Other Single Skin | 12 | 20 | [24 empty] | 80 | 2 | [14 empty] | Moving material on the roof and cleaning the roof on the level 5 peel off panels and re screw | 68
21066 | SLC 4 Project Trident | 2022-02-11 | Naza Padron |  | Subcontractor | Marc Ribar | false |  |  |  |  | 4 |  | false |  | 2 boom lifts 60' | [5 empty] | Perforated Tubing | [22 empty] | 30 | 20 |  |  |  |  | 640 | 20
1658 | #NO MATCH | 2022-02-10 | MITCH CHANCEY |  | JWMCD Crew | Rod Grove | true |  |  |  |  | 12 |  | false |  | 85’ boom, 35’ electric boom, 10k forklift | false |  |  |  |  | Insulation Plate Subgirt |  |  | 34 | 8 | [22 empty] | 96 | 8 |  |  | 1450 | 8
20067 | BNA PROJECT 5 | 2022-02-10 | Dillon Bowman / Manny Sandoval | Manny, Sterling, Martin, Alan, Chad, Dalton, Tony Jr, Keith - Airwave: (North) 24ft Pieces of Flashing, 30 Panels Installed - Airwave: (South) 15 Pieces of Flashing, and 160ft of dry-in | JWMCD Crew | Marc Ribar | false |  |  |  |  | 8 |  | false |  | 1 Scissor, 2 Boom | false |  |  |  |  | Other | [12 empty] | 30 | [19 empty] | 550 | [5 empty] | 160 |  |  |  |  | 64
21010 | 17th & Grand | 2022-02-10 | Fredy veliz | 2 people cleaning and removing material from L 5 north 2 people moving delivered material up to L5 | Subcontractor | Denis Usatenko | true | North elevation not done in time |  |  |  | 8 |  | false |  | Swing stage | [5 empty] | Coping Insulation Other Single Skin | 22 | 23 | [24 empty] | 160 | 4 | [12 empty] | 60 | 6 |  | 6
21066 | SLC 4 Project Trident | 2022-02-10 | Naza Padron |  | Subcontractor | Marc Ribar | false |  |  |  |  | 4 |  | false |  | 2 boom lifts 60' | [5 empty] | Perforated Tubing | [22 empty] | 21 | 8 |  |  |  |  | 220 | 4
21066 | SLC 4 Project Trident | 2022-02-10 | Naza Padron |  | Subcontractor | Marc Ribar | false |  |  |  |  | 4 |  | false |  | 2 boom lifts 60' | [5 empty] | Perforated Tubing | [22 empty] | 21 | 8 |  |  |  |  | 220 | 4
21066 | SLC 4 Project Trident | 2022-02-10 | Naza padron | Progress since start date to February 10 2022 | Subcontractor | Marc Ribar | false |  |  |  |  | 4 |  | false |  | 2 boom lifts 60' | [5 empty] | Other Tubing | [22 empty] | 42 | 56 |  |  |  |  | 680 | 64
1658 | #NO MATCH | 2022-02-09 | MITCH CHANCEY |  | JWMCD Crew | Rod Grove | true |  |  |  |  | 8 |  | true | 7 CRATES OF FS12 1 SKID WITH REMAKES FOR FS48 | 85’ BOOM, 35’ ELECTRIC BOOM, 10K FORKLIFT | false |  |  |  |  | Plate Subgirt |  |  | 18 | 8 | [26 empty] | 1560 | 8
20067 | BNA PROJECT 5 | 2022-02-09 | Dillon Bowman / Manny Sandoval | Manny, Sterling, Martin, Allan, Chad, Dalton, Tony Jr, Keith -Airwave: (South) Installed 40 pieces of starter flashing, followed by 30 pieces of RPS. - Airwave: (North) Installed 20 Panels of ACM. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 8 |  | false |  | 1 Scissor, 2 Boom | false |  |  |  |  | ACM Other | 20 | 24 | [10 empty] | 30 | 40
21010 | 17th & Grand | 2022-02-09 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 10 |  | true | Insulation, panels | Swigs stage |  |  |  | 2 |  | ACM Layout Other | [22 empty] | 10 | 12
21010 | 17th & Grand | 2022-02-09 | Fredy veliz |  | Subcontractor | Denis Usatenko | [5 empty] | 8 |  | true | Insulation& panels | Swing stage |  |  |  | 2 |  | ACM Layout Other | [43 empty] | 12
21011 | Beaumeade | 2022-02-09 | Marvin blanco | 4 day waiting on material and pieces for the scaffolding | Subcontractor | Steve Fudge | true | Pieces for the scaffolding and silicone |  |  |  | 7 |  | false | [7 empty] | Other Overly Roof Panel Single Skin
1658 | #NO MATCH | 2022-02-08 | MITCH CHANCEY |  | JWMCD Crew | Rod Grove | false |  |  |  |  | 5 |  | false |  | 85' boom, 35' electric boom, 10k forklift | false |  |  |  |  | Insulation Subgirt | [26 empty] | 130 | 8 |  |  | 940 | 8
20067 | BNA PROJECT 5 | 2022-02-08 | Dillon Bowman / Manny Sandoval | Manny, William "Sterling," Martin, Allan and Tony Jr, Dalton, Keith - GT North: Per HP directive, drill two holes for conduit lines into the north elevation. - Airwave South: RPS prep, apply gasket to tracks, installed 7 starter pieces, and two panels of RPS - Airwave North: 5 knife edge panels installed. . | JWMCD Crew | Marc Ribar | false |  |  |  |  | 7 |  | false |  | 1 Scissor, 2 Booms | false |  |  |  |  | ACM Other | 5 | 5.5 | [41 empty] | 8
1658 | #NO MATCH | 2022-02-07 | Mitch Chancey |  | JWMCD Crew | Rod Grove | true |  |  |  |  | 5 |  | false |  | 85” boom, 35” electric boom, 10k forklift | false |  |  |  |  | Plate Subgirt |  |  | 16 | 8.5 | [26 empty] | 120 | 8.5
20067 | BNA PROJECT 5 | 2022-02-07 | Dillon Bowman / Manny Sandoval | Night Work - Keith, Dalton, Tony - Conditions: Icy - Conpleted dry-in for available substrate: Applied primer, and waterproof membrane to approximately 300ft | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 |  | false |  | 1 Scissor, 2 Booms | false |  |  |  |  | Other | [42 empty] | Primer and Waterproof Membrane | 5.5
20067 | BNA PROJECT 5 | 2022-02-07 | Dillon Bowman / Manny Sandoval | Manny, William "Sterling," Martin, Allan - Murtons' Hole: (Inventory Management) Prepare materials for pick-up, and prepare MH for delivery. Spent some time cleaning up per HP's emphasis. - Airwave: Move ACM materials up to airwave, uncrate and begin layout for RPS. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 4 |  | true | BM09 | 1 Scissor, 2 Booms | false
1658 | #NO MATCH | 2022-02-04 | MITCH CHANCEY |  | JWMCD Crew | Rod Grove | false |  |  |  |  | 1 |  | false |  | 35’ boom, 85’ boom. 10k forklift | false |  |  |  |  | Other | [42 empty] | Nothing installed. Was called in to move material at Turners request. | 3
20067 | BNA PROJECT 5 | 2022-02-04 | Dillon Bowman | No Crew - Rain Out | JWMCD Crew | Marc Ribar | true | Rain |  |  | Rain |  |  | false |  |  | false
20067 | BNA PROJECT 5 | 2022-02-04 | Dillon Bowman | Rainout | JWMCD Crew | Marc Ribar | true |  |  |  | Rain Out |  |  | false |  | 2 boom | false
20067 | BNA PROJECT 5 | 2022-02-03 | Dillon Bowman / Manny Sandoval | Night Work - Manny Sandoval, William Sandoval, Keith Dukarm, Dalton Polisnki, Chad McCoy - GT Circulation: Fab and Install 2 Panels, Reset Flashing - GT North: Replace 20ft Flashing with End Caps - Stair Tower of Parking Garage: Replace TC: 2 Guys, 1 HR - GT South: Final Panel above window installed, 45 ft of Window Trim. Caulking | JWMCD Crew | Marc Ribar | false |  |  |  |  | 8 |  | false |  | 1 Scissor, 2 Boom | false |  |  |  |  | IMP Other | [43 empty] | 8
20067 | BNA PROJECT 5 | 2022-02-02 | Dillon Bowman | Rain Out | JWMCD Crew | Marc Ribar | true | [6 empty] | false |  |  | false
1658 | #NO MATCH | 2022-02-01 | MITCH CHANCEY |  | JWMCD Crew | Rod Grove | false |  |  |  |  | 6 |  | false |  | 35’ boom , 85’ boom, 10k forklift | false |  |  |  |  | Plate Subgirt |  |  | 19 | 9 | [26 empty] | 180 | 9
1658 | #NO MATCH | 2022-02-01 | nick akins |  | JWMCD Crew | Rod Grove | false |  |  |  |  | 2 |  | false |  |  | false
20067 | BNA PROJECT 5 | 2022-02-01 | Dillon Bowman / Manny Sandoval | Chris Butry, Mike Russel, Tony Graves Jr - GT: 1 Fabricated Panel Installed, 40ft of Flashing, 4 Corner Panels fab'd not installed. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 |  | false |  | 1 Scissor, 2 Booms | false |  |  |  |  | Flashing Other | [32 empty] | 40 | [10 empty] | 8
20067 | BNA PROJECT 5 | 2022-02-01 | Dillon Bowman / Manny Sandoval | Night Work - Manny Sandoval, William Sandoval, Keith Dukarm, Dalton Polisnki - Airwave: 360ft dry-in, 400ft flashing, Materials Logistics | JWMCD Crew | Marc Ribar | false |  |  |  |  | 3 |  | false |  | 1 Scissor, 2 Booms | false |  |  |  |  | Flashing Other | [32 empty] | 40 | 3 | [8 empty] | Dryin - Primer, and Waterproof Membrane | 5
20067 | BNA PROJECT 5 | 2022-01-31 | Dillon Bowman (Manny Sandoval) | Airwave: Hauled Flashing and Waterproof Membrane; Crated 2 Crates of RPS and 1 Gang Box; Install 14 Panels of ACM. - GT-Circulation: Remove panels for HP truss repairs. | JWMCD Crew | Marc Ribar | false |  |  |  |  | 8 |  | true | Reveals for FS03 and Partial for FS08 | 1 Scissor, 2 Boom | [5 empty] | ACM | 14 | 8
19028 | Kistler Rolled Panels | 2022-01-26 | Chad mccoy | We started our morning realizing that the panels were made to be cut out around the perimeter of the ceiling in the elevator shaft. What this means is that I would’ve had to cut each individual tube out and there is 12 of them around three sides and I would’ve had to cut 4 inches wide by an inch and a half deep in each panel and what this would’ve caused is it would’ve caused the panels to be flimsy. Megan told us to simply but up to them so that’s what I did. The first panel was crucial it took a little bit of time because it needed to line up with the joints on the outside and it needed to follow the wall where it tapered. The three panels with the taper were different lengths. So no matter what I couldn’t line the first one up perfectly with the middle one and I could line the third one perfectly with the metal one so we split the difference and it is what it is. Five out of the six soffit panels had to be cut and routed. There was five outlet boxes that had to be laid out and cut out so that a firebox and four cover caps could go on. I also had to cut around conduit that ran up the wall and up the outside of the beams. The four outside panels had to have the width changed to match the inside dimension of the steel. And of course the last three panels the longer panels was 12 inches too long so they had to be cut to fit. All the panels had to be installed with one guy on a ladder being tied off in another guy on top of the elevator system being tied off due to the limited access for other ladders or scaffolding. | JWMCD Crew | Chris Ball | true | Obstacles in ceiling, outlets, firebox outlet, conduit, 4x6 steel tubing, all for cutting, And we had to stand on top of the elevator and elevator I beam |  |  | Windy and cold | 3 |  | false |  |  | false |  |  |  |  | ACM | 6
19028 | Kistler Rolled Panels | 2022-01-25 | Chad mccoy | We started today laying out and installing the wall panels in the elevator. The very first panel was over 13 foot tall I would not fit in the bottom door so it had to be taken through the second floor door and handed down on the edge of the elevator to walk it into position. The left-hand side panels needed minor modifications to install the right hand side panels had to have multiple modifications +4 x 4 holes cut in them, plus a ibeam , plus electrical tubes. The left and the right side of the structure had no wood blocking going up we had to wait for her to open the structure just to be able to attach our panels where they need to go. One panel had to be cut in half one panel had to be cut into three pieces and then the last panel had to be cut in half so this may the total panels installed 10 instead of six. There was multiple layouts that had to be established and on certain panels there was multiple sides that had to have a layout for a different penetration I was going to thru the panel | JWMCD Crew | Chris Ball | true | There was a couple of occasions where we had to reposition the elevator to get a panel in and at the same time we had to have a person below the elevator and people on top the elevator that way that we could install the panel because the panels were 13 and 12 foot tall. The crazy amount of penetrations in these panels it made no sense on the panel layout with three panels of the wall these panels should’ve been broken down into six panels or eight panels and each penetration have their own joint. |  |  | Rain all day | 3 |  | false |  |  | false |  |  |  |  | ACM | 10
19028 | Kistler Rolled Panels | 2022-01-24 | Chad mccoy | We started our day going thru all what we left behind to make sure it was all still there. We went and got the damaged panels that Woodward took down and we installed clips on them so we could install them. The trickiest part of today was getting the scaffolding every where we needed it. We installed the two panels on the 3 level patio. And then we went and went thru all the left over panels to get the closest size we could fine. Once we got to the roof we had to get all scaffolding to the 34 floor and put it together. I had to lay out for a scupper and a electric outlet. We also had to measure all the panels for Jason. And mark certain ones on the prints for him. | JWMCD Crew | Chris Ball | true | The scaffolding moving and erecting was horrible. The elevator on.y went to 31. So everything had to but carried up the stairs |  |  | Rain | 3 |  | true | I brought a trailer with scaffolding and two boxes. |  | false |  |  |  |  | Other | [42 empty] | Fasade panels. 3
19028 | Kistler Rolled Panels | 2022-01-18 | Chad mccoy | We hung the rest of the panels today on the attraction. We also finished hanging and peeling the panels on the gas door. We started cleanup as well on the grounds and prepping for tomorrow’s cleanup and caulking day to finish out the attraction besides the elevator shaft. I have sent multiple images of this elevator shaft that were coming back to do next week and I have a meeting with Megan in the morning over it and it’s going to be horrible. At one point of the curtain wall on the attraction class is higher than the other section of glass so I called Jason and Megan and made sure that they were aware that the panels we’re gonna hang 3 inches below the section of glass and there’s no way that we could’ve fixed it because I have to stay plum level and square and we have a two inch system depth. We also search the entire site for backer rod this was something that Jason was supposed to bring back with him when he brought the trailer so that we can load everything up to go home this weekend but I went to Lowe’s and I bought some and I spent $36 on masking tape and 60 feedback rod. The last panel that we added to the guest room door has scratches and a dent in it but it’s the only panel that goes there and I don’t have one to replace it that’s in better shape | JWMCD Crew | Chris Ball | false |  |  |  |  | 4 |  | false |  | 125z, 32foot scissor | false |  |  |  |  | ACM Other | 3 | [41 empty] | Cascade panel on gas door
19028 | Kistler Rolled Panels | 2022-01-17 | Chad McCoy | We continued installing after Sunday’s work we also prepped the panel on the cash store and prep the gas door with the brackets at the panel hangs on we peeled all the panels and we started cleaning. The corner did not want to fit the structure when we tried to put it on so it took a couple of attempts and some modifications to the building and to the corner to get it to fit due to the area that the corner had to be hung it took all four of us to hang this panel two and a scissor one of the roof and one of the boom. We were also told by Megan that the panels that are on the tall wall we’re supposed to line up with the joints on the stone but due to the panel sizes there’s no way that this could’ve happened the panels were 3/8 bigger than the stone and the panels are supposed to have a half inch joint but the stone only has a 3/8 joint so there’s no way that we’ve could’ve done this | JWMCD Crew | Chris Ball | false |  |  |  |  | 4 |  | false |  | 125z boom. 32 foot scissor | false |  |  |  |  | ACM | 3
19028 | Kistler Rolled Panels | 2022-01-15 | Chad mccoy | Besides having to modify panels it was a pretty good day, Each panel has to have a type of modification to it either it’s cutting in routing or it simply cutting it down to size or it’s drilling holes in counter so I can come or it’s all of the above | JWMCD Crew | Chris Ball | true | Simply having to modify the panels to the original prints just takes time |  |  | Raining | 4 |  | false |  | 125z. Scissor lift | false |  |  |  |  | ACM | 10
19028 | Kistler Rolled Panels | 2022-01-11 | Chad mccoy | We installed all the hat channel that we could and we work the problem or try to work the problem with the damaged panels from the storm. Upon looking into how to secure the panels that we’re going to put up I noticed that the install does not match the prints | JWMCD Crew | Chris Ball | false |  |  |  |  | 4 |  | false |  | 125 z boom. 32 ft scissor | false |  |  |  |  | Subgirt | [30 empty] | 325
19028 | Kistler Rolled Panels | 2022-01-10 | THEREALMCCOY Chad McCoy | We have panels on site. But none of them are starter panels. They are a random assortment. We are going to install every panel we can and await for other equipment we have angled steel that has to be cut out of soffit panels | JWMCD Crew | Chris Ball | true | We need those other panels. Or equipment for storm damage |  |  | Clear/cold | 4 |  | false |  |  | false |  |  | 1.5 |  | ACM Layout | 4
19028 | Kistler Rolled Panels | 2022-01-08 | Chad mccoy | We install the corners today, These corners had to be modified on multiple sides for installation we also had to figure out a way to put somebody on the roof and have them stationary to help hold the panel in place when we said it these panels did not fit in the basket. We did get them they are installed after those two corners were installed we had to peel the wall next to the event area and I had to clean the entire wall because of all the glue residue that is on this wall in the bottom four panels are the panels at the paint is peeling off of. It is very time-consuming to have to modify these panels in the field on multiple edges when I know the building was scanned the structure was measured and we had the previous panels to look at and go by | JWMCD Crew | Chris Ball | true | The glue down in Tampa I felt like came off better than this glue that is attached to these panels but having to clean these panels is time consuming |  |  | Two storms came through nothing bad | 4 |  | false |  | 125 boom | false |  |  | 2 |  | ACM Layout | 3
19028 | Kistler Rolled Panels | 2022-01-07 | Chad mccoy | We were asked to start working on a certain side of the building today due to a photo shoot that they did not want the boom lift in the pictures, but because we don’t have all the panels I had to relay out other sections of the wall and start from scratch instead of continuing a continuous installation, Woodward started cutting the wall back today but they cut 1 foot stopped covered it up and left, We got asked today to move material to make a water walkway for pedestrians. | JWMCD Crew | Chris Ball | true | A constant delays going to be that each panel Has to be prepped for cut routed to a specific spot instead of them being ready to install like every other job |  |  | cold and cloudy | 4 |  | false |  | 125 z boom | false |  |  |  |  | ACM Other | 7 | [41 empty] | Hat channel, Layout had to be transferred from one side of the building to the other side of the building so that we can make sure that joints were going to line up but if you look at the prints no joints lineup anywhere
19028 | Kistler Rolled Panels | 2022-01-06 | Chad McCoy | ALL PANELS NEED CUT AND ROUTED, | JWMCD Crew | Chris Ball | true | All panels have to be modified and extruded, the structure is not the same in any location, |  |  | Clear With small storms | 4 |  | true | Flat stock and one crate of loose material | 125 z | false |  |  | 2 |  | ACM Layout Other | 12 | [41 empty] | Hat channel was installed. On the layout I had to make decisions with layout on the wall. And then transfer to panels for field cuts 12- 2 panels removed and modified and reinstalled
19006 | Kistler Rolled Panels | 2021-12-30 |  |  | JWMCD Crew | Chris Ball | false | [6 empty] | false |  |  | false
19006 | Kistler Rolled Panels | 2021-12-30 |  |  | JWMCD Crew | Chris Ball | false | [6 empty] | false |  |  | false
21010 | 17th & Grand | 2021-12-29 | Chad McCoy | We tried installed the louver on the 5 floor with Dennis. It over hung brick edge by 1/4. I took the louver apart and I cut 7/8 off of it and rebuilt it. And then we lugged it up to the 5;floor up the stairs and installed it | JWMCD Crew | Denis Usatenko | true | Louver hole to small, louver had to have all fins cut to make smaller, |  |  | Cloudy | 2 |  | true | Tapcons screws snacks | Scissor lift | false |  |  |  |  | Flashing Other | [32 empty] | 12 | [9 empty] | Louvers
21010 | 17th & Grand | 2021-12-29 | Chad McCoy | Pics only | JWMCD Crew | Denis Usatenko | false |  |  |  |  | 2 |  | false |  |  | false
19006 | Kistler Rolled Panels | 2021-12-19 | Chad McCoy | We went in today to try and wrap up an end early on the TIAA cluster that’s going on. When we started installing to the left of the smoke room this is the widest coping that we have it is 21 1/4 or 21 5/16 inside diameter on the coping when you measure the cleats on the top they range from 21 1/4 to 21 3/8. So the combination of the front of the cleats being too big now I have coping that is the same inside diameter as the outside diameter of the cleats on the top and we are fighting the railing system that the glass is being held up in. The coping is so tight trying to hook the front and bring it over that it is leaving score marks on the inside of the coping where it drags along the edge of the cleat when you curl the coping from front to back to engage it. At some points with this coping the back cleat sticks down below the coping and half an inch so if you’ve got to engage it into a half inch return you have 1 inch of travel that you must accomplish before it all engage and there is absolutely no way that this is possible. Due to it Being Sunday as soon as we saw that we could not install this coping without modifying either Cloete or coping I called the day we cleaned up and left because there’s no reason to do this or double time when it can be done on straight time if we were swinging and banging on install with the rest of it yes but I made a car we left early | JWMCD Crew | Chris Ball | true | Coping |  |  | Sunny | 5 |  | false |  | 135 boom/ lull | false |  |  |  |  | Coping | [40 empty] | 24 | 6
21028 | Fieldhouse | 2021-11-08 | Rick Hearn | Started replacing all perf panel hex screws with Powder coated phillips, took measurements for ACM panels beyond front steel on 1st story | Subcontractor | Drake De Tomasi | false |  |  |  | Clear | 2 |  | false |  | Scissor | [5 empty] | Plate |  |  |  | 5.5
21028 | Fieldhouse | 2021-11-05 | Rick Hearn | Finish caulking west side of FHJ | Subcontractor | Drake De Tomasi | false |  |  |  | Normal | 2 |  | false |  | 150 ft boom | [5 empty] | ACM | 0 | 8
21028 | Fieldhouse | 2021-11-04 | Rick Hearn | Peeled all and caulked some of the previously installed panels | Subcontractor | Drake De Tomasi | true | Secured missing panel at Mcd shop at 2:00, took to site and field fabbed and installed |  |  | Normal | 2 |  | false |  | 150ft boom | [5 empty] | ACM | 1 | 10
21028 | Fieldhouse | 2021-11-03 | Rick Heran | Installed 8 panels on top story | Subcontractor | Drake De Tomasi | true | Missing top story final panel |  |  | Cold |  |  | false |  | 150 ft boom | [5 empty] | ACM | 8 | 10
21028 | Fieldhouse | 2021-11-02 | Rick Hearn | Installed 2nd row west side window panels | Subcontractor | Drake De Tomasi | false |  |  |  | Normal | 2 |  | true | 150ft boom | 150ft boom | [5 empty] | ACM | 9 | 10
21028 | Fieldhouse | 2021-11-01 | Rick Hearn. FHJ | Lost use of onsite boom. 150ft boom ordered for tues | Subcontractor | Drake De Tomasi | true | Lack of lift |  |  | Normal |  |  | false |  | 0 | [5 empty] | ACM | 1 | 7
21028 | Fieldhouse | 2021-10-31 | Rick Hearn | 2nd story band above windows, FHJ | Subcontractor | Drake De Tomasi | false |  |  |  | Clear | 2 |  | false |  | AMI Boom | [5 empty] | ACM | 8 | 8
21028 | Fieldhouse | 2021-10-28 | Buttrey |  | JWMCD Crew | Drake De Tomasi |  |  |  |  | Rain | 5 |  |  |  | Scissor | [5 empty] | ACM | 5 | 10
21028 | Fieldhouse | 2021-10-27 | Buttrey |  | JWMCD Crew | Drake De Tomasi |  |  |  |  | Shitty | 5 |  |  |  | Scissor |  |  |  | 2 |  | ACM Layout Perforated | 1 | 3 | 5 | 31
21028 | Fieldhouse | 2021-10-26 | C Buttrey | Two guys did a second coat on the framing then everyone was on perforated panels. Took quite a bit of time to sort through the panels. | JWMCD Crew | Drake De Tomasi |  |  |  |  | Cloudy | 5 |  |  |  | Scissor | [5 empty] | Perforated |  |  | 8 | 61
21028 | Fieldhouse | 2021-10-25 | Chris Buttrey | Over weekend they guys took down all the old fencing material and ground the welds. Monday we moved all panels up to level 5 for the roof during the rain then came back and put a coat of paint on all the framing. | JWMCD Crew | Drake De Tomasi |  |  |  |  | Wind and rain | 5 |  |  |  | Scissor
21028 | Fieldhouse | 2021-10-21 | Chris Buttrey | Demoing the fence and track from the frames in the valet parking area | JWMCD Crew | Drake De Tomasi | false |  |  |  | Overcast | 3 |  | false |  | 1 scissor
21028 | Fieldhouse | 2021-10-20 | Chris Buttrey | Took down old subgirt and insulation, sealed the holes and reinstalled the new stuff and put on the corner flashing. Also brought down all materials from removal down from multiple levels of the roof. | JWMCD Crew | Drake De Tomasi | false |  |  |  |  | 3 |  | false | [7 empty] | Flashing Insulation Single Skin Subgirt | [6 empty] | 5 | 4 | [18 empty] | 10 | 1 |  |  | 60 | 1 | 15 | 1
21028 | Fieldhouse | 2021-10-19 | Chris Buttrey | Rest of time was setting up swing stage, moving material down levels and removing the old sub girt and insulation | JWMCD Crew | Drake De Tomasi | false |  |  |  | Sunny | 3 |  | false | [7 empty] | Insulation Single Skin Subgirt | [6 empty] | 4 | 2 | [18 empty] | 200 | 1 |  |  | 50 | 1
25031 | LLU Mars US Warehouse | 2021-03-19 | Abner aguilar | We put all the cooping | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | No |  | Coping | [40 empty] | 16 | 44
25031 | LLU Mars US Warehouse | 2021-03-19 | Abner aguilar | We clean the site and peel all the acm paper and get 2 palltes of dilvey acm panel | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | No |  | Coping | [40 empty] | 6
25031 | LLU Mars US Warehouse | -1 | Abner aguilar | The had ofanother trade and accident so they stop us for 2 hour for the ambulance to entre and we went to a meeting | Subcontractor | Laura Forero | No |  | No |  | Cloudy | 4 | 44 | No |  | Boom lift | No |  |  | Yes | West | ACM | 14 | 44
24045 | TMMMS Childcare |  | Heyvi | We've finished all the ACM except for two panels that we'll manufacture on Friday. We have a problem with the top of the fiber cement. We need you to fix that problem as soon as possible. | Subcontractor | Chris Buttrey | true | Lightning and thunder | true |  | 2 hours | 3 | 8 | true |  | Lift | false |  |  |  |  | ACM |  | 8
24077 | IAD 667 TI | 2026-04-17 | Fredy veliz | Elevation sc3 we working on the lats section ,the channels already been installs we will do braces and blades on monday | Subcontractor | Chris Buttrey | No |  | No |  | Hot | 6 | 54 | No |  | 2 150 articulate boom lifts ,65 straight boom lift ,10k load | No |  |  | No |  | Louvre | [24 empty] | Installing blades levation sc3 section 2 and 3 | 54

## Comments
Row 862 | its been corrected | Nick Akins | 10/24/25 8:47 AM
Row 862 | wrong job. wrong pictures. looks like MCH | Chris Ball | 10/24/25 4:53 AM
| @nakins@jwmcd.com | Chris Ball | 10/24/25 4:54 AM
Row 923 | these pictures are working @nakins@jwmcd.com | Chris Ball | 10/15/25 8:23 AM
Row 948 | @nakins@jwmcd.com WHAT DATE SHOULD I USE FOR THIS? | Cole Norona | 06/09/25 8:31 AM
Row 1589 | @nakins@jwmcd.com WRONG JOB #? | Cole Norona | 06/09/25 8:15 AM
Row 1746 | @nakins@jwmcd.com no photos were included in this entry | Cole Norona | 05/06/25 4:48 AM
Row 1826 | @nakins@jwmcd.com the job number they used is a brand new job. do you know which job this is for? | Cole Norona | 04/16/25 5:40 AM
Row 1869 | @nakins@jwmcd.com no photos were provided for this entry | Cole Norona | 04/04/25 7:25 AM
Row 1923 | @nakins@jwmcd.com @wmcdougall@jwmcd.com this is a blank photo. let me know if you want this added to the job folder | Cole Norona | 04/01/25 6:57 AM
Row 1946 | @nakins@jwmcd.com What is the job number for this? | Cole Norona | 03/20/25 10:35 AM
Row 1958 | no need. thank you | Nick Akins | 04/02/25 5:25 AM
Row 1958 | @wmcdougall@jwmcd.com @nakins@jwmcd.com picture is blank. do you want me to add to folder? | Cole Norona | 04/01/25 7:09 AM
Row 1978 | @cvanmeter@jwmcd.com Please ask Marvin to either correct the date or provide you with a correct date so I can fix this in your job folder. For now, I used 3.11 | Cole Norona | 03/05/25 6:12 AM
| I reached out to him, if he is able to it will be corrected. | Colton Van Meter | 03/05/25 2:01 PM
| Thank you! If easier I can update the date! | Cole Norona | 03/05/25 4:12 PM
Row 1992 | @nakins@jwmcd.com What is the correct date? | Cole Norona | 03/05/25 6:12 AM
Row 2006 | @nakins@jwmcd.com Which job is this for? Looks like they inputted a brand new job number that shouldn't be installing just yet | Cole Norona | 03/07/25 10:27 AM
| Maybe 24023? | Cole Norona | 03/07/25 10:28 AM
Row 2342 | @nakins@jwmcd.com Which job does this belong to? | Cole Norona | 11/25/24 10:01 AM
| 23054, I fixed it. Best, NICK AKINS Field Operations Manager / Project Manager John W. McDougall Inc. 832.948.2317 ¦ jwmcd.com | Nick Akins | 11/25/24 10:47 AM
Row 4528 | Alpolic has been notified and I'm still waiting on a response that we can move forward with. material arrived in 5 different batches. I have asked Chad to pull the remainder of the canopy panels so we can determine how far the color variation is. I will loop @nakins@jwmcd.com in as soon as i have more information. | Josh McPherson | 05/26/22 6:39 PM
Row 4915 | @nakins@jwmcd.com I am assuming the date for this is 7/24? I used that so let me know if not | Cole Norona | 07/25/25 8:03 AM

## Summary
Panel/ACM MH | 0.47613
Plate Panel/Plate Panels MH | 0.76248
Single Skin Qty Installed/Single Skin MH | 1.741
IMP Qty Installed/IMP MH | 0.37358
Overly Roof Panels Qty/Overly Roof Panels MH | 1.0051
Genesis Panel Qty Installed/Genesis Panel MH | 5.5987
Caulking LF Installed/Caulking MH | 11.5353
Corrugatesd Screens/Corrugated-Screen Wall MH | 1.1218
Louvre Qty Installed/Louvre MH | 0.34227
Insulation SQFT Installed/Insulation MH | 31.2996
Tubing Linear Ft Installed/Tubing MH | 8.632
Subgrit Zee Linear Ft Installed/Subgrit Zee MH | 15.3884
Flashing Linear Ft Installed/Flashing MH | 8.975
Hat Channel Linear Ft Installed/Hat Channel MH | 12.5928
Trim Linear Ft Installed/Trim Install MH | 14.8508
AWB SQFT Installed/AWB MH | 117.439
Coping Linear Ft Installed/Coping MH | 9.8644