## PMO Summary Rollup
PROJECT DASHBOARD LINK | JOB NAME | SHORT JOB NO | Type | JOB HEALTH | Budget Health | Job Number | Job Number 2 | % COMPLETE | START DATE | FINISH DATE | PM | Budget % Spent | CONTRACT VALUE | INITIAL BUDGET | CHANGE ORDER BUDGET | Current Cv | CURRENT BUDGET | ACTUAL COST | Committed Cost | PROJECTED SPEND | BUDGET REMAINING | BUDGET TO BE ALLOCATED | Amount Received to date (CASH RECEIVED) | Recognized Revenue (Earned) | Account Billed (Amount Billed to Date) | Last Billing Date | Left to bill | Backlog | AMOUNT BILLED TO DATE | BILLING POSITIVE | Received - Actual Cost | Profit | Current Margin | Initial Margin | MARKUP INITIAL BUDGET % | MARKUP CHANGE ORDER % | Change Order Sell | Total Value of Executed Change Orders | Total Value of Submitted Change Orders | Total Value of Rejected Change Orders | Total Value of Voided Change Orders | Total CV - AC- CC-PS | Spectrum CV | Spectrum minus Smartsheet | Archive Project
Project Dashboard | 1000 Church YMCA | 23028 | Supply + Install | Green | Green | 101023028 | 101023028 | 98% | 2023-07-27 | 2026-05-29 | Dillon Bowman | 95.51% | 184830 | 134700 | 11775 | 200950.14 | 146475 | 139897.47 | 0 | 6577.53 | 0 | 0 | 197337 | 191927 | 197337 | 2025-10-23 | 3613.14 | 9023.14 | 197337 | 57439.53 | 57439.53 | 54475.14 | 27.11% | 27.12% | 37.22% | 36.9% | 16120.14 | 11775 | 0 | 0 | 0 | 54475.14 | 200950.14 | 0
Project Dashboard | BNA Concourse D | 23029 | Supply + Install | Green | Green | 101023029 | 101023029 | 98% | 2024-07-01 | 2026-01-19 | Marc Ribar | 99.96% | 5099000 | 3902000 | 61873 | 5192967 | 3877779.06 | 3876138.77 | 0 | 1638.14 | 2.15 | 2.15 | 5044901 | 5190889 | 5192967 | 2026-04-15 | 0 | 2078 | 5192967 | 1316828.23 | 1168762.23 | 1315187.94 | 25.33% | 23.48% | 30.68% | 51.87% | 93967 | 61873 | 0 | 0 | 0 | 1315190.09 | 5192967 | 0
Project Dashboard | Equinix DC2 | 23051 | Supply + Install | Green | Green | 101023051 | 101023051 | 100% | 2023-12-29 | 2025-10-22 | Dillon Bowman | 96.81% | 241000 | 168123 | 4900 | 248000 | 141060.97 | 136560.85 | 4500 | 0.12 | -1.09e-13 | -1.09e-13 | 248000 | 240088 | 248000 | 2025-12-23 | 0 | 7912 | 248000 | 111439.15 | 111439.15 | 106939.03 | 43.12% | 30.24% | 43.35% | 42.86% | 7000 | 4900 | 0 | 4840 | 0 | 106939.03 | 248000 | 0
Project Dashboard | GCDC Building 2/VA1.2 | 24005 | Supply + Install | Green | Green | 101024005 | 101024005 | 99% | 2024-02-01 | 2026-03-16 | Joe Hoyle | 98.86% | 3065000 | 2083294.25 | 150550 | 3287436 | 1715844.25 | 1696246.94 | 442.35 | 19154.96 | -1.6342e-12 | -1.6342e-12 | 3262687 | 3249856 | 3269473 | 2025-12-19 | 17963 | 37580 | 3269473 | 1573226.06 | 1566440.06 | 1571591.75 | 47.81% | 32.03% | 47.12% | 47.75% | 222436 | 150550 | 20000 | 0 | 0 | 1571591.75 | 3269473 | -17963
Project Dashboard | VUMC MCE 3rd Floor | 24012 | AMI | Green | Green | 101024012 | 101024012 | 100% | 2024-02-14 | 2026-02-06 | Laura Forero | 100% | 11500 | 9020 | 0 | 11500 | 5880.17 | 5880.17 | 0 | 0 | 0 | 0 | 11500 | 11500 | 11500 | 2025-12-23 | 0 | 0 | 11500 | 5619.83 | 5619.83 | 5619.83 | 48.87% | 21.57% | 27.49% | 0% | 0 | 0 | 0 | 0 | 0 | 5619.83 | 11500 | 0
Project Dashboard | QTS-NAL1-DC1 | 24018 | Supply + Install | Green | Red | 101024018 | 101024018 | 95% | 2024-02-21 | 2026-02-13 | Joe Hoyle | 99.46% | 1850000 | 1361434 | 764641.23 | 2895314.98 | 1921346 | 1910900.78 | 331.44 | 32921.03 | -22807.25 | -22807.25 | 2691789 | 2857675 | 2895314 | 2026-04-15 | 0.98 | 37639.98 | 2895314 | 984413.22 | 780888.22 | 973968.98 | 33.64% | 26.41% | 35.89% | 36.71% | 1045314.98 | 764641.23 | 6457.5 | 0 | 0 | 951161.73 | 2895314.98 | 0
Project Dashboard | QTS PJC1 DC1 | 24019 | Supply + Install | Green | Green | 101024019 | 101024019 | 95% | 2024-02-26 | 2026-07-13 | Dillon Bowman | 95.37% | 2209000 | 1597686 | 158000 | 2439967 | 1656951.99 | 1580239.4 | 0 | 76712.59 | 2.9559e-12 | 2.9559e-12 | 2317968 | 2326996 | 2439967 | 2025-11-21 | 0 | 112971 | 2439967 | 859727.6 | 737728.6 | 783015.01 | 32.09% | 27.67% | 38.26% | 46.18% | 230967 | 158000 | -117415.36 | 0 | 200500 | 783015.01 | 2439967 | 0
Project Dashboard | USA Med School | 24022 | Supply + Install | Green | Red | 101024022 | 101024022 | 80% | 2024-03-08 | 2026-07-31 | Cole Norona | 35.27% | 98880 | 72028.2 | 0 | 98880 | 72028.2 | 25406.63 | 0 | 46694.57 | -73 | -73 | 47700 | 34874 | 53000 | 2026-02-20 | 45880 | 64006 | 53000 | 27593.37 | 22293.37 | 26851.8 | 27.16% | 27.16% | 37.28% | 0% | 0 | 0 | 0 | 15653 | 630 | 26778.8 | 98880 | 0
Project Dashboard | 1740 Division | 24026 | Supply + Install | Green | Green | 101024026 | 101024026 | 91% | 2024-04-12 | 2026-05-06 | Chris Buttrey | 40.96% | 204000 | 151975 | 8338.11 | 218138.11 | 160313.11 | 65658.34 | 0 | 94654.77 | 9.9476e-14 | 9.9476e-14 | 124325 | 89349 | 146369 | 2026-03-10 | 71769.11 | 128789.11 | 146369 | 80710.66 | 58666.66 | 57825 | 26.51% | 25.5% | 34.23% | 69.56% | 14138.11 | 8338.11 | 0 | 0 | 0 | 57825 | 218138.11 | 0
Project Dashboard | CHI Memorial Hospital | 24028 | Supply + Install | Green | Red | 101024028 | 101024028 | 100% | 2024-04-23 | 2025-09-09 | Josh McPherson | 95.16% | 1123712 | 845223 | 171709.25 | 1344227.31 | 1053372.49 | 1002358.93 | 3433.59 | 48897.75 | -1317.78 | -1317.78 | 1050702 | 1279166 | 1167447 | 2025-11-24 | 176780.31 | 65061.31 | 1167447 | 165088.07 | 48343.07 | 290854.82 | 21.64% | 24.78% | 32.95% | 28.42% | 220515.31 | 171709.25 | 0 | 0 | 527943 | 289537.04 | 1344227.31 | 0
Project Dashboard | Vantage TX-21 | 24030 | Supply + Install | Green | Red | 101024030 | 101024030 | 91% | 2024-04-26 | 2026-06-26 | Chris Buttrey | 87.98% | 1595000 | 1191414 | 45000 | 1666552 | 1036414 | 911785.63 | 18743.81 | 105994.07 | -109.51 | -109.51 | 1329750 | 1466232 | 1477500 | 2026-02-09 | 189052 | 200320 | 1477500 | 565714.37 | 417964.37 | 630138 | 37.81% | 25.3% | 33.87% | 59% | 71552 | 45000 | 160651.2 | 0 | 0 | 630028.49 | 1666552 | 0
Project Dashboard | AJ Capital 3 | 24031 | AMI | Green | Red | 101024031 | 101024031 | 100% | 2024-04-16 | 2026-01-15 | Laura Forero | 100.2% | 48000 | 35969 | 11040 | 62612 | 41019.63 | 41092.63 | 0 | 0 | -73 | -73 | 62612 | 62612 | 62612 | 2025-12-23 | 0 | 0 | 62612 | 21519.37 | 21519.37 | 21592.37 | 34.49% | 25.06% | 33.45% | 32.36% | 14612 | 11040 | 0 | 0 | 0 | 21519.37 | 62612 | 0
Project Dashboard | Courtesy Chevrolet GMC | 24038 | Supply Only | Green | Green | 101024038 | 101024038 | 26% | 2024-06-03 | 2026-02-18 | Laura Forero | 0.09466% | 12980 | 8736.64 | 0 | 12980 | 8736.64 | 8.27 | 0 | 8728.37 | 0 | 0 | 0 | 11 | 0 | 2026-04-01 | 12980 | 12969 | 0 | -8.27 | -8.27 | 4243.36 | 32.69% | 32.69% | 48.57% | 0% | 0 | 0 | 0 | 0 | 0 | 4243.36 | 12980 | 0
Project Dashboard | The Visionary | 24039 | Supply + Install | Green | Red | 101024039 | 101024039 | 98% | 2024-07-01 | 2026-05-07 | Carlos Silva | 90.08% | 3928900 | 3027957 | 0 | 3928900 | 3027957 | 2727602.09 | 169162.48 | 137282.08 | -6089.65 | -6089.65 | 2989440 | 3529330 | 3615100 | 2026-03-20 | 313800 | 399570 | 3615100 | 887497.91 | 261837.91 | 900943 | 22.93% | 22.93% | 29.75% | 0% | 0 | 0 | 46060 | 0 | 0 | 894853.35 | 3928900 | 0
Project Dashboard | TMMMS Childcare | 24045 | Supply + Install | Green | Green | 101024045 | 101024045 | 100% | 2024-07-05 | 2025-11-28 | Chris Buttrey | 100% | 800000 | 600623 | 24900 | 842283.12 | 628486.98 | 628486.98 | 0 | 0 | 0 | 0 | 800168 | 842283 | 842283 | 2025-12-15 | 0.12 | 0.12 | 842283 | 213796.02 | 171681.02 | 213796.14 | 25.38% | 24.92% | 33.2% | 69.81% | 42283.12 | 24900 | 2963.98 | 47000 | 0 | 213796.14 | 842283.12 | 0
Project Dashboard | UAB Biomedical Research and Psycholgy | 24046 | Supply + Install | Yellow | Red | 101024046 | 101024046 | 98% | 2024-07-15 | 2026-02-16 | Wylie McDougall | 94.01% | 4039750 | 3152309 | -58770.5 | 3952097.26 | 2957940.03 | 2780674.64 | 55378.63 | 122383.19 | -496.43 | -496.43 | 3413909 | 3715366 | 3926347 | 2026-03-20 | 25750.26 | 236731.26 | 3926347 | 1145672.36 | 633234.36 | 994157.23 | 25.16% | 21.97% | 28.15% | 49.14% | -87652.74 | -58770.5 | -16546 | 0 | 19635 | 993660.8 | 3952097.26 | 0
Project Dashboard | QTS NAL2 DC1 | 24048 | Supply + Install | Green | Green | 101024048 | 101024048 | 89% | 2024-06-26 | 2026-04-03 | Joe Hoyle | 98.11% | 105000 | 0 | 1815431.85 | 2504001 | 1765431.85 | 1732125.93 | 841.44 | 32464.46 | 0.02 | 0.02 | 2239782 | 2389067 | 2504001 | 2026-04-17 | 0 | 114934 | 2504001 | 771875.07 | 507656.07 | 738569.15 | 29.5% | #INVALID OPERATION | 0% | 32.14% | 2399001 | 1815431.85 | 103302.96 | 0 | 0 | 738569.17 | 2504001 | 0
Project Dashboard | TN Titans Stadium | 24051 | Supply Only | Green | Red | 101024051 | 101024051 | 89% | 2021-12-01 | 2026-05-15 | Marc Ribar | 70.61% | 8831070 | 6821503 | 64150 | 8924815 | 6831350 | 4823731.49 | 201953.21 | 1766988 | 38677.3 | 38677.3 | 6723832 | 6344650 | 7280832 | 2026-04-16 | 1643983 | 2580165 | 7280832 | 2457100.51 | 1900100.51 | 2093465 | 23.46% | 22.76% | 29.46% | 46.13% | 93745 | 64150 | 0 | 0 | 709800 | 2132142.3 | 8924815 | 0
Project Dashboard | Rowan BWI 150 | 24057 | Supply + Install | Green | Green | 101024057 | 101024057 | 100% | 2021-12-01 | 2026-01-09 | Dillon Bowman | 96.95% | 6089000 | 4168839 | 430761 | 6519761 | 4404600 | 4270103.47 | 24165.32 | 110330.71 | 0.5 | 0.5 | 6454563 | 6285049 | 6519761 | 2026-02-09 | 0 | 234712 | 6519761 | 2249657.53 | 2184459.53 | 2115161 | 32.44% | 31.53% | 46.06% | 0% | 430761 | 430761 | 0 | 0 | 139585 | 2115161.5 | 6519761 | 0
Project Dashboard | QTS NAL2 DC2 | 24065 | Supply + Install | Green | Red | 101024065 | 101024065 | 86% | 2024-07-19 | 2026-05-08 | Joe Hoyle | 98.04% | 2541045 | 1912342 | 24850 | 2574165 | 1887000 | 1849929.92 | 492.94 | 36964.18 | -387.04 | -387.04 | 2308041 | 2523711 | 2572629 | 2026-02-17 | 1536 | 50454 | 2572629 | 722699.08 | 458111.08 | 687165 | 26.69% | 24.74% | 32.88% | 33.28% | 33120 | 24850 | 26660 | 20925 | 0 | 686777.96 | 2574165 | 0
Project Dashboard | QTS NAL1 DC2 | 24068 | Supply + Install | Green | Green | 101024068 | 101024068 | 87% | 2024-09-10 | 2026-04-10 | Joe Hoyle | 98.21% | 1801949 | 1369550.995 | 672083.25 | 2691013 | 1944135.145 | 1909328.73 | 22658.2 | 12148.22 | -0.005 | -0.005 | 2421911 | 2544621 | 2691013 | 2026-01-09 | 0 | 146392 | 2691013 | 781684.27 | 512582.27 | 746877.855 | 27.75% | 24% | 31.57% | 32.28% | 889064 | 672083.25 | 0 | 0 | 0 | 746877.85 | 2691013 | 0
Project Dashboard | TCAT Pulaski | 24069 | Supply + Install | Green | Red | 101024069 | 101024069 | 96% | 2024-09-11 | 2026-06-04 | Chris Buttrey | 97.31% | 773155 | 575257 | 14153.1 | 792212 | 627313.1 | 610448.94 | 2901.8 | 14935.36 | -973 | -973 | 734497 | 770901 | 787212 | 2026-03-31 | 5000 | 21311 | 787212 | 176763.06 | 124048.06 | 164898.9 | 20.81% | 25.6% | 34.4% | 34.65% | 19057 | 14153.1 | 0 | 0 | 0 | 163925.9 | 792212 | 0
Project Dashboard | Maury Regional Med Center | 24070 | AMI | Green | Red | 101024070 | 101024070 | 100% | 2024-09-13 | 2026-01-26 | Cole Norona | 100% | 33500 | 25273 | 267.4 | 33935 | 19308.43 | 19308.43 | 0 | 472 | -472 | -472 | 33935 | 33935 | 33935 | 2025-11-24 | 0 | 0 | 33935 | 14626.57 | 14626.57 | 14626.57 | 43.1% | 24.56% | 32.55% | 62.68% | 435 | 267.4 | 0 | 0 | 0 | 14154.57 | 33935 | 0
Project Dashboard | RS Gass State Lab | 24071 | AMI | Green | Red | 101024071 | 101024071 | 98% | 2024-10-11 | 2026-04-15 | Cole Norona | 100.2% | 579000 | 429388 | -21300 | 559600 | 456946.37 | 458059.62 | 0 | 0 | -1113.25 | -1113.25 | 586600 | 559600 | 559600 | 2026-04-17 | 0 | 0 | 559600 | 101540.38 | 128540.38 | 102653.63 | 18.34% | 25.84% | 34.84% | -8.92% | -19400 | -21300 | 4880 | 1863.6 | -31839.4 | 101540.38 | 559600 | 0
Project Dashboard | LCK064 | 24072 | Supply + Install | Green | Red | 101024072 | 101024072 | 81% | 2024-10-01 | 2026-05-04 | Joe Hoyle | 88.72% | 1748000 | 1301017 | 1276243 | 3463000 | 2500000 | 2217998.94 | 184230.09 | 96229.44 | 1541.53 | 1541.53 | 2686948 | 3072373 | 3415250 | 2026-04-30 | 47750 | 390627 | 3415250 | 1197251.06 | 468949.06 | 963000 | 27.81% | 25.57% | 34.36% | 34.38% | 1715000 | 1276243 | 7475 | 0 | 0 | 964541.53 | 3463000 | 0
Project Dashboard | DIDD Perf | 24073 | Supply + Install | Green | Green | 101024073 | 101024073 | 81% | 2024-10-07 | 2026-06-05 | Dillon Bowman | 25.51% | 177750 | 115360 | 9350 | 192550 | 124710 | 31815.03 | 0 | 92894.97 | 0 | 0 | 64750 | 49119 | 94250 | 2026-03-25 | 98300 | 143431 | 94250 | 62434.97 | 32934.97 | 67840 | 35.23% | 35.1% | 54.08% | 58.29% | 14800 | 9350 | 0 | 0 | 0 | 67840 | 192550 | 0
Project Dashboard | DIDD ACM | 24074 | AMI | Green | Green | 101024074 | 101024074 | 90% | 2024-10-07 | 2027-04-06 | Dillon Bowman | 58.91% | 313000 | 239069 | 0 | 313000 | 239069 | 140841.42 | 0 | 98226.99 | 0.59 | 0.59 | 160000 | 184388 | 265000 | 2026-03-25 | 48000 | 128612 | 265000 | 124158.58 | 19158.58 | 73931 | 23.62% | 23.62% | 30.92% | 0% | 0 | 0 | 0 | 0 | 0 | 73931.59 | 313000 | 0
Project Dashboard | Demonbreun Hill | 24075 | Supply + Install | Green | Green | 101024075 | 101024075 | 54% | 2024-10-11 | 2027-11-11 | Laura Forero | 2.345% | 370000 | 275179 | 3745 | 375014 | 278924 | 6540 | 0 | 272384.003 | -0.003 | -0.003 | 0 | 8775 | 0 |  | 375014 | 366239 | 0 | -6540 | -6540 | 96090 | 25.62% | 25.63% | 34.46% | 33.89% | 5014 | 3745 | 0 | 0 | 0 | 96089.997 | 375014.1 | 0.1
Project Dashboard | GCDC Security Building | 24076 | Supply + Install | Red | Green | 101024076 | 101024076 | 20% | 2021-12-01 | 2025-06-24 | Nick Akins | 99.61% | 119500 | 93504.48 | 0 | 119500 | 108606.08 | 108182.08 | 424 | 0 | -2.1317e-13 | -2.1317e-13 | 119500 | 119033 | 119500 | 2025-09-17 | 0 | 467 | 119500 | 11317.92 | 11317.92 | 10893.92 | 9.116% | 21.75% | 27.8% | 0% | 0 | 0 | 0 | 0 | 0 | 10893.92 | 119500 | 0
Project Dashboard | IAD 667 TI | 24077 | Supply + Install | Green | Red | 101024077 | 101024077 | 80% | 2024-10-24 | 2026-05-04 | Chris Buttrey | 87.84% | 2730000 | 2050000 | 0 | 2730000 | 2040000 | 1791996.96 | 143885.42 | 106375.57 | -2257.95 | -2257.95 | 2100600 | 2386293 | 2484300 | 2026-03-20 | 245700 | 343707 | 2484300 | 692303.04 | 308603.04 | 690000 | 25.27% | 24.91% | 33.17% | 0% | 0 | 0 | 0 | 0 | 0 | 687742.05 | 2730000 | 0
Project Dashboard | IAD 668 TI | 24078 | Supply + Install | Green | Green | 101024078 | 101024078 | 70% | 2024-10-24 | 2026-06-29 | Chris Buttrey | 0.3025% | 3545000 | 2650000 | 0 | 3545000 | 2650000 | 8017.3 | 2159439 | 482543.7 | 0 | 0 | 226800 | 10635 | 252000 | 2025-12-10 | 3293000 | 3534365 | 252000 | 243982.7 | 218782.7 | 895000 | 25.25% | 25.25% | 33.77% | 0% | 0 | 0 | 0 | 0 | 0 | 895000 | 3545000 | 0
Project Dashboard | Nashville Youth Campus | 24079 | Supply + Install | Red | Red | 101024079 | 101024079 | 72% | 2024-12-19 | 2026-12-01 | Joe Hoyle | 36.1% | 8448000 | 6174337 | 311410 | 9039946.75 | 6485747.01 | 2341167.42 | 2208391 | 2041225.31 | -105036.72 | -105036.72 | 1516195 | 3263420 | 3968041 | 2026-03-11 | 5071905.75 | 5776526.75 | 3968041 | 1626873.58 | -824972.42 | 2554199.74 | 28.25% | 26.91% | 36.82% | 90.09% | 591946.75 | 311410 | 423586.64 | 0 | 0 | 2449163.02 | 9039946.75 | 0
Project Dashboard | DLR DFW37 | 24081 | Supply + Install | Red | Red | 101024081 | 101024081 | 75% | 2025-05-07 | 2026-09-14 | Cole Norona | 28.01% | 601500 | 439016 | 3394229 | 5248952 | 3833245 | 1073871.68 | 1796769.83 | 970746.3 | -8142.81 | -8142.81 | 1341765 | 1470231 | 2263136 | 2026-03-20 | 2985816 | 3778721 | 2263136 | 1189264.32 | 267893.32 | 1415707 | 26.97% | 27.01% | 37.01% | 36.92% | 4647452 | 3394229 | 0 | 69132 | 0 | 1407564.19 | 5248953 | 1
Project Dashboard | GTN Cable | 24082 | Supply + Install | Red | Red | 101024082 | 101024082 | 43% | 2024-12-02 | 2025-06-27 | Josh McPherson <jmcpherson@jwmcd.com>, Nick Akins <nakins@jwmcd.com> | 95.69% | 142000 | 100001 | 0 | 142000 | 100001 | 95691.98 | 323.88 | 5231.32 | -1246.18 | -1246.18 | 134900 | 135879 | 142000 | 2025-09-18 | 0 | 6121 | 142000 | 46308.02 | 39208.02 | 41999 | 29.58% | 29.58% | 42% | 0% | 0 | 0 | 3440 | 0 | 0 | 40752.82 | 142000 | 0
Project Dashboard | Academic Zone | 24086 | Supply + Install | Green | Green | 101024086 | 101024086 | 4% | 2025-01-03 | 2028-04-19 | Dillon Bowman | 20.88% | 3285894 | 2510158 | 0 | 3285894 | 2510158 | 524088.62 | 0 | 1986069.38 | 0 | 0 | 97438 | 686094 | 633438 | 2026-03-25 | 2652456 | 2599800 | 633438 | 109349.38 | -426650.62 | 775736 | 23.61% | 23.61% | 30.9% | 0% | 0 | 0 | 0 | 0 | 0 | 775736 | 3285894 | 0
Project Dashboard | BSU Innovation Center | 24089 | Supply + Install | Green | Red | 101024089 | 101024089 | 85% | 2022-02-28 | 2026-08-10 | Marc Ribar | 76.17% | 660531 | 497900 | -12063 | 654679 | 485837 | 370044.48 | 49033.99 | 100974 | -34215.47 | -34215.47 | 523343 | 498668 | 610863 | 2026-03-25 | 43816 | 156011 | 610863 | 240818.52 | 153298.52 | 168842 | 25.79% | 24.62% | 32.66% | -51.49% | -5852 | -12063 | 0 | 0 | 0 | 134626.53 | 654679 | 0
Project Dashboard | BNA Baggage Handling | 25001 | Supply + Install | Green | Green | 101025001 | 101025001 | 50% | 2022-02-28 | 2026-06-19 | Marc Ribar | 0% | 648064 | 475809 | -14320.74 | 633743.26 | 461488.26 | 0 | 0 | 461488 | 0.26 | 0.26 | 20911 | 190 | 23411 | 2026-03-20 | 610332.26 | 633553.26 | 23411 | 23411 | 20911 | 172255 | 27.18% | 26.58% | 36.2% | 0% | -14320.74 | -14320.74 | 0 | 0 | 0 | 172255.26 | 633743.26 | 0
Project Dashboard | Med Center Health | 25002 | Supply + Install | Green | Green | 101025002 | 101025002 | 99% | 2025-05-23 | 2026-10-02 | Carlos Silva | 71.28% | 3018078 | 2313272 | -1248118.17 | 1768669.79 | 1116428.58 | 795767.12 | 226063.5 | 94598.04 | -0.08 | -0.08 | 1458839 | 1273619 | 2178000 | 2026-02-20 | -409330.21 | 495050.79 | 2178000 | 1382232.88 | 663071.88 | 652241.21 | 36.88% | 23.35% | 30.47% | 0.1034% | -1249408.21 | -1248118.17 | 20030 | 0 | 0 | 652241.13 | 1768669.79 | 0
Project Dashboard | IAD 500 TI | 25004 | Supply + Install | Green | Green | 101025004 | 101025004 | 71% | 2025-01-06 | 2026-09-08 | Chris Buttrey | 0.1234% | 3956000 | 2869161 | 723410 | 4942147 | 3592571 | 4432.07 | 3125862.87 | 462276.06 | 0 | 0 | 106200 | 5930 | 138000 | 2026-04-30 | 4804147 | 4936217 | 138000 | 133567.93 | 101767.93 | 1349576 | 27.31% | 27.47% | 37.88% | 36.32% | 986147 | 723410 | 0 | 0 | 0 | 1349576 | 4942147 | 0
Project Dashboard | CAT Financial Nashville HQ | 25005 | Supply + Install | Green | Red | 101025005 | 101025005 | 99% | 2025-01-24 | 2026-04-17 | Chris Buttrey | 59.36% | 9000 | 6750 | 0 | 9000 | 6750 | 4006.91 | 548.75 | 2196.99 | -2.65 | -2.65 | 950 | 5342 | 9000 | 2026-03-20 | 0 | 3658 | 9000 | 4993.09 | -3056.91 | 2250 | 25% | 25% | 33.33% | 0% | 0 | 0 | 0 | 0 | 0 | 2247.35 | 9000 | 0
Project Dashboard | MALETA Housing and Dining | 25006 | AMI | Red | Red | 101025006 | 101025006 | 83% | 2025-01-14 | 2026-08-03 | Cole Norona | 10.01% | 416250 | 310225.6 | 3715 | 421235 | 313940.6 | 31440.86 | 0 | 282649.74 | -150 | -150 | 89000 | 42165 | 133985 | 2026-03-25 | 287250 | 379070 | 133985 | 102544.14 | 57559.14 | 107294.4 | 25.47% | 25.47% | 34.18% | 34.19% | 4985 | 3715 | 0 | 0 | 0 | 107144.4 | 421235 | 0
Project Dashboard | QTS ATL2 DC10 | 25007 | Supply + Install | Red | Red | 101025007 | 101025007 | 76% | 2025-03-07 | 2026-05-07 | Nick Akins | 70.29% | 1366500 | 991271 | 0 | 1366500 | 992074.76 | 697313.27 | 91535.48 | 252353.18 | -49127.17 | -49127.17 | 1015820 | 960512 | 1069285 | 2026-02-13 | 297215 | 405988 | 1069285 | 371971.73 | 318506.73 | 374425.24 | 27.4% | 27.46% | 37.85% | 0% | 0 | 0 | 0 | 0 | 0 | 325298.07 | 1366500 | 0
Project Dashboard | Columbia State Tech Center | 25008 | AMI | Red | Green | 101025008 | 101025008 | 93% | 2025-01-17 | 2026-06-22 | Laura Forero | 85.7% | 149000 | 107685 | 0 | 149000 | 107685 | 92288.48 | 0 | 15396.52 | -8.9706e-14 | -8.9706e-14 | 141000 | 127693 | 149000 | 2026-03-25 | 0 | 21307 | 149000 | 56711.52 | 48711.52 | 41315 | 27.73% | 27.73% | 38.37% | 0% | 0 | 0 | 0 | 0 | 0 | 41315 | 149000 | 0
Project Dashboard | TOA Spring Hill MOB | 25010 | AMI | Green | Red | 101025010 | 101025010 | 98% | 2025-01-29 | 2026-04-06 | Cole Norona | 79.82% | 334000 | 248980 | 0 | 334000 | 248980 | 198746 | 272.8 | 60097 | -10135.8 | -10135.8 | 250000 | 266598 | 320000 | 2026-03-30 | 14000 | 67402 | 320000 | 121254 | 51254 | 85020 | 25.46% | 25.46% | 34.15% | 0% | 0 | 0 | 0 | 0 | 0 | 74884.2 | 334000 | 0
Project Dashboard | St Jude Hospital | 25012 | Supply + Install | Red | Red | 101025012 | 101025012 | 40% | 2025-02-01 | 2027-01-20 | Wylie McDougall | 37.52% | 710500 | 542810.5 | 1493509 | 2663341 | 1961296.5 | 735790.61 | 55643.98 | 1200190.24 | -30328.33 | -30328.33 | 1025175 | 999285 | 1079131 | 2026-03-20 | 1584210 | 1664056 | 1079131 | 343340.39 | 289384.39 | 702044.5 | 26.36% | 23.6% | 30.89% | 30.76% | 1952841 | 1493509 | 3776 | 1333 | 0 | 671716.17 | 2663341 | 0
Project Dashboard | Rockdale CJAC | 25016 | Supply + Install | Green | Green | 101025016 | 101025016 | 83% | 2025-04-28 | 2026-06-10 | Dillon Bowman | 56.64% | 448584 | 341786.02 | 0 | 448584 | 341786.02 | 193576.89 | 77233.12 | 70976.01 | 0 | 0 | 161376 | 254077 | 342570 | 2026-03-25 | 106014 | 194507 | 342570 | 148993.11 | -32200.89 | 106797.98 | 23.81% | 23.81% | 31.25% | 0% | 0 | 0 | 1125 | 0 | 0 | 106797.98 | 448584 | 0
Project Dashboard | Nashville Yards Park | 25017 | Supply + Install | Green | Green | 101025017 | 101025017 | 98% | 2025-02-13 | 2026-04-18 | Dillon Bowman | 92.56% | 208500 | 142822 | -14750 | 187505 | 128072.003 | 118539.21 | 0 | 9532.775 | 0.018 | 0.018 | 178128 | 173554 | 187505 | 2026-04-02 | 0 | 13951 | 187505 | 68965.79 | 59588.79 | 59432.997 | 31.7% | 31.5% | 45.99% | 42.34% | -20995 | -14750 | 0 | 0 | 0 | 59433.015 | 187505 | 0
Project Dashboard | Vantage VA15 | 25022 | Supply + Install | Red | Red | 101025022 | 101025022 | 70% | 2025-05-02 | 2026-06-08 | Thomas Mooers | 68.42% | 2039000 | 1574977 | 84760 | 2196907.75 | 1736212.54 | 1187860.59 | 177327.89 | 385815.14 | -14791.08 | -14791.08 | 1295808 | 1503124 | 2002386 | 2026-04-30 | 194521.75 | 693783.75 | 2002386 | 814525.41 | 107947.41 | 460695.21 | 20.97% | 22.76% | 29.46% | 86.3% | 157907.75 | 84760 | 0 | 0 | -97967.05 | 445904.13 | 2196908 | 0.25
Project Dashboard | QTS MAN1 DC6 | 25025 | Supply + Install | Green | Green | 101025025 | 101025025 | 95% | 2025-05-21 | 2026-06-02 | Dillon Bowman | 85.42% | 1543000 | 1210773 | 0 | 1543000 | 1259823.38 | 1076096.63 | 90453.48 | 93272.67 | 0.6 | 0.6 | 611775 | 1318030 | 1516500 | 2026-04-15 | 26500 | 224970 | 1516500 | 440403.37 | -464321.63 | 283176.62 | 18.35% | 21.53% | 27.44% | 0% | 0 | 0 | 0 | 0 | 0 | 283177.22 | 1543000 | 0
Project Dashboard | Lourdes CC Phase 2 | 25029 | Supply + Install | Green | Red | 101025029 | 101025029 | 68% | 2025-05-15 | 2026-09-17 | Dillon Bowman | 72.06% | 201500 | 158758 | 0 | 201500 | 158758 | 114406.77 | 34197.84 | 11797.665 | -1644.275 | -1644.275 | 165700 | 145200 | 173000 | 2026-03-10 | 28500 | 56300 | 173000 | 58593.23 | 51293.23 | 42742 | 21.21% | 21.21% | 26.92% | 0% | 0 | 0 | 0 | 0 | 25650 | 41097.725 | 201500 | 0
Project Dashboard | 510 W Tremont | 25030 | Supply + Install | Green | Green | 101025030 | 101025030 | 67% | 2025-06-23 | 2026-06-23 | Laura Forero | 30.34% | 182500 | 132758 | 63876 | 270000 | 196634 | 59659.27 | 48400 | 88574.33 | 0.4 | 0.4 | 30150 | 81918 | 128180 | 2026-03-30 | 141820 | 188082 | 128180 | 68520.73 | -29509.27 | 73366 | 27.17% | 27.26% | 37.47% | 36.98% | 87500 | 63876 | 0 | 0 | 0 | 73366.4 | 270000 | 0
Project Dashboard | LLU Mars US Warehouse | 25031 | Supply + Install | Red | Green | 101025031 | 101025031 | 83% | 2025-04-07 | 2026-08-18 | Laura Forero | 74.8% | 576448 | 429174.38 | 29353 | 616151.2 | 458527.38 | 342963.51 | 62259.69 | 53304.18 | 1.0232e-12 | 1.0232e-12 | 294452 | 457819 | 523345 | 2026-03-20 | 92806.2 | 158332.2 | 523345 | 180381.49 | -48511.51 | 157623.82 | 25.58% | 25.55% | 34.32% | 35.26% | 39703.2 | 29353 | 0 | 26199 | 0 | 157623.82 | 607107.2 | -9044
Project Dashboard | Amazon IAD181 | 25032 | Supply + Install | Green | Green | 101025032 | 101025032 | 83% | 2025-08-27 | 2026-12-09 | Matt Rassmussen | 49.6% | 370000 | 286570 | 6500 | 382810 | 293070 | 145349.68 | 89374.47 | 58345.83 | 0.02 | 0.02 | 27000 | 189873 | 142000 | 2026-03-20 | 240810 | 192937 | 142000 | -3349.68 | -118349.68 | 89740 | 23.44% | 22.55% | 29.11% | 97.08% | 12810 | 6500 | 2400 | 0 | 0 | 89740.02 | 382810 | 0
Project Dashboard | Converge Office Building | 25033 | Supply + Install | Red | Red | 101025033 | 101025033 | 50% | 2026-01-21 | 2026-09-24 | Chris Buttrey | 34.63% | 639720 | 474156 | 0 | 639720 | 474156 | 164210.23 | 0 | 313067.47 | -3121.7 | -3121.7 | 184248 | 221535 | 344720 | 2026-04-15 | 295000 | 418185 | 344720 | 180509.77 | 20037.77 | 165564 | 25.88% | 25.88% | 34.92% | 0% | 0 | 0 | -9270 | 0 | 0 | 162442.3 | 639720 | 0
Project Dashboard | Titans Jabez | 25035 | Supply Only | Green | Red | 101025035 | 101025035 | 27% | 2026-08-20 | 2027-05-14 | Marc Ribar | 66.02% | 385544 | 289400 | 232000 | 685969 | 521400 | 344205.08 | 22649.61 | 155937 | -1391.69 | -1391.69 | 388844 | 452876 | 576344 | 2026-03-26 | 109625 | 233093 | 576344 | 232138.92 | 44638.92 | 164569 | 23.99% | 24.94% | 33.22% | 29.49% | 300425 | 232000 | 0 | 0 | 0 | 163177.31 | 685969 | 0
Project Dashboard | TCAT Chattanooga | 25036 | Supply + Install | Red | Green | 101025036 | 101025036 | 87% | 2025-06-27 | 2026-01-26 | Josh McPherson | 90.11% | 512322.5 | 413102.73 | 45205.2 | 564711.5 | 432060.97 | 389311.29 | 21802.19 | 20946.86 | 0.63 | 0.63 | 471344 | 493024 | 496152 | 2026-01-28 | 68559.5 | 71687.5 | 496152 | 106840.71 | 82032.71 | 132650.53 | 23.49% | 19.37% | 24.02% | 15.89% | 52389 | 45205.2 | 0 | 0 | 0 | 132651.16 | 553711.5 | -11000
Project Dashboard | Chestnut Street Office | 25037 | AMI | Green | Green | 101025037 | 101025037 | 88% | 2025-05-20 | 2026-07-24 | Laura Forero | 1.083% | 290500 | 212439 | 12447 | 307490 | 224886 | 2435 | 0 | 222451 | 0 | 0 | 31500 | 6426 | 91500 | 2026-03-30 | 215990 | 301064 | 91500 | 89065 | 29065 | 82604 | 26.86% | 26.87% | 36.75% | 36.5% | 16990 | 12447 | 0 | 29060 | 0 | 82604 | 307490 | 0
Project Dashboard | Chestnut Street Venue | 25038 | AMI | Red | Green | 101025038 | 101025038 | 74% | 2025-05-20 | 2026-06-17 | Laura Forero | 4.827% | 60000 | 43671 | 6775 | 69170 | 50446 | 2435 | 0 | 48011 | 0 | 0 | 15000 | 3005 | 27730 | 2026-02-25 | 41440 | 66165 | 27730 | 25295 | 12565 | 18724 | 27.07% | 27.21% | 37.39% | 35.35% | 9170 | 6775 | 0 | 0 | 0 | 18724 | 62220 | -6950
Project Dashboard | Moses Lincoln Vitrine | 25040 | Supply + Install | Green | Green | 101025040 | 101025040 | 97% | 2025-06-02 | 2026-02-13 | Laura Forero | 100% | 185000 | 135310 | 19247 | 211500 | 143311.44 | 143311.44 | 0 | 0 | -9.9476e-14 | -9.9476e-14 | 185000 | 211500 | 211500 | 2026-02-25 | 0 | 0 | 211500 | 68188.56 | 41688.56 | 68188.56 | 32.24% | 26.86% | 36.72% | 37.68% | 26500 | 19247 | 0 | 0 | 0 | 68188.56 | 211500 | 0
Project Dashboard | Wedgewood Bldg E | 25041 | AMI | Green | Red | 101025041 | 101025041 | 78% | 2025-06-05 | 2026-06-09 | Wylie McDougall | 67.49% | 41000 | 30741 | -1666.12 | 41197.88 | 29074.88 | 19622.87 | 0 | 9525.52 | -73.51 | -73.51 | 8000 | 27804 | 27387 | 2026-03-30 | 13810.88 | 13393.88 | 27387 | 7764.13 | -11622.87 | 12123 | 29.43% | 27.67% | 38.25% | -21.85% | -1302.12 | -1666.12 | 3240 | 0 | 0 | 12049.49 | 41197.88 | 0
Project Dashboard | IAD 183 | 25042 | Supply + Install | Green | Red | 101025042 | 101025042 | 66% | 2025-07-08 | 2027-05-20 | Carlos Silva | 58.58% | 2458000 | 1879103 | 0 | 2458000 | 1879103 | 1100799.58 | 1251265.27 | 626777.15 | -1099739 | -1099739 | 95580 | 1439896 | 106200 | 2025-09-26 | 2351800 | 1018104 | 106200 | -994599.58 | -1005219.58 | 578897 | 23.55% | 23.55% | 30.81% | 0% | 0 | 0 | 0 | 0 | 0 | -520842 | 2458000 | 0
Project Dashboard | MALETA Firing Range | 25044 | AMI | Green | Green | 101025044 | 101025044 | 76% | 2025-06-10 | 2027-01-28 | Cole Norona | 3.138% | 282500 | 211787 | 0 | 282500 | 211787 | 6645.34 | 0 | 205141.26 | 0.4 | 0.4 | 117500 | 8870 | 117500 | 2025-10-23 | 165000 | 273630 | 117500 | 110854.66 | 110854.66 | 70713 | 25.03% | 25.03% | 33.39% | 0% | 0 | 0 | 0 | 0 | 0 | 70713.4 | 282500 | 0
Project Dashboard | DLR IAD59 | 25045 | Supply + Install | Green | Green | 101025045 | 101025045 | 81% | 2025-06-09 | 2026-08-12 | Carlos Silva | 9.016% | 508000 | 378490.68 | 253070 | 868766.55 | 631560.68 | 56942.93 | 313802.42 | 260815.35 | -0.02 | -0.02 | 311110 | 78362 | 477478 | 2026-04-15 | 391288.55 | 790404.55 | 477478 | 420535.07 | 254167.07 | 237205.87 | 27.3% | 25.49% | 34.22% | 42.56% | 360766.55 | 253070 | 0 | 0 | 0 | 237205.85 | 868766.55 | 0
Project Dashboard | East Nashville FSER | 25048 | AMI | Green | Green | 101025048 | 101025048 | 84% | 2025-07-02 | 2026-04-10 | Wylie McDougall | 61.19% | 14500 | 9390.6 | 0 | 14500 | 9390.6 | 5745.68 | 0 | 3645.99 | -1.07 | -1.07 | 2500 | 8872 | 14500 | 2026-03-30 | 0 | 5628 | 14500 | 8754.32 | -3245.68 | 5109.4 | 35.24% | 35.24% | 54.41% | 0% | 0 | 0 | 0 | 0 | 0 | 5108.33 | 14500 | 0
Project Dashboard | 801 Retail | 25049 | Supply + Install | Green | Green | 101025049 | 101025049 | 0% | 2026-08-20 | 2027-05-14 | Nick Akins | 50% | 12003 | 7500 | 0 | 12003 | 6000 | 3000 | 0 | 3000 | 0 | 0 | 12003 | 4801 | 12003 | 2025-10-31 | 0 | 7202 | 12003 | 9003 | 9003 | 6003 | 50.01% | 37.52% | 60.04% | 0% | 0 | 0 | 0 | 0 | 0 | 6003 | 12003 | 0
Project Dashboard | LTW062 Fit Out | 25050 | Supply + Install | Green | Green | 101025050 | 101025050 | 88% | 2025-10-16 | 2027-01-25 | Dillon Bowman | 100% | 474700 | 346253 | 0 | 474700 | 381601.54 | 381601.54 | 0 | 0 | 0 | 0 | 166320 | 461537 | 184800 | 2026-04-01 | 289900 | 13163 | 184800 | -196801.54 | -215281.54 | 93098.46 | 19.61% | 27.06% | 37.1% | 0% | 0 | 0 | 0 | 0 | 0 | 93098.46 | 461537 | -13163
Project Dashboard | East End UMC | 25051 | Supply Only | Green | Green | 101025051 | 101025051 | 80% | 2025-07-21 | 2026-06-19 | Cole Norona | 6.952% | 50485 | 29367 | 0 | 50485 | 29367 | 2041.6 | 0 | 27325.4 | 0 | 0 | 10000 | 3508 | 10000 | 2025-09-19 | 40485 | 46977 | 10000 | 7958.4 | 7958.4 | 21118 | 41.83% | 41.83% | 71.91% | 0% | 0 | 0 | 0 | 0 | 0 | 21118 | 50485 | 0
Project Dashboard | TEMA Warehouse | 25052 | Supply + Install | Green | Red | 101025052 | 101025052 | 90% | 2025-08-05 | 2026-05-21 | Andre Van Der Merwe | 76.47% | 729000 | 544249 | 2985 | 733000 | 547234 | 418486.89 | 69000 | 59770.98 | -23.87 | -23.87 | 64600 | 560671 | 548000 | 2026-03-20 | 185000 | 172329 | 548000 | 129513.11 | -353886.89 | 185766 | 25.34% | 25.34% | 33.95% | 34% | 4000 | 2985 | 0 | 4701 | 0 | 185742.13 | 733000 | 0
Project Dashboard | Altra Clarkville | 25054 | Supply + Install | Green | Green | 101025054 | 101025054 | 58% | 2025-08-03 | 2026-09-03 | Andre Van Der Merwe | 31.02% | 338166 | 250213 | 16424 | 361083.49 | 266637 | 82713.06 | 9804.88 | 174119.06 | 0 | 0 | 164350 | 112008 | 173000 | 2026-03-13 | 188083.49 | 249075.49 | 173000 | 90286.94 | 81636.94 | 94446.49 | 26.16% | 26.01% | 35.15% | 39.54% | 22917.49 | 16424 | 0 | 10644 | 0 | 94446.49 | 361083.49 | 0
Project Dashboard | Mercedes Body Shop Reno | 25055 | Supply + Install | Green | Red | 101025055 | 101025055 | 95% | 2025-08-06 | 2026-10-12 | Andre Van Der Merwe | 89.2% | 89000 | 62429 | 7178.19 | 100210.6 | 69607.19 | 62087.06 | 333.17 | 7534.11 | -347.15 | -347.15 | 56525 | 89387 | 100210 | 2026-03-25 | 0.6 | 10823.6 | 100210 | 38122.94 | -5562.06 | 30603.41 | 30.54% | 29.86% | 42.56% | 56.18% | 11210.6 | 7178.19 | 0 | 0 | 0 | 30256.26 | 100210.6 | 0
Project Dashboard | Oppidan Ashland | 25056 | Supply + Install | Green | Green | 101025056 | 101025056 | 60% | 2026-09-01 | 2027-08-09 | Carlos Silva | 0.5348% | 184000 | 134492 | 0 | 184000 | 134492 | 719.22 | 0 | 133772.78 | 0 | 0 | 8075 | 975 | 14500 | 2026-03-13 | 169500 | 183025 | 14500 | 13780.78 | 7355.78 | 49508 | 26.91% | 26.91% | 36.81% | 0% | 0 | 0 | 0 | 0 | 0 | 49508 | 184000 | 0
Project Dashboard | Brentsville HS Turf Facility | 25058 | Supply + Install | Green | Green | 101025058 | 101025058 | 52% | 2025-09-30 | 2027-07-21 | Laura Forero | 5.263% | 400465 | 297146 | 0 | 400465 | 297146 | 15639.45 | 247093.19 | 34413.36 | -2.3004e-12 | -2.3004e-12 | 0 | 21064 | 46015 | 2026-03-20 | 354450 | 379401 | 46015 | 30375.55 | -15639.45 | 103319 | 25.8% | 25.8% | 34.77% | 0% | 0 | 0 | 0 | 0 | 0 | 103319 | 400465 | 0
Project Dashboard | Allen Samuels CDJR and LC | 25059 | Supply + Install | Green | Red | 101025059 | 101025059 | 96% | 2025-09-01 | 2026-12-15 | Andre Van Der Merwe | 95.94% | 238000 | 179195 | 4497 | 244606.66 | 211347.17 | 202765.33 | 246.93 | 9021.18 | -686.27 | -686.27 | 214200 | 234920 | 244606 | 2026-03-25 | 0.66 | 9686.66 | 244606 | 41840.67 | 11434.67 | 33259.49 | 13.6% | 24.71% | 32.82% | 46.91% | 6606.66 | 4497 | 0 | 0 | 0 | 32573.22 | 244606.66 | 0
Project Dashboard | Legislative Plaza | 25060 | AMI | Green | Green | 101025060 | 101025060 | 59% | 2026-02-06 | 2026-09-17 | Cole Norona | 8.385% | 112500 | 84906 | 0 | 112500 | 85049 | 7131 | 0 | 77918 | 0 | 0 | 22500 | 9427 | 22500 | 2026-01-01 | 90000 | 103073 | 22500 | 15369 | 15369 | 27451 | 24.4% | 24.53% | 32.5% | 0% | 0 | 0 | 0 | 0 | 0 | 27451 | 112500 | 0
Project Dashboard | BNA Concourse A | 25061 | Supply + Install | Green | Red | 101025061 | 101025061 | 34% | 2025-10-08 | 2027-05-13 | Andre Van Der Merwe | 0.9011% | 6836000 | 5196920 | 0 | 6836000 | 5196920 | 46827.04 | 2114270.53 | 3036659.55 | -837.12 | -837.12 | 60000 | 61524 | 110000 | 2026-03-13 | 6726000 | 6774476 | 110000 | 63172.96 | 13172.96 | 1639080 | 23.98% | 23.98% | 31.54% | 0% | 0 | 0 | 0 | 0 | 0 | 1638242.88 | 6836000 | 0
Project Dashboard | VUMC Link | 25062 | AMI | Green | Green | 101025062 | 101025062 | 48% | 2025-10-08 | 2026-12-17 | Laura Forero | 7.707% | 12200 | 8745 | 0 | 12200 | 8745 | 674 | 0 | 8071 | 0 | 0 | 1500 | 940 | 1500 | 2025-11-24 | 10700 | 11260 | 1500 | 826 | 826 | 3455 | 28.32% | 28.32% | 39.51% | 0% | 0 | 0 | 0 | 0 | 0 | 3455 | 12200 | 0
Project Dashboard | Amazon DVH01 | 25064 | Supply Only | Green | Red | 101025064 | 101025064 | 100% | 2025-08-22 | 2026-09-17 | Cole Norona | 100% | 57000 | 38085 | 3785 | 62705 | 18009.69 | 18009.69 | 0 | 3000 | -3000 | -3000 | 44705 | 62705 | 62705 | 2026-02-13 | 0 | 0 | 62705 | 44695.31 | 26695.31 | 44695.31 | 71.28% | 33.18% | 49.67% | 50.73% | 5705 | 3785 | 0 | 0 | 0 | 41695.31 | 62705 | 0
Project Dashboard | Crosswinds Casino Resort | 25065 | Supply + Install | Green | Green | 101025065 | 101025065 | 19% | 2025-11-27 | 2027-12-10 | Matt Rassmussen | 1.425% | 7664385 | 5911854 | 28200 | 7713462 | 5940054 | 84638.91 | 1159983.87 | 4695431.22 | 0 | 0 | 343175 | 148084 | 386237 | 2026-03-20 | 7327225 | 7565378 | 386237 | 301598.09 | 258536.09 | 1773408 | 22.99% | 22.87% | 29.64% | 74.03% | 49077 | 28200 | 0 | 0 | 0 | 1773408 | 7672756 | -40706
Project Dashboard | Goodwill Opportunity Center | 25066 | AMI | Green | Green | 101025066 | 101025066 | 56% | 2025-10-30 | 2026-10-28 | Andre Van Der Merwe | 5.429% | 55000 | 40332 | -1007 | 57799.27 | 39325 | 2135 | 0 | 37190 | 0 | 0 | 6000 | 3000 | 21000 | 2026-02-25 | 36799.27 | 54799.27 | 21000 | 18865 | 3865 | 18474.27 | 31.96% | 26.67% | 36.37% | -378% | 2799.27 | -1007 | 0 | 0 | 0 | 18474.27 | 54949.27 | -2850
Project Dashboard | Harison Bend | 25067 | Supply Only | Green | Red | 101025067 | 101025067 | 58% | 2025-10-08 | 2026-05-19 | Andre Van Der Merwe | 74.5% | 63800 | 46390 | 0 | 63800 | 46390 | 34560.06 | 0 | 11975.94 | -146 | -146 | 56500 | 47531 | 56500 | 2026-01-28 | 7300 | 16269 | 56500 | 21939.94 | 21939.94 | 17410 | 27.29% | 27.29% | 37.53% | 0% | 0 | 0 | 0 | 0 | 0 | 17264 | 63800 | 0
Project Dashboard | 5 City Retail North | 25068 | Supply + Install | Green | Green | 101025068 | 101025068 | 0% | 2026-08-20 | 2027-05-14 | Brent Tidwell | 57.89% | 5570 | 3909.01 | 1635 | 7910 | 5544.01 | 3209.21 | 0 | 2334.8 | 0 | 0 | 7910 | 4579 | 7910 | 2026-02-25 | 0 | 3331 | 7910 | 4700.79 | 4700.79 | 2365.99 | 29.91% | 29.82% | 42.49% | 43.12% | 2340 | 1635 | 0 | 0 | 0 | 2365.99 | 7910 | 0
Project Dashboard | Henry Horten State Park Inn | 25069 | AMI | Green | Green | 101025069 | 101025069 | 72% | 2025-12-02 | 2026-06-15 | Andre Van Der Merwe | 8.117% | 42450 | 28027 | 0 | 42450 | 28027 | 2275 | 0 | 25752 | 0 | 0 | 8000 | 3446 | 8000 | 2026-01-30 | 34450 | 39004 | 8000 | 5725 | 5725 | 14423 | 33.98% | 33.98% | 51.46% | 0% | 0 | 0 | 1320 | 0 | 0 | 14423 | 42450 | 0
Project Dashboard | 1401 Church St | 25070 | AMI | Green | Green | 101025070 | 101025070 | 0% | 2026-08-20 | 2027-05-14 | Wylie McDougall | 2.704% | 128000 | 91887.31 | 0 | 128000 | 91887.31 | 2485 | 0 | 89402.31 | 0 | 0 | 14500 | 3456 | 25000 | 2026-03-30 | 103000 | 124544 | 25000 | 22515 | 12015 | 36112.69 | 28.21% | 28.21% | 39.3% | 0% | 0 | 0 | 0 | 0 | 0 | 36112.69 | 128000 | 0
Project Dashboard | IAD181 Fitout | 25071 | Supply + Install | Green | Green | 101025071 | 101025071 | 61% | 2025-12-26 | 2026-09-10 | Matt Rassmussen | 1.758% | 2034000 | 1553000 | 0 | 2034000 | 1553000 | 27294.34 | 1109992.66 | 415713 | 0 | 0 | 0 | 35798 | 94000 | 2026-03-20 | 1940000 | 1998202 | 94000 | 66705.66 | -27294.34 | 481000 | 23.65% | 23.65% | 30.97% | 0% | 0 | 0 | 0 | 0 | 0 | 481000 | 2034000 | 0
Project Dashboard | QTS ATL2 DC5 | 25072 | Supply + Install | Green | Green | 101025072 | 101025072 | 43% | 2026-01-01 | 2027-05-14 | Andre Van Der Merwe | 0.2068% | 4505500 | 3482050 | 0 | 4505500 | 3482050 | 7201.11 | 0 | 3474848.89 | 0 | 0 | 117000 | 9461 | 130000 | 2026-02-13 | 4375500 | 4496039 | 130000 | 122798.89 | 109798.89 | 1023450 | 22.72% | 22.72% | 29.39% | 0% | 0 | 0 | -27155.64 | 0 | 0 | 1023450 | 4505500 | 0
Project Dashboard | QTS Rebranding | 25073 | Supply + Install | Green | Red | 101025073 | 101025073 | 16% | 2026-01-01 | 2027-03-26 | Andre Van Der Merwe | 51.88% | 255000 | 179288 | 2415 | 257415 | 181703 | 94266.7 | 40 | 89132.27 | -1735.97 | -1735.97 | 0 | 133546 | 232415 | 2026-03-23 | 25000 | 123869 | 232415 | 138148.3 | -94266.7 | 75712 | 29.41% | 29.69% | 42.23% | 0% | 2415 | 2415 | 0 | 0 | 0 | 73976.03 | 257415 | 0
Project Dashboard | AWS CMH 207 | 25074 | Supply + Install | Green | Green | 101025074 | 101025074 | 39% | 2026-01-15 | 2026-11-23 | Matt Rassmussen | 0.2372% | 4566411 | 3533619 | 0 | 4566411 | 3533619 | 8380.16 | 1702541.64 | 1822697.2 | 0 | 0 | 0 | 10959 | 85000 | 2026-03-20 | 4481411 | 4555452 | 85000 | 76619.84 | -8380.16 | 1032792 | 22.62% | 22.62% | 29.23% | 0% | 0 | 0 | 0 | 0 | 0 | 1032792 | 4566411 | 0
Project Dashboard | St Thomas West Canopy Replace | 25075 | Supply + Install | Green | Red | 101025075 | 101025075 | 70% | 2025-12-22 | 2027-03-26 | Chris Buttrey | 16.63% | 262000 | 189606 | 0 | 262000 | 189606 | 31527.64 | 35310.46 | 158909.23 | -36141.33 | -36141.33 | 0 | 43570 | 262000 | 2026-03-26 | 0 | 218430 | 262000 | 230472.36 | -31527.64 | 72394 | 27.63% | 27.63% | 38.18% | 0% | 0 | 0 | 0 | 0 | 0 | 36252.67 | 262000 | 0
Project Dashboard | TSB Building | 25076 | Supply + Install | Green | Green | 101025076 | 101025076 | 44% | 2026-01-26 | 2026-10-12 | Laura Forero | 0.2209% | 842850 | 644098.67 | 0 | 842850 | 644098.67 | 1422.8 | 244969.68 | 397706.19 | 0 | 0 | 0 | 1854 | 0 |  | 842850 | 840996 | 0 | -1422.8 | -1422.8 | 198751.33 | 23.58% | 23.58% | 30.86% | 0% | 0 | 0 | 0 | 0 | 0 | 198751.33 | 842850 | 0
Project Dashboard | Andrews Sports Medicine | 25077 | Supply + Install | Green | Green | 101025077 | 101025077 | 9% | 2026-03-03 | 2026-11-18 | Carlos Silva | 0.4507% | 2873450 | 2186283.45 | 0 | 2873450 | 2186283.45 | 9853.44 | 153989 | 2022441.01 | 0 | 0 | 0 | 12930 | 0 |  | 2873450 | 2860520 | 0 | -9853.44 | -9853.44 | 687166.55 | 23.91% | 23.91% | 31.43% | 0% | 0 | 0 | 205861.12 | 0 | 0 | 687166.55 | 2873450 | 0
Project Dashboard | AWS CMH 208 | 25078 | Supply + Install | Green | Green | 101025078 | 101025078 | 40% | 2026-01-13 | 2026-11-20 | Matt Rassmussen | 0.1361% | 4566411 | 3533619 | 0 | 4566411 | 3533619 | 4809.66 | 1702541.64 | 1826267.7 | 0 | 0 | 0 | 6392 | 85000 | 2026-03-20 | 4481411 | 4560019 | 85000 | 80190.34 | -4809.66 | 1032792 | 22.62% | 22.62% | 29.23% | 0% | 0 | 0 | 0 | 0 | 0 | 1032792 | 4566411 | 0
Project Dashboard | Edition Hotel | 26001 | Supply + Install | Red | Red | 101026001 | 101026001 | 26% | 2026-01-19 | 2028-02-21 | Joe Hoyle | 2.54% | 2122000 | 1595118 | 63904 | 2207030 | 1659022 | 42136.96 | 81933.23 | 1552126.96 | -17175.15 | -17175.15 | 0 | 56058 | 0 |  | 2207030 | 2150972 | 0 | -42136.96 | -42136.96 | 548008 | 24.83% | 24.83% | 33.03% | 33.06% | 85030 | 63904 | 37480 | 0 | 0 | 530832.85 | 2207030 | 0
Project Dashboard | World Outreach Church | 26002 | AMI | Green | Green | 101026002 | 101026002 | 44% | 2026-01-26 | 2026-12-17 | Laura Forero | 4.152% | 113000 | 85989 | 0 | 113000 | 85989 | 3570 | 0 | 82419 | 0 | 0 | 0 | 4689 | 10500 | 2026-02-25 | 102500 | 108311 | 10500 | 6930 | -3570 | 27011 | 23.9% | 23.9% | 31.41% | 0% | 0 | 0 | 0 | 0 | 0 | 27011 | 113000 | 0
Project Dashboard | Hollingshead Residence | 26004 | Supply + Install | Green | Green | 101026004 | 101026004 | 0% | 2026-08-20 | 2027-05-14 | Cole Norona | 1.968% | 218500 | 160571 | 0 | 218500 | 160571 | 3159.74 | 0 | 157411.26 | 0 | 0 | 0 | 4304 | 0 |  | 218500 | 214196 | 0 | -3159.74 | -3159.74 | 57929 | 26.51% | 26.51% | 36.08% | 0% | 0 | 0 | 0 | 0 | 0 | 57929 | 218500 | 0
Project Dashboard | Empower K2 Office | 26005 | AMI | Green | Green | 101026005 | 101026005 | 46% | 2026-03-09 | 2026-12-08 | Laura Forero | 1.792% | 108000 | 78128 | 0 | 108000 | 78128 | 1400 | 0 | 76728 | 0 | 0 | 0 | 1933 | 0 |  | 108000 | 106067 | 0 | -1400 | -1400 | 29872 | 27.66% | 27.66% | 38.23% | 0% | 0 | 0 | 0 | 0 | 0 | 29872 | 108000 | 0
Project Dashboard | AWS IAD 196 197 198 | 26006 | Supply + Install | Green | Green | 101026006 | 101026006 | 0% | 2026-08-20 | 2027-05-14 | Chris Buttrey | 0% | 6446000 | 4928614 | 0 | 6446000 | 4928614 | 0 | 0 | 4928614 | 0 | 0 | 0 | 0 | 0 |  | 6446000 | 6446000 | 0 | 0 | 0 | 1517386 | 23.54% | 23.54% | 30.79% | 0% | 0 | 0 | 0 | 0 | 0 | 1517386 | 6446000 | 0
Project Dashboard | BG Parking Deck LVL4 | 26007 | Supply + Install | Green | Red | 101026007 | 101026007 | 0% | 2026-08-20 | 2027-05-14 | Cole Norona | 1.282% | 18500 | 12576.5 | 0 | 18500 | 12576.5 | 161.18 | 5.3 | 12425.8 | -15.78 | -15.78 | 0 | 236 | 0 | 2026-03-20 | 18500 | 18264 | 0 | -161.18 | -161.18 | 5923.5 | 32.02% | 32.02% | 47.1% | 0% | 0 | 0 | 0 | 0 | 0 | 5907.72 | 18500 | 0
Project Dashboard | Chase Bank Montgomery | 26008 | Supply Only | Green | Green | 101026008 | 101026008 | 100% | 2026-09-01 | 2026-09-17 | Cole Norona | 100% | 16500 | 970.47 | 0 | 1500 | 430.47 | 430.47 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 2026-03-20 | 0 | 0 | 1500 | 1069.53 | -430.47 | 1069.53 | 71.3% | 94.12% | 1600% | 0% | -15000 | 0 | 0 | 0 | 0 | 1069.53 | 1500 | 0
Project Dashboard | 5th & Summer Leasing Office | 26009 | Supply Only | Green | Green | 101026009 | 101026009 | 0% | 2026-08-20 | 2027-05-14 | Cole Norona | 0.5187% | 13498 | 9616 | 0 | 13498 | 9616 | 49.88 | 0 | 9566.12 | 0 | 0 | 0 | 70 | 0 |  | 13498 | 13428 | 0 | -49.88 | -49.88 | 3882 | 28.76% | 28.76% | 40.37% | 0% | 0 | 0 | 0 | 0 | 0 | 3882 | 13498 | 0
Project Dashboard | ASCTE Research and Dorm | 26010 | Supply + Install | Green | Green | 101026010 | 101026010 | 34% | 2026-03-11 | 2026-11-03 | Colton Van Meter | 0.5308% | 734250 | 563344 | 0 | 734250 | 563344 | 2990.22 | 147312.2 | 413041.58 | 0 | 0 | 0 | 3891 | 0 |  | 734250 | 730359 | 0 | -2990.22 | -2990.22 | 170906 | 23.28% | 23.28% | 30.34% | 0% | 0 | 0 | 19213 | 0 | 0 | 170906 | 734250 | 0
Project Dashboard | 2nd Ave Mockup Build | 26011 | Supply + Install | Green | Green | 101026011 | 101026011 | 0% | 2026-08-20 | 2027-05-14 | Wylie McDougall | 100% | 3000 | 2250 | 0 | 3000 | 2264.37 | 2264.55 | 0 | 0 | -0.18 | -0.18 | 3000 | 3000 | 3000 | 2026-03-18 | 0 | 0 | 3000 | 735.45 | 735.45 | 735.63 | 24.52% | 25% | 33.33% | 0% | 0 | 0 | 0 | 0 | 0 | 735.45 | 3000 | 0
Project Dashboard | Franklin City Hall | 26012 | AMI | Green | Red | 101026012 | 101026012 | 65% | 2026-03-12 | 2026-07-27 | Jason Gilles | 4.58% | 8725 | 5657 | 0 | 8725 | 6877 | 315 | 0 | 5527 | 1035 | 1035 | 0 | 470 | 2500 | 2026-03-25 | 6225 | 8255 | 2500 | 2185 | -315 | 1848 | 21.18% | 35.16% | 54.23% | 0% | 0 | 0 | 0 | 0 | 0 | 2883 | 8725 | 0
Project Dashboard | Vantage VA41 | 26013 | Supply + Install | Green | Green | 101026013 | 101026013 | 34% | 2026-09-01 | 2027-09-24 | Colton Van Meter | 0.1114% | 1742500 | 1330785 | 0 | 1742500 | 1330785 | 1481.91 | 0 | 1329303.09 | 0 | 0 | 0 | 1916 | 0 |  | 1742500 | 1740584 | 0 | -1481.91 | -1481.91 | 411715 | 23.63% | 23.63% | 30.94% | 0% | 0 | 0 | 0 | 0 | 0 | 411715 | 1742500 | 0
Project Dashboard | Highlands College | 26015 | Supply + Install | Green | Green | 101026015 | 101026015 | 55% | 2026-03-04 | 2026-08-13 | Matt Rassmussen | 0.7922% | 169976 | 129277 | 0 | 169976 | 129277 | 1024.19 | 28915 | 99337.81 | 0 | 0 | 0 | 1359 | 0 |  | 169976 | 168617 | 0 | -1024.19 | -1024.19 | 40699 | 23.94% | 23.94% | 31.48% | 0% | 0 | 0 | 4600 | 0 | 0 | 40699 | 169976 | 0
Project Dashboard | DLR DFW40 | 26016 | Supply + Install | Green | Red | 101026016 | 101026016 | 0% | 2026-08-20 | 2027-05-14 | Cole Norona | 0.643% | 693000 | 511452 | 0 | 693000 | 511452 | 3288.79 | 117748.94 | 393703.06 | -3288.79 | -3288.79 | 0 | 0 | 0 |  | 693000 | 693000 | 0 | -3288.79 | -3288.79 | 181548 | 26.2% | 26.2% | 35.5% | 0% | 0 | 0 | 0 | 0 | 0 | 178259.21 | 693000 | 0
Project Dashboard | 601 Lafayette Tower | 26017 | Supply + Install | Green | Red | 101026017 | 101026017 | 0% | 2026-08-20 | 2027-05-14 | Laura Forero | 0.6148% | 706000 | 1704.64 | 0 | 706000 | 1704.64 | 10.48 | 0 | 1704.64 | -10.48 | -10.48 | 0 | 4306 | 0 |  | 706000 | 701694 | 0 | -10.48 | -10.48 | 704295.36 | 99.76% | 99.76% | 41316% | 0% | 0 | 0 | 0 | 0 | 0 | 704284.88 | 706000 | 0
Project Dashboard | PH95 Phase 2 IAD 874 | 26018 | Supply + Install | Green | Green | 101026018 | 101026018 | 25% | 2026-03-27 | 2026-12-17 | Colton Van Meter | 0% | 2320000 | 1770850 | 0 | 2320000 | 1770850 | 0 | 0 | 1770850 | 0 | 0 | 0 | 0 | 0 |  | 2320000 | 2320000 | 0 | 0 | 0 | 549150 | 23.67% | 23.67% | 31.01% | 0% | 0 | 0 | 0 | 0 | 0 | 549150 | 2320000 | 0
Project Dashboard | IAD 669 TI | 26019 | Supply + Install | Green | Yellow | 101026019 | 101026019 | 0% | 2026-08-20 | 2027-05-14 | Chris Buttrey | 0% | 3995000 | 2996250 | 0 | 3995000 | 2996250 | 0 | 0 | 0 | 2996250 | 2996250 | 0 | 0 | 0 |  | 3995000 | 3995000 | 0 | 0 | 0 | 998750 | 25% | 25% | 33.33% | 0% | 0 | 0 | 0 | 0 | 0 | 3995000 | 3995000 | 0
Project Dashboard | IAD 670 TI | 26020 | Supply + Install | Green | Yellow | 101026020 | 101026020 | 0% | 2026-08-20 | 2027-05-14 | Chris Buttrey | 0% | 4362000 | 3271500 | 0 | 4362000 | 3271500 | 0 | 0 | 0 | 3271500 | 3271500 | 0 | 0 | 0 |  | 4362000 | 4362000 | 0 | 0 | 0 | 1090500 | 25% | 25% | 33.33% | 0% | 0 | 0 | 0 | 0 | 0 | 4362000 | 4362000 | 0
Project Dashboard | ALE060 COPT Potranco | 26021 | Supply + Install | Yellow | Green | 101026021 | 101026021 | 28% | 2026-04-16 | 2026-08-25 | Matt Rassmussen | 0% | 2220000 | 1619670 | 0 | 2220000 | 1619670 | 0 | 0 | 1619670 | 0 | 0 | 0 | 0 | 0 |  | 2220000 | 2220000 | 0 | 0 | 0 | 600330 | 27.04% | 27.04% | 37.06% | 0% | 0 | 0 | 0 | 0 | 0 | 600330 | 2220000 | 0
Project Dashboard | LTW061 | 26022 | Supply + Install | Green | Green | 101026022 | 101026022 | 20% | 2026-03-20 | 2026-09-15 | Matt Rassmussen | 0% | 1531656 | 1078768 | 0 | 1531656 | 1078768 | 0 | 815842.78 | 262925.22 | -3.0013e-11 | -3.0013e-11 | 0 | 0 | 0 |  | 1531656 | 1531656 | 0 | 0 | 0 | 452888 | 29.57% | 29.57% | 41.98% | 0% | 0 | 0 | 0 | 0 | 0 | 452888 | 1531656 | 0
Project Dashboard | NSH Atlanta ED | 26023 | Supply + Install | Green | Red | 101026023 | 101026023 | 0% | 2026-08-20 | 2027-05-14 | Carlos Silva | 0.001043% | 1368000 | 1026000 | 0 | 1368000 | 1026000 | 10.7 | 0 | 0 | 1025989.3 | 1025989.3 | 0 | 0 | 0 |  | 1368000 | 1368000 | 0 | -10.7 | -10.7 | 342000 | 25% | 25% | 33.33% | 0% | 0 | 0 | 0 | 0 | 0 | 1367989.3 | 1368000 | 0
Project Dashboard | QTS ALT2 DC6 | 26024 | Supply + Install | Green | Green | 101026024 | 101026024 | 13% | 2026-04-08 | 2027-10-08 | Colton Van Meter | 0% | 4537000 | 3464632 | 0 | 4537000 | 3464632 | 0 | 0 | 3464632 | 0 | 0 | 0 | 0 | 0 |  | 4537000 | 4537000 | 0 | 0 | 0 | 1072368 | 23.64% | 23.64% | 30.95% | 0% | 0 | 0 | 0 | 0 | 0 | 1072368 | 4537000 | 0
Project Dashboard | CyrusOne NVA 11 | 26025 | Supply + Install | Green | Yellow | 101026025 | 101026025 | 0% | 2026-08-20 | 2027-05-14 | TBC | 0% | 720000 | 540000 | 0 | 720000 | 540000 | 0 | 0 | 0 | 540000 | 540000 | 0 | 0 | 0 |  | 720000 | 720000 | 0 | 0 | 0 | 180000 | 25% | 25% | 33.33% | 0% | 0 | 0 | 0 | 0 | 0 | 720000 | 720000 | 0
Project Dashboard | QTS ATL2 DC7 | 26026 | Supply + Install | Green | Yellow | 101026026 | 101026026 | 0% | 2026-08-20 | 2027-05-14 | Colton Van Meter | 0% | 3289500 | 2467125 | 0 | 3289500 | 2467125 | 0 | 0 | 0 | 2467125 | 2467125 | 0 | 0 | 0 |  | 3289500 | 3289500 | 0 | 0 | 0 | 822375 | 25% | 25% | 33.33% | 0% | 0 | 0 | 0 | 0 | 0 | 3289500 | 3289500 | 0
Project Dashboard | Cannon Ford Moss Point | 26027 |  | Green | Yellow | 101026027 | 101026027 | 0% | 2026-08-20 | 2027-05-14 | TBC | 0% | 119500 | 89625 | 0 | 119500 | 89625 | 0 | 0 | 0 | 89625 | 89625 | 0 | 0 | 0 |  | 119500 | 119500 | 0 | 0 | 0 | 29875 | 25% | 25% | 33.33% | 0% | 0 | 0 | 0 | 0 | 0 | 119500 | 119500 | 0

## Summary
Total Number of Active Projects | 116
Total Contract Value | 179541013.62
Total Initial Budget | 122655296.125
Total Change Order Budget | 11162295.05
Total Current Budget | 132237695.108
Total Actual Cost | 51564182.25
Total Projected Spend | 49222418.773
Total Budget Remaining | 8973023.205
Total Value of Submitted Change Orders | 934135.4
Total Value of Executed Change Orders | 11162295.05
Total Value of Rejected Change Orders | 231350.6
Total Value of Voided Change Orders | 1493936.55
Total Amount Invoiced To date | 78288687
Total Contract - Projected Spend | 130318594.847
Total Invoiced - Actual Cost | 26724504.75
Commited Cost | 22478070.88
Profit | 47303318.512
AC + CC | 74042253.13
Current CV total | 179541013.62
Current CV - Billed | 101252326.62
Recognized revenue | 71353500
CV - recognized revenue | 108187513.62
Average Margin | 26.35%
CV-BAC | 47303318.512
Total of Sold COR | 15604606.12
Budget Health | Red
Install Jobs | 86
Supply Jobs | 29
Cost to come | 71700489.653
Cost to come check | 80673512.858
Over / Under Billed | 6935187