## Production Schedule
Unique Tag | ID | Duplicate Entry | Job Name | Job Address | PM | PM Phone | System | Crating Plan | Release Notes | Description | Included with this issue | Misc Materials | Production Folder | Percent Panels Released | Total Panels Released | Total Quoted Panels | Panel Qty | Part Qty | Sketch Qty | Extrusion Qty | Reveal LF | Program Material Qty | Prog Run Time | Material | Material Type | Material Desc | Material Grain | Outsource Eng | Outsource Eng Group | Ranked Priority | Days to Release | Responsible | Eng Manager | Evaluation By | LO By | LO Check By | Sketch By | Sketch Check By | Correction By | Eng Returned | AXYZ Prog By | Laser Prog By | Punch Prog By | Prog Complete | Prog Returned | Release By | Date Submitted | Short Engineering Lead | Release To Shop Target | Released to Shop Actual | Short Fab Lead | Shop Complete By Date | Ship To Coating Target | Ship Target | Adjusted Ship Date | Requested Ship Date | Ship Actual | Ship To Coating Actual | Material In Stock | Sheet Qty | Material Date | Post Prod Coating | Coating Process | Vendor Coating Info | Post Coating Shipping Instructions | Screw Color | Screws Ordered | Shop Drawings | Scan | Scan Location | FD | FD Location | Calcs | Calcs Location | Remake Piecemarks | Original Release | RP Reason | RM Reason | Remake Request By | Station | LO | Sketch | CNC | Prog CNC | Vendor Cut | Flat Laser | Tube Laser | Prog Laser | Punch | Prog Punch | Roll | Shear | Cidan | Mill | Prog Mill | Extrusion Saw | 1st Manual | Brake | Prog Brake | 2nd Manual | Weld | Robot Weld | Prog Robot Weld | Metal Finish | CNB | Fab | Assembly | Processing Customer No | Short Job No | Release Type | Rework Release Type | Release No | Nonconformance # | Release No H1 | Highest Release | Process Required Start Date | Eng Hold | Eng Hold Start | Eng Hold End | Eng Days On Hold | Prog Hold | Prog Hold Start | Prog Hold End | Prog Days On Hold | Process Hold | Process Hold Start | Process Hold End | Process Days On Hold | QC Hold | QC Hold Start | QC Hold End | QC Days On Hold | Total Days On Hold | Drafting Hours | Shop Hours | Laser Hours | Punch Hours | Mill Hours | Roll Hours | 1st Manual Hours | Brake Hours | 2nd Manual Hours | Weld Hours | Assembly Hours | Partial Shipment | Shipping Method | Total # Crates | Total # Skids | Programs Required | Required Processes | Date Programming Received | Date Programming Complete | Days In Programming | Date QC Received | Days In QC | Date Crating Received | Days In Crating | Program Lead | Shipping Department | Date Ready to Ship | Ship Late | Ship v Target | Latest Comment | Department | Discard Issue | Inhouse PM | Inhouse Drafter | Inhouse Checker | Inhouse Name | Generate Inhouse (Manual) | Week to Ship | Tube Bender | Band Saw | 5030 | Tube Bender Hours | Band Saw Hours
1 | 24060-BM01 |  | Loves Blacksburg | 116 Preister Road Blacksburg, SC 29702 | Cole Norona | 931.591.9340 |  |  |  | 102: 6 pieces at 10ft 103: 8 pieces at 10ft |  | 102: 6 pieces at 10ft 103: 8 pieces at 10ft | Q:\Jobs\24060 - Loves Blacksburg\04_Production\24060BM01 | N/A | N/A | N/A |  | 14 | 2 | - | - | 3 |  | 18 Ga. X 48" X 120" Steel Sheet, No Grain | Steel Sheet | 18 Ga. X 48" X 120" | No |  |  | 1 | -302 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi | [6 empty] | Hennadii Stakhurskyi | 2025-01-08 16:50 |  | 2025-02-12 | 2025-01-13 |  | 2025-02-19 |  | 2025-02-21 |  | 2025-02-21 |  |  | YES | 2 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 24060 | BM |  | 01 |  | 1 | 24060-BM01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 12 | 28 | [10 empty] | Hot Shot |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2025-02-06 | 3 | David Hasty | Ramon Estrada, Shane Watson | 2025-02-10 |  | Issue Still in Process |  | 1010 |  | Cole Norona | Hennadii Stakhurskyi | Denis Usatenko | 24060-BM01 In-House |  | 2025, Week 08
2 | 24071-FS10.R |  | RS Gass State Lab | 975 RS Gass Blvd Nashville, TN 37216 | Cole Norona | 931.591.9340 | 400 |  |  | (25) of 1 5/8" reveals at 8' long |  | (25) of 1 5/8" reveals at 8' long | Q:\Jobs\24071 - RS Gass State Lab\04_Production\24071FS10R | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 200 | Drop | na | 4mm X 62" X 196", Bright Silver Metallic FR ACM, Grain | FR ACM | 4mm X 62" X 196", Bright Silver Metallic | Yes |  |  | 29 | -50 | Ramon Estrada, Shane Watson | Denis Usatenko | [12 empty] | Denis Usatenko | 2026-01-21 08:28 | TRUE | 2026-02-11 | 2026-01-21 | TRUE | 2026-02-06 |  | 2026-01-26 |  | 2026-01-26 |  |  | YES | 45 | [5 empty] | N/A | N/A | Approved | YES | Q:\Jobs\24071 - RS Gass State Lab\03_Engineering\02_FD Docs\24071_FS10 | YES | Q:\Jobs\24071 - RS Gass State Lab\03_Engineering\02_FD Docs\24071_FS10 | NO | [6 empty] | Ready to Ship | [11 empty] | TRUE | [16 empty] | 24071 | FS |  | 10.R |  | 0 | 24071-FS11 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 1 | [10 empty] | Customer Pick Up |  |  |  | Shear |  |  | No Program Requested |  | QC Not Requested | 2026-01-23 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2026-01-23 |  | Issue Still in Process |  | 1010 |  | Cole Norona |  |  | 24071-FS10.R In-House |  | 2026, Week 05
3 | 24051-FS200 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | MOONSTONE BAND ON LEVEL 7 |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS200 | 34.48% | 6643 | 19268 | 131 | 131 | 2 | 917 | 700 | 196 X 62 - 44 | 18:17:07 | 4MM FR CORE MOONSTONE METALLIC FR ACM, Grain | FR ACM | 4MM FR CORE MOONSTONE METALLIC | Yes |  |  | 19 | -218 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-03-07 16:19 |  | 2025-05-29 | 2025-04-15 |  | 2025-06-17 |  | 2025-06-19 |  | 2025-06-19 |  |  | YES | 250 | 2025-04-10 |  |  |  |  | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 200 |  | 200 | 24051-FS231 |  |  | 2025-03-21 | 2025-03-25 | 3 |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | 3 | 4 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-04-14 | 2025-04-14 | 1 |  | Issue Still In Process |  | Crating Start Date Not Recorded | David Hasty | Ramon Estrada, Shane Watson | 2025-06-19 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS200 In-House |  | 2025, Week 25
4 | 24051-FS201 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | level 400 moonstone |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS201 | 50.09% | 9651 | 19268 | 109 | 109 | 2 | 1090 | 700 | Sheet Size Quantity 196 x 62 in 55 | 00d20h30m49s | 4MM MOONSTONE METALLIC 62 X 196 FR ACM, Grain | FR ACM | 4MM MOONSTONE METALLIC 62 X 196 | Yes |  |  | 43 | -107 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-03-10 09:04 |  | 2025-10-31 | 2025-10-21 |  | 2025-11-19 |  | 2025-11-21 |  | 2025-11-21 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 201 |  | 201 | 24051-FS231 |  |  | 2025-03-21 | 2025-10-14 | 148 |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | 148 | 4 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-10-21 | 2025-10-21 | 1 |  | QC Not Requested | 2025-10-30 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-10-31 |  | Issue Still in Process | Arnold Jurado - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS201 In-House |  | 2025, Week 47
5 | 24051-FS205 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | South Elevation 700 level. Install Direction Left to Right | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | 2 SETS - INSTALL DRAWINGS 750 LF - 1 5/8" REVEALS TO MATCH 725 pcs - Corner Clips 1450 pcs﻿ - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS205 | 50.7% | 9769 | 19268 | 118 | 118 | 2 | 1180 | 750 | 59 sheets | 00d22h08m40s | Alpolic - 4mm - 880 pcs - [62 X 196] - MOONSTONE METALLIC FR ACM, Grain | FR ACM | Alpolic - 4mm - 880 pcs - [62 X 196] - MOONSTONE METALLIC | Yes |  |  | 43 | -107 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-03-21 05:40 |  | 2025-10-31 | 2025-10-23 |  | 2025-11-19 |  | 2025-11-21 |  | 2025-11-21 |  |  | YES | 500 | 2025-04-10 |  |  |  |  | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 205 |  | 205 | 24051-FS231 |  |  | 2025-03-21 | 2025-10-16 | 150 |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | 150 | 8 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-10-22 | 2025-10-23 | 2 |  | QC Not Requested | 2025-11-07 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-11-07 |  | Issue Still in Process | Arnold Jurado - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS205 In-House |  | 2025, Week 47
6 | 24051-FS206 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | LEVEL 400 INSTALL LEFT TO RIGHT |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS206 | 34.85% | 6715 | 19268 | 72 | 72 | 2 | 504 | 600 | 196 X 62 - 24 | 10:02:09 | 4MM FR CORE MOONSTONE METALLIC 62 X 196 FR ACM, Grain | FR ACM | 4MM FR CORE MOONSTONE METALLIC 62 X 196 | Yes |  |  | 22 | -214 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-03-21 14:52 |  | 2025-06-04 | 2025-04-15 |  | 2025-06-23 |  | 2025-06-25 |  | 2025-06-25 |  |  | NO | 500 | 2025-04-10 |  |  |  |  | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans |  | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 206 |  | 206 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-04-15 | 2025-04-15 | 1 |  | QC Not Requested | 2025-06-18 | 6 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-25 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS206 In-House |  | 2025, Week 26
7 | 24051-FS209.1 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | SOUTH LEVEL 50 WING WALL | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( 350 LF) 1-5/8" Reveals * ( 16 LF) JR2 | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS209.1 | 70.04% | 13495 | 19268 | 36 | 76 | 50 | 292 | 350 | 13 SHEETS | 00d05h30m19s | 4mm X 62" X 196", MOONSTONE METALLIC FR ACM, Grain | FR ACM | 4mm X 62" X 196", MOONSTONE METALLIC | Yes |  |  | 87 | -25 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Denis Usatenko | 2026-01-09 15:46 |  | 2026-02-09 | 2026-02-25 | TRUE | 2026-03-13 |  | 2026-03-02 |  | 2026-03-02 |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 209.1 |  | 209.1 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 40 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-02-24 | 2026-02-25 | 2 |  | QC Not Requested | 2026-03-24 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-24 |  | Issue Still in Process | Arnold Jurado - @dusatenko@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS209.1 In-House |  | 2026, Week 010
8 | 24051-FS212 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | NORTH LEVEL 400 INSTALL RIGHT TO LEFT |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS212 | 34.99% | 6741 | 19268 | 26 | 26 | 2 | 182 | 300 | 196 X 62 - 9 | 03:38:58 | 4MM FR CORE MOONSTONE METALLIC 62X196 FR ACM, Grain | FR ACM | 4MM FR CORE MOONSTONE METALLIC 62X196 | Yes |  |  | 12 | -224 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-04-04 15:52 |  | 2025-05-21 | 2025-04-15 |  | 2025-06-09 |  | 2025-06-11 |  | 2025-06-11 |  |  | NO | 500 | 2025-04-10 |  |  |  |  | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 212 |  | 212 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 50 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-04-15 | 2025-04-15 | 1 |  | QC Not Requested | 2025-06-18 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-19 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS212 In-House |  | 2025, Week 24
9 | 25002-FS11.1 |  | Med Center Health | 250 Park Street Bowling Green, KY 42101 | Carlos Silva | 980.246.6545 | 600 |  |  | PLEASE SEE ATTACHED IMAGE COLUMNS NORTH - WEST ELEVATION 238, 239, 240, 241, 129/242 130/242 131/242 132/242 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (215 LF) 1-3/4" Reveals * (14 LF) PE1N * (10 PCS) PET * (180 PCS) PE2N | "Q:\Jobs\25002 - Med Center Health\04_Production\25002FS11.1" | 80.59% | 1623 | 2014 | 18 | 18 | 2 | 50 | 215 | 18 SHEETS | 00d04h02m33s | ACM: 4mm X 62" X 196", MICA GRAY FR ACM, Grain | FR ACM | ACM: 4mm X 62" X 196", MICA GRAY | Yes |  |  | 1 | -10 | Corey Howse | Denis Usatenko | Gabriela Hoyle | Gabriela Hoyle |  | Gabriela Hoyle | Denis Usatenko | Gabriela Hoyle |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Gabriela Herrera, Gabriela Hoyle | 2026-02-05 10:05 | TRUE | 2026-02-26 | 2026-03-18 | TRUE | 2026-04-03 |  | 2026-03-02 |  | 2026-03-02 |  |  | YES | 00 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Clean and Brake | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 25002 | FS |  | 11.1 |  | 11.1 | 25002-FS16 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 5 | 20 | [10 empty] | Semi |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-03-16 | 2026-03-17 | 2 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Tony Graves - still waiting on the roller to be fixed. | 1010 |  | Carlos Silva | Gabriela Hoyle | Denis Usatenko | 25002-FS11.1 In-House |  | 2026, Week 010
10 | 26014-02-ST01 |  | 2026 R & D | 3731 Amy Lynn Drive Nashville, TN 37218-3813 | TBC |  | --- |  | Deliver part 260112ST-1001 to Paul Roberts after deburr. Neither DA, timesaver, nor paint/powder are required for 260112ST. Parts are needed as soon as possible. Parts 26014-01-1001 and 26014-01-1002 go to PWX and return to JWM. Provide drawings to PWX for powder instruction. Ship to paint and ship target are for the sign parts. |  |  |  |  | N/A | N/A | N/A |  | 10 | 3 |  |  |  |  | Min. drop 11 Ga. SS Sheet, No Grain | SS Sheet | Min. drop 11 Ga. | No |  |  | 1 | -54 | Rogerson Jean-Charles, Sean Doss | David Hasty | [8 empty] | Chris Gambrel |  |  |  |  | 2026-01-13 15:24 | TRUE | 2026-02-03 | 2026-01-15 | TRUE | 2026-02-02 | 2026-01-15 | 2026-01-22 |  | 2026-01-22 |  |  | YES |  |  | TRUE | Powder Coat | PWX. Sign is black, backer plate is white. Provide drawings to PWX for specific instructions. | Coating Ship Back To JWM |  |  | None Available | NO |  | NO |  | NO | [6 empty] | QC | [5 empty] | TRUE | [22 empty] | 26014-02 | ST |  | 01 |  | 1 | 26014-02-ST01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 2 | 2 | [13 empty] | Flat Laser | Flat Laser Powder Coat |  |  | No Program Requested | 2026-01-28 | 57 (In Progress) |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | TBC |  |  | 26014-02-ST01 In-House | TRUE | 2026, Week 04
11 | 24051-FS46.1 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | SOUTH LEVEL 200 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( 504LF) 1-5/8" Reveals * ( 107 pcs) Corner Clips * ( 214 pcs ) Color Matching Screws﻿ * ( 140 LF) JR2 (EXTENDED?) | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS46.1 | 65.81% | 12681 | 19268 | 56 | 56 | 8 | 362 | 140 | 13 sheets | 00d06h31m30s | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 75 | -46 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Ailen Niedfeld |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Ailen Niedfeld | 2025-12-18 16:23 |  | 2026-01-12 | 2026-01-27 | TRUE | 2026-02-12 |  | 2026-02-02 |  | 2026-02-02 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans |  | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 46.1 |  | 46.1 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 16 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab | 2026-01-24 | 2026-01-26 | 1 |  | QC Not Requested | 2026-03-02 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-03 |  | Issue Still in Process | Arnold Jurado - @aniedfeld@jwmcd.com | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS46.1 In-House |  | 2026, Week 06
12 | 24051-FS46C |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS | COPING FOR SOUTH LEVEL 200 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | 2 SETS - INSTALL DRAWINGS 150 LF - 1 5/8" REVEALS TO MATCH 200 pcs - Corner Clips 400 pcs - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS46C | 53.35% | 10280 | 19268 | 25 | 25 | 2 | 175 | 150 | 3 SHEETS | 00d02h35m22s | Alpolic - 4mm - 3600 pcs - [62 X 196] - TOB BLACK FR ACM, No Grain | FR ACM | Alpolic - 4mm - 3600 pcs - [62 X 196] - TOB BLACK | No |  |  | 52 | -96 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-16 10:32 |  | 2025-11-17 | 2025-11-10 |  | 2025-12-04 |  | 2025-12-08 |  | 2025-12-08 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 46C |  | 0 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 8 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-11-06 | 2025-11-07 | 2 |  | QC Not Requested | 2025-12-05 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-12-08 |  | Issue Still in Process | Arnold Jurado - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS46C In-House | TRUE | 2025, Week 50
13 | 24051-FS47C |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS | COPING FOR FS 47. | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | 2 SETS - INSTALL DRAWINGS 700 LF - 1 5/8" REVEALS TO MATCH 400 pcs - Corner Clips 800 pcs - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS47C | 53.87% | 10379 | 19268 | 99 | 99 | 2 | 693 | 700 | 20 SHEETS | 00d11h55m27s | Alpolic - 4mm - 3600 pcs - [62 X 196] - TOB BLACK FR ACM, No Grain | FR ACM | Alpolic - 4mm - 3600 pcs - [62 X 196] - TOB BLACK | No |  |  | 54 | -92 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-16 14:44 |  | 2025-11-21 | 2025-11-10 |  | 2025-12-10 |  | 2025-12-12 |  | 2025-12-12 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 47C |  | 0 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 16 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-11-06 | 2025-11-07 | 2 |  | QC Not Requested | 2025-12-08 | 5 | David Hasty | Ramon Estrada, Shane Watson | 2025-12-12 |  | Issue Still in Process | Arnold Jurado - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS47C In-House | TRUE | 2025, Week 50
14 | 24051-FS48 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS | EAST LEVEL 200 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | 2 SETS - INSTALL DRAWINGS 600 LF - 1 5/8" REVEALS TO MATCH 600 LF - 1 1/8" REVEALS TO MATCH 500 pcs - Corner Clips 1000 pcs﻿ - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS48 | 54.9% | 10578 | 19268 | 124 | 124 | 2 | 992 | 1200 | 42 | 21:14:58 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 54 | -92 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-16 15:36 |  | 2025-11-21 | 2025-11-18 |  | 2025-12-10 |  | 2025-12-12 |  | 2025-12-12 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 48 |  | 48 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 24 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-11-18 | 2025-11-18 | 1 |  | QC Not Requested | 2025-12-10 | 3 | David Hasty | Ramon Estrada, Shane Watson | 2025-12-12 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS48 In-House |  | 2025, Week 50
15 | 24051-FS49 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS EVERY CRATE REQUIRES PR2 | EAST LEVEL 200 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | 2 SETS - INSTALL DRAWINGS 600 LF - 1 5/8" REVEALS TO MATCH 600 LF - 1 1/8" REVEALS TO MATCH 600 LF - PR2 | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS49 | 55.54% | 10702 | 19268 | 124 | 124 | 2 | 571 | 750 | 9 | 09:12:28 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 56 | -91 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-16 15:47 |  | 2025-11-24 | 2025-11-18 |  | 2025-12-11 |  | 2025-12-15 |  | 2025-12-15 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 49 |  | 49 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-11-18 | 2025-11-18 | 1 |  | QC Not Requested | 2025-12-10 | 4 | David Hasty | Ramon Estrada, Shane Watson | 2025-12-15 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS49 In-House |  | 2025, Week 51
16 | 24051-FS50 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS | AEAST LEVEL 200 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | 2 SETS - INSTALL DRAWINGS 600 LF - 1 5/8" REVEALS TO MATCH 600 LF - 1 1/8" REVEALS TO MATCH 250 pcs - Corner Clips 500 pcs﻿ - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS50 | 56.19% | 10826 | 19268 | 124 | 124 | 4 | 744 | 1200 | 39 | 16:51:46 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 56 | -91 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-16 15:52 |  | 2025-11-24 | 2025-11-18 |  | 2025-12-11 |  | 2025-12-15 |  | 2025-12-15 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 50 |  | 50 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-11-18 | 2025-11-18 | 1 |  | QC Not Requested | 2025-12-15 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-12-15 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS50 In-House |  | 2025, Week 51
17 | 24051-FS50C |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS | EAST LEVEL 200 COPING | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | 2 SETS - INSTALL DRAWINGS 200 LF - 1 5/8" REVEALS TO MATCH 50 pcs - Corner Clips 100 pcs﻿ - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS50C | 56.31% | 10850 | 19268 | 24 | 24 | 2 | 168 | 200 | 3 | 02:29:59 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 56 | -91 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-16 16:01 |  | 2025-11-24 | 2025-11-18 |  | 2025-12-11 |  | 2025-12-15 |  | 2025-12-15 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 50C |  | 0 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 40 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-11-18 | 2025-11-18 | 1 |  | QC Not Requested | 2025-12-15 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-12-15 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS50C In-House |  | 2025, Week 51
18 | 24051-FS51 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS EVERY CRATE REQUIRES PR2 | EAST LEVEL 300 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | 2 SETS - INSTALL DRAWINGS 700 LF - 1 5/8" REVEALS TO MATCH 500 LF - 1 1/8" REVEALS TO MATCH 200 LF - PR2 500 pcs - Corner Clips 1000 pcs﻿ - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS51 | 56.93% | 10970 | 19268 | 120 | 120 | 9 | 825 | 1200 | 34 | 16:19:31 | 4M X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4M X 62" X 196", TOB BLACK | No |  |  | 61 | -73 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-21 10:25 |  | 2025-12-18 | 2025-11-18 |  | 2026-01-06 |  | 2026-01-08 |  | 2026-01-08 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 51 |  | 51 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-11-18 | 2025-11-18 | 1 |  | QC Not Requested | 2026-01-03 | 4 | David Hasty | Ramon Estrada, Shane Watson | 2026-01-08 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS51 In-House |  | 2026, Week 02
19 | 24051-FS51C |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS | EAST LEVEL 300 COPING | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | 2 SETS - INSTALL DRAWINGS 250 LF - 1 5/8" REVEALS TO MATCH 175 pcs - Corner Clips 350 pcs﻿ - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS51C | 57.14% | 11010 | 19268 | 40 | 40 | 3 | 280 | 250 | 4 | 04:05:04 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 59 | -75 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-21 10:29 |  | 2025-12-16 | 2025-11-18 |  | 2026-01-02 |  | 2026-01-06 |  | 2026-01-06 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 51C |  | 0 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 40 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-11-18 | 2025-11-18 | 1 |  | QC Not Requested | 2026-01-03 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-01-06 |  | Issue Still in Process | Issiah Havens - @jdavis@jwmcd.com @hstakhurskyi@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS51C In-House |  | 2026, Week 02
20 | 24051-FS217 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS | REF SHOP DRAWING 4113. EAST ELEVATION ON THE SOUTH SIDE. CL S16 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | 2 SETS - INSTALL DRAWINGS 100 LF - 1 5/8" REVEALS TO MATCH 25 pcs - Corner Clips 50 pcs - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS217 | 51.48% | 9919 | 19268 | 12 | 12 | 3 | 84 | 100 | 4 | 01:41:18 | Alpolic - 4mm - 880 pcs - [62 X 196] - MOONSTONE METALLIC FR ACM, Grain | FR ACM | Alpolic - 4mm - 880 pcs - [62 X 196] - MOONSTONE METALLIC | Yes |  |  | 50 | -97 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-16 14:27 |  | 2025-11-14 | 2025-10-30 |  | 2025-12-03 |  | 2025-12-05 |  | 2025-12-05 |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 217 |  | 217 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 16 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-10-29 | 2025-10-29 | 1 |  | QC Not Requested | 2025-11-14 | 9 | David Hasty | Ramon Estrada, Shane Watson | 2025-11-26 |  | Issue Still in Process | Issiah Havens - @jdavis@jwmcd.com @hstakhurskyi@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS217 In-House |  | 2025, Week 49
21 | 24051-FS218 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS | EAST LEVEL 300 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | 2 SETS - INSTALL DRAWINGS 600 LF - 1 5/8" REVEALS TO MATCH 590 pcs - Corner Clips 1180 pcs - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS218 | 51.98% | 10016 | 19268 | 97 | 97 | 2 | 970 | 600 | 49 | 18:13:15 | Alpolic - 4mm - 880 pcs - [62 X 196] - MOONSTONE METALLIC FR ACM, Grain | FR ACM | Alpolic - 4mm - 880 pcs - [62 X 196] - MOONSTONE METALLIC | Yes |  |  | 50 | -97 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-20 08:49 |  | 2025-11-14 | 2025-10-30 |  | 2025-12-03 |  | 2025-12-05 |  | 2025-12-05 |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 218 |  | 218 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 180 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-10-29 | 2025-10-29 | 1 |  | QC Not Requested | 2025-11-15 | 6 | David Hasty | Ramon Estrada, Shane Watson | 2025-11-24 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS218 In-House |  | 2025, Week 49
22 | 24051-FS219 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS | EAST LEVEL 400 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | 2 SETS - INSTALL DRAWINGS 650 LF - 1 5/8" REVEALS TO MATCH 660 pcs - Corner Clips 1320 pcs - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS219 | 52.55% | 10125 | 19268 | 109 | 109 | 2 | 1090 | 650 | 55 | 20:28:06 | Alpolic - 4mm - 880 pcs - [62 X 196] - MOONSTONE METALLIC FR ACM, Grain | FR ACM | Alpolic - 4mm - 880 pcs - [62 X 196] - MOONSTONE METALLIC | Yes |  |  | 49 | -99 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-21 15:15 |  | 2025-11-12 | 2025-10-30 |  | 2025-12-01 |  | 2025-12-03 |  | 2025-12-03 |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 219 |  | 219 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 12 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-10-29 | 2025-10-29 | 1 |  | QC Not Requested | 2025-12-05 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-12-08 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS219 In-House |  | 2025, Week 49
23 | 24051-FS221 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | Moonstone panels for sheet 6110 install right to left | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (75 LF) 1-5/8" Reveals | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS221 | 65.88% | 12694 | 19268 | 13 | 13 | 3 | 91 | 55 | 5 | 01:53:04 | 4mm X 62" X 196", moonstone metallic FR ACM, Grain | FR ACM | 4mm X 62" X 196", moonstone metallic | Yes |  |  | 75 | -46 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Ailen Niedfeld |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Ailen Niedfeld | 2025-12-19 11:17 |  | 2026-01-19 | 2026-01-27 | TRUE | 2026-02-12 |  | 2026-02-09 |  | 2026-02-09 |  |  | YES | 200 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans |  | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 221 |  | 221 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 16 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-01-23 | 2026-01-27 | 3 |  | QC Not Requested | 2026-02-27 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2026-02-28 |  | Issue Still in Process | Issiah Havens - @jdavis@jwmcd.com PROGRAMMED. @aniedfeld@jwmcd.com please print all programming documents in the "PROGRAMMING DOCS" folder | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS221 In-House | TRUE | 2026, Week 07
24 | 24051-FS223 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | LEVEL 50 NORTH ELEVATION | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (500 LF) 1-5/8" Reveals * (100 LF) 1-1/8" Reveals * (20 LF) JR-Extended * (24 pcs) 2' - 0" x 2' - 0" x 1-5/8" Corner reveals | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS223 | 75.47% | 14541 | 19268 | 44 | 90 | 59 | 387 | 700 | 23 | 08:01:00 | 4mm X 62" X 196", MOONSTONE METALLIC FR ACM, Grain | FR ACM | 4mm X 62" X 196", MOONSTONE METALLIC | Yes |  |  | 2 | -6 | Corey Howse | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2026-02-02 10:58 |  | 2026-02-23 | 2026-03-24 | TRUE | 2026-04-09 |  | 2026-03-16 |  | 2026-03-16 |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Clean and Brake | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 223 |  | 223 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 12 | 40 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-03-24 | 2026-03-24 | 1 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Issiah Havens - @dusatenko@jwmcd.com @jdavis@jwmcd.com programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS223 In-House |  | 2026, Week 12
25 | 24051-FS224 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | NORTH FIELD MEASURES |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (8 LF) JR2 | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS224 | 75.48% | 14543 | 19268 | 2 | 2 | 2 | 16 | 0 | 1 | 00:17:51 | 4mm X 62" X 196", MOONSTONE METALLIC FR ACM, Grain | FR ACM | 4mm X 62" X 196", MOONSTONE METALLIC | Yes |  |  | 101 | -6 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2026-02-05 11:31 | TRUE | 2026-02-26 | 2026-03-24 | TRUE | 2026-04-09 |  | 2026-03-16 |  | 2026-03-16 |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 224 |  | 224 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 2 | 4 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-03-24 | 2026-03-24 | 1 |  | QC Not Requested | 2026-03-27 | 7 | David Hasty | Ramon Estrada, Shane Watson | 2026-04-06 |  | Issue Still in Process | Issiah Havens - @dusatenko@jwmcd.com @jdavis@jwmcd.com programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS224 In-House |  | 2026, Week 12
26 | 24051-FS67 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | THIS IS WEST ELEVTION LEVEL 00 - 200 FIELD MEASURES. PLEASE NOT THAT THEY ARE PROVIDING FINISHED PANEL SIZES. |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (60 LF) 1-5/8" Reveals * (11 LF) JR-EXTENDED * 70 PCS CORNER CLIPS * 162 PCS COLOR MATCHING SCREWS | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS67 | 66.46% | 12806 | 19268 | 14 | 14 | 14 | 138 | 60 | 4 | 01:51:35 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 79 | -43 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Gabriela Herrera |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Gabriela Herrera | 2025-12-16 11:38 | TRUE | 2026-01-06 | 2026-01-30 | TRUE | 2026-02-17 |  | 2026-01-19 |  | 2026-01-19 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 67 |  | 67 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 16 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-01-30 | 2026-01-30 | 1 |  | QC Not Requested | 2026-02-20 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-02-23 |  | Issue Still in Process | Issiah Havens - @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS67 In-House |  | 2026, Week 04
27 | 24051-FS72 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | LEVEL 300 NORTH ELEVATION | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (1300 LF) 1-5/8" Reveals * (100 LF) 1-1/8" Reveals﻿ * (120 LF) JR2 | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS72 | 67% | 12910 | 19268 | 104 | 104 | 12 | 704 | 1400 | 104 SHEETS | 00d21h07m06s | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 81 | -34 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-12-18 10:38 |  | 2026-01-12 | 2026-02-12 | TRUE | 2026-03-02 |  | 2026-02-02 |  | 2026-02-02 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 72 |  | 72 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab | 2026-02-11 | 2026-02-12 | 2 |  | QC Not Requested | 2026-03-04 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-04 |  | Issue Still in Process | Arnold Jurado - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS72 In-House | TRUE | 2026, Week 06
28 | 24051-FS73 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | NORTH LEVEL 50 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( 750 LF) 1-5/8" Reveals * ( 150 LF) 1-1/8" Reveals * ( 120 LF) JR-EXTENDED | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS73 | 67.34% | 12976 | 19268 | 66 | 66 | 24 | 386 | 900 | 65 SHEETS | 00d12h40m13s | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 81 | -34 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-12-18 11:12 |  | 2026-01-12 | 2026-02-12 | TRUE | 2026-03-02 |  | 2026-02-02 |  | 2026-02-02 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 73 |  | 73 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 16 | 120 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab | 2026-02-11 | 2026-02-12 | 2 |  | QC Not Requested | 2026-03-04 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-05 |  | Issue Still in Process | Arnold Jurado - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS73 In-House |  | 2026, Week 06
29 | 24051-FS56 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS | EAST LEVEL 400 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * 700 LF - 1 1/8" REVEALS TO MATCH * 1300 LF - 1 5/8" REVEALS TO MATCH * 300 pcs - Corner Clips * 600 pcs﻿ - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS56 | 59.37% | 11439 | 19268 | 149 | 149 | 2 | 894 | 2000 | 38 SHEETS | 00d19h23m01s | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 67 | -57 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-21 16:13 |  | 2026-01-09 | 2025-12-12 |  | 2026-01-28 |  | 2026-01-30 |  | 2026-01-30 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 56 |  | 56 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-12-11 | 2025-12-12 | 2 |  | QC Not Requested | 2026-01-29 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-01-30 |  | Issue Still in Process | Arnold Jurado - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS56 In-House |  | 2026, Week 05
30 | 24051-FS56C |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS | EAST LEVEL 400 COPING | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * 800 LF - 1 1/8" REVEALS TO MATCH * 200 LF - 1 5/8" REVEALS TO MATCH * 600 pcs - Corner Clips * 1200 pcs﻿ - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS56C | 60.14% | 11588 | 19268 | 149 | 149 | 2 | 1043 | 1000 | 15 | 15:13:12 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 68 | -56 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-22 08:48 |  | 2026-01-12 | 2025-12-12 |  | 2026-01-29 |  | 2026-02-02 |  | 2026-02-02 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 56C |  | 0 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-12-11 | 2025-12-12 | 2 |  | QC Not Requested | 2026-02-02 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2026-02-02 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS56C In-House |  | 2026, Week 06
31 | 24051-FS57 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS | EAST LEVEL 700 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * 800 LF - 1 5/8" REVEALS TO MATCH * 650 pcs - Corner Clips * 1300 pcs﻿ - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS57 | 62.76% | 12092 | 19268 | 158 | 158 | 2 | 1264 | 800 | 79 | 29:17:45 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 71 | -48 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-22 10:24 |  | 2026-01-22 | 2025-12-18 |  | 2026-02-10 |  | 2026-02-12 |  | 2026-02-12 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 57 |  | 57 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-12-17 | 2025-12-18 | 2 |  | QC Not Requested | 2026-02-11 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-02-12 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS57 In-House |  | 2026, Week 07
32 | 24051-FS58 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | * EVERY CRATE REQUIRES REVEALS * EVERY CRATE REQUIRES JR2 | EAST LEVEL 7 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * 800 LF - 1 5/8" REVEALS TO MATCH * 250 LF - 1 1/8" REVEALS TO MATCH * 750 LF - JR2 | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS58 | 63.58% | 12250 | 19268 | 158 | 158 | 2 | 726 | 1050 | 15 | 12:08:15 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 70 | -49 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-22 10:32 |  | 2026-01-21 | 2025-12-18 |  | 2026-02-09 |  | 2026-02-11 |  | 2026-02-11 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 58 |  | 58 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-12-17 | 2025-12-18 | 2 |  | QC Not Requested | 2026-02-10 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-02-11 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS58 In-House |  | 2026, Week 07
33 | 24051-FS59 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | * EVERY CRATE REQUIRES REVEALS | EAST LEVEL 700 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * 1400 LF - 1 5/8" REVEALS TO MATCH * 750 LF - 1 1/8" REVEALS TO MATCH * 170 pcs - Corner Clips * 340 pcs﻿ - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS59 | 64.4% | 12408 | 19268 | 158 | 158 | 2 | 1106 | 2150 | 53 | 23:29:47 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 60 | -74 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-22 10:43 |  | 2025-12-12 | 2025-12-18 | TRUE | 2026-01-05 |  | 2026-01-02 |  | 2026-01-02 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 59 |  | 59 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-12-17 | 2025-12-18 | 2 |  | QC Not Requested | 2026-03-05 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-05 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS59 In-House |  | 2026, Week 01
34 | 24051-FS59C |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | * EVERY CRATE REQUIRES REVEALS | EAST LEVEL 700 COPING | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * 900 LF - 1 5/8" REVEALS TO MATCH * 700 pcs - Corner Clips * 1400 pcs﻿ - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS59C | 65.22% | 12566 | 19268 | 158 | 158 | 2 | 1106 | 900 | 32 | 18:55:34 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 75 | -46 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-22 10:59 |  | 2026-01-26 | 2025-12-18 |  | 2026-02-12 |  | 2026-02-16 |  | 2026-02-16 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 59C |  | 0 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-12-17 | 2025-12-18 | 2 |  | QC Not Requested | 2026-02-14 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2026-02-16 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS59C In-House |  | 2026, Week 08
35 | 24051-FS54 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS ﻿EVERY CRATE REQUIRES JR2 | EAST LEVEL 400 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * 600 LF - 1 5/8" REVEALS TO MATCH * 400 LF - 1 1/8" REVEALS TO MATCH * 540 LF - JR2 * 550 pcs - Corner Clips * 1100 pcs﻿ - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS54 | 60.91% | 11737 | 19268 | 149 | 149 | 4 | 1033 | 1000 | 41 | 20:09:33 | 4mm X 62" X 196", TOP BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOP BLACK | No |  |  | 64 | -64 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-21 15:52 |  | 2025-12-31 | 2025-12-12 |  | 2026-01-19 |  | 2026-01-21 |  | 2026-01-21 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 54 |  | 54 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-12-11 | 2025-12-12 | 2 |  | QC Not Requested | 2026-01-18 | 3 | David Hasty | Ramon Estrada, Shane Watson | 2026-01-21 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS54 In-House |  | 2026, Week 04
36 | 24051-FS55 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS ﻿EVERY CRATE REQUIRES JR2 | EAST LEVEL 400 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * 1400 LF - 1 1/8" REVEALS TO MATCH * 250 LF - 1 5/8" REVEALS TO MATCH * 700 LF - JR2 | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS55 | 61.69% | 11886 | 19268 | 149 | 149 | 2 | 771 | 1650 | 10 SHEETS | 00d10h52m51s | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 66 | -63 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-21 15:57 |  | 2026-01-01 | 2025-12-12 |  | 2026-01-20 |  | 2026-01-22 |  | 2026-01-22 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 55 |  | 55 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-12-11 | 2025-12-12 | 2 |  | QC Not Requested | 2026-01-21 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-01-22 |  | Issue Still in Process | Arnold Jurado - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS55 In-House |  | 2026, Week 04
37 | 24051-FS29 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | NORTH LEVEL 4 INSTALL RIGHT TO LEFT |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS29 | 35.39% | 6819 | 19268 | 78 | 78 | 6 | 483 | 900 | 196 X 62 - 17 | 09:45:07 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 12 | -224 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-04-04 15:50 |  | 2025-05-21 | 2025-04-15 |  | 2025-06-09 |  | 2025-06-11 |  | 2025-06-11 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 29 |  | 29 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-04-14 | 2025-04-14 | 1 |  | QC Not Requested | 2025-06-05 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-05 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS29 In-House |  | 2025, Week 24
38 | 24051-FS29C |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | COPING FOR LEVEL 400 NORTH | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (200 LF) 1-5/8" Reveals | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS29C | 74.47% | 14349 | 19268 | 26 | 26 | 2 | 182 | 200 | 3 SHEETS | 00d02h40m56s | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 93 | -19 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Denis Usatenko, Hennadii Stakhurskyi | 2026-02-02 09:42 |  | 2026-02-23 | 2026-03-05 | TRUE | 2026-03-23 |  | 2026-03-16 |  | 2026-03-16 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 29C |  | 0 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 40 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-03-04 | 2026-03-05 | 2 |  | QC Not Requested | 2026-03-11 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-12 |  | Issue Still in Process | Arnold Jurado - @dusatenko@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS29C In-House |  | 2026, Week 12
39 | 24051-FS30 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | NORTH LEVEL 400 INSTALL DIRECTION RIGHT TO LEFT |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS30 | 36.05% | 6947 | 19268 | 128 | 128 | 2 | 768 | 1600 | 196 X 62 - 32 | 16:28:28 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 12 | -224 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-04-07 09:12 |  | 2025-05-21 | 2025-04-15 |  | 2025-06-09 |  | 2025-06-11 |  | 2025-06-11 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 30 |  | 30 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-04-14 | 2025-04-14 | 1 |  | QC Not Requested | 2025-06-05 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-06 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS30 In-House |  | 2025, Week 24
40 | 24051-FS31 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | NORTH LEVEL 400 INSTALL RIGHT TO LEFT |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS31 | 36.72% | 7075 | 19268 | 128 | 128 | 2 | 587 | 850 | 196 X 62 - 9 | 09:20:31 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 15 | -223 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-04-07 09:16 |  | 2025-05-22 | 2025-04-15 |  | 2025-06-10 |  | 2025-06-12 |  | 2025-06-12 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 31 |  | 31 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-04-14 | 2025-04-14 | 1 |  | QC Not Requested | 2025-06-06 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-06 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS31 In-House |  | 2025, Week 24
41 | 24051-FS32 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | NORTH LEVEL 400 INSTALL RIGHT TO LEFT |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS32 | 37.38% | 7203 | 19268 | 128 | 128 | 2 | 1024 | 1200 | 196 X 62 - 43 | 21:41:33 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 16 | -222 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-04-07 09:34 |  | 2025-05-23 | 2025-04-15 |  | 2025-06-11 |  | 2025-06-13 |  | 2025-06-13 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 32 |  | 32 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-04-14 | 2025-04-14 | 1 |  | QC Not Requested | 2025-06-06 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-09 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS32 In-House |  | 2025, Week 24
42 | 24051-FS33 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | NORTH LEVEL 7 RIGHT TO LEFT INSTALL |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS33 | 38.22% | 7364 | 19268 | 161 | 161 | 2 | 966 | 2100 | 196 X 62 - 54 | 23:37:44 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 17 | -219 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-04-07 16:16 |  | 2025-05-28 | 2025-04-15 |  | 2025-06-16 |  | 2025-06-18 |  | 2025-06-18 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 33 |  | 33 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-04-14 | 2025-04-15 | 2 |  | QC Not Requested | 2025-06-10 | 3 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-12 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS33 In-House |  | 2025, Week 25
43 | 24051-FS33C |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | COPING FOR WEST LEVEL 7 - TO SHIP WITH THE BALANCE OF THE AREA PANELS. |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS33C | 41.86% | 8065 | 19268 | 161 | 161 | 2 | 1127 | 800 | 196 X 62 - 33 | 19:30:16 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 25 | -202 | Unassigned | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-05-05 09:22 |  | 2025-06-20 | 2025-05-07 |  | 2025-07-09 |  | 2025-07-11 |  | 2025-07-11 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 33C |  | 0 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 200 | [13 empty] | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-05-06 | 2025-05-07 | 2 |  | QC Not Requested | 2025-06-17 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-18 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed, Paneltracker | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS33C In-House |  | 2025, Week 28
44 | 24051-FS34 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | NORTH LEVEL 700 INSTALL RIGHT TO LEFT |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS34 | 39.05% | 7525 | 19268 | 161 | 161 | 2 | 734 | 1000 | 196 X 62 - 15 | 12:15:15 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 19 | -218 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-04-07 16:18 |  | 2025-05-29 | 2025-04-15 |  | 2025-06-17 |  | 2025-06-19 |  | 2025-06-19 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 34 |  | 34 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-04-14 | 2025-04-15 | 2 |  | QC Not Requested | 2025-06-11 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-12 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS34 In-House |  | 2025, Week 25
45 | 24051-FS35 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | NORTH LEVEL 7 INSTALL RIGHT TO LEFT |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS35 | 39.88% | 7685 | 19268 | 160 | 160 | 3 | 1100 | 1400 | 196 X 62 - 43 | 20:52:00 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 21 | -217 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-04-07 16:20 |  | 2025-05-30 | 2025-04-15 |  | 2025-06-18 |  | 2025-06-20 |  | 2025-06-20 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 35 |  | 35 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-04-14 | 2025-04-15 | 2 |  | QC Not Requested | 2025-06-12 | 3 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-16 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS35 In-House |  | 2025, Week 25
46 | 24051-FS36 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | PLEASE NOTE THIS RELEASE IS FIELD PANELS AND THE PERIMETER PANELS WILL BE INSTALLED ONCE THESE ARE IN PLACE WEST LEVEL 00 WINGS |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS36 | 43.95% | 8469 | 19268 | 84 | 84 | 10 | 588 | 1100 | 196 X 62 - 84 | 17:44:16 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 31 | -188 | Unassigned | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-06-04 10:30 |  | 2025-07-10 | 2025-06-17 |  | 2025-07-29 |  | 2025-07-31 |  | 2025-07-31 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | YES | Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\01_Calcs\2025-5-27_LOCSHA STADIUM CALC PACKAGE | [5 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 36 |  | 36 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 40 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-06-17 | 2025-06-17 | 1 |  | QC Not Requested | 2025-06-20 | 3 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-24 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed, panel tracker | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS36 In-House |  | 2025, Week 31
47 | 24026-BM01 |  | 1740 Division | 1740 Division St. Nashville, TN 37203 | Chris Buttrey | 615.517.9885 | [6 empty] | Q:\Jobs\24026 - 1740 Division\04_Production\24026BM01 | N/A | N/A | N/A | 0 | 200 | 1 | 0 | 0 | 50 | na | ASHOP STOCK 48x120x16ga galv Galv Sheet, No Grain | Galv Sheet | ASHOP STOCK 48x120x16ga galv | No |  |  | 30 | -46 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2025-10-17 15:04 |  | 2026-02-05 | 2025-10-20 |  | 2026-02-12 |  | 2026-02-16 |  | 2026-02-16 |  |  | YES | 100 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 24026 | BM |  | 01 |  | 1 | 24026-BM01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 2 | 16 | [10 empty] | In House |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2025-11-06 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-11-07 |  | Issue Still in Process |  | 1010 |  | Chris Buttrey | Denis Usatenko |  | 24026-BM01 In-House |  | 2026, Week 08
48 | 24026-FS01 |  | 1740 Division | 1740 Division St. Nashville, TN 37203 | Chris Buttrey | 615.517.9885 | 400 CAULK |  |  | use 10/502 dimensions have color matched screws if needed | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 Sets Install Drawings * ( 150 PCS) PE2N [3" CLIP'S] * ( 10 PCS) PET [3" CLIP'S] * (32 LF) PE1N * * ( 30 pcs) Corner Clips * (60 pcs) Fab Screws | Q:\Jobs\24026 - 1740 Division\04_Production\24026FS01 | 5.959% | 23 | 386 | 23 | 23 | 23 | 259 | 0 | 6 SHEETS | 00d02h30m41s | 4mm X 62" X 196", MTLC DCX CPPR FR ACM, Grain | FR ACM | 4mm X 62" X 196", MTLC DCX CPPR | Yes |  |  | 1 | 7 | Joshua Davis | Denis Usatenko | Gabriela Hoyle | Denis Usatenko | Nadira Vlatkovic | Nadira Vlatkovic | Hennadii Stakhurskyi | Nadira Vlatkovic |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Gabriela Herrera, Nadira Vlatkovic | 2026-01-16 10:53 |  | 2026-04-06 | 2026-04-08 | TRUE | 2026-04-24 |  | 2026-04-27 |  | 2026-03-13 |  |  | YES | 10 | [5 empty] | FAB SCREW | YES | Approved | YES | Q:\Jobs\24026 - 1740 Division\03_Engineering\02_FD Docs\FS01 Canopy | NO |  | NO | [6 empty] | AXYZ 34 | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24026 | FS |  | 01 |  | 1 | 24026-FS01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 24 | 30 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-04-08 | 2026-04-08 | 1 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Chris Buttrey - yes, sorry | 1010 |  | Chris Buttrey | Nadira Vlatkovic | Hennadii Stakhurskyi | 24026-FS01 In-House |  | 2026, Week 18
49 | 24051-FS82 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | RETURN WALL ON LEVEL 150 NORTH | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (30 LF) 1-5/8" Reveals * (20 LF) 1-1/8" Reveals * (6 LF) JR2 * (75 CNT) CS Skrews | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS82 | 74.88% | 14427 | 19268 | 4 | 4 | 4 | 26 | 50 | 68 X 62 - 2 (DROPS) | 00:21:17 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 95 | -15 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Denis Usatenko, Hennadii Stakhurskyi | 2026-02-02 13:24 |  | 2026-02-23 | 2026-03-11 | TRUE | 2026-03-27 |  | 2026-03-16 |  | 2026-03-16 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 82 |  | 82 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 8 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-03-10 | 2026-03-10 | 1 |  | QC Not Requested | 2026-03-16 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-17 |  | Issue Still in Process | Issiah Havens - @dusatenko@jwmcd.com @jdavis@jwmcd.com programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS82 In-House |  | 2026, Week 12
50 | 24051-FS83 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | LEVEL 150 RETURN WALL SOUTH ELEVATION | The red ones only | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (30 LF) 1-5/8" Reveals * (20 LF) 1-1/8" Reveals * (6 LF) JR2 * (75 CNT) CS Skrews | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS83 | 74.9% | 14431 | 19268 | 4 | 4 | 4 | 26 | 50 | 68 X 62 - 3 (DROPS) | 00:26:36 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 95 | -15 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Denis Usatenko | 2026-02-02 13:26 |  | 2026-02-23 | 2026-03-11 | TRUE | 2026-03-27 |  | 2026-03-16 |  | 2026-03-16 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 83 |  | 83 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 8 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-03-10 | 2026-03-10 | 1 |  | QC Not Requested | 2026-03-16 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-17 |  | Issue Still in Process | Issiah Havens - @dusatenko@jwmcd.com @jdavis@jwmcd.com programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS83 In-House |  | 2026, Week 12
51 | 24051-FS84 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | NORTH FIELD MEASURED PANELS MULTIPLE LEVELS |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (160 LF) 1-5/8" Reveals * (100 LF) 1-1/8" Reveals * (32 LF) JR2 * (300 CNT) CS Skrews | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS84 | 75.02% | 14455 | 19268 | 24 | 24 | 24 | 164 | 260 | 68 x 62 in 10 SHEETS 196 x 62 in 3 SHEETS | 00d02h37m08s | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 98 | -14 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Denis Usatenko | 2026-02-02 13:59 |  | 2026-02-23 | 2026-03-12 | TRUE | 2026-03-30 |  | 2026-03-16 |  | 2026-03-16 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 84 |  | 84 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 40 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-03-11 | 2026-03-11 | 1 |  | QC Not Requested | 2026-03-20 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-21 |  | Issue Still in Process | Arnold Jurado - @dusatenko@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS84 In-House |  | 2026, Week 12
52 | 24051-FS85 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | SOUTH FIELD MEASURES | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (25 LF) 1-5/8" Reveals * (8 LF) JR2 | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS85 | 75.04% | 14459 | 19268 | 4 | 4 | 4 | 38 | 25 | 68 x 62 in 1 SHEET 196 x 62 in 1 SHEET | 00d00h27m57s | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 98 | -14 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Denis Usatenko | 2026-02-02 14:51 |  | 2026-02-23 | 2026-03-12 | TRUE | 2026-03-30 |  | 2026-03-16 |  | 2026-03-16 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 85 |  | 85 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 8 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-03-11 | 2026-03-11 | 1 |  | QC Not Requested | 2026-03-20 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-23 |  | Issue Still in Process | Arnold Jurado - @dusatenko@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS85 In-House |  | 2026, Week 12
53 | 24051-RP11 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 |  |  |  | Peeled polly for inspection |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051RP11 | 48.19% | 9286 | 19268 | 1 | 1 | 0 | 0 | 0 | 196 X 62 - 1 | 00:12:32 | 4MM FR CORE MOONSTONE METALLIC 62X196 FR ACM, Grain | FR ACM | 4MM FR CORE MOONSTONE 62 X 196 | Yes |  |  | 34 | -183 | Unassigned | Denis Usatenko | [5 empty] | Paul J Roberts | TRUE | Issiah Havens |  |  |  |  | Gabriela Herrera | 2025-08-05 06:20 |  | 2025-08-05 | 2025-08-05 |  | 2025-08-05 |  | 2025-08-14 |  | 2025-08-14 |  |  | YES | [15 empty] | S4112-2BA02 | FS215 | HUMAN ERROR |  | jdavis@jwmcd.com | RTS Titans |  |  | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 |  | RP | 11 | -- | 11 | 24051-RP58 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | [15 empty] | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-08-05 |  | 183 (In Progress) |  | QC Not Requested | 2025-08-09 | 4 | David Hasty | Ramon Estrada, Shane Watson | 2025-08-14 |  | 0 | Issiah Havens - @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar |  |  | 24051-RP11 In-House |  | 2025, Week 33
54 | 24051-RP13 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 |  |  |  | Panels damaged in Alu Bender |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051RP13 | 48.63% | 9370 | 19268 | 84 | 84 | 10 | 588 | 0 | 196 X 62 - 84 | 17:29:09 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | [5 empty] | 34 | -183 | Unassigned | Denis Usatenko | [5 empty] | Paul J Roberts |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-08-05 06:47 |  | 2025-08-05 | 2025-08-05 |  | 2025-08-05 | [22 empty] | Whole release | FS36 | MACHINE |  | jdavis@jwmcd.com | RTS Titans |  |  | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 |  | RP | 13 | -- | 13 | 24051-RP58 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | [15 empty] | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-08-05 | 2025-08-05 | 1 |  | QC Not Requested | 2025-08-20 | 4 | David Hasty | Ramon Estrada, Shane Watson | 2025-08-25 |  | 0 | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED, SEE NOTES ON MATERIAL SUMMARY REPORT | 1010 |  | Marc Ribar |  |  | 24051-RP13 In-House |  | #INVALID DATA TYPE
55 | 24051-RP14 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 |  |  |  | Panels damaged in Alu Bender |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051RP14 | 48.75% | 9394 | 19268 | 24 | 24 | 2 | 144 | 0 | 196 X 62 - 8 | 03:20:33 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | [5 empty] | 34 | -183 | Unassigned | Denis Usatenko | [5 empty] | Paul J Roberts |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-08-05 06:49 |  | 2025-08-05 | 2025-08-05 |  | 2025-08-05 | [22 empty] | Whole release | FS37 | MACHINE |  | jdavis@jwmcd.com | RTS Titans |  |  | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 |  | RP | 14 | -- | 14 | 24051-RP58 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | [15 empty] | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-08-05 | 2025-08-05 | 1 |  | QC Not Requested | 2025-08-22 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-08-25 |  | 0 | Issiah Havens - @jdavis@jwmcd.com @hstakhurskyi@jwmcd.com PROGRAMMED, SEE NOTES ON MATERIAL SUMMARY REPORT | 1010 |  | Marc Ribar |  |  | 24051-RP14 In-House |  | #INVALID DATA TYPE
56 | 24051-RP15 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 |  |  |  | Panels damaged in Alu Bender |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051RP15 | 49.25% | 9490 | 19268 | 96 | 96 | 2 | 576 | 0 | 196 X 62 - 24 | 12:17:45 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | [5 empty] | 34 | -183 | Unassigned | Denis Usatenko | [5 empty] | Paul J Roberts |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-08-05 06:51 |  | 2025-08-05 | 2025-08-05 |  | 2025-08-05 | [22 empty] | Whole release | FS39 | MACHINE |  | jdavis@jwmcd.com | RTS Titans |  |  | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 |  | RP | 15 | -- | 15 | 24051-RP58 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | [15 empty] | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-08-05 | 2025-08-05 | 1 |  | QC Not Requested | 2025-08-22 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-08-22 |  | 0 | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED, SEE NOTES ON MATERIAL SUMMARY REPORT | 1010 |  | Marc Ribar |  |  | 24051-RP15 In-House |  | #INVALID DATA TYPE
57 | 24051-RP16 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 |  |  |  | dents and missing panels |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051RP16 | 49.28% | 9495 | 19268 | 5 | 5 | 4 | 0 | 0 | 196 X 62 - 5 | 00:58:21 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | [5 empty] | 39 | -178 | Unassigned | Denis Usatenko | [5 empty] | Paul J Roberts |  | Arnold Jurado, Issiah Havens |  |  |  |  | Gabriela Herrera | 2025-08-12 07:11 |  | 2025-08-12 | 2025-08-12 |  | 2025-08-12 |  | 2025-08-25 |  | 2025-08-25 | [18 empty] | E5401-1CA01 E5401-1CA06 E5401-1CA07 X2 E5401-1CA08 | FS42 | MATERIAL DEFECT |  | jdavis@jwmcd.com | RTS Titans |  |  | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 |  | RP | 16 | -- | 16 | 24051-RP58 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | [15 empty] | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-08-12 |  | 178 (In Progress) |  | QC Not Requested | 2025-08-21 | 3 | David Hasty | Ramon Estrada, Shane Watson | 2025-08-25 |  | 0 | Issiah Havens - @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar |  |  | 24051-RP16 In-House |  | 2025, Week 35
58 | 25035-FS02.1 |  | Titans Jabez | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | Reveals for FS02 and 03. |  | * SKETCH * CUT LIST |  | Q:\Jobs\25035 - Titans Jabez\04_Production\25035FS02.1 | N/A | N/A | N/A | 0 | 27 | 2 | 52 | 0 | 1 SHEET | 00d00h18m41s | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 80 | -38 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2026-01-16 08:35 | TRUE | 2026-02-06 | 2026-01-21 |  | 2026-02-24 |  | 2026-02-26 |  | 2026-02-26 |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans |  | TRUE | TRUE | [8 empty] | TRUE | [12 empty] | TRUE |  |  |  | 25035 | FS |  | 02.1 |  | 2.1 | 25035-FS04 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 24 | 600 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Shear | 2026-01-19 | 2026-01-20 | 2 |  | QC Not Requested | 2026-01-23 | 25 | David Hasty | Ramon Estrada, Shane Watson | 2026-02-26 |  | Issue Still in Process | Arnold Jurado - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 25035-FS02.1 In-House | TRUE | 2026, Week 09
59 | 25035-FS03 |  | Titans Jabez | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | CUSTOM ARCH |  | MATERRIAL TO BE SHIPPED TO SPECTRUM TO BE PAINTED TOB BLACK. A112 CLIPS & ACM ANGLES ARE TO BE SHIPPED LOOSE WITH THE PANELS TO THE SITE RERFERENCE PO 26436 | THE EXTRUSIONS CAN BE INSTALLED ON THE PANELS AS LONG AS THERE IS NO SILICONE OR ADHEASIVES ON ANY KIND. OTHERWISE, THESE PARTS WILL NEED TO BE APPLIED AFTER THE PANELS ARE PAINTED. | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (753LF) JR2 * REVEALS FROM FS02.1 | Q:\Jobs\25035 - Titans Jabez\04_Production\25035FS03 | Unavailable | 613 |  | 160 | 320 | 8 | 640 | 0 | 39 | 26:11:48 | .125" X 60" X 144", 3003- Mill Alum Sheet, No Grain | Alum Sheet | .125" X 60" X 144", 3003- Mill | No |  |  | 11 | -32 | Ramon Estrada, Shane Watson | David Hasty | David Hasty | Frank Dean | David Hasty | Jonathan Dorsey | David Hasty | Jonathan Dorsey |  |  |  | Chris Gambrel | TRUE |  |  | 2026-01-05 11:13 |  | 2026-02-13 | 2026-01-19 |  | 2026-03-04 | 2026-02-27 | 2026-03-06 |  | 2026-03-06 |  | 2026-03-03 | YES | 80 | 2026-01-05 | TRUE | Powder Coat | SPECTRUM 535 Bev Rd. Youngstown, OH 44512 ATTN JARRED RUGGIERI 412-789-4459 | Coating Ship Back To JWM | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Shipped To Painter | TRUE | TRUE | [6 empty] | TRUE | 7000 TruMatic | [7 empty] | TRUE | [6 empty] | TRUE | TRUE |  |  | 25035 | FS |  | 03 |  | 3 | 25035-FS04 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 32 | 240 | [10 empty] | In House |  |  | Punch | 7000 TruMatic Brake Clean and Brake Fab Powder Coat | 2026-01-16 | 2026-01-19 | 2 |  | QC Not Requested | 2026-02-22 | 4 | David Hasty | Ramon Estrada, Shane Watson | 2026-02-26 |  | Issue Still in Process | Marc Ribar - @gholland@jwmcd.com @jdavis@jwmcd.com @cball@jwmcd.com @tgraves@jwmcd.com THIS RELEASE NEEDS TO GO WITH FS02 TO SPECTRUM FOR COATING WHICH IS READY TO SHIP. BOTH WERE RELEAED AT THE SAME TIME & WE NEED TO GET THIS OUT OF THE SHOP. PLEASE PROVIDE A SHIP DATE. | 1010 |  | Marc Ribar | Jonathan Dorsey | David Hasty | 25035-FS03 In-House | TRUE | 2026, Week 010
60 | 25035-FS04 |  | Titans Jabez | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | Do all panels not just FD. | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  |  | 218 | [6 empty] | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No | TRUE | Fortitude | 1 | -34 | Hennadii Stakhurskyi/Fortitude | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  |  |  | Hennadii Stakhurskyi | 2026-02-04 11:56 |  | 2026-03-02 |  |  |  |  | 2026-03-23 |  | 2026-03-23 |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Sketch | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 25035 | FS |  | 04 |  | 4 | 25035-FS04 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 24 | 230 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 25035-FS04 In-House |  | 2026, Week 13
61 | 24082-FL03 |  | GTN Cable | 1 Meta Loop Gallatin, TN 37066 | Josh McPherson, Nick Akins | [7 empty] | \\192.168.2.10\ashop_data\Jobs\24082 - GTN Cable\04_Production\24082FL03 | N/A | N/A | N/A | 0 | 32 | 2 | 0 | 0 | 12.25 | na | 22GA. X 48" X 120" Regal Gray Steel Sheet, No Grain | Steel Sheet | 22GA. X 48" X 120" Regal Gray | No |  |  | 3 | -217 | Ramon Estrada, Shane Watson | Denis Usatenko | [5 empty] | Denis Usatenko | [6 empty] | Denis Usatenko | 2025-06-12 10:56 | TRUE | 2025-06-20 | 2025-06-12 | TRUE | 2025-06-18 |  | 2025-06-17 |  | 2025-06-17 |  |  | YES | 25 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 24082 | FL |  | 03 |  | 3 | 24082-FL03 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 4 | [10 empty] | In House |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2025-07-14 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-07-15 |  | Issue Still in Process |  | 1010 |  | Josh McPherson, Nick Akins |  |  | 24082-FL03 In-House |  | 2025, Week 25
62 | 25014-11-ST01 |  | R&D | Nashville, TN 37218 | TBC |  | --- |  | Completed order to be taken to shipping area when finished. This order will be picked up with 25014-11-ST02. Notify Paul Roberts in engineering when complete. | Use smallest drop available to program for 1/8" steel plate. Material thickness may vary slightly if 1/8" is not available. Update material information if thickness changes. | Sketches Programming Files |  | Q:\Jobs\25014-11 - Pressure Washer Base\Production\25014-11-ST01 | N/A | N/A | N/A | 0 | 1 | 1 | 0 | 0 | 1 | 00:00:18 | 1/8" thick, minimum drop Steel Sheet, No Grain | Steel Sheet | 1/8" thick, minimum drop | No |  |  | 19 | -91 | Ramon Estrada, Shane Watson | David Hasty |  |  |  | Frank Dean | David Hasty | Frank Dean |  |  | Chris Gambrel |  | TRUE |  | Frank Dean | 2025-11-21 06:54 | TRUE | 2025-12-12 | 2025-11-25 | TRUE | 2025-12-11 |  | 2025-12-06 |  | 2025-12-06 |  |  | YES | [8 empty] | None Available | NO |  | NO |  | NO | [6 empty] | Ready to Ship |  | TRUE |  |  |  | TRUE |  | TruLaser 3040 | [20 empty] | 25014-11 | ST |  | 01 |  | 1 | 25014-11-ST02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 2 | 2 | [10 empty] | Customer Pick Up |  |  | Flat Laser | TruLaser 3040 | 2025-11-25 | 2025-11-25 | 1 | 2025-12-05 | 1 | 2025-12-05 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-12-06 |  | Issue Still in Process | Chris Gambrel - @fdean@jwmcd.com @dhasty@jwmcd.com flat program completed. | 1010 |  | TBC | Frank Dean | David Hasty | 25014-11-ST01 In-House | TRUE | 2025, Week 49
63 | 25014-11-ST02 |  | R&D | Nashville, TN 37218 | TBC |  | --- |  | Cut materials into 5' sections. Keep drops with cut materials. Completed order to be taken to shipping area when finished. This order will be picked up with 25014-11-ST01. Notify Paul Roberts in engineering when complete. | Materials are in the boneyard, directly across from the shipping department. Measure material thicknesses and update material information to include thickness. Raw material quantities are unknown. Update part quantity to reflect projected total number of parts that will be shipped. Include potential drops in the part quantity. | Sketches Programming Files |  | Q:\Jobs\25014-11 - Pressure Washer Base\Production\25014-11-ST02 | N/A | N/A | N/A | 0 | 232 | 3 | 0 | 0 | Tube - 21 sticks @ 25'6" 1 x 1 Angle - 24 sticks @ 20' 1 1/2 x 1 1/2 Angle - 20 sticks @ 20' | 00:39:00 | 1" X 1" X 1/8" Steel Angle, 1 1/2" X 1 1/2" X 1/4" Steel Angle, 3" X 1.5" X 13ga. wall Steel Tube Alum Tube, No Grain | Alum Tube | 1" X 1" X 1/8" Steel Angle, 1 1/2" X 1 1/2" X 1/4" Steel Angle, 3" X 1.5" X 13ga. wall Steel Tube | No |  |  | 19 | -91 | Ramon Estrada, Shane Watson | David Hasty |  |  |  | Frank Dean | David Hasty | Frank Dean |  |  | Arnold Jurado |  | TRUE |  | Frank Dean | 2025-11-21 07:01 | TRUE | 2025-12-12 | 2025-11-25 | TRUE | 2025-12-11 |  | 2025-12-06 |  | 2025-12-06 |  |  | YES | [8 empty] | None Available | NO |  | NO |  | NO | [6 empty] | Ready to Ship |  | TRUE |  |  |  |  | TRUE | [21 empty] | 25014-11 | ST |  | 02 |  | 2 | 25014-11-ST02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 2 | 2 | [10 empty] | Customer Pick Up |  |  | Tube Laser | Tube Laser | 2025-11-25 | 2025-11-25 | 1 | 2025-12-05 | 1 | 2025-12-05 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-12-06 |  | Issue Still in Process | Issiah Havens - @fdean@jwmcd.com program complete | 1010 |  | TBC | Frank Dean | David Hasty | 25014-11-ST02 In-House | TRUE | 2025, Week 49
64 | 25016-BM201 |  | Rockdale CJAC | 981 Milstead Avenue NE Conyers, GA 30012 | Dillon Bowman | 518.860.9477 | CUSTOM ARCH |  | Mock-Up (Girts) (12) 2" Z-Girts | Mock-Up (Girts) (12) 2" Z-Girts |  |  | \\jw-vm-ashop\ASHOP_DATA\Jobs\25016 - Rockdale CJAC\04_Production\25016BM201 | 97.55% | 319 | 327 | 12 | 12 | 1 | 0 | 0 | 1 | na | 16g Galv 48 x 120 Galv Sheet, No Grain | Galv Sheet | 16g Galv 48 x 120 | No |  |  | 14 | -161 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2025-08-21 08:57 | TRUE | 2025-08-29 | 2025-08-22 |  | 2025-09-04 |  | 2025-09-08 |  | 2025-09-08 |  |  | YES | [6 empty] | N/A | NO | N/A (Process Customer Provided Blanks) | NO |  | NO |  | NO | [6 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25016 | BM |  | 201 |  | 201 | 25016-BM201 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 0.25 | 2 | [10 empty] | Hot Shot |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2025-08-27 | 9 | David Hasty | Ramon Estrada, Shane Watson | 2025-09-08 |  | Issue Still in Process |  | 1010 |  | Dillon Bowman | Denis Usatenko |  | 25016-BM201 In-House |  | 2025, Week 37
65 | 25016-FL200 |  | Rockdale CJAC | 981 Milstead Avenue NE Conyers, GA 30012 | Dillon Bowman | 518.860.9477 | CUSTOM ARCH |  | Mock-Up (FL's) | Mock-Up (FL's) - Please check the FD Folder for Dimension Adjustments |  |  | Q:\Jobs\25016 - Rockdale CJAC\04_Production\25016FL200 | 100% | 327 | 327 | 8 | 8 | 3 | 0 | 0 |  | na | 48 x 120 - .040 - 48 x 120 - Dark Bronze Alum Sheet, No Grain | Alum Sheet | 48 x 120 - .040 - 48 x 120 - Dark Bronze | No |  |  | 14 | -161 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Chance Dill | Denis Usatenko | Chance Dill | [6 empty] | Chance Dill | 2025-08-21 08:56 | TRUE | 2025-08-29 | 2025-08-25 |  | 2025-09-04 |  | 2025-09-08 |  | 2025-09-08 |  |  | YES | [6 empty] | N/A | N/A | N/A (Process Customer Provided Blanks) | NO |  | NO |  | NO | [6 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25016 | FL |  | 200 |  | 200 | 25016-FL200 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 4 | [10 empty] | Hot Shot |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2025-08-27 | 9 | David Hasty | Ramon Estrada, Shane Watson | 2025-09-08 |  | Issue Still in Process | Denis Usatenko - They are there | 1010 |  | Dillon Bowman | Chance Dill | Denis Usatenko | 25016-FL200 In-House |  | 2025, Week 37
66 | 25016-MU101 |  | Rockdale CJAC | 981 Milstead Avenue NE Conyers, GA 30012 | Dillon Bowman | 518.860.9477 | 400 |  | Courthouse ACM - Use Pewter Screws on Dillon's Shelf in the Tool Crib |  |  |  | Q:\Jobs\25016 - Rockdale CJAC\04_Production\25016MU101 | 93.58% | 306 | 327 | 4 | 5 | 5 | 48 | 0 | 2 | 00:33:24 | 62 x 196 FR ACM - Nissan Gray (3A) - 24033 FR ACM, Grain | FR ACM | 62 x 196 FR ACM - Nissan Gray (3A) - 24033 | Yes |  |  | 4 | -210 | Ramon Estrada, Shane Watson | Denis Usatenko |  | Gabriela Herrera | Denis Usatenko | Gabriela Herrera | Denis Usatenko | Gabriela Herrera |  | Issiah Havens |  |  | TRUE |  | Gabriela Herrera | 2025-05-30 12:26 | TRUE | 2025-06-20 | 2025-06-04 |  | 2025-06-27 |  | 2025-07-01 |  | 2025-07-01 |  |  | YES | [6 empty] | N/A | YES | N/A (Process Customer Provided Blanks) | NO |  | YES | Q:\Jobs\25016 - Rockdale CJAC\03_Engineering\02_FD Docs\25016 - MU 101 - Courthouse ACM | NO | [6 empty] | Ready to Ship | TRUE | TRUE | TRUE | AXYZ 34 | [20 empty] | TRUE | TRUE |  |  | 25016 | MU |  | 101 |  | 101 | 25016-MU123 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 2 | 8 | [10 empty] | Hot Shot |  |  | AXYZ | AXYZ 34 Clean and Brake Fab | 2025-06-04 | 2025-06-04 | 1 |  | QC Not Requested | 2025-06-11 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-11 |  | Issue Still in Process | Issiah Havens - @gherrera@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed, panel tracker | 1010 |  | Dillon Bowman | Gabriela Herrera | Denis Usatenko | 25016-MU101 In-House |  | 2025, Week 27
67 | 25016-MU103 |  | Rockdale CJAC | 981 Milstead Avenue NE Conyers, GA 30012 | Dillon Bowman | 518.860.9477 | CUSTOM ARCH |  | Courthouse Flashing |  |  |  |  | N/A | N/A | N/A | 0 | 8 | 4 | 0 | 0 | N/A | N/A | 48 x 120 - .040 - Fabral - Black/Gray Alum Sheet, No Grain | Alum Sheet | 48 x 120 - .040 - Fabral - Black/Gray | No |  |  | 4 | -210 | Ramon Estrada, Shane Watson | David Hasty | Denis Usatenko |  |  | Gabriela Herrera | Denis Usatenko | Gabriela Herrera | [6 empty] | Gabriela Herrera | 2025-05-30 12:33 | TRUE | 2025-06-20 | 2025-06-03 |  | 2025-06-27 |  | 2025-07-01 |  | 2025-07-01 |  |  | YES | [6 empty] | N/A | NO | N/A (Process Customer Provided Blanks) | NO |  | YES | Q:\Jobs\25016 - Rockdale CJAC\03_Engineering\02_FD Docs\25016 - MU 103 - Courthouse Flashing and Coping | NO | [6 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25016 | MU |  | 103 |  | 103 | 25016-MU123 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 2 | [10 empty] | Hot Shot |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2025-06-18 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-19 |  | Issue Still in Process | Paul J Roberts - @dusatenko@jwmcd.com Standard flashing. | 1010 |  | Dillon Bowman | Gabriela Herrera | Denis Usatenko | 25016-MU103 In-House |  | 2025, Week 27
68 | 25016-MU121 |  | Rockdale CJAC | 981 Milstead Avenue NE Conyers, GA 30012 | Dillon Bowman | 518.860.9477 | 400 |  | Admin Mock-UP ACM | Use Pewter Screws on Dillon's Shelf in the Tool Crib |  |  | Q:\Jobs\25016 - Rockdale CJAC\04_Production\25016MU121 | 93.88% | 307 | 327 | 1 | 1 | 1 | 5 | 0 | 1 | 00:09:20 | 62 x 196 FR ACM - Nissan Gray (3A) - 24033 FR ACM, Grain | FR ACM | 62 x 196 FR ACM - Nissan Gray (3A) - 24033 | Yes |  |  | 4 | -210 | Ramon Estrada, Shane Watson | Denis Usatenko |  | Gabriela Herrera |  | Gabriela Herrera | Denis Usatenko | Gabriela Herrera |  | Issiah Havens |  |  | TRUE |  | Gabriela Herrera | 2025-05-30 12:37 | TRUE | 2025-06-20 | 2025-06-04 |  | 2025-06-27 |  | 2025-07-01 |  | 2025-07-01 |  |  | YES | [6 empty] | PEWTER | YES | N/A (Process Customer Provided Blanks) | NO |  | YES | Q:\Jobs\25016 - Rockdale CJAC\03_Engineering\02_FD Docs\25016 - MU 121 | NO | [6 empty] | Ready to Ship | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 25016 | MU |  | 121 |  | 121 | 25016-MU123 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 2 | [10 empty] | Hot Shot |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-06-04 | 2025-06-04 | 1 |  | QC Not Requested | 2025-06-11 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-11 |  | Issue Still in Process | Issiah Havens - @gherrera@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed, panel tracker | 1010 |  | Dillon Bowman | Gabriela Herrera | Denis Usatenko | 25016-MU121 In-House |  | 2025, Week 27
69 | 25016-MU122 |  | Rockdale CJAC | 981 Milstead Avenue NE Conyers, GA 30012 | Dillon Bowman | 518.860.9477 | CUSTOM ARCH |  | Admin Building - Mock-Up - Girts |  |  |  |  | N/A | N/A | N/A | 0 | 2 | 1 | 0 | 0 | N/A | N/A | 16g Galv 48 x 120 Galv Sheet, No Grain | Galv Sheet | 16g Galv 48 x 120 | No |  |  | 4 | -210 | Ramon Estrada, Shane Watson | David Hasty | Denis Usatenko |  |  | Gabriela Herrera | Denis Usatenko | Gabriela Herrera | [6 empty] | Gabriela Herrera | 2025-05-30 12:40 | TRUE | 2025-06-20 | 2025-06-03 |  | 2025-06-27 |  | 2025-07-01 |  | 2025-07-01 |  |  | YES | [6 empty] | N/A | N/A | N/A (Process Customer Provided Blanks) | NO |  | YES | Q:\Jobs\25016 - Rockdale CJAC\03_Engineering\02_FD Docs\25016 - MU 122 - Admin Bldg Mock-Up - Girts | NO | [6 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25016 | MU |  | 122 |  | 122 | 25016-MU123 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 1 | [10 empty] | Hot Shot |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2025-06-18 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-19 |  | Issue Still in Process | Paul J Roberts - @dusatenko@jwmcd.com 16 Ga. zees. | 1010 |  | Dillon Bowman | Gabriela Herrera | Denis Usatenko | 25016-MU122 In-House |  | 2025, Week 27
70 | 25016-MU123 |  | Rockdale CJAC | 981 Milstead Avenue NE Conyers, GA 30012 | Dillon Bowman | 518.860.9477 | CUSTOM ARCH |  | Admin Bldg Mock-up Flashing |  |  |  |  | N/A | N/A | N/A | 0 | 2 | 2 | 0 | 0 | N/A | N/A | 48 x 120 - .040 - Fabral - Black/Gray (22007) Alum Sheet, No Grain | Alum Sheet | 48 x 120 - .040 - Fabral - Black/Gray (22007) | No |  |  | 4 | -210 | Ramon Estrada, Shane Watson | David Hasty | Denis Usatenko |  |  | Gabriela Herrera | Denis Usatenko | Gabriela Herrera | [6 empty] | Gabriela Herrera | 2025-05-30 12:42 | TRUE | 2025-06-20 | 2025-06-03 |  | 2025-06-27 |  | 2025-07-01 |  | 2025-07-01 |  |  | YES | [6 empty] | N/A | N/A | N/A (Process Customer Provided Blanks) | NO |  | YES | Q:\Jobs\25016 - Rockdale CJAC\03_Engineering\02_FD Docs\25016 - MU 123 - Admin Bldg Mock-Up - Flashing | NO | [6 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25016 | MU |  | 123 |  | 123 | 25016-MU123 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 1 | [10 empty] | Hot Shot |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2025-06-18 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-19 |  | Issue Still in Process | Allen Duke - For me? Thanks, ALLEN DUKE Processing Estimating Manager John W. McDougall Inc. 615.321.3900 ¦ jwmcd.com | 1010 |  | Dillon Bowman | Gabriela Herrera | Denis Usatenko | 25016-MU123 In-House |  | 2025, Week 27
71 | 25017-FL99 |  | Nashville Yards Park | Nashville, TN 37203 | Dillon Bowman | 518.860.9477 |  |  | Corner Trim Fix | Corner Trim Fix | * Sketch |  | Q:\Jobs\25017 - Nashville Yards Park\04_Production\25017FL99 | N/A | N/A | N/A | 0 | 2 | 1 | 0 | 0 | 0.5 - SHT | na | .032 x 48 x 120 - Hemlock Green - 25017 Alum Sheet, Grain | Alum Sheet | .032 x 48 x 120 - Hemlock Green - 25017 | Yes |  |  | 25 | -69 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2025-12-23 10:24 |  | 2026-01-05 | 2025-12-23 |  | 2026-01-12 |  | 2026-01-14 |  | 2026-01-14 |  |  | YES | 7 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25017 | FL |  | 99 |  | 99 | 25017-FL99 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 0.25 | 2 | [10 empty] | Hot Shot |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2025-12-29 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-12-29 |  | Issue Still in Process | Mitch Chancey - @dbowman@jwmcd.com @swatson@jwmcd.com @tgraves@jwmcd.com LOOSE ON THE TREE | 1010 |  | Dillon Bowman | Denis Usatenko |  | 25017-FL99 In-House |  | 2026, Week 03
72 | 24051-FS37 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | EAST LEVEL 050 BAND |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS37 | 44.15% | 8507 | 19268 | 24 | 24 | 2 | 159 | 270 | 196 X 62 - 8 | 03:23:31 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 26 | -195 | Unassigned | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-06-09 14:53 | TRUE | 2025-06-30 | 2025-07-02 | TRUE | 2025-07-18 |  | 2025-07-14 |  | 2025-07-14 |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | YES | Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\01_Calcs\2025-5-27_LOCSHA STADIUM CALC PACKAGE | [5 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 37 |  | 37 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 48 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-07-01 | 2025-07-02 | 2 |  | QC Not Requested | 2025-07-09 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-07-09 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed w/ PT | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS37 In-House |  | 2025, Week 29
73 | 24051-FS38 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | EAST LEVEL 050 |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS38 | 44.62% | 8597 | 19268 | 90 | 90 | 6 | 576 | 650 | 196 X 62 - 21 | 11:20:52 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 26 | -195 | Unassigned | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-06-09 14:56 | TRUE | 2025-06-30 | 2025-07-02 | TRUE | 2025-07-18 |  | 2025-07-14 |  | 2025-07-14 |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | YES | Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\01_Calcs\2025-5-27_LOCSHA STADIUM CALC PACKAGE | [5 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 38 |  | 38 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 125 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-07-02 | 2025-07-02 | 1 |  | QC Not Requested | 2025-07-15 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-07-15 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed w/ PT | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS38 In-House |  | 2025, Week 29
74 | 24051-FS39 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | EAST LEVEL 050 |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS39 | 45.12% | 8693 | 19268 | 96 | 96 | 2 | 576 | 1150 | 196 X 62 - 24 | 12:26:52 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 26 | -195 | Unassigned | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-06-09 15:09 | TRUE | 2025-06-30 | 2025-07-02 | TRUE | 2025-07-18 |  | 2025-07-14 |  | 2025-07-14 |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | YES | Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\01_Calcs\2025-5-27_LOCSHA STADIUM CALC PACKAGE | [5 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 39 |  | 39 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 125 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-07-01 | 2025-07-02 | 2 |  | QC Not Requested | 2025-07-09 | 3 | David Hasty | Ramon Estrada, Shane Watson | 2025-07-11 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed w/ PT | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS39 In-House |  | 2025, Week 29
75 | 24051-FS40 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | EAST LEVEL 050 |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS40 | 45.61% | 8789 | 19268 | 96 | 96 | 2 | 442 | 1000 | 196 X 62 - 7 | 07:05:50 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 26 | -195 | Unassigned | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-06-09 15:14 | TRUE | 2025-06-30 | 2025-07-02 | TRUE | 2025-07-18 |  | 2025-07-15 |  | 2025-07-15 |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | YES | Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\01_Calcs\2025-5-27_LOCSHA STADIUM CALC PACKAGE | [5 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 40 |  | 40 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 125 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-07-01 | 2025-07-02 | 2 |  | QC Not Requested | 2025-07-15 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-07-15 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed w/ PT | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS40 In-House |  | 2025, Week 29
76 | 24051-FS41 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | EAST LEVEL 050 |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS41 | 46.11% | 8885 | 19268 | 96 | 96 | 2 | 768 | 1050 | 196 X 62 - 48 | 17:56:09 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 26 | -195 | Unassigned | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-06-09 15:16 |  | 2025-07-01 | 2025-07-02 | TRUE | 2025-07-18 |  | 2025-07-22 |  | 2025-07-22 |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | YES | Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\01_Calcs\2025-5-27_LOCSHA STADIUM CALC PACKAGE | [5 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 41 |  | 41 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 125 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-07-01 | 2025-07-02 | 2 |  | QC Not Requested | 2025-07-19 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-07-22 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed w/ PT | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS41 In-House |  | 2025, Week 30
77 | 24051-FS42 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | EAST LEVEL 050 PLEASE NOTE PANELS INSTALL FROM THE RIGHT TO THE LEFT. ALSO THE DIMENSION CHANGE IN THE 1ST BAY. THE REVISED DRAWING REMOVES THE 1ST ROW OF PANELS TO BE FIELD DIMENSIONED. |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS42 | 46.74% | 9005 | 19268 | 120 | 120 | 8 | 725 | 1700 | 196 X 62 - 115 | 23:47:40 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 38 | -179 | Unassigned | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-06-09 15:46 |  | 2025-07-23 | 2025-07-07 |  | 2025-08-11 |  | 2025-08-13 |  | 2025-08-13 |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | YES | Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\01_Calcs\2025-5-27_LOCSHA STADIUM CALC PACKAGE | [5 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 42 |  | 42 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 200 | [13 empty] | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-07-02 | 2025-07-02 | 1 |  | QC Not Requested | 2025-08-12 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-08-13 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed w/ PT | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS42 In-House |  | 2025, Week 33
78 | 24079-FS03 |  | Nashville Youth Campus | 1354 Brick Church Pike Nashville, TN 37207 | Joe Hoyle | 828.334.7808 | --- |  | FIBER CEMENT - LAYOUT CARD #003 NO JWM FABRICATION | AREA B - West rescan to capture the elevation to the left of the radiused wall. Reference elevations 5/NY-06 and 1/NY-35 of the fiber shop drawings. Please provide the fiber panel layout per the AAN AFC drawings. Coordinate with the FS02 and FS101 layouts. | [6 empty] | 33 | [6 empty] | TBD LAYOUT ONLY, Grain | LAYOUT ONLY | TBD | Yes |  |  | 1 | -39 | Denis Usatenko | David Hasty | Denis Usatenko | [12 empty] | 2026-01-19 15:58 |  | 2026-02-23 |  |  |  |  | 2026-03-16 |  | 2026-03-16 |  |  | YES | 999 | [5 empty] | N/A | N/A | Approved As Noted | YES | Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - NYCE - FS103 AREA D\NYCE 103 & 105 SCANS\Wall=Rescan | NO |  | NO | [6 empty] | Evaluation | [28 empty] | 24079 | FS |  | 03 |  | 3 | 24079-FS303 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 20 | 0 | [10 empty] | Customer Pick Up | [6 empty] | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Joe Hoyle |  |  | 24079-FS03 In-House |  | 2026, Week 12
79 | 24079-FS101 |  | Nashville Youth Campus | 1354 Brick Church Pike Nashville, TN 37207 | Joe Hoyle | 828.334.7808 | 400 |  | AREA B - ACM Release | AREA B - ACM Release Parapet dimensions are in the photos folder. Job is not 100%, there are missing frames, columns and sheathing. We'll be coordinating with the field to resolve missing information. | * 2 SETS - INSTALL DRAWINGS * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * (1500 LF) 16ga, flat-strap for install * (1400 LF) 1-5/8" Reveals * (100 LF) 1-5/8" Reveals﻿ * (1100 LF) JR2 * (270 LF) 0.05" thick by 1.25" wide min. STRAP for Panel Fab | Q:\Jobs\24079 - Nashville Youth Campus\04_Production\24079FS101 | Unavailable | 201 |  | 173 | 176 | 149 | 1370 | 1450 | 96 SHEETS | 01d07h19m43s | 4mm X 62" X 196" 'CWM - Cloud White MATTE' FR ACM, Grain | FR ACM | 4mm X 62" X 196" 'CWM - Cloud White MATTE' | Yes |  | MTPK | 40 | -5 | Ramon Estrada, Shane Watson | Denis Usatenko | Denis Usatenko | Denis Usatenko | Denis Usatenko | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Denis Usatenko, Hennadii Stakhurskyi | 2025-12-16 07:38 |  | 2026-02-02 | 2026-03-25 | TRUE | 2026-04-10 |  | 2026-02-23 |  | 2026-02-23 |  |  | YES | 275 | [5 empty] | MATCH COLOR | NO | Approved As Noted | YES | Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - NYCE - FS01 AREA B | YES | Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - NYCE - FS01 AREA B\Photos | YES | TBD | [5 empty] | Ready to Ship | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24079 | FS |  | 101 |  | 101 | 24079-FS303 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 120 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-03-23 | 2026-03-25 | 3 |  | QC Not Requested | 2026-04-02 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2026-04-02 |  | Issue Still in Process | Arnold Jurado - @dusatenko@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Joe Hoyle | Hennadii Stakhurskyi | Denis Usatenko | 24079-FS101 In-House |  | 2026, Week 09
80 | 24079-FS102 |  | Nashville Youth Campus | 1354 Brick Church Pike Nashville, TN 37207 | Joe Hoyle | 828.334.7808 | 400 |  | AREA D | AREA D - ACM Release #001. Connect layout with FS101. Coordinate FS102 with FS02. Check panel alignment across both approved ACM and fiber shop drawings. Parapet dimensions are in the photos folder. Job is not 100%, there are missing frames, columns and sheathing. We'll be coordinating with the field to resolve missing information. Drawing indicating the extent of scope is found in the FD Docs folder. Calcs are not complete. | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * (1500 lft) 16ga, flat-strap for the FIELD * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  |  | 192 | 198 | 162 |  |  |  |  | 4mm X 62" X 196" 'Cloud White Matte' FR ACM, Grain | FR ACM | 4mm X 62" X 196" 'Cloud White Matte' | Yes |  | MTPK | 1 | -39 | Denis Usatenko | Denis Usatenko | Denis Usatenko | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  |  |  | Hennadii Stakhurskyi | 2026-01-19 15:36 |  | 2026-02-23 |  |  |  |  | 2026-03-16 |  | 2026-03-16 |  |  | YES | 370 | [5 empty] | MATCH COLOR | YES | Approved As Noted | YES | Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - NYCE - FS103 AREA D | NO |  | NO | [6 empty] | Sketch Check | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24079 | FS |  | 102 |  | 102 | 24079-FS303 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 80 | 462 | [10 empty] | Customer Pick Up In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Joe Hoyle | Hennadii Stakhurskyi | Denis Usatenko | 24079-FS102 In-House |  | 2026, Week 12
81 | 24051-FS04 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | WEST LEVEL 400 UPPER BAND |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS04 | 28% | 5396 | 19268 | 153 | 153 | 2 | 918 | 1780 | 196 X 62 - 39 | 19:54:09 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 1 | -260 | Ramon Estrada, Shane Watson | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-03-06 15:22 |  | 2025-04-01 | 2025-03-19 |  | 2025-04-18 |  | 2025-04-22 |  | 2025-04-22 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Partially Shipped | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 04 |  | 4 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-03-18 | 2025-03-19 | 2 |  | QC Not Requested | 2025-04-21 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-04-22 |  | Issue Still in Process | Samantha Krantz - Reveals done 4-7-25 | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS04 In-House |  | 2025, Week 17
82 | 24051-FS05 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | WEST LEVEL 4 MIDDLE ROW |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS05 | 28.8% | 5549 | 19268 | 153 | 153 | 2 | 707 | 1050 | 196 X 62 - 11 | 11:21:07 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 1 | -260 | Ramon Estrada, Shane Watson | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-03-06 15:34 |  | 2025-04-01 | 2025-03-19 |  | 2025-04-18 |  | 2025-04-22 |  | 2025-04-22 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Partially Shipped | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 05 |  | 5 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-03-18 | 2025-03-19 | 2 |  | QC Not Requested | 2025-04-21 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-04-22 |  | Issue Still in Process | Samantha Krantz - Reveals done 4-7-25 | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS05 In-House |  | 2025, Week 17
83 | 24051-FS06 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | LEVEL 4 BOTTOM ROW OF PANELS |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS06 | 29.59% | 5702 | 19268 | 153 | 153 | 4 | 1071 | 2160 | 196 X 62 - 42 | 20:53:28 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 3 | -259 | Ramon Estrada, Shane Watson | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-03-06 15:37 |  | 2025-04-02 | 2025-03-20 |  | 2025-04-21 |  | 2025-04-23 |  | 2025-04-23 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Partially Shipped | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 06 |  | 6 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-03-19 | 2025-03-19 | 1 |  | QC Not Requested | 2025-04-23 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-04-23 |  | Issue Still in Process | Samantha Krantz - Reveals done 4-10-25 | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS06 In-House |  | 2025, Week 17
84 | 24051-FS10 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | South Elevation 700 level. Install Direction Left to Right |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS10 | 30.42% | 5862 | 19268 | 160 | 160 | 2 | 1120 | 2080 | 196 X 62 - 54 | 23:52:07 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 4 | -250 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-03-21 05:31 |  | 2025-04-15 | 2025-03-27 |  | 2025-05-02 |  | 2025-05-06 |  | 2025-05-06 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 10 |  | 10 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-03-26 | 2025-03-26 | 1 |  | QC Not Requested | 2025-05-05 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-05-06 |  | Issue Still in Process | Samantha Krantz - Reveals done 4-13-25 | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS10 In-House |  | 2025, Week 19
85 | 24051-FS42.1 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | EAST LEVEL 200 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (1582 LF) 1-5/8" Reveals * ( 100 pcs) Corner Clips * ( 200 pcs ) Color Matching Screws﻿ * ( 242 LF) JR2 (EXTENDED?) | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS42.1 | 66.39% | 12792 | 19268 | 98 | 98 | 14 | 661 | 1582 | 48 | 14:53:45 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 75 | -46 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Ailen Niedfeld |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Ailen Niedfeld | 2025-12-20 05:46 |  | 2026-01-23 | 2026-01-27 | TRUE | 2026-02-12 |  | 2026-02-13 |  | 2026-02-13 |  |  | YES | 750 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 42.1 |  | 42.1 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 12 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-01-24 | 2026-01-27 | 2 |  | QC Not Requested | 2026-03-19 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-19 |  | Issue Still in Process | Issiah Havens - @jdavis@jwmcd.com programmed. @aniedfeld@jwmcd.com please print all documents from the "PROGRAMMING DOCS" folder | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS42.1 In-House |  | 2026, Week 07
86 | 24051-FS43 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | EAST ELEVATION LEVEL 050. INSTRALL DIRECTION ROGHT TO LEFT. BOTTOM LEFT OUT OF RELEASE TO FIELD MEASURE. |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS43 | 47.57% | 9165 | 19268 | 160 | 160 | 8 | 969 | 2200 | 196 X 62 - 155 | 31:54:12 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 33 | -186 | Unassigned | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-06-10 16:15 |  | 2025-07-14 | 2025-07-07 |  | 2025-07-31 |  | 2025-08-04 |  | 2025-08-04 |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | YES | Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\01_Calcs\2025-5-27_LOCSHA STADIUM CALC PACKAGE | [5 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 43 |  | 43 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 250 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-07-02 | 2025-07-03 | 2 |  | QC Not Requested | 2025-08-16 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-08-18 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed w/ PT | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS43 In-House |  | 2025, Week 32
87 | 24051-FS43.1 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | LEVEL 50 EAST ELEVATION | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (437 LF) 1-5/8" Reveals | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS43.1 | 65.37% | 12596 | 19268 | 30 | 30 | 4 | 183 | 437 | 30 | 06:02:31 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 71 | -48 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Ailen Niedfeld |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Ailen Niedfeld | 2025-12-19 09:24 |  | 2026-01-19 | 2026-01-23 | TRUE | 2026-02-10 |  | 2026-02-09 |  | 2026-02-09 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans |  | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 43.1 |  | 43.1 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 80 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-01-23 | 2026-01-23 | 1 |  | Issue Still In Process |  | Crating Start Date Not Recorded | David Hasty | Ramon Estrada, Shane Watson | 2026-03-03 |  | Issue Still in Process | Issiah Havens - @aniedfeld@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS43.1 In-House |  | 2026, Week 07
88 | 24051-FS44 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | EAST ELEVATION LEVEL 050. BOTTOM ROW LEFT OFF RELEASE FOR FIELD MEASURE. |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS44 | 48.19% | 9285 | 19268 | 120 | 120 | 8 | 725 | 1700 | 196 X 62 - 115 | 23:47:40 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 40 | -176 | Unassigned | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-06-10 16:26 |  | 2025-07-28 | 2025-07-07 |  | 2025-08-14 |  | 2025-08-18 |  | 2025-08-18 |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | YES | Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\01_Calcs\2025-5-27_LOCSHA STADIUM CALC PACKAGE | [5 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 44 |  | 44 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-07-02 | 2025-07-03 | 2 |  | QC Not Requested | 2025-08-12 | 5 | David Hasty | Ramon Estrada, Shane Watson | 2025-08-18 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed w/ PT | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS44 In-House |  | 2025, Week 34
89 | 24051-FS45 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS EVERY CRATE REQUIRES JR2 | NORTH LEVEL 200 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | 2 SETS - INSTALL DRAWINGS 375 LF - 1 5/8" REVEALS TO MATCH 140 LF - JR2 175 pcs - Corner Clips 350 pcs - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS45 | 53.09% | 10229 | 19268 | 78 | 78 | 9 | 468 | 375 | 17 SHEETS | 00d09h48m52s | Alpolic - 4mm - 3600 pcs - [62 X 196] - TOB BLACK FR ACM, No Grain | FR ACM | Alpolic - 4mm - 3600 pcs - [62 X 196] - TOB BLACK | No |  |  | 47 | -103 | Unassigned | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-15 16:14 |  | 2025-11-05 | 2025-11-07 | TRUE | 2025-11-25 |  | 2025-11-26 |  | 2025-11-26 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 45 |  | 45 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 140 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-11-06 | 2025-11-06 | 1 |  | QC Not Requested | 2025-11-13 | 8 | David Hasty | Ramon Estrada, Shane Watson | 2025-11-24 |  | Issue Still in Process | Arnold Jurado - @hstakhurskyi@jwmcd.com @dusatenko@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS45 In-House | TRUE | 2025, Week 48
90 | 24048-RM02 |  | QTS NAL2 DC1 | 785 Beech Rd SW New Albany, OH 43054 | Joe Hoyle | 828.334.7808 | 400 |  | Panels missing from original delivery. Ship ASAP. | Loading dock soffit remakes. Pull materials from 24065. |  | TBD | Q:\Jobs\24048 - QTS NAL2 DC1\04_Production\24048RM02 | 102.4% | 1768 | 1727 | 3 | 3 | 3 | 0 | 0 | 160 X 62 - 3 SHEETS | 00:13:04 | 4mm X 62" X 160" 'SMX Silver' FR ACM, Grain | FR ACM | 4mm X 62" X 160" 'SMX Silver' | Yes |  |  | 16 | -157 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Chance Dill | Denis Usatenko | Chance Dill |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Chance Dill | 2025-08-25 06:33 | TRUE | 2025-08-27 | 2025-08-25 | TRUE | 2025-09-10 |  | 2025-08-28 |  | 2025-08-28 |  |  | YES | 81 | [5 empty] | MATCH COLOR | YES | Approved As Noted | NO |  | YES | Q:\Jobs\24048 - QTS NAL2 DC1\03_Engineering\02_FD Docs\24048 - Loading Dock Soffit | YES | Q:\Jobs\24048 - QTS NAL2 DC1\03_Engineering\04_Calcs | 201-2Q02 201-2Q06 201-2Q07 | FS12 |  | SHIPPING |  | Ready to Ship |  | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24048 | RM |  | 02 |  | 2 | 24048-RM02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 4 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-08-25 | 2025-08-25 | 1 |  | QC Not Requested | 2025-08-27 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-08-28 |  | Issue Still in Process | Arnold Jurado - @cdill@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Joe Hoyle | Chance Dill | Denis Usatenko | 24048-RM02 In-House |  | 2025, Week 35
91 | 24051-BM01 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 |  |  | issue does not ship as its own separate order. Will be sent to jobsite as needed with FS releases. | JR-Extended (1500 pcs @ 10'-0") Use stock 0.125 AL |  |  |  | N/A | N/A | N/A | 0 | 1900 | 1 | 0 | 0 | 150 | 0 | .125" X 60" X 120", 3003-H12 Mill Alum Sheet, No Grain | Alum Sheet | .125" X 60" X 120", 3003-H12 Mill | No |  |  | 17 | -219 | Unassigned | Denis Usatenko | Paul J Roberts |  |  | Paul J Roberts | Terry Jones | Paul J Roberts | [6 empty] | Paul J Roberts | 2025-03-05 10:42 |  | 2025-06-09 | 2025-03-14 |  | 2025-06-16 |  | 2025-06-18 |  | 2025-06-18 |  |  | YES | 100 | [19 empty] | RTS Titans |  | TRUE | [9 empty] | TRUE | [5 empty] | TRUE | [10 empty] | 24051 | BM |  | 01 |  | 1 | 24051-BM02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 60 | [10 empty] | In House |  |  |  | Brake Shear |  |  | No Program Requested |  | QC Not Requested | 2025-06-18 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-18 |  | Issue Still in Process | Paul J Roberts - @dusatenko@jwmcd.com I switched check over to Terry. | 1010 |  | Marc Ribar | Paul J Roberts | Terry Jones | 24051-BM01 In-House |  | 2025, Week 25
92 | 24051-BM02 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 |  |  | BUNDLE 700 LF FOR FS10C & 710 LF FOR FS33C PUT THESE PARTS IN THE RELEASE BUNDLES TO ENSURE THE MATERIAL IS SHIPPED WITH THE PANELS. |  | * Sketch |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051BM02 | N/A | N/A | N/A | 0 | 141 | 1 | 0 | 0 | 9 - SHTS | NA | .063" X 48" X 120", 3003 Mill Alum Sheet, No Grain | Alum Sheet | .063" X 48" X 120", 3003 Mill | No |  |  | 69 | -52 | Unassigned | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-01-05 13:34 |  | 2026-01-28 | 2026-01-05 |  | 2026-02-04 |  | 2026-02-06 |  | 2026-02-06 |  |  | YES | 12 | [19 empty] | RTS Titans |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 24051 | BM |  | 02 |  | 2 | 24051-BM02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 2 | 6 | [10 empty] | In House |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2026-01-19 | 9 | David Hasty | Ramon Estrada, Shane Watson | 2026-01-29 |  | Issue Still in Process | Denis Usatenko - 141 | 1010 |  | Marc Ribar | Denis Usatenko |  | 24051-BM02 In-House |  | 2026, Week 06
93 | 25032-FL01 |  | Amazon IAD181 | 43649 Light Speed Plaza Sterling, VA 20166 | Matt Rassmussen |  |  |  | Morin Dove Gray |  | * Sketches |  | Q:\Jobs\25032 - Amazon IAD181\04_Production\25032FL01 | N/A | N/A | N/A | 0 | 287 | 16 | 0 | 0 | 29 - SHTS | na | 22ga, 48 x 120 - Dove Gray Steel Sheet, No Grain | Steel Sheet | 22ga, 48 x 120 - Dove Gray | No |  |  | 2 | -17 | Samantha Krantz, Shane Jones | Denis Usatenko | Denis Usatenko |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-02-04 08:44 |  | 2026-03-18 | 2026-02-13 |  | 2026-03-25 |  | 2026-03-27 |  | 2026-03-27 |  |  | YES | 40 | 2026-03-06 | [18 empty] | Shear |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25032 | FL |  | 01 |  | 1 | 25032-FL01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 16 | [10 empty] | LTL |  |  |  | Cidan Shear |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - @mrassmussen@jwmcd.com I will look and come by your desk. I deleted your note about reviewing. | 1010 |  | Matt Rassmussen | Denis Usatenko |  | 25032-FL01 In-House | TRUE | 2026, Week 13
94 | 24081-FS01 |  | DLR DFW37 | 1502 Ferris Rd Garland, TX 75044 | Cole Norona | 931.591.9340 | 400 |  | POST PAINTED INSTRUCTIONS *SEE FOLLOWING NOTES*: -Do NOT apply stiffeners; crate the stiffeners/1199 so post painter can apply them. These will still need to be cut AND bundled/labeled per panel part. Stiffeners MUST have tape on them prior to shipping. -Mark the panel numbers on the side that is NOT painted in marker, NO STICKERS -Do NOT tape extrusions -Extremely important that the part lists are included in the crates for post painter﻿ GANG FORM CORNER REVEALS | -Material used is .125 60" x 144" 3003, returns to be bent not routed -This release is for Sector A & C; Elevations 202, 203, 204 (Black Color) -We are released off our frame-to drawings. Please work off our drawings for measurements. I did add the glazing drawings in case those were needed. | SKETCHES PROGRAMMING FILES EXTRUSION CUT LIST YELLOW LABELS | 16 RETICULATED BAFFLES 19 LF JR2 | Q:\Jobs\24081 - DLR DFW37\04_Production\24081-FS01 | Unavailable | 127 | 0 | 109 | 308 | 44 | 674 | 0 | 28 | 05:13:45 | .125"x 60”x144", 3003 Alum Sheet, No Grain | Alum Sheet | .125"x 60”x144", 3003 | No |  |  | 2 | -40 | Ramon Estrada, Shane Watson | David Hasty | David Hasty | Frank Dean | David Hasty | Frank Dean | David Hasty | Frank Dean |  |  |  | Chris Gambrel | TRUE |  | Frank Dean | 2026-01-07 15:34 |  | 2026-01-30 | 2026-02-04 | TRUE | 2026-02-20 | 2026-02-20 | 2026-02-20 |  | 2026-02-20 |  | 2026-02-25 | YES | 215 |  | TRUE | Post Paint | Air Performance 159 Genco Drive Hartford, AL 36344 Attn: Jake Faundez 941.718.2839 jfaundez@airperformancellc.com | Coating Ship To Site | FAB SCREW | N/A | Approved | NO |  | NO |  | YES | Q:\Jobs\24081 - DLR DFW37\03_Engineering\02_FD Docs\24081FS01 | [5 empty] | Shipped To Painter | TRUE | TRUE | [6 empty] | TRUE | 7000 TruMatic | [5 empty] | TRUE |  | TRUE | [6 empty] | TRUE | TRUE |  |  | 24081 | FS |  | 01 |  | 1 | 24081-FS05 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 40 | 170 | [10 empty] | Hot Shot |  |  | Punch | 7000 TruMatic Brake Clean and Brake Extrusion Saw Fab Post Paint | 2026-02-03 | 2026-02-04 | 2 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Chris Gambrel - @fdean@jwmcd.com @jdorsey@jwmcd.com @dhasty@jwmcd.com flat programs completed. | 1010 |  | Cole Norona | Frank Dean | David Hasty | 24081-FS01 In-House | TRUE | 2026, Week 08
95 | 24081-FS02 |  | DLR DFW37 | 1502 Ferris Rd Garland, TX 75044 | Cole Norona | 931.591.9340 | 400 |  | POST PAINTED INSTRUCTIONS *SEE FOLLOWING NOTES*: -Do NOT apply stiffeners; crate the stiffeners/1199 so post painter can apply them. These will still need to be cut AND bundled/labeled per panel part. Stiffeners MUST have tape on them prior to shipping. -Mark the panel numbers on the side that is NOT painted in marker, NO STICKERS -Do NOT tape extrusions -Extremely important that the part lists are included in the crates for post painter GANG FORM CORNER REVEALS | -Material used is .125 60" x 144" 3003, returns to be bent not routed -This release is for Sector B & Entry Canopy; Elevations 206, 207, 208, 209 (Black Color) -We are released off our frame-to drawings. Please work off our drawings for measurements. I did add the glazing drawings in case those were needed. | SKETCHES PROGRAMMING FILES YELLOW LABELS EXTRUSION CUT LIST | 20 RETICULATED BAFFLES 55 LF JR2 | Q:\Jobs\24081 - DLR DFW37\04_Production\24081-FS02 | Unavailable | 250 | 0 | 123 | 349 | 57 | 750 | 0 | 46 | 06:57:07 | .125"x 60”x144", 3003 Alum Sheet, No Grain | Alum Sheet | .125"x 60”x144", 3003 | No |  |  | 3 | -39 | Ramon Estrada, Shane Watson | David Hasty | David Hasty | Jonathan Dorsey | David Hasty | Jonathan Dorsey | David Hasty | Jonathan Dorsey |  |  |  | Chris Gambrel | TRUE |  | Jonathan Dorsey | 2026-01-07 15:46 |  | 2026-01-30 | 2026-02-05 | TRUE | 2026-02-23 | 2026-02-20 | 2026-02-20 |  | 2026-02-20 |  | 2026-02-25 | YES | 215 |  | TRUE | Post Paint | Air Performance 159 Genco Drive Hartford, AL 36344 Attn: Jake Faundez 941.718.2839 jfaundez@airperformancellc.com | Coating Ship To Site | FAB SCREW | N/A | Approved | NO |  | NO |  | YES | Q:\Jobs\24081 - DLR DFW37\03_Engineering\02_FD Docs\24081FS02 | [5 empty] | Shipped To Painter | TRUE | TRUE | [6 empty] | TRUE | 7000 TruMatic | [5 empty] | TRUE |  | TRUE | [7 empty] | TRUE |  |  | 24081 | FS |  | 02 |  | 2 | 24081-FS05 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 42 | 195 | [10 empty] | Hot Shot |  |  | Punch | 7000 TruMatic Brake Extrusion Saw Fab Post Paint | 2026-02-04 | 2026-02-05 | 2 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Chris Gambrel - @fdean@jwmcd.com @jdorsey@jwmcd.com @dhasty@jwmcd.com flat programs completed. | 1010 |  | Cole Norona | Jonathan Dorsey | David Hasty | 24081-FS02 In-House | TRUE | 2026, Week 08
96 | 24081-FS03 |  | DLR DFW37 | 1502 Ferris Rd Garland, TX 75044 | Cole Norona | 931.591.9340 | 400 |  | POST PAINTED INSTRUCTIONS *SEE FOLLOWING NOTES*: -Do NOT apply stiffeners; crate the stiffeners/1199 so post painter can apply them. These will still need to be cut AND bundled/labeled per panel part. Stiffeners MUST have tape on them prior to shipping. -Mark the panel numbers on the side that is NOT painted in marker, NO STICKERS -Do NOT tape extrusions -Extremely important that the part lists are included in the crates for post painter GANG FORM CORNER REVEALS | -Material used is .125 60" x 144" 3003, returns to be bent not routed -This release is for Guard House: Elevations 301, 303 (Black Color) -We are released off our frame-to drawings. Please work off our drawings for measurements. I did add the glazing drawings in case those were needed. | SKETCHES PROGRAMMING FILES YELLOW LABELS EXTRUSION CUT LIST | 10 LF JR2 | Q:\Jobs\24081 - DLR DFW37\04_Production\24081-FS03 | Unavailable | 274 | 0 | 24 | 88 | 19 | 172 | 0 | 7 | 01:21:40 | .125"x 60”x144", 3003 Alum Sheet, No Grain | Alum Sheet | .125"x 60”x144", 3003 | No |  |  | 5 | -37 | Ramon Estrada, Shane Watson | David Hasty | David Hasty | Frank Dean | David Hasty | Frank Dean | David Hasty | Frank Dean |  |  |  | Chris Gambrel | TRUE |  | Frank Dean | 2026-01-07 15:54 |  | 2026-01-30 | 2026-02-09 | TRUE | 2026-02-25 | 2026-02-27 | 2026-02-20 |  | 2026-02-20 |  | 2026-03-03 | YES | 215 |  | TRUE | Post Paint | Air Performance 159 Genco Drive Hartford, AL 36344 Attn: Jake Faundez 941.718.2839 jfaundez@airperformancellc.com | Coating Ship To Site | FAB SCREW | N/A | Approved | NO |  | NO |  | YES | Q:\Jobs\24081 - DLR DFW37\03_Engineering\02_FD Docs\24081FS03 | [5 empty] | Shipped To Painter | TRUE | TRUE | [6 empty] | TRUE | 7000 TruMatic | [5 empty] | TRUE | [8 empty] | TRUE | TRUE |  |  | 24081 | FS |  | 03 |  | 3 | 24081-FS05 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 10 | 40 | [10 empty] | Hot Shot |  |  | Punch | 7000 TruMatic Clean and Brake Extrusion Saw Fab Post Paint | 2026-02-06 | 2026-02-06 | 1 |  | QC Not Requested | 2026-02-22 | 5 | David Hasty | Ramon Estrada, Shane Watson | 2026-02-27 |  | Issue Still in Process | Chris Gambrel - @fdean@jwmcd.com @jdorsey@jwmcd.com @dhasty@jwmcd.com flat program completed. | 1010 |  | Cole Norona | Frank Dean | David Hasty | 24081-FS03 In-House | TRUE | 2026, Week 08
97 | 24081-FS04 |  | DLR DFW37 | 1502 Ferris Rd Garland, TX 75044 | Cole Norona | 931.591.9340 | 400 |  | POST PAINTED INSTRUCTIONS *SEE FOLLOWING NOTES*: -Do NOT apply stiffeners; crate the stiffeners/1199 so post painter can apply them. These will still need to be cut AND bundled/labeled per panel part. Stiffeners MUST have tape on them prior to shipping. -Mark the panel numbers on the side that is NOT painted in marker, NO STICKERS -Do NOT tape extrusions -Extremely important that the part lists are included in the crates for post painter GANG FORM CORNER REVEALS | -Material used is .125 60" x 144" 3003, returns to be bent not routed -This release is for Guardhouse; Elevations 302 (Gray Color) -We are released off our frame-to drawings. Please work off our drawings for measurements. I did add the glazing drawings in case those were needed. | SKETCHES PROGRAMMING FILES YELLOW LABELS EXTRUSION CUT LIST | 130 LF JR2 | Q:\Jobs\24081 - DLR DFW37\04_Production\24081-FS04 | Unavailable | 368 | 0 | 94 | 243 | 63 | 483 | 0 | 24 | 04:54:13 | .125"x 60”x144", 3003 Alum Sheet, No Grain | Alum Sheet | .125"x 60”x144", 3003 | No |  |  | 8 | -36 | Ramon Estrada, Shane Watson | David Hasty | David Hasty | Frank Dean | David Hasty | Frank Dean | David Hasty | Frank Dean |  |  |  | Chris Gambrel | TRUE |  |  | 2026-01-07 15:58 |  | 2026-01-30 | 2026-02-10 | TRUE | 2026-02-26 | 2026-02-20 | 2026-02-20 |  | 2026-02-20 |  | 2026-03-03 | YES | 215 |  | TRUE | Post Paint | Air Performance 159 Genco Drive Hartford, AL 36344 Attn: Jake Faundez 941.718.2839 jfaundez@airperformancellc.com | Coating Ship To Site | FAB SCREW | N/A | Approved | NO |  | NO |  | YES | Q:\Jobs\24081 - DLR DFW37\03_Engineering\02_FD Docs\24081FS04 | [5 empty] | Shipped To Painter | TRUE | TRUE | [6 empty] | TRUE | 7000 TruMatic | [5 empty] | TRUE |  | TRUE | [6 empty] | TRUE | TRUE |  |  | 24081 | FS |  | 04 |  | 4 | 24081-FS05 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 35 | 150 | [10 empty] | Hot Shot |  |  | Punch | 7000 TruMatic Brake Clean and Brake Extrusion Saw Fab Post Paint | 2026-02-09 | 2026-02-10 | 2 |  | QC Not Requested | 2026-02-25 | 5 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-03 |  | Issue Still in Process | Chris Gambrel - @fdean@jwmcd.com @jdorsey@jwmcd.com @dhasty@jwmcd.com flat programs completed | 1010 |  | Cole Norona | Frank Dean | David Hasty | 24081-FS04 In-House | TRUE | 2026, Week 08
98 | 24081-FS05 |  | DLR DFW37 | 1502 Ferris Rd Garland, TX 75044 | Cole Norona | 931.591.9340 | 400 |  | POST PAINTED INSTRUCTIONS *SEE FOLLOWING NOTES*: -Do NOT apply stiffeners; crate the stiffeners/1199 so post painter can apply them. These will still need to be cut AND bundled/labeled per panel part. Stiffeners MUST have tape on them prior to shipping. -Mark the panel numbers on the side that is NOT painted in marker, NO STICKERS -Do NOT tape extrusions -Extremely important that the part lists are included in the crates for post painter GANG FORM CORNER REVEALS LABEL PANELS WITH MARKER AFTER PUNCH | -Material used is .125 60" x 144" 3003, returns to be bent not routed -This release is for Penthouse; Elevation 210 (Gray Color) -We are released off our frame-to drawings. Please work off our drawings for measurements. I was able to obtain measurements of this wall during my visit. I did add the glazing drawings in case those were needed. | SKETCHES PROGRAMMING FILES YELLOW LABELS EXTRUSION CUT LIST | 165 LF JR2 | Q:\Jobs\24081 - DLR DFW37\04_Production\24081-FS05 | Unavailable | 479 | 0 | 111 | 345 | 32 | 788 | 0 | 94 | 10:27:30 | .125"x 60”x144", 3003 Alum Sheet, No Grain | Alum Sheet | .125"x 60”x144", 3003 | No |  |  | 9 | -35 | Ramon Estrada, Shane Watson | David Hasty | David Hasty | Frank Dean | David Hasty | Frank Dean | David Hasty | Frank Dean |  |  |  | Chris Gambrel | TRUE |  |  | 2026-01-09 09:51 |  | 2026-01-30 | 2026-02-11 | TRUE | 2026-02-27 | 2026-02-20 | 2026-02-20 |  | 2026-02-20 |  | 2026-03-03 | YES | 215 |  | TRUE | Post Paint | Air Performance 159 Genco Drive Hartford, AL 36344 Attn: Jake Faundez 941.718.2839 jfaundez@airperformancellc.com | Coating Ship To Site | FAB SCREW | N/A | Approved | NO |  | YES | Q:\Jobs\24081 - DLR DFW37\03_Engineering\02_FD Docs\24081FS05 | YES | Q:\Jobs\24081 - DLR DFW37\03_Engineering\02_FD Docs\24081FS05 | [5 empty] | Shipped To Painter | TRUE | TRUE | [6 empty] | TRUE | 7000 TruMatic | [7 empty] | TRUE | [10 empty] | 24081 | FS |  | 05 |  | 5 | 24081-FS05 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 40 | 180 | [10 empty] | Hot Shot |  |  | Punch | 7000 TruMatic Brake Post Paint | 2026-02-10 | 2026-02-11 | 2 |  | QC Not Requested | 2026-02-26 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-02-28 |  | Issue Still in Process | Jonathan Dorsey - Jonathan Dorsey reacted to your message: | 1010 |  | Cole Norona | Frank Dean | David Hasty | 24081-FS05 In-House | TRUE | 2026, Week 08
99 | 23028-FS99 |  | 1000 Church YMCA | 1000 Church Street Nashville, TN 37203 | Dillon Bowman | 518.860.9477 | 600 |  | Last Soffit Panel | Last Soffit Panel See SD Folder for Notes | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * 6 LF 1 3/4" COLOR MATCHING REVEALS * 24 PCS PET 3" CLIPS * 6 PCS PE2N 3" CLIPS | Q:\Jobs\23028 - 1000 Church YMCA\04_Production\23028FS99 | 229.8% | 108 | 47 | 1 | 1 | 1 | 36 | 6 | 1 | 00:16:33 | 4mm x 62 x 196 - Cosmic Gray Mica - 23028 FR ACM, Grain | FR ACM | 4mm x 62 x 196 - Cosmic Gray Mica - 23028 | Yes |  |  | 27 | -67 | Ramon Estrada, Shane Watson | Denis Usatenko |  | Denis Usatenko |  | Gabriela Herrera | Denis Usatenko | Gabriela Herrera |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Gabriela Herrera | 2025-12-08 13:34 | TRUE | 2025-12-29 | 2025-12-22 |  | 2026-01-14 |  | 2026-01-16 |  | 2026-01-16 |  |  | YES | 8 | [5 empty] | MATCH COLOR | YES | Approved As Noted | YES | Q:\Jobs\23028 - 1000 Church YMCA\03_Engineering\02_FD Docs\23028 - FS99 | NO |  | NO | [6 empty] | Ready to Ship | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 23028 | FS |  | 99 |  | 99 | 23028-FS99 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 2 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-12-22 | 2025-12-22 | 1 |  | QC Not Requested | 2026-01-02 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2026-01-02 |  | Issue Still in Process | Issiah Havens - @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Dillon Bowman | Gabriela Herrera | Denis Usatenko | 23028-FS99 In-House |  | 2026, Week 03
100 | 24001-BM14 |  | McEwen Northside | 4020 Aspen Grove Drive Franklin, TN 37067 | Josh McPherson | 615.939.2359 |  |  |  | Replicate BM10 with required quantities. For assembling FS09. |  |  | Q:\Jobs\24001 - McEwen Northside\04_Production\24001BM14 | N/A | N/A | N/A | 0 | 12 | 1 | 0 | 0 | 1 |  | 16 Ga. X 48" X 120" Galv Sheet, No Grain | Galv Sheet | 16 Ga. X 48" X 120" | No |  |  | 2 | -296 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi | [6 empty] | Hennadii Stakhurskyi | 2025-02-11 11:06 |  | 2025-02-19 | 2025-02-11 |  | 2025-02-27 |  | 2025-03-03 |  | 2025-03-03 |  |  | YES | 43 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 24001 | BM |  | 14 |  | 14 | 24001-BM14 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 0.25 | 1 | [10 empty] | In House |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2025-02-18 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-02-19 |  | Issue Still in Process |  | 1010 |  | Josh McPherson | Hennadii Stakhurskyi | Denis Usatenko | 24001-BM14 In-House |  | 2025, Week 010
101 | 25007-BM03 |  | QTS ATL2 DC10 | 167 Tyrone Road, Bldg 1000 Fayetteville, GA 30214 | Nick Akins | 832.948.2317 |  |  |  | 80 pieces of 10 sticks: 2" zee | * Sketch |  | Q:\Jobs\25007 - QTS ATL2 DC10\04_Production\25007BM03 | N/A | N/A | N/A | 0 | 80 | 1 | 0 | 0 | 6.75 - SHT | na | 16 Ga. X 48" X 120" Galv Sheet, No Grain | Galv Sheet | 16 Ga. X 48" X 120" | No |  |  | 23 | -76 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2025-11-10 16:26 |  | 2025-12-25 | 2025-11-10 |  | 2026-01-01 |  | 2026-01-05 |  | 2026-01-05 |  |  | YES | 270 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25007 | BM |  | 03 |  | 3 | 25007-BM03 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 4 | [10 empty] | Conestoga Hot Shot Semi |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2025-11-11 | 5 | David Hasty | Ramon Estrada, Shane Watson | 2025-11-17 |  | Issue Still in Process |  | 1010 |  | Nick Akins | Denis Usatenko |  | 25007-BM03 In-House |  | 2026, Week 02
102 | 25008-FS05 |  | Columbia State Tech Center | 1665 Hampshire Pike Columbia, TN 38401 | Laura Forero | 615.788.7739 | 400 CAULK |  | This is mainly a caulked job, but please check because there are some panels that need countersink screws. Yes, the color match screws are ordered. | This release includes 202, 203, and 220 complete elevations. For elevations 206-209, we are only fabricating the exterior panels. There are no scans for any elevations. But we do have pictures. Please use the FD in the folder AMI Q. In there, I have asked questions to the GC and all of them have been answered. Elevations 202, 206, 207, 208, and 209 will have a system depth of 2-1/4" Elevations 206 and 220 will have the normal system depth, 4-1/4' The panels next to the storefront have changed the extrusions to a PR2/JR2. This applies to elevations 206-209 and 220. Please check the panels that are next to the light fixtures, because that side will need countersink screws. | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * 47 LF JR2 * 220 PCS CORNER CLIPS * 440 PCS FAB CREWS | Q:\Jobs\25008 - Columbia State Tech Center\04_Production\25008FS05 | 95.88% | 512 | 534 | 101 | 101 | 83 | 645 | 0 | 38 | 14:22:48 | Alucobond 4mm X 62" X 196", Oyster FR ACM, No Grain | FR ACM | Alucobond 4mm X 62" X 196", Oyster | No |  |  | 3 | -39 | Ramon Estrada, Shane Watson | Denis Usatenko | Gabriela Herrera | Gabriela Herrera |  | Gabriela Herrera | Denis Usatenko | Gabriela Herrera |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Gabriela Herrera | 2025-12-12 13:30 |  | 2026-01-28 | 2026-02-05 | TRUE | 2026-02-23 |  | 2026-02-18 |  | 2026-02-18 |  | 2026-02-16 | YES | 107 | [5 empty] | FAB SCREW | YES | Approved As Noted | NO |  | YES | Q:\Jobs\25008 - Columbia State Tech Center\03_Engineering\02_FD Docs\25008 FS05 | NO | [6 empty] | Shipped To Painter | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 25008 | FS |  | 05 |  | 5 | 25008-FS07 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 35 | 130 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-02-04 | 2026-02-05 | 2 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Issiah Havens - @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Laura Forero | Gabriela Herrera | Denis Usatenko | 25008-FS05 In-House |  | 2026, Week 08
103 | 24051-FS01 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | WEST LEVEL 7. TOP BAND OF BLACK PANELS |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS01 | 25.56% | 4925 | 19268 | 160 | 160 | 2 | 1120 | 3010 | 196 X 62 - 54 | 23:41:26 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 1 | -272 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-03-06 11:18 | TRUE | 2025-03-27 | 2025-03-17 | TRUE | 2025-04-02 |  | 2025-03-31 |  | 2025-03-31 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 01 |  | 1 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 360 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-03-17 | 2025-03-17 | 1 |  | QC Not Requested | 2025-04-11 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-04-11 |  | Issue Still in Process | Samantha Krantz - Reveals done 4-7-25 | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS01 In-House |  | 2025, Week 14
104 | 24051-FS01C |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | COPING FOR WEST LEVEL 7 - TO SHIP WITH THE BALANCE OF THE AREA PANELS. IS DIRECTLY ABOVE FS01. |  |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS01C | 42.69% | 8225 | 19268 | 160 | 160 | 2 | 1120 | 800 | 196 X 62 - 32 | 19:19:02 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 23 | -210 | Unassigned | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-05-04 09:32 |  | 2025-06-10 | 2025-05-07 |  | 2025-06-27 |  | 2025-07-01 |  | 2025-07-01 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO | \\192.168.2.10\ashop_data\Jobs\24051 - TN Titans Stadium\03_Engineering\02_FD Docs\FS_TOB BLACK\24051FS01C-L700 W Coping | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 01C |  | 0 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-05-06 | 2025-05-07 | 2 |  | QC Not Requested | 2025-06-17 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-18 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed and in PanelTracker | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS01C In-House |  | 2025, Week 27
105 | 24051-FS02 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | WEST LEVEL 7 MIDDLE BAND OF THE BLACK PANELS |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS02 | 26.38% | 5083 | 19268 | 158 | 158 | 2 | 726 | 1050 | 196 X 62 - 15 | 12:13:37 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 2 | -263 | Unassigned | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-03-06 11:23 |  | 2025-03-27 | 2025-03-18 |  | 2025-04-15 |  | 2025-04-17 |  | 2025-04-17 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 02 |  | 2 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-03-18 | 2025-03-18 | 1 |  | QC Not Requested | 2025-04-16 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-04-17 |  | Issue Still in Process | Samantha Krantz - Reveals done 4-7-25 | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS02 In-House |  | 2025, Week 16
106 | 24051-FS03 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | WEST LEVEL 7 BOTTOM BLACK PANELS |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS03 | 27.21% | 5243 | 19268 | 160 | 160 | 2 | 1280 | 2460 | 196 X 62 - 80 | 29:31:12 | 4MM FR CORE TOB BLACK 62X196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62X196 | No |  |  | 3 | -262 | Unassigned | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-03-06 11:43 |  | 2025-03-28 | 2025-03-18 |  | 2025-04-16 |  | 2025-04-18 |  | 2025-04-18 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ 34 | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 03 |  | 3 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  | 2025-03-20 | 2025-03-20 | 1 |  |  |  | No Hold | 1 | 8 | 300 | [13 empty] | AXYZ | AXYZ 34 Clean and Brake Fab | 2025-03-18 | 2025-03-18 | 1 |  | Issue Still In Process |  | Crating Start Date Not Recorded | David Hasty | Ramon Estrada, Shane Watson | 2025-04-18 |  | Issue Still in Process | Samantha Krantz - Reveals done 4-7-25 | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS03 In-House |  | 2025, Week 16
107 | 25052-BM01 |  | TEMA Warehouse | 3901 Stewarts Lane Nashville, TN 37218 | Andre Van Der Merwe | 315.261.0333 |  |  |  | 16 x 10' x 7/8" 16ga hat channels | * Sketch |  | Q:\Jobs\25052 - TEMA Warehouse\04_Production\25052BM01 | N/A | N/A | N/A | 0 | 16 | 1 | 0 | 0 | 2 - SHT | na | 16 ga 48" x 120" galvanized Galv Sheet, No Grain | Galv Sheet | 16 ga 48" x 120" galvanized | No |  |  | 23 | -76 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2025-11-10 15:43 |  | 2025-12-25 | 2025-11-12 |  | 2026-01-01 |  | 2026-01-05 |  | 2026-01-05 |  |  | YES | 270 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25052 | BM |  | 01 |  | 1 | 25052-BM01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 2 | 5 | [10 empty] | Hot Shot |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2025-11-13 | 3 | David Hasty | Ramon Estrada, Shane Watson | 2025-11-17 |  | Issue Still in Process |  | 1010 |  | Andre Van Der Merwe | Denis Usatenko |  | 25052-BM01 In-House |  | 2026, Week 02
108 | 25052-FL01 |  | TEMA Warehouse | 3901 Stewarts Lane Nashville, TN 37218 | Andre Van Der Merwe | 315.261.0333 |  |  | SHIP WITH FS01. | 101: 4 1/2" x 100LF | * Sketch |  | Q:\Jobs\25052 - TEMA Warehouse\04_Production\25052FL01 | N/A | N/A | N/A | 0 | 10 | 1 | 0 | 0 | 1 - SHT | na | .040" X 48" X 120" Cityscape Alum Sheet, Grain | Alum Sheet | .040" X 48" X 120" Cityscape | Yes |  |  | 26 | -68 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2025-11-11 09:40 |  | 2026-01-06 | 2025-11-14 |  | 2026-01-13 |  | 2026-01-15 |  | 2026-01-15 |  |  | YES | 2 | 2025-12-09 | [9 empty] | YES | Q:\Jobs\25052 - TEMA Warehouse\03_Engineering\02_FD Docs\25052FL01 | [7 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25052 | FL |  | 01 |  | 1 | 25052-FL01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 6 | [10 empty] | Hot Shot |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2025-12-17 | 6 | David Hasty | Ramon Estrada, Shane Watson | 2025-12-24 |  | Issue Still in Process | Mitch Chancey - 1 BUNDLE ON THE TREE @avdm@jwmcd.com @swatson@jwmcd.com @tgraves@jwmcd.com | 1010 |  | Andre Van Der Merwe | Denis Usatenko |  | 25052-FL01 In-House |  | 2026, Week 03
109 | 24051-RP17 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 |  |  |  | Scratches from CNC |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051RP17 | 49.28% | 9496 | 19268 | 1 | 1 | 0 | 0 | 0 | 196 X 62 - 1 | 00:13:42 | [6 empty] | 40 | -176 | Unassigned | David Hasty | [5 empty] | Paul J Roberts |  | Arnold Jurado, Issiah Havens |  |  |  |  | Gabriela Herrera | 2025-08-14 09:57 |  | 2025-08-14 | 2025-08-14 |  | 2025-08-14 | [22 empty] | N300-1J41 | RP12 | HUMAN ERROR |  | jdavis@jwmcd.com | RTS Titans |  |  | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 |  | RP | 17 | -- | 17 | 24051-RP58 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | [15 empty] | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-08-14 |  | 176 (In Progress) |  | QC Not Requested | 2025-08-16 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-08-18 |  | 0 | Issiah Havens - @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar |  |  | 24051-RP17 In-House |  | #INVALID DATA TYPE
110 | 24051-RP20 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 |  |  |  | Roller marks from Alu Bender |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051RP20 | 49.52% | 9542 | 19268 | 46 | 46 | 0 | 0 | 0 | 196 X 62 - 19 SHEETS | 07:45:29 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | [5 empty] | 42 | -149 | Unassigned | Denis Usatenko | [5 empty] | Paul J Roberts |  | Arnold Jurado, Issiah Havens |  |  |  |  | Gabriela Herrera | 2025-09-22 08:43 |  | 2025-09-22 | 2025-09-22 |  | 2025-09-22 |  | 2025-09-23 |  | 2025-09-23 | [18 empty] | 1D41 (36) 1D43 (8) 1D40 (2) | FS12 | MACHINE |  | jdavis@jwmcd.com | RTS Titans |  |  | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 |  | RP | 20 | -- | 20 | 24051-RP58 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | [15 empty] | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-09-22 |  | 149 (In Progress) |  | QC Not Requested | 2025-09-23 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-09-23 |  | 0 | Arnold Jurado - @jdavis@jwmcd.com PROGRAMED | 1010 |  | Marc Ribar |  |  | 24051-RP20 In-House |  | 2025, Week 39
111 | 24051-FS213 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS | NORTH LEVEL 7 INSTALL RIGHT TO LEFT | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | 2 SETS - INSTALL DRAWINGS 700 LF - 1 5/8" REVEALS TO MATCH 850 pcs - Corner Clips 1700 pcs - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS213 | 51.42% | 9907 | 19268 | 138 | 138 | 2 | 1380 | 700 | 69 | 26:02:10 | Alpolic - 4mm - 880 pcs - [62 X 196] - MOONSTONE METALLIC FR ACM, Grain | FR ACM | Alpolic - 4mm - 880 pcs - [62 X 196] - MOONSTONE METALLIC | Yes |  |  | 45 | -106 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-04-07 16:22 |  | 2025-11-03 | 2025-10-23 |  | 2025-11-20 |  | 2025-11-24 |  | 2025-11-24 |  |  | YES | 500 | 2025-04-08 |  |  |  |  | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 213 |  | 213 | 24051-FS231 |  |  | 2025-04-14 | 2025-10-14 | 132 |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | 132 | 4 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-10-23 | 2025-10-23 | 1 |  | QC Not Requested | 2025-11-08 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-11-11 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS213 In-House |  | 2025, Week 48
112 | 24051-FS215 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | PLEASE NOTE THIS RELEASE IS FIELD PANELS AND THE PERIMETER PANELS WILL BE INSTALLED ONCE THESE ARE IN PLACE SOUTRH ELEVATION LEVEL 00 WINGS |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS215 | 44.03% | 8483 | 19268 | 14 | 14 | 14 | 98 | 200 | 196 X 62 - 14 | 02:55:18 | 4MM FR CORE MOONSTONE METALLIC 62X196 FR ACM, Grain | FR ACM | 4MM FR CORE MOONSTONE METALLIC 62X196 | Yes |  |  | 31 | -188 | Unassigned | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-06-04 10:28 |  | 2025-07-10 | 2025-06-17 |  | 2025-07-29 |  | 2025-07-31 |  | 2025-07-31 |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | YES | Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\01_Calcs\2025-5-27_LOCSHA STADIUM CALC PACKAGE | [5 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 215 |  | 215 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 40 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-06-17 | 2025-06-17 | 1 |  | QC Not Requested | 2025-06-24 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-24 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed, panel tracker | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS215 In-House |  | 2025, Week 31
113 | 25040-FL01 |  | Moses Lincoln Vitrine | 2001 MacCorkle Ave St. Albans, WV 25177 | Laura Forero | 615.788.7739 |  |  | This flashing has to be shipped with 25040FS01 Please use the leftover material from 24065 - QTS NAL2 DC2, BNT WHITE 0.32 | There is only one flashing profile for the whole job. Please make a 10' stick they will cut it in the field to whatever they need. The profile and the quantities are in the file attached. | * Sketch |  | Q:\Jobs\25040 - Moses Lincoln Vitrine\04_Production\25040FL01 | N/A | N/A | N/A | 0 | 1 | 1 | 0 | 0 | 0.33 - SHT | na | .032" X 60" X 120", BNT WHITE [24065] Alum Sheet, No Grain | Alum Sheet | .032" X 60" X 120", BNT WHITE [24065] | No |  |  | 22 | -80 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2025-12-02 14:52 |  | 2025-12-19 | 2025-12-05 |  | 2025-12-26 |  | 2025-12-30 |  | 2025-12-30 |  |  | YES | 1 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25040 | FL |  | 01 |  | 1 | 25040-FL01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 0.5 | 1 | [10 empty] | Hot Shot |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2025-12-08 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-12-09 |  | Issue Still in Process | Mitch Chancey - @lforero@jwmcd.com @swatson@jwmcd.com @tgraves@jwmcd.com LOOSE ON THE TREE | 1010 |  | Laura Forero | Denis Usatenko |  | 25040-FL01 In-House |  | 2025, Week 01
114 | 25028-FL02 |  | TN Soybean Council | 100 Executive Drive Jackson, TN 38305 | Cole Norona | 931.591.9340 |  |  | 3 @ 10FT PULL BRIGHT SILVER METALLIC MATERIAL FROM 24048 | 101 COPING 3PCS @ 10FT YOU CAN LOCATE THE DIMENSIONS NEEDED AT Q:\Jobs\25028 - TN Soybean Council\03_Engineering\02_FD Docs\25028FL02 |  |  | \\jw-vm-ashop\ASHOP_DATA\Jobs\25028 - TN Soybean Council\04_Production\25028FL02 | N/A | N/A | N/A | 0 | 4 | 1 | 0 | 0 | 3 | na | 22G X 48" X 120", BRIGHT SILVER METALLIC Alum Sheet, Grain | Alum Sheet | 22G X 48" X 120", BRIGHT SILVER METALLIC | Yes |  |  | 13 | -177 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2025-08-07 13:26 | TRUE | 2025-08-15 | 2025-08-07 | TRUE | 2025-08-13 |  | 2025-08-08 |  | 2025-08-08 |  |  | YES | 3 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25028 | FL |  | 02 |  | 2 | 25028-FL02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 1 | [10 empty] | In House |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2025-08-07 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-08-08 |  | Issue Still in Process |  | 1010 |  | Cole Norona | Denis Usatenko |  | 25028-FL02 In-House |  | 2025, Week 32
115 | 25028-FS01 |  | TN Soybean Council | 100 Executive Drive Jackson, TN 38305 | Cole Norona | 931.591.9340 | 400 CAULK |  |  |  |  | (2 Boxes) Dowsil 795 Gray Caulk (1 Roll) 5/8" Backer Rod 1550LF (1 Box) Red 1/8" Shims (1 Box) Black 1/4" Shims (1,000 pcs) #12 x 1 3/4" Tek3 Screws (1,000 pcs) #14 x 1 3/4" Tapcon Screws | Q:\Jobs\25028 - TN Soybean Council\04_Production\25028FS01 | 118.8% | 38 | 32 | 26 | 26 | 26 | 175 | 0 | 8 | 03:29:24 | 4mm X 62" X 196", Bright Silver Metallic FR ACM, Grain | FR ACM | 4mm X 62" X 196", Bright Silver Metallic | Yes |  |  | 9 | -194 | Ramon Estrada, Shane Watson | Denis Usatenko | Samuel Lucas | Samuel Lucas |  | Samuel Lucas | Denis Usatenko | Samuel Lucas |  | Issiah Havens |  |  | TRUE |  | Samuel Lucas | 2025-06-12 07:58 | TRUE | 2025-07-03 | 2025-06-27 |  | 2025-07-21 |  | 2025-07-23 |  | 2025-07-23 |  |  | YES | 12 | [5 empty] | FAB SCREW | YES | Approved | YES | Q:\Jobs\25028 - TN Soybean Council\03_Engineering\02_FD Docs\25028FS01\SCAN | YES | Q:\Jobs\25028 - TN Soybean Council\03_Engineering\02_FD Docs\25028FS01\FIELD DIMENSIONS | NO | [6 empty] | Ready to Ship | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 25028 | FS |  | 01 |  | 1 | 25028-FS01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 14 | 46 | [10 empty] | Hot Shot |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-06-27 | 2025-06-27 | 1 |  | QC Not Requested | 2025-07-09 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-07-09 |  | Issue Still in Process | Issiah Havens - @slucas@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed w/ PanelTracker | 1010 |  | Cole Norona | Samuel Lucas | Denis Usatenko | 25028-FS01 In-House |  | 2025, Week 30
116 | 25029-FL97 |  | Lourdes CC Phase 2 | 1510 Lone Oak Road Paducah, KY 42003 | Dillon Bowman | 518.860.9477 |  |  | MU - FL Closure Z | MU - FL Closure Z (Sketch in FD Folder) |  |  | Q:\Jobs\25029 - Lourdes CC Phase 2\04_Production\25029FL97 | N/A | N/A | N/A | 0 | 1 | 1 | 0 | 0 | DROP | na | .40 x 48 x 120 - Bone White - 23008/25029 Alum Sheet, No Grain | Alum Sheet | .40 x 48 x 120 - Bone White - 23008/25029 | No |  |  | 21 | -85 | Ramon Estrada, Shane Watson | Denis Usatenko | Denis Usatenko |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2025-12-15 08:56 | TRUE | 2025-12-23 | 2025-12-15 | TRUE | 2025-12-19 |  | 2025-12-17 |  | 2025-12-17 |  |  | YES | 40 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25029 | FL |  | 97 |  | 97 | 25029-FL97 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 0.25 | 1 | [10 empty] | In House |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2025-12-16 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-12-17 |  | Issue Still in Process | Mitch Chancey - @dbowman@jwmcd.com @swatson@jwmcd.com @tgraves@jwmcd.com LOOSE ON TREE | 1010 |  | Dillon Bowman | Denis Usatenko |  | 25029-FL97 In-House |  | 2025, Week 51
117 | 24057-BM10 |  | Rowan BWI 150 | Intersection of Ballenger Creek Pkwy & Mountville Road Frederick, MD 21703 | Dillon Bowman | 518.860.9477 |  |  | Cleat for FL100 | Cleat for FL100 - See Notes for Dims, |  |  | Q:\Jobs\24057 - Rowan BWI 150\04_Production\24057BM10 | N/A | N/A | N/A |  | 11 |  |  |  | 1.5 |  | 48 x 120 (22g Glav) Galv Sheet, No Grain | Galv Sheet | 48 x 120 (22g Glav) | No |  |  | 11 | -184 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Michael Venable | Denis Usatenko | Michael Venable | [6 empty] | Michael Venable | 2025-07-23 10:10 | TRUE | 2025-07-31 | 2025-07-24 |  | 2025-08-04 |  | 2025-08-06 |  | 2025-08-06 |  |  | YES | 155 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 24057 | BM |  | 10 |  | 10 | 24057-BM10 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 2 | [10 empty] | Hot Shot |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2025-07-29 | 4 | David Hasty | Ramon Estrada, Shane Watson | 2025-08-01 |  | Issue Still in Process |  | 1010 |  | Dillon Bowman | Michael Venable | Denis Usatenko | 24057-BM10 In-House |  | 2025, Week 32
118 | 25025-BM100 |  | QTS MAN1 DC6 | 9540 Godwin Drive Manassas, VA 20110 | Dillon Bowman | 518.860.9477 |  |  | 1/2" Hat Channel - 10ft sticks Downspout Cover - Added Girt for Change Order | Downspout Cover - Added Girt for Change Order | * Sketch |  | Q:\Jobs\25025 - QTS MAN1 DC6\04_Production\25025BM100 | N/A | N/A | N/A | 0 | 870 | 1 | 0 | 0 | 108.75 - SHTS | na | 16g x 48 x 120 Galv Sheet, No Grain | Galv Sheet | 16g x 48 x 120 | No |  |  | Shipped | Shipped | Job Complete | Denis Usatenko | David Hasty |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-02-11 00:46 | TRUE | 2026-02-19 | 2026-02-13 |  | 2026-02-23 |  | 2026-02-25 |  | 2026-02-25 | 2026-02-25 |  | YES | 325 | [19 empty] | Shipped |  | TRUE | [9 empty] | TRUE | [5 empty] | TRUE | [10 empty] | 25025 | BM |  | 100 |  | 100 | 25025-BM100 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 0.5 | 60 | [10 empty] | Hot Shot |  |  |  | Brake Shear |  |  | No Program Requested |  | QC Not Requested | 2026-02-26 | -2 | David Hasty | Ramon Estrada, Shane Watson | 2026-02-25 |  | 0 | Samantha Krantz - Shipped 200 pieces 2-24-26 | 1010 |  | Dillon Bowman | Denis Usatenko |  | 25025-BM100 In-House |  | 2026, Week 09
119 | 24057-FL10 |  | Rowan BWI 150 | Intersection of Ballenger Creek Pkwy & Mountville Road Frederick, MD 21703 | Dillon Bowman | 518.860.9477 |  |  | Bldg D Coping | Bldg D Coping - Material is different that what we have used before. - Dims and Quantities in FD Folder |  |  | Q:\Jobs\24057 - Rowan BWI 150\04_Production\24057FL10 | N/A | N/A | N/A | 0 | 7 | 3 | 0 | 0 | 5 | NA | 42" x 120" 24g Shasta White - 24057 Alum Sheet, No Grain | Alum Sheet | 42" x 120" 24g Shasta White - 24057 | No |  |  | 11 | -184 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Michael Venable | Denis Usatenko | Michael Venable | [6 empty] | Michael Venable | 2025-07-23 09:08 | TRUE | 2025-07-31 | 2025-07-24 |  | 2025-08-04 |  | 2025-08-06 |  | 2025-08-06 |  |  | YES | 14 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 24057 | FL |  | 10 |  | 10 | 24057-FL10 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 2 | [10 empty] | Hot Shot |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2025-07-29 | 4 | David Hasty | Ramon Estrada, Shane Watson | 2025-08-01 |  | Issue Still in Process |  | 1010 |  | Dillon Bowman | Michael Venable | Denis Usatenko | 24057-FL10 In-House |  | 2025, Week 32
120 | 24074-FS06 |  | DIDD ACM | 275 Stewarts Ferry Pike Nashville, TN 37214 | Dillon Bowman | 518.860.9477 | 400 |  | Release 4 - (Part 1 of 2) Pages 207, 208, 209 | ENG - Scan and Notes from Brian in Folder ENG - Josh and I did prelim review, notes from that in FD Folder. | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (216 LF) 1-5/8" Reveals * (16 LF) JR2 * (50 PCS) Corner Clips * (100 PCS) Color Matched Screws | Q:\Jobs\24074 - DIDD ACM\04_Production\24074FS06 | 58.66% | 779 | 1328 | 40 | 40 | 38 | 219 | 216 | 12 | 04:56:48 | 4mm x 62 x 196 - Dark Gray - 24074 FR ACM, No Grain | FR ACM | 4mm x 62 x 196 - Dark Gray - 24074 | No |  | MTPK | 41 | -3 | Ramon Estrada, Shane Watson | Denis Usatenko |  | Chance Dill |  | Chance Dill | Denis Usatenko | Chance Dill |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Chance Dill | 2026-02-09 11:04 |  | 2026-03-26 | 2026-03-26 |  | 2026-04-14 |  | 2026-04-16 |  | 2026-03-30 |  |  | YES | 330 | [5 empty] | MATCH COLOR | YES | Approved As Noted | YES | Q:\Jobs\24074 - DIDD ACM\03_Engineering\02_FD Docs\24074 - FS06 and FS07 and FS08 | YES | Q:\Jobs\24074 - DIDD ACM\03_Engineering\02_FD Docs\24074 - FS06 and FS07 and FS08 | NO | [6 empty] | Ready to Ship | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24074 | FS |  | 06 |  | 6 | 24074-FS10 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 40 | 343 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-03-26 | 2026-03-26 | 1 |  | QC Not Requested | 2026-04-03 | 8 | David Hasty | Ramon Estrada, Shane Watson | 2026-04-14 |  | Issue Still in Process | Mitch Chancey - @dusatenko@jwmcd.com @dbowman@jwmcd.com Still need installs | 1010 |  | Dillon Bowman | Chance Dill | Denis Usatenko | 24074-FS06 In-House |  | 2026, Week 16
121 | 24074-FS07 |  | DIDD ACM | 275 Stewarts Ferry Pike Nashville, TN 37214 | Dillon Bowman | 518.860.9477 | 400 |  | Release 07 - Part 2 of 2 Pages: 214, 216, 217, 245, 246 | ENG - Scan and Notes from Brian in Folder ENG - Josh and I did prelim review, notes from that in FD Folder. | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 * (90 pcs) 2' - 0" x 0' - 10", 1 5/8" Wide reveals | Q:\Jobs\24074 - DIDD ACM\04_Production\24074FS07 |  |  | 1328 | 155 | 218 | 180 | 0 | 0 |  |  | 4mm x 62 x 196 - Dark Gray FR ACM, No Grain | FR ACM | 4mm x 62 x 196 - Dark Gray | No |  | MTPK | 1 | -14 | Arnold Jurado, Issiah Havens | Denis Usatenko |  | Chance Dill |  | Chance Dill | Denis Usatenko | Chance Dill |  | Arnold Jurado, Issiah Havens |  |  |  |  | Chance Dill | 2026-02-09 11:10 |  | 2026-03-30 |  |  |  |  | 2026-04-20 |  | 2026-04-06 |  |  | YES | 330 | [5 empty] | MATCH COLOR | YES | Approved As Noted | YES | Q:\Jobs\24074 - DIDD ACM\03_Engineering\02_FD Docs\24074 - FS06 and FS07 | YES | Q:\Jobs\24074 - DIDD ACM\03_Engineering\02_FD Docs\24074 - FS06 and FS07 | NO | [6 empty] | CNC Programming | TRUE | TRUE | TRUE | AXYZ Titans Line | [6 empty] | TRUE | [13 empty] | TRUE | TRUE |  |  | 24074 | FS |  | 07 |  | 7 | 24074-FS10 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 50 | 385 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab Roller | 2026-04-16 |  | 1 (In Progress) |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - @cdill@jwmcd.com Corrections required. | 1010 |  | Dillon Bowman | Chance Dill | Denis Usatenko | 24074-FS07 In-House |  | 2026, Week 17
122 | 24051-FS16C |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | SOUTH LEVEL 300 COPING FOR FS 16. PLEASE STORE NEXT TO FS 16 SO THE DETAIL CAN BE SHIPPED COMPLETE WHEN NEEDED. |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (300 LF) 1-5/8" Reveals﻿ * ( 106 pcs) Corner Clips * ( 212 pcs ) Color Matching Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS16C | 65.51% | 12623 | 19268 | 27 | 27 | 2 | 189 | 300 | 3 | 02:45:09 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 71 | -48 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Ailen Niedfeld |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Ailen Niedfeld | 2025-12-18 15:39 |  | 2026-01-19 | 2026-01-23 | TRUE | 2026-02-10 |  | 2026-02-09 |  | 2026-02-09 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans |  | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 16C |  | 0 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 40 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-01-23 | 2026-01-23 | 1 |  | QC Not Requested | 2026-02-23 | 6 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-02 |  | Issue Still in Process | Issiah Havens - @aniedfeld@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS16C In-House |  | 2026, Week 07
123 | 24079-BM04C |  | Nashville Youth Campus | 1354 Brick Church Pike Nashville, TN 37207 | Joe Hoyle | 828.334.7808 |  |  | 1-1/2" AFC sub-framing. Hole required for powder-coating. | 3600 1-1/2" zees @ 10'. Include hole for hanging/powder. AFC sub-framing for half the podium. 1-1/2" x 1-1/2" x 1-1/2" |  | TBD | Q:\Jobs\24079 - Nashville Youth Campus\04_Production\24079BM04C | N/A | N/A | N/A | 0 | 3600 | 1 | 0 | 0 | 328 | 06:00:48 | 48" x 120" - 16 ga Steel Sheet, No Grain | Steel Sheet | 48" x 120" - 16 ga | No |  |  | 1 | -43 | Samantha Krantz, Shane Jones | Denis Usatenko | David Hasty |  |  | Jonathan Dorsey | David Hasty | Jonathan Dorsey |  |  |  | Chris Gambrel | TRUE |  | Jonathan Dorsey | 2026-01-15 09:13 |  | 2026-02-10 | 2026-02-03 |  | 2026-02-17 | 2026-02-05 | 2026-02-19 |  | 2026-02-19 |  |  | NO |  | 2026-01-23 | TRUE | Powder Coat | Matte Black PowderWorx Jason Makuch jmakuch@pwx615.com | Coating Ship To Site | [14 empty] | Shear |  | TRUE | [6 empty] | TRUE | 7000 TruMatic |  | TRUE | [5 empty] | TRUE | [10 empty] | 24079 | BM |  | 04C |  | 0 | 24079-BM00 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 40 | [10 empty] | In House |  |  | Punch | 7000 TruMatic Brake Powder Coat Shear | 2026-01-23 | 2026-01-29 | 5 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Chris Gambrel - @jdorsey@jwmcd.com @dhasty@jwmcd.com flat programs completed. | 1010 |  | Joe Hoyle | Jonathan Dorsey | David Hasty | 24079-BM04C In-House | TRUE | 2026, Week 08
124 | 24079-FL07 |  | Nashville Youth Campus | 1354 Brick Church Pike Nashville, TN 37207 | Joe Hoyle | 828.334.7808 |  |  | *ACM Flashings for FS102. To be shipped together ﻿*USE THE LONG DROPS FOR THE SPLICE-PLATES [YOU CAN LEAVE THEM AT 8"] | TO MATCH FL05. FL05 SKETCH FOUND IN FD DOCS FOLDER. Please provide open hem with 6" splice. (Part QTY includes splice. 110 sticks @ 10' + 110 splice at 6") | * SKETCHES | TBD | Q:\Jobs\24079 - Nashville Youth Campus\04_Production\24079FL07 | N/A | N/A | N/A | 0 | 220 | 2 | 0 | 0 | 22 - SHTS | NA | .032" Alum. 48" x 120", CWM Cloud White Matte Alum Sheet, Grain | Alum Sheet | .032" Alum. 48" x 120", CWM Cloud White Matte | Yes |  |  | 31 | -43 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-01-29 15:05 |  | 2026-02-10 | 2026-02-03 |  | 2026-02-17 |  | 2026-02-19 |  | 2026-02-19 |  |  | YES | 138 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 24079 | FL |  | 07 |  | 7 | 24079-FL14 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 6 | [10 empty] | Customer Pick Up In House |  |  |  | Cidan Shear |  |  | No Program Requested |  | Issue Still In Process |  | Crating Start Date Not Recorded | David Hasty | Ramon Estrada, Shane Watson | 2026-02-06 |  | Issue Still in Process |  | 1010 |  | Joe Hoyle | Denis Usatenko |  | 24079-FL07 In-House |  | 2026, Week 08
125 | 24079-FL08 |  | Nashville Youth Campus | 1354 Brick Church Pike Nashville, TN 37207 | Joe Hoyle | 828.334.7808 |  |  | *AFC Flashings for FS02. ﻿*SPLICES CAN BE LONGER | TO MATCH FL04. FL04 SKETCH FOUND IN FD DOCS FOLDER. Please provide open hem with 6" splice. (Part QTY includes splice. 80 sticks @ 10' + 80 splice at 6") | * SKETCHES | TBD | Q:\Jobs\24079 - Nashville Youth Campus\04_Production\24079FL08 | N/A | N/A | N/A | 0 | 160 | 2 | 0 | 0 | 22 - SHTS | NA | .032" x 48" x 120", BNT White Alum Sheet, No Grain | Alum Sheet | .032" x 48" x 120", BNT White | No |  |  | 31 | -43 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-01-29 15:17 |  | 2026-02-10 | 2026-02-03 |  | 2026-02-17 |  | 2026-02-19 |  | 2026-02-19 |  |  | YES | 23 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 24079 | FL |  | 08 |  | 8 | 24079-FL14 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 6 | [10 empty] | Customer Pick Up In House |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2026-02-05 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-02-06 |  | Issue Still in Process |  | 1010 |  | Joe Hoyle | Denis Usatenko |  | 24079-FL08 In-House |  | 2026, Week 08
126 | 24079-FL09 |  | Nashville Youth Campus | 1354 Brick Church Pike Nashville, TN 37207 | Joe Hoyle | 828.334.7808 |  |  | AFC flashings for FS01 - AFC to Mullion = TBX Silver | TO MATCH FL03. FL03 SKETCH FOUND IN FD DOCS FOLDER. FOLLOW COMMENTS AND DIMENSIONS ON THE PDF. Please provide open hem with 6" splice ONLY ON JAMB TRIM (3" x 3-1/2" ANGLE). | * SKETCHES |  | Q:\Jobs\24079 - Nashville Youth Campus\04_Production\24079FL09 | N/A | N/A | N/A | 0 | 295 | 3 | 0 | 0 | 43.75 - SHTS | NA | .032" x 48" x 120", TBX Silver Alum Sheet, Grain | Alum Sheet | .032" x 48" x 120", TBX Silver | Yes |  |  | 31 | -43 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-01-29 15:31 |  | 2026-02-10 | 2026-02-03 |  | 2026-02-17 |  | 2026-02-19 |  | 2026-02-19 |  |  | YES | 59 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 24079 | FL |  | 09 |  | 9 | 24079-FL14 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 8 | [10 empty] | Customer Pick Up In House |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2026-02-09 | 24 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-12 |  | Issue Still in Process |  | 1010 |  | Joe Hoyle | Denis Usatenko |  | 24079-FL09 In-House |  | 2026, Week 08
127 | 24081-FL01 |  | DLR DFW37 | 1502 Ferris Rd Garland, TX 75044 | Cole Norona | 931.591.9340 |  |  | Write the part number in marker on the NON PAINTED side for post painter-NO STICKERS | RED Notes are for Engineering. BLUE notes are for Post Painter. Splice plates needed for profile 201A For profile 201A, a 3/4" tab is needed for Post Painter. This job is released off our guaranteed dimensions. (7) 104 @ 10' (18) 105 @ 10' (10) 108 @ 10' (22) 202A @ 10' (22) 202B @ 10' (12) 203 @ 10' (8) 204 @ 10' (7) 205A @ 10' (12) 206 @ 10' | SKETCHES |  | Q:\Jobs\24081 - DLR DFW37\04_Production\24081-FL01 | N/A | N/A | N/A | 0 | 118 | 9 | 0 | 0 | 21 | N/A | .040" X 48" X 120"; 3003 Alum Sheet, No Grain | Alum Sheet | .040" X 48" X 120"; 3003 | No |  |  | 1 | -42 | Ramon Estrada, Shane Watson | Denis Usatenko | David Hasty |  |  | Frank Dean | David Hasty | Frank Dean |  |  | Chris Gambrel |  |  |  | Frank Dean | 2026-01-30 08:23 |  | 2026-02-11 | 2026-02-12 | TRUE | 2026-02-18 | 2026-02-20 | 2026-02-20 |  | 2026-02-20 |  | 2026-02-25 | YES | 64 |  | TRUE | Post Paint | Air Performance 159 Genco Drive Hartford, AL 36344 Attn: Jake Faundez 941.718.2839 jfaundez@airperformancellc.com | Coating Ship To Site | [14 empty] | Shipped To Painter |  | TRUE | [9 empty] | TRUE | [5 empty] | TRUE | [10 empty] | 24081 | FL |  | 01 |  | 1 | 24081-FL02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 25 | [10 empty] | Hot Shot |  |  |  | Brake Post Paint Shear |  |  | No Program Requested |  | QC Not Requested | 2026-02-18 | 4 | David Hasty | Ramon Estrada, Shane Watson | 2026-02-23 |  | Issue Still in Process | David Hasty - @fdean@jwmcd.com corrections required | 1010 |  | Cole Norona | Frank Dean | David Hasty | 24081-FL01 In-House | TRUE | 2026, Week 08
128 | 25017-ST02 |  | Nashville Yards Park | Nashville, TN 37203 | Dillon Bowman | 518.860.9477 | CUSTOM ARCH |  | Additional Support Steel |  | SKETCHES PROGRAM FILES |  | Q:\Jobs\25017 - Nashville Yards Park\04_Production\25017ST02 | N/A | N/A | N/A | 0 | 16 | 1 | 0 | 0 | 8 (DROP 130X48) | 00:08:52 | SS SHEET 11g 304-DROP (FROM PROCESSING) SS Sheet, No Grain | SS Sheet | SS SHEET 11g 304-DROP (FROM PROCESSING) | No |  |  | 1 | -54 | Rogerson Jean-Charles, Sean Doss | David Hasty | David Hasty |  |  | Jonathan Dorsey | David Hasty | Jonathan Dorsey |  |  | Chris Gambrel |  | TRUE |  |  | 2026-01-13 10:54 | TRUE | 2026-02-03 | 2026-01-15 | TRUE | 2026-02-02 |  | 2026-01-20 |  | 2026-01-20 |  |  | YES | [8 empty] | N/A (Process Customer Provided Blanks) | NO |  | NO |  | NO | [6 empty] | QC | [5 empty] | TRUE |  | TruLaser 3040 | [9 empty] | TRUE | [10 empty] | 25017 | ST |  | 02 |  | 2 | 25017-ST02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 4 | [10 empty] | In House |  |  | Flat Laser | Brake TruLaser 3040 | 2026-01-15 | 2026-01-15 | 1 | 2026-01-28 | 57 (In Progress) |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Chris Gambrel - @fdean@jwmcd.com @dhasty@jwmcd.com @jdorsey@jwmcd.com flat program completed | 1010 |  | Dillon Bowman | Jonathan Dorsey | David Hasty | 25017-ST02 In-House | TRUE | 2026, Week 04
129 | 24051-FS25 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | NORTH ELEVATION 300 INSTALL DIRECTION RIGHT TO LEFT |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS25 | 40.14% | 7735 | 19268 | 50 | 50 | 4 | 415 | 560 | 196 X 62 - 13 | 06:39:04 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 10 | -231 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-04-04 14:12 |  | 2025-05-12 | 2025-04-15 |  | 2025-05-29 |  | 2025-06-02 |  | 2025-06-02 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 25 |  | 25 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 100 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-04-14 | 2025-04-14 | 1 |  | QC Not Requested | 2025-06-02 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-02 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS25 In-House |  | 2025, Week 23
130 | 24051-FS10C |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | Release Notes COPING FOR SOUTH LEVEL 7 - TO SHIP WITH THE BALANCE OF THE AREA PANELS. |  |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS10C | 43.52% | 8385 | 19268 | 160 | 160 | 2 | 1120 | 800 | 196 X 62 - 32 | 19:19:02 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 24 | -208 | Unassigned | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-05-05 08:59 |  | 2025-06-12 | 2025-05-07 |  | 2025-07-01 |  | 2025-07-03 |  | 2025-07-03 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 10C |  | 0 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-05-06 | 2025-05-07 | 2 |  | QC Not Requested | 2025-06-17 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-18 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed, paneltracker | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS10C In-House |  | 2025, Week 27
131 | 24051-FS11 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | South Elevation 700 level. Install Direction Left to Right |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS11 | 31.25% | 6022 | 19268 | 160 | 160 | 2 | 740 | 1050 | 196 X 62 - 15 | 12:11:07 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 5 | -249 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-03-21 05:35 |  | 2025-04-16 | 2025-03-27 |  | 2025-05-05 |  | 2025-05-07 |  | 2025-05-07 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 11 |  | 11 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-03-26 | 2025-03-27 | 2 |  | QC Not Requested | 2025-05-06 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-05-07 |  | Issue Still in Process | Samantha Krantz - Reveals done 4-21-25 | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS11 In-House |  | 2025, Week 19
132 | 24051-FS12 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | South Elevation 700 level. Install Direction Left to Right |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS12 | 32.08% | 6182 | 19268 | 160 | 160 | 4 | 1113 | 1830 | 196 X 62 - 45 | 21:45:18 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 6 | -244 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-03-21 05:37 |  | 2025-04-23 | 2025-03-27 |  | 2025-05-12 |  | 2025-05-14 |  | 2025-05-14 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 12 |  | 12 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-03-26 | 2025-03-27 | 2 |  | QC Not Requested | 2025-05-10 | 3 | David Hasty | Ramon Estrada, Shane Watson | 2025-05-14 |  | Issue Still in Process | Samantha Krantz - Reveals done 4-21-25 | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS12 In-House |  | 2025, Week 20
133 | 24051-FS13 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | Level 400 Install Direction Left to Right |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS13 | 32.66% | 6292 | 19268 | 110 | 110 | 2 | 660 | 1450 | 196 X 62 - 28 | 14:11:46 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 7 | -241 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-03-21 14:26 |  | 2025-04-28 | 2025-03-27 |  | 2025-05-15 |  | 2025-05-19 |  | 2025-05-19 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 13 |  | 13 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-03-27 | 2025-03-27 | 1 |  | QC Not Requested | 2025-05-15 | 3 | David Hasty | Ramon Estrada, Shane Watson | 2025-05-19 |  | Issue Still in Process | Samantha Krantz - Reveals done 4-30-25 | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS13 In-House |  | 2025, Week 21
134 | 24051-FS13C |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | COPING FOR SOUTH LEVEL 400 |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (600 LF) 1-5/8" Reveals | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS13C | 74.2% | 14297 | 19268 | 106 | 106 | 2 | 742 | 600 | 11 | 10:50:09 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 91 | -20 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2026-02-05 11:25 |  | 2026-02-27 | 2026-03-04 | TRUE | 2026-03-20 |  | 2026-03-20 |  | 2026-03-20 |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 13C |  | 0 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-03-04 | 2026-03-04 | 1 |  | QC Not Requested | 2026-03-19 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-19 |  | Issue Still in Process | Issiah Havens - @dusatenko@jwmcd.com @jdavis@jwmcd.com programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS13C In-House |  | 2026, Week 12
135 | 24051-FS74 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | SOUTH LEVEL 300 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (450 LF) 1-5/8" Reveals * (150 LF) 1-1/8" Reveals * (120 LF) JR2 | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS74 | 67.55% | 13015 | 19268 | 39 | 39 | 6 | 288 | 600 | 39 SHEETS | 00d07h57m00s | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 81 | -34 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-12-18 15:11 |  | 2026-01-12 | 2026-02-12 | TRUE | 2026-03-02 |  | 2026-02-02 |  | 2026-02-02 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 74 |  | 74 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 24 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab | 2026-02-11 | 2026-02-12 | 2 |  | QC Not Requested | 2026-03-19 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-19 |  | Issue Still in Process | Arnold Jurado - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS74 In-House |  | 2026, Week 06
136 | 24051-FS75 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | SOUTH LEVEL 50 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( 900 LF) 1-5/8" Reveals * ( 120 LF) JR-EXTENDED | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS75 | 67.98% | 13098 | 19268 | 83 | 83 | 22 | 487 | 900 | 82 sheets | 00d16h04m17s | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 81 | -34 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2026-01-12 10:58 | TRUE | 2026-02-02 | 2026-02-12 | TRUE | 2026-03-02 |  | 2026-02-13 |  | 2026-02-13 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 75 |  | 75 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 24 | 160 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab | 2026-02-11 | 2026-02-12 | 2 |  | QC Not Requested | 2026-03-14 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-16 |  | Issue Still in Process | Arnold Jurado - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS75 In-House |  | 2026, Week 07
137 | 24051-FS76 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | LEVEL 300 EAST ELEVATION | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (2000 LF) 1-5/8" Reveals * (200 LF) 1-1/8" Reveals﻿ * (200 LF) JR2 | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS76 | 68.77% | 13250 | 19268 | 152 | 152 | 6 | 1032 | 2200 | 152 SHEETS | 01d07h03m12s | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 81 | -34 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-12-19 11:43 |  | 2026-01-19 | 2026-02-12 | TRUE | 2026-03-02 |  | 2026-02-09 |  | 2026-02-09 |  |  | YES | 750 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans |  | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 76 |  | 76 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab | 2026-02-11 | 2026-02-12 | 2 |  | QC Not Requested | 2026-03-18 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-19 |  | Issue Still in Process | Mitch Chancey - 1 REMAKE 3/19/25 | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS76 In-House |  | 2026, Week 07
138 | 24051-FS52C |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS | EAST LEVEL 300 COPING | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | 2 SETS - INSTALL DRAWINGS 350 LF - 1 5/8" REVEALS TO MATCH 150 pcs - Corner Clips 300 pcs﻿ - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS52C | 57.5% | 11080 | 19268 | 70 | 70 | 3 | 490 | 350 | 7 SHEETS | 00d07h07m58s | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 62 | -70 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-21 11:03 |  | 2025-12-23 | 2025-12-04 |  | 2026-01-09 |  | 2026-01-13 |  | 2026-01-13 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 52C |  | 0 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 140 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-12-04 | 2025-12-04 | 1 |  | QC Not Requested | 2026-01-10 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-01-13 |  | Issue Still in Process | Arnold Jurado - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS52C In-House |  | 2026, Week 03
139 | 24051-FS53 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS ﻿EVERY CRATE REQUIRES JR2 | EAST LEVEL 200 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * 600 LF - 1 5/8" REVEALS TO MATCH * 200 LF - 1 1/8" REVEALS TO MATCH * 140 LF - JR2 | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS53 | 61.94% | 11934 | 19268 | 48 | 48 | 6 | 350 | 800 | 46 | 09:47:09 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 64 | -64 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-21 14:42 |  | 2025-12-31 | 2025-12-12 |  | 2026-01-19 |  | 2026-01-21 |  | 2026-01-21 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 53 |  | 53 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 80 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-12-11 | 2025-12-12 | 2 |  | QC Not Requested | 2026-01-15 | 5 | David Hasty | Ramon Estrada, Shane Watson | 2026-01-21 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS53 In-House |  | 2026, Week 04
140 | 24051-FS52 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS EVERY CRATE REQUIRES PR2 | EAST LEVEL 300 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | 2 SETS - INSTALL DRAWINGS 1200 LF - 1 5/8" REVEALS TO MATCH 700 LF - 1 1/8" REVEALS TO MATCH 330 LF - JR2 450 pcs - Corner Clips 900 pcs﻿ - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS52 | 58.59% | 11290 | 19268 | 210 | 210 | 9 | 1442 | 1900 | 59 SHEETS | 01d04h25m04s | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 62 | -70 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-21 10:58 |  | 2025-12-23 | 2025-12-04 |  | 2026-01-09 |  | 2026-01-13 |  | 2026-01-13 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 52 |  | 52 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 12 | 320 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-12-04 | 2025-12-04 | 1 |  | QC Not Requested | 2026-01-12 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-01-13 |  | Issue Still in Process | Arnold Jurado - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS52 In-House | TRUE | 2026, Week 03
141 | 24051-FS216 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS | NORTH ELEVATION LEVEL 200 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | 2 SETS - INSTALL DRAWINGS 150 LF - 1 5/8" REVEALS TO MATCH 130 LF - JR2 110 pcs - Corner Clips 220 pcs - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS216 | 52.68% | 10151 | 19268 | 26 | 26 | 3 | 225 | 150 | 9 | 03:56:14 | Alpolic - 4mm - 880 pcs - [62 X 196] - MOONSTONE METALLIC FR ACM, Grain | FR ACM | Alpolic - 4mm - 880 pcs - [62 X 196] - MOONSTONE METALLIC | Yes |  |  | 45 | -106 | Unassigned | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-15 15:56 | TRUE | 2025-11-05 | 2025-10-30 |  | 2025-11-20 |  | 2025-11-24 |  | 2025-11-24 |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 216 |  | 216 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 40 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-10-29 | 2025-10-29 | 1 |  | QC Not Requested | 2025-11-15 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-11-17 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS216 In-House |  | 2025, Week 48
142 | 24030-FL02 |  | Vantage TX-21 | 3800 Wiseman Blvd San Antonio, TX 78251 | Chris Buttrey | 615.517.9885 |  |  | * Ships with FL01 and BM02 | Profiles 301 and 306, Qtys listed on file. 10ft lengths Material is on hold currently from Fabral, expected by new years | * SKETCHES |  | Q:\Jobs\24030 - Vantage TX-21\04_Production\24030FL02 | N/A | N/A | N/A | 0 | 265 | 3 | 0 | 0 | 53.75 - SHT | na | 0.040, 48x120 Bone White﻿ [24030] Alum Sheet, No Grain | Alum Sheet | 0.040, 48x120 Bone White﻿ [24030] | No |  |  | 4 | -57 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2025-11-03 15:01 |  | 2026-01-21 | 2025-11-17 |  | 2026-01-28 |  | 2026-01-30 |  | 2026-01-30 |  |  | NO | 60 | 2026-01-02 | [18 empty] | Partially Shipped |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 24030 | FL |  | 02 |  | 2 | 24030-FL02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 32 | [10 empty] | Semi |  |  |  | Cidan Shear |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Mitch Chancey - crate #1 out 1/30/26 | 1010 |  | Chris Buttrey | Denis Usatenko |  | 24030-FL02 In-House | TRUE | 2026, Week 05
143 | 24051-FS25.1 FM |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | PLEASE PUT THIS PANEL IN FS25 OR CRATE AND PUT ON TOP IF POSSIBLE. THESE PANELS WILL SHIP WITH 25. | NORTH LEVEL 300 FM DIMENSIONS | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (8 LF) 1-5/8" Reveals * ( 3 pcs) Corner Clips * ( 6 pcs ) Color Matching Screws﻿ * ( 8 LF) JR2 | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS25.1 | 65.52% | 12625 | 19268 | 2 | 2 | 2 | 16 | 8 | 1 | 00:12:40 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 71 | -48 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Ailen Niedfeld |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Ailen Niedfeld | 2025-12-18 11:28 |  | 2026-01-15 | 2026-01-23 | TRUE | 2026-02-10 |  | 2026-02-05 |  | 2026-02-05 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 25.1 FM |  | 0 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 1 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-01-23 | 2026-01-23 | 1 |  | QC Not Requested | 2026-02-02 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-02-03 |  | Issue Still in Process | Issiah Havens - @aniedfeld@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS25.1 FM In-House |  | 2026, Week 06
144 | 24051-FS26 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | NORTH LEVEL 300 RIGHT TO LEFT INSTALL |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS26 | 41.02% | 7904 | 19268 | 169 | 169 | 4 | 1183 | 1800 | 196 X 62 - 81 | 26:42:30 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 10 | -231 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-04-04 14:16 |  | 2025-05-12 | 2025-04-15 |  | 2025-05-29 |  | 2025-06-02 |  | 2025-06-02 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 26 |  | 26 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-04-14 | 2025-04-14 | 1 |  | QC Not Requested | 2025-06-02 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-06-02 |  | Issue Still in Process | Marc Ribar - @mchancey@jwmcd.com @swatson@jwmcd.com I show this release has shipped in 3 deliveries from 8-15 to 9-29. Please confirm | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS26 In-House |  | 2025, Week 23
145 | 24051-FS26C |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | NORTH LEVEL 300 COPING RELEASE | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (200 LF) 1-5/8" Reveals | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS26C | 74.34% | 14323 | 19268 | 26 | 26 | 3 | 182 | 200 | 3 | 02:40:59 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 91 | -20 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2026-02-02 09:22 |  | 2026-02-23 | 2026-03-04 | TRUE | 2026-03-20 |  | 2026-03-16 |  | 2026-03-16 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 26C |  | 0 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 40 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-03-04 | 2026-03-04 | 1 |  | QC Not Requested | 2026-03-15 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-16 |  | Issue Still in Process | Issiah Havens - @dusatenko@jwmcd.com @jdavis@jwmcd.com programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS26C In-House |  | 2026, Week 12
146 | 24051-FS45C |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS | COPING FOR FS 45 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | 2 SETS - INSTALL DRAWINGS 180 LF - 1 5/8" REVEALS TO MATCH 110 pcs - Corner Clips 220 pcs - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS45C | 53.22% | 10255 | 19268 | 26 | 26 | 3 | 186 | 180 | 3 | 02:41:17 | Alpolic - 4mm - 3600 pcs - [62 X 196] - TOB BLACK FR ACM, No Grain | FR ACM | Alpolic - 4mm - 3600 pcs - [62 X 196] - TOB BLACK | No |  |  | 47 | -103 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-24 11:28 | TRUE | 2025-11-14 | 2025-11-07 | TRUE | 2025-11-25 |  | 2025-11-17 |  | 2025-11-17 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 45C |  | 0 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 40 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-11-06 | 2025-11-06 | 1 |  | QC Not Requested | 2025-11-10 | 5 | David Hasty | Ramon Estrada, Shane Watson | 2025-11-14 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS45C In-House | TRUE | 2025, Week 47
147 | 24051-FS46 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EVERY CRATE REQUIRES REVEALS EVERY CRATE REQUIRES JR2 | SOUTH LEVEL 200 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | 2 SETS - INSTALL DRAWINGS 350 LF - 1 5/8" REVEALS TO MATCH 200 LF - 1 1/8" REVEALS TO MATCH 140 LF - JR2 150 pcs - Corner Clips 300 pcs - Color Matched Screws | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS46 | 54.26% | 10454 | 19268 | 75 | 75 | 6 | 465 | 350 | 16 SHEETS | 00d09h25m21s | Alpolic - 4mm - 3600 pcs - [62 X 196] - TOB BLACK FR ACM, No Grain | FR ACM | Alpolic - 4mm - 3600 pcs - [62 X 196] - TOB BLACK | No |  |  | 52 | -96 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-10-16 10:26 |  | 2025-11-17 | 2025-11-10 |  | 2025-12-04 |  | 2025-12-08 |  | 2025-12-08 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 46 |  | 46 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 150 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-11-06 | 2025-11-07 | 2 |  | QC Not Requested | 2025-12-04 | 3 | David Hasty | Ramon Estrada, Shane Watson | 2025-12-08 |  | Issue Still in Process | Arnold Jurado - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS46 In-House | TRUE | 2025, Week 50
148 | 24019-RO07 |  | QTS PJC1 DC1 | 159 Princeton Hightstown Rd. East Windsor, NJ 08520 | Dillon Bowman | 518.860.9477 | 400 |  | Freedom Wall Remakes SHIP THEM FLAT!! PLEASE DO NOT ASSEMBLE﻿!! | Freedom Wall Remakes We will cut, route and then ship them flat. Please do not assemble. | * SKETCHES * CUT LIST * COLOR LABELS * CODING FILES * EXTRUSION LIST | * 15 LF 1 5/8" COLOR MATCHING REVEALS * 8 PCS CORNER CLIPS * 48 COLOR MATCHING SCREWS | Q:\Jobs\24019 - QTS PJC1 DC1\04_Production\24019RO07 | 47.88% | 824 | 1721 | 4 | 4 | 4 | 24 | 15 | 2 SHEETS | 00d00h30m08s | 4mm x 62 x 196 - Ron Red - 25025 FR ACM, No Grain | FR ACM | 4mm x 62 x 196 - Ron Red - 25025 | No |  |  | 28 | -53 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Gabriela Herrera | Denis Usatenko | Gabriela Herrera |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Gabriela Herrera | 2026-01-14 05:56 | TRUE | 2026-02-04 | 2026-01-16 | TRUE | 2026-02-03 |  | 2026-01-21 |  | 2026-01-21 |  |  | YES | 109 | [5 empty] | MATCH COLOR | YES | Approved As Noted | NO |  | NO |  | NO |  | 215-3Z10* 215-3Z41* 215-3Z26* 215-3Z43* w/ minor changes | 24019 FS06 |  |  |  | Ready to Ship |  | TRUE | TRUE | [21 empty] | TRUE |  |  |  | 24019 | RO |  | 07 |  | 7 | 24019-RO07 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 3 | [10 empty] | Hot Shot |  |  | AXYZ | AXYZ Clean and Brake | 2026-01-15 | 2026-01-15 | 1 |  | Issue Still In Process |  | Crating Start Date Not Recorded | David Hasty | Ramon Estrada, Shane Watson | 2026-01-20 |  | Issue Still in Process | Arnold Jurado - @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Dillon Bowman | Gabriela Herrera | Denis Usatenko | 24019-RO07 In-House |  | 2026, Week 04
149 | 24020-FL07 |  | QTS ATL2 DC2 Osgood | 1435 Hwy 54 W Fayetteville, GA 30214 | Dillon Bowman | 518.860.9477 | --- |  | Punch Flashing | Punch Flashing |  |  | Q:\Jobs\24020 - QTS ATL2 Osgood\04_Production\24020FL07 | 76.45% | 224 | 293 | 2 | 2 | 1 | 0 | 0 | 0.33 | na | 48 x 120 22g Galv Sheet, No Grain | Galv Sheet | 48 x 120 22g | No |  |  | 10 | -192 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2025-07-17 10:36 | TRUE | 2025-07-25 | 2025-07-17 | TRUE | 2025-07-23 |  | 2025-07-18 |  | 2025-07-18 |  |  | YES | 176 | [5 empty] | N/A | NO | N/A (Process Customer Provided Blanks) | NO |  | NO |  | NO |  | FL06 Profile 1/1 | 24020 - FL06 |  | FIELD DIMENSION/SCAN |  | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 24020 | FL |  | 07 |  | 7 | 24020-FL07 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 1 | [10 empty] | Hot Shot |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2025-07-17 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2025-07-17 |  | Issue Still in Process | Mitch Chancey - @dbowman@jwmcd.com @tgraves@jwmcd.com @swatson@jwmcd.com loose on the tree | 1010 |  | Dillon Bowman | Denis Usatenko |  | 24020-FL07 In-House |  | 2025, Week 29
150 | 24051-FS14 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | Level 400 Install Direction Left to Right |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS14 | 33.23% | 6402 | 19268 | 110 | 110 | 2 | 490 | 550 | 196 X 62 - 8 | 08:02:54 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 8 | -239 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-03-21 14:31 |  | 2025-04-30 | 2025-03-27 |  | 2025-05-19 |  | 2025-05-21 |  | 2025-05-21 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans |  | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 14 |  | 14 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 200 | [13 empty] | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-03-27 | 2025-03-27 | 1 |  | QC Not Requested | 2025-05-17 | 3 | David Hasty | Ramon Estrada, Shane Watson | 2025-05-21 |  | Issue Still in Process | Samantha Krantz - Reveals done 4-30-25 | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS14 In-House |  | 2025, Week 21
151 | 24051-FS15 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | Level 400 Install Direction Left to Right |  |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS15 | 33.8% | 6512 | 19268 | 110 | 110 | 2 | 880 | 1680 | 196 X 62 - 37 | 18:38:45 | 4MM FR CORE TOB BLACK 62 X 196 FR ACM, No Grain | FR ACM | 4MM FR CORE TOB BLACK 62 X 196 | No |  |  | 9 | -238 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-03-21 14:39 |  | 2025-05-01 | 2025-03-27 |  | 2025-05-20 |  | 2025-05-22 |  | 2025-05-22 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans |  | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 15 |  | 15 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2025-03-27 | 2025-03-27 | 1 |  | QC Not Requested | 2025-05-21 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-05-22 |  | Issue Still in Process | Samantha Krantz - Reveals done 4-30-25 | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS15 In-House |  | 2025, Week 21
152 | 24051-FS225 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | WET FIELD MEASURES LEVEL 150 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 19268 | 26 | [6 empty] | 4mm X 62" X 196", MOONSTONE METALLIC FR ACM, Grain | FR ACM | 4mm X 62" X 196", MOONSTONE METALLIC | Yes |  |  | 1 | -39 | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  |  |  | Hennadii Stakhurskyi | 2026-02-02 15:29 |  | 2026-02-23 |  |  |  |  | 2026-03-16 |  | 2026-03-16 |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | LO |  |  |  | AXYZ Titans Line | [24 empty] | 24051 | FS |  | 225 |  | 225 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 8 | [10 empty] | In House | [6 empty] | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Paul J Roberts - @hstakhurskyi@jwmcd.com Marc is looking for this in the shop, when can this be done and released? @dusatenko@jwmcd.com | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS225 In-House |  | 2026, Week 12
153 | 24046-FL12 |  | UAB Biomedical Research and Psycholgy | 1500 University Blvd Birmingham, AL 35233 | Wylie McDougall | 615.426.7650 |  |  | Please crate all profiles together. Do not crate with FL13. 2 separate parts of the building. |  |  |  | \\jw-vm-ashop\ASHOP_DATA\Jobs\24046 - UAB Biomedical Research\04_Production\24046FL12 | N/A | N/A | N/A |  | 119 | 3 | 0 | 0 | 12.5 | na | .032" X 48" X 120", Cityscape Alum Sheet, No Grain | Alum Sheet | .032" X 48" X 120", Cityscape | No |  |  | 17 | -155 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2025-09-03 08:05 | TRUE | 2025-09-11 | 2025-09-03 |  | 2025-09-12 |  | 2025-09-16 |  | 2025-09-16 |  |  | YES | 23 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 24046 | FL |  | 12 |  | 12 | 24046-FL13 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 2 | 7 | [10 empty] | Hot Shot |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2025-09-08 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-09-09 |  | Issue Still in Process |  | 1010 |  | Wylie McDougall | Denis Usatenko |  | 24046-FL12 In-House |  | 2025, Week 38
154 | 24046-FL13 |  | UAB Biomedical Research and Psycholgy | 1500 University Blvd Birmingham, AL 35233 | Wylie McDougall | 615.426.7650 | [6 empty] | \\jw-vm-ashop\ASHOP_DATA\Jobs\24046 - UAB Biomedical Research\04_Production\24046FL13 | N/A | N/A | N/A | 0 | 53 | 3 | 0 | 0 | 8.25 | na | 0.032" X 48" X 120", Cityscape Alum Sheet, No Grain | Alum Sheet | 0.032" X 48" X 120", Cityscape | No |  |  | 17 | -155 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2025-09-03 08:08 | TRUE | 2025-09-11 | 2025-09-03 |  | 2025-09-12 |  | 2025-09-16 |  | 2025-09-16 |  |  | YES | 23 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 24046 | FL |  | 13 |  | 13 | 24046-FL13 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 6 | 7 | [10 empty] | Hot Shot |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2025-09-08 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2025-09-09 |  | Issue Still in Process |  | 1010 |  | Wylie McDougall | Denis Usatenko |  | 24046-FL13 In-House |  | 2025, Week 38
155 | 24051-FS77 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | EAST LEVEL 300 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (1400 LF) 1-5/8" Reveals * (500 LF) 1-1/8" Reveals﻿ * (180 LF)﻿ - JR2 ﻿* (180 LF)﻿ - JR-EXTENDED | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS77 | 69.85% | 13459 | 19268 | 209 | 209 | 14 | 1432 | 1900 | 74 SHEETS | 01d04h46m48s | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 81 | -34 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-12-19 16:11 |  | 2026-01-19 | 2026-02-12 | TRUE | 2026-03-02 |  | 2026-02-09 |  | 2026-02-09 |  |  | YES | 750 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 77 |  | 77 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 24 | 400 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab | 2026-02-11 | 2026-02-11 | 1 |  | QC Not Requested | 2026-03-20 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-23 |  | Issue Still in Process | Arnold Jurado - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS77 In-House |  | 2026, Week 07
156 | 24051-FS78 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | TRELLIS ON SOUTH 1. PANELS ARE TO BE MADE WITHOUT CUT OUT FOR THE BEAMS. THESE WILL BE FIELD CUT. 2. SEND OUT PRECUT AR2's FOR THE CUT OUTS. | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( 1000 LF) 1-5/8" Reveals * ( 360﻿ LF) - JR2 | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS78 | 72.78% | 14023 | 19268 | 180 | 180 | 26 | 1201 | 1000 | 44 | 21:23:19 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 89 | -22 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-12-21 05:56 |  | 2026-01-23 | 2026-03-02 | TRUE | 2026-03-18 |  | 2026-02-13 |  | 2026-02-13 |  |  | YES | 750 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans |  |  |  | AXYZ Titans Line | [24 empty] | 24051 | FS |  | 78 |  | 78 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 16 | 300 | [10 empty] | In House |  |  |  |  | 2026-02-27 | 2026-03-02 | 2 |  | QC Not Requested | 2026-03-12 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-13 |  | Issue Still in Process | Issiah Havens - @dusatenko@jwmcd.com @jdavis@jwmcd.com programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS78 In-House |  | 2026, Week 07
157 | 24051-FS78.1 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | TRELLIS ON SOUTH 1. PANELS ARE TO BE MADE WITHOUT CUT OUT FOR THE BEAMS. THESE WILL BE FIELD CUT. 2. SEND OUT PRECUT AR2's FOR THE CUT OUTS. | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | Stadium\04_Production\24051FS78.1 * 2 SETS - INSTALL DRAWINGS * ( 1000 LF) 1-5/8" Reveals * ( 12 LF) -JR2 | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS78.1 | 73.65% | 14191 | 19268 | 168 | 168 | 19 | 1095 | 1000 | 48 | 21:12:04 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 89 | -22 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-12-21 06:08 |  | 2026-01-23 | 2026-03-02 | TRUE | 2026-03-18 |  | 2026-02-13 |  | 2026-02-13 |  |  | YES | 750 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 78.1 |  | 78.1 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 24 | 300 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-02-27 | 2026-03-02 | 2 |  | QC Not Requested | 2026-03-16 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-17 |  | Issue Still in Process | Issiah Havens - @dusatenko@jwmcd.com @jdavis@jwmcd.com programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS78.1 In-House |  | 2026, Week 07
158 | 24051-FS78.2 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  |  | SOUTH LEVEL 400 TRELLIS | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( 2800 LF) 1-5/8" Reveals * ( 750 LF) 1-1/8" Reveals | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS78.2 | 71.84% | 13843 | 19268 | 348 | 348 | 12 | 2784 | 3550 | 78 x 62 in 303 SHEETS 196 x 62 in 15 SHEETS | 02d20h37m42s | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 88 | -23 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Denis Usatenko, Hennadii Stakhurskyi | 2025-12-21 06:18 |  | 2026-01-30 | 2026-02-27 | TRUE | 2026-03-17 |  | 2026-02-20 |  | 2026-02-20 |  |  | YES | 750 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 78.2 |  | 78.2 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 24 | 600 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab | 2026-02-26 | 2026-02-26 | 1 |  | QC Not Requested | 2026-03-14 | 6 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-23 |  | Issue Still in Process | Arnold Jurado - @jdavis@jwmcd.com ALL DONE | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS78.2 In-House | TRUE | 2026, Week 08
159 | 24039-FS14 |  | The Visionary | 3800 J.B. Hunt Drive Rogers, AR 72758 | Carlos Silva | 980.246.6545 | PEX |  | Please, add 100 LF 16GA 6"wide Strapping for install Very Important to review the size of the ACM sheets we are using, because we ordered 2 different sizes so we need to be sure we are using the correct one based on the optimization results. | ANTHRACITE SILVER Elevations: Sheets: 244, 245 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (1400 LF) - 3 5/8" Reveals * (440 LF) - PE1N * (100 LF) - JR2 * (800 pcs) - PEX [3" CLIP`S] * (200 pcs) - PET [3" CLIP`S] | Q:\Jobs\24039 - The Visionary\04_Production\24039FS14 | 102.2% | 3172 | 3104 | 176 | 197 | 160 | 2128 | 1400 | 65 | 17:44:50 | (ACM): 4mm X 62" X 196" ANTHRACITE SILVER FR ACM, Grain | FR ACM | (ACM): 4mm X 62" X 196" ANTHRACITE SILVER | Yes |  |  | 5 | -43 | Ramon Estrada, Shane Watson | Denis Usatenko | Denis Usatenko | Denis Usatenko | Denis Usatenko | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-12-01 16:31 |  | 2026-01-20 | 2026-01-30 | TRUE | 2026-02-17 |  | 2026-02-10 |  | 2026-02-10 |  |  | YES | 198 | [5 empty] | FAB SCREW | YES | Approved | YES | Q:\Jobs\24039 - The Visionary\03_Engineering\02_FD Docs\12_SCAN 112525 CS complete building | NO |  | NO | [6 empty] | Partially Shipped | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24039 | FS |  | 14 |  | 14 | 24039-FS15 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 45 | 80 | [10 empty] | Semi |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-01-28 | 2026-01-30 | 3 |  | QC Not Requested | 2026-02-06 | 50 (In Progress) | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Carlos Silva | Hennadii Stakhurskyi | Denis Usatenko | 24039-FS14 In-House |  | 2026, Week 07
160 | 24039-FS15 |  | The Visionary | 3800 J.B. Hunt Drive Rogers, AR 72758 | Carlos Silva | 980.246.6545 | PEX |  | Please, add 200 LF 16GA 6"wide Strapping for install Very Important to review the size of the ACM sheets we are using, because we ordered 2 different sizes so we need to be sure we are using the correct one based on the optimization results. | ANTHRACITE SILVER METALLIC Elevations: 62 / 241 61 / 241 64 / 242 63 / 242 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (900 LF) - 3 5/8" Reveals * (280 LF) - PE1N * (20 LF) - JR2 * (600 pcs) - PEX [3" CLIP`S] * (75 pcs) - PET [3" CLIP`S] | Q:\Jobs\24039 - The Visionary\04_Production\24039FS15 | 104.5% | 3245 | 3104 | 73 | 99 | 53 | 1059 | 900 | 42 SHEETS | 00d06h42m27s | ACM: 4mm X 62" X 130", ANTHRACITE SILVER METALLIC FR ACM, Grain | FR ACM | ACM: 4mm X 62" X 130", ANTHRACITE SILVER METALLIC | Yes |  |  | 6 | -41 | Ramon Estrada, Shane Watson | Denis Usatenko | Denis Usatenko | Denis Usatenko | Denis Usatenko | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2025-12-02 09:06 |  | 2026-01-22 | 2026-02-03 | TRUE | 2026-02-19 |  | 2026-02-12 |  | 2026-02-12 |  |  | YES | 00 | [5 empty] | FAB SCREW | YES | Approved | YES | Q:\Jobs\24039 - The Visionary\03_Engineering\02_FD Docs\12_SCAN 112525 CS complete building | NO |  | NO | [6 empty] | Partially Shipped | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24039 | FS |  | 15 |  | 15 | 24039-FS15 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 45 | 80 | [10 empty] | Semi |  |  | AXYZ | AXYZ Clean and Brake Fab | 2026-02-02 | 2026-02-03 | 2 |  | QC Not Requested | 2026-02-10 | 48 (In Progress) | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Carlos Silva - @tgraves@jwmcd.com @mchancey@jwmcd.com this will be the next shipping on 02/13. | 1010 |  | Carlos Silva | Hennadii Stakhurskyi | Denis Usatenko | 24039-FS15 In-House | TRUE | 2026, Week 07
161 | 25035-FS02 |  | Titans Jabez | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | CUSTOM ARCH |  | MATERRIAL TO BE SHIPPED TO SPECTRUM TO BE PAINTED MOONSTONE METALLIC. A112 CLIPS & ACM ANGLES ARE TO BE SHIPPED LOOSE WITH THE PANELS TO THE SITE RERFERENCE PO 26436 CUT 9 OF "25035FS-1101-BAR," COUNTERSINK, AND THEN SHEAR TO SIZE. | THE EXTRUSIONS CAN BE INSTALLED ON THE PANELS AS LONG AS THERE IS NO SILICONE OR ADHEASIVES ON ANY KIND. OTHERWISE, THESE PARTS WILL NEED TO BE APPLIED AFTER THE PANELS ARE PAINTED. | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * REVEALS FROM FS02.1 | Q:\Jobs\25035 - Titans Jabez\04_Production\25035FS02 | Unavailable | 453 |  | 109 | 600 | 13 | 411 | 0 | 48 | 20:41:00 | .125" X 60" X 144", 3003 Mill Alum Sheet, No Grain | Alum Sheet | .125" X 60" X 144", 3003 Mill | No |  |  | 5 | -37 | Ramon Estrada, Shane Watson | David Hasty | David Hasty | Frank Dean | David Hasty | Jonathan Dorsey | David Hasty | Jonathan Dorsey |  |  |  | Chris Gambrel | TRUE |  | Frank Dean | 2026-01-05 11:00 |  | 2026-02-06 | 2026-01-16 |  | 2026-02-25 | 2026-02-06 | 2026-02-27 |  | 2026-02-27 |  | 2026-03-03 | YES | 120 | 2026-01-05 | TRUE | Post Paint | SPECTRUM 535 Bev Rd. Youngstown, OH 44512 ATTN JARRED RUGGIERI 412-789-4459 | Coating Ship Back To JWM | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Shipped To Painter | TRUE | TRUE | [6 empty] | TRUE | 7000 TruMatic | [7 empty] | TRUE | [6 empty] | TRUE | TRUE |  |  | 25035 | FS |  | 02 |  | 2 | 25035-FS04 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 24 | 250 | [10 empty] | In House |  |  | Punch | 7000 TruMatic Brake Clean and Brake Fab Post Paint | 2026-01-16 | 2026-01-16 | 1 |  | QC Not Requested | 2026-02-11 | 3 | David Hasty | Ramon Estrada, Shane Watson | 2026-02-13 |  | Issue Still in Process | David Hasty - @jdavis@jwmcd.com please send to CNB before forming | 1010 |  | Marc Ribar | Jonathan Dorsey | David Hasty | 25035-FS02 In-House | TRUE | 2026, Week 09
162 | 24081-FL02 |  | DLR DFW37 | 1502 Ferris Rd Garland, TX 75044 | Cole Norona | 931.591.9340 |  |  | DO NOT BREAK TAB OFF OF FL-1004 Write the part number in marker on the NON PAINTED side for post painter-NO STICKERS | (26) 201A @ 9'-11 1/4" with 3/4" tab | SKETCHES PROGRAMMING FILES |  | Q:\Jobs\24081 - DLR DFW37\04_Production\24081-FL02 | N/A | N/A | N/A | 0 | 78 | 2 | 0 | 0 | 26 | 00:18:36 | .040" X 48" X 120"; 3003 Alum Sheet Alum Sheet, No Grain | Alum Sheet | .040" X 48" X 120"; 3003 Alum Sheet | No |  |  | 5 | -37 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Frank Dean | David Hasty | Frank Dean |  |  | Chris Gambrel |  | TRUE |  |  | 2026-02-12 07:55 | TRUE | 2026-02-20 | 2026-02-12 |  | 2026-02-25 | 2026-02-20 | 2026-02-27 |  | 2026-02-27 |  | 2026-03-03 | YES | 64 |  | TRUE | Post Paint | Air Performance 159 Genco Drive Hartford, AL 36344 Attn: Jake Faundez 941.718.2839 jfaundez@airperformancellc.com | Coating Ship To Site | [14 empty] | Shipped To Painter | [5 empty] | TRUE |  | TruLaser 3040 | [9 empty] | TRUE | [10 empty] | 24081 | FL |  | 02 |  | 2 | 24081-FL02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 2 | [10 empty] | Hot Shot |  |  | Flat Laser | Brake Post Paint TruLaser 3040 | 2026-02-12 | 2026-02-12 | 1 |  | Issue Still In Process |  | Crating Start Date Not Recorded | David Hasty | Ramon Estrada, Shane Watson | 2026-02-27 |  | Issue Still in Process | Chris Gambrel - @fdean@jwmcd.com @dhasty@jwmcd.com flat program completed. | 1010 |  | Cole Norona | Frank Dean | David Hasty | 24081-FL02 In-House | TRUE | 2026, Week 09
163 | 24051-FS76.1 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | LOWWR BAND NOT INCLUDED IN THE FLAT WALL. |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (400 LF) 1-5/8" Reveals * (180 LF) JR2-EXTENDED | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS76.1 | 74.85% | 14423 | 19268 | 74 | 74 | 4 | 625 | 400 | 18 | 09:31:15 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 94 | -18 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2026-02-12 13:56 |  | 2026-03-05 | 2026-03-05 |  | 2026-03-24 |  | 2026-03-26 |  | 2026-03-26 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 76.1 |  | 76.1 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-03-04 | 2026-03-05 | 2 |  | QC Not Requested | 2026-03-20 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-23 |  | Issue Still in Process | Issiah Havens - @dusatenko@jwmcd.com @jdavis@jwmcd.com programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS76.1 In-House |  | 2026, Week 13
164 | 26014-03-ST01 |  | 2026 R & D | 3731 Amy Lynn Drive Nashville, TN 37218-3813 | TBC |  | CUSTOM ARCH |  | THIS RELEASE GROUPS THE THREE FINISHED PRODUCTS FROM ST02 AND ST03 FOR DELIVERY TO THE CUSTOMER. LET WYLIE McDOUGALL KNOW WHEN THIS RELEASE IS READY AND HE WILL DELIVER IT TO THE CUSTOMER. CUSTOMER NEEDS THESE PARTS BEFORE MARCH 1ST. |  |  |  | Q:\Jobs\26014-03 - Oyster Cooker\04_Production\26014-03-ST01 | N/A | N/A | N/A | 0 | 3 | 1 | 0 | 0 | 0 | 0 | COMPETED WELDMENTS FOR DELIVERY |  | COMPETED WELDMENTS FOR DELIVERY |  |  |  | 1 | -30 | Hunter Clouse | David Hasty |  |  |  | Paul J Roberts | David Hasty | Paul J Roberts | [6 empty] | Frank Dean, Paul J Roberts | 2026-02-12 17:00 | TRUE | 2026-03-05 | 2026-02-18 | TRUE | 2026-03-06 |  | 2026-02-26 |  | 2026-02-26 |  |  | YES | [8 empty] | None Available | NO |  | YES | Q:\Jobs\26014-03 - Oyster Cooker\03_Engineering\03_FS_Issues\02_FD Docs | NO | [6 empty] | 7000 TubeLaser 20 |  | TRUE | [24 empty] | TRUE |  | 26014-03 | ST |  | 01 |  | 1 | 26014-03-ST03.1 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 24 | 32 | [10 empty] | Customer Pick Up |  |  |  | Assembly |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | David Hasty - @proberts@jwmcd.com corrections could happen if you feel like doing them :) | 1010 |  | TBC | Paul J Roberts | David Hasty | 26014-03-ST01 In-House |  | 2026, Week 09
165 | 24051-FS86 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | THIS RELEASE IS HOT. PLEASE EXPEDITE. SHIP TARGET IS AGRESSIVE. | WEST LEVEL 400 PANELS HIGHLIGHTED IN RED USE SUPLIED DIMENSIONS. GREEN AS DIMENSIONED IN OUR SHOPS | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (400 LF) 1-5/8" Reveals * (200 LF) 1-1/8" Reveals * (180 LF) JR2 | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS86 | 75.24% | 14497 | 19268 | 38 | 38 | 27 | 289 | 600 | 68 x 62 in 2 SHEETS 196 x 62 in 31 SHEETS | 00d06h33m03s | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 98 | -14 | Unassigned | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi, Tara Chambers-Douglas | 2026-02-13 15:30 | TRUE | 2026-03-06 | 2026-03-12 | TRUE | 2026-03-30 |  | 2026-03-04 |  | 2026-03-04 |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 86 |  | 86 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 40 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-03-12 | 2026-03-12 | 1 |  | QC Not Requested | 2026-03-21 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-23 |  | Issue Still in Process | Mitch Chancey - @mribar@jwmcd.com @tgraves@jwmcd.com @sjones@jwmcd.com @swatson@jwmcd.com Panels are ready, waiting on the reveals | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS86 In-House |  | 2026, Week 010
166 | 24079-FS04 |  | Nashville Youth Campus | 1354 Brick Church Pike Nashville, TN 37207 | Joe Hoyle | 828.334.7808 | --- |  | FOR LAYOUT PURPOSES ONLY. NO FAB. | Please confirm heights for all fiber panels referenced in FDDOCS FS103 folder. 1/NY-11 (Partial - see PDF) 1/NY-12 1/NY-30 1/NY-31 IPartial - see PDF) | [6 empty] | 173 | [6 empty] | 48" X 120" LAYOUT ONLY, Grain | LAYOUT ONLY | 48" X 120" | Yes |  |  | 3 | -29 | Denis Usatenko | David Hasty | Denis Usatenko | [12 empty] | 2026-02-16 12:25 |  | 2026-03-09 |  |  |  |  | 2026-03-30 |  | 2026-03-30 |  |  | YES | 999 | [5 empty] | N/A | N/A | Approved As Noted | YES | Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - NYCE - FS103 - Area A | YES | Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - NYCE - FS103 - Area A | NO | [6 empty] | Evaluation | [28 empty] | 24079 | FS |  | 04 |  | 4 | 24079-FS303 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 0 | [10 empty] | Customer Pick Up | [6 empty] | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Joe Hoyle |  |  | 24079-FS04 In-House |  | 2026, Week 14
167 | 26014-03-ST02 |  | 2026 R & D | 3731 Amy Lynn Drive Nashville, TN 37218-3813 | TBC |  | CUSTOM ARCH |  | ALUMINUM WELDMENT, FLAT LASER, AND FORM DRAWINGS FOR OYSTER COOKER. THIS RELEASE IS USED IN ST01 AND REQUIRES PARTS FROM ST02.1 TO COMPLETE WELDING. WELDMENT 26014-03FS-1004 REQUIRES McMASTER-CARR P/N 1581A531, WHICH HAS BEEN ORDERED FOR THIS JOB. ALUMINUM SHEET HAS BEEN ORDERED FOR THIS JOB. |  |  |  | Q:\Jobs\26014-03 - Oyster Cooker\04_Production\26014-03-ST02 | N/A | N/A | N/A | 0 | 9 | 9 | 0 | 0 | 2 | 00:27:39 | 1/8 X 60 X 120 Alum Sheet, No Grain | Alum Sheet | 1/8 X 60 X 120 | No |  |  | 1 | -30 | Hunter Clouse | David Hasty |  |  |  | Paul J Roberts | David Hasty | Paul J Roberts |  |  | Chris Gambrel |  | TRUE |  |  | 2026-02-17 17:31 | TRUE | 2026-03-10 | 2026-02-18 | TRUE | 2026-03-06 |  | 2026-02-27 |  | 2026-02-27 |  |  | YES | [8 empty] | None Available | NO |  | NO |  | NO | [6 empty] | TruLaser 3040 |  | TRUE | [6 empty] | TRUE | 7000 TruMatic | [7 empty] | TRUE |  |  | TRUE | [7 empty] | 26014-03 | ST |  | 02 |  | 2 | 26014-03-ST03.1 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 24 | 24 | [13 empty] | Punch | 7000 TruMatic Brake Weld | 2026-02-17 | 2026-02-18 | 2 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Joshua Davis - it shouldnt be there. I have not started this job yet | 1010 |  | TBC | Paul J Roberts | David Hasty | 26014-03-ST02 In-House |  | 2026, Week 09
168 | 26014-03-ST02.1 |  | 2026 R & D | 3731 Amy Lynn Drive Nashville, TN 37218-3813 | TBC |  | CUSTOM ARCH |  | THIS RELEASE CONTAINS ALUMINUM TUBE LASER PARTS REQUIRED FOR USE IN WELDMENTS IN RELEASE 26014-03-ST02. ALUMINUM PIPE HAS BEEN ORDERED FOR THIS JOB. |  |  |  | Q:\Jobs\26014-03 - Oyster Cooker\04_Production\26014-03-ST02.1 | N/A | N/A | N/A | 0 | 10 | 3 | 0 | 0 | 1 @240 | 1 min 30sec | Ø1" Sch. 40 X 120" (min) Alum Pipe, No Grain | Alum Pipe | Ø1" Sch. 40 X 120" (min) | No |  |  | 1 | -30 | Hunter Clouse | David Hasty |  |  |  | Paul J Roberts | David Hasty | Paul J Roberts |  |  | Arnold Jurado |  | TRUE |  |  | 2026-02-17 17:34 | TRUE | 2026-03-10 | 2026-02-18 | TRUE | 2026-03-06 |  | 2026-02-27 |  | 2026-02-27 |  |  | YES | [8 empty] | None Available | NO |  | NO |  | NO | [6 empty] | 7000 TubeLaser 20 |  | TRUE |  |  |  |  | TRUE | [13 empty] | TRUE | [7 empty] | 26014-03 | ST |  | 02.1 |  | 2.1 | 26014-03-ST03.1 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 2 | 2 | [13 empty] | Tube Laser | Tube Laser Weld | 2026-02-17 | 2026-02-18 | 2 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Arnold Jurado - @dhasty@jwmcd.com done | 1010 |  | TBC | Paul J Roberts | David Hasty | 26014-03-ST02.1 In-House | TRUE | 2026, Week 09
169 | 26014-03-ST03 |  | 2026 R & D | 3731 Amy Lynn Drive Nashville, TN 37218-3813 | TBC |  | CUSTOM ARCH |  | STAINLESS WELDMENT AND TUBE LASER DRAWINGS FOR OYSTER COOKER..THIS RELEASE IS USED IN ST01 AND REQUIRES PARTS FROM ST03.1 TO COMPLETE WELDING. REWORK DRAWING 26014-03FS-2003 REQUIRES McMASTER-CARR P/N 4813K42, WHICH HAS BEEN ORDERED FOR THIS JOB. THIS REWORK PART IS REQUIRED FOR USE IN WELDMENT DRAWING 26014-03FS-2002, AND THE REWORK MUST BE COMPLETED BEFORE USE IN THE WELDMENT. WELDMENT 26014-03FS-2002 ALSO REQUIRES McMASTER-CARR P/NS 1947K73 & 4464K499, WHICH ARE USED WITHOUT MODIFICATION AND HAVE BEEN PURCHASED FOR THIS JOB. STAINLESS ANGLE HAS BEEN ORDERED FOR THIS JOB. |  |  |  | Q:\Jobs\26014-03 - Oyster Cooker\04_Production\26014-03-ST03 | N/A | N/A | N/A | 0 | 8 | 6 | 0 | 0 | 1 @240 | 1 min 7 sec | 1 1/4 X 1 1/4 X 1/8 X 240 SS Angle, No Grain | SS Angle | 1 1/4 X 1 1/4 X 1/8 X 240 | No |  |  | 1 | -30 | Hunter Clouse | David Hasty |  |  |  | Paul J Roberts | David Hasty | Paul J Roberts |  |  | Arnold Jurado |  | TRUE |  |  | 2026-02-17 17:53 | TRUE | 2026-03-10 | 2026-02-18 | TRUE | 2026-03-06 |  | 2026-02-27 |  | 2026-02-27 |  |  | YES | [8 empty] | None Available | NO |  | NO |  | NO | [6 empty] | 7000 TubeLaser 20 |  | TRUE |  |  |  |  | TRUE | [13 empty] | TRUE | [7 empty] | 26014-03 | ST |  | 03 |  | 3 | 26014-03-ST03.1 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 12 | [13 empty] | Tube Laser | Tube Laser Weld | 2026-02-17 | 2026-02-18 | 2 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Arnold Jurado - @dhasty@jwmcd.com done | 1010 |  | TBC | Paul J Roberts | David Hasty | 26014-03-ST03 In-House | TRUE | 2026, Week 09
170 | 26014-03-ST03.1 |  | 2026 R & D | 3731 Amy Lynn Drive Nashville, TN 37218-3813 | TBC |  | CUSTOM ARCH |  | THIS RELEASE CONTAINS STAINLESS FLAT LASER AND FORMED PARTS REQUIRED FOR USE IN WELDMENTS IN RELEASE 26014-03-ST03. USE 11 Ga STAINLESS MINIMUM DROP FOR THIS JOB. |  |  |  | Q:\Jobs\26014-03 - Oyster Cooker\04_Production\26014-03-ST03.1 | N/A | N/A | N/A | 0 | 6 | 2 | 0 | 0 | 1 | 00:00:13 | 11 Ga. minimum drop SS Sheet, No Grain | SS Sheet | 11 Ga. minimum drop | No |  |  | 1 | -30 | Hunter Clouse | David Hasty |  |  |  | Paul J Roberts | David Hasty | Paul J Roberts |  |  | Chris Gambrel |  | TRUE |  |  | 2026-02-17 17:57 | TRUE | 2026-03-10 | 2026-02-18 | TRUE | 2026-03-06 |  | 2026-02-27 |  | 2026-02-27 |  |  | YES | [8 empty] | None Available | NO |  | NO |  | NO | [6 empty] | TruLaser 3040 |  | TRUE |  |  |  | TRUE |  | TruLaser 3040 | [9 empty] | TRUE |  |  | TRUE | [7 empty] | 26014-03 | ST |  | 03.1 |  | 3.1 | 26014-03-ST03.1 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 3 | [13 empty] | Flat Laser | Brake TruLaser 3040 Weld | 2026-02-17 | 2026-02-18 | 2 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Chris Gambrel - @proberts@jwmcd.com @dhasty@jwmcd.com @jdorsey@jwmcd.com flat program completed. | 1010 |  | TBC | Paul J Roberts | David Hasty | 26014-03-ST03.1 In-House |  | 2026, Week 09
171 | 25002-BM06 |  | Med Center Health | 250 Park Street Bowling Green, KY 42101 | Carlos Silva | 980.246.6545 |  |  | USE 16 GA. COLD ROLLED FROM 24079 | Drill (4) 3/8" holes distributed on the length (please see the layout attached) . 10 pieces of each= 20 pieces total | SKETCHES PROGRAMMING FILES |  | Q:\Jobs\25002 - Med Center Health\04_Production\25002BM06 | N/A | N/A | N/A | 0 | 29 | 3 | 0 | 0 | 9 | 00:08:57 | Steel Sheet: 16 Ga. X 48" X 120" Steel Sheet, No Grain | Steel Sheet | Steel Sheet: 16 Ga. X 48" X 120" | No |  |  | 10 | -33 | Ramon Estrada, Shane Watson | Denis Usatenko | David Hasty |  |  | Frank Dean | David Hasty | Frank Dean |  |  | Chris Gambrel |  | TRUE |  | Frank Dean | 2026-02-18 11:07 | TRUE | 2026-02-26 | 2026-02-25 | TRUE | 2026-03-03 | 2026-03-02 | 2026-03-04 |  | 2026-03-04 |  | 2026-03-23 | YES | 00 |  | TRUE | Powder Coat | PowderWorx615 1438 Highway 96 Burns, TN 37029 | Coating Ship To Site | [14 empty] | Shipped To Painter | [5 empty] | TRUE |  | TruLaser 3040 | [20 empty] | 25002 | BM |  | 06 |  | 6 | 25002-BM07 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 4 | [13 empty] | Flat Laser | Powder Coat TruLaser 3040 | 2026-02-25 | 2026-02-25 | 1 |  | Issue Still In Process |  | Crating Start Date Not Recorded | David Hasty | Ramon Estrada, Shane Watson | 2026-03-16 |  | Issue Still in Process | Carlos Silva - @dhasty@jwmcd.com @tgraves@jwmcd.com @rharmon@jwmcd.com @jmcpherson@jwmcd.com when this will be shipped to PowderWorx615? | 1010 |  | Carlos Silva | Frank Dean | David Hasty | 25002-BM06 In-House | TRUE | 2026, Week 010
172 | 1040-30791-ST08 |  | AFI - YANCEY | CUSTOMER PICK-UP | Hannah Sadloski, Lisa Ellison |  | --- | TRUE | ASSEMBLE IN CRATING (10) YBCO-01034 / D / BIRDSCREEN KIT (10) YBCO-01065 / D / DISCHARGE WALL (10)YBCO-01020 / D / FRONT WALL KIT (10) YBCO-01024 / D / INTAKE WALL KIT (10) YBCO-01043 / D / RIGHT WALL KIT (10) YBCO-01054 / D / LEFT WALL KIT (10) YBCO-01040 / D / TRYSTAR BASE KIT (20) YBCO-01038 / D / TRANSFORMER BRACKET KIT (10) YBCO-01252 / D / SOUND BAFFLE KIT (10) YBCO-01029 / D / REAR FIXED WALL (0) D5BA22-24-32 / D / UREA TANK BRACKET (10) D5K56-37-3-2-019-AL / D / EXHAUST BEAUTY RING |  | SAW CUT LIST KIT LIST (CRATING PLAN) YANCEY MATERIAL SAW DAILY FORM | ADDITIONAL PARTS FOR PACKAGING FROM TUBE LASER AND FLAT/FORM OPERATIONS PER KIT LIST 1.5 X 1.5 X .125 Alum. Angle 2 X 2 X .125 Alum. Angle 2 X 3 X .190 Alum. Angle 2 X 2 X .125 Alum. Tube 2 X 2 X .125 Alum. Tube 2 X 3 X .125 Alum. Tube 2 X 3 X .125 Alum. Tube 2 X 3 X .250 Alum. Tube 2 X 4 X .125 Alum. Tube 2 X 4 X .250 Alum. Tube 2 X 6 X .250 Alum. Tube | T:\01 IN-PROCESS ORDERS\0002 SPECTRUM\104030791 AFI YANCEY MULTIPLE POS\03_Production | N/A | N/A | N/A | 0 | 120 | 0 | 4050 | 0 | N/A | N/A | SEE MISC MATERIALS: Alum Angle, Alum Tube | Alum Tube | SEE MISC MATERIALS: Alum Angle, |  |  |  | 35 | -22 | Ramon Estrada, Shane Watson | David Hasty | [5 empty] | David Hasty | [6 empty] | Frank Dean | 2026-02-19 08:10 | TRUE | 2026-03-02 | 2026-03-03 | TRUE | 2026-03-18 |  | 2026-03-20 |  | 2026-03-20 |  |  | YES | [20 empty] | Ready to Ship | [15 empty] | TRUE | [10 empty] | TRUE | 15000 | 1040-30791 | ST |  | 08 |  | 8 | 1040-30791-ST10 | 2026-03-02 |  |  |  | No Hold |  |  |  | No Hold |  | 2026-02-27 | 2026-02-27 | 1 |  |  |  | No Hold | 1 | [12 empty] | Customer Pick Up |  |  |  | Assembly Extrusion Saw |  |  | No Program Requested |  | Issue Still In Process |  | Crating Start Date Not Recorded | David Hasty | Ramon Estrada, Shane Watson | 2026-04-08 |  | Issue Still in Process | Hannah Sadloski - @dhasty@jwmcd.com @fdean@jwmcd.com @lellison@jwmcd.com Updated ST08 documents will not be ready until I get inventory hard count from shop for ST07. This may impact the saw cut sheets for ST08. @tgraves@jwmcd.com | 1040 |  | Hannah Sadloski, Lisa Ellison |  |  | 1040-30791-ST08 In-House |  | 2026, Week 12
173 | 24071-FS11 |  | RS Gass State Lab | 975 RS Gass Blvd Nashville, TN 37216 | Cole Norona | 931.591.9340 | 400 |  |  | NADIRA-LETS HOP ON A CALL ONCE YOU GET THIS TO DISCUSS ELEVATIONS 201, 306 & 317 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 Sets Install Drawings * ( 300 LF) 1 5/8" Reveals * ( 181 LF) STRAP FOR PANELS * ( 5 PCS) JR2-8'-0"Lenght * (200 pcs) Corner Clips * ( 600 pcs) Color Screws | Q:\Jobs\24071 - RS Gass State Lab\04_Production\24071FS11 | 93.48% | 2482 | 2655 | 50 | 69 | 64 | 506 | 300 | 32 | 09:59:46 | 4mm X 62" X 196", BRIGHT METALLIC SILVER FR ACM, Grain | FR ACM | 4mm X 62" X 196", BRIGHT METALLIC SILVER | Yes |  |  | 2 | 5 | Mitch Chancey | Denis Usatenko | Nadira Vlatkovic | Nadira Vlatkovic |  | Nadira Vlatkovic | Hennadii Stakhurskyi | Nadira Vlatkovic |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Gabriela Herrera, Nadira Vlatkovic | 2026-02-19 12:44 |  | 2026-03-25 | 2026-04-06 | TRUE | 2026-04-22 |  | 2026-04-15 |  | 2026-04-15 |  |  | YES | 43 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\24071 - RS Gass State Lab\03_Engineering\02_FD Docs\24071_FS11\SCAN | YES | Q:\Jobs\24071 - RS Gass State Lab\03_Engineering\02_FD Docs\24071_FS11 | YES | Q:\Jobs\24071 - RS Gass State Lab\03_Engineering\02_FD Docs\24071_FS11\CALCS | [5 empty] | Crating | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24071 | FS |  | 11 |  | 11 | 24071-FS11 |  |  | 2026-04-02 | 2026-04-02 | 1 |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | 1 | 15 | 80 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-04-03 | 2026-04-06 | 2 |  | QC Not Requested | 2026-04-16 | 1 (In Progress) | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - Drawings | 1010 |  | Cole Norona | Nadira Vlatkovic | Hennadii Stakhurskyi | 24071-FS11 In-House |  | 2026, Week 16
174 | 25075-FS01 |  | St Thomas West Canopy Replace | 4220 Harding Pike Nashville, TN 37205 | Chris Buttrey | 615.517.9885 | 400 |  |  | See PDF for general layout. joints can be laid out how we need to. I would generally follow how it currently is in the photos. Location for everything Q:\Jobs\25075 - St Thomas West Canopy Replace\03_Engineering\02_FD Docs\00_25075_FS01 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (22 pcs) 10" x 2' - 0", 1-5/8" Corner Reveals * (48 pcs) 2' - 0" x 2' - 0", 1-5/8" Corner Reveals * 218 LF JR2﻿ * 700 LF 1-5/8" COLOR MATCHING REVEALS * 212 PCS CORNER CLIPPS * 424 PCS COLOR MATCHING SRCEWS | Q:\Jobs\25075 - St Thomas West Canopy Replace\04_Production\25075FS01 | Unavailable | 82 |  | 82 | 92 | 75 | - | - | 37 SHEETS | 00d13h26m37s | 4mm X 62" X 196", DWDMIC DFC/RND FR ACM, Grain | FR ACM | 4mm X 62" X 196", DWDMIC DFC/RND | Yes |  | MTPK | 1 | 3 | Mitch Chancey | Denis Usatenko |  | Denis Usatenko | Denis Usatenko | Gabriela Herrera | Denis Usatenko | Gabriela Herrera |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Gabriela Herrera | 2026-02-20 16:24 |  | 2026-03-27 | 2026-04-02 | TRUE | 2026-04-20 |  | 2026-04-17 |  | 2026-04-17 |  |  | YES | 50 | 2026-03-18 |  |  |  |  | MATCH COLOR | NO | N/A (Process Customer Provided Blanks) | YES | Q:\Jobs\25075 - St Thomas West Canopy Replace\03_Engineering\02_FD Docs\00_25075_FS01 | YES | Q:\Jobs\25075 - St Thomas West Canopy Replace\03_Engineering\02_FD Docs\00_25075_FS01 | NO | [6 empty] | Crating | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 25075 | FS |  | 01 |  | 1 | 25075-FS01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 40 | 150 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-04-02 | 2026-04-02 | 1 |  | QC Not Requested | 2026-04-16 | 1 (In Progress) | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Arnold Jurado - @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Chris Buttrey | Gabriela Herrera | Denis Usatenko | 25075-FS01 In-House |  | 2026, Week 16
175 | 25022-FS07 |  | Vantage VA15 | 45210 Vantage Data Plaza Sterling, VA 20166 | Thomas Mooers |  | 400 |  | I attached field dimensions to this ERF |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | (500) LF 1/2" DENVER FOAM B-ROD (100) CS - RED 1/8" SHIMS (100) CS - BLACK 1/4" SHIMS (1000) #12 X 2" HH TEK 2 SCREWS * 2 SETS - INSTALL DRAWINGS * ( 63 LF) 1-5/8" REVEALS * (4 pcs) CORNER CLIPS * ( 16 pcs ) COLOR MATCHING SCREWS | Q:\Jobs\25022 - Vantage VA15\04_Production\25022FS07 | 93.61% | 571 | 610 | 52 | 0 | 9 | 212 | 63 | 8 SHEETS | 00d04h11m37s | 4mm X 50" X 150", Cadet Gray FR ACM, No Grain | FR ACM | 4mm X 50" X 150", Cadet Gray | No |  |  | 38 | -7 | Ramon Estrada, Shane Watson | Denis Usatenko | Ailen Niedfeld | Ailen Niedfeld |  | Ailen Niedfeld | Denis Usatenko | Ailen Niedfeld |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Ailen Niedfeld | 2026-02-24 10:41 |  | 2026-03-17 | 2026-03-23 | TRUE | 2026-04-08 |  | 2026-04-07 |  | 2026-04-07 |  |  | YES | 19 | [5 empty] | Cadet Gray | YES | Approved | NO |  | YES | Q:\Jobs\25022 - Vantage VA15\03_Engineering\01_Shop Drawings\02_Approved Drawings | YES | Standard Set | [5 empty] | Ready to Ship | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 25022 | FS |  | 07 |  | 7 | 25022-FS12 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 8 | [10 empty] | Hot Shot |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-03-23 | 2026-03-23 | 1 |  | QC Not Requested | 2026-03-26 | 4 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-31 |  | Issue Still in Process | Arnold Jurado - @aniedfeld@jwmcd.com @jdavis@jwmcd.com programmed | 1010 |  | Thomas Mooers | Ailen Niedfeld | Denis Usatenko | 25022-FS07 In-House |  | 2026, Week 15
176 | 25067-FS02 |  | Harison Bend | 830 Discovery Lane Knoxville, TN 37918 | Andre Van Der Merwe | 315.261.0333 | 400 CAULK |  |  |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (1000) CS - RED 1/8" SHIMS * (1000) CS - BLACK 1/4" SHIMS * (2000) #12 X 1 1/2" HH TEK 3 SCREWS * ( 50 LF)5" x 10', 16GA strapping * 1 Roll - Backer rod 5/8" * 1 Case Caulking COLOR TBD BY PM * (180 LF) 1-5/8" REVEALS * ( 45pcs) CORNER CLIPS * ( 100 pcs ) COLOR MATCHING SCREWS * ( 10 LF) JR2 | Q:\Jobs\25067 - Harison Bend\04_Production\25067FS02 | 134.1% | 118 | 88 | 29 | 29 | 29 | 166 | 180 | 9 | 03:30:00 | 4mm x 62" x 196" Grey Metallic JY 3550 FR ACM, Grain | FR ACM | 4mm x 62" x 196" Grey Metallic JY 3550 | Yes |  |  | 2 | 9 | Joshua Davis | Denis Usatenko |  | Denis Usatenko |  | Ailen Niedfeld | Denis Usatenko | Ailen Niedfeld |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Ailen Niedfeld | 2026-02-25 11:23 |  | 2026-04-09 | 2026-04-09 |  | 2026-04-28 |  | 2026-04-30 |  | 2026-04-30 |  |  | YES | 13 | [5 empty] | N/A | NO | None Available | YES | Q:\Jobs\25067 - Harison Bend\03_Engineering\02_FD Docs\25067 FS02\HARRISON BEND Canopy Scan\Harison_Bend | YES | Q:\Jobs\25067 - Harison Bend\03_Engineering\02_FD Docs\25067 FS02 | NO | [6 empty] | AXYZ 34 | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 25067 | FS |  | 02 |  | 2 | 25067-FS02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 16 | 35 | [10 empty] | Hot Shot |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-04-07 | 2026-04-09 | 3 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - Installs | 1010 |  | Andre Van Der Merwe | Ailen Niedfeld | Denis Usatenko | 25067-FS02 In-House |  | 2026, Week 18
177 | 25022-FS08 |  | Vantage VA15 | 45210 Vantage Data Plaza Sterling, VA 20166 | Thomas Mooers |  | 400 |  |  | Please layout panels from dimensions on shop drawings from center and bottom. (See drawing). | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * (1296 LF) 1 5/8" Reveals * (8 PCS) JR2-8'-0" Length | Q:\Jobs\25022 - Vantage VA15\04_Production\25022FS08 | 85.08% | 519 | 610 | 60 | 60 | 12 | 402 | 1296 | 150 X 62 - 54 | 12:11:09 | 4mm X 62" X 150", Vantage Blue FR ACM, Grain | FR ACM | 4mm X 62" X 150", Vantage Blue | Yes |  |  | 37 | -9 | Ramon Estrada, Shane Watson | Denis Usatenko |  | Chance Dill |  | Chance Dill | Denis Usatenko | Chance Dill |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Chance Dill | 2026-02-25 16:00 |  | 2026-03-18 | 2026-03-13 |  | 2026-04-06 |  | 2026-04-08 |  | 2026-04-08 |  |  | YES | 173 | [5 empty] | Vantage Blue | YES | Approved | NO |  | NO |  | YES | Standard | [5 empty] | Ready to Ship | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 25022 | FS |  | 08 |  | 8 | 25022-FS12 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 8 | [10 empty] | Hot Shot |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-03-13 | 2026-03-13 | 1 |  | QC Not Requested | 2026-03-27 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-27 |  | Issue Still in Process | Chance Dill - Install Drawings to shop 3/19/2026 | 1010 |  | Thomas Mooers | Chance Dill | Denis Usatenko | 25022-FS08 In-House |  | 2026, Week 15
178 | 24069-RM04 |  | TCAT Pulaski | 1233 East College Street Pulaski, TN 38478 | Chris Buttrey | 615.517.9885 | GENESIS |  | REMAKE FOR FS05 | no changes needed, just got a deep scratch in the field. color will be same, sunstorm stainless steel | SKETCHES PROGRAMMING FILES | 2 FOAM BAFFLES | Q:\Jobs\24069 - TCAT Pulaski\04_Production\24069RM04 | Unavailable | 1158 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 00:02:33 | .080" X 60" X 108", 3003 Alum Alum Sheet, No Grain | Alum Sheet | .080" X 60" X 108", 3003 Alum | No |  |  | 12 | -16 | Ramon Estrada, Shane Watson | David Hasty |  |  |  | Frank Dean | [5 empty] | Chris Gambrel | TRUE |  | Frank Dean | 2026-03-02 07:46 |  | 2026-03-09 | 2026-03-02 |  | 2026-03-26 | 2026-03-20 | 2026-03-30 |  |  |  | 2026-03-16 | YES | 42 |  | TRUE | Post Paint | Spectrum Bev Rd Youngstown, OH | Coating Ship To Site | N/A | N/A | Approved | NO |  | NO |  | NO |  | (1) 1133 | FS05 |  | FIELD INSTALLERS |  | Shipped To Painter | [8 empty] | TRUE | 7000 TruMatic | [7 empty] | TRUE | [10 empty] | 24069 | RM |  | 04 |  | 4 | 24069-RM05 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 4 | [10 empty] | Hot Shot |  |  | Punch | 7000 TruMatic Brake Post Paint | 2026-03-02 | 2026-03-02 | 1 |  | QC Not Requested | 2026-03-10 | 4 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-13 |  | Issue Still in Process | Mitch Chancey - i was going to wrap it in foam then shrink wrap it and sprinter | 1010 |  | Chris Buttrey | Frank Dean |  | 24069-RM04 In-House | TRUE | 2026, Week 14
179 | 23028-FL205 |  | 1000 Church YMCA | 1000 Church Street Nashville, TN 37203 | Dillon Bowman | 518.860.9477 |  |  | Closure piece | sketch in Fd Folder - part of FL 201 | * Sketch |  | Q:\Jobs\23028 - 1000 Church YMCA\04_Production\23028FL205 | N/A | N/A | N/A | 0 | 4 | 1 | 0 | 0 | 0.75 - SHT | na | .080 48 x 196 - focus black - 23071 Alum Sheet, No Grain | Alum Sheet | .080 48 x 196 - focus black - 23071 | No |  |  | 34 | -29 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-03-02 12:34 | TRUE | 2026-03-10 | 2026-03-03 | TRUE | 2026-03-09 |  | 2026-03-06 |  |  |  |  | YES | 22 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 23028 | FL |  | 205 |  | 205 | 23028-FL205 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 0.25 | 2 | [14 empty] | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2026-03-03 | 5 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-09 |  | Issue Still in Process |  | 1010 |  | Dillon Bowman | Denis Usatenko |  | 23028-FL205 In-House |  | 2026, Week 010
180 | 25017-RO01 |  | Nashville Yards Park | Nashville, TN 37203 | Dillon Bowman | 518.860.9477 | 400 |  | Column Remake - No Changes | Column Remake - No Changes | * SKETCHES * COLOR LABELS * PANEL CUT LIST * TIGER SAW EXTRUSION LIST * CODING FILES | * 14 LF 1 5/8" COLOR MATCHING REVEALS * 4 PCS CORNER CLIPS * 8 PCS COLOR MATCHING SCREWS | Q:\Jobs\25017 - Nashville Yards Park\04_Production\25017RO01 | 184.9% | 98 | 53 | 1 | 3 | 2 | 12 | 14 | 1 SHEET | 00d00h14m23s | 4mm x 62 x 196 - Midnight Black - 25017 FR ACM, No Grain | FR ACM | 4mm x 62 x 196 - Midnight Black - 25017 | No |  |  | 36 | -21 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Gabriela Herrera |  | Gabriela Herrera |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Gabriela Herrera | 2026-03-02 15:57 | TRUE | 2026-03-23 | 2026-03-03 | TRUE | 2026-03-19 |  | 2026-03-16 |  |  |  |  | NO | 3 | 2026-03-06 |  |  |  |  | MATCH COLOR | YES | Approved | NO |  | NO |  | NO |  | (1) 202-1A19 (2) Part-a-j | FS01 |  |  |  | Ready to Ship |  | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 25017 | RO |  | 01 |  | 1 | 25017-RO02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 0.25 | 3 | [13 empty] | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-03-03 | 2026-03-03 | 1 |  | QC Not Requested | 2026-03-09 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2026-03-09 |  | Issue Still in Process | Arnold Jurado - @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Dillon Bowman | Gabriela Herrera |  | 25017-RO01 In-House |  | 2026, Week 12
181 | 25029-MU02 |  | Lourdes CC Phase 2 | 1510 Lone Oak Road Paducah, KY 42003 | Dillon Bowman | 518.860.9477 | CUSTOM ARCH |  | Memorial Screen Wall Mock-up (Small) | Memorial Screen Wall Mock-up (Small) 18" x 18" Client is asking for a small sample of the screen. Just the face, no returns required. I have indicate a portion of the screen wall they'd like to see sampled. | SKETCHES PROGRAM FILES |  | Q:\Jobs\25029 - Lourdes CC Phase 2\04_Production\25029MU02 | 77.44% | 127 | 164 | 1 | 1 | 1 | 0 | 0 | 1 | 00:01:40 | .125 x 60 x 120 - 3003 Mill Alum Sheet, No Grain | Alum Sheet | .125 x 60 x 120 - 3003 Mill | No |  |  | 3 | -20 | Hunter Clouse | David Hasty | David Hasty |  |  | Jonathan Dorsey | David Hasty | Jonathan Dorsey |  |  | Chris Gambrel |  | TRUE |  | Jonathan Dorsey | 2026-03-03 14:41 | TRUE | 2026-03-24 | 2026-03-04 | TRUE | 2026-03-20 |  | 2026-03-13 |  |  |  |  | YES | [6 empty] | N/A | N/A | N/A (Process Customer Provided Blanks) | NO |  | YES | Q:\Jobs\25029 - Lourdes CC Phase 2\03_Engineering\02_FD Docs\25025 - MU02 - Memorial Screen Wall | NO | [6 empty] | TruLaser 3040 |  | TRUE |  |  |  | TRUE |  | TruLaser 3040 | [20 empty] | 25029 | MU |  | 02 |  | 2 | 25029-MU10 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 2 | [10 empty] | In House |  |  | Flat Laser | TruLaser 3040 | 2026-03-04 | 2026-03-04 | 1 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Dillon Bowman - Good Morning John, Weld should not be needed for MU02. Thanks! @jdorsey@jwmcd.com | 1010 |  | Dillon Bowman | Jonathan Dorsey | David Hasty | 25029-MU02 In-House | TRUE | 2026, Week 11
182 | 24051-FS87 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | NORTH LEVEL 350 INSALL DIRECTION LEFT TO RIGHT |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (300 LF) 1-5/8" Reveals * (160 LF) JR2 | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS87 | 75.76% | 14597 | 19268 | 54 | 54 | 6 | 292 | 300 | 68 X 62 - 33 196 X 62 - 1 | 07:49:07 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 4 | 6 | Corey Howse | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Nadira Vlatkovic | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2026-03-04 08:34 |  | 2026-03-25 | 2026-04-07 | TRUE | 2026-04-23 |  | 2026-04-15 |  |  |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Clean and Brake | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 87 |  | 87 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 16 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-04-07 | 2026-04-07 | 1 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Nadira Vlatkovic | 24051-FS87 In-House |  | 2026, Week 16
183 | 24051-FS88 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | WEST LEVEL 350 INSTALL DIRECTION RIGH TO LEFT |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (440 LF) 1-5/8" Reveals * (200 LF) JR2 | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS88 | 76.16% | 14675 | 19268 | 78 | 78 | 8 | 417 | 440 | 196 X 62 - 9 68 X 62 - 25 | 10:13:31 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 102 | 6 | Unassigned | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Nadira Vlatkovic | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2026-03-04 09:52 |  | 2026-03-25 | 2026-04-07 | TRUE | 2026-04-23 |  | 2026-04-15 |  |  |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 88 |  | 88 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 20 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-04-07 | 2026-04-07 | 1 |  | QC Not Requested | 2026-04-10 | 3 | David Hasty | Ramon Estrada, Shane Watson | 2026-04-14 |  | Issue Still in Process | Issiah Havens - @jdavis@jwmcd.com @hstakhurskyi@jwmcd.com programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Nadira Vlatkovic | 24051-FS88 In-House |  | 2026, Week 16
184 | 24051-FS89 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | WEST LEVEL 50 - HOLD ON PANELS AT THE HANDRAIL |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (300 LF) 1-5/8" Reveals * (64 LF) JR-EXTENDED | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS89 | 76.7% | 14779 | 19268 | 40 | 40 | 19 | 388 | 300 | 12 | 06:31:18 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 5 | 12 | Joshua Davis | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Nadira Vlatkovic | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Hennadii Stakhurskyi | 2026-03-04 11:38 |  | 2026-03-25 | 2026-04-15 | TRUE | 2026-05-01 |  | 2026-04-15 |  |  |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | AXYZ 34 | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 89 |  | 89 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 40 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-04-15 | 2026-04-15 | 1 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com Programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Nadira Vlatkovic | 24051-FS89 In-House |  | 2026, Week 16
185 | 24051-FS36.2 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | WEST WINGS LEVEL 00 |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (250 LF) 1-5/8" Reveals | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS36.2 | 76.36% | 14713 | 19268 | 38 | 38 | 12 | 152 | 250 | 7 | 03:57:43 | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 1 | 7 | Corey Howse | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Nadira Vlatkovic | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Denis Usatenko, Hennadii Stakhurskyi | 2026-03-04 13:37 |  | 2026-03-25 | 2026-04-08 | TRUE | 2026-04-24 |  | 2026-04-15 |  |  |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Fabrication | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 36.2 |  | 36.2 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 40 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-04-07 | 2026-04-08 | 2 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Nadira Vlatkovic | 24051-FS36.2 In-House |  | 2026, Week 16
186 | 24051-FS226 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | WEST LEVEL 00 |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (250 LF) 1-5/8" Reveals | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS226 | 76.49% | 14739 | 19268 | 26 | 26 | 4 | 182 | 250 | 13 | 04:22:57 | 4mm X 62" X 196", MOONSTONE METALLIC FR ACM, Grain | FR ACM | 4mm X 62" X 196", MOONSTONE METALLIC | Yes |  |  | 1 | 7 | Corey Howse | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Denis Usatenko, Hennadii Stakhurskyi | 2026-03-04 13:58 |  | 2026-03-25 | 2026-04-08 | TRUE | 2026-04-24 |  | 2026-04-15 |  |  |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Fabrication | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 226 |  | 226 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 40 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-04-08 | 2026-04-08 | 1 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com programmed | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS226 In-House |  | 2026, Week 16
187 | 25030-FS01 |  | 510 W Tremont | 510 W Tremont Charlotte, NC 28203 | Laura Forero | 615.788.7739 | 400 |  | If possible, please cut this along with 25030FS02. The plan is to ship this with 25030BM01 and 25030FS02. | This release includes the following elevations: 201, 202, and 203 elevations The current scan in the folder has the whole job and includes the balconies. Also in the FD folder is the glazing SD. I have highlighted the areas that affect the panels. For the top panels, there is going to be an EIFS cornice in the PDF. I added the dimension that is visible in the scan. Please use these dimensions for all the areas where we are next to the EIFS cornice The EIFS between the windows in elevation 201 will hold to the storefront. Also, the area above the roof level is not looking great in the scan, but in the PDF, there are some dimensions. Please use that. Each balcony has its own name, so it's easier to identify the pictures for each balcony. The brick in these elevations is not installed, but the GC is giving us the set dimensions where the brick is going to stand. | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 292 | 88 | [6 empty] | Alfrex, 4mm X 62" X 130", Graphite Metallic FR ACM, Grain | FR ACM | Alfrex, 4mm X 62" X 130", Graphite Metallic | Yes |  | MTPK | 1 | -10 | Chance Dill | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic | Chance Dill | Denis Usatenko | Chance Dill |  | Arnold Jurado, Issiah Havens |  |  |  |  | Chance Dill | 2026-03-05 15:18 |  | 2026-04-03 |  |  |  |  | 2026-04-24 |  |  |  |  | YES | 92 | [5 empty] | MATCH COLOR | YES | Approved As Noted | YES | Q:\Jobs\25030 - 510 W Tremont\03_Engineering\02_FD Docs\25030FS01&FS02\SCAN | YES | Q:\Jobs\25030 - 510 W Tremont\03_Engineering\02_FD Docs\25030FS01&FS02 | NO | [6 empty] | Correction | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25030 | FS |  | 01 |  | 1 | 25030-FS02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 50 | 240 | [10 empty] | Hot Shot Semi |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - @cdill@jwmcd.com Correcitnos required | 1010 |  | Laura Forero | Chance Dill | Denis Usatenko | 25030-FS01 In-House |  | 2026, Week 17
188 | 25030-FS02 |  | 510 W Tremont | 510 W Tremont Charlotte, NC 28203 | Laura Forero | 615.788.7739 | 400 |  | If possible, please cut this along with 25030FS01. The plan is to ship this with 25030BM01 and 25030FS01. | This release includes the following elevations: 204, 205, and 206 elevations The current scan in the folder has the whole job and includes the balconies. Also in the FD folder is the glazing SD. I have highlighted the areas that affect the panels. For the top panels, the condition changed because the concrete and the sheathing don't align. Each balcony has its own name, so it's easier to identify the pictures for each balcony.The details 30/409 and 34/410 might change pending a question to the GC regarding what to do with the bumpout and how building the panels straight will be affected by the duct that is coming out from the balconies | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 292 | 84 | [6 empty] | Alfrex, 4mm X 62" X 130", Graphite Metallic FR ACM, Grain | FR ACM | Alfrex, 4mm X 62" X 130", Graphite Metallic | Yes |  | MTPK | 1 | -10 | Chance Dill | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic | Chance Dill | Denis Usatenko | Chance Dill |  | Arnold Jurado, Issiah Havens |  |  |  |  | Chance Dill | 2026-03-05 16:16 |  | 2026-04-03 |  |  |  |  | 2026-04-24 |  |  |  |  | YES | 120 | [5 empty] | MATCH COLOR | YES | Approved As Noted | YES | Q:\Jobs\25030 - 510 W Tremont\03_Engineering\02_FD Docs\25030FS01&FS02\SCAN | YES | Q:\Jobs\25030 - 510 W Tremont\03_Engineering\02_FD Docs\25030FS01&FS02 | NO | [6 empty] | Sketch | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25030 | FS |  | 02 |  | 2 | 25030-FS02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 40 | 240 | [10 empty] | Hot Shot Semi |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Nadira Vlatkovic - @dusatenko@jwmcd.com Layout is ready to be sketched. | 1010 |  | Laura Forero | Chance Dill | Denis Usatenko | 25030-FS02 In-House |  | 2026, Week 17
189 | 25022-FS10 |  | Vantage VA15 | 45210 Vantage Data Plaza Sterling, VA 20166 | Thomas Mooers |  | 400 |  | NA | Elevations on 211, 212, 213. All Dimensions are edge of drywall. Not edge of panel. | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (1777 LF) 1-5/8" Reveals * (100 pcs) 2' - 0" x 1' - 0" x 1-5/8" wide Corner Reveal * (64 LF) JR2 * 196 PCS CORNER CLIPS * 488 PCS COLOR MATCHING SCREWS | Q:\Jobs\25022 - Vantage VA15\04_Production\25022FS10 | 126.4% | 771 | 610 | 200 | 200 | 46 | 1055 | 2077 | 60 | 25:18:41 | 4mm X 62" X 196", Alabaster Mask FR ACM, Grain | FR ACM | 4mm X 62" X 196", Alabaster Mask | Yes |  |  | 42 | 1 | Ramon Estrada, Shane Watson | Denis Usatenko | Gabriela Herrera | Gabriela Herrera |  | Gabriela Herrera | Denis Usatenko | Gabriela Herrera |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Gabriela Herrera | 2026-03-06 15:59 | TRUE | 2026-03-27 | 2026-03-31 | TRUE | 2026-04-16 |  | 2026-04-07 |  |  |  |  | YES | 63 | [5 empty] | Alabaster | YES | Approved | NO |  | YES | Q:\Jobs\25022 - Vantage VA15\03_Engineering\02_FD Docs\25022 FS10 | YES | Standard | [5 empty] | Ready to Ship | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 25022 | FS |  | 10 |  | 10 | 25022-FS12 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 16 | [10 empty] | Hot Shot |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-03-31 | 2026-03-31 | 1 |  | Issue Still In Process |  | Crating Start Date Not Recorded | David Hasty | Ramon Estrada, Shane Watson | 2026-04-08 |  | Issue Still in Process | Gabriela Herrera - ID were taken to the shop | 1010 |  | Thomas Mooers | Gabriela Herrera | Denis Usatenko | 25022-FS10 In-House |  | 2026, Week 15
190 | 25022-FS11 |  | Vantage VA15 | 45210 Vantage Data Plaza Sterling, VA 20166 | Thomas Mooers |  | 400 |  | NA | Elevation 213. Dimensions are edge of drywall. | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( 60 LF) 1-5/8" Reveals * ( 80 pcs) 2' - 0" x 1' - 0" x 1-5/8" wide Corner Reveal * (23 LF) JR2 | Q:\Jobs\25022 - Vantage VA15\04_Production\25022FS11 | 138.2% | 843 | 610 | 72 | 72 | 20 | 350 | 60 | 13 | 07:51:38 | 4mm X 62" X 196", Timeless Beige FR ACM, Grain | FR ACM | 4mm X 62" X 196", Timeless Beige | Yes |  |  | 42 | 1 | Ramon Estrada, Shane Watson | Denis Usatenko | Gabriela Herrera | Gabriela Herrera |  | Ailen Niedfeld | Denis Usatenko | Ailen Niedfeld |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Ailen Niedfeld | 2026-03-06 16:08 | TRUE | 2026-03-27 | 2026-03-31 | TRUE | 2026-04-16 |  | 2026-04-06 |  |  |  |  | YES | 17 | [5 empty] | Beige | YES | Approved | NO |  | YES | Q:\Jobs\25022 - Vantage VA15\03_Engineering\02_FD Docs\25022 FS11 | YES | Standard | [5 empty] | Ready to Ship | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 25022 | FS |  | 11 |  | 11 | 25022-FS12 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 6 | 8 | [10 empty] | Hot Shot |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-03-30 | 2026-03-31 | 2 |  | QC Not Requested | 2026-04-03 | 4 | David Hasty | Ramon Estrada, Shane Watson | 2026-04-08 |  | Issue Still in Process | Gabriela Herrera - ID were taken to the shop | 1010 |  | Thomas Mooers | Ailen Niedfeld | Denis Usatenko | 25022-FS11 In-House |  | 2026, Week 15
191 | 25006-FS03 |  | MALETA Housing and Dining | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  | Priority 1: 36-38/214, 39-40/215, and 41-42/216 (Total panels: 216) GRAPHITE |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 2058 | 216 | [6 empty] | 4mm X 62" X 196", GRAPHITE FR ACM, Grain | FR ACM | 4mm X 62" X 196", GRAPHITE | Yes |  | MTPK | 1 | -3 | Samuel Lucas | Denis Usatenko |  | Denis Usatenko | Nadira Vlatkovic | Samuel Lucas | Denis Usatenko | Samuel Lucas |  | Arnold Jurado, Issiah Havens |  |  |  |  | Samuel Lucas | 2026-03-11 07:54 |  | 2026-04-14 |  |  |  |  | 2026-05-05 |  |  |  |  | YES | 430 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS03-04 BUILDING C 213-219 ELEV\SCAN | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS03-04 BUILDING C 213-219 ELEV\FD | NO | [6 empty] | Correction | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25006 | FS |  | 03 |  | 3 | 25006-FS13 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 60 | 360 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - @slucas@jwmcd.com Corrections required. | 1010 |  | Cole Norona | Samuel Lucas | Denis Usatenko | 25006-FS03 In-House |  | 2026, Week 19
192 | 25006-FS04 |  | MALETA Housing and Dining | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | Priority 2: 43-44/216, 45-46/217, and 47-49/218 (Total panels: 232) GRAPHITE | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 2058 | 232 | [6 empty] | 4mm X 62" X 196", GRAPHITE FR ACM, Grain | FR ACM | 4mm X 62" X 196", GRAPHITE | Yes |  | MTPK | 5 | 7 | Nadira Vlatkovic | Denis Usatenko |  | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens |  |  |  |  | Denis Usatenko | 2026-03-11 07:56 |  | 2026-04-24 |  |  |  |  | 2026-05-15 |  |  |  |  | YES | 430 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS03-04 BUILDING C 213-219 ELEV\SCAN | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS03-04 BUILDING C 213-219 ELEV\FD | NO | [6 empty] | LO Check | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25006 | FS |  | 04 |  | 4 | 25006-FS13 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 60 | 360 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - @nvlatkovic@jwmcd.com Chance or Samuel should be avilable. | 1010 |  | Cole Norona |  | Denis Usatenko | 25006-FS04 In-House |  | 2026, Week 20
193 | 25006-FS05 |  | MALETA Housing and Dining | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | Priority 3: 25/213 & 50/219 (Total panels: 18) TERRA COTA | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 2058 | 18 | [6 empty] | 4mm X 62" X 196", TERRA COTA FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TERRA COTA | No |  | MTPK | 2 | 3 | Nadira Vlatkovic | Denis Usatenko |  | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens |  |  |  |  | Denis Usatenko | 2026-03-11 08:08 |  | 2026-04-20 |  |  |  |  | 2026-05-11 |  |  |  |  | YES | 30 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS05 BUILDING C 213-219 ELEV\SCAN | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS05 BUILDING C 213-219 ELEV\FD | NO | [6 empty] | LO Check | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25006 | FS |  | 05 |  | 5 | 25006-FS13 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 5 | 30 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - 4/22 - Think we can convince the shop to shrink timeframe on 18 panels? It is almost ready. I will not be surprised if its 4/20 | 1010 |  | Cole Norona |  | Denis Usatenko | 25006-FS05 In-House |  | 2026, Week 20
194 | 25029-MU03 |  | Lourdes CC Phase 2 | 1510 Lone Oak Road Paducah, KY 42003 | Dillon Bowman | 518.860.9477 | CUSTOM ARCH |  | Custom Leafs - Please put on Dillon's desk when complete. | Custom Leafs | SKETCHES PROGAMMING FILES |  | Q:\Jobs\25029 - Lourdes CC Phase 2\04_Production\25029MU03 | N/A | N/A | N/A | 0 | 2 | 1 | 0 | 0 | 1 | 00:00:31 | 11g STEEL 60 x 144 (From Processing) drops if possible Steel Sheet, No Grain | Steel Sheet | 11g STEEL 60 x 144 (From Processing) drops if possible | No |  |  | 4 | -15 | Hunter Clouse | David Hasty |  |  |  | Jonathan Dorsey | David Hasty | Jonathan Dorsey |  |  | Chris Gambrel |  | TRUE |  | Jonathan Dorsey | 2026-03-11 08:12 | TRUE | 2026-04-01 | 2026-03-11 | TRUE | 2026-03-27 |  | 2026-03-13 |  |  |  |  | YES | [6 empty] | N/A | N/A | None Available | NO |  | NO |  | NO | [6 empty] | TruLaser 3040 |  | TRUE |  |  |  | TRUE |  | TruLaser 3040 | [12 empty] | TRUE | [7 empty] | 25029 | MU |  | 03 |  | 3 | 25029-MU10 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 2 | 2 | [10 empty] | In House |  |  | Flat Laser | TruLaser 3040 Weld | 2026-03-11 | 2026-03-11 | 1 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Chris Gambrel - @jdorsey@jwmcd.com @dhasty@jwmcd.com flat program completed. | 1010 |  | Dillon Bowman | Jonathan Dorsey | David Hasty | 25029-MU03 In-House | TRUE | 2026, Week 11
195 | 25006-FS06 |  | MALETA Housing and Dining | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | Priority 4: 26-28/210, 29-31/211, and 32-34/212 (Total panels: 246) GRAPHITE | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 2058 | 246 | [6 empty] | 4mm X 62" X 196", GRAPHITE FR ACM, Grain | FR ACM | 4mm X 62" X 196", GRAPHITE | Yes |  | MTPK | 7 | 13 | Nadira Vlatkovic | Denis Usatenko |  | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens |  |  |  |  | Denis Usatenko | 2026-03-11 08:13 |  | 2026-05-04 |  |  |  |  | 2026-05-25 |  |  |  |  | YES | 430 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS06-BUILDING B & C SOUTH 210-212 ELEV\SCAN | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS06-BUILDING B & C SOUTH 210-212 ELEV\FD | NO | [6 empty] | LO Check | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25006 | FS |  | 06 |  | 6 | 25006-FS13 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 70 | 400 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Cole Norona |  | Denis Usatenko | 25006-FS06 In-House |  | 2026, Week 22
196 | 24051-FS71.1 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | NEED 30 PCS OF PR2 CUT TO 4'-4.5" LONG. |  | EXTRUSION CUT LIST |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FS71.1 | N/A | N/A | N/A | 0 | 0 | 1 | 30 | 0 | 0 | N/A | 400 SERIES PR2 Alum Structural Shape, No Grain | Alum Structural Shape | 400 SERIES PR2 | No |  |  | 95 | -15 | Unassigned | David Hasty |  |  |  | Frank Dean | David Hasty | Frank Dean |  |  |  |  | TRUE |  | Frank Dean | 2026-03-11 16:12 | TRUE | 2026-04-01 | 2026-03-11 | TRUE | 2026-03-27 |  | 2026-03-12 |  |  |  |  | YES | 0 | [5 empty] | N/A | N/A | Approved | NO |  | NO |  | NO | [6 empty] | RTS Titans |  | TRUE | [13 empty] | TRUE | [12 empty] | 24051 | FS |  | 71.1 |  | 71.1 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 4 | [10 empty] | In House |  |  |  | Extrusion Saw |  | 2026-03-12 | Program Start Date Not Recorded |  | Issue Still In Process |  | Crating Start Date Not Recorded | David Hasty | Ramon Estrada, Shane Watson | 2026-03-12 |  | Issue Still in Process |  | 1010 |  | Marc Ribar | Frank Dean | David Hasty | 24051-FS71.1 In-House | TRUE | 2026, Week 11
197 | 26011-ST01 |  | 2nd Ave Mockup Build | 185 2nd ave Nashville, TN 37201 | Wylie McDougall | 615.426.7650 | CUSTOM ARCH |  | This is for the lower trough. Refer to marked up shop drawings. |  | SKETCHES PROGRAMMING FILES |  | Q:\Jobs\26011 - 2nd Ave Mockup Build\04_Production\26011ST01 | N/A | N/A | N/A | 0 | 4 | 4 | 0 | 0 | 1 | 00:00:34 | .062" X 60" X 120" Alum Sheet, No Grain | Alum Sheet | .062" X 60" X 120" | No |  |  | 5 | -10 | Hunter Clouse | David Hasty |  |  |  | Jonathan Dorsey | David Hasty | Jonathan Dorsey |  |  | Chris Gambrel |  | TRUE |  | Jonathan Dorsey | 2026-03-11 16:34 | TRUE | 2026-04-01 | 2026-03-18 | TRUE | 2026-04-03 |  | 2026-03-23 |  |  |  |  | YES | [8 empty] | None Available | NO |  | YES | Q:\Jobs\26011 - 2nd Ave Mockup Build\03_Engineering\02_FD Docs\ST01 | NO | [6 empty] | TruLaser 3040 |  | TRUE |  |  |  | TRUE |  | TruLaser 3040 | [9 empty] | TRUE |  |  | TRUE | [7 empty] | 26011 | ST |  | 01 |  | 1 | 26011-ST01.1 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 5 | 3 | [10 empty] | Customer Pick Up |  |  | Flat Laser | Brake TruLaser 3040 Weld | 2026-03-17 | 2026-03-18 | 2 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Chris Gambrel - @jdorsey@jwmcd.com @dhasty@jwmcd.com flat program completed. | 1010 |  | Wylie McDougall | Jonathan Dorsey | David Hasty | 26011-ST01 In-House | TRUE | 2026, Week 13
198 | 26011-ST1.1 |  | 2nd Ave Mockup Build | 185 2nd ave Nashville, TN 37201 | Wylie McDougall | 615.426.7650 | TUBE SUPPORT SYSTEM |  | 2x2 Angle that supports the trough | 2x2 Angle that supports the trough | SKETCHES PROGRAM FILES |  | Q:\Jobs\26011 - 2nd Ave Mockup Build\04_Production\26011ST1.1 | N/A | N/A | N/A | 0 | 1 | 1 | 0 | 0 | 1 @ 20' | 00:00:13 | 2"x2"x16' Alum Angle, No Grain | Alum Angle | 2"x2"x16' | No |  |  | 4 | -10 | Hunter Clouse | David Hasty |  |  |  | Jonathan Dorsey | David Hasty | Jonathan Dorsey |  |  | Issiah Havens |  | TRUE |  | Jonathan Dorsey | 2026-03-11 16:36 | TRUE | 2026-04-01 | 2026-03-18 | TRUE | 2026-04-03 |  | 2026-03-23 |  |  |  |  | YES | [8 empty] | Approved | NO |  | YES | Q:\Jobs\26011 - 2nd Ave Mockup Build\03_Engineering\02_FD Docs\ST01 | NO | [6 empty] | 7000 TubeLaser 20 |  | TRUE |  |  |  |  | TRUE | 7000 TubeLaser 20 | [20 empty] | 26011 | ST |  | 1.1 |  | 1.1 | 26011-ST01.1 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 1 | [10 empty] | Customer Pick Up |  |  | Tube Laser | 7000 TubeLaser 20 | 2026-03-18 | 2026-03-18 | 1 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Wylie McDougall | Jonathan Dorsey | David Hasty | 26011-ST1.1 In-House | TRUE | 2026, Week 13
199 | 26009-FS01 |  | 5th & Summer Leasing Office | 725 South 5th Street Nashville, TN 37206 | Cole Norona | 931.591.9340 | 400 |  | Color Matched Screws under job 24080 | Depth of the ACM band 1 1/8". Once drafter assigned, please reach out to me as there is a small area on the separate window section on the South Elevation that came out to 3/4" due to the waterproof/sheathing stuck out further and wanted to review that together. No shop drawings - we will use our LO to submit to GC for approval. Attached old install drawings from the same building in case you need as reference (may not need them or irrelevant) | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 23 | 9 | [6 empty] | 4mm X 62" X 196", Elegant Black FR ACM, No Grain | FR ACM | 4mm X 62" X 196", Elegant Black | No |  |  | 101 | -10 | Unassigned | Denis Usatenko |  | Denis Usatenko | [5 empty] | Arnold Jurado, Issiah Havens | [5 empty] | 2026-03-13 08:18 | TRUE | 2026-04-03 |  |  |  |  | 2026-04-20 |  |  |  |  | YES | 3 | [5 empty] | MATCH COLOR | YES | N/A (Process Customer Provided Blanks) | YES | Q:\Jobs\26009 - 5th & Summer Leasing Office\03_Engineering\02_FD Docs\26009FS01 5th & Summer Leasing Office\Scan | NO |  | NO | [6 empty] | LO Check | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 26009 | FS |  | 01 |  | 1 | 26009-FS01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 9 | 16 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - @cnorona@jwmcd.com Are we good to sketch? | 1010 |  | Cole Norona |  |  | 26009-FS01 In-House |  | 2026, Week 17
200 | 24051-FS90 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | NORTH LEVEL 150 |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 19268 | 117 | [6 empty] | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 2 | -10 | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  |  |  | Hennadii Stakhurskyi | 2026-03-13 14:13 |  | 2026-04-03 |  |  |  |  | 2026-04-24 |  |  |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Float | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 90 |  | 90 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 16 | 240 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS90 In-House |  | 2026, Week 17
201 | 24051-FS91 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | NORTH LEVEL 300 |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 19268 | 36 | [6 empty] | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 2 | -10 | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  |  |  | Hennadii Stakhurskyi | 2026-03-13 14:26 |  | 2026-04-03 |  |  |  |  | 2026-04-24 |  |  |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Float | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 91 |  | 91 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 40 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS91 In-House |  | 2026, Week 17
202 | 24051-FS227 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | NORTH LEVEL 300 |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 19268 | 119 | [6 empty] | 4mm X 62" X 196", MOONSTONE METALLIC FR ACM, Grain | FR ACM | 4mm X 62" X 196", MOONSTONE METALLIC | Yes |  |  | 2 | -10 | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  |  |  | Hennadii Stakhurskyi | 2026-03-13 14:43 |  | 2026-04-03 |  |  |  |  | 2026-04-24 |  |  |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Float | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 227 |  | 227 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS227 In-House |  | 2026, Week 17
203 | 25002-FS13 |  | Med Center Health | 250 Park Street Bowling Green, KY 42101 | Carlos Silva | 980.246.6545 | 600 |  |  | Canopy main entrance. |  | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-3/4" Reveals * ( LF) JR2 |  |  |  | 2014 | 30 | [6 empty] | ACM: 4mm X 62" X 196", MICA GRAY FR ACM, Grain | FR ACM | ACM: 4mm X 62" X 196", MICA GRAY | Yes |  |  | 1 | -10 | Ailen Niedfeld | Denis Usatenko | Ailen Niedfeld | Ailen Niedfeld | Denis Usatenko | Ailen Niedfeld | Denis Usatenko | Ailen Niedfeld |  | Arnold Jurado, Issiah Havens |  |  |  |  | Ailen Niedfeld | 2026-03-13 14:44 | TRUE | 2026-04-03 |  |  |  |  | 2026-04-17 |  |  |  |  | YES | 00 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25002 - Med Center Health\03_Engineering\02_FD Docs\MCH - Northwest SCAN\med center 11.6 | NO |  | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25002 | FS |  | 13 |  | 13 | 25002-FS16 |  | TRUE | 2026-03-27 |  | 15 (ON HOLD) |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | 15 | 8 | 8 | [10 empty] | Semi |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Ailen Niedfeld - Still need the slope on the bottom detail 56/615. AND mullion(s) location of all 3 windows/doors in relationship to the building. @csilva@jwmcd.com | 1010 |  | Carlos Silva | Ailen Niedfeld | Denis Usatenko | 25002-FS13 In-House |  | 2026, Week 16
204 | 24051-FS92 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | SOUTH LEVEL 300 PLEASE NOTE DIMENSION CHANGES DUE TO RFI 3442 INCLUDED. CHANGES ARE NOTED ON THE SECTIONS OVERLAID ON THE RELEASE DRAWINGS. |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 19268 | 104 | [6 empty] | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 9 | -5 | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  |  |  | Hennadii Stakhurskyi | 2026-03-13 16:08 |  | 2026-04-10 |  |  |  |  | 2026-05-01 |  |  |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Float | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 92 |  | 92 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 80 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS92 In-House |  | 2026, Week 18
205 | 24051-FS93 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | SOUTH LEVEL 150 |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) 1-1/8" Reveals * ( LF) JR-Extended |  |  |  | 19268 | 131 | 133 | 43 |  |  |  |  | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 5 | -8 | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  |  |  | Denis Usatenko, Hennadii Stakhurskyi | 2026-03-16 11:30 |  | 2026-04-07 |  |  |  |  | 2026-04-28 |  |  |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Correction | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 93 |  | 93 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 16 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - @hstakhurskyi@jwmcd.com Corrections reqyuired. | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS93 In-House |  | 2026, Week 18
206 | 24079-FS103 |  | Nashville Youth Campus | 1354 Brick Church Pike Nashville, TN 37207 | Joe Hoyle | 828.334.7808 | 400 |  | AREA A - Tower ACM West/South Elevations | REFERENCE AAN DRAWINGS WHEN WORKING ON LAYOUT. GRAIN OF PANELS AT WEST AND EAST ELEVATIONS WAS ROTATED TO REMOVE THE HORIZONTAL JOINT ON THE SKYWARD PORTION OF THE TOWER PARAPET. | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  |  | 111 | [6 empty] | 4mm 62" x 196" 'RRM River Rock Grey' FR ACM, Grain | FR ACM | 4mm 62" x 196" 'RRM River Rock Grey' | Yes |  |  | 2 | 3 | Nadira Vlatkovic | Denis Usatenko |  | Denis Usatenko | Nadira Vlatkovic |  |  |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-03-16 12:29 |  | 2026-04-20 |  |  |  |  | 2026-05-11 |  |  |  |  | YES | 300 | [5 empty] | MATCH COLOR | YES | Approved As Noted | YES | Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - NYCE - FS103 - SW Tower Scans | NO |  | YES | Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - CALCS | [5 empty] | LO Check | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24079 | FS |  | 103 |  | 103 | 24079-FS303 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 40 | 80 | [10 empty] | Customer Pick Up In House |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Joe Hoyle |  |  | 24079-FS103 In-House |  | 2026, Week 20
207 | 24051-FS94 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | LEVEL 350 SOUTH AND WEST |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 19268 | 79 | [6 empty] | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 5 | -8 | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  |  |  | Denis Usatenko, Hennadii Stakhurskyi | 2026-03-16 12:47 |  | 2026-04-07 |  |  |  |  | 2026-04-28 |  |  |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Float | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 94 |  | 94 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 16 | 140 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS94 In-House |  | 2026, Week 18
208 | 24079-BM04D |  | Nashville Youth Campus | 1354 Brick Church Pike Nashville, TN 37207 | Joe Hoyle | 828.334.7808 |  |  | Sub-framing for AFC Panels Shipping to PowderWorx for post-painting. Materials need to be RUST-FREE before leaving the shop. PW will reject our delivery if there is rust on the materials. Sheet count pulled from inventory. Let me know if it's incorrect. | 3-5/8" DEEP version of BM04C ( 1-1/2" X 3-5/8" X 1-1/2" ) | SKETCHES PROGRAM | TBD | Q:\Jobs\24079 - Nashville Youth Campus\04_Production\24079BM04D | Unavailable | 386 |  | 185 | 1295 | 1 | 0 | 0 | 185 | 01:39:54 | 16GA 48" X 120" COLD ROLLED STEEL Steel Sheet, No Grain | Steel Sheet | 16GA 48" X 120" COLD ROLLED STEEL | No |  |  | 1 | -6 | Joshua Davis | Denis Usatenko | David Hasty |  |  | Jonathan Dorsey | David Hasty | Jonathan Dorsey | TRUE |  |  | Chris Gambrel | TRUE |  |  | 2026-03-16 14:01 |  | 2026-04-02 | 2026-03-27 |  | 2026-04-09 | 2026-04-06 | 2026-04-13 |  |  |  |  | YES | 185 |  | TRUE | Powder Coat | Matte Black PowderWorx Jason Makuch jmakuch@pwx615.com | Coating Ship To Site | [14 empty] | TruPunch 5000 |  | TRUE | [6 empty] | TRUE | TruPunch 5000 |  | TRUE | [5 empty] | TRUE | [10 empty] | 24079 | BM |  | 04D |  | 0 | 24079-BM00 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 40 | [10 empty] | Customer Pick Up In House |  |  | Punch | Brake Powder Coat Shear TruPunch 5000 | 2026-03-27 | 2026-03-27 | 1 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Joe Hoyle - Thanks, I'll get more materials ordered. | 1010 |  | Joe Hoyle | Jonathan Dorsey | David Hasty | 24079-BM04D In-House |  | 2026, Week 16
209 | 24051-FS95 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | LEVEL 400 SOUTH ELEVATION |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 19268 | 96 | [6 empty] | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 5 | -8 | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  |  |  | Denis Usatenko, Hennadii Stakhurskyi | 2026-03-16 15:35 |  | 2026-04-07 |  |  |  |  | 2026-04-28 |  |  |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Float | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 95 |  | 95 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 16 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS95 In-House |  | 2026, Week 18
210 | 24051-FS228 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | SOUTH ELEVATION LEVEL 300 |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 19268 | 95 | [6 empty] | 4mm X 62" X 196", MOONSTONE METALLIC FR ACM, Grain | FR ACM | 4mm X 62" X 196", MOONSTONE METALLIC | Yes |  |  | 5 | -8 | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  |  |  | Denis Usatenko, Hennadii Stakhurskyi | 2026-03-16 15:49 |  | 2026-04-07 |  |  |  |  | 2026-04-28 |  |  |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Float | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 228 |  | 228 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 16 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS228 In-House |  | 2026, Week 18
211 | 24051-FS96 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | WEST LEVEL 300 |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 19268 | 52 | [6 empty] | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TOB BLACK | No |  |  | 9 | -5 | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  |  |  | Denis Usatenko, Hennadii Stakhurskyi | 2026-03-17 07:25 |  | 2026-04-10 |  |  |  |  | 2026-05-01 |  |  |  |  | YES | 1000 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Float | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 96 |  | 96 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 16 | 100 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS96 In-House |  | 2026, Week 18
212 | 24051-FS229 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | WEST LEVEL 300 |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 19268 | 109 | [6 empty] | 4mm X 62" X 196", MOONSTONE METALLIC FR ACM, Grain | FR ACM | 4mm X 62" X 196", MOONSTONE METALLIC | Yes |  |  | 9 | -5 | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  |  |  | Denis Usatenko, Hennadii Stakhurskyi | 2026-03-17 07:53 |  | 2026-04-10 |  |  |  |  | 2026-05-01 |  |  |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Float | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 229 |  | 229 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 16 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS229 In-House |  | 2026, Week 18
213 | 24051-FS230 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | EAST LEVEL 200 |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 19268 | 67 | [6 empty] | 4mm X 62" X 196", MOONSTONE METALLIC FR ACM, Grain | FR ACM | 4mm X 62" X 196", MOONSTONE METALLIC | Yes |  |  | 9 | -5 | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  |  |  | Denis Usatenko, Hennadii Stakhurskyi | 2026-03-17 09:09 |  | 2026-04-10 |  |  |  |  | 2026-05-01 |  |  |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Float | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 230 |  | 230 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 16 | 40 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS230 In-House |  | 2026, Week 18
214 | 24079-BM01B |  | Nashville Youth Campus | 1354 Brick Church Pike Nashville, TN 37207 | Joe Hoyle | 828.334.7808 |  |  | Courthouse 2" zee balance. Cottage/Garage/ARF to come later... | Slotted zee-mtl to match BM01. |  | TBD | Q:\Jobs\24079 - Nashville Youth Campus\04_Production\24079BM01B | N/A | N/A | N/A | 0 | 2217 | 1 | 0 | 0 | 247 | 05:30:58 | 48" x 120" Galvanized Sheet 16 ga Galv Sheet, No Grain | Galv Sheet | 48" x 120" Galvanized Sheet 16 ga | No |  |  | 3 | -4 | Samantha Krantz, Shane Jones | Denis Usatenko | David Hasty |  |  | Jonathan Dorsey | David Hasty | Jonathan Dorsey |  |  |  | Chris Gambrel | TRUE |  | Jonathan Dorsey | 2026-03-18 13:13 |  | 2026-04-06 | 2026-03-24 |  | 2026-04-13 |  | 2026-04-15 |  |  |  |  | YES | 999 | [19 empty] | Shear |  | TRUE | [6 empty] | TRUE | TruPunch 5000 |  | TRUE | TRUE | [15 empty] | 24079 | BM |  | 01B |  | 0 | 24079-BM00 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 80 | [10 empty] | Customer Pick Up In House |  |  | Punch | Cidan Shear TruPunch 5000 | 2026-03-24 | 2026-03-24 | 1 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Chris Gambrel - @jdorsey@jwmcd.com @dhasty@jwmcd.com flat program completed, 247 sheets X 9 parts = 2223 parts after shear. | 1010 |  | Joe Hoyle | Jonathan Dorsey | David Hasty | 24079-BM01B In-House |  | 2026, Week 16
215 | 24074-FS08 |  | DIDD ACM | 275 Stewarts Ferry Pike Nashville, TN 37214 | Dillon Bowman | 518.860.9477 | 400 |  | Release 5 (1/3) - Pages: 210 - most in FS06-07, 214 - most is in FS07, 223, 224, 226, 229, 230, 231, 232 |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 1328 | 186 | [6 empty] | 4mm x 62 x 196 Dark Gray, Alfrex 24074 FR ACM, No Grain | FR ACM | 4mm x 62 x 196 Dark Gray, Alfrex 24074 | No |  | MTPK | 1 | 1 | Nadira Vlatkovic | Denis Usatenko |  | Denis Usatenko | Nadira Vlatkovic | Chance Dill | Denis Usatenko | Chance Dill |  | Arnold Jurado, Issiah Havens |  |  |  |  | Chance Dill | 2026-03-19 08:30 |  | 2026-04-16 |  |  |  |  | 2026-05-07 |  |  |  |  | YES | 62 | [5 empty] | MATCH COLOR | YES | Approved As Noted | YES | Q:\Jobs\24074 - DIDD ACM\03_Engineering\02_FD Docs\24074 - FS08 and FS09 | YES | Q:\Jobs\24074 - DIDD ACM\03_Engineering\02_FD Docs\24074 - FS08 and FS09 | NO | [6 empty] | LO Check | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24074 | FS |  | 08 |  | 8 | 24074-FS10 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 90 | 335 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Dillon Bowman | Chance Dill | Denis Usatenko | 24074-FS08 In-House |  | 2026, Week 19
216 | 24074-FS09 |  | DIDD ACM | 275 Stewarts Ferry Pike Nashville, TN 37214 | Dillon Bowman | 518.860.9477 | 400 |  | Release 5 (2/3) - Pages: 223, 234, 235, 237, 239, 240 | Release 5 (2/3) - Pages: 223, 234, 235, 237, 239, 240 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 1328 | 120 | [6 empty] | 4mm x 62 x 196 - Dark Gray, Alfrex 24074 FR ACM, No Grain | FR ACM | 4mm x 62 x 196 - Dark Gray, Alfrex 24074 | No |  | MTPK | 4 | 6 | Nadira Vlatkovic | Denis Usatenko |  | Denis Usatenko | Nadira Vlatkovic | Chance Dill | Denis Usatenko | Chance Dill |  | Arnold Jurado, Issiah Havens |  |  |  |  | Chance Dill | 2026-03-19 08:35 |  | 2026-04-23 |  |  |  |  | 2026-05-14 |  |  |  |  | YES | 141 | [5 empty] | MATCH COLOR | YES | Approved As Noted | YES | Q:\Jobs\24074 - DIDD ACM\03_Engineering\02_FD Docs\24074 - FS08 and FS09 and FS10 | YES | Q:\Jobs\24074 - DIDD ACM\03_Engineering\02_FD Docs\24074 - FS08 and FS09 and FS10 | NO | [6 empty] | LO Check | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24074 | FS |  | 09 |  | 9 | 24074-FS10 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 60 | 200 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Dillon Bowman | Chance Dill | Denis Usatenko | 24074-FS09 In-House |  | 2026, Week 20
217 | 24074-FS10 |  | DIDD ACM | 275 Stewarts Ferry Pike Nashville, TN 37214 | Dillon Bowman | 518.860.9477 | 400 |  | Release 5 (3/3) - 214, 223, 224, 242, 243, 246 | Release 5 (3/3) - 214, 223, 224, 242, 243, 246 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS |  | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  | 1328 | 130 | [6 empty] | 4mm 62 x 196 - Black, Alfrex 24074 FR ACM, No Grain | FR ACM | 4mm 62 x 196 - Black, Alfrex 24074 | No |  | MTPK | 6 | 11 | Nadira Vlatkovic | Denis Usatenko |  | Denis Usatenko | Nadira Vlatkovic | Chance Dill | Denis Usatenko | Chance Dill |  | Arnold Jurado, Issiah Havens |  |  |  |  | Chance Dill | 2026-03-19 08:39 |  | 2026-04-30 |  |  |  |  | 2026-05-21 |  |  |  |  | YES | 51 | [5 empty] | MATCH COLOR | YES | Approved As Noted | YES | Q:\Jobs\24074 - DIDD ACM\03_Engineering\02_FD Docs\24074 - FS08 and FS09 and FS10 | YES | Q:\Jobs\24074 - DIDD ACM\03_Engineering\02_FD Docs\24074 - FS08 and FS09 and FS10 | NO | [6 empty] | LO Check | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24074 | FS |  | 10 |  | 10 | 24074-FS10 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 75 | 234 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Dillon Bowman | Chance Dill | Denis Usatenko | 24074-FS10 In-House |  | 2026, Week 21
218 | 25061-FS01 |  | BNA Concourse A | 1 Terminal Drive Nashville, TN 37214 | Andre Van Der Merwe | 315.261.0333 | 400 |  |  | MOCK UP PANELS USE MATERIAL FROM 23029 CONC D | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS * CODING FILES | * 14 LF JR2 * 3 LF 1 5/8" COLOR MATCHING REVEALS * 8 PCS CORNER CLIPS * 16 PCS COLOR MATCHING REVEALS | Q:\Jobs\25061 - BNA Concourse A\04_Production\25061FS01 | 0.2412% | 3 | 1244 | 3 | 3 | 3 | 33 | 3 | 1 | 00:22:58 | 4mm X 62" X 196", CHAMPAGNE GOLD [23029] FR ACM, Grain | FR ACM | 4mm X 62" X 196", CHAMPAGNE GOLD [23029] | Yes |  |  | 49 | 5 | Ramon Estrada, Shane Watson | Denis Usatenko |  | Gabriela Herrera |  | Gabriela Herrera | Nadira Vlatkovic | Gabriela Herrera |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Gabriela Herrera | 2026-03-19 13:50 | TRUE | 2026-04-09 | 2026-04-06 | TRUE | 2026-04-22 |  | 2026-04-24 |  |  |  |  | YES | 20 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Ready to Ship | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 25061 | FS |  | 01 |  | 1 | 25061-FS01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 8 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-04-06 | 2026-04-06 | 1 |  | QC Not Requested | 2026-04-09 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-04-10 |  | Issue Still in Process | Issiah Havens - @gherrera@jwmcd.com @jdavis@jwmcd.com programmed | 1010 |  | Andre Van Der Merwe | Gabriela Herrera | Nadira Vlatkovic | 25061-FS01 In-House |  | 2026, Week 17
219 | 24081-RO01 |  | DLR DFW37 | 1502 Ferris Rd Garland, TX 75044 | Cole Norona | 931.591.9340 | 400 |  | POST PAINTED INSTRUCTIONS *SEE FOLLOWING NOTES*: -Do NOT apply stiffeners; crate the stiffeners/1199 so post painter can apply them. Stiffeners MUST have tape on them prior to shipping. -Mark the panel number on the side that is NOT painted in marker, NO STICKER -Do NOT tape extrusions -Extremely important that the part list is included in the crate for post painter | TAKING A SHEET OF MATERIAL FROM 25045 WITH CARLOS SILVA'S APPROVAL | SKETCHES PROGRAMMING FILES EXTRUSION CUT LIST |  | Q:\Jobs\24081 - DLR DFW37\04_Production\24081-RO01 | Unavailable | 480 | 0 | 1 | 1 | 1 | 10 | 0 | 1 | 00:03:10 |  | Alum Sheet | .125" X 48" X 102", 3003 | No |  |  | 13 | -6 | Ramon Estrada, Shane Watson | David Hasty | David Hasty |  |  | Frank Dean | David Hasty | Frank Dean |  |  |  | Chris Gambrel | TRUE |  | Frank Dean | 2026-03-23 08:56 | TRUE | 2026-04-13 | 2026-03-24 | TRUE | 2026-04-09 | 2026-03-26 | 2026-03-26 |  |  |  | 2026-04-01 | YES | 1 |  | TRUE | Post Paint | UNITED ENERTECH ATTN: LAURA GREGG 3005 S. HICKORY ST CHATTANOOGA, TN 37407 | Coating Ship To Site | FAB SCREW | YES | Approved | NO |  | NO |  | NO |  | (1) 1078 | FS02 |  |  |  | Shipped To Painter |  | TRUE | [6 empty] | TRUE | 7000 TruMatic | [7 empty] | TRUE | [7 empty] | TRUE |  |  | 24081 | RO |  | 01 |  | 1 | 24081-RO01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 2 | [10 empty] | Hot Shot |  |  | Punch | 7000 TruMatic Brake Fab Post Paint | 2026-03-23 | 2026-03-24 | 2 |  | Issue Still In Process |  | Crating Start Date Not Recorded | David Hasty | Ramon Estrada, Shane Watson | 2026-03-31 |  | Issue Still in Process | Cole Norona - @tgraves@jwmcd.com @rharmon@jwmcd.com @jmcpherson@jwmcd.com When can we expect this panel to be ready to ship? This was expected to be ready by 3/26 and post painter is at a halt till they receive. It is just one panel for remake and has been with the shop since 3/24 | 1010 |  | Cole Norona | Frank Dean | David Hasty | 24081-RO01 In-House |  | 2026, Week 13
220 | 25010-FS09 |  | TOA Spring Hill MOB | Reserve Blvd Spring Hill, TN 37174 | Cole Norona | 931.591.9340 | 400 |  |  | 224 ELEV 222 RCP 211 RCP & COLUMNS 205 COLUMNS | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 819 | 111 | [6 empty] | 4mm X 62" X 196", Tender Oak FR ACM, Grain | FR ACM | 4mm X 62" X 196", Tender Oak | Yes |  |  | 2 | 3 | Samuel Lucas | Denis Usatenko | Samuel Lucas | Samuel Lucas |  | Samuel Lucas | Denis Usatenko | Samuel Lucas |  | Arnold Jurado, Issiah Havens |  |  |  |  | Samuel Lucas | 2026-03-23 12:42 |  | 2026-04-20 |  |  |  |  | 2026-05-11 |  |  |  |  | YES | 67 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25010 - TOA Spring Hill MOB\03_Engineering\02_FD Docs\25010FS09\SCANS | YES | Q:\Jobs\25010 - TOA Spring Hill MOB\03_Engineering\02_FD Docs\25010FS09\DIMENSIONS | YES | Q:\Jobs\25010 - TOA Spring Hill MOB\03_Engineering\02_FD Docs\25010FS09\CALCS | [5 empty] | Correction | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25010 | FS |  | 09 |  | 9 | 25010-FS09 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 20 | 40 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - @slucas@jwmcd.com Corrections required. | 1010 |  | Cole Norona | Samuel Lucas | Denis Usatenko | 25010-FS09 In-House |  | 2026, Week 20
221 | 24069-RM05 |  | TCAT Pulaski | 1233 East College Street Pulaski, TN 38478 | Chris Buttrey | 615.517.9885 | GENESIS |  | Ships to spectrum | We originally drew this as stainless steel. I modified the drawing to say Gray velvet. u can use the sketch I have included or modify original. | SKETCHES PROGRAMMING FILES |  | Q:\Jobs\24069 - TCAT Pulaski\04_Production\24069RM05 | Unavailable | 1159 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 00:02:51 | .080" X 60" X 108", 3003 Alum Sheet, No Grain | Alum Sheet | .080" X 60" X 108", 3003 | No |  |  | 14 | -2 | Ramon Estrada, Shane Watson | David Hasty | David Hasty |  |  | Frank Dean | David Hasty | Frank Dean |  |  |  | Chris Gambrel | TRUE |  | Frank Dean | 2026-03-23 13:40 |  | 2026-03-27 | 2026-03-24 |  | 2026-04-15 | 2026-04-02 | 2026-04-17 |  |  |  | 2026-04-09 | YES | 42 |  | TRUE | Post Paint | Spectrum | Coating Ship To Site | N/A | N/A | Approved | NO |  | NO |  | NO |  | (1) 1237 | FS08 |  | SHIPPING |  | Shipped To Painter |  | TRUE | [6 empty] | TRUE | 7000 TruMatic | [7 empty] | TRUE | [10 empty] | 24069 | RM |  | 05 |  | 5 | 24069-RM05 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 2 | [10 empty] | Hot Shot |  |  | Punch | 7000 TruMatic Brake Post Paint | 2026-03-23 | 2026-03-24 | 2 |  | QC Not Requested | 2026-04-06 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-04-07 |  | Issue Still in Process | Chris Gambrel - @fdean@jwmcd.com @dhasty@jwmcd.com flat program completed | 1010 |  | Chris Buttrey | Frank Dean | David Hasty | 24069-RM05 In-House |  | 2026, Week 16
222 | 24079-FS101.1 |  | Nashville Youth Campus | 1354 Brick Church Pike Nashville, TN 37207 | Joe Hoyle | 828.334.7808 | 400 |  | AREA B - ACM Release | AREA B - ACM Release 208, 209, 210 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (1200 LF) 1-5/8" Reveals * (700 LF) - JR2 * (1500 LF) 16ga, flat-strap | Q:\Jobs\24079 - Nashville Youth Campus\04_Production\24079FS101.1 | Unavailable | 549 |  | 163 | 189 | 140 | 1512 | 1200 | 99 | 30:39:09 | 4mm X 62" X 196" 'CWM - Cloud White MATTE' FR ACM, Grain | FR ACM | 4mm X 62" X 196" 'CWM - Cloud White MATTE' | Yes |  | MTPK | 48 | 4 | Ramon Estrada, Shane Watson | Denis Usatenko | Denis Usatenko | Denis Usatenko | Denis Usatenko | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Denis Usatenko, Hennadii Stakhurskyi | 2026-03-24 08:54 | TRUE | 2026-04-14 | 2026-04-03 | TRUE | 2026-04-21 |  | 2026-02-23 |  | 2026-02-23 |  |  | YES | 275 | [5 empty] | MATCH COLOR | NO | Approved As Noted | YES | Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - NYCE - FS01 AREA B | YES | Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - NYCE - FS01 AREA B\Photos | YES | TBD | [5 empty] | Ready to Ship | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24079 | FS |  | 101.1 |  | 101.1 | 24079-FS303 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 120 | 200 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-04-02 | 2026-04-03 | 2 |  | QC Not Requested | 2026-04-09 | 6 | David Hasty | Ramon Estrada, Shane Watson | 2026-04-16 |  | Issue Still in Process | Issiah Havens - @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com programmed | 1010 |  | Joe Hoyle | Hennadii Stakhurskyi | Denis Usatenko | 24079-FS101.1 In-House |  | 2026, Week 09
223 | 25029-MU10 |  | Lourdes CC Phase 2 | 1510 Lone Oak Road Paducah, KY 42003 | Dillon Bowman | 518.860.9477 | CUSTOM ARCH |  | Memorial Tree Base Plate (Temp Plate for Anchors) -Give to Dillon Bowman once complete | Memorial Tree Base Plate (Temp Plate for Anchors) Sketch with Paul Roberts | SKETCHES PROGRAM |  | Q:\Jobs\25029 - Lourdes CC Phase 2\04_Production\25029MU10 | 78.05% | 128 | 164 | 1 | 1 | 1 | 0 | 0 | 1 | 00:00:52 | 1/4 x 48 x 60 - For Processing Inventory Alum Sheet, No Grain | Alum Sheet | 1/4 x 48 x 60 - For Processing Inventory | No |  |  | 6 | 3 | Hunter Clouse | David Hasty |  |  |  | Jonathan Dorsey | David Hasty | Jonathan Dorsey |  |  | Chris Gambrel |  | TRUE |  | Jonathan Dorsey | 2026-03-24 11:17 | TRUE | 2026-04-14 | 2026-04-02 | TRUE | 2026-04-20 |  | 2026-03-27 |  |  |  |  | YES |  | 2026-03-26 |  |  |  |  | N/A | N/A | N/A (Process Customer Provided Blanks) | NO |  | NO |  | NO | [6 empty] | TruLaser 3040 |  | TRUE |  |  |  | TRUE |  | TruLaser 3040 | [20 empty] | 25029 | MU |  | 10 |  | 10 | 25029-MU10 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 2 | 2 | [10 empty] | In House |  |  | Flat Laser | TruLaser 3040 | 2026-04-02 | 2026-04-02 | 1 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Chris Gambrel - @jdorsey@jwmcd.com @dhasty@jwmcd.com flat program completed | 1010 |  | Dillon Bowman | Jonathan Dorsey | David Hasty | 25029-MU10 In-House |  | 2026, Week 13
224 | 25017-RO02 |  | Nashville Yards Park | Nashville, TN 37203 | Dillon Bowman | 518.860.9477 | 400 |  | Re-Order of Panel from RO01 | Re-Order of Panel from RO01 | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS * CODING FILES | * 14 LF 1 5/8" COLOR MATCHING REVEALS * 4 PCS CORNER CLIPS * 8 PCS COLOR MATCHING SCREWS | Q:\Jobs\25017 - Nashville Yards Park\04_Production\25017RO02 | 186.8% | 99 | 53 | 1 | 3 | 2 | 12 | 14 | 1 | 00:13:46 |  | FR ACM | 4mm x 62 x 196 - Midnight Black | No |  |  | 3 | -4 | Corey Howse | David Hasty |  |  |  | Gabriela Herrera |  |  |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Gabriela Herrera | 2026-03-24 12:42 | TRUE | 2026-04-14 | 2026-03-25 |  | 2026-04-13 |  | 2026-04-15 |  |  |  |  | YES | 2 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO |  | 202-1A19 | RO01 |  |  |  | Clean and Brake |  | TRUE | TRUE | AXYZ Titans Line | [6 empty] | TRUE | [13 empty] | TRUE | TRUE |  |  | 25017 | RO |  | 02 |  | 2 | 25017-RO02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 3 | [10 empty] | In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab Roller | 2026-03-25 | 2026-03-25 | 1 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Issiah Havens - @gherrera@jwmcd.com @jdavis@jwmcd.com programmed | 1010 |  | Dillon Bowman | Gabriela Herrera |  | 25017-RO02 In-House |  | 2026, Week 16
225 | 25029-FS50 |  | Lourdes CC Phase 2 | 1510 Lone Oak Road Paducah, KY 42003 | Dillon Bowman | 518.860.9477 | GRAVITY |  | Memorial Garden Screen Panels | Memorial Garden Screen Panels ENG - panels have changed to 1/4" Plate. | SKETCHES |  |  |  |  | 164 | 8 | 4 | 4 | 0 | 0 |  |  | 1/4" 60 x 120 6061 - 25029 Alum Sheet, No Grain | Alum Sheet | 1/4" 60 x 120 6061 - 25029 | No |  |  | 1 | 3 | Jonathan Dorsey | David Hasty | David Hasty |  |  | Jonathan Dorsey | David Hasty | Jonathan Dorsey |  |  |  | Chris Gambrel |  |  | Jonathan Dorsey | 2026-03-24 13:07 |  | 2026-04-20 |  |  |  |  | 2026-05-11 |  |  |  |  | NO | 9 | 2026-03-30 |  |  |  |  | N/A | N/A | Approved As Noted | NO |  | NO |  | YES | Q:\Jobs\25029 - Lourdes CC Phase 2\03_Engineering\02_FD Docs\25029 - FS50 | [5 empty] | Correction |  | TRUE | [6 empty] | TRUE | [8 empty] | TRUE | [10 empty] | 25029 | FS |  | 50 |  | 50 | 25029-FS50 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 16 | [10 empty] | In House |  |  | Punch | Brake Punch |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | David Hasty - @jdorsey@jwmcd.com Correction required | 1010 |  | Dillon Bowman | Jonathan Dorsey | David Hasty | 25029-FS50 In-House |  | 2026, Week 20
226 | 25022-FS12 |  | Vantage VA15 | 45210 Vantage Data Plaza Sterling, VA 20166 | Thomas Mooers |  | 400 |  | The Coping Panels on Page 207 will be caulked in the field. | Elevations 13-14/207 Elevation 15/208 Elevation 17/209 (yellow panels). | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (750 LF) 1-5/8" Reveals * (197 LF) JR2 * 6 PCS 1' x 1' x 1-5/8" L SHAPED REVEALS * 36 PCS CORNER CLIPS * 72 PCS ﻿COLOR MATCHING SCREWS | Q:\Jobs\25022 - Vantage VA15\04_Production\25022FS12 | 150.7% | 919 | 610 | 76 | 77 | 43 | 621 | 762 | 150 x 50 in 11 SHEETS 196 x 62 in 24 SHEETS | 00d10h19m54s | 4mm X 50" X 150", Cadet Gray 4mm X 62" X 196", Cadet Gray FR ACM, Grain | FR ACM | 4mm X 50" X 150", Cadet Gray 4mm X 62" X 196", Cadet Gray | Yes |  |  | 4 | 9 | Mitch Chancey | Denis Usatenko |  | Gabriela Herrera |  | Gabriela Herrera | Denis Usatenko | Gabriela Herrera |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Gabriela Herrera | 2026-03-24 13:18 | TRUE | 2026-04-14 | 2026-04-10 | TRUE | 2026-04-28 |  | 2026-04-24 |  |  |  |  | YES | 19 | [5 empty] | Gray | YES | Approved | NO |  | YES | Q:\Jobs\25022 - Vantage VA15\03_Engineering\02_FD Docs | YES | Standard | [5 empty] | Crating | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25022 | FS |  | 12 |  | 12 | 25022-FS12 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 5 | 55 | [10 empty] | Hot Shot |  |  | AXYZ | AXYZ Clean and Brake Fab | 2026-04-10 | 2026-04-10 | 1 |  | QC Not Requested | 2026-04-15 | 2 (In Progress) | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Arnold Jurado - @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Thomas Mooers | Gabriela Herrera | Denis Usatenko | 25022-FS12 In-House |  | 2026, Week 17
227 | 24079-FL13 |  | Nashville Youth Campus | 1354 Brick Church Pike Nashville, TN 37207 | Joe Hoyle | 828.334.7808 |  |  | Jamb and Drip flashings for remainder of level 1 & 2 of NYCE Courthouse. Customer pick-up. | 98 x shallow drip 48 x shallow j Drawings located in FD Docs folder under FL-013 (Server issues ATM, drawings to be uploaded ASAP) | * Sketches | TBX | Q:\Jobs\24079 - Nashville Youth Campus\04_Production\24079FL13 | N/A | N/A | N/A | 0 | 146 | 2 | 0 | 0 | 32.5 - SHTS | na | .032" Alum. 48" x 120" TBX Silver Alum Sheet, Grain | Alum Sheet | .032" Alum. 48" x 120" TBX Silver | Yes |  |  | 38 | -7 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-03-24 14:27 | TRUE | 2026-04-01 | 2026-03-24 |  | 2026-04-08 |  | 2026-04-10 |  |  |  |  | YES | 32 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 24079 | FL |  | 13 |  | 13 | 24079-FL14 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 6 | [10 empty] | Customer Pick Up |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2026-04-13 | 4 | David Hasty | Ramon Estrada, Shane Watson | 2026-04-16 |  | Issue Still in Process |  | 1010 |  | Joe Hoyle | Denis Usatenko |  | 24079-FL13 In-House |  | 2026, Week 15
228 | 24073-FS01 |  | DIDD Perf | 275 Stewarts Ferry Pike Nashville, TN 37214 | Dillon Bowman | 518.860.9477 | TUBE SUPPORT SYSTEM |  | DIDD Perf Screens CRATE WITH SCREWS ONLY, FOR PAINTER | DIDD Perf Screens - Calcs still pending for fastener strategy, submitting to get panels rolling, per Josh | [5 empty] | 55 | 53 | [6 empty] | .190 x 72 x 120 - 5052 Alum 24074 Alum Sheet, No Grain | Alum Sheet | .190 x 72 x 120 - 5052 Alum 24074 | No |  |  | 1 | 12 | Frank Dean | David Hasty | David Hasty |  |  | Frank Dean | David Hasty | Frank Dean |  |  |  | Chris Gambrel |  |  | Frank Dean | 2026-03-25 08:36 |  | 2026-05-01 |  |  |  | 2026-05-13 | 2026-05-22 |  |  |  |  | YES | 58 |  | TRUE | Post Paint | Commercial Painters Inc 350 Herron Dr, Nashville, TN 37210 Bobby Tate (615.405.6240) | Coating Ship Back To JWM | N/A | NO | Approved | YES | Q:\Jobs\24073 - DIDD Perf\03_Engineering\02_FD Docs\24073 - FS01 | NO |  | NO | [6 empty] | Sketch |  | TRUE | [6 empty] | TRUE | [8 empty] | TRUE | [10 empty] | 24073 | FS |  | 01 |  | 1 | 24073-FS01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 50 | 100 | [10 empty] | Hot Shot |  |  | Punch | Brake Post Paint Punch |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Dillon Bowman - 24" Confirmed by PWP For Fasteners @dhasty@jwmcd.com | 1010 |  | Dillon Bowman | Frank Dean | David Hasty | 24073-FS01 In-House |  | 2026, Week 21
229 | 25029-ST51 |  | Lourdes CC Phase 2 | 1510 Lone Oak Road Paducah, KY 42003 | Dillon Bowman | 518.860.9477 | GRAVITY |  | Tube Supports - will be welded to base plate (ST52) | Tubes - Calcs changed size of tubes and size of panels. See Notes in FD Folder. - Calcs pending only the anchor info | [5 empty] | N/A | 0 | 10 | 1 | 0 | 0 |  |  | 1/4 x 6 x 6 - Alum Tube - 6061-T6 (25029) Alum Tube, No Grain | Alum Tube | 1/4 x 6 x 6 - Alum Tube - 6061-T6 (25029) | No |  |  | 4 | 8 | Jonathan Dorsey | David Hasty | David Hasty |  |  | Jonathan Dorsey | David Hasty | Jonathan Dorsey |  |  | Arnold Jurado |  |  |  |  | 2026-03-26 09:30 |  | 2026-04-27 |  |  |  | 2026-05-11 | 2026-05-18 |  |  |  |  | NO |  | 2026-04-03 | TRUE | Powder Coat | PWX | Coating Ship Back To JWM |  |  | Approved As Noted | NO |  | NO |  | NO | [6 empty] | Correction | [28 empty] | 25029 | ST |  | 51 |  | 51 | 25029-ST73 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 3 | 5 | [10 empty] | In House |  |  |  | Powder Coat |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | David Hasty - @jdorsey@jwmcd.com Corrections required | 1010 |  | Dillon Bowman | Jonathan Dorsey | David Hasty | 25029-ST51 In-House |  | 2026, Week 21
230 | 25029-ST52 |  | Lourdes CC Phase 2 | 1510 Lone Oak Road Paducah, KY 42003 | Dillon Bowman | 518.860.9477 | TUBE SUPPORT SYSTEM |  | base plate - to be welded to ST51 Tubes |  |  | (0) TUBE, SILPRUF CAULK (0) LF 1/2" DENVER FOAM B-ROD (0) CS - RED 1/8" SHIMS (0) CS - BLACK 1/4" SHIMS (0) #10 X 1" HH TEK 2 SCREWS (0) #12 X 1 1/2" HH TEK 2 SCREWS (0) #12 X 2" HH TEK 2 SCREWS (0) #12 X 2" HH TEK 5 SCREWS (0) TAPCONS |  |  |  | N/A | 0 | 10 | 1 | 0 | 0 |  |  | 1/4" 60 x 120 6061 - 25029 Alum Sheet, No Grain | Alum Sheet | 1/4" 60 x 120 6061 - 25029 | No |  |  | 2 | 7 | Jonathan Dorsey | David Hasty | David Hasty |  |  | Jonathan Dorsey | David Hasty | Jonathan Dorsey |  |  | Chris Gambrel |  |  |  | Jonathan Dorsey | 2026-03-26 09:44 |  | 2026-04-24 |  |  |  | 2026-05-11 | 2026-05-15 |  |  |  |  | NO |  | 2026-04-03 | TRUE | Powder Coat | PWX | Coating Ship Back To JWM |  |  | None Available | NO |  | NO |  | NO | [6 empty] | Correction | [5 empty] | TRUE | [22 empty] | 25029 | ST |  | 52 |  | 52 | 25029-ST73 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 3 | [10 empty] | In House |  |  | Flat Laser | Flat Laser Powder Coat |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | David Hasty - @jdorsey@jwmcd.com Good to go | 1010 |  | Dillon Bowman | Jonathan Dorsey | David Hasty | 25029-ST52 In-House |  | 2026, Week 20
231 | 25008-FS07 |  | Columbia State Tech Center | 1665 Hampshire Pike Columbia, TN 38401 | Laura Forero | 615.788.7739 | 400 CAULK |  | Please use the extrusion that AMI sent back from the release 2500FS05 | This is the last release for Columbia State; these panels are the interior part of the vestibules. It includes elevations: 206, 207, 208, and 209. AMI put all the dimensions in a CAD file. AMI wants us to keep the standard 2-1/4 system depth everywhere; we are not going to follow the sheathing like shown in the details. AMI is going to add a corner flashing to cover the sheathing left exposed. For the bottom detail, we are going to be 3/4" above the floor, because the slab is inconsistent. This would make the tighter area 1/2".This applies to both areas. See the attached PDF for AMI dimensions and the comments. | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) JR2 |  |  |  | 534 | 58 | [6 empty] | Alucobond, 4mm X 62" X 196", Oyster FR ACM, No Grain | FR ACM | Alucobond, 4mm X 62" X 196", Oyster | No |  |  | 1 | 10 | Gabriela Herrera | Denis Usatenko | Gabriela Herrera | Gabriela Herrera |  | Gabriela Herrera | Denis Usatenko | Gabriela Herrera |  | Arnold Jurado, Issiah Havens |  |  |  |  | Gabriela Herrera | 2026-03-27 11:48 |  | 2026-04-29 |  |  |  |  | 2026-05-20 |  |  |  |  | YES | 46 | [5 empty] | FAB SCREW | YES | Approved As Noted | NO |  | YES | Q:\Jobs\25008 - Columbia State Tech Center\03_Engineering\02_FD Docs\25008 FS07 | NO | [6 empty] | Evaluation | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25008 | FS |  | 07 |  | 7 | 25008-FS07 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 30 | 110 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Laura Forero | Gabriela Herrera | Denis Usatenko | 25008-FS07 In-House |  | 2026, Week 21
232 | 25037-FS01 |  | Chestnut Street Office | 440 Chestnut Street Nashville, TN 37203 | Laura Forero | 615.788.7739 | 400 |  | We have more than 200 parts for this first release. This is a request per AMI so they can optimize the material and follow the GC schedule. The color for this job is SLATE GRAY. | There are 2 scans for the same building. Please use SCAN: Chestnut 030426 1 for the parapet width on LEVEL 4, the back of the parapet on LEVEL 4, and for the complete LEVEL 5. Please use Scan: Chestnut Office South 1, for the front elevations 304, 305, 306, 307, and 308. The PDF that has the comments from AMI and mine is the latest set. This includes some changes that will have to be applied to the install drawings to make sure we have the most up-to-date drawings based on the GC markups. Please send the PDF LF NOTES to BOSNIA when requesting ID. There is a wood blocking installed on the face wall; the inside face of the blocking is the edge of the ACM panel. The parapet on LEVEL 5 is missing a 2x6 blocking on top of it. On the back of the parapet, please make sure the termination bar is covered by our ACM panels (follow the comments on detail 5/403). | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 679 | 218 | [6 empty] | Reynobond, 4mm X 62" X 196", Slate Gray FR ACM, No Grain | FR ACM | Reynobond, 4mm X 62" X 196", Slate Gray | No |  | MTPK | 7 | 13 | Nadira Vlatkovic | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  |  |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-03-30 09:29 |  | 2026-05-04 |  |  |  |  | 2026-05-25 |  |  |  |  | YES | 323 | [5 empty] | MATCH COLOR | NO | Approved As Noted | YES | Q:\Jobs\25037 - Chestnut Street Office\03_Engineering\02_FD Docs\25037FS01 & FS02\scans | YES | Q:\Jobs\25037 - Chestnut Street Office\03_Engineering\02_FD Docs\25037FS01 & FS02 | NO | [6 empty] | LO Check | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25037 | FS |  | 01 |  | 1 | 25037-FS02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 60 | 475 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - @nvlatkovic@jwmcd.com Scan can be missaligned and needs to be moved into the correct position. | 1010 |  | Laura Forero |  |  | 25037-FS01 In-House |  | 2026, Week 22
233 | 25037-FS02 |  | Chestnut Street Office | 440 Chestnut Street Nashville, TN 37203 | Laura Forero | 615.788.7739 | 400 |  | We have more than 200 parts for this first release. This is a request per AMI so they can optimize the material and follow the GC schedule. The color for this job is SLATE GRAY. | There are 2 scans for the same building. Please use SCAN: Chestnut 030426 1 for the parapet width on LEVEL 4, the back of the parapet on LEVEL 4, and for the complete LEVEL 5. Please use Scan: Chestnut Office South 1, for the front elevations 304, 305, 306, 307, and 308. The PDF that has the comments from AMI and mine is the latest set. This includes some changes that will have to be applied to the install drawings to make sure we have the most up-to-date drawings based on the GC markups. Please send the PDF LF NOTES to BOSNIA when requesting ID. There is a wood blocking installed on the face wall; the inside face of the blocking is the edge of the ACM panel. There is also a wood block for the panel on LEVEL 4 that represents the bottom of the ACM. The panels that are on each slab, since there is no brick installed, we are going to follow the window SD to make the end of the mullion the end of the AC panels. The soffit panels from elevations 1/201 and 2/202 are on hold until the brick is installed. | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 679 | 204 | [6 empty] | Reynobond, 4mm X 62" X 196", Slate Gray FR ACM, No Grain | FR ACM | Reynobond, 4mm X 62" X 196", Slate Gray | No | TRUE | MTPK | 5 | 23 | Denis Usatenko/MTPK | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  |  |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-03-30 09:43 |  | 2026-05-18 |  |  |  |  | 2026-06-08 |  |  |  |  | YES | 204 | [5 empty] | MATCH COLOR | NO | Approved As Noted | YES | Q:\Jobs\25037 - Chestnut Street Office\03_Engineering\02_FD Docs\25037FS01 & FS02\scans | YES | Q:\Jobs\25037 - Chestnut Street Office\03_Engineering\02_FD Docs\25037FS01 & FS02 | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25037 | FS |  | 02 |  | 2 | 25037-FS02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 50 | 450 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Laura Forero |  |  | 25037-FS02 In-House |  | 2026, Week 24
234 | 25044-FS01 |  | MALETA Firing Range | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | FS01 - 32-33/213; 125 GRAPHITE PANELS | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 1810 | 125 | [6 empty] | 4mm X 62" X 196", GRAPHITE MICA FR ACM, Grain | FR ACM | 4mm X 62" X 196", GRAPHITE MICA | Yes | TRUE | MPTK | 1 | 12 | Denis Usatenko/MPTK | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-03-30 15:06 |  | 2026-05-01 |  |  |  |  | 2026-05-22 |  |  |  |  | YES | 160 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01-FS09\SCAN | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01-FS09\Hand Dims & Scope of Work | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25044 | FS |  | 01 |  | 1 | 25044-FS11 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 60 | 200 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - Working Scan recieved 4/09 | 1010 |  | Cole Norona |  | Denis Usatenko | 25044-FS01 In-House |  | 2026, Week 21
235 | 25044-FS02 |  | MALETA Firing Range | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | FS02 - 34-35/214; 134 GRAPHITE PANELS | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 1810 | 135 | [6 empty] | 4mm X 62" X 196", GRAPHITE MICA FR ACM, Grain | FR ACM | 4mm X 62" X 196", GRAPHITE MICA | Yes | TRUE | MPTK | 3 | 18 | Denis Usatenko/MPTK | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-03-30 15:10 |  | 2026-05-11 |  |  |  |  | 2026-05-31 |  |  |  |  | YES | 160 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01-FS09\SCAN | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01-FS09\Hand Dims & Scope of Work | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25044 | FS |  | 02 |  | 2 | 25044-FS11 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 65 | 210 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - Working Scan recieved 4/09 | 1010 |  | Cole Norona |  | Denis Usatenko | 25044-FS02 In-House |  | 2026, Week 22
236 | 25044-FS03 |  | MALETA Firing Range | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | FS03 - 1-3/201; 150 GRAPHITE PANELS | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 1810 | 150 | [6 empty] | 4mm X 62" X 196", GRAPHITE MICA FR ACM, Grain | FR ACM | 4mm X 62" X 196", GRAPHITE MICA | Yes | TRUE | MPTK | 4 | 25 | Denis Usatenko/MPTK | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-03-30 15:14 |  | 2026-05-20 |  |  |  |  | 2026-06-10 |  |  |  |  | YES | 160 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01-FS09\SCAN | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01-FS09\Hand Dims & Scope of Work | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25044 | FS |  | 03 |  | 3 | 25044-FS11 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 70 | 245 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - Working Scan recieved 4/09 | 1010 |  | Cole Norona |  | Denis Usatenko | 25044-FS03 In-House |  | 2026, Week 24
237 | 25044-FS04 |  | MALETA Firing Range | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | FS04 - 4-5/202; 113 GRAPHITE PANELS | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 1810 | 113 | [6 empty] | 4mm X 62" X 196", GRAPHITE MICA FR ACM, Grain | FR ACM | 4mm X 62" X 196", GRAPHITE MICA | Yes | TRUE | MPTK | 5 | 32 | Denis Usatenko/MPTK | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-03-30 15:17 |  | 2026-05-29 |  |  |  |  | 2026-06-19 |  |  |  |  | YES | 160 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01-FS09\SCAN | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01-FS09\Hand Dims & Scope of Work | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25044 | FS |  | 04 |  | 4 | 25044-FS11 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 50 | 190 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - Working Scan recieved 4/09 | 1010 |  | Cole Norona |  | Denis Usatenko | 25044-FS04 In-House |  | 2026, Week 25
238 | 25044-FS05 |  | MALETA Firing Range | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | FS05 - 9-10/204 & 13,15/206; 111 GRAPHITE PANELS | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 1810 | 111 | [6 empty] | 4mm X 62" X 196", GRAPHITE MICA FR ACM, Grain | FR ACM | 4mm X 62" X 196", GRAPHITE MICA | Yes | TRUE | MPTK | 6 | 37 | Denis Usatenko/MPTK | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-03-30 15:20 |  | 2026-06-05 |  |  |  |  | 2026-06-26 |  |  |  |  | YES | 160 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01-FS09\SCAN | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01-FS09\Hand Dims & Scope of Work | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25044 | FS |  | 05 |  | 5 | 25044-FS11 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 50 | 190 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - Working Scan recieved 4/09 | 1010 |  | Cole Norona |  | Denis Usatenko | 25044-FS05 In-House |  | 2026, Week 26
239 | 25044-FS06 |  | MALETA Firing Range | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | FS06 - 20-21/208; 203 GRAPHITE PANELS | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 1810 | 203 | [6 empty] | 4mm X 62" X 196", GRAPHITE PANELS FR ACM, Grain | FR ACM | 4mm X 62" X 196", GRAPHITE PANELS | Yes | TRUE | MPTK | 7 | 43 | Denis Usatenko/MPTK | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-03-30 15:24 |  | 2026-06-15 |  |  |  |  | 2026-07-06 |  |  |  |  | YES | 160 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01-FS09\SCAN | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01-FS09\Hand Dims & Scope of Work | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25044 | FS |  | 06 |  | 6 | 25044-FS11 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 95 | 340 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - Working Scan recieved 4/09 | 1010 |  | Cole Norona |  | Denis Usatenko | 25044-FS06 In-House |  | 2026, Week 28
240 | 25044-FS07 |  | MALETA Firing Range | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | FS07 - 22-24/209 & 25/210; 160 GRAPHITE PANELS | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 1810 | 160 | [6 empty] | 4mm X 62" X 196", GRAPHITE MICA FR ACM, Grain | FR ACM | 4mm X 62" X 196", GRAPHITE MICA | Yes | TRUE | MPTK | 8 | 50 | Denis Usatenko/MPTK | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-03-30 15:28 |  | 2026-06-24 |  |  |  |  | 2026-07-15 |  |  |  |  | YES | 160 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01-FS09\SCAN | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01-FS09\Hand Dims & Scope of Work | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25044 | FS |  | 07 |  | 7 | 25044-FS11 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 80 | 270 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - Working Scan recieved 4/09 | 1010 |  | Cole Norona |  | Denis Usatenko | 25044-FS07 In-House |  | 2026, Week 29
241 | 25044-FS08 |  | MALETA Firing Range | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | FS08 - 26/210 & 27/211; 163 GRAPHITE PANELS | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 1810 | 163 | [6 empty] | 4mm X 62" X 196", GRAPHITE MICA FR ACM, Grain | FR ACM | 4mm X 62" X 196", GRAPHITE MICA | Yes | TRUE | MPTK | 9 | 55 | Denis Usatenko/MPTK | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-03-30 15:30 |  | 2026-07-01 |  |  |  |  | 2026-07-22 |  |  |  |  | YES | 160 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01-FS09\SCAN | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01-FS09\Hand Dims & Scope of Work | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25044 | FS |  | 08 |  | 8 | 25044-FS11 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 80 | 270 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - Working Scan recieved 4/09 | 1010 |  | Cole Norona |  | Denis Usatenko | 25044-FS08 In-House |  | 2026, Week 30
242 | 25044-FS09 |  | MALETA Firing Range | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | FS09 - 28/211 & 29-31/212; 86 GRAPHITE PANELS | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 1810 | 86 | [6 empty] | 4mm X 62" X 196", GRAPHITE MICA FR ACM, Grain | FR ACM | 4mm X 62" X 196", GRAPHITE MICA | Yes | TRUE | MPTK | 10 | 60 | Denis Usatenko/MPTK | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-03-30 15:33 |  | 2026-07-08 |  |  |  |  | 2026-07-29 |  |  |  |  | YES | 160 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01-FS09\SCAN | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01-FS09\Hand Dims & Scope of Work | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25044 | FS |  | 09 |  | 9 | 25044-FS11 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 40 | 145 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - Working Scan recieved 4/09 | 1010 |  | Cole Norona |  | Denis Usatenko | 25044-FS09 In-House |  | 2026, Week 31
243 | 25044-FS10 |  | MALETA Firing Range | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | FS10 - 1-2/301 & 3/302; 185 GRAPHITE PANELS | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 1810 | 185 | [6 empty] | 4mm X 62" X 196", GRAPHITE MICA FR ACM, Grain | FR ACM | 4mm X 62" X 196", GRAPHITE MICA | Yes | TRUE | MPTK | 12 | 67 | Denis Usatenko/MPTK | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-03-30 15:41 |  | 2026-07-17 |  |  |  |  | 2026-08-07 |  |  |  |  | YES | 160 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS10-FS11\SCAN | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS10-FS11\Hand Dims & Scope of Work | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25044 | FS |  | 10 |  | 10 | 25044-FS11 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 90 | 300 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - Working Scan recieved 4/09 | 1010 |  | Cole Norona |  | Denis Usatenko | 25044-FS10 In-House |  | 2026, Week 32
244 | 25044-FS11 |  | MALETA Firing Range | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | FS11 - 4-5/303 & 6/304; 185 GRAPHITE PANELS | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 1810 | 185 | [6 empty] | 4mm X 62" X 196", GRAPHITE MICA FR ACM, Grain | FR ACM | 4mm X 62" X 196", GRAPHITE MICA | Yes | TRUE | MPTK | 13 | 73 | Denis Usatenko/MPTK | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-03-30 15:47 |  | 2026-07-27 |  |  |  |  | 2026-08-17 |  |  |  |  | YES | 160 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS10-FS11\SCAN | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS10-FS11\Hand Dims & Scope of Work | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25044 | FS |  | 11 |  | 11 | 25044-FS11 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 90 | 300 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - Working Scan recieved 4/09 | 1010 |  | Cole Norona |  | Denis Usatenko | 25044-FS11 In-House |  | 2026, Week 34
245 | 25044-FS01.1 |  | MALETA Firing Range | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | FS12 - 6-8/203, 7/203A, & 12/206; 34 TERRA COTA PANELS | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 1810 | 34 | [6 empty] | 4mm X 62" X 196", SPICY HUE MATTE DC MASK FR ACM, Grain | FR ACM | 4mm X 62" X 196", SPICY HUE MATTE DC MASK | Yes | TRUE | MPTK | 1 | 12 | Denis Usatenko/MPTK | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-03-30 15:57 |  | 2026-05-01 |  |  |  |  | 2026-05-22 |  |  |  |  | YES | 15 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01.1\SCAN | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01.1\Hand Dims & Scope of Work | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25044 | FS |  | 01.1 |  | 1.1 | 25044-FS11 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 17 | 57 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - Working Scan recieved 4/09 | 1010 |  | Cole Norona |  | Denis Usatenko | 25044-FS01.1 In-House |  | 2026, Week 21
246 | 25044-FS01.2 |  | MALETA Firing Range | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | FS13 - 9,11/204, 14-15/206, 16/207, 25-26/210, 1-2/301, 5/303 & 6/304; 193 BLUE PANELS | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 1810 | 193 | [6 empty] | 4mm X 62" X 196", AZURE BLUE FR ACM, No Grain | FR ACM | 4mm X 62" X 196", AZURE BLUE | No | TRUE | MPTK | 10 | 60 | Denis Usatenko/MPTK | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-03-30 16:02 |  | 2026-07-08 |  |  |  |  | 2026-07-29 |  |  |  |  | YES | 14 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01.2\SCAN | YES | Q:\Jobs\25044 - MALETA Firing Range\03_Engineering\02_FD Docs\25044FS01.2\Hand Dims & Scope of Work | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25044 | FS |  | 01.2 |  | 1.2 | 25044-FS11 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 95 | 325 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Denis Usatenko - Working Scan recieved 4/09 | 1010 |  | Cole Norona |  | Denis Usatenko | 25044-FS01.2 In-House |  | 2026, Week 31
247 | 26014-04-ST01 |  | 2026 R & D | 3731 Amy Lynn Drive Nashville, TN 37218-3813 | TBC |  | GRAVITY |  | PROGRAMS IN R&D FOLDER | Tubing Structure | SKETCHES PROGRAMMING FILES | (0) TUBE, SILPRUF CAULK (0) LF 1/2" DENVER FOAM B-ROD (0) CS - RED 1/8" SHIMS (0) CS - BLACK 1/4" SHIMS (0) #10 X 1" HH TEK 2 SCREWS (0) #12 X 1 1/2" HH TEK 2 SCREWS (0) #12 X 2" HH TEK 2 SCREWS (0) #12 X 2" HH TEK 5 SCREWS (0) TAPCONS | Q:\Jobs\26014-04 - Remodel\04_Production\26014-04ST01 | N/A | N/A | N/A | 0 | 8 | 7 | 0 | 0 | 3 @ 16ft | 4.32 | 2" x 4" x 1/4" x16' Alum Tubing Alum Tube, No Grain | Alum Tube | 2" x 4" x 1/4" x16' Alum Tubing | No |  |  | 5 | 7 | Hunter Clouse | David Hasty | David Hasty |  |  | Frank Dean | David Hasty | Frank Dean |  |  | Arnold Jurado |  | TRUE | TRUE | Frank Dean | 2026-03-31 07:00 | TRUE | 2026-04-21 | 2026-04-08 | TRUE | 2026-04-24 |  | 2026-04-06 |  |  |  |  | YES | [8 empty] | None Available | NO |  | NO |  | NO | [6 empty] | 7000 TubeLaser 20 |  | TRUE |  |  |  |  | TRUE | [13 empty] | TRUE | [7 empty] | 26014-04 | ST |  | 01 |  | 1 | 26014-04-ST02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 10 | 10 | [10 empty] | In House |  |  | Tube Laser | Tube Laser Weld | 2026-04-07 | 2026-04-08 | 2 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Arnold Jurado - @fdean@jwmcd.com done programming | 1010 |  | TBC | Frank Dean | David Hasty | 26014-04-ST01 In-House |  | 2026, Week 15
248 | 26014-04-FS01 |  | 2026 R & D | 3731 Amy Lynn Drive Nashville, TN 37218-3813 | TBC |  | GRAVITY |  |  | Engineering Office Panels | SKETCHES PROGRAMMING FILES | (0) TUBE, SILPRUF CAULK (0) LF 1/2" DENVER FOAM B-ROD (0) CS - RED 1/8" SHIMS (0) CS - BLACK 1/4" SHIMS (0) #10 X 1" HH TEK 2 SCREWS (0) #12 X 1 1/2" HH TEK 2 SCREWS (0) #12 X 2" HH TEK 2 SCREWS (0) #12 X 2" HH TEK 5 SCREWS (0) TAPCONS | Q:\Jobs\26014-04 - Remodel\04_Production\26014-04FS01 | Unavailable | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 4 | 01:45:54 | 48"x 96" x .125" 3003 Alum. Alum Sheet, Grain | Alum Sheet | 48"x 96" x .125" 3003 Alum. | Yes |  |  | 1 | 7 | Joshua Davis | David Hasty |  |  |  | Frank Dean | David Hasty | Frank Dean |  |  |  | Chris Gambrel | TRUE |  | Frank Dean | 2026-03-31 07:10 | TRUE | 2026-04-21 | 2026-04-08 | TRUE | 2026-04-24 |  | 2026-04-06 |  |  |  |  | NO | 4 | 2026-04-03 |  |  |  |  | N/A | NO | None Available | NO |  | NO |  | NO | [6 empty] | 7000 TruMatic |  | TRUE | [6 empty] | TRUE | 7000 TruMatic | [7 empty] | TRUE | [10 empty] | 26014-04 | FS |  | 01 |  | 1 | 26014-04-FS01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 6 | 10 | [10 empty] | In House |  |  | Punch | 7000 TruMatic Brake | 2026-04-07 | 2026-04-08 | 2 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Chris Gambrel - @fdean@jwmcd.com changed from 48X102 to 48X96, program completed. | 1010 |  | TBC | Frank Dean | David Hasty | 26014-04-FS01 In-House |  | 2026, Week 15
249 | 25065-MU01 |  | Crosswinds Casino Resort | 777 Jackpot Way Park City, Kansas 67147 | Matt Rassmussen |  | 400 |  | Image Blue Panels | We will release this from shop drawings | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 9703 | 18 | 14 | [5 empty] | 4mm x 62 x 196 Image Blue FR ACM, No Grain | FR ACM | 4mm x 62 x 196 Image Blue | No |  |  | 6 | 12 | Denis Usatenko | Denis Usatenko | Gabriela Herrera | Gabriela Herrera |  | Gabriela Herrera | Denis Usatenko | Gabriela Herrera |  | Arnold Jurado, Issiah Havens |  |  |  |  | Gabriela Herrera | 2026-03-31 10:19 |  | 2026-05-01 |  |  |  |  | 2026-05-22 |  |  |  |  | NO |  | 2026-04-24 |  |  |  |  | MATCH COLOR | NO | Approved | NO |  | NO |  | NO | [6 empty] | Sketch Check | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25065 | MU |  | 01 |  | 1 | 25065-MU20 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 20 | [10 empty] | Semi |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Gabriela Herrera - @dusatenko@jwmcd.com Q:\Jobs\25065 - Crosswinds Casino Resort\03_Engineering\03_FS_Issues\03_Check\25065MU01 | 1010 |  | Matt Rassmussen | Gabriela Herrera | Denis Usatenko | 25065-MU01 In-House |  | 2026, Week 21
250 | 25065-MU02 |  | Crosswinds Casino Resort | 777 Jackpot Way Park City, Kansas 67147 | Matt Rassmussen |  | 400 |  | Loyal Blue panels |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 9703 | 15 | 13 | [5 empty] | 4mm x 62 x 196, Loyal Blue FR ACM, No Grain | FR ACM | 4mm x 62 x 196, Loyal Blue | No |  |  | 2 | 17 | Gabriela Herrera | Denis Usatenko | Gabriela Herrera | Gabriela Herrera |  | Gabriela Herrera | Denis Usatenko | Gabriela Herrera |  | Arnold Jurado, Issiah Havens |  |  |  |  | Gabriela Herrera | 2026-03-31 10:22 |  | 2026-05-08 |  |  |  |  | 2026-05-29 |  |  |  |  | NO |  | 2026-04-30 |  |  |  |  | MATCH COLOR | NO | Approved | NO |  | NO |  | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25065 | MU |  | 02 |  | 2 | 25065-MU20 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 18 | [10 empty] | Semi |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Matt Rassmussen | Gabriela Herrera | Denis Usatenko | 25065-MU02 In-House |  | 2026, Week 22
251 | 25065-MU03 |  | Crosswinds Casino Resort | 777 Jackpot Way Park City, Kansas 67147 | Matt Rassmussen |  | 400 |  | Tuscan Sun = Yellow panels | MOCKUP! please be careful | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 9703 | 6 | 6 | [5 empty] | 4mm x 62 x 196, Tuscan Sun FR ACM, No Grain | FR ACM | 4mm x 62 x 196, Tuscan Sun | No |  |  | 2 | 17 | Gabriela Herrera | Denis Usatenko | Gabriela Herrera | Gabriela Herrera |  | Gabriela Herrera | Denis Usatenko | Gabriela Herrera |  | Arnold Jurado, Issiah Havens |  |  |  |  | Gabriela Herrera | 2026-03-31 10:25 |  | 2026-05-08 |  |  |  |  | 2026-05-29 |  |  |  |  | NO |  | 2026-04-30 |  |  |  |  | MATCH COLOR | NO | Approved | NO |  | NO |  | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25065 | MU |  | 03 |  | 3 | 25065-MU20 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 2 | 8 | [10 empty] | Semi |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Matt Rassmussen | Gabriela Herrera | Denis Usatenko | 25065-MU03 In-House |  | 2026, Week 22
252 | 25065-MU04 |  | Crosswinds Casino Resort | 777 Jackpot Way Park City, Kansas 67147 | Matt Rassmussen |  | 400 |  | West Pewter Mica Panels |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 9703 | 15 | 13 | [5 empty] | 4mm x 62 x 196, West Pewter Mica FR ACM, Grain | FR ACM | 4mm x 62 x 196, West Pewter Mica | Yes |  |  | 2 | 17 | Gabriela Herrera | Denis Usatenko | Gabriela Herrera | Gabriela Herrera |  | Gabriela Herrera | Denis Usatenko | Gabriela Herrera |  | Arnold Jurado, Issiah Havens |  |  |  |  | Gabriela Herrera | 2026-03-31 10:27 |  | 2026-05-08 |  |  |  |  | 2026-05-29 |  |  |  |  | NO |  | 2026-04-30 |  |  |  |  | MATCH COLOR | NO | Approved | NO |  | NO |  | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25065 | MU |  | 04 |  | 4 | 25065-MU20 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 8 | 20 | [10 empty] | Semi |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Matt Rassmussen | Gabriela Herrera | Denis Usatenko | 25065-MU04 In-House |  | 2026, Week 22
253 | 25065-MU05 |  | Crosswinds Casino Resort | 777 Jackpot Way Park City, Kansas 67147 | Matt Rassmussen |  | CUSTOM ARCH |  | We want to form the Morin panel profiles using the Cidan. | Morin MX-9 panel profile to be made in the Cidan | [5 empty] | 9703 | 3 | 1 | [5 empty] | 22ga x 48 x 120, Morin Weathered Zinc Steel Sheet, Grain | Steel Sheet | 22ga x 48 x 120, Morin Weathered Zinc | Yes |  |  | 10 | 17 | Denis Usatenko | David Hasty | Denis Usatenko |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-03-31 10:33 |  | 2026-05-08 |  |  |  |  | 2026-05-29 |  |  |  |  | NO |  | 2026-04-30 |  |  |  |  | N/A | NO | Approved | NO |  | NO |  | NO | [6 empty] | Evaluation |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25065 | MU |  | 05 |  | 5 | 25065-MU20 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 1 | [10 empty] | Semi |  |  |  | Cidan Shear |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Matt Rassmussen | Denis Usatenko |  | 25065-MU05 In-House |  | 2026, Week 22
254 | 25065-MU11 |  | Crosswinds Casino Resort | 777 Jackpot Way Park City, Kansas 67147 | Matt Rassmussen |  | CUSTOM ARCH |  | Trim | Image Blue | * Sketch |  |  |  |  | 9703 | 1 | 1 | [5 empty] | .040 x 48 x 120, Image Blue Alum Sheet, No Grain | Alum Sheet | .040 x 48 x 120, Image Blue | No |  |  | 10 | 17 | Denis Usatenko | David Hasty | Denis Usatenko |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-03-31 10:38 |  | 2026-05-08 |  |  |  |  | 2026-05-29 |  |  |  |  | NO |  | 2026-05-29 |  |  |  |  | N/A | NO | Approved | NO |  | NO |  | NO | [6 empty] | Evaluation |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25065 | MU |  | 11 |  | 11 | 25065-MU20 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 1 | [10 empty] | Semi |  |  |  | Cidan Shear |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Matt Rassmussen | Denis Usatenko |  | 25065-MU11 In-House |  | 2026, Week 22
255 | 25065-MU12 |  | Crosswinds Casino Resort | 777 Jackpot Way Park City, Kansas 67147 | Matt Rassmussen |  | CUSTOM ARCH |  | Trim | Loyal Blue | * Sketch |  |  |  |  | N/A | 0 | 2 | [5 empty] | .032 x 48 x 120, Loyal Blue Alum Sheet, No Grain | Alum Sheet | .032 x 48 x 120, Loyal Blue | No |  |  | 10 | 17 | Denis Usatenko | David Hasty | Denis Usatenko |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-03-31 10:40 |  | 2026-05-08 |  |  |  |  | 2026-05-29 |  |  |  |  | NO |  | 2026-04-30 |  |  |  |  | N/A | NO | Approved | NO |  | NO |  | NO | [6 empty] | Evaluation |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25065 | MU |  | 12 |  | 12 | 25065-MU20 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 1 | [10 empty] | Semi |  |  |  | Cidan Shear |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Matt Rassmussen | Denis Usatenko |  | 25065-MU12 In-House |  | 2026, Week 22
256 | 25065-MU13 |  | Crosswinds Casino Resort | 777 Jackpot Way Park City, Kansas 67147 | Matt Rassmussen |  | CUSTOM ARCH |  | Trim | Tuscan Sun | * Sketch |  |  |  |  | N/A | 0 | 1 | [5 empty] | .040 x 48 x 120, Tuscan Sun Alum Sheet, No Grain | Alum Sheet | .040 x 48 x 120, Tuscan Sun | No |  |  | 10 | 17 | Denis Usatenko | David Hasty | Denis Usatenko |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-03-31 10:41 |  | 2026-05-08 |  |  |  |  | 2026-05-29 |  |  |  |  | NO |  | 2026-04-30 |  |  |  |  | N/A | NO | Approved | NO |  | NO |  | NO | [6 empty] | Evaluation |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25065 | MU |  | 13 |  | 13 | 25065-MU20 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 1 | [10 empty] | Semi |  |  |  | Cidan Shear |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Matt Rassmussen | Denis Usatenko |  | 25065-MU13 In-House |  | 2026, Week 22
257 | 25065-MU14 |  | Crosswinds Casino Resort | 777 Jackpot Way Park City, Kansas 67147 | Matt Rassmussen |  | CUSTOM ARCH |  | Trim | West Pewter Mica | * Sketch |  |  |  |  | N/A | 0 | 3 | [5 empty] | .040 x 62 x 196, West Pewter Mica Alum Sheet, Grain | Alum Sheet | .040 x 62 x 196, West Pewter Mica | Yes |  |  | 10 | 17 | Denis Usatenko | David Hasty | Denis Usatenko |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-03-31 10:43 |  | 2026-05-08 |  |  |  |  | 2026-05-29 |  |  |  |  | NO |  | 2026-04-30 |  |  |  |  | N/A | NO | Approved | NO |  | NO |  | NO | [6 empty] | Evaluation |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25065 | MU |  | 14 |  | 14 | 25065-MU20 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 1 | [10 empty] | Semi |  |  |  | Cidan Shear |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Matt Rassmussen | Denis Usatenko |  | 25065-MU14 In-House |  | 2026, Week 22
258 | 25065-MU15 |  | Crosswinds Casino Resort | 777 Jackpot Way Park City, Kansas 67147 | Matt Rassmussen |  | CUSTOM ARCH |  | Trim | Weathered Zinc | * Sketch |  |  |  |  | N/A | 0 | 6 | [5 empty] | 22ga x 48 x 120, Morin Weathered Zinc Steel Sheet, Grain | Steel Sheet | 22ga x 48 x 120, Morin Weathered Zinc | Yes |  |  | 10 | 17 | Denis Usatenko | David Hasty | Denis Usatenko |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-03-31 10:45 |  | 2026-05-08 |  |  |  |  | 2026-05-29 |  |  |  |  | NO |  | 2026-04-30 |  |  |  |  | N/A | NO | Approved | NO |  | NO |  | NO | [6 empty] | Evaluation |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25065 | MU |  | 15 |  | 15 | 25065-MU20 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 1 | [10 empty] | Semi |  |  |  | Cidan Shear |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Matt Rassmussen | Denis Usatenko |  | 25065-MU15 In-House |  | 2026, Week 22
259 | 25065-MU20 |  | Crosswinds Casino Resort | 777 Jackpot Way Park City, Kansas 67147 | Matt Rassmussen |  | CUSTOM ARCH |  | Subframing for mockup | Zee and hat | * Sketch |  |  |  |  | N/A | 0 | 3 | [5 empty] | 16ga x 48 x 120 Steel Sheet, No Grain | Steel Sheet | 16ga x 48 x 120 | No |  |  | 10 | 17 | Denis Usatenko | David Hasty | Denis Usatenko |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-03-31 13:38 |  | 2026-05-08 |  |  |  |  | 2026-05-29 |  |  |  |  | YES | [6 empty] | N/A | NO | Approved | NO |  | NO |  | NO | [6 empty] | Evaluation |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25065 | MU |  | 20 |  | 20 | 25065-MU20 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 1 | [10 empty] | Semi |  |  |  | Cidan Shear |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Matt Rassmussen | Denis Usatenko |  | 25065-MU20 In-House |  | 2026, Week 22
260 | 25029-ST70 |  | Lourdes CC Phase 2 | 1510 Lone Oak Road Paducah, KY 42003 | Dillon Bowman | 518.860.9477 | CUSTOM ARCH |  | Tree Panels | Memorial Tree Panels - to be integrated with ST71 and ST72 Link for Info: Q:\Jobs\25029 - Lourdes CC Phase 2\03_Engineering\02_FD Docs\25029 - ST70, ST71, ST72 | [5 empty] | N/A |  | 6 | 2 |  |  |  |  | 3/8 x 60 x 144 - Steel Steel Sheet, No Grain | Steel Sheet | 3/8 x 60 x 144 - Steel | No |  |  | 1 | 7 | David Hasty | David Hasty | David Hasty | Jonathan Dorsey | David Hasty | Jonathan Dorsey | David Hasty | Jonathan Dorsey | [7 empty] | 2026-03-31 14:44 |  | 2026-04-24 |  |  |  |  | 2026-05-15 |  |  |  |  | NO |  | 2026-04-14 | [6 empty] | None Available | NO |  | NO |  | NO | [6 empty] | Sketch Check | TRUE | TRUE |  |  |  | TRUE | [17 empty] | TRUE |  |  |  |  | 25029 | ST |  | 70 |  | 70 | 25029-ST73 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 15 | 2 | [13 empty] | Flat Laser | Flat Laser |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Dillon Bowman | Jonathan Dorsey | David Hasty | 25029-ST70 In-House |  | 2026, Week 20
261 | 25029-ST71 |  | Lourdes CC Phase 2 | 1510 Lone Oak Road Paducah, KY 42003 | Dillon Bowman | 518.860.9477 | CUSTOM ARCH |  | Memorial Tree Mast/Post | Memorial Tree Mast/Post (to be integrated with ST70 and ST72) Folder Link : Q:\Jobs\25029 - Lourdes CC Phase 2\03_Engineering\02_FD Docs\25029 - ST70, ST71, ST72 | [5 empty] | N/A |  | 1 | 1 |  |  |  |  | XXX TBD Pending Calcs Steel Tube, No Grain | Steel Tube | XXX TBD Pending Calcs | No |  |  | 2 | 7 | Jonathan Dorsey | David Hasty |  |  |  | Jonathan Dorsey | David Hasty | Jonathan Dorsey |  |  | Arnold Jurado |  |  |  | Jonathan Dorsey | 2026-03-31 14:47 |  | 2026-04-24 |  |  |  |  | 2026-05-15 |  |  |  |  | NO |  | 2026-04-14 | [6 empty] | None Available | NO |  | NO |  | NO | [6 empty] | Sketch |  | TRUE |  |  |  |  | TRUE | [21 empty] | 25029 | ST |  | 71 |  | 71 | 25029-ST73 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 3 | [10 empty] | Hot Shot |  |  | Tube Laser | Tube Laser |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Dillon Bowman | Jonathan Dorsey | David Hasty | 25029-ST71 In-House |  | 2026, Week 20
262 | 25029-ST72 |  | Lourdes CC Phase 2 | 1510 Lone Oak Road Paducah, KY 42003 | Dillon Bowman | 518.860.9477 | CUSTOM ARCH |  | Memorial Tree Base Plate | Memorial Tree Base Plate (to be integrated with ST70 + ST71) Q:\Jobs\25029 - Lourdes CC Phase 2\03_Engineering\02_FD Docs\25029 - ST70, ST71, ST72 | [5 empty] | N/A |  | 1 | 1 |  |  |  |  | 3/4" x 48 x 120 - Steel (25029) Steel Sheet, No Grain | Steel Sheet | 3/4" x 48 x 120 - Steel (25029) | No |  |  | 1 | 7 | David Hasty | David Hasty | David Hasty |  |  | Jonathan Dorsey | David Hasty | Jonathan Dorsey |  |  | Chris Gambrel |  |  |  | Jonathan Dorsey | 2026-03-31 14:50 |  | 2026-04-24 |  |  |  |  | 2026-05-15 |  |  |  |  | NO |  | 2026-04-14 | [6 empty] | None Available | NO |  | NO |  | NO | [6 empty] | Sketch Check |  | TRUE |  |  |  | TRUE | [17 empty] | TRUE |  |  |  |  | 25029 | ST |  | 72 |  | 72 | 25029-ST73 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 2 | 10 | [13 empty] | Flat Laser | Flat Laser |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Dillon Bowman | Jonathan Dorsey | David Hasty | 25029-ST72 In-House |  | 2026, Week 20
263 | 25041-FS02 |  | Wedgewood Bldg E | 314 Leon Loop Nashville, TN 37203 | Wylie McDougall | 615.426.7650 | 400 | [8 empty] | 155 | 31 | [6 empty] | 4mm X 62" X 125", Black FR ACM, No Grain | FR ACM | 4mm X 62" X 125", Black | No |  |  | 2 | 14 | Ailen Niedfeld | Denis Usatenko | Ailen Niedfeld | Ailen Niedfeld |  | Ailen Niedfeld | Denis Usatenko | Ailen Niedfeld |  | Arnold Jurado, Issiah Havens |  |  |  |  | Ailen Niedfeld | 2026-03-31 15:52 |  | 2026-05-05 |  |  |  |  | 2026-05-26 |  |  |  |  | YES | 34 | [5 empty] | BLACK | YES | Approved | NO |  | YES | Q:\Jobs\25041 - Wedgewood Bldg E\03_Engineering\02_FD Docs\25041 FS02 | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [7 empty] | TRUE | [13 empty] | TRUE | TRUE |  |  | 25041 | FS |  | 02 |  | 2 | 25041-FS02 |  | TRUE | 2026-04-09 |  | 6 (ON HOLD) |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | 6 | 10 | 50 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab Roller |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Ailen Niedfeld - @wmcdougall@jwmcd.com let me know when it's off hold, thanks! | 1010 |  | Wylie McDougall | Ailen Niedfeld | Denis Usatenko | 25041-FS02 In-House |  | 2026, Week 22
264 | 25006-FS07 |  | MALETA Housing and Dining | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | ELEVATION 15-17/207 & 18-21/208; 190 GRAPHITE PANELS | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 2058 | 190 | [6 empty] | 4mm X 62" X 196", GRAPHITE MICA FR ACM, Grain | FR ACM | 4mm X 62" X 196", GRAPHITE MICA | Yes |  | MTPK | 9 | 20 | Nadira Vlatkovic | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-04-01 08:49 |  | 2026-05-13 |  |  |  |  | 2026-06-03 |  |  |  |  | YES | 531 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS07-FS08-A-B SOUTH 207-209 ELEV\SCANS | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS07-FS08-A-B SOUTH 207-209 ELEV\FIELD DIMENSIONS | NO | [6 empty] | LO Check | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25006 | FS |  | 07 |  | 7 | 25006-FS13 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 90 | 300 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Cole Norona |  | Denis Usatenko | 25006-FS07 In-House |  | 2026, Week 23
265 | 25006-FS08 |  | MALETA Housing and Dining | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | ELEVATION 22-25/209; 83 GRAPHITE PANELS | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 2058 | 83 | [6 empty] | 4mm X 62" X 196", GRAPHITE MICA FR ACM, Grain | FR ACM | 4mm X 62" X 196", GRAPHITE MICA | Yes |  | MTPK | 10 | 27 | Nadira Vlatkovic | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-04-01 08:51 |  | 2026-05-22 |  |  |  |  | 2026-06-12 |  |  |  |  | YES | 531 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS07-FS08-A-B SOUTH 207-209 ELEV\SCANS | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS07-FS08-A-B SOUTH 207-209 ELEV\FIELD DIMENSIONS | NO | [6 empty] | LO Check | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25006 | FS |  | 08 |  | 8 | 25006-FS13 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 40 | 140 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Cole Norona |  | Denis Usatenko | 25006-FS08 In-House |  | 2026, Week 24
266 | 25012-MU07 |  | St Jude Hospital | 671 St. Jude Place Memphis, TN 38105 | Wylie McDougall | 615.426.7650 | 400 |  |  |  |  | SEE NOTE ON MATERIAL [use 24015] | Q:\Jobs\25012 - St Jude Hospital\04_Production\25012MU07 | 4.811% | 28 | 582 | 8 | 8 | 1 | 0 | 0 | 1 SHEET | 00d00h08m53s | 4mm X 62" X 196", Slate Gray [24015] FR ACM, No Grain | FR ACM | 4mm X 62" X 196", Slate Gray [24015] | No |  |  | 5 | 9 | Corey Howse | Denis Usatenko |  |  |  | Ailen Niedfeld | Gabriela Herrera | Ailen Niedfeld |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Ailen Niedfeld | 2026-04-01 12:16 | TRUE | 2026-04-22 | 2026-04-10 | TRUE | 2026-04-28 |  | 2026-04-14 |  |  |  |  | YES | [6 empty] | N/A | N/A | N/A (Process Customer Provided Blanks) | NO |  | YES | Q:\Jobs\25012 - St Jude Hospital\03_Engineering\02_FD Docs\MU07 | NO | [6 empty] | Clean and Brake |  | TRUE | TRUE | [21 empty] | TRUE |  |  |  | 25012 | MU |  | 07 |  | 7 | 25012-MU07 |  |  | 2026-04-07 | 2026-04-07 | 1 |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | 1 | 1 | 2 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake | 2026-04-09 | 2026-04-10 | 2 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Arnold Jurado - @aniedfeld@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Wylie McDougall | Ailen Niedfeld | Gabriela Herrera | 25012-MU07 In-House |  | 2026, Week 16
267 | 1040-30791-ST09 |  | AFI - YANCEY | CUSTOMER PICK-UP | Hannah Sadloski, Lisa Ellison |  | --- | TRUE | ASSEMBLE IN CRATING (15) YBCO-01034 / D / BIRDSCREEN KIT (15) YBCO-01065 / D / DISCHARGE WALL (15)YBCO-01020 / D / FRONT WALL KIT (15) YBCO-01024 / D / INTAKE WALL KIT (15) YBCO-01043 / D / RIGHT WALL KIT (15) YBCO-01054 / D / LEFT WALL KIT (15) YBCO-01040 / D / TRYSTAR BASE KIT (30) YBCO-01038 / D / TRANSFORMER BRACKET KIT (15) YBCO-01252 / D / SOUND BAFFLE KIT (15) YBCO-01029 / D / REAR FIXED WALL (0) D5BA22-24-32 / D / UREA TANK BRACKET (20) D5K56-37-3-2-019-AL / D / EXHAUST BEAUTY RING |  | SAW CUT LIST KIT LIST (CRATING PLAN) YANCEY MATERIAL SAW DAILY FORM | ADDITIONAL PARTS FOR PACKAGING FROM TUBE LASER AND FLAT/FORM OPERATIONS PER KIT LIST 1.5 X 1.5 X .125 Alum. Angle 2 X 2 X .125 Alum. Angle 2 X 3 X .190 Alum. Angle 2 X 2 X .125 Alum. Tube 2 X 2 X .125 Alum. Tube 2 X 3 X .125 Alum. Tube 2 X 3 X .125 Alum. Tube 2 X 3 X .250 Alum. Tube 2 X 4 X .125 Alum. Tube 2 X 4 X .250 Alum. Tube 2 X 6 X .250 Alum. Tube | T:\01 IN-PROCESS ORDERS\0002 SPECTRUM\104030791 AFI YANCEY MULTIPLE POS\03_Production | N/A | N/A | N/A | 0 | 185 | 0 | 6095 | 0 | N/A | N/A | SEE MISC MATERIALS: Alum Angle, Alum Tube | Alum Tube | SEE MISC MATERIALS: Alum Angle, |  |  |  | 1 | -7 | Tony Graves | David Hasty | [5 empty] | David Hasty | [6 empty] | Frank Dean | 2026-04-01 14:21 | TRUE | 2026-04-01 | 2026-04-01 | TRUE | 2026-04-08 |  | 2026-04-10 |  |  |  |  | YES | [20 empty] | Assembly | [15 empty] | TRUE | [10 empty] | TRUE | 15000 | 1040-30791 | ST |  | 09 |  | 9 | 1040-30791-ST10 | 2026-04-01 |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | [12 empty] | Customer Pick Up |  |  |  | Assembly Extrusion Saw |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1040 |  | Hannah Sadloski, Lisa Ellison |  |  | 1040-30791-ST09 In-House |  | 2026, Week 15
268 | 25005-ST02 |  | CAT Financial Nashville HQ | 2120 West End Avenue Nashville, TN 37203 | Chris Buttrey | 615.517.9885 | CUSTOM ARCH |  |  | 4 parts, 3 parts only need to get longer with the original profile. 1 part we need to add a leg for a bottom termination. dimension are on the marked up drawings i will be attaching. call me if any questions. 6155179885 the drawing I marked up says 12 ga but the production sketches say 11ga material, so we need to keep it 11ga, i just sent for jim to order material, copied David | SKETCHES PROGRAMMING FILES |  | K:\25005 - CAT Financial Nashville HQ\25005 - CAT Financial Nashville HQ_DXF | N/A | N/A | N/A | 0 | 4 | 2 | 0 | 0 | 1 | 00:01:33 | 11 Ga. X 48" X 120" HR P&O STL Steel Sheet, No Grain | Steel Sheet | 11 Ga. X 48" X 120" HR P&O STL | No |  |  | 6 | 3 | Hunter Clouse | David Hasty | David Hasty |  |  | Frank Dean | David Hasty | Frank Dean |  |  | Chris Gambrel |  | TRUE |  | Frank Dean | 2026-04-02 08:13 | TRUE | 2026-04-23 | 2026-04-02 | TRUE | 2026-04-20 | 2026-04-06 | 2026-04-13 |  |  |  |  | NO |  | 2026-04-06 | TRUE | Powder Coat | powderworks | Coating Ship Back To JWM |  |  | Approved | NO |  | NO |  | NO | [6 empty] | TruLaser 3040 |  | TRUE |  |  |  | TRUE |  | TruLaser 3040 | [9 empty] | TRUE | [7 empty] | TRUE |  |  | 25005 | ST |  | 02 |  | 2 | 25005-ST02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 2 | 4 | [10 empty] | In House |  |  | Flat Laser | Brake Fab Powder Coat TruLaser 3040 | 2026-04-02 | 2026-04-02 | 1 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Chris Gambrel - @fdean@jwmcd.com @dhasty@jwmcd.com flat program completed | 1010 |  | Chris Buttrey | Frank Dean | David Hasty | 25005-ST02 In-House |  | 2026, Week 16
269 | 26014-04-ST02 |  | 2026 R & D | 3731 Amy Lynn Drive Nashville, TN 37218-3813 | TBC |  | GRAVITY |  | Base plate will weld to 24014-04-ST01 drop is available in the shed﻿. labeled as 152430 | Base plates and angles for 26014-04-FS01 | SKETCHES PROGRAMMING FILES | (0) TUBE, SILPRUF CAULK (0) LF 1/2" DENVER FOAM B-ROD (0) CS - RED 1/8" SHIMS (0) CS - BLACK 1/4" SHIMS (0) #10 X 1" HH TEK 2 SCREWS (0) #12 X 1 1/2" HH TEK 2 SCREWS (0) #12 X 2" HH TEK 2 SCREWS (0) #12 X 2" HH TEK 5 SCREWS (0) TAPCONS | Q:\Jobs\26014-04 - Remodel\04_Production\26014-04ST02 | N/A | N/A | N/A | 0 | 15 | 4 | 0 | 0 | 1 | 00:01:46 | 48 x 96 x .25 6061 Alum Sheet, No Grain | Alum Sheet | 48 x 96 x .25 6061 | No |  |  | 8 | 7 | Hunter Clouse | David Hasty |  |  |  | Frank Dean | David Hasty | Frank Dean |  |  | Chris Gambrel |  | TRUE |  | Frank Dean | 2026-04-02 09:46 | TRUE | 2026-04-23 | 2026-04-08 | TRUE | 2026-04-24 | 2026-04-09 | 2026-04-16 |  |  |  |  | NO |  | 2026-04-03 | TRUE | Powder Coat | PWX | Coating Ship Back To JWM |  |  | None Available | NO |  | NO |  | NO | [6 empty] | TruLaser 3040 |  | TRUE |  |  |  | TRUE |  | TruLaser 3040 | [9 empty] | TRUE |  |  | TRUE | [7 empty] | 26014-04 | ST |  | 02 |  | 2 | 26014-04-ST02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 1 | [10 empty] | In House |  |  | Flat Laser | Brake Powder Coat TruLaser 3040 Weld | 2026-04-07 | 2026-04-08 | 2 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Chris Gambrel - @fdean@jwmcd.com @dhasty@jwmcd.com flat program completed | 1010 |  | TBC | Frank Dean | David Hasty | 26014-04-ST02 In-House |  | 2026, Week 16
270 | 24051-FS231 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 | 400 |  | NORTH LEVEL 150 |  |  | (0) TUBE, SILPRUF CAULK (0) LF 1/2" DENVER FOAM B-ROD (0) CS - RED 1/8" SHIMS (0) CS - BLACK 1/4" SHIMS (0) #10 X 1" HH TEK 2 SCREWS (0) #12 X 1 1/2" HH TEK 2 SCREWS (0) #12 X 2" HH TEK 2 SCREWS (0) #12 X 2" HH TEK 5 SCREWS (0) TAPCONS |  |  |  | 19268 | 1 | [6 empty] | 4mm X 62" X 196", MOONSTONE METALLIC FR ACM, Grain | FR ACM | 4mm X 62" X 196", MOONSTONE METALLIC | Yes |  |  | 14 | 6 | Hennadii Stakhurskyi | Denis Usatenko |  | Hennadii Stakhurskyi |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  |  |  | Hennadii Stakhurskyi | 2026-04-02 15:00 | TRUE | 2026-04-23 |  |  |  |  | 2026-05-04 |  |  |  |  | YES | 500 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | NO |  | NO | [6 empty] | Float |  | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24051 | FS |  | 231 |  | 231 | 24051-FS231 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 4 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Marc Ribar | Hennadii Stakhurskyi | Denis Usatenko | 24051-FS231 In-House |  | 2026, Week 19
271 | 26014-05-FS01 |  | 2026 R & D | 3731 Amy Lynn Drive Nashville, TN 37218-3813 | TBC |  | 400 |  | Shipping Closure Contact George Holland |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 1 SET - LO DRAWINGS * (192 LF) 1-5/8" Reveals * (120 LF) JR2 | Q:\Jobs\26014-05 - Shipping wall\04_Production\26014-05FS01 | Unavailable | 0 | 0 | 25 | 25 | 3 | 148 | 192 | 13 SHEETS | 00d03h53m13s | 4mm X 62" X 196", Gray Velvet [21040] FR ACM, Grain | FR ACM | 4mm X 62" X 196", Gray Velvet [21040] | Yes |  |  | 50 | 7 | Ramon Estrada, Shane Watson | Denis Usatenko |  | Denis Usatenko |  | Chance Dill | Nadira Vlatkovic | Chance Dill |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Chance Dill | 2026-04-02 17:38 | TRUE | 2026-04-23 | 2026-04-08 | TRUE | 2026-04-24 |  | 2026-04-14 |  |  |  |  | YES | 34 | [5 empty] | MATCH COLOR | NO | None Available | NO |  | NO |  | NO | [6 empty] | Ready to Ship | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 26014-05 | FS |  | 01 |  | 1 | 26014-05-FS01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 10 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab | 2026-04-07 | 2026-04-08 | 2 |  | QC Not Requested | 2026-04-14 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-04-15 |  | Issue Still in Process | Arnold Jurado - @cdill@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | TBC | Chance Dill | Nadira Vlatkovic | 26014-05-FS01 In-House |  | 2026, Week 16
272 | 24079-FS102.1 |  | Nashville Youth Campus | 1354 Brick Church Pike Nashville, TN 37207 | Joe Hoyle | 828.334.7808 | 400 |  | AREA D | AREA D - ACM Release #001. Connect layout with FS101. Coordinate FS102 with FS02. Check panel alignment across both approved ACM and fiber shop drawings. Parapet dimensions are in the photos folder. Job is not 100%, there are missing frames, columns and sheathing. We'll be coordinating with the field to resolve missing information. Drawing indicating the extent of scope is found in the FD Docs folder. Calcs are not complete. |  | 1500 lft of 16ga, flat-strap |  |  |  |  | 308 | [6 empty] | 4mm X 62" X 196" 'Cloud White Matte' FR ACM, Grain | FR ACM | 4mm X 62" X 196" 'Cloud White Matte' | Yes |  | MTPK | 14 | 6 | Hennadii Stakhurskyi | Denis Usatenko | Denis Usatenko | Denis Usatenko | Hennadii Stakhurskyi | Hennadii Stakhurskyi | Nadira Vlatkovic | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  |  |  | Denis Usatenko, Hennadii Stakhurskyi | 2026-04-02 17:47 | TRUE | 2026-04-23 |  |  |  |  | 2026-03-16 |  | 2026-03-16 |  |  | YES | 370 | [5 empty] | MATCH COLOR | YES | Approved As Noted | YES | Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - NYCE - FS103 AREA D | NO |  | NO | [6 empty] | Sketch | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 24079 | FS |  | 102.1 |  | 102.1 | 24079-FS303 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 80 | 462 | [10 empty] | Customer Pick Up In House |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Joe Hoyle | Hennadii Stakhurskyi | Nadira Vlatkovic | 24079-FS102.1 In-House |  | 2026, Week 12
273 | 24079-FS201 |  | Nashville Youth Campus | 1354 Brick Church Pike Nashville, TN 37207 | Joe Hoyle | 828.334.7808 | 400 |  | First of thirteen ACM releases for the NYCE - Cottages Ship with 'RRM River Rock Gray' flashing releases. (Specific release number TBD) | First of 8 cottage clerestories. Located on page 233 of approved cottage shop drawings. Next Cottage release will be clerestories 2-8. Reference shop drawings dated 2/25/26, located in FD_Docs folder for FS201. Scope is highlighted on page 102. | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  |  | 41 | [6 empty] | 4mm X 62" X 196" 'RRM River Rock Gray' FR ACM, Grain | FR ACM | 4mm X 62" X 196" 'RRM River Rock Gray' | Yes | TRUE | MTPK | 1 | 8 | Denis Usatenko/MTPK | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-04-06 12:56 |  | 2026-04-27 |  |  |  |  | 2026-05-18 |  |  |  |  | YES | 300 | [5 empty] | MATCH COLOR | YES | Approved As Noted | YES | Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - FS201 - Cottage E Clerestory | NO |  | YES | Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - CALCS | [5 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24079 | FS |  | 201 |  | 201 | 24079-FS303 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 20 | 60 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Joe Hoyle |  | Denis Usatenko | 24079-FS201 In-House |  | 2026, Week 21
274 | 25031-FL06 |  | LLU Mars US Warehouse | 145 Liebherr Drive Tupelo, MS 38801 | Laura Forero | 615.788.7739 | --- |  | THIS IS A TEST PIECE WE CAN USE ANY COLOR FOR THE 0.040" ALSO PART 201 SLIDES INTO PART 202 | There is an issue with the flashing installed, and we have to cover what is installed. Please see the attached sketch for the profile and the quantities. Is very important that PART 201 slides into PART 202. Also, the maximum opening that Part 202 can have is 1/8" | SKETCHES |  | Q:\Jobs\25031 - LLU Mars US Warehouse\04_Production\25031FL06 | N/A | N/A | N/A | 0 | 2 | 2 | 0 | 0 | 1 | N/A | .040" X 48" X 120", ANY COLOR Alum Sheet, No Grain | Alum Sheet | .040" X 48" X 120", ANY COLOR | No |  |  | Shipped | Shipped | Job Complete | Denis Usatenko |  |  |  | Frank Dean | David Hasty | Frank Dean | [6 empty] | Frank Dean | 2026-04-06 14:59 | TRUE | 2026-04-14 | 2026-04-07 | TRUE | 2026-04-13 |  | 2026-04-07 |  |  | 2026-04-16 |  | YES | 1 | [19 empty] | Shipped |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25031 | FL |  | 06 |  | 6 | 25031-FL08 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 0.25 | 1 | [14 empty] | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2026-04-09 | 6 | David Hasty | Ramon Estrada, Shane Watson | 2026-04-16 | TRUE | -8 | Tony Graves - @lforero@jwmcd.com @tgraves@jwmcd.com @rharmon@jwmcd.com these are being formed after lunch. @sjones@jwmcd.com | 1010 |  | Laura Forero | Frank Dean | David Hasty | 25031-FL06 In-House |  | 2026, Week 15
275 | 25002-FS14 |  | Med Center Health | 250 Park Street Bowling Green, KY 42101 | Carlos Silva | 980.246.6545 | 600 |  |  | This is a Change order, we are adding this panels that goes inside the vestibule. Attached you will find the field measures pictures and a CAD file that I used for quantification. | [5 empty] | 2014 | 00 | [6 empty] | ACM: 4mm X 62" X 196" MICA CHAMPAGNE FR ACM, Grain | FR ACM | ACM: 4mm X 62" X 196" MICA CHAMPAGNE | Yes |  |  | 5 | 8 | Denis Usatenko | Denis Usatenko | Denis Usatenko | Denis Usatenko | [5 empty] | Arnold Jurado, Issiah Havens | [5 empty] | 2026-04-06 15:43 | TRUE | 2026-04-27 |  |  |  |  | 2026-05-04 |  |  |  |  | NO | 14 | 2026-04-08 |  |  |  |  | MATCH COLOR | YES | Approved | NO |  | YES | Q:\Jobs\25002 - Med Center Health\03_Engineering\02_FD Docs\PHOTOS VESTIBULE MAIN ENTRANCE FS14 | NO | [6 empty] | Evaluation | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25002 | FS |  | 14 |  | 14 | 25002-FS16 |  |  | 2026-04-10 | 2026-04-13 | 2 |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | 2 | 10 | 10 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Josh McPherson - Thanks Carlos. Denis let us know if there is anything else that you need. | 1010 |  | Carlos Silva |  |  | 25002-FS14 In-House |  | 2026, Week 19
276 | 26014-06-ST01 |  | 2026 R & D | 3731 Amy Lynn Drive Nashville, TN 37218-3813 | TBC |  | CUSTOM ARCH |  | Added weep holes to uprights and lower cross section members | PWX Titus Cart | SKETCHES PROGRAMS | 6 Casters PN: SCC-KP92S630-SSR | Q:\Jobs\26014-06 - PWX Titus Base\Production\26014-ST01 | N/A | N/A | N/A | 0 | 45 | 9 | 0 | 0 | 6 | 18 mins | 6" x 4" x .25" Steel Tube 2" x 2" x 3/16" Steel Angle 4" x 4" x .125" Steel Tube Steel Tube, No Grain | Steel Tube | 6" x 4" x .25" Steel Tube 2" x 2" x 3/16" Steel Angle 4" x 4" x .125" Steel Tube | No |  |  | 1 | 9 | Hunter Clouse | David Hasty |  |  |  | Jonathan Dorsey | David Hasty | Jonathan Dorsey |  |  | Arnold Jurado |  | TRUE |  | Jonathan Dorsey | 2026-04-07 06:56 | TRUE | 2026-04-28 | 2026-04-10 | TRUE | 2026-04-28 |  | 2026-04-17 |  |  |  |  | NO |  | 2026-04-10 | [6 empty] | None Available | NO |  | NO |  | NO | [6 empty] | 7000 TubeLaser 28 |  | TRUE |  |  |  |  | TRUE | [13 empty] | TRUE | [7 empty] | 26014-06 | ST |  | 01 |  | 1 | 26014-06-ST01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 3 | 15 | [10 empty] | In House |  |  | Tube Laser | Tube Laser Weld | 2026-04-09 | 2026-04-09 | 1 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Jonathan Dorsey - @ajurado@jwmcd.com 1001-02 AND 1001-03 added drainage weep holes | 1010 |  | TBC | Jonathan Dorsey | David Hasty | 26014-06-ST01 In-House |  | 2026, Week 16
277 | 25007-RM01 |  | QTS ATL2 DC10 | 167 Tyrone Road, Bldg 1000 Fayetteville, GA 30214 | Nick Akins | 832.948.2317 | 400 |  |  | Panel Number 207-1B02 was made with the wrong mitered corner direction. Please review the attachment and reach out for more explanation. We will need to fabricate reveals to go with this panel. Fully fabricate with extrusions around the porimitor as well. |  | Reveal5/8 - 30LF Color matching screws: 4 Corner clips: 2 | Q:\Jobs\25007 - QTS ATL2 DC10\04_Production\25007RM01-FS01 | 68.9% | 113 | 164 | 1 | 1 | 1 | 6 | 30 | 1 | 00:12:12 | 4mm X 50" X 105", 62" X 196" Ron Red Apolic PE ACM, No Grain | PE ACM | 4mm X 50" X 105", 62" X 196" Ron Red Apolic | No |  |  | 3 | 8 | Mitch Chancey | Denis Usatenko |  |  |  | Ailen Niedfeld | Denis Usatenko | Ailen Niedfeld |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Ailen Niedfeld | 2026-04-07 09:15 | TRUE | 2026-04-09 | 2026-04-09 | TRUE | 2026-04-27 |  | 2026-04-17 |  |  |  |  | YES | 3 | [5 empty] | MATCH COLOR | YES | None Available | NO |  | NO |  | NO |  | (1) 207-1B02 | FS01 |  | ENGINEERING |  | Crating |  | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 25007 | RM |  | 01 |  | 1 | 25007-RM01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 2 | [10 empty] | Sprinter Van |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-04-08 | 2026-04-09 | 2 |  | QC Not Requested | 2026-04-16 | 1 (In Progress) | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Issiah Havens - @aniedfeld@jwmcd.com @jdavis@jwmcd.com programmed | 1010 |  | Nick Akins | Ailen Niedfeld | Denis Usatenko | 25007-RM01 In-House |  | 2026, Week 16
278 | 25012-FS02 |  | St Jude Hospital | 671 St. Jude Place Memphis, TN 38105 | Wylie McDougall | 615.426.7650 | 400 |  |  | This is a Guaranteed dimension release. We will release all panels and hold off on the end panels to be fabricated in the field. | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * (95 LF) 1-5/8" REVEALS * ( 310pcs) CORNER CLIPS * ( 620pcs ) COLOR MATCHING SCREWS * (475 LF) JR2 | Q:\Jobs\25012 - St Jude Hospital\04_Production\25012FS02 | 15.12% | 88 | 582 | 60 | 60 | 8 | 406 | 95 | 60 SHEETS | 00d14h20m55s | 4mm X 62" X 196", Ultra-Cool Carmine Red FR ACM, No Grain | FR ACM | 4mm X 62" X 196", Ultra-Cool Carmine Red | No |  |  | 7 | 40 | Joshua Davis | Denis Usatenko | Ailen Niedfeld | Ailen Niedfeld | Denis Usatenko | Ailen Niedfeld | Denis Usatenko | Ailen Niedfeld |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Ailen Niedfeld | 2026-04-07 09:19 |  | 2026-05-22 | 2026-04-15 |  | 2026-06-10 |  | 2026-06-12 |  |  |  |  | YES | 341 | [5 empty] | RED | YES | Approved | NO |  | YES | Q:\Jobs\25012 - St Jude Hospital\03_Engineering\02_FD Docs\FS02 | NO | [6 empty] | AXYZ 34 | TRUE | TRUE | TRUE | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 25012 | FS |  | 02 |  | 2 | 25012-FS02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 12 | 120 | [10 empty] | Semi |  |  | AXYZ | AXYZ Titans Line Clean and Brake Fab | 2026-04-15 | 2026-04-15 | 1 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Ailen Niedfeld - @wmcdougall@jwmcd.com Left printed sketches at your desk to review, @dusatenko@jwmcd.com has paperwork for shop. Card is actively in Release to Shop. | 1010 |  | Wylie McDougall | Ailen Niedfeld | Denis Usatenko | 25012-FS02 In-House |  | 2026, Week 24
279 | 24039-FL35 |  | The Visionary | 3800 J.B. Hunt Drive Rogers, AR 72758 | Carlos Silva | 980.246.6545 |  |  |  | Flashing, sill flashing and coping different elevations | * SKETCHES |  | Q:\Jobs\24039 - The Visionary\04_Production\24039FL35 | N/A | N/A | N/A | 0 | 62 | 6 | 0 | 0 | 25 - SHTS | NA | Aluminum Sheet: .040" X 48" X 120", ANTHRACITE Alum Sheet, Grain | Alum Sheet | Aluminum Sheet: .040" X 48" X 120", ANTHRACITE | Yes |  |  | 45 | 2 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-04-07 13:33 | TRUE | 2026-04-15 | 2026-04-10 |  | 2026-04-17 |  | 2026-04-21 |  |  |  |  | YES | 00 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 24039 | FL |  | 35 |  | 35 | 24039-FL37 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 2 | 10 | [10 empty] | Semi |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2026-04-15 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-04-16 |  | Issue Still in Process |  | 1010 |  | Carlos Silva | Denis Usatenko |  | 24039-FL35 In-House |  | 2026, Week 17
280 | 24039-BM18 |  | The Visionary | 3800 J.B. Hunt Drive Rogers, AR 72758 | Carlos Silva | 980.246.6545 |  |  | CLEATS for FL35 copings | CLEATS for FL35 copings | * Sketches |  | Q:\Jobs\24039 - The Visionary\04_Production\24039BM18 | N/A | N/A | N/A | 0 | 36 | 1 | 0 | 0 | 9 - SHTS |  | (Galvanized Sheet): 22 Ga. X 48" X 120" Galv Sheet, No Grain | Galv Sheet | (Galvanized Sheet): 22 Ga. X 48" X 120" | No |  |  | 45 | 2 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-04-07 13:38 | TRUE | 2026-04-15 | 2026-04-10 |  | 2026-04-17 |  | 2026-04-21 |  |  |  |  | YES | 00 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 24039 | BM |  | 18 |  | 18 | 24039-BM19 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 0.5 | 4 | [10 empty] | Semi |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2026-04-15 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-04-16 |  | Issue Still in Process |  | 1010 |  | Carlos Silva | Denis Usatenko |  | 24039-BM18 In-House |  | 2026, Week 17
281 | 24039-FL36 |  | The Visionary | 3800 J.B. Hunt Drive Rogers, AR 72758 | Carlos Silva | 980.246.6545 |  |  |  | COPINGS DIFFERENT ELEVATIONS | * Sketches |  | Q:\Jobs\24039 - The Visionary\04_Production\24039FL36 | N/A | N/A | N/A | 0 | 60 | 5 | 0 | 0 | 60 - SHTS |  | Aluminum Sheet: .040" X 48" X 120", OCEAN MASK Alum Sheet, Grain | Alum Sheet | Aluminum Sheet: .040" X 48" X 120", OCEAN MASK | Yes |  |  | 4 | 2 | Samantha Krantz, Shane Jones | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-04-07 15:16 | TRUE | 2026-04-15 | 2026-04-13 | TRUE | 2026-04-17 |  | 2026-04-21 |  |  |  |  | YES | 000 | [19 empty] | Shear |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 24039 | FL |  | 36 |  | 36 | 24039-FL37 |  |  | 2026-04-13 | 2026-04-13 | 1 |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | 1 | 2 | 8 | [10 empty] | Semi |  |  |  | Cidan Shear |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Carlos Silva | Denis Usatenko |  | 24039-FL36 In-House |  | 2026, Week 17
282 | 24039-FL37 |  | The Visionary | 3800 J.B. Hunt Drive Rogers, AR 72758 | Carlos Silva | 980.246.6545 |  |  |  | coping Elev. 237, 245 Silver Metallic | * Sketches |  | Q:\Jobs\24039 - The Visionary\04_Production\24039FL37 | N/A | N/A | N/A | 0 | 16 | 1 | 0 | 0 | 16 - SHTS | na | Aluminum Sheet: .040" X 48" X 120", SILVER METALLIC Alum Sheet, Grain | Alum Sheet | Aluminum Sheet: .040" X 48" X 120", SILVER METALLIC | Yes |  |  | 4 | 2 | Samantha Krantz, Shane Jones | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-04-07 15:24 | TRUE | 2026-04-15 | 2026-04-13 | TRUE | 2026-04-17 |  | 2026-04-21 |  |  |  |  | YES | 00 | [19 empty] | Shear |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 24039 | FL |  | 37 |  | 37 | 24039-FL37 |  |  | 2026-04-13 | 2026-04-13 | 1 |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | 1 | 1 | 6 | [10 empty] | Semi |  |  |  | Cidan Shear |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Carlos Silva | Denis Usatenko |  | 24039-FL37 In-House |  | 2026, Week 17
283 | 24039-BM19 |  | The Visionary | 3800 J.B. Hunt Drive Rogers, AR 72758 | Carlos Silva | 980.246.6545 |  |  | CLEATS for COPINGS FL36, FL37 | CLEATS for COPINGS FL36, FL37 | * Sketches |  | Q:\Jobs\24039 - The Visionary\04_Production\24039BM19 | N/A | N/A | N/A | 0 | 340 | 5 | 0 | 0 | 85.5 - SHTS | NA | Galvanized Sheet: 22 Ga. X 48" X 120" Galv Sheet, No Grain | Galv Sheet | Galvanized Sheet: 22 Ga. X 48" X 120" | No |  |  | 4 | 2 | Samantha Krantz, Shane Jones | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-04-07 15:38 | TRUE | 2026-04-15 | 2026-04-13 | TRUE | 2026-04-17 |  | 2026-04-21 |  |  |  |  | YES | 00 | [19 empty] | Shear |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 24039 | BM |  | 19 |  | 19 | 24039-BM19 |  |  | 2026-04-13 | 2026-04-13 | 1 |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | 1 | 1 | 6 | [10 empty] | Semi |  |  |  | Cidan Shear |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Carlos Silva | Denis Usatenko |  | 24039-BM19 In-House |  | 2026, Week 17
284 | 25010-RO06 |  | TOA Spring Hill MOB | Reserve Blvd Spring Hill, TN 37174 | Cole Norona | 931.591.9340 | 400 |  |  | elevation 216/217 from FS05. 6 oak panels PANELS WERE NOT MADE AS TWO OAK PANELS | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 819 | 6 | 0 | [5 empty] | 4mm X 62" X 196", TENDER OAK FR ACM, Grain | FR ACM | 4mm X 62" X 196", TENDER OAK | Yes |  |  | 3 | 11 | Samuel Lucas | Denis Usatenko | Samuel Lucas | Samuel Lucas |  | Samuel Lucas | Denis Usatenko | Samuel Lucas |  | Arnold Jurado, Issiah Havens |  |  |  |  | Samuel Lucas | 2026-04-09 09:02 | TRUE | 2026-04-30 |  |  |  |  | 2026-04-15 |  |  |  |  | YES | 17 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25010 - TOA Spring Hill MOB\03_Engineering\02_FD Docs\25010RO06 | YES | Q:\Jobs\25010 - TOA Spring Hill MOB\03_Engineering\02_FD Docs\25010RO06 | YES | Q:\Jobs\25010 - TOA Spring Hill MOB\03_Engineering\02_FD Docs\25010RO06 | (2) 216-1T01 (2) 217-2R01 (2) 217-1R07 | FS05 |  |  |  | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25010 | RO |  | 06 |  | 6 | 25010-RO07 |  | TRUE | 2026-04-10 |  | 5 (ON HOLD) |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | 5 | 1 | 8 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Samuel Lucas - @cnorona@jwmcd.com on hold til further info | 1010 |  | Cole Norona | Samuel Lucas | Denis Usatenko | 25010-RO06 In-House |  | 2026, Week 16
285 | 25010-RO07 |  | TOA Spring Hill MOB | Reserve Blvd Spring Hill, TN 37174 | Cole Norona | 931.591.9340 | 400 |  |  | ELEVATION 208. FS06.1. 6 GRAY PANELS NEW PANEL DIMENSIONS | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) 1-5/8" Reveals * ( LF) JR2 |  |  |  | 819 | 3 | 0 | [5 empty] | 4mm X 62" X 196", SUNSHINE GRAY FR ACM, No Grain | FR ACM | 4mm X 62" X 196", SUNSHINE GRAY | No |  |  | 3 | 11 | Samuel Lucas | Denis Usatenko | Samuel Lucas | Samuel Lucas |  | Samuel Lucas | Denis Usatenko | Samuel Lucas |  | Arnold Jurado, Issiah Havens |  |  |  |  | Samuel Lucas | 2026-04-09 09:06 | TRUE | 2026-04-30 |  |  |  |  | 2026-04-15 |  |  |  |  | YES | 61 | [5 empty] | MATCH COLOR | YES | Approved | NO |  | YES | Q:\Jobs\25010 - TOA Spring Hill MOB\03_Engineering\02_FD Docs\25010RO07 | NO |  | (1) 208-1T01B (1) 208-1T02B (1) 208-1T03B | FS06.1 |  |  |  | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25010 | RO |  | 07 |  | 7 | 25010-RO07 |  | TRUE | 2026-04-10 |  | 5 (ON HOLD) |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | 5 | 1 | 5 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Samuel Lucas - @cnorona@jwmcd.com on hold til further info | 1010 |  | Cole Norona | Samuel Lucas | Denis Usatenko | 25010-RO07 In-House |  | 2026, Week 16
286 | 25061-BM01 |  | BNA Concourse A | 1 Terminal Drive Nashville, TN 37214 | Andre Van Der Merwe | 315.261.0333 |  |  | MOCK UP FLASHINGS |  | * Sketch | NA | Q:\Jobs\25061 - BNA Concourse A\04_Production\25061BM01 | N/A | N/A | N/A | 0 | 21 | 4 | 0 | 0 | 4 | na | 16 Ga. X 48" X 120" Galv Sheet, No Grain | Galv Sheet | 16 Ga. X 48" X 120" | No |  |  | 42 | 1 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Gabriela Herrera | [6 empty] | TRUE |  | Gabriela Herrera | 2026-04-09 16:02 | TRUE | 2026-04-17 | 2026-04-10 | TRUE | 2026-04-16 |  | 2026-04-17 |  |  |  |  | YES | 50 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25061 | BM |  | 01 |  | 1 | 25061-BM01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 8 | [10 empty] | In House |  |  |  | Cidan Shear |  | 2026-04-10 | Program Start Date Not Recorded |  | QC Not Requested | 2026-04-13 | 4 | David Hasty | Ramon Estrada, Shane Watson | 2026-04-16 |  | Issue Still in Process |  | 1010 |  | Andre Van Der Merwe | Gabriela Herrera |  | 25061-BM01 In-House |  | 2026, Week 16
287 | 25061-FL01 |  | BNA Concourse A | 1 Terminal Drive Nashville, TN 37214 | Andre Van Der Merwe | 315.261.0333 |  |  | MOCK UP FLASHINGS |  | * SKETCHES | NA | Q:\Jobs\25061 - BNA Concourse A\04_Production\25061FL01 | N/A | N/A | N/A | 0 | 48 | 15 | 0 | 0 | 30 | na | 22 Ga. X 30.5" X 122", Champagne Gold (smooth) Galv Sheet, Grain | Galv Sheet | 22 Ga. X 30.5" X 122", Champagne Gold (smooth) | Yes |  |  | 1 | 1 | Samantha Krantz, Shane Jones | Denis Usatenko |  |  |  | Gabriela Herrera | [6 empty] | TRUE |  | Gabriela Herrera | 2026-04-09 16:15 | TRUE | 2026-04-17 | 2026-04-10 | TRUE | 2026-04-16 |  | 2026-04-17 |  |  |  |  | YES | 30 | [19 empty] | Cidan |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25061 | FL |  | 01 |  | 1 | 25061-FL01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 16 | [10 empty] | In House |  |  |  | Cidan Shear |  | 2026-04-10 | Program Start Date Not Recorded |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Andre Van Der Merwe | Gabriela Herrera |  | 25061-FL01 In-House |  | 2026, Week 16
288 | 24051-FL01 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 |  |  | CHANGE ORDER 2 - PERF FLASHING PLEASE PUT PROTECTIVE FILM ON MATERIAL TO ELIMINATE DAMAGE |  | SKETCHES PROGRAMMING FILES |  | Q:\Jobs\24051 - TN Titans Stadium\04_Production\24051FL01 | N/A | N/A | N/A | 0 | 25 | 1 | 0 | 0 | 4 | 07:56:55 | .040" X 48" X 120", TOB BLACK Alum Sheet, No Grain | Alum Sheet | .040" X 48" X 120", TOB BLACK | No |  |  | 1 | 5 | Drew Adams, Hunter Clouse, Ronnie Harmon, Tony Graves | Denis Usatenko | David Hasty |  |  | Frank Dean | David Hasty | Frank Dean |  |  |  | Chris Gambrel | TRUE |  | Frank Dean | 2026-04-10 09:30 | TRUE | 2026-04-20 | 2026-04-16 | TRUE | 2026-04-22 |  | 2026-04-24 |  |  |  |  | YES | 100 | [19 empty] | Release to Shop |  | TRUE | [6 empty] | TRUE | 7000 TruMatic | [7 empty] | TRUE | [10 empty] | 24051 | FL |  | 01 |  | 1 | 24051-FL01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 16 | [10 empty] | In House |  |  | Punch | 7000 TruMatic Brake | 2026-04-15 | 2026-04-16 | 2 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Chris Gambrel - @fdean@jwmcd.com @dhasty@jwmcd.com flat program completed | 1010 |  | Marc Ribar | Frank Dean | David Hasty | 24051-FL01 In-House |  | 2026, Week 17
289 | 25022-RM01 |  | Vantage VA15 | 45210 Vantage Data Plaza Sterling, VA 20166 | Thomas Mooers |  | 400 |  |  | Engineering: These remakes are corner panels. Face of Panel should be 4' 7/8" wide. The return face of panel is correct. | * SKETCHES * COLOR LABELS * TIGER SAW EXTRUSION LIST * PANEL CUT LIST * ﻿CODING FILES | * 4 LF JR2 * 8 PCS CORNER CLIPS * 24 PCS COLOR MATCHING SCREWS | Q:\Jobs\25022 - Vantage VA15\04_Production\25022RM01 | 152% | 927 | 610 | 4 | 4 | 4 | 43 | - | 4 SHEETS | 00d00h58m16s | 4mm X 62" X 196", Vantage blue FR ACM, Grain | FR ACM | 4mm X 62" X 196", Vantage blue | Yes |  |  | 5 | 12 | Joshua Davis | Denis Usatenko |  | Gabriela Herrera |  | Gabriela Herrera | Denis Usatenko | Gabriela Herrera |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Gabriela Herrera | 2026-04-10 13:52 | TRUE | 2026-04-14 | 2026-04-15 | TRUE | 2026-05-01 |  | 2026-04-23 |  |  |  |  | YES | 4 | [5 empty] | Gray | YES | Approved | NO |  | YES | Q:\Jobs\25022 - Vantage VA15\03_Engineering\02_FD Docs | YES | Standard | 204-2GAAA09 204-2GAAA07 204-2GAAA05 204-2GAAA03 | FS09 |  | FIELD DIMENSION/SCAN |  | AXYZ 34 |  | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25022 | RM |  | 01 |  | 1 | 25022-RM02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 4 | 8 | [10 empty] | Hot Shot |  |  | AXYZ | AXYZ Clean and Brake Fab | 2026-04-13 | 2026-04-15 | 3 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Arnold Jurado - @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Thomas Mooers | Gabriela Herrera | Denis Usatenko | 25022-RM01 In-House |  | 2026, Week 17
290 | 25022-RM02 |  | Vantage VA15 | 45210 Vantage Data Plaza Sterling, VA 20166 | Thomas Mooers |  | 400 |  |  |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS |  | Q:\Jobs\25022 - Vantage VA15\04_Production\25022RM02-FS04 | 150.8% | 920 | 610 | 1 | 1 | 1 | 4 | 27 | 1 SHEET | 00d00h12m25s | 4mm X 48" X 120", Cadet Gray FR ACM, Grain | FR ACM | 4mm X 48" X 120", Cadet Gray | Yes |  |  | 3 | 10 | Joshua Davis | Denis Usatenko | Gabriela Herrera |  |  | Gabriela Herrera |  |  |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Gabriela Herrera | 2026-04-10 14:26 | TRUE | 2026-04-14 | 2026-04-13 | TRUE | 2026-04-29 |  | 2026-04-23 |  |  |  |  | YES | 20 | [5 empty] | Gray | YES | Approved | YES | Engineering Folder | NO |  | YES | Standard | (1) 209-1N10 | FS04 |  | FIELD INSTALLERS |  | AXYZ 34 |  | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25022 | RM |  | 02 |  | 2 | 25022-RM02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 1 | [10 empty] | Hot Shot |  |  | AXYZ | AXYZ Clean and Brake Fab | 2026-04-13 | 2026-04-14 | 2 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Arnold Jurado - @gherrera@jwmcd.com @jdavis@jwmcd.com PROGGRAMMED | 1010 |  | Thomas Mooers | Gabriela Herrera |  | 25022-RM02 In-House |  | 2026, Week 17
291 | 24079-RP03 |  | Nashville Youth Campus | 1354 Brick Church Pike Nashville, TN 37207 | Joe Hoyle | 828.334.7808 |  |  |  | Bad Tabs Parts Moved |  |  |  | Unavailable | 551 |  | 2 | 4 | 0 | 0 | 0 | 1 SHEET | 00d00h24m39s | 4mm X 62" X 196" 'CWM - Cloud White MATTE' FR ACM, Grain | [5 empty] | Shipped | Shipped | Job Complete | Denis Usatenko | [5 empty] | Paul J Roberts |  | Arnold Jurado, Issiah Havens |  |  |  |  | Gabriela Herrera | 2026-04-11 09:44 |  | 2026-04-11 | 2026-04-13 |  | 2026-04-13 |  |  |  |  | 2026-04-16 | [17 empty] | TRIM (X4) 209-3F33 208-3F17 | FS101.1 | MACHINE |  | jdavis@jwmcd.com | Shipped |  |  | TRUE | AXYZ 34 | [20 empty] | TRUE | TRUE |  |  | 24079 |  | RP | 03 | -- | 3 | 24079-RP03 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | [15 empty] | AXYZ | AXYZ 34 Clean and Brake Fab | 2026-04-11 |  | 4 (In Progress) |  | QC Not Requested | 2026-04-15 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-04-16 | TRUE | 0 | Arnold Jurado - @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Joe Hoyle |  |  | 24079-RP03 In-House |  | #INVALID DATA TYPE
292 | 24071-RP14 |  | RS Gass State Lab | 975 RS Gass Blvd Nashville, TN 37216 | Cole Norona | 931.591.9340 |  |  |  | Bad copes |  |  |  | 93.52% | 2483 | 2655 | 1 | 0 | 0 | 0 | 0 | 1 SHEET | 00d00h14m34s | 4mm X 62" X 196", BRIGHT METALLIC SILVER FR ACM, Grain | [5 empty] | Shipped | Shipped | Job Complete | Denis Usatenko | [5 empty] | Paul J Roberts |  | Arnold Jurado, Issiah Havens |  |  |  |  | Gabriela Herrera | 2026-04-11 09:46 |  | 2026-04-11 | 2026-04-13 |  | 2026-04-13 |  |  |  |  | 2026-04-16 | [17 empty] | 306-1NF08A | FS11 | MACHINE |  | jdavis@jwmcd.com | Shipped |  |  | TRUE | AXYZ 34 | [20 empty] | TRUE | TRUE |  |  | 24071 |  | RP | 14 | -- | 14 | 24071-RP15 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | [15 empty] | AXYZ | AXYZ 34 Clean and Brake Fab | 2026-04-11 |  | 4 (In Progress) |  | QC Not Requested | 2026-04-15 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-04-16 | TRUE | 0 | Arnold Jurado - @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Cole Norona |  |  | 24071-RP14 In-House |  | #INVALID DATA TYPE
293 | 24079-FS301 |  | Nashville Youth Campus | 1354 Brick Church Pike Nashville, TN 37207 | Joe Hoyle | 828.334.7808 | 400 |  | ARF Release # 001 of 004. Update inventory after completing release. | AAN and 'For Record' Drawings located in FD Docs folder. REL#001 includes all panels on west elevation along with the small north elevation prior to the canopy. Reference pages 206 through 208. Scope breakdown document located in FD Docs folder. |  | TBD |  |  |  |  | 143 | [6 empty] | 4mm X 62" X 196" 'Cloud White Matte' FR ACM, Grain | FR ACM | 4mm X 62" X 196" 'Cloud White Matte' | Yes | TRUE | MTPK | 2 | 13 | Denis Usatenko/MTPK | Denis Usatenko |  | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-04-12 19:38 |  | 2026-05-04 |  |  |  |  | 2026-05-25 |  |  |  |  | YES | 635 | [5 empty] | MATCH COLOR | YES | Approved As Noted | YES | Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - FS301 - ARF 1.0 | NO |  | YES | Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - CALCS | [5 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24079 | FS |  | 301 |  | 301 | 24079-FS303 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 60 | 180 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Joe Hoyle |  | Denis Usatenko | 24079-FS301 In-House |  | 2026, Week 22
294 | 24079-FS302 |  | Nashville Youth Campus | 1354 Brick Church Pike Nashville, TN 37207 | Joe Hoyle | 828.334.7808 | 400 |  | ARF Release # 002 of 004. Update inventory after completing release. | AAN and 'For Record' Drawings located in FD Docs folder. REL#002 includes all canopy panels and half of the east elevation panels. Reference elevations on pages 205, 206 and 211. Scope breakdown document located in FD Docs folder. |  | TBD |  |  |  |  | 188 | [6 empty] | 4mm X 62" X 196" 'Cloud White Matte' FR ACM, Grain | FR ACM | 4mm X 62" X 196" 'Cloud White Matte' | Yes | TRUE | MTPK | 2 | 13 | Denis Usatenko/MTPK | Denis Usatenko |  | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-04-12 19:47 | TRUE | 2026-05-04 |  |  |  |  | 2026-05-18 |  |  |  |  | YES | 635 | [5 empty] | MATCH COLOR | YES | Approved As Noted | YES | Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - FS301 - ARF 1.0 | NO |  | YES | Calcs Location Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - CALCS | [5 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24079 | FS |  | 302 |  | 302 | 24079-FS303 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 80 | 220 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Joe Hoyle |  | Denis Usatenko | 24079-FS302 In-House |  | 2026, Week 21
295 | 24079-FS303 |  | Nashville Youth Campus | 1354 Brick Church Pike Nashville, TN 37207 | Joe Hoyle | 828.334.7808 | 400 |  | ARF Release # 003 of 004. Update inventory after completing release. | AAN and 'For Record' Drawings located in FD Docs folder. REL#003 includes the remaining east elevation panels and all roof panels. Reference elevations on pages 202, 203, 204, 208, and 212. Scope breakdown document located in FD Docs folder. |  | TBD |  |  |  |  | 165 | [6 empty] | 4mm X 62" X 196" 'Cloud White Matte' FR ACM, Grain | FR ACM | 4mm X 62" X 196" 'Cloud White Matte' | Yes | TRUE | MTPK | 2 | 13 | Denis Usatenko/MTPK | Denis Usatenko |  | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-04-12 19:54 |  | 2026-05-04 |  |  |  |  | 2026-05-25 |  |  |  |  | YES | 635 | [5 empty] | MATCH COLOR | YES | Approved As Noted | YES | Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - FS301 - ARF 1.0 | NO |  | YES | Calcs Location Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - CALCS | [5 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24079 | FS |  | 303 |  | 303 | 24079-FS303 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 80 | 180 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Joe Hoyle |  | Denis Usatenko | 24079-FS303 In-House |  | 2026, Week 22
296 | 25022-RO03 |  | Vantage VA15 | 45210 Vantage Data Plaza Sterling, VA 20166 | Thomas Mooers |  | 400 |  |  | Panels damaged by another trade. These are remakes. | * SKETCHES * PANEL CUT LIST * TIGER SAW EXTRUSION LIST * CODING FILES * ﻿COLOR LABELS |  | Q:\Jobs\25022 - Vantage VA15\04_Production\25022RO03-FS04 | 151.3% | 923 | 610 | 3 | 3 | 1 | 12 | - | 3 SHEETS | 00d00h37m15s | 4mm X 48" X 120", Cadet Gray FR ACM, Grain | FR ACM | 4mm X 48" X 120", Cadet Gray | Yes |  |  | 4 | 11 | Joshua Davis | Denis Usatenko |  |  |  | Gabriela Herrera |  |  |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Gabriela Herrera | 2026-04-13 08:32 | TRUE | 2026-05-04 | 2026-04-14 | TRUE | 2026-04-30 |  | 2026-04-27 |  |  |  |  | YES | 20 | 2026-04-27 |  |  |  |  | Gray | YES | Approved | YES | Not needed | NO |  | YES | Standard | (3) 209-1N10 | FS04 |  |  |  | AXYZ 34 |  | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25022 | RO |  | 03 |  | 3 | 25022-RO03 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 3 | [10 empty] | Hot Shot |  |  | AXYZ | AXYZ Clean and Brake Fab | 2026-04-13 | 2026-04-14 | 2 |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Arnold Jurado - @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Thomas Mooers | Gabriela Herrera |  | 25022-RO03 In-House |  | 2026, Week 18
297 | 25025-FL11 |  | QTS MAN1 DC6 | 9540 Godwin Drive Manassas, VA 20110 | Dillon Bowman | 518.860.9477 |  |  | South Elevation FL | South Elevation FL - Profile 104 in SMX Silver | * Sketch |  | Q:\Jobs\25025 - QTS MAN1 DC6\04_Production\25025FL11 | N/A | N/A | N/A | 0 | 10 | 1 | 0 | 0 | 2 - SHTS | na | .032 x 48 x 120 - SMX Silver (25025) Alum Sheet, No Grain | Alum Sheet | .032 x 48 x 120 - SMX Silver (25025) | No |  |  | 45 | 2 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-04-13 10:08 | TRUE | 2026-04-21 | 2026-04-13 | TRUE | 2026-04-17 |  | 2026-04-17 |  |  |  |  | YES | 15 | [19 empty] | Ready to Ship |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25025 | FL |  | 11 |  | 11 | 25025-FL11 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 0.5 | 2 | [10 empty] | Sprinter Van |  |  |  | Cidan Shear |  |  | No Program Requested |  | QC Not Requested | 2026-04-15 | 2 | David Hasty | Ramon Estrada, Shane Watson | 2026-04-16 |  | Issue Still in Process | Mitch Chancey - LOOSE ON THE TREE | 1010 |  | Dillon Bowman | Denis Usatenko |  | 25025-FL11 In-House |  | 2026, Week 16
298 | 25025-RO02 |  | QTS MAN1 DC6 | 9540 Godwin Drive Manassas, VA 20110 | Dillon Bowman | 518.860.9477 | 400 |  | Freedom Wall base RO | Freedom Wall base RO | * SKETCH * COLOR LABELS * CODING FILES *﻿ PANEL CUT LIST * TIGER SAW EXTRUSION LIST | * 2 PCS CORNER CLIPS * 4 PCS COLOR MATCHING SCREWS | Q:\Jobs\25025 - QTS MAN1 DC6\04_Production\25025RO02-FS21 | 187.2% | 1269 | 678 | 1 | 1 | 1 | 6 | - | 1 SHEET | 00d00h11m15s | 4mm x 62 x 196 - Ron Red (25025) FR ACM, No Grain | FR ACM | 4mm x 62 x 196 - Ron Red (25025) | No |  |  | 51 | 10 | Ramon Estrada, Shane Watson | Denis Usatenko |  |  |  | Gabriela Herrera |  |  |  | Arnold Jurado, Issiah Havens |  |  | TRUE |  | Gabriela Herrera | 2026-04-13 10:12 | TRUE | 2026-05-04 | 2026-04-13 | TRUE | 2026-04-29 |  | 2026-04-17 |  |  |  |  | YES | 22 | [5 empty] | MATCH COLOR | YES | Approved As Noted | NO |  | NO |  | NO |  | 222-3B03 | FS21 |  |  |  | Ready to Ship |  | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25025 | RO |  | 02 |  | 2 | 25025-RO02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 0.25 | 3 | [10 empty] | Sprinter Van |  |  | AXYZ | AXYZ Clean and Brake Fab | 2026-04-13 | 2026-04-14 | 2 |  | QC Not Requested | 2026-04-16 | 1 | David Hasty | Ramon Estrada, Shane Watson | 2026-04-16 |  | Issue Still in Process | Arnold Jurado - @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | 1010 |  | Dillon Bowman | Gabriela Herrera |  | 25025-RO02 In-House |  | 2026, Week 16
299 | 25006-FS09 |  | MALETA Housing and Dining | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | ELEVATION 205-206; 152 GRAPHITE | [5 empty] | 2058 | 152 | [6 empty] | 4mm X 62" X 196", GRAPHITE MICA FR ACM, Grain | FR ACM | 4mm X 62" X 196", GRAPHITE MICA | Yes | TRUE | MTPK | 6 | 32 | Denis Usatenko/MTPK | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-04-13 10:19 |  | 2026-05-29 |  |  |  |  | 2026-06-19 |  |  |  |  | YES | 531 | [5 empty] | MATCH COLOR | YES | Approved As Noted | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS09 ELEVATION 205-206 | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS09 ELEVATION 205-206 | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25006 | FS |  | 09 |  | 9 | 25006-FS13 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 70 | 250 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Cole Norona |  | Denis Usatenko | 25006-FS09 In-House |  | 2026, Week 25
300 | 25006-FS10 |  | MALETA Housing and Dining | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | ELEVATION 203-204; 140 GRAPHITE SCANS IN FS09 FOLDER DUE TO STORAGE SPACE | [5 empty] | 2058 | 140 | [6 empty] | 4mm X 62" X 196", GRAPHITE MICA FR ACM, Grain | FR ACM | 4mm X 62" X 196", GRAPHITE MICA | Yes | TRUE | MTPK | 7 | 41 | Denis Usatenko/MTPK | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-04-13 10:29 |  | 2026-06-11 |  |  |  |  | 2026-07-02 |  |  |  |  | YES | 531 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS10 ELEVATION 203-204 | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS10 ELEVATION 203-204 | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [22 empty] | TRUE |  |  | 25006 | FS |  | 10 |  | 10 | 25006-FS13 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 40 | 235 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Cole Norona |  | Denis Usatenko | 25006-FS10 In-House |  | 2026, Week 27
301 | 25006-FS11 |  | MALETA Housing and Dining | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | ELEVATION 201, 222-223; 201 GRAPHITE SCANS IN FS09 FOLDER DUE TO STORAGE SPACE | [5 empty] | 2058 | 201 | [6 empty] | 4mm X 62" X 196", GRAPHITE MICA FR ACM, Grain | FR ACM | 4mm X 62" X 196", GRAPHITE MICA | Yes | TRUE | MTPK | 8 | 50 | Denis Usatenko/MTPK | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-04-13 10:29 |  | 2026-06-24 |  |  |  |  | 2026-07-15 |  |  |  |  | YES | 531 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS11 ELEVATION 201 222-223 | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS11 ELEVATION 201 222-223 | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25006 | FS |  | 11 |  | 11 | 25006-FS13 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 100 | 340 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Cole Norona |  | Denis Usatenko | 25006-FS11 In-House |  | 2026, Week 29
302 | 25006-FS12 |  | MALETA Housing and Dining | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | ELEVATION 220-221; 192 GRAPHITE SCANS IN FS09 FOLDER DUE TO STORAGE SPACE | [5 empty] | 2058 | 192 | [6 empty] | 4mm X 62" X 196", GRAPHITE MICA FR ACM, Grain | FR ACM | 4mm X 62" X 196", GRAPHITE MICA | Yes | TRUE | MTPK | 9 | 58 | Denis Usatenko/MTPK | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-04-13 10:29 |  | 2026-07-06 |  |  |  |  | 2026-07-27 |  |  |  |  | YES | 531 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS12 ELEVATION 220-221 | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS12 ELEVATION 220-221 | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25006 | FS |  | 12 |  | 12 | 25006-FS13 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 93 | 323 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Cole Norona |  | Denis Usatenko | 25006-FS12 In-House |  | 2026, Week 31
303 | 25006-FS13 |  | MALETA Housing and Dining | Nashville, TN 37209 | Cole Norona | 931.591.9340 | 400 |  |  | ELEVATION 223; 28 TERRA COTA SCANS IN FS09 FOLDER DUE TO STORAGE SPACE | [5 empty] | 2058 | 28 | [6 empty] | 4mm X 62" X 196", TERRA COTA FR ACM, No Grain | FR ACM | 4mm X 62" X 196", TERRA COTA | No | TRUE | MTPK | 10 | 63 | Denis Usatenko/MTPK | Denis Usatenko | Denis Usatenko | Denis Usatenko | Nadira Vlatkovic |  | Denis Usatenko |  |  | Arnold Jurado, Issiah Havens | [5 empty] | 2026-04-13 10:30 |  | 2026-07-13 |  |  |  |  | 2026-08-03 |  |  |  |  | YES | 27 | [5 empty] | MATCH COLOR | YES | Approved | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS13 ELEVATION 223 | YES | Q:\Jobs\25006 - MALETA Housing and Dining\03_Engineering\02_FD Docs\25006FS13 ELEVATION 223 | NO | [6 empty] | LO | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25006 | FS |  | 13 |  | 13 | 25006-FS13 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 12 | 45 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Cole Norona |  | Denis Usatenko | 25006-FS13 In-House |  | 2026, Week 32
304 | 25029-ST73 |  | Lourdes CC Phase 2 | 1510 Lone Oak Road Paducah, KY 42003 | Dillon Bowman | 518.860.9477 | CUSTOM ARCH |  | Anchors for Base Plate | Anchors for Base Plate - 19" | [5 empty] | N/A |  | 6 | [5 empty] | 3/4" x 120" - ASTMF1554 Grade 36 Steel (Tool Crib) Steel Custom Shape, No Grain | Steel Custom Shape | 3/4" x 120" - ASTMF1554 Grade 36 Steel (Tool Crib) | No |  |  | 5 | 13 | Jonathan Dorsey | David Hasty |  |  |  | Jonathan Dorsey | David Hasty | Jonathan Dorsey | [6 empty] | Jonathan Dorsey | 2026-04-13 10:32 | TRUE | 2026-05-04 |  |  |  |  | 2026-04-15 |  |  |  |  | YES | [8 empty] | None Available | NO |  | NO |  | NO | [6 empty] | Sketch | [28 empty] | 25029 | ST |  | 73 |  | 73 | 25029-ST73 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 0.5 | 2 | [10 empty] | In House | [6 empty] | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Dillon Bowman | Jonathan Dorsey | David Hasty | 25029-ST73 In-House |  | 2026, Week 16
305 | 25002-FS15 |  | Med Center Health | 250 Park Street Bowling Green, KY 42101 | Carlos Silva | 980.246.6545 | 600 |  |  | the last panels are missing in different places around the building info location: Q:\Jobs\25002 - Med Center Health\03_Engineering\02_FD Docs\Photos and SD FS15 Also, I add a panel was damaged. attached you will find the image showing the damaged panel. | [5 empty] | 2014 | 12 | [6 empty] | ACM 4mm X 62" X 196", MICA MHJ CPPR FR ACM, Grain | FR ACM | ACM 4mm X 62" X 196", MICA MHJ CPPR | Yes |  |  | 7 | 13 | Denis Usatenko | Denis Usatenko | Denis Usatenko | Denis Usatenko | [5 empty] | Arnold Jurado, Issiah Havens | [5 empty] | 2026-04-13 11:02 | TRUE | 2026-05-04 |  |  |  |  | 2026-05-11 |  |  |  |  | YES | 14 | [5 empty] | N/A | N/A | Approved | NO |  | YES | Q:\Jobs\25002 - Med Center Health\03_Engineering\02_FD Docs\Photos and SD FS15 | NO | [6 empty] | Evaluation | TRUE | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25002 | FS |  | 15 |  | 15 | 25002-FS16 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 3 | 8 | [10 empty] | In House |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Carlos Silva |  |  | 25002-FS15 In-House |  | 2026, Week 20
306 | 1040-30791-ST10 |  | AFI - YANCEY | CUSTOMER PICK-UP | Hannah Sadloski, Lisa Ellison |  | --- | TRUE | ASSEMBLE IN CRATING (15) YBCO-01034 / D / BIRDSCREEN KIT (15) YBCO-01065 / D / DISCHARGE WALL (15)YBCO-01020 / D / FRONT WALL KIT (15) YBCO-01024 / D / INTAKE WALL KIT (15) YBCO-01043 / D / RIGHT WALL KIT (15) YBCO-01054 / D / LEFT WALL KIT (15) YBCO-01040 / D / TRYSTAR BASE KIT (30) YBCO-01038 / D / TRANSFORMER BRACKET KIT (15) YBCO-01252 / D / SOUND BAFFLE KIT (15) YBCO-01029 / D / REAR FIXED WALL (0) D5BA22-24-32 / D / UREA TANK BRACKET (20) D5K56-37-3-2-019-AL / D / EXHAUST BEAUTY RING |  | SAW CUT LIST KIT LIST (CRATING PLAN) YANCEY MATERIAL SAW DAILY FORM | ADDITIONAL PARTS FOR PACKAGING FROM TUBE LASER AND FLAT/FORM OPERATIONS PER KIT LIST 1.5 X 1.5 X .125 Alum. Angle 2 X 2 X .125 Alum. Angle 2 X 3 X .190 Alum. Angle 2 X 2 X .125 Alum. Tube 2 X 2 X .125 Alum. Tube 2 X 3 X .125 Alum. Tube 2 X 3 X .125 Alum. Tube 2 X 3 X .250 Alum. Tube 2 X 4 X .125 Alum. Tube 2 X 4 X .250 Alum. Tube 2 X 6 X .250 Alum. Tube | T:\01 IN-PROCESS ORDERS\0002 SPECTRUM\104030791 AFI YANCEY MULTIPLE POS\03_Production | N/A | N/A | N/A | 0 | 185 | 0 | 6095 | 0 | N/A | N/A | SEE MISC MATERIALS: Alum Angle, Alum Tube | Alum Tube | SEE MISC MATERIALS: Alum Angle, |  |  |  | 1 | 5 | Unassigned | David Hasty | [5 empty] | David Hasty | [6 empty] | Frank Dean | 2026-04-14 13:08 | TRUE | 2026-04-15 | 2026-04-14 | TRUE | 2026-04-22 |  | 2026-04-24 |  |  |  |  | YES | [20 empty] | Extrusion Saw | [15 empty] | TRUE | [10 empty] | TRUE | 15000 | 1040-30791 | ST |  | 10 |  | 10 | 1040-30791-ST10 | 2026-04-15 |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | [12 empty] | Customer Pick Up |  |  |  | Assembly Extrusion Saw |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1040 |  | Hannah Sadloski, Lisa Ellison |  |  | 1040-30791-ST10 In-House |  | 2026, Week 17
307 | 24079-RM01 |  | Nashville Youth Campus | 1354 Brick Church Pike Nashville, TN 37207 | Joe Hoyle | 828.334.7808 | 400 |  | SUBCONTRACTOR PICK-UP | West/South elevation parapet remakes. Parapet depth to be 19-1/4". All other dimensions to stay the same. Reference latest Courthouse shop drawings (Rev3 Upd 2 - dated 2/28/26) | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 SETS - INSTALL DRAWINGS * ( LF) JR2 |  |  |  |  | 37 | 39 | [6 empty] | FR ACM | 4mm X 62" X 196" 'Cloud White Matte' | Yes |  |  | 13 | 1 | Hennadii Stakhurskyi | David Hasty |  |  |  | Hennadii Stakhurskyi | Denis Usatenko | Hennadii Stakhurskyi |  | Arnold Jurado, Issiah Havens |  |  |  |  | Hennadii Stakhurskyi | 2026-04-14 15:10 | TRUE | 2026-04-16 |  |  |  |  | 2026-04-24 |  |  |  |  | YES | 635 | [5 empty] | MATCH COLOR | YES | Approved As Noted | YES | Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - NYCE - FS101 AREA B | YES | Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - NYCE - FS101 AREA B\Photos | YES | Q:\Jobs\24079 - Nashville Youth Campus\03_Engineering\02_FD Docs\24079 - CALCS | 205-3B22 205-3B23 205-3B24 205-3B25 205-3B26 205-3B27 205-3B28 205-3B29 205-3B30 205-3B31 205-3B32 205-3B33 205-3B34 205-3B35 205-3B36 205-3B37 206-3B15 206-3B16 206-3B17 206-3B18 206-3B19 206-3B20 206-3B21 207-3B01a 207-3B01b 207-3B01c 207-3B02 207-3B03 207-3B04 207-3B05 207-3B06 207-3B07 207-3B08 207-3B09 207-3B10 207-3B11 207-3B12 207-3B13 207-3B14 | FS101 |  | ENGINEERING |  | Sketch |  | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 24079 | RM |  | 01 |  | 1 | 24079-RM01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 2 | 40 | [10 empty] | Customer Pick Up |  |  | AXYZ | AXYZ Clean and Brake Fab |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Joe Hoyle | Hennadii Stakhurskyi | Denis Usatenko | 24079-RM01 In-House |  | 2026, Week 17
308 | 25067-FL02 |  | Harison Bend | 830 Discovery Lane Knoxville, TN 37918 | Andre Van Der Merwe | 315.261.0333 |  |  |  | 8 x 10' flashing/coping | * Sketch |  | Q:\Jobs\25067 - Harison Bend\04_Production\25067FL02 | N/A | N/A | N/A | 0 | 8 | 1 | 0 | 0 | 2 - SHTS | na | .040" X 48" X 120", Gray Metallic Alum Sheet, Grain | Alum Sheet | .040" X 48" X 120", Gray Metallic | Yes |  |  | 7 | 4 | Samantha Krantz, Shane Jones | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-04-15 07:58 | TRUE | 2026-04-23 | 2026-04-15 | TRUE | 2026-04-21 |  | 2026-04-23 |  |  |  |  | YES | 3 | [19 empty] | Shear |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25067 | FL |  | 02 |  | 2 | 25067-FL02 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 2 | 4 | [10 empty] | Hot Shot |  |  |  | Cidan Shear |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Andre Van Der Merwe | Denis Usatenko |  | 25067-FL02 In-House |  | 2026, Week 17
309 | 25022-BM06 |  | Vantage VA15 | 45210 Vantage Data Plaza Sterling, VA 20166 | Thomas Mooers | [5 empty] | * Sketch |  | Q:\Jobs\25022 - Vantage VA15\04_Production\25022BM06 | N/A | N/A | N/A | 0 | 500 | 1 | 0 | 0 | 62.5 - SHTS | na | 16 Ga. X 48" X 120" Galv Sheet, No Grain | Galv Sheet | 16 Ga. X 48" X 120" | No |  |  | 7 | 4 | Samantha Krantz, Shane Jones | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-04-15 09:00 | TRUE | 2026-04-23 | 2026-04-15 | TRUE | 2026-04-21 |  | 2026-04-22 |  |  |  |  | YES | 63 | [19 empty] | Shear |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25022 | BM |  | 06 |  | 6 | 25022-BM06 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 0 | 10 | [10 empty] | Hot Shot |  |  |  | Cidan Shear |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Drew Adams - We currently have 9 jobs on the Shear, and 3 more scheduled before 04/22. We just got this Released to Shop today. I think we will need to discuss. @tmooers@jwmcd.com @jmcpherson@jwmcd.com @tgraves@jwmcd.com @sjones@jwmcd.com | 1010 |  | Thomas Mooers | Denis Usatenko |  | 25022-BM06 In-House |  | 2026, Week 17
310 | 25031-RO01 |  | LLU Mars US Warehouse | 145 Liebherr Drive Tupelo, MS 38801 | Laura Forero | 615.788.7739 | 400 |  | I'm looking to have these 3 panels done by Wednesday of next week, 4/22. The plan is to ship this with 25031FL08 on Thursday of next week. | Another trade scratched our panels, and the GC needs to move a pipe. The quantities and the sketches are attached. | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * 2 PCS CORNER CLIPS * 4 PCS COLOR MATCHING SCREWS * 35 LF 1 5/8" ﻿COLOR MATCHING REVEALS * 18 LF JR2 | Q:\Jobs\25031 - LLU Mars US Warehouse\04_Production\25031RO01 |  |  | 504 | 3 | 3 | 3 | 38 | 35 |  |  | Alpolic 4mm X 62" X 196", Dusty Grey Alpolic DROP 4mm X 62" X 84", Dusty Grey FR ACM, No Grain | FR ACM | Alpolic 4mm X 62" X 196", Dusty Grey Alpolic DROP 4mm X 62" X 84", Dusty Grey | No |  |  | 6 | 15 | Arnold Jurado, Issiah Havens | Denis Usatenko |  |  |  | Gabriela Herrera |  |  |  | Arnold Jurado, Issiah Havens |  |  |  |  | Gabriela Herrera | 2026-04-15 11:10 | TRUE | 2026-05-06 |  |  |  |  | 2026-04-22 |  |  |  |  | YES | 1 | [5 empty] | MATCH COLOR | YES | Approved As Noted | NO |  | YES | Q:\Jobs\25031 - LLU Mars US Warehouse\03_Engineering\02_FD Docs\25031ROO1 | NO |  | (1) 302-B05 (1) 302-B06 (1) 302-B08 | FS01 |  |  |  | CNC Programming |  | TRUE |  | AXYZ Titans Line | [20 empty] | TRUE | TRUE |  |  | 25031 | RO |  | 01 |  | 1 | 25031-RO01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 0.25 | 5 | [10 empty] | Hot Shot Sprinter Van |  |  |  | Clean and Brake Fab | 2026-04-16 |  | 1 (In Progress) |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Gabriela Herrera - Yes, I'll do it after lunch. | 1010 |  | Laura Forero | Gabriela Herrera |  | 25031-RO01 In-House |  | 2026, Week 17
311 | 25031-FL08 |  | LLU Mars US Warehouse | 145 Liebherr Drive Tupelo, MS 38801 | Laura Forero | 615.788.7739 |  |  | The plan is to ship this with 25031RO01 on Thursday of next week | Please see attached the flashing quantities and profile | * Sketch |  | Q:\Jobs\25031 - LLU Mars US Warehouse\04_Production\25031FL08 | N/A | N/A | N/A | 0 | 6 | 1 | 0 | 0 | 2 - SHTS | na | Alpolic, .032" X 48" X 120", Dusty Grey Alum Sheet, No Grain | Alum Sheet | Alpolic, .032" X 48" X 120", Dusty Grey | No |  |  | 7 | 4 | Samantha Krantz, Shane Jones | Denis Usatenko |  |  |  | Denis Usatenko | [8 empty] | Denis Usatenko | 2026-04-15 11:13 | TRUE | 2026-04-23 | 2026-04-15 | TRUE | 2026-04-21 |  | 2026-04-22 |  |  |  |  | YES | 2 | [19 empty] | Shear |  | TRUE | [9 empty] | TRUE | TRUE | [15 empty] | 25031 | FL |  | 08 |  | 8 | 25031-FL08 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 0.25 | 2 | [10 empty] | Sprinter Van |  |  |  | Cidan Shear |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Laura Forero | Denis Usatenko |  | 25031-FL08 In-House |  | 2026, Week 17
312 | 25002-FS16 |  | Med Center Health | 250 Park Street Bowling Green, KY 42101 | Carlos Silva | 980.246.6545 | 600 |  |  | Gray Mica panels needed in different Elevations includes a RM of 2 damaged panels (201-2CA33) and (201-2CA32) Q:\Jobs\25002 - Med Center Health\03_Engineering\02_FD Docs\PHOTOS & SD MICA GRAY FS16 | [5 empty] | 2014 | 00 | [6 empty] | ACM: 4mm X 62" X 196", MICA GRAY FR ACM, Grain | FR ACM | ACM: 4mm X 62" X 196", MICA GRAY | Yes |  |  | 8 | 15 | Denis Usatenko | Denis Usatenko | [13 empty] | 2026-04-15 11:50 | TRUE | 2026-05-06 |  |  |  |  | 2026-05-06 |  |  |  |  | YES | 00 | [5 empty] | FAB SCREW | YES | Approved | NO |  | YES | Q:\Jobs\25002 - Med Center Health\03_Engineering\02_FD Docs\PHOTOS & SD MICA GRAY FS15 | NO | [35 empty] | 25002 | FS |  | 16 |  | 16 | 25002-FS16 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 7 | 20 | [10 empty] | In House | [6 empty] | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Carlos Silva |  |  | 25002-FS16 In-House |  | 2026, Week 19
313 | 25059-RM05 |  | Allen Samuels CDJR and LC | 1623 Hwy 45 Bypass Jackson, TN 38305 | Andre Van Der Merwe | 315.261.0333 | 408 |  |  |  | * SKETCHES * CUT LIST * EXTRUSION TIGER SAW LIST * COLOR LABELS | * ( LF) 1-5/8" Reveals | Q:\Jobs\25059 - Allen Samuels CDJR and LC\04_Production\25059RM05 |  |  | 358 | 1 | 1 | 1 | - | - |  |  | 4mm X 62" X 196", BSX Silver FR ACM, Grain | FR ACM | 4mm X 62" X 196", BSX Silver | Yes |  |  | 5 | 2 | Arnold Jurado, Issiah Havens | Denis Usatenko |  |  |  | Gabriela Herrera |  |  |  | Arnold Jurado, Issiah Havens |  |  |  |  | Gabriela Herrera | 2026-04-15 16:14 | TRUE | 2026-04-17 |  |  |  |  | 2026-04-23 |  |  |  |  | YES | 2 | [5 empty] | SILVER | YES | Approved | NO |  | NO |  | NO |  | 1 x 206-1T131 | FS02 |  | ENGINEERING |  | CNC Programming |  | TRUE | TRUE | [21 empty] | TRUE | TRUE |  |  | 25059 | RM |  | 05 |  | 5 | 25059-RM05 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 4 | [10 empty] | Hot Shot |  |  | AXYZ | AXYZ Clean and Brake Fab | 2026-04-16 |  | 1 (In Progress) |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Gabriela Herrera - Yes, I'll do it after lunch. | 1010 |  | Andre Van Der Merwe | Gabriela Herrera |  | 25059-RM05 In-House |  | 2026, Week 17
314 | 25002-BM07 |  | Med Center Health | 250 Park Street Bowling Green, KY 42101 | Carlos Silva | 980.246.6545 |  |  |  | Zees for columns, Denis, can you help me with the Sketch? I am not sure if the column Details on the shops drawings FS11.1 are updated. so I am not sure of the sizes of the zees will be holding the column panels. | [5 empty] | N/A |  | 24 | [5 empty] | Galvanized Sheet: 20 Ga. X 48" X 120" Galv Sheet, No Grain | Galv Sheet | Galvanized Sheet: 20 Ga. X 48" X 120" | No |  |  | 4 | 6 | Denis Usatenko | Denis Usatenko | [13 empty] | 2026-04-15 16:41 | TRUE | 2026-04-23 |  |  |  |  | 2026-04-29 |  |  |  |  | YES | 00 | [48 empty] | 25002 | BM |  | 07 |  | 7 | 25002-BM07 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 2 | 6 | [10 empty] | In House | [6 empty] | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Carlos Silva |  |  | 25002-BM07 In-House |  | 2026, Week 18
315 | 24079-FL14 |  | Nashville Youth Campus | 1354 Brick Church Pike Nashville, TN 37207 | Joe Hoyle | 828.334.7808 |  |  | Transition flashings for AFC. Courthouse Tower. | Transition flashings for AFC Tower. Reference details 2 and 3/NY-50 from approved as noted fiber drawings located within FDDocs folder. Perforated Transitions x 60 sticks (provide a standard perf pattern for approval. There are no airflow requirements with the fiber at this location) Non-Perf Transitions x 460 Keep stretchout at 6" or under. |  | TBD |  |  |  | N/A |  | 520 | [5 empty] | .032" 'BNT Bone White' Alum Sheet, No Grain | Alum Sheet | .032" 'BNT Bone White' | No |  |  | 4 | 14 | David Hasty | Denis Usatenko | David Hasty | [12 empty] | 2026-04-16 10:35 |  | 2026-05-05 |  |  |  |  | 2026-05-14 |  |  |  |  | NO | 130 | 2026-04-30 | [18 empty] | Evaluation | [28 empty] | 24079 | FL |  | 14 |  | 14 | 24079-FL14 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 2 | 40 | [10 empty] | Customer Pick Up | [6 empty] | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Joe Hoyle |  |  | 24079-FL14 In-House |  | 2026, Week 20
316 | 25036-FL22 |  | TCAT Chattanooga | 4501 Amnicola Highway Chattanooga, TN 37406 | Josh McPherson | 615.939.2359 |  |  | Material will be picked up by Kevin and Starlin for installation on Saturday 4/18/2026 | Material arriving tomorrow 2 sheets of 48x120 Zinc Gray | SKETCH |  | Q:\Jobs\25036 - TCAT Chattanooga\04_Production\25036FL22 |  |  | N/A | 0 | 10 | 1 | 0 | 0 |  |  | 22 Ga. 48x120 Zinc Gray Steel Sheet, No Grain | Steel Sheet | 22 Ga. 48x120 Zinc Gray | No |  |  | 1 | 7 | David Hasty | Denis Usatenko |  |  |  | Frank Dean | David Hasty | Frank Dean | [7 empty] | 2026-04-16 12:34 | TRUE | 2026-04-24 |  |  |  |  | 2026-04-17 |  |  |  |  | NO | 2 | 2026-04-17 | [18 empty] | Sketch Check | [11 empty] | TRUE | TRUE | [15 empty] | 25036 | FL |  | 22 |  | 22 | 25036-FL22 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 10 | [10 empty] | In House |  |  |  | Cidan Shear |  |  | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process | Josh McPherson - 1/2" is fine. Im only getting 6 per sheet the extra tenth wont affect yield. | 1010 |  | Josh McPherson | Frank Dean | David Hasty | 25036-FL22 In-House |  | 2026, Week 16
317 | 24046-RO06 |  | UAB Biomedical Research and Psycholgy | 1500 University Blvd Birmingham, AL 35233 | Wylie McDougall | 615.426.7650 | 400 |  | CUT AND SHIP FLAT NO EXTRUSIONS MUST BE BAD BATCH DATED 9/??/25 | [6 empty] | 3446 | 17 | 18 | [5 empty] | 4mm X 62" X 130", Silver Metallic FR ACM, Grain | FR ACM | 4mm X 62" X 130", Silver Metallic | Yes |  |  | 9 | 16 | Denis Usatenko | Denis Usatenko | [13 empty] | 2026-04-16 13:12 | TRUE | 2026-05-07 |  |  |  |  | 2026-04-20 |  |  |  |  | YES | 20 | [5 empty] | SILVER | YES | Approved | NO |  | YES | Q:\Jobs\24046 - UAB Biomedical Research\03_Engineering\02_FD Docs\24046 RO05 | NO |  | (3)210-2TG09 (1)210-2TG37B (1)210-2TG37A (4)210-2TG38 (4)210-2TG38.1 (1)210-2TG40 (1)210-2TG20 (2)210-2TG42 | FS31 | [32 empty] | 24046 | RO |  | 06 |  | 6 | 24046-RO06 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | 1 | 4 | [10 empty] | Hot Shot | [6 empty] | No Program Requested |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | Issue Still in Process |  | 1010 |  | Wylie McDougall |  |  | 24046-RO06 In-House |  | 2026, Week 17
318 | 25075-RP01 |  | St Thomas West Canopy Replace | 4220 Harding Pike Nashville, TN 37205 | Chris Buttrey | 615.517.9885 |  |  |  | Scratches and parts moved | [6 empty] | 2 | 6 | 0 | 0 | 0 |  |  | 4mm X 62" X 196", DWDMIC DFC/RND FR ACM, Grain | [5 empty] | 2 | 1 | Arnold Jurado, Issiah Havens | Denis Usatenko | [5 empty] | Paul J Roberts |  | Arnold Jurado, Issiah Havens |  |  |  |  | Gabriela Herrera | 2026-04-16 13:15 |  | 2026-04-16 | [25 empty] | 1H10 2-1f06 S-REV X6 | FS01 | HUMAN ERROR |  | jdavis@jwmcd.com | CNC Programming |  |  | TRUE | AXYZ 34 | [20 empty] | TRUE | TRUE |  |  | 25075 |  | RP | 01 | -- | 1 | 25075-RP01 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | [15 empty] | AXYZ | AXYZ 34 Clean and Brake Fab | 2026-04-16 |  | 1 (In Progress) |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | 0 |  | 1010 |  | Chris Buttrey |  |  | 25075-RP01 In-House |  | #INVALID DATA TYPE
319 | 24051-RP58 |  | TN Titans Stadium | 1 Titans Way Nashville, TN 37213 | Marc Ribar | 360.798.3603 |  |  |  | Material had dents | [5 empty] | 19268 | 1 | 0 | 0 | 0 | 0 |  |  | 4mm X 62" X 196", TOB BLACK FR ACM, No Grain | [5 empty] | 2 | 1 | Arnold Jurado, Issiah Havens | Denis Usatenko | [5 empty] | Paul J Roberts |  | Arnold Jurado, Issiah Havens |  |  |  |  | Gabriela Herrera | 2026-04-16 13:18 |  | 2026-04-16 | [25 empty] | W3107-1AA24 | FS36.2 | MATERIAL DEFECT |  | jdavis@jwmcd.com | CNC Programming |  |  | TRUE | AXYZ 34 | [20 empty] | TRUE | TRUE |  |  | 24051 |  | RP | 58 | -- | 58 | 24051-RP58 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | [15 empty] | AXYZ | AXYZ 34 Clean and Brake Fab | 2026-04-16 |  | 1 (In Progress) |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | 0 |  | 1010 |  | Marc Ribar |  |  | 24051-RP58 In-House |  | #INVALID DATA TYPE
320 | 24071-RP15 |  | RS Gass State Lab | 975 RS Gass Blvd Nashville, TN 37216 | Cole Norona | 931.591.9340 |  |  |  | Improper programming led to parts moving during cut | [5 empty] | N/A | 0 | 3 | 0 | 0 | 0 |  |  | 4mm X 62" X 196", BRIGHT METALLIC SILVER FR ACM, Grain | [5 empty] | 2 | 1 | Arnold Jurado, Issiah Havens | Denis Usatenko | [5 empty] | Paul J Roberts |  | Arnold Jurado, Issiah Havens |  |  |  |  | Gabriela Herrera | 2026-04-16 13:21 |  | 2026-04-16 | [25 empty] | 318-1NA03B (X3) | FS11 | PROGRAMMING |  | jdavis@jwmcd.com | CNC Programming |  |  | TRUE | AXYZ 34 | [20 empty] | TRUE | TRUE |  |  | 24071 |  | RP | 15 | -- | 15 | 24071-RP15 |  |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold |  |  |  | No Hold | No Hold | [15 empty] | AXYZ | AXYZ 34 Clean and Brake Fab | 2026-04-16 |  | 1 (In Progress) |  | Issue Still In Process |  | Issue Still In Process | David Hasty | Ramon Estrada, Shane Watson |  |  | 0 |  | 1010 |  | Cole Norona |  |  | 24071-RP15 In-House |  | #INVALID DATA TYPE

## Pre-Release
SEARCH JOB ID:
PRE-RELEASE SCHEDULE — Jobs Not Yet Released to Shop
Jobs currently in: LO, LO Check, Sketch, Sketch Check, Evaluation, Float, Correction, CNC Programming, Program Complete, Release to Shop
ID | Job Name | PM | Panel Qty | Part Qty | Material Type | Ship Target | Current Station | Op 1 | Op 2 | Op 3 | Notes
25075-RP01 | St Thomas West Canopy Replace | Chris Buttrey | 2 | 6 | 0 | 0 | CNC Programming | AXYZ 34 | Clean and Brake | Fab | 04/16/2026…
24051-RP58 | TN Titans Stadium | Marc Ribar | 1 | 0 | 0 | 0 | CNC Programming | AXYZ 34 | Clean and Brake | Fab | 04/16/2026…
24071-RP15 | RS Gass State Lab | Cole Norona | 0 | 3 | 0 | 0 | CNC Programming | AXYZ 34 | Clean and Brake | Fab | 04/16/2026…
24079-FS03 | Nashville Youth Campus | Joe Hoyle | 33 | 0 | LAYOUT ONLY | 2026-03-16 | Evaluation |  |  |  | 04/16/2026…Evaluation
24079-FS102 | Nashville Youth Campus | Joe Hoyle | 192 | 198 | FR ACM | 2026-03-16 | Sketch Check | AXYZ Titans Line | Clean and Brake | Fab | 04/16/2026…Sketch Check
24051-FS225 | TN Titans Stadium | Marc Ribar | 26 | 0 | FR ACM | 2026-03-16 | LO |  |  |  | 03/23...Next for Titans--1 of 3 still late*03/24 Lay Out*03/26…LO*03/30…LO*03/31…LO*04/02…LO*04/09…LO*04/16/2026…LO
24079-FS102.1 | Nashville Youth Campus | Joe Hoyle | 308 | 0 | FR ACM | 2026-03-16 | Sketch | AXYZ Titans Line | Clean and Brake | Fab | 04/16/2026…Sketch
25035-FS04 | Titans Jabez | Marc Ribar | 218 | 0 | FR ACM | 2026-03-23 | Sketch | AXYZ Titans Line | Clean and Brake | Fab | 04/16/2026…Sketch
24079-FS04 | Nashville Youth Campus | Joe Hoyle | 173 | 0 | LAYOUT ONLY | 2026-03-30 | Evaluation |  |  |  | 04/16/2026…Evaluation
25010-RO06 | TOA Spring Hill MOB | Cole Norona | 6 | 0 | FR ACM | 2026-04-15 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25010-RO07 | TOA Spring Hill MOB | Cole Norona | 3 | 0 | FR ACM | 2026-04-15 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25029-ST73 | Lourdes CC Phase 2 | Dillon Bowman | 0 | 6 | Steel Custom Shape | 2026-04-15 | Sketch |  |  |  | 04/16/2026…Sketch
25002-FS13 | Med Center Health | Carlos Silva | 30 | 0 | FR ACM | 2026-04-17 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25036-FL22 | TCAT Chattanooga | Josh McPherson | 0 | 10 | Steel Sheet | 2026-04-17 | Sketch Check | Cidan | Shear |  | 04/16/2026…MUST RUN FRIDAY AND FINISH BY EOS. REFER TO EMAIL.
24074-FS07 | DIDD ACM | Dillon Bowman | 155 | 218 | FR ACM | 2026-04-20 | CNC Programming | AXYZ Titans Line | Clean and Brake | Fab | *03/30...4' Panals Rolled*04/02…Sketch*04/09…CNC*04/16/2026…CNC Programming
26009-FS01 | 5th & Summer Leasing Office | Cole Norona | 9 | 0 | FR ACM | 2026-04-20 | LO Check | AXYZ | Clean and Brake | Fab | 04/16/2026…LO Check
25031-RO01 | LLU Mars US Warehouse | Laura Forero | 3 | 3 | FR ACM | 2026-04-22 | CNC Programming | Clean and Brake | Fab |  | 04/16/2026…CNC Programming
25059-RM05 | Allen Samuels CDJR and LC | Andre Van Der Merwe | 1 | 1 | FR ACM | 2026-04-23 | CNC Programming | AXYZ | Clean and Brake | Fab | 04/16/2026…CNC Programming
25030-FS01 | 510 W Tremont | Laura Forero | 88 | 0 | FR ACM | 2026-04-24 | Correction | AXYZ | Clean and Brake | Fab | 04/16/2026…Correction
25030-FS02 | 510 W Tremont | Laura Forero | 84 | 0 | FR ACM | 2026-04-24 | Sketch | AXYZ | Clean and Brake | Fab | 04/16/2026…Sketch
24051-FS90 | TN Titans Stadium | Marc Ribar | 117 | 0 | FR ACM | 2026-04-24 | Float | AXYZ | Clean and Brake | Fab | 04/16/2026…Float
24051-FS91 | TN Titans Stadium | Marc Ribar | 36 | 0 | FR ACM | 2026-04-24 | Float | AXYZ | Clean and Brake | Fab | 04/16/2026…Float
24051-FS227 | TN Titans Stadium | Marc Ribar | 119 | 0 | FR ACM | 2026-04-24 | Float | AXYZ | Clean and Brake | Fab | 04/16/2026…Float
24051-FL01 | TN Titans Stadium | Marc Ribar | 0 | 25 | Alum Sheet | 2026-04-24 | Release to Shop | 7000 TruMatic | Brake |  | 04/16/2026…Release to Shop
24079-RM01 | Nashville Youth Campus | Joe Hoyle | 37 | 39 | FR ACM | 2026-04-24 | Sketch | AXYZ | Clean and Brake | Fab | 04/16/2026…Sketch
24051-FS93 | TN Titans Stadium | Marc Ribar | 131 | 133 | FR ACM | 2026-04-28 | Correction | AXYZ | Clean and Brake | Fab | 04/14...Next Titans Requesting//Scheduled to be released to the shop 04/20.*04/16/2026…Correction
24051-FS94 | TN Titans Stadium | Marc Ribar | 79 | 0 | FR ACM | 2026-04-28 | Float | AXYZ | Clean and Brake | Fab | 04/16/2026…Float
24051-FS95 | TN Titans Stadium | Marc Ribar | 96 | 0 | FR ACM | 2026-04-28 | Float | AXYZ | Clean and Brake | Fab | 04/16/2026…Float
24051-FS228 | TN Titans Stadium | Marc Ribar | 95 | 0 | FR ACM | 2026-04-28 | Float | AXYZ | Clean and Brake | Fab | 04/16/2026…Float
24051-FS92 | TN Titans Stadium | Marc Ribar | 104 | 0 | FR ACM | 2026-05-01 | Float | AXYZ | Clean and Brake | Fab | 04/16/2026…Float
24051-FS96 | TN Titans Stadium | Marc Ribar | 52 | 0 | FR ACM | 2026-05-01 | Float | AXYZ | Clean and Brake | Fab | 04/16/2026…Float
24051-FS229 | TN Titans Stadium | Marc Ribar | 109 | 0 | FR ACM | 2026-05-01 | Float | AXYZ | Clean and Brake | Fab | 04/16/2026…Float
24051-FS230 | TN Titans Stadium | Marc Ribar | 67 | 0 | FR ACM | 2026-05-01 | Float | AXYZ | Clean and Brake | Fab | 04/16/2026…Float
24051-FS231 | TN Titans Stadium | Marc Ribar | 1 | 0 | FR ACM | 2026-05-04 | Float | AXYZ | Clean and Brake | Fab | 04/16/2026…Float
25002-FS14 | Med Center Health | Carlos Silva | 00 | 0 | FR ACM | 2026-05-04 | Evaluation | AXYZ | Clean and Brake | Fab | 04/16/2026…Evaluation
25006-FS03 | MALETA Housing and Dining | Cole Norona | 216 | 0 | FR ACM | 2026-05-05 | Correction | AXYZ | Clean and Brake | Fab | Not expected out of engineering before 04/15…Needs to ship 05/12*HOAR*04/16/2026…Correction
24074-FS08 | DIDD ACM | Dillon Bowman | 186 | 0 | FR ACM | 2026-05-07 | LO Check | AXYZ | Clean and Brake | Fab | 04/16/2026…LO Check
25006-FS05 | MALETA Housing and Dining | Cole Norona | 18 | 0 | FR ACM | 2026-05-11 | LO Check | AXYZ | Clean and Brake | Fab | Not expected out of engineering before 04/17…Needs to ship 05/12*HOAR*04/16/2026…LO Check
24079-FS103 | Nashville Youth Campus | Joe Hoyle | 111 | 0 | FR ACM | 2026-05-11 | LO Check | AXYZ | Clean and Brake | Fab | 04/16/2026…LO Check
25010-FS09 | TOA Spring Hill MOB | Cole Norona | 111 | 0 | FR ACM | 2026-05-11 | Correction | AXYZ | Clean and Brake | Fab | 04/16/2026…Correction
25029-FS50 | Lourdes CC Phase 2 | Dillon Bowman | 8 | 4 | Alum Sheet | 2026-05-11 | Correction | Brake | Punch |  | 04/16/2026…Correction
25002-FS15 | Med Center Health | Carlos Silva | 12 | 0 | FR ACM | 2026-05-11 | Evaluation | AXYZ | Clean and Brake | Fab | 04/16/2026…Evaluation
24074-FS09 | DIDD ACM | Dillon Bowman | 120 | 0 | FR ACM | 2026-05-14 | LO Check | AXYZ | Clean and Brake | Fab | 04/16/2026…LO Check
24079-FL14 | Nashville Youth Campus | Joe Hoyle | 0 | 520 | Alum Sheet | 2026-05-14 | Evaluation |  |  |  | 04/16/2026…
25006-FS04 | MALETA Housing and Dining | Cole Norona | 232 | 0 | FR ACM | 2026-05-15 | LO Check | AXYZ | Clean and Brake | Fab | HOAR*04/16/2026…LO Check
25029-ST52 | Lourdes CC Phase 2 | Dillon Bowman | 0 | 10 | Alum Sheet | 2026-05-15 | Correction | Flat Laser | Powder Coat |  | 04/16/2026…Correction
25029-ST70 | Lourdes CC Phase 2 | Dillon Bowman | 0 | 6 | Steel Sheet | 2026-05-15 | Sketch Check | Flat Laser |  |  | 04/16/2026…Sketch Check
25029-ST71 | Lourdes CC Phase 2 | Dillon Bowman | 0 | 1 | Steel Tube | 2026-05-15 | Sketch | Tube Laser |  |  | 04/16/2026…Sketch
25029-ST72 | Lourdes CC Phase 2 | Dillon Bowman | 0 | 1 | Steel Sheet | 2026-05-15 | Sketch Check | Flat Laser |  |  | 04/16/2026…Sketch Check
25029-ST51 | Lourdes CC Phase 2 | Dillon Bowman | 0 | 10 | Alum Tube | 2026-05-18 | Correction | Powder Coat |  |  | 04/16/2026…Correction
24079-FS201 | Nashville Youth Campus | Joe Hoyle | 41 | 0 | FR ACM | 2026-05-18 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
24079-FS302 | Nashville Youth Campus | Joe Hoyle | 188 | 0 | FR ACM | 2026-05-18 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25008-FS07 | Columbia State Tech Center | Laura Forero | 58 | 0 | FR ACM | 2026-05-20 | Evaluation | AXYZ | Clean and Brake | Fab | 04/16/2026…Evaluation
24074-FS10 | DIDD ACM | Dillon Bowman | 130 | 0 | FR ACM | 2026-05-21 | LO Check | AXYZ | Clean and Brake | Fab | 04/16/2026…LO Check
24073-FS01 | DIDD Perf | Dillon Bowman | 53 | 0 | Alum Sheet | 2026-05-22 | Sketch | Brake | Post Paint | Punch | 04/16/2026…Sketch
25044-FS01 | MALETA Firing Range | Cole Norona | 125 | 0 | FR ACM | 2026-05-22 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25044-FS01.1 | MALETA Firing Range | Cole Norona | 34 | 0 | FR ACM | 2026-05-22 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25065-MU01 | Crosswinds Casino Resort | Matt Rassmussen | 18 | 14 | FR ACM | 2026-05-22 | Sketch Check | AXYZ | Clean and Brake | Fab | 04/16/2026…Sketch Check
25006-FS06 | MALETA Housing and Dining | Cole Norona | 246 | 0 | FR ACM | 2026-05-25 | LO Check | AXYZ | Clean and Brake | Fab | HOAR*04/16/2026…LO Check
25037-FS01 | Chestnut Street Office | Laura Forero | 218 | 0 | FR ACM | 2026-05-25 | LO Check | AXYZ | Clean and Brake | Fab | 04/16/2026…LO Check
24079-FS301 | Nashville Youth Campus | Joe Hoyle | 143 | 0 | FR ACM | 2026-05-25 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
24079-FS303 | Nashville Youth Campus | Joe Hoyle | 165 | 0 | FR ACM | 2026-05-25 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25041-FS02 | Wedgewood Bldg E | Wylie McDougall | 31 | 0 | FR ACM | 2026-05-26 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25065-MU02 | Crosswinds Casino Resort | Matt Rassmussen | 15 | 13 | FR ACM | 2026-05-29 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25065-MU03 | Crosswinds Casino Resort | Matt Rassmussen | 6 | 6 | FR ACM | 2026-05-29 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25065-MU04 | Crosswinds Casino Resort | Matt Rassmussen | 15 | 13 | FR ACM | 2026-05-29 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25065-MU05 | Crosswinds Casino Resort | Matt Rassmussen | 3 | 1 | Steel Sheet | 2026-05-29 | Evaluation | Cidan | Shear |  | 04/16/2026…Evaluation
25065-MU11 | Crosswinds Casino Resort | Matt Rassmussen | 1 | 1 | Alum Sheet | 2026-05-29 | Evaluation | Cidan | Shear |  | 04/16/2026…Evaluation
25065-MU12 | Crosswinds Casino Resort | Matt Rassmussen | 0 | 2 | Alum Sheet | 2026-05-29 | Evaluation | Cidan | Shear |  | 04/16/2026…Evaluation
25065-MU13 | Crosswinds Casino Resort | Matt Rassmussen | 0 | 1 | Alum Sheet | 2026-05-29 | Evaluation | Cidan | Shear |  | 04/16/2026…Evaluation
25065-MU14 | Crosswinds Casino Resort | Matt Rassmussen | 0 | 3 | Alum Sheet | 2026-05-29 | Evaluation | Cidan | Shear |  | 04/16/2026…Evaluation
25065-MU15 | Crosswinds Casino Resort | Matt Rassmussen | 0 | 6 | Steel Sheet | 2026-05-29 | Evaluation | Cidan | Shear |  | 04/16/2026…Evaluation
25065-MU20 | Crosswinds Casino Resort | Matt Rassmussen | 0 | 3 | Steel Sheet | 2026-05-29 | Evaluation | Cidan | Shear |  | 04/16/2026…Evaluation
25044-FS02 | MALETA Firing Range | Cole Norona | 135 | 0 | FR ACM | 2026-05-31 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25006-FS07 | MALETA Housing and Dining | Cole Norona | 190 | 0 | FR ACM | 2026-06-03 | LO Check | AXYZ | Clean and Brake | Fab | HOAR*04/16/2026…LO Check
25037-FS02 | Chestnut Street Office | Laura Forero | 204 | 0 | FR ACM | 2026-06-08 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25044-FS03 | MALETA Firing Range | Cole Norona | 150 | 0 | FR ACM | 2026-06-10 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25006-FS08 | MALETA Housing and Dining | Cole Norona | 83 | 0 | FR ACM | 2026-06-12 | LO Check | AXYZ | Clean and Brake | Fab | HOAR*04/16/2026…LO Check
25044-FS04 | MALETA Firing Range | Cole Norona | 113 | 0 | FR ACM | 2026-06-19 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25006-FS09 | MALETA Housing and Dining | Cole Norona | 152 | 0 | FR ACM | 2026-06-19 | LO | AXYZ | Clean and Brake | Fab | HOAR*04/16/2026…LO
25044-FS05 | MALETA Firing Range | Cole Norona | 111 | 0 | FR ACM | 2026-06-26 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25006-FS10 | MALETA Housing and Dining | Cole Norona | 140 | 0 | FR ACM | 2026-07-02 | LO | AXYZ | Fab |  | HOAR*04/16/2026…LO
25044-FS06 | MALETA Firing Range | Cole Norona | 203 | 0 | FR ACM | 2026-07-06 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25044-FS07 | MALETA Firing Range | Cole Norona | 160 | 0 | FR ACM | 2026-07-15 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25006-FS11 | MALETA Housing and Dining | Cole Norona | 201 | 0 | FR ACM | 2026-07-15 | LO | AXYZ | Clean and Brake | Fab | HOAR*04/16/2026…LO
25044-FS08 | MALETA Firing Range | Cole Norona | 163 | 0 | FR ACM | 2026-07-22 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25006-FS12 | MALETA Housing and Dining | Cole Norona | 192 | 0 | FR ACM | 2026-07-27 | LO | AXYZ | Clean and Brake | Fab | HOAR*04/16/2026…LO
25044-FS09 | MALETA Firing Range | Cole Norona | 86 | 0 | FR ACM | 2026-07-29 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25044-FS01.2 | MALETA Firing Range | Cole Norona | 193 | 0 | FR ACM | 2026-07-29 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25006-FS13 | MALETA Housing and Dining | Cole Norona | 28 | 0 | FR ACM | 2026-08-03 | LO | AXYZ | Clean and Brake | Fab | HOAR*04/16/2026…LO
25044-FS10 | MALETA Firing Range | Cole Norona | 185 | 0 | FR ACM | 2026-08-07 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
25044-FS11 | MALETA Firing Range | Cole Norona | 185 | 0 | FR ACM | 2026-08-17 | LO | AXYZ | Clean and Brake | Fab | 04/16/2026…LO
Formulas:
Ship Target = IF([ID]="","",IFERROR(VLOOKUP([ID],'Job Operations'!$A4:AA304,9,FALSE),""))

## AXYZ Titans CNC Schedule
| 24030 FL03 | SEARCH JOB ID: | 24030 FL03 | ❌ NOT FOUND
AXYZ TITANS LINE SCHEDULE — Jobs At or Coming to AXYZ Titans Line
Includes jobs currently at AXYZ Titans Line station AND jobs with AXYZ Titans Line as an operation. Sorted by Start By date.
ID | Job Name | PM | Panel Qty | Part Qty | Material Type | Ship Target | Queue Position | Hrs to Complete CNC | CNC Start By | Next Op | Following Op | Notes
24079-FS102.1 | Nashville Youth Campus | Joe Hoyle | 308 | 0 | FR ACM | 2026-03-16 | Sketch | 44 | 2026-03-03 | Clean and Brake | Fab | 04/16/2026…Sketch
24079-FS102 | Nashville Youth Campus | Joe Hoyle | 192 | 198 | FR ACM | 2026-03-16 | Sketch Check | 27.4286 | 2026-03-05 | Clean and Brake | Fab | 04/16/2026…Sketch Check
25035-FS04 | Titans Jabez | Marc Ribar | 218 | 0 | FR ACM | 2026-03-23 | Sketch | 31.1429 | 2026-03-12 | Clean and Brake | Fab | 04/16/2026…Sketch
24074-FS07 | DIDD ACM | Dillon Bowman | 155 | 218 | FR ACM | 2026-04-20 | CNC Programming | 22.1429 | 2026-04-10 | Clean and Brake | Fab | *03/30...4' Panals Rolled*04/02…Sketch*04/09…CNC*04/16/2026…CNC Programming
24051-FS89 | TN Titans Stadium | Marc Ribar | 40 | 40 | FR ACM | 2026-04-15 | 1st | 5.7143 | 2026-04-08 | Clean and Brake | Fab | 04/14...Next Titans Requesting//Scheduled to be released to the shop 04/16.*04/16/2026…AXYZ 34
25022-RM01 | Vantage VA15 | Thomas Mooers | 4 | 4 | FR ACM | 2026-04-23 | 2nd | 0.57143 | 2026-04-16 | Clean and Brake | Fab | 04/16/2026…AXYZ 34
25022-RM02 | Vantage VA15 | Thomas Mooers | 1 | 1 | FR ACM | 2026-04-23 | 3rd | 0.14286 | 2026-04-16 | Clean and Brake | Fab | 04/16/2026…AXYZ 34
24026-FS01 | 1740 Division | Chris Buttrey | 23 | 23 | FR ACM | 2026-04-27 | 4th | 3.2857 | 2026-04-20 | Clean and Brake | Fab | 04/15...Date adjusted to 04/27.*04/16/2026…AXYZ 34
25022-RO03 | Vantage VA15 | Thomas Mooers | 3 | 3 | FR ACM | 2026-04-27 | 5th | 0.42857 | 2026-04-20 | Clean and Brake | Fab | 04/16/2026…AXYZ 34
25067-FS02 | Harison Bend | Andre Van Der Merwe | 29 | 29 | FR ACM | 2026-04-30 | 6th | 4.1429 | 2026-04-23 | Clean and Brake | Fab | 04/15…CNC...Confirmed Shipdate of 04/22 with PM.*04/16/2026…AXYZ 34
25012-FS02 | St Jude Hospital | Wylie McDougall | 60 | 60 | FR ACM | 2026-06-12 | 7th | 8.5714 | 2026-06-04 | Clean and Brake | Fab | 04/16/2026…AXYZ 34
Formulas:
Ship Target = IF([ID]="","",IFERROR(VLOOKUP([ID],'Job Operations'!$A4:AA304,9,FALSE),""))
CNC Start By = IF(OR([ID]="",[Ship Target]=""),"",WORKDAY.INTL([Ship Target],-(5+CEILING([Hrs to Complete CNC]/8,1)),"0000001"))

## AXYZ CNC Schedule
|  | SEARCH JOB ID: | 25067-FS02 | 🟢 ON TIME | Harison Bend | Ship: 04/30/2026
AXYZ SCHEDULE — Jobs At or Coming to AXYZ
Includes jobs currently at AXYZ 34 station AND jobs with AXYZ as an operation. Sorted by Start By date.
ID | Job Name | PM | Panel Qty | Part Qty | Material Type | Ship Target | Queue Position | Hrs to Complete CNC | CNC Start By | Next Op | Following Op | Notes
25010-RO06 | TOA Spring Hill MOB | Cole Norona | 6 | 0 | FR ACM | 2026-04-15 | LO | 0.85714 | 2026-04-08 | Clean and Brake | Fab | 04/16/2026…LO
25010-RO07 | TOA Spring Hill MOB | Cole Norona | 3 | 0 | FR ACM | 2026-04-15 | LO | 0.42857 | 2026-04-08 | Clean and Brake | Fab | 04/16/2026…LO
25002-FS13 | Med Center Health | Carlos Silva | 30 | 0 | FR ACM | 2026-04-17 | LO | 4.2857 | 2026-04-10 | Clean and Brake | Fab | 04/16/2026…LO
26009-FS01 | 5th & Summer Leasing Office | Cole Norona | 9 | 0 | FR ACM | 2026-04-20 | LO Check | 1.2857 | 2026-04-13 | Clean and Brake | Fab | 04/16/2026…LO Check
24051-FS90 | TN Titans Stadium | Marc Ribar | 117 | 0 | FR ACM | 2026-04-24 | Float | 16.7143 | 2026-04-15 | Clean and Brake | Fab | 04/16/2026…Float
24051-FS227 | TN Titans Stadium | Marc Ribar | 119 | 0 | FR ACM | 2026-04-24 | Float | 17 | 2026-04-15 | Clean and Brake | Fab | 04/16/2026…Float
25022-RM01 | Vantage VA15 | Thomas Mooers | 4 | 4 | FR ACM | 2026-04-23 | 1st | 0.57143 | 2026-04-16 | Clean and Brake | Fab | 04/16/2026…AXYZ 34
25022-RM02 | Vantage VA15 | Thomas Mooers | 1 | 1 | FR ACM | 2026-04-23 | 2nd | 0.14286 | 2026-03-30 | Clean and Brake | Fab | 04/16/2026…AXYZ 34
25059-RM05 | Allen Samuels CDJR and LC | Andre Van Der Merwe | 1 | 1 | FR ACM | 2026-04-23 | CNC Programming | 0.14286 | 2026-03-30 | Clean and Brake | Fab | 04/16/2026…CNC Programming
25030-FS01 | 510 W Tremont | Laura Forero | 88 | 0 | FR ACM | 2026-04-24 | Correction | 12.5714 | 2026-03-30 | Clean and Brake | Fab | 04/16/2026…Correction
25030-FS02 | 510 W Tremont | Laura Forero | 84 | 0 | FR ACM | 2026-04-24 | Sketch | 12 | 2026-04-16 | Clean and Brake | Fab | 04/16/2026…Sketch
24051-FS91 | TN Titans Stadium | Marc Ribar | 36 | 0 | FR ACM | 2026-04-24 | Float | 5.1429 | 2026-04-17 | Clean and Brake | Fab | 04/16/2026…Float
24079-RM01 | Nashville Youth Campus | Joe Hoyle | 37 | 39 | FR ACM | 2026-04-24 | Sketch | 5.2857 | 2026-04-17 | Clean and Brake | Fab | 04/16/2026…Sketch
24051-FS93 | TN Titans Stadium | Marc Ribar | 131 | 133 | FR ACM | 2026-04-28 | Correction | 18.7143 | 2026-04-18 | Clean and Brake | Fab | 04/14...Next Titans Requesting//Scheduled to be released to the shop 04/20.*04/16/2026…Correction
25022-RO03 | Vantage VA15 | Thomas Mooers | 3 | 3 | FR ACM | 2026-04-27 | 3rd | 0.42857 | 2026-04-20 | Clean and Brake | Fab | 04/16/2026…AXYZ 34
24051-FS94 | TN Titans Stadium | Marc Ribar | 79 | 0 | FR ACM | 2026-04-28 | Float | 11.2857 | 2026-04-20 | Clean and Brake | Fab | 04/16/2026…Float
24051-FS95 | TN Titans Stadium | Marc Ribar | 96 | 0 | FR ACM | 2026-04-28 | Float | 13.7143 | 2026-04-20 | Clean and Brake | Fab | 04/16/2026…Float
24051-FS228 | TN Titans Stadium | Marc Ribar | 95 | 0 | FR ACM | 2026-04-28 | Float | 13.5714 | 2026-04-20 | Clean and Brake | Fab | 04/16/2026…Float
24051-FS92 | TN Titans Stadium | Marc Ribar | 104 | 0 | FR ACM | 2026-05-01 | Float | 14.8571 | 2026-04-23 | Clean and Brake | Fab | 04/16/2026…Float
24051-FS229 | TN Titans Stadium | Marc Ribar | 109 | 0 | FR ACM | 2026-05-01 | Float | 15.5714 | 2026-04-23 | Clean and Brake | Fab | 04/16/2026…Float
24051-FS230 | TN Titans Stadium | Marc Ribar | 67 | 0 | FR ACM | 2026-05-01 | Float | 9.5714 | 2026-04-23 | Clean and Brake | Fab | 04/16/2026…Float
24051-FS96 | TN Titans Stadium | Marc Ribar | 52 | 0 | FR ACM | 2026-05-01 | Float | 7.4286 | 2026-04-24 | Clean and Brake | Fab | 04/16/2026…Float
25006-FS03 | MALETA Housing and Dining | Cole Norona | 216 | 0 | FR ACM | 2026-05-05 | Correction | 30.8571 | 2026-04-24 | Clean and Brake | Fab | Not expected out of engineering before 04/15…Needs to ship 05/12*HOAR*04/16/2026…Correction
24051-FS231 | TN Titans Stadium | Marc Ribar | 1 | 0 | FR ACM | 2026-05-04 | Float | 0.14286 | 2026-04-27 | Clean and Brake | Fab | 04/16/2026…Float
24074-FS08 | DIDD ACM | Dillon Bowman | 186 | 0 | FR ACM | 2026-05-07 | LO Check | 26.5714 | 2026-04-27 | Clean and Brake | Fab | 04/16/2026…LO Check
25002-FS14 | Med Center Health | Carlos Silva | 00 | 0 | FR ACM | 2026-05-04 | Evaluation | 0 | 2026-04-28 | Clean and Brake | Fab | 04/16/2026…Evaluation
24079-FS103 | Nashville Youth Campus | Joe Hoyle | 111 | 0 | FR ACM | 2026-05-11 | LO Check | 15.8571 | 2026-05-02 | Clean and Brake | Fab | 04/16/2026…LO Check
25010-FS09 | TOA Spring Hill MOB | Cole Norona | 111 | 0 | FR ACM | 2026-05-11 | Correction | 15.8571 | 2026-05-02 | Clean and Brake | Fab | 04/16/2026…Correction
25006-FS05 | MALETA Housing and Dining | Cole Norona | 18 | 0 | FR ACM | 2026-05-11 | LO Check | 2.5714 | 2026-05-04 | Clean and Brake | Fab | Not expected out of engineering before 04/17…Needs to ship 05/12*HOAR*04/16/2026…LO Check
25002-FS15 | Med Center Health | Carlos Silva | 12 | 0 | FR ACM | 2026-05-11 | Evaluation | 1.7143 | 2026-05-04 | Clean and Brake | Fab | 04/16/2026…Evaluation
25006-FS04 | MALETA Housing and Dining | Cole Norona | 232 | 0 | FR ACM | 2026-05-15 | LO Check | 33.1429 | 2026-05-04 | Clean and Brake | Fab | HOAR*04/16/2026…LO Check
24074-FS09 | DIDD ACM | Dillon Bowman | 120 | 0 | FR ACM | 2026-05-14 | LO Check | 17.1429 | 2026-05-05 | Clean and Brake | Fab | 04/16/2026…LO Check
24079-FS302 | Nashville Youth Campus | Joe Hoyle | 188 | 0 | FR ACM | 2026-05-18 | LO | 26.8571 | 2026-05-07 | Clean and Brake | Fab | 04/16/2026…LO
25041-FS02 | Wedgewood Bldg E | Wylie McDougall | 31 | 0 | FR ACM | 2026-05-26 | LO | 4.4286 | 2026-05-19 | Clean and Brake | Fab | 04/16/2026…LO
24079-FS201 | Nashville Youth Campus | Joe Hoyle | 41 | 0 | FR ACM | 2026-05-18 | LO | 5.8571 | 2026-05-11 | Clean and Brake | Fab | 04/16/2026…LO
25008-FS07 | Columbia State Tech Center | Laura Forero | 58 | 0 | FR ACM | 2026-05-20 | Evaluation | 8.2857 | 2026-05-12 | Clean and Brake | Fab | 04/16/2026…Evaluation
24074-FS10 | DIDD ACM | Dillon Bowman | 130 | 0 | FR ACM | 2026-05-21 | LO Check | 18.5714 | 2026-05-12 | Clean and Brake | Fab | 04/16/2026…LO Check
25044-FS01 | MALETA Firing Range | Cole Norona | 125 | 0 | FR ACM | 2026-05-22 | LO | 17.8571 | 2026-05-13 | Clean and Brake | Fab | 04/16/2026…LO
25006-FS06 | MALETA Housing and Dining | Cole Norona | 246 | 0 | FR ACM | 2026-05-25 | LO Check | 35.1429 | 2026-05-13 | Clean and Brake | Fab | HOAR*04/16/2026…LO Check
25037-FS01 | Chestnut Street Office | Laura Forero | 218 | 0 | FR ACM | 2026-05-25 | LO Check | 31.1429 | 2026-05-14 | Clean and Brake | Fab | 04/16/2026…LO Check
25044-FS01.1 | MALETA Firing Range | Cole Norona | 34 | 0 | FR ACM | 2026-05-22 | LO | 4.8571 | 2026-05-15 | Clean and Brake | Fab | 04/16/2026…LO
25065-MU01 | Crosswinds Casino Resort | Matt Rassmussen | 18 | 14 | FR ACM | 2026-05-22 | Sketch Check | 2.5714 | 2026-05-15 | Clean and Brake | Fab | 04/16/2026…Sketch Check
24079-FS301 | Nashville Youth Campus | Joe Hoyle | 143 | 0 | FR ACM | 2026-05-25 | LO | 20.4286 | 2026-05-15 | Clean and Brake | Fab | 04/16/2026…LO
24079-FS303 | Nashville Youth Campus | Joe Hoyle | 165 | 0 | FR ACM | 2026-05-25 | LO | 23.5714 | 2026-05-15 | Clean and Brake | Fab | 04/16/2026…LO
25065-MU02 | Crosswinds Casino Resort | Matt Rassmussen | 15 | 13 | FR ACM | 2026-05-29 | LO | 2.1429 | 2026-05-22 | Clean and Brake | Fab | 04/16/2026…LO
25065-MU03 | Crosswinds Casino Resort | Matt Rassmussen | 6 | 6 | FR ACM | 2026-05-29 | LO | 0.85714 | 2026-05-22 | Clean and Brake | Fab | 04/16/2026…LO
25065-MU04 | Crosswinds Casino Resort | Matt Rassmussen | 15 | 13 | FR ACM | 2026-05-29 | LO | 2.1429 | 2026-05-22 | Clean and Brake | Fab | 04/16/2026…LO
25044-FS02 | MALETA Firing Range | Cole Norona | 135 | 0 | FR ACM | 2026-05-31 | LO | 19.2857 | 2026-05-22 | Clean and Brake | Fab | 04/16/2026…LO
25006-FS07 | MALETA Housing and Dining | Cole Norona | 190 | 0 | FR ACM | 2026-06-03 | LO Check | 27.1429 | 2026-05-23 | Clean and Brake | Fab | HOAR*04/16/2026…LO Check
25037-FS02 | Chestnut Street Office | Laura Forero | 204 | 0 | FR ACM | 2026-06-08 | LO | 29.1429 | 2026-05-28 | Clean and Brake | Fab | 04/16/2026…LO
25044-FS03 | MALETA Firing Range | Cole Norona | 150 | 0 | FR ACM | 2026-06-10 | LO | 21.4286 | 2026-06-01 | Clean and Brake | Fab | 04/16/2026…LO
25006-FS08 | MALETA Housing and Dining | Cole Norona | 83 | 0 | FR ACM | 2026-06-12 | LO Check | 11.8571 | 2026-06-04 | Clean and Brake | Fab | HOAR*04/16/2026…LO Check
25044-FS04 | MALETA Firing Range | Cole Norona | 113 | 0 | FR ACM | 2026-06-19 | LO | 16.1429 | 2026-06-10 | Clean and Brake | Fab | 04/16/2026…LO
25006-FS09 | MALETA Housing and Dining | Cole Norona | 152 | 0 | FR ACM | 2026-06-19 | LO | 21.7143 | 2026-06-10 | Clean and Brake | Fab | HOAR*04/16/2026…LO
25044-FS05 | MALETA Firing Range | Cole Norona | 111 | 0 | FR ACM | 2026-06-26 | LO | 15.8571 | 2026-06-18 | Clean and Brake | Fab | 04/16/2026…LO
25044-FS06 | MALETA Firing Range | Cole Norona | 203 | 0 | FR ACM | 2026-07-06 | LO | 29 | 2026-06-25 | Clean and Brake | Fab | 04/16/2026…LO
25006-FS10 | MALETA Housing and Dining | Cole Norona | 140 | 0 | FR ACM | 2026-07-02 | LO | 20 | 2026-06-23 | Fab |  | HOAR*04/16/2026…LO
25006-FS11 | MALETA Housing and Dining | Cole Norona | 201 | 0 | FR ACM | 2026-07-15 | LO | 28.7143 | 2026-07-04 | Clean and Brake | Fab | HOAR*04/16/2026…LO
25044-FS07 | MALETA Firing Range | Cole Norona | 160 | 0 | FR ACM | 2026-07-15 | LO | 22.8571 | 2026-07-06 | Clean and Brake | Fab | 04/16/2026…LO
25044-FS08 | MALETA Firing Range | Cole Norona | 163 | 0 | FR ACM | 2026-07-22 | LO | 23.2857 | 2026-07-13 | Clean and Brake | Fab | 04/16/2026…LO
25006-FS12 | MALETA Housing and Dining | Cole Norona | 192 | 0 | FR ACM | 2026-07-27 | LO | 27.4286 | 2026-07-16 | Clean and Brake | Fab | HOAR*04/16/2026…LO
25044-FS01.2 | MALETA Firing Range | Cole Norona | 193 | 0 | FR ACM | 2026-07-29 | LO | 27.5714 | 2026-07-18 | Clean and Brake | Fab | 04/16/2026…LO
25044-FS09 | MALETA Firing Range | Cole Norona | 86 | 0 | FR ACM | 2026-07-29 | LO | 12.2857 | 2026-07-21 | Clean and Brake | Fab | 04/16/2026…LO
25006-FS13 | MALETA Housing and Dining | Cole Norona | 28 | 0 | FR ACM | 2026-08-03 | LO | 4 | 2026-07-27 | Clean and Brake | Fab | HOAR*04/16/2026…LO
25044-FS10 | MALETA Firing Range | Cole Norona | 185 | 0 | FR ACM | 2026-08-07 | LO | 26.4286 | 2026-07-28 | Clean and Brake | Fab | 04/16/2026…LO
25044-FS11 | MALETA Firing Range | Cole Norona | 185 | 0 | FR ACM | 2026-08-17 | LO | 26.4286 | 2026-08-06 | Clean and Brake | Fab | 04/16/2026…LO
Formulas:
Ship Target = IF([ID]="","",IFERROR(VLOOKUP([ID],'Job Operations'!$A4:AA304,9,FALSE),""))
Ship Target = IFERROR(VLOOKUP([ID],'Job Operations'!$A:$I,9,FALSE),"")
CNC Start By = IF(OR([ID]="",[Ship Target]=""),"",WORKDAY.INTL([Ship Target],-(5+CEILING([Hrs to Complete CNC]/8,1)),"0000001"))
CNC Start By = IFERROR(VLOOKUP([ID],'Job Operations'!$A:$N,14,FALSE),"")

## Clean and Brake Schedule
|  | SEARCH JOB ID: | 25067-FS02 | 🟢 ON TIME | Harison Bend | Ship: 04/30/2026 | Station: AXYZ 34
CLEAN AND BRAKE SCHEDULE — Jobs At or Coming to Clean and Brake
Includes jobs currently at Clean and Brake station AND jobs with Clean and Brake as an operation. Sorted by Start By date.
ID | Job Name | PM | Panel Qty | Part Qty | Material Type | Ship Target | Current Station | Queue Position | C&B Start By | Next Op | Notes
25002-FS11.1 | Med Center Health | Carlos Silva | 18 | 18 | FR ACM | 2026-03-02 | 1st | 1st | 2026-02-06 | Fab | Received Radius Templete, waiting for Roller Maint.**03/23 Roller should be back up this morning*03/24 Roller still down AM*03/26…C&B*03/27…Still at C&B needs to roll then back to C&B*03/31…No Update*04/02…Roller still down.*04/09…Roller still down.*04/16/2026…Clean and Brake
24051-FS223 | TN Titans Stadium | Marc Ribar | 44 | 90 | FR ACM | 2026-03-16 | 2nd | 2nd | 2026-02-20 | Fab | 03/23...Next for Titans--1 of 3 still late*03/24 Corrections*03/26…Titans line*03/30…Affected by Roller being down. Panals too large to run in small roller.*03/31…No update*04/02…Roller still down.*04/09…Roller still down.*04/16/2026…Clean and Brake
24079-FS102 | Nashville Youth Campus | Joe Hoyle | 192 | 198 | FR ACM | 2026-03-16 | Sketch Check | #2 on Titans | 2026-02-20 | Fab | 04/16/2026…Sketch Check
24079-FS102.1 | Nashville Youth Campus | Joe Hoyle | 308 | 0 | FR ACM | 2026-03-16 | Sketch | #1 on Titans | 2026-02-20 | Fab | 04/16/2026…Sketch
25035-FS04 | Titans Jabez | Marc Ribar | 218 | 0 | FR ACM | 2026-03-23 | Sketch | #3 on Titans | 2026-02-27 | Fab | 04/16/2026…Sketch
25017-RO02 | Nashville Yards Park | Dillon Bowman | 1 | 3 | FR ACM | 2026-04-15 | 3rd | 3rd | 2026-03-12 | Fab | 03/27…C&B, needs to roll then back to C&B*03/30…Affected by Roller being down.*03/31…No Update*04/02…Roller still down.*04/09…Roller still down.*04/16/2026…Clean and Brake
24074-FS07 | DIDD ACM | Dillon Bowman | 155 | 218 | FR ACM | 2026-04-20 | CNC Programming | #4 on Titans | 2026-03-17 | Fab | *03/30...4' Panals Rolled*04/02…Sketch*04/09…CNC*04/16/2026…CNC Programming
24051-FS87 | TN Titans Stadium | Marc Ribar | 54 | 54 | FR ACM | 2026-04-15 | 4th | 4th | 2026-03-23 | Fab | Must be RTS on Friday 04/17*04/16/2026…Clean and Brake
24051-FS89 | TN Titans Stadium | Marc Ribar | 40 | 40 | FR ACM | 2026-04-15 | AXYZ 34 | #5 on Titans | 2026-03-23 | Fab | 04/14...Next Titans Requesting//Scheduled to be released to the shop 04/16.*04/16/2026…AXYZ 34
25010-RO06 | TOA Spring Hill MOB | Cole Norona | 6 | 0 | FR ACM | 2026-04-15 | LO | #1 on AXYZ | 2026-03-23 | Fab | 04/16/2026…LO
25010-RO07 | TOA Spring Hill MOB | Cole Norona | 3 | 0 | FR ACM | 2026-04-15 | LO | #2 on AXYZ | 2026-03-23 | Fab | 04/16/2026…LO
25002-FS13 | Med Center Health | Carlos Silva | 30 | 0 | FR ACM | 2026-04-17 | LO | #3 on AXYZ | 2026-03-25 | Fab | 04/16/2026…LO
26009-FS01 | 5th & Summer Leasing Office | Cole Norona | 9 | 0 | FR ACM | 2026-04-20 | LO Check | #4 on AXYZ | 2026-03-27 | Fab | 04/16/2026…LO Check
25022-RM01 | Vantage VA15 | Thomas Mooers | 4 | 4 | FR ACM | 2026-04-23 | AXYZ 34 | #6 on Titans | 2026-03-31 | Fab | 04/16/2026…AXYZ 34
25022-RM02 | Vantage VA15 | Thomas Mooers | 1 | 1 | FR ACM | 2026-04-23 | AXYZ 34 | #7 on Titans | 2026-03-31 | Fab | 04/16/2026…AXYZ 34
25059-RM05 | Allen Samuels CDJR and LC | Andre Van Der Merwe | 1 | 1 | FR ACM | 2026-04-23 | CNC Programming | #9 on AXYZ | 2026-03-31 | Fab | 04/16/2026…CNC Programming
25012-MU07 | St Jude Hospital | Wylie McDougall | 8 | 8 | FR ACM | 2026-04-14 | 5th | 5th | 2026-04-01 |  | 04/16/2026…Clean and Brake
25030-FS01 | 510 W Tremont | Laura Forero | 88 | 0 | FR ACM | 2026-04-24 | Correction | #10 on AXYZ | 2026-04-01 | Fab | 04/16/2026…Correction
25030-FS02 | 510 W Tremont | Laura Forero | 84 | 0 | FR ACM | 2026-04-24 | Sketch | #11 on AXYZ | 2026-04-01 | Fab | 04/16/2026…Sketch
24051-FS90 | TN Titans Stadium | Marc Ribar | 117 | 0 | FR ACM | 2026-04-24 | Float | #5 on AXYZ | 2026-04-01 | Fab | 04/16/2026…Float
24051-FS91 | TN Titans Stadium | Marc Ribar | 36 | 0 | FR ACM | 2026-04-24 | Float | #12 on AXYZ | 2026-04-01 | Fab | 04/16/2026…Float
24051-FS227 | TN Titans Stadium | Marc Ribar | 119 | 0 | FR ACM | 2026-04-24 | Float | #6 on AXYZ | 2026-04-01 | Fab | 04/16/2026…Float
24079-RM01 | Nashville Youth Campus | Joe Hoyle | 37 | 39 | FR ACM | 2026-04-24 | Sketch | #13 on AXYZ | 2026-04-01 | Fab | 04/16/2026…Sketch
24026-FS01 | 1740 Division | Chris Buttrey | 23 | 23 | FR ACM | 2026-04-27 | AXYZ 34 | #8 on Titans | 2026-04-03 | Fab | 04/15...Date adjusted to 04/27.*04/16/2026…AXYZ 34
25022-RO03 | Vantage VA15 | Thomas Mooers | 3 | 3 | FR ACM | 2026-04-27 | AXYZ 34 | #9 on Titans | 2026-04-03 | Fab | 04/16/2026…AXYZ 34
24051-FS93 | TN Titans Stadium | Marc Ribar | 131 | 133 | FR ACM | 2026-04-28 | Correction | #14 on AXYZ | 2026-04-04 | Fab | 04/14...Next Titans Requesting//Scheduled to be released to the shop 04/20.*04/16/2026…Correction
24051-FS94 | TN Titans Stadium | Marc Ribar | 79 | 0 | FR ACM | 2026-04-28 | Float | #16 on AXYZ | 2026-04-04 | Fab | 04/16/2026…Float
24051-FS95 | TN Titans Stadium | Marc Ribar | 96 | 0 | FR ACM | 2026-04-28 | Float | #17 on AXYZ | 2026-04-04 | Fab | 04/16/2026…Float
24051-FS228 | TN Titans Stadium | Marc Ribar | 95 | 0 | FR ACM | 2026-04-28 | Float | #18 on AXYZ | 2026-04-04 | Fab | 04/16/2026…Float
25067-FS02 | Harison Bend | Andre Van Der Merwe | 29 | 29 | FR ACM | 2026-04-30 | AXYZ 34 | #10 on Titans | 2026-04-07 | Fab | 04/15…CNC...Confirmed Shipdate of 04/22 with PM.*04/16/2026…AXYZ 34
24051-FS92 | TN Titans Stadium | Marc Ribar | 104 | 0 | FR ACM | 2026-05-01 | Float | #19 on AXYZ | 2026-04-08 | Fab | 04/16/2026…Float
24051-FS96 | TN Titans Stadium | Marc Ribar | 52 | 0 | FR ACM | 2026-05-01 | Float | #22 on AXYZ | 2026-04-08 | Fab | 04/16/2026…Float
24051-FS229 | TN Titans Stadium | Marc Ribar | 109 | 0 | FR ACM | 2026-05-01 | Float | #20 on AXYZ | 2026-04-08 | Fab | 04/16/2026…Float
24051-FS230 | TN Titans Stadium | Marc Ribar | 67 | 0 | FR ACM | 2026-05-01 | Float | #21 on AXYZ | 2026-04-08 | Fab | 04/16/2026…Float
25031-RO01 | LLU Mars US Warehouse | Laura Forero | 3 | 3 | FR ACM | 2026-04-22 | CNC Programming | CNC Programming | 2026-04-09 |  | 04/16/2026…CNC Programming
24051-FS231 | TN Titans Stadium | Marc Ribar | 1 | 0 | FR ACM | 2026-05-04 | Float | #24 on AXYZ | 2026-04-10 | Fab | 04/16/2026…Float
25002-FS14 | Med Center Health | Carlos Silva | 00 | 0 | FR ACM | 2026-05-04 | Evaluation | #26 on AXYZ | 2026-04-10 | Fab | 04/16/2026…Evaluation
25006-FS03 | MALETA Housing and Dining | Cole Norona | 216 | 0 | FR ACM | 2026-05-05 | Correction | #23 on AXYZ | 2026-04-11 | Fab | Not expected out of engineering before 04/15…Needs to ship 05/12*HOAR*04/16/2026…Correction
24074-FS08 | DIDD ACM | Dillon Bowman | 186 | 0 | FR ACM | 2026-05-07 | LO Check | #25 on AXYZ | 2026-04-14 | Fab | 04/16/2026…LO Check
25006-FS05 | MALETA Housing and Dining | Cole Norona | 18 | 0 | FR ACM | 2026-05-11 | LO Check | #29 on AXYZ | 2026-04-17 | Fab | Not expected out of engineering before 04/17…Needs to ship 05/12*HOAR*04/16/2026…LO Check
24079-FS103 | Nashville Youth Campus | Joe Hoyle | 111 | 0 | FR ACM | 2026-05-11 | LO Check | #27 on AXYZ | 2026-04-17 | Fab | 04/16/2026…LO Check
25010-FS09 | TOA Spring Hill MOB | Cole Norona | 111 | 0 | FR ACM | 2026-05-11 | Correction | #28 on AXYZ | 2026-04-17 | Fab | 04/16/2026…Correction
25002-FS15 | Med Center Health | Carlos Silva | 12 | 0 | FR ACM | 2026-05-11 | Evaluation | #30 on AXYZ | 2026-04-17 | Fab | 04/16/2026…Evaluation
24074-FS09 | DIDD ACM | Dillon Bowman | 120 | 0 | FR ACM | 2026-05-14 | LO Check | #32 on AXYZ | 2026-04-21 | Fab | 04/16/2026…LO Check
25006-FS04 | MALETA Housing and Dining | Cole Norona | 232 | 0 | FR ACM | 2026-05-15 | LO Check | #31 on AXYZ | 2026-04-22 | Fab | HOAR*04/16/2026…LO Check
25041-FS02 | Wedgewood Bldg E | Wylie McDougall | 31 | 0 | FR ACM | 2026-05-26 | LO | #34 on AXYZ | 2026-04-22 | Fab | 04/16/2026…LO
24079-FS201 | Nashville Youth Campus | Joe Hoyle | 41 | 0 | FR ACM | 2026-05-18 | LO | #35 on AXYZ | 2026-04-24 | Fab | 04/16/2026…LO
24079-FS302 | Nashville Youth Campus | Joe Hoyle | 188 | 0 | FR ACM | 2026-05-18 | LO | #33 on AXYZ | 2026-04-24 | Fab | 04/16/2026…LO
25008-FS07 | Columbia State Tech Center | Laura Forero | 58 | 0 | FR ACM | 2026-05-20 | Evaluation | #36 on AXYZ | 2026-04-27 | Fab | 04/16/2026…Evaluation
24074-FS10 | DIDD ACM | Dillon Bowman | 130 | 0 | FR ACM | 2026-05-21 | LO Check | #37 on AXYZ | 2026-04-28 | Fab | 04/16/2026…LO Check
25044-FS01 | MALETA Firing Range | Cole Norona | 125 | 0 | FR ACM | 2026-05-22 | LO | #38 on AXYZ | 2026-04-29 | Fab | 04/16/2026…LO
25044-FS01.1 | MALETA Firing Range | Cole Norona | 34 | 0 | FR ACM | 2026-05-22 | LO | #41 on AXYZ | 2026-04-29 | Fab | 04/16/2026…LO
25065-MU01 | Crosswinds Casino Resort | Matt Rassmussen | 18 | 14 | FR ACM | 2026-05-22 | Sketch Check | #42 on AXYZ | 2026-04-29 | Fab | 04/16/2026…Sketch Check
25006-FS06 | MALETA Housing and Dining | Cole Norona | 246 | 0 | FR ACM | 2026-05-25 | LO Check | #39 on AXYZ | 2026-05-01 | Fab | HOAR*04/16/2026…LO Check
25037-FS01 | Chestnut Street Office | Laura Forero | 218 | 0 | FR ACM | 2026-05-25 | LO Check | #40 on AXYZ | 2026-05-01 | Fab | 04/16/2026…LO Check
24079-FS301 | Nashville Youth Campus | Joe Hoyle | 143 | 0 | FR ACM | 2026-05-25 | LO | #43 on AXYZ | 2026-05-01 | Fab | 04/16/2026…LO
24079-FS303 | Nashville Youth Campus | Joe Hoyle | 165 | 0 | FR ACM | 2026-05-25 | LO | #44 on AXYZ | 2026-05-01 | Fab | 04/16/2026…LO
25065-MU02 | Crosswinds Casino Resort | Matt Rassmussen | 15 | 13 | FR ACM | 2026-05-29 | LO | #45 on AXYZ | 2026-05-06 | Fab | 04/16/2026…LO
25065-MU03 | Crosswinds Casino Resort | Matt Rassmussen | 6 | 6 | FR ACM | 2026-05-29 | LO | #46 on AXYZ | 2026-05-06 | Fab | 04/16/2026…LO
25065-MU04 | Crosswinds Casino Resort | Matt Rassmussen | 15 | 13 | FR ACM | 2026-05-29 | LO | #47 on AXYZ | 2026-05-06 | Fab | 04/16/2026…LO
25044-FS02 | MALETA Firing Range | Cole Norona | 135 | 0 | FR ACM | 2026-05-31 | LO | #48 on AXYZ | 2026-05-08 | Fab | 04/16/2026…LO
25006-FS07 | MALETA Housing and Dining | Cole Norona | 190 | 0 | FR ACM | 2026-06-03 | LO Check | #49 on AXYZ | 2026-05-11 | Fab | HOAR*04/16/2026…LO Check
25037-FS02 | Chestnut Street Office | Laura Forero | 204 | 0 | FR ACM | 2026-06-08 | LO | #50 on AXYZ | 2026-05-15 | Fab | 04/16/2026…LO
25044-FS03 | MALETA Firing Range | Cole Norona | 150 | 0 | FR ACM | 2026-06-10 | LO | #51 on AXYZ | 2026-05-18 | Fab | 04/16/2026…LO
25006-FS08 | MALETA Housing and Dining | Cole Norona | 83 | 0 | FR ACM | 2026-06-12 | LO Check | #52 on AXYZ | 2026-05-20 | Fab | HOAR*04/16/2026…LO Check
25012-FS02 | St Jude Hospital | Wylie McDougall | 60 | 60 | FR ACM | 2026-06-12 | AXYZ 34 | #11 on Titans | 2026-05-20 | Fab | 04/16/2026…AXYZ 34
25044-FS04 | MALETA Firing Range | Cole Norona | 113 | 0 | FR ACM | 2026-06-19 | LO | #53 on AXYZ | 2026-05-27 | Fab | 04/16/2026…LO
25006-FS09 | MALETA Housing and Dining | Cole Norona | 152 | 0 | FR ACM | 2026-06-19 | LO | #54 on AXYZ | 2026-05-27 | Fab | HOAR*04/16/2026…LO
25044-FS05 | MALETA Firing Range | Cole Norona | 111 | 0 | FR ACM | 2026-06-26 | LO | #55 on AXYZ | 2026-06-03 | Fab | 04/16/2026…LO
25044-FS06 | MALETA Firing Range | Cole Norona | 203 | 0 | FR ACM | 2026-07-06 | LO | #56 on AXYZ | 2026-06-12 | Fab | 04/16/2026…LO
25044-FS07 | MALETA Firing Range | Cole Norona | 160 | 0 | FR ACM | 2026-07-15 | LO | #59 on AXYZ | 2026-06-22 | Fab | 04/16/2026…LO
25006-FS11 | MALETA Housing and Dining | Cole Norona | 201 | 0 | FR ACM | 2026-07-15 | LO | #58 on AXYZ | 2026-06-22 | Fab | HOAR*04/16/2026…LO
25044-FS08 | MALETA Firing Range | Cole Norona | 163 | 0 | FR ACM | 2026-07-22 | LO | #60 on AXYZ | 2026-06-29 | Fab | 04/16/2026…LO
25006-FS12 | MALETA Housing and Dining | Cole Norona | 192 | 0 | FR ACM | 2026-07-27 | LO | #61 on AXYZ | 2026-07-03 | Fab | HOAR*04/16/2026…LO
25044-FS09 | MALETA Firing Range | Cole Norona | 86 | 0 | FR ACM | 2026-07-29 | LO | #63 on AXYZ | 2026-07-06 | Fab | 04/16/2026…LO
25044-FS01.2 | MALETA Firing Range | Cole Norona | 193 | 0 | FR ACM | 2026-07-29 | LO | #62 on AXYZ | 2026-07-06 | Fab | 04/16/2026…LO
25006-FS13 | MALETA Housing and Dining | Cole Norona | 28 | 0 | FR ACM | 2026-08-03 | LO | #64 on AXYZ | 2026-07-10 | Fab | HOAR*04/16/2026…LO
25044-FS10 | MALETA Firing Range | Cole Norona | 185 | 0 | FR ACM | 2026-08-07 | LO | #65 on AXYZ | 2026-07-15 | Fab | 04/16/2026…LO
25044-FS11 | MALETA Firing Range | Cole Norona | 185 | 0 | FR ACM | 2026-08-17 | LO | #66 on AXYZ | 2026-07-24 | Fab | 04/16/2026…LO
25075-RP01 | St Thomas West Canopy Replace | Chris Buttrey | 2 | 6 | 0 | 0 | CNC Programming | CNC Programming |  | Fab | 04/16/2026…
24051-RP58 | TN Titans Stadium | Marc Ribar | 1 | 0 | 0 | 0 | CNC Programming | CNC Programming |  | Fab | 04/16/2026…
24071-RP15 | RS Gass State Lab | Cole Norona | 0 | 3 | 0 | 0 | CNC Programming | CNC Programming |  | Fab | 04/16/2026…
Formulas:
Ship Target = IF([ID]="","",IFERROR(VLOOKUP([ID],'Job Operations'!$A4:AA304,9,FALSE),""))
C&B Start By = IF([ID]="","",IFERROR(VLOOKUP([ID],'Job Operations'!$A4:AA304,16,FALSE),""))

## Fab Schedule
|  | SEARCH JOB ID: | 24051-FS225 | 🔴 LATE | TN Titans Stadium | Ship: 03/16/2026 | Station: LO
FAB SCHEDULE — Jobs At or Coming to Fabrication
Includes jobs currently at Fabrication station AND jobs with Fab as an operation. Sorted by Start By date.
ID | Job Name | PM | Panel Qty | Part Qty | Material Type | Ship Target | Current Station | Queue Position | Fab Start By | First Op | Previous Op | Notes
25002-FS11.1 | Med Center Health | Carlos Silva | 18 | 18 | FR ACM | 2026-03-02 | Clean and Brake | #1 on C&B | 2026-02-17 | AXYZ Titans Line | Clean and Brake | Received Radius Templete, waiting for Roller Maint.**03/23 Roller should be back up this morning*03/24 Roller still down AM*03/26…C&B*03/27…Still at C&B needs to roll then back to C&B*03/31…No Update*04/02…Roller still down.*04/09…Roller still down.*04/16/2026…Clean and Brake
24051-FS223 | TN Titans Stadium | Marc Ribar | 44 | 90 | FR ACM | 2026-03-16 | Clean and Brake | #2 on C&B | 2026-03-03 | AXYZ Titans Line | Clean and Brake | 03/23...Next for Titans--1 of 3 still late*03/24 Corrections*03/26…Titans line*03/30…Affected by Roller being down. Panals too large to run in small roller.*03/31…No update*04/02…Roller still down.*04/09…Roller still down.*04/16/2026…Clean and Brake
24079-FS102 | Nashville Youth Campus | Joe Hoyle | 192 | 198 | FR ACM | 2026-03-16 | Sketch Check | #3 on C&B | 2026-03-03 | AXYZ Titans Line | Clean and Brake | 04/16/2026…Sketch Check
24079-FS102.1 | Nashville Youth Campus | Joe Hoyle | 308 | 0 | FR ACM | 2026-03-16 | Sketch | #4 on C&B | 2026-03-03 | AXYZ Titans Line | Clean and Brake | 04/16/2026…Sketch
25005-ST02 | CAT Financial Nashville HQ | Chris Buttrey | 0 | 4 | Steel Sheet | 2026-04-13 | TruLaser 3040 | TruLaser 3040 | 2026-03-03 | Brake | Fab | 04/16/2026…TruLaser 3040
25035-FS04 | Titans Jabez | Marc Ribar | 218 | 0 | FR ACM | 2026-03-23 | Sketch | #5 on C&B | 2026-03-10 | AXYZ Titans Line | Clean and Brake | 04/16/2026…Sketch
25017-RO02 | Nashville Yards Park | Dillon Bowman | 1 | 3 | FR ACM | 2026-04-15 | Clean and Brake | #6 on C&B | 2026-03-23 | AXYZ Titans Line | Clean and Brake | 03/27…C&B, needs to roll then back to C&B*03/30…Affected by Roller being down.*03/31…No Update*04/02…Roller still down.*04/09…Roller still down.*04/16/2026…Clean and Brake
24074-FS07 | DIDD ACM | Dillon Bowman | 155 | 218 | FR ACM | 2026-04-20 | CNC Programming | #7 on C&B | 2026-03-27 | AXYZ Titans Line | Clean and Brake | *03/30...4' Panals Rolled*04/02…Sketch*04/09…CNC*04/16/2026…CNC Programming
24051-FS87 | TN Titans Stadium | Marc Ribar | 54 | 54 | FR ACM | 2026-04-15 | Clean and Brake | #8 on C&B | 2026-04-02 | AXYZ Titans Line | Clean and Brake | Must be RTS on Friday 04/17*04/16/2026…Clean and Brake
24051-FS89 | TN Titans Stadium | Marc Ribar | 40 | 40 | FR ACM | 2026-04-15 | AXYZ 34 | #9 on C&B | 2026-04-02 | AXYZ Titans Line | Clean and Brake | 04/14...Next Titans Requesting//Scheduled to be released to the shop 04/16.*04/16/2026…AXYZ 34
24051-FS36.2 | TN Titans Stadium | Marc Ribar | 38 | 38 | FR ACM | 2026-04-15 | 1st | 1st | 2026-04-02 | AXYZ Titans Line | Clean and Brake | 04/16/2026…Fabrication
24051-FS226 | TN Titans Stadium | Marc Ribar | 26 | 26 | FR ACM | 2026-04-15 | 2nd | 2nd | 2026-04-02 | AXYZ Titans Line | Clean and Brake | 04/16/2026…Fabrication
25010-RO06 | TOA Spring Hill MOB | Cole Norona | 6 | 0 | FR ACM | 2026-04-15 | LO | #10 on C&B | 2026-04-02 | AXYZ | Clean and Brake | 04/16/2026…LO
25010-RO07 | TOA Spring Hill MOB | Cole Norona | 3 | 0 | FR ACM | 2026-04-15 | LO | #11 on C&B | 2026-04-02 | AXYZ | Clean and Brake | 04/16/2026…LO
25002-FS13 | Med Center Health | Carlos Silva | 30 | 0 | FR ACM | 2026-04-17 | LO | #12 on C&B | 2026-04-04 | AXYZ | Clean and Brake | 04/16/2026…LO
26009-FS01 | 5th & Summer Leasing Office | Cole Norona | 9 | 0 | FR ACM | 2026-04-20 | LO Check | #13 on C&B | 2026-04-07 | AXYZ | Clean and Brake | 04/16/2026…LO Check
25022-RM01 | Vantage VA15 | Thomas Mooers | 4 | 4 | FR ACM | 2026-04-23 | AXYZ 34 | #14 on C&B | 2026-04-10 | AXYZ | Clean and Brake | 04/16/2026…AXYZ 34
25022-RM02 | Vantage VA15 | Thomas Mooers | 1 | 1 | FR ACM | 2026-04-23 | AXYZ 34 | #15 on C&B | 2026-04-10 | AXYZ | Clean and Brake | 04/16/2026…AXYZ 34
25059-RM05 | Allen Samuels CDJR and LC | Andre Van Der Merwe | 1 | 1 | FR ACM | 2026-04-23 | CNC Programming | #16 on C&B | 2026-04-10 | AXYZ | Clean and Brake | 04/16/2026…CNC Programming
25030-FS01 | 510 W Tremont | Laura Forero | 88 | 0 | FR ACM | 2026-04-24 | Correction | #18 on C&B | 2026-04-11 | AXYZ | Clean and Brake | 04/16/2026…Correction
25030-FS02 | 510 W Tremont | Laura Forero | 84 | 0 | FR ACM | 2026-04-24 | Sketch | #19 on C&B | 2026-04-11 | AXYZ | Clean and Brake | 04/16/2026…Sketch
24051-FS90 | TN Titans Stadium | Marc Ribar | 117 | 0 | FR ACM | 2026-04-24 | Float | #20 on C&B | 2026-04-11 | AXYZ | Clean and Brake | 04/16/2026…Float
24051-FS91 | TN Titans Stadium | Marc Ribar | 36 | 0 | FR ACM | 2026-04-24 | Float | #21 on C&B | 2026-04-11 | AXYZ | Clean and Brake | 04/16/2026…Float
24051-FS227 | TN Titans Stadium | Marc Ribar | 119 | 0 | FR ACM | 2026-04-24 | Float | #22 on C&B | 2026-04-11 | AXYZ | Clean and Brake | 04/16/2026…Float
24079-RM01 | Nashville Youth Campus | Joe Hoyle | 37 | 39 | FR ACM | 2026-04-24 | Sketch | #23 on C&B | 2026-04-11 | AXYZ | Clean and Brake | 04/16/2026…Sketch
24026-FS01 | 1740 Division | Chris Buttrey | 23 | 23 | FR ACM | 2026-04-27 | AXYZ 34 | #24 on C&B | 2026-04-14 | AXYZ Titans Line | Clean and Brake | 04/15...Date adjusted to 04/27.*04/16/2026…AXYZ 34
25022-RO03 | Vantage VA15 | Thomas Mooers | 3 | 3 | FR ACM | 2026-04-27 | AXYZ 34 | #25 on C&B | 2026-04-14 | AXYZ | Clean and Brake | 04/16/2026…AXYZ 34
24051-FS93 | TN Titans Stadium | Marc Ribar | 131 | 133 | FR ACM | 2026-04-28 | Correction | #26 on C&B | 2026-04-15 | AXYZ | Clean and Brake | 04/14...Next Titans Requesting//Scheduled to be released to the shop 04/20.*04/16/2026…Correction
24051-FS94 | TN Titans Stadium | Marc Ribar | 79 | 0 | FR ACM | 2026-04-28 | Float | #27 on C&B | 2026-04-15 | AXYZ | Clean and Brake | 04/16/2026…Float
24051-FS95 | TN Titans Stadium | Marc Ribar | 96 | 0 | FR ACM | 2026-04-28 | Float | #28 on C&B | 2026-04-15 | AXYZ | Clean and Brake | 04/16/2026…Float
24051-FS228 | TN Titans Stadium | Marc Ribar | 95 | 0 | FR ACM | 2026-04-28 | Float | #29 on C&B | 2026-04-15 | AXYZ | Clean and Brake | 04/16/2026…Float
25067-FS02 | Harison Bend | Andre Van Der Merwe | 29 | 29 | FR ACM | 2026-04-30 | AXYZ 34 | #30 on C&B | 2026-04-17 | AXYZ Titans Line | Clean and Brake | 04/15…CNC...Confirmed Shipdate of 04/22 with PM.*04/16/2026…AXYZ 34
24051-FS92 | TN Titans Stadium | Marc Ribar | 104 | 0 | FR ACM | 2026-05-01 | Float | #31 on C&B | 2026-04-18 | AXYZ | Clean and Brake | 04/16/2026…Float
24051-FS96 | TN Titans Stadium | Marc Ribar | 52 | 0 | FR ACM | 2026-05-01 | Float | #32 on C&B | 2026-04-18 | AXYZ | Clean and Brake | 04/16/2026…Float
24051-FS229 | TN Titans Stadium | Marc Ribar | 109 | 0 | FR ACM | 2026-05-01 | Float | #33 on C&B | 2026-04-18 | AXYZ | Clean and Brake | 04/16/2026…Float
24051-FS230 | TN Titans Stadium | Marc Ribar | 67 | 0 | FR ACM | 2026-05-01 | Float | #34 on C&B | 2026-04-18 | AXYZ | Clean and Brake | 04/16/2026…Float
24051-FS231 | TN Titans Stadium | Marc Ribar | 1 | 0 | FR ACM | 2026-05-04 | Float | #36 on C&B | 2026-04-21 | AXYZ | Clean and Brake | 04/16/2026…Float
25002-FS14 | Med Center Health | Carlos Silva | 00 | 0 | FR ACM | 2026-05-04 | Evaluation | #37 on C&B | 2026-04-21 | AXYZ | Clean and Brake | 04/16/2026…Evaluation
25006-FS03 | MALETA Housing and Dining | Cole Norona | 216 | 0 | FR ACM | 2026-05-05 | Correction | #38 on C&B | 2026-04-22 | AXYZ | Clean and Brake | Not expected out of engineering before 04/15…Needs to ship 05/12*HOAR*04/16/2026…Correction
24074-FS08 | DIDD ACM | Dillon Bowman | 186 | 0 | FR ACM | 2026-05-07 | LO Check | #39 on C&B | 2026-04-24 | AXYZ | Clean and Brake | 04/16/2026…LO Check
25006-FS05 | MALETA Housing and Dining | Cole Norona | 18 | 0 | FR ACM | 2026-05-11 | LO Check | #40 on C&B | 2026-04-28 | AXYZ | Clean and Brake | Not expected out of engineering before 04/17…Needs to ship 05/12*HOAR*04/16/2026…LO Check
24079-FS103 | Nashville Youth Campus | Joe Hoyle | 111 | 0 | FR ACM | 2026-05-11 | LO Check | #41 on C&B | 2026-04-28 | AXYZ | Clean and Brake | 04/16/2026…LO Check
25010-FS09 | TOA Spring Hill MOB | Cole Norona | 111 | 0 | FR ACM | 2026-05-11 | Correction | #42 on C&B | 2026-04-28 | AXYZ | Clean and Brake | 04/16/2026…Correction
25002-FS15 | Med Center Health | Carlos Silva | 12 | 0 | FR ACM | 2026-05-11 | Evaluation | #43 on C&B | 2026-04-28 | AXYZ | Clean and Brake | 04/16/2026…Evaluation
24074-FS09 | DIDD ACM | Dillon Bowman | 120 | 0 | FR ACM | 2026-05-14 | LO Check | #44 on C&B | 2026-05-01 | AXYZ | Clean and Brake | 04/16/2026…LO Check
25006-FS04 | MALETA Housing and Dining | Cole Norona | 232 | 0 | FR ACM | 2026-05-15 | LO Check | #45 on C&B | 2026-05-02 | AXYZ | Clean and Brake | HOAR*04/16/2026…LO Check
25041-FS02 | Wedgewood Bldg E | Wylie McDougall | 31 | 0 | FR ACM | 2026-05-26 | LO | #46 on C&B | 2026-05-02 | AXYZ | Clean and Brake | 04/16/2026…LO
24079-FS201 | Nashville Youth Campus | Joe Hoyle | 41 | 0 | FR ACM | 2026-05-18 | LO | #47 on C&B | 2026-05-05 | AXYZ | Clean and Brake | 04/16/2026…LO
24079-FS302 | Nashville Youth Campus | Joe Hoyle | 188 | 0 | FR ACM | 2026-05-18 | LO | #48 on C&B | 2026-05-05 | AXYZ | Clean and Brake | 04/16/2026…LO
25008-FS07 | Columbia State Tech Center | Laura Forero | 58 | 0 | FR ACM | 2026-05-20 | Evaluation | #49 on C&B | 2026-05-07 | AXYZ | Clean and Brake | 04/16/2026…Evaluation
24074-FS10 | DIDD ACM | Dillon Bowman | 130 | 0 | FR ACM | 2026-05-21 | LO Check | #50 on C&B | 2026-05-08 | AXYZ | Clean and Brake | 04/16/2026…LO Check
25044-FS01 | MALETA Firing Range | Cole Norona | 125 | 0 | FR ACM | 2026-05-22 | LO | #51 on C&B | 2026-05-09 | AXYZ | Clean and Brake | 04/16/2026…LO
25044-FS01.1 | MALETA Firing Range | Cole Norona | 34 | 0 | FR ACM | 2026-05-22 | LO | #52 on C&B | 2026-05-09 | AXYZ | Clean and Brake | 04/16/2026…LO
25065-MU01 | Crosswinds Casino Resort | Matt Rassmussen | 18 | 14 | FR ACM | 2026-05-22 | Sketch Check | #53 on C&B | 2026-05-09 | AXYZ | Clean and Brake | 04/16/2026…Sketch Check
25006-FS06 | MALETA Housing and Dining | Cole Norona | 246 | 0 | FR ACM | 2026-05-25 | LO Check | #54 on C&B | 2026-05-12 | AXYZ | Clean and Brake | HOAR*04/16/2026…LO Check
25037-FS01 | Chestnut Street Office | Laura Forero | 218 | 0 | FR ACM | 2026-05-25 | LO Check | #55 on C&B | 2026-05-12 | AXYZ | Clean and Brake | 04/16/2026…LO Check
24079-FS301 | Nashville Youth Campus | Joe Hoyle | 143 | 0 | FR ACM | 2026-05-25 | LO | #56 on C&B | 2026-05-12 | AXYZ | Clean and Brake | 04/16/2026…LO
24079-FS303 | Nashville Youth Campus | Joe Hoyle | 165 | 0 | FR ACM | 2026-05-25 | LO | #57 on C&B | 2026-05-12 | AXYZ | Clean and Brake | 04/16/2026…LO
25065-MU02 | Crosswinds Casino Resort | Matt Rassmussen | 15 | 13 | FR ACM | 2026-05-29 | LO | #58 on C&B | 2026-05-16 | AXYZ | Clean and Brake | 04/16/2026…LO
25065-MU03 | Crosswinds Casino Resort | Matt Rassmussen | 6 | 6 | FR ACM | 2026-05-29 | LO | #59 on C&B | 2026-05-16 | AXYZ | Clean and Brake | 04/16/2026…LO
25065-MU04 | Crosswinds Casino Resort | Matt Rassmussen | 15 | 13 | FR ACM | 2026-05-29 | LO | #60 on C&B | 2026-05-16 | AXYZ | Clean and Brake | 04/16/2026…LO
25044-FS02 | MALETA Firing Range | Cole Norona | 135 | 0 | FR ACM | 2026-05-31 | LO | #61 on C&B | 2026-05-19 | AXYZ | Clean and Brake | 04/16/2026…LO
25006-FS07 | MALETA Housing and Dining | Cole Norona | 190 | 0 | FR ACM | 2026-06-03 | LO Check | #62 on C&B | 2026-05-21 | AXYZ | Clean and Brake | HOAR*04/16/2026…LO Check
25037-FS02 | Chestnut Street Office | Laura Forero | 204 | 0 | FR ACM | 2026-06-08 | LO | #63 on C&B | 2026-05-26 | AXYZ | Clean and Brake | 04/16/2026…LO
25044-FS03 | MALETA Firing Range | Cole Norona | 150 | 0 | FR ACM | 2026-06-10 | LO | #64 on C&B | 2026-05-28 | AXYZ | Clean and Brake | 04/16/2026…LO
25006-FS08 | MALETA Housing and Dining | Cole Norona | 83 | 0 | FR ACM | 2026-06-12 | LO Check | #65 on C&B | 2026-05-30 | AXYZ | Clean and Brake | HOAR*04/16/2026…LO Check
25012-FS02 | St Jude Hospital | Wylie McDougall | 60 | 60 | FR ACM | 2026-06-12 | AXYZ 34 | #66 on C&B | 2026-05-30 | AXYZ Titans Line | Clean and Brake | 04/16/2026…AXYZ 34
25044-FS04 | MALETA Firing Range | Cole Norona | 113 | 0 | FR ACM | 2026-06-19 | LO | #67 on C&B | 2026-06-06 | AXYZ | Clean and Brake | 04/16/2026…LO
25006-FS09 | MALETA Housing and Dining | Cole Norona | 152 | 0 | FR ACM | 2026-06-19 | LO | #68 on C&B | 2026-06-06 | AXYZ | Clean and Brake | HOAR*04/16/2026…LO
25044-FS05 | MALETA Firing Range | Cole Norona | 111 | 0 | FR ACM | 2026-06-26 | LO | #69 on C&B | 2026-06-13 | AXYZ | Clean and Brake | 04/16/2026…LO
25044-FS06 | MALETA Firing Range | Cole Norona | 203 | 0 | FR ACM | 2026-07-06 | LO | #70 on C&B | 2026-06-23 | AXYZ | Clean and Brake | 04/16/2026…LO
25044-FS07 | MALETA Firing Range | Cole Norona | 160 | 0 | FR ACM | 2026-07-15 | LO | #71 on C&B | 2026-07-02 | AXYZ | Clean and Brake | 04/16/2026…LO
25006-FS11 | MALETA Housing and Dining | Cole Norona | 201 | 0 | FR ACM | 2026-07-15 | LO | #72 on C&B | 2026-07-02 | AXYZ | Clean and Brake | HOAR*04/16/2026…LO
25044-FS08 | MALETA Firing Range | Cole Norona | 163 | 0 | FR ACM | 2026-07-22 | LO | #73 on C&B | 2026-07-09 | AXYZ | Clean and Brake | 04/16/2026…LO
25006-FS12 | MALETA Housing and Dining | Cole Norona | 192 | 0 | FR ACM | 2026-07-27 | LO | #74 on C&B | 2026-07-14 | AXYZ | Clean and Brake | HOAR*04/16/2026…LO
25044-FS09 | MALETA Firing Range | Cole Norona | 86 | 0 | FR ACM | 2026-07-29 | LO | #75 on C&B | 2026-07-16 | AXYZ | Clean and Brake | 04/16/2026…LO
25044-FS01.2 | MALETA Firing Range | Cole Norona | 193 | 0 | FR ACM | 2026-07-29 | LO | #76 on C&B | 2026-07-16 | AXYZ | Clean and Brake | 04/16/2026…LO
25006-FS13 | MALETA Housing and Dining | Cole Norona | 28 | 0 | FR ACM | 2026-08-03 | LO | #77 on C&B | 2026-07-21 | AXYZ | Clean and Brake | HOAR*04/16/2026…LO
25044-FS10 | MALETA Firing Range | Cole Norona | 185 | 0 | FR ACM | 2026-08-07 | LO | #78 on C&B | 2026-07-25 | AXYZ | Clean and Brake | 04/16/2026…LO
25044-FS11 | MALETA Firing Range | Cole Norona | 185 | 0 | FR ACM | 2026-08-17 | LO | #79 on C&B | 2026-08-04 | AXYZ | Clean and Brake | 04/16/2026…LO
25031-RO01 | LLU Mars US Warehouse | Laura Forero | 3 | 3 | FR ACM | 2026-04-22 | CNC Programming | #35 on C&B |  | Clean and Brake | Fab | 04/16/2026…CNC Programming
25006-FS10 | MALETA Housing and Dining | Cole Norona | 140 | 0 | FR ACM | 2026-07-02 | LO | #57 on AXYZ |  | AXYZ | Fab | HOAR*04/16/2026…LO
25075-RP01 | St Thomas West Canopy Replace | Chris Buttrey | 2 | 6 | 0 | 0 | CNC Programming | #80 on C&B |  | AXYZ 34 | Clean and Brake | 04/16/2026…
24051-RP58 | TN Titans Stadium | Marc Ribar | 1 | 0 | 0 | 0 | CNC Programming | #81 on C&B |  | AXYZ 34 | Clean and Brake | 04/16/2026…
24071-RP15 | RS Gass State Lab | Cole Norona | 0 | 3 | 0 | 0 | CNC Programming | #82 on C&B |  | AXYZ 34 | Clean and Brake | 04/16/2026…
Formulas:
Ship Target = IF([ID]="","",IFERROR(VLOOKUP([ID],'Job Operations'!$A4:AA304,9,FALSE),""))
Ship Target = IFERROR(VLOOKUP([ID],'Job Operations'!$A:$I,9,FALSE),"")
Fab Start By = IF([ID]="","",IFERROR(VLOOKUP([ID],'Job Operations'!$A4:AA304,18,FALSE),""))
Fab Start By = IFERROR(VLOOKUP([ID],'Job Operations'!$A:$R,18,FALSE),"")

## Shear Schedule
SEARCH JOB ID:
SHEAR SCHEDULE — Jobs At or Coming to Shear
Includes jobs currently at Shear station AND jobs with Shear as an operation. Sorted by Ship Target date.
ID | Job Name | PM | Panel Qty | Part Qty | Material Type | Ship Target | Current Station | Queue Position | Shear Start By | Next Op | Following Op | Notes
24079-BM04C | Nashville Youth Campus | Joe Hoyle | 0 | 3600 | Steel Sheet | 2026-02-19 | Shear | 1st | 2025-12-18 | Brake | Powder Coat | 04/15/2026…Shear*04/16/2026…Shear
25032-FL01 | Amazon IAD181 | Matt Rassmussen | 0 | 287 | Steel Sheet | 2026-03-27 | Shear | 2nd | 2026-03-13 |  |  | 04/15/2026…Shear*04/16/2026…Shear
24079-BM04D | Nashville Youth Campus | Joe Hoyle | 185 | 1295 | Steel Sheet | 2026-04-13 | TruPunch 5000 | #3 on Shear | 2026-03-30 | Powder Coat | Shear | 04/16/2026…TruPunch 5000
24079-BM01B | Nashville Youth Campus | Joe Hoyle | 0 | 2217 | Galv Sheet | 2026-04-15 | Shear | 4th | 2026-04-01 | TruPunch 5000 |  | 04/15/2026…Shear*04/16/2026…Shear
25061-FL01 | BNA Concourse A | Andre Van Der Merwe | 0 | 48 | Galv Sheet | 2026-04-17 | Cidan | #5 on Shear | 2026-04-03 |  |  | 04/15/2026…Shear*04/16/2026…Cidan
25036-FL22 | TCAT Chattanooga | Josh McPherson | 0 | 10 | Steel Sheet | 2026-04-17 | Sketch Check | #6 on Shear | 2026-04-03 |  |  | 04/16/2026…MUST RUN FRIDAY AND FINISH BY EOS. REFER TO EMAIL.
24039-FL36 | The Visionary | Carlos Silva | 0 | 60 | Alum Sheet | 2026-04-21 | Shear | 7th | 2026-04-07 |  |  | 04/15/2026…Shear*04/16/2026…Shear
24039-FL37 | The Visionary | Carlos Silva | 0 | 16 | Alum Sheet | 2026-04-21 | Shear | 8th | 2026-04-07 |  |  | 04/15/2026…Shear*04/16/2026…Shear
24039-BM19 | The Visionary | Carlos Silva | 0 | 340 | Galv Sheet | 2026-04-21 | Shear | 9th | 2026-04-07 |  |  | 04/15/2026…Shear*04/16/2026…Shear
25022-BM06 | Vantage VA15 | Thomas Mooers | 0 | 500 | Galv Sheet | 2026-04-22 | Shear | 10th | 2026-04-08 |  |  | 04/16/2026…Shear..PLEASE RUN THIS JOB NEXT IN SHEAR/CIDAN CANNOT MISS SHIPDATE
25031-FL08 | LLU Mars US Warehouse | Laura Forero | 0 | 6 | Alum Sheet | 2026-04-22 | Shear | 11st | 2026-04-08 |  |  | 04/16/2026…Shear
25067-FL02 | Harison Bend | Andre Van Der Merwe | 0 | 8 | Alum Sheet | 2026-04-23 | Shear | 12nd | 2026-04-09 |  |  | 04/16/2026…Shear
25065-MU05 | Crosswinds Casino Resort | Matt Rassmussen | 3 | 1 | Steel Sheet | 2026-05-29 | Evaluation | #13 on Shear | 2026-05-15 |  |  | 04/16/2026…Evaluation
25065-MU11 | Crosswinds Casino Resort | Matt Rassmussen | 1 | 1 | Alum Sheet | 2026-05-29 | Evaluation | #14 on Shear | 2026-05-15 |  |  | 04/16/2026…Evaluation
25065-MU12 | Crosswinds Casino Resort | Matt Rassmussen | 0 | 2 | Alum Sheet | 2026-05-29 | Evaluation | #15 on Shear | 2026-05-15 |  |  | 04/16/2026…Evaluation
25065-MU13 | Crosswinds Casino Resort | Matt Rassmussen | 0 | 1 | Alum Sheet | 2026-05-29 | Evaluation | #16 on Shear | 2026-05-15 |  |  | 04/16/2026…Evaluation
25065-MU14 | Crosswinds Casino Resort | Matt Rassmussen | 0 | 3 | Alum Sheet | 2026-05-29 | Evaluation | #17 on Shear | 2026-05-15 |  |  | 04/16/2026…Evaluation
25065-MU15 | Crosswinds Casino Resort | Matt Rassmussen | 0 | 6 | Steel Sheet | 2026-05-29 | Evaluation | #18 on Shear | 2026-05-15 |  |  | 04/16/2026…Evaluation
25065-MU20 | Crosswinds Casino Resort | Matt Rassmussen | 0 | 3 | Steel Sheet | 2026-05-29 | Evaluation | #19 on Shear | 2026-05-15 |  |  | 04/16/2026…Evaluation
Formulas:
Ship Target = IF([ID]="","",VLOOKUP([ID],'Job Operations'!$A:$Z,9,FALSE))

## Cidan Schedule
|  | SEARCH JOB ID: | 24030-BM02 | 🟢 ON TIME |  | Ship:
CIDAN SCHEDULE — Jobs At or Coming to Cidan
Includes jobs currently at Cidan station AND jobs with Cidan as an operation. Sorted by Ship Target date.
ID | Job Name | PM | Panel Qty | Part Qty | Material Type | Ship Target | Current Station | Queue Position | Cidan Start By | Next Op | Following Op | Notes
25032-FL01 | Amazon IAD181 | Matt Rassmussen | 0 | 287 | Steel Sheet | 2026-03-27 | Shear | #1 on Cidan | 2026-03-02 | Shear |  | 04/15/2026…Shear*04/16/2026…Shear
24079-BM01B | Nashville Youth Campus | Joe Hoyle | 0 | 2217 | Galv Sheet | 2026-04-15 | Shear | #2 on Cidan | 2026-03-20 | Shear | TruPunch 5000 | 04/15/2026…Shear*04/16/2026…Shear
25061-FL01 | BNA Concourse A | Andre Van Der Merwe | 0 | 48 | Galv Sheet | 2026-04-17 | Cidan | 3rd | 2026-03-23 | Shear |  | 04/15/2026…Shear*04/16/2026…Cidan
25036-FL22 | TCAT Chattanooga | Josh McPherson | 0 | 10 | Steel Sheet | 2026-04-17 | Sketch Check | #4 on Cidan | 2026-03-23 | Shear |  | 04/16/2026…MUST RUN FRIDAY AND FINISH BY EOS. REFER TO EMAIL.
24039-FL36 | The Visionary | Carlos Silva | 0 | 60 | Alum Sheet | 2026-04-21 | Shear | #5 on Cidan | 2026-03-26 | Shear |  | 04/15/2026…Shear*04/16/2026…Shear
24039-FL37 | The Visionary | Carlos Silva | 0 | 16 | Alum Sheet | 2026-04-21 | Shear | #6 on Cidan | 2026-03-26 | Shear |  | 04/15/2026…Shear*04/16/2026…Shear
24039-BM19 | The Visionary | Carlos Silva | 0 | 340 | Galv Sheet | 2026-04-21 | Shear | #7 on Cidan | 2026-03-26 | Shear |  | 04/15/2026…Shear*04/16/2026…Shear
25022-BM06 | Vantage VA15 | Thomas Mooers | 0 | 500 | Galv Sheet | 2026-04-22 | Shear | #8 on Cidan | 2026-03-27 | Shear |  | 04/16/2026…Shear..PLEASE RUN THIS JOB NEXT IN SHEAR/CIDAN CANNOT MISS SHIPDATE
25031-FL08 | LLU Mars US Warehouse | Laura Forero | 0 | 6 | Alum Sheet | 2026-04-22 | Shear | #9 on Cidan | 2026-03-27 | Shear |  | 04/16/2026…Shear
25067-FL02 | Harison Bend | Andre Van Der Merwe | 0 | 8 | Alum Sheet | 2026-04-23 | Shear | #10 on Cidan | 2026-03-28 | Shear |  | 04/16/2026…Shear
25065-MU05 | Crosswinds Casino Resort | Matt Rassmussen | 3 | 1 | Steel Sheet | 2026-05-29 | Evaluation | #11 on Cidan | 2026-05-04 | Shear |  | 04/16/2026…Evaluation
25065-MU11 | Crosswinds Casino Resort | Matt Rassmussen | 1 | 1 | Alum Sheet | 2026-05-29 | Evaluation | #12 on Cidan | 2026-05-04 | Shear |  | 04/16/2026…Evaluation
25065-MU12 | Crosswinds Casino Resort | Matt Rassmussen | 0 | 2 | Alum Sheet | 2026-05-29 | Evaluation | #13 on Cidan | 2026-05-04 | Shear |  | 04/16/2026…Evaluation
25065-MU13 | Crosswinds Casino Resort | Matt Rassmussen | 0 | 1 | Alum Sheet | 2026-05-29 | Evaluation | #14 on Cidan | 2026-05-04 | Shear |  | 04/16/2026…Evaluation
25065-MU14 | Crosswinds Casino Resort | Matt Rassmussen | 0 | 3 | Alum Sheet | 2026-05-29 | Evaluation | #15 on Cidan | 2026-05-04 | Shear |  | 04/16/2026…Evaluation
25065-MU15 | Crosswinds Casino Resort | Matt Rassmussen | 0 | 6 | Steel Sheet | 2026-05-29 | Evaluation | #16 on Cidan | 2026-05-04 | Shear |  | 04/16/2026…Evaluation
25065-MU20 | Crosswinds Casino Resort | Matt Rassmussen | 0 | 3 | Steel Sheet | 2026-05-29 | Evaluation | #17 on Cidan | 2026-05-04 | Shear |  | 04/16/2026…Evaluation
Formulas:
Ship Target = IF([ID]="","",IFERROR(VLOOKUP([ID],'Job Operations'!A:I,9,FALSE),""))
Ship Target = IF([ID]="","",VLOOKUP([ID],'Job Operations'!A:I,9,FALSE))
Cidan Start By = IF([ID]="","",IFERROR(IF(VLOOKUP([ID],'Job Operations'!A:M,13,FALSE)="Cidan",VLOOKUP([ID],'Job Operations'!A:N,14,FALSE),IF(VLOOKUP([ID],'Job Operations'!A:O,15,FALSE)="Cidan",VLOOKUP([ID],'Job Operations'!A:P,16,FALSE),"")),""))

## Extrusion Saw Schedule
SEARCH JOB ID:
EXTRUSION SAW SCHEDULE — Jobs At or Coming to Extrusion Saw
Includes jobs currently at Extrusion Saw station AND jobs with Extrusion Saw as an operation. Sorted by Start By date.
ID | Job Name | PM | Panel Qty | Part Qty | Material Type | Ship Target | Current Station | Queue Position | Saw Start By | Next Op | Notes
1040-30791-ST09 | AFI - YANCEY | Hannah Sadloski, Lisa Ellison | 0 | 185 | Alum Tube | 2026-04-10 | Assembly | Assembly | 2026-04-04 | Assembly | 04/16/2026…Assembly
1040-30791-ST10 | AFI - YANCEY | Hannah Sadloski, Lisa Ellison | 0 | 185 | Alum Tube | 2026-04-24 | Extrusion Saw | 1st | 2026-04-18 | Assembly
Formulas:
Saw Start By = IF([ID]="","",[Ship Target]-6)

## Punch Schedule
SEARCH JOB ID:
PUNCH SCHEDULE — Jobs At or Coming to Punch
Includes jobs currently at Punch station AND jobs with Punch as an operation. Sorted by Start By date.
ID | Job Name | PM | Panel Qty | Part Qty | Material Type | Ship Target | Current Station | Queue Position | Punch Start By | Next Op | Notes
24079-BM04D | Nashville Youth Campus | Joe Hoyle | 185 | 1295 | Steel Sheet | 2026-04-13 | TruPunch 5000 | #1 on Punch | 2026-03-30 | Powder Coat | 04/16/2026…TruPunch 5000
24079-BM01B | Nashville Youth Campus | Joe Hoyle | 0 | 2217 | Galv Sheet | 2026-04-15 | Shear | #2 on Punch | 2026-04-01 | Shear | 04/15/2026…Shear*04/16/2026…Shear
25029-FS50 | Lourdes CC Phase 2 | Dillon Bowman | 8 | 4 | Alum Sheet | 2026-05-11 | Correction | #3 on Punch | 2026-04-27 | Punch | 04/16/2026…Correction
24073-FS01 | DIDD Perf | Dillon Bowman | 53 | 0 | Alum Sheet | 2026-05-22 | Sketch | #4 on Punch | 2026-05-08 | Post Paint | 04/16/2026…Sketch
Formulas:
Ship Target = IF([ID]="","",IFERROR(VLOOKUP([ID],'Job Operations'!A:I,9,FALSE),""))
Punch Start By = IF([ID]="","",IFERROR(VLOOKUP([ID],'Job Operations'!A:I,9,FALSE)-14,""))

## Roller Schedule
SEARCH JOB ID:
ROLLER SCHEDULE — Jobs At or Coming to Roller
Includes jobs currently at Roller station AND jobs with Roller as an operation. Sorted by Start By date.
ID | Job Name | PM | Panel Qty | Part Qty | Material Type | Ship Target | Current Station | Queue Position | Roller Start By | Next Op | Notes
No Roller jobs found | [7 empty] | 0

## Ship Schedule
SHIP SCHEDULE — Jobs by Ship Date (Bottleneck Analysis) | [7 empty] | Summary Statistics
Shows all jobs grouped by ship date to identify shipping bottlenecks. Sorted by Ship Target date. | [7 empty] | Total Jobs: | 286
Legend: | 🔴 5+ jobs = High bottleneck |  | 🟡 3-4 jobs = Medium load |  | ⚪ 1-2 jobs = Normal |  |  | Unique Ship Dates: | 138
Ship Date | Job ID | Job Name | PM | Panel Qty | Part Qty | Current Station | Jobs on This Date | High Bottleneck Dates: | 12
2025-02-21 | 24060-BM01 | Loves Blacksburg | Cole Norona | 0 | 14 | Ready to Ship | 1 | Max Jobs/Day: | 13
2025-03-03 | 24001-BM14 | McEwen Northside | Josh McPherson | 0 | 12 | Ready to Ship | 1
2025-03-31 | 24051-FS01 | TN Titans Stadium | Marc Ribar | 160 | 160 | RTS Titans | 1 | Top Bottleneck Dates ⬇️ (Select below) |  |  | All Ship Dates
2025-04-17 | 24051-FS02 | TN Titans Stadium | Marc Ribar | 158 | 158 | RTS Titans | 1 | Date | Jobs |  | 2025-02-21
2025-04-18 | 24051-FS03 | TN Titans Stadium | Marc Ribar | 160 | 160 | RTS Titans | 1 | 2025-07-01 | 6 |  | 2025-03-03
2025-04-22 | 24051-FS04 | TN Titans Stadium | Marc Ribar | 153 | 153 | Partially Shipped | 2 | 2026-02-02 | 5 |  | 2025-03-31
2025-04-22 | 24051-FS05 | TN Titans Stadium | Marc Ribar | 153 | 153 | Partially Shipped | 2 | 2026-02-09 | 5 |  | 2025-04-17
2025-04-23 | 24051-FS06 | TN Titans Stadium | Marc Ribar | 153 | 153 | Partially Shipped | 1 | 2026-02-20 | 7 |  | 2025-04-18
2025-05-06 | 24051-FS10 | TN Titans Stadium | Marc Ribar | 160 | 160 | RTS Titans | 1 | 2026-02-27 | 6 |  | 2025-04-22
2025-05-07 | 24051-FS11 | TN Titans Stadium | Marc Ribar | 160 | 160 | RTS Titans | 1 | 2026-03-16 | 13 |  | 2025-04-23
2025-05-14 | 24051-FS12 | TN Titans Stadium | Marc Ribar | 160 | 160 | RTS Titans | 1 | 2026-04-15 | 10 |  | 2025-05-06
2025-05-19 | 24051-FS13 | TN Titans Stadium | Marc Ribar | 110 | 110 | RTS Titans | 1 | 2026-04-17 | 8 |  | 2025-05-07
2025-05-21 | 24051-FS14 | TN Titans Stadium | Marc Ribar | 110 | 110 | RTS Titans | 1 | 2026-04-21 | 5 |  | 2025-05-14
2025-05-22 | 24051-FS15 | TN Titans Stadium | Marc Ribar | 110 | 110 | RTS Titans | 1 | 2026-04-24 | 8 |  | 2025-05-19
2025-06-02 | 24051-FS25 | TN Titans Stadium | Marc Ribar | 50 | 50 | RTS Titans | 2 | (Snapshot - filter main data for updates) |  |  | 2025-05-21
2025-06-02 | 24051-FS26 | TN Titans Stadium | Marc Ribar | 169 | 169 | RTS Titans | 2 |  |  |  | 2025-05-22
2025-06-11 | 24051-FS212 | TN Titans Stadium | Marc Ribar | 26 | 26 | RTS Titans | 3 | Today's Date- | 2026-04-16 |  | 2025-06-02
2025-06-11 | 24051-FS29 | TN Titans Stadium | Marc Ribar | 78 | 78 | RTS Titans | 3 | Jobs Due To Ship Today- | 2 |  | 2025-06-11
2025-06-11 | 24051-FS30 | TN Titans Stadium | Marc Ribar | 128 | 128 | RTS Titans | 3 |  |  |  | 2025-06-12
2025-06-12 | 24051-FS31 | TN Titans Stadium | Marc Ribar | 128 | 128 | RTS Titans | 1 | 24074-FS06 |  |  | 2025-06-13
2025-06-13 | 24051-FS32 | TN Titans Stadium | Marc Ribar | 128 | 128 | RTS Titans | 1 | 26014-04-ST02 |  |  | 2025-06-17
2025-06-17 | 24082-FL03 | GTN Cable | Josh McPherson, Nick Akins | 0 | 32 | Ready to Ship | 1 |  |  |  | 2025-06-18
2025-06-18 | 24051-FS33 | TN Titans Stadium | Marc Ribar | 161 | 161 | RTS Titans | 2 | 👆 Select ANY date to see jobs shipping that day |  |  | 2025-06-19
2025-06-18 | 24051-BM01 | TN Titans Stadium | Marc Ribar | 0 | 1900 | RTS Titans | 2 | Select Ship Date: | 2025-04-17 |  | 2025-06-20
2025-06-19 | 24051-FS200 | TN Titans Stadium | Marc Ribar | 131 | 131 | RTS Titans | 2 | Jobs on Selected Date: | 1 |  | 2025-06-25
2025-06-19 | 24051-FS34 | TN Titans Stadium | Marc Ribar | 161 | 161 | RTS Titans | 2 | Job ID |  |  | 2025-07-01
2025-06-20 | 24051-FS35 | TN Titans Stadium | Marc Ribar | 160 | 160 | RTS Titans | 1 | Jobs Shipping on Selected Date: | Job Name | Station | 2025-07-03
2025-06-25 | 24051-FS206 | TN Titans Stadium | Marc Ribar | 72 | 72 | RTS Titans | 1 | 24051-FS02 | TN Titans Stadium | RTS Titans | 2025-07-11
2025-07-01 | 25016-MU101 | Rockdale CJAC | Dillon Bowman | 4 | 5 | Ready to Ship | 6 |  |  |  | 2025-07-14
2025-07-01 | 25016-MU103 | Rockdale CJAC | Dillon Bowman | 0 | 8 | Ready to Ship | 6 |  |  |  | 2025-07-15
2025-07-01 | 25016-MU121 | Rockdale CJAC | Dillon Bowman | 1 | 1 | Ready to Ship | 6 |  |  |  | 2025-07-18
2025-07-01 | 25016-MU122 | Rockdale CJAC | Dillon Bowman | 0 | 2 | Ready to Ship | 6 |  |  |  | 2025-07-22
2025-07-01 | 25016-MU123 | Rockdale CJAC | Dillon Bowman | 0 | 2 | Ready to Ship | 6 |  |  |  | 2025-07-23
2025-07-01 | 24051-FS01C | TN Titans Stadium | Marc Ribar | 160 | 160 | RTS Titans | 6 |  |  |  | 2025-07-31
2025-07-03 | 24051-FS10C | TN Titans Stadium | Marc Ribar | 160 | 160 | RTS Titans | 1 |  |  |  | 2025-08-04
2025-07-11 | 24051-FS33C | TN Titans Stadium | Marc Ribar | 161 | 161 | RTS Titans | 1 |  |  |  | 2025-08-06
2025-07-14 | 24051-FS37 | TN Titans Stadium | Marc Ribar | 24 | 24 | RTS Titans | 3 |  |  |  | 2025-08-08
2025-07-14 | 24051-FS38 | TN Titans Stadium | Marc Ribar | 90 | 90 | RTS Titans | 3 |  |  |  | 2025-08-13
2025-07-14 | 24051-FS39 | TN Titans Stadium | Marc Ribar | 96 | 96 | RTS Titans | 3 |  |  |  | 2025-08-14
2025-07-15 | 24051-FS40 | TN Titans Stadium | Marc Ribar | 96 | 96 | RTS Titans | 1 |  |  |  | 2025-08-18
2025-07-18 | 24020-FL07 | QTS ATL2 DC2 Osgood | Dillon Bowman | 2 | 2 | Ready to Ship | 1 |  |  |  | 2025-08-25
2025-07-22 | 24051-FS41 | TN Titans Stadium | Marc Ribar | 96 | 96 | RTS Titans | 1 |  |  |  | 2025-08-28
2025-07-23 | 25028-FS01 | TN Soybean Council | Cole Norona | 26 | 26 | Ready to Ship | 1 |  |  |  | 2025-09-08
2025-07-31 | 24051-FS36 | TN Titans Stadium | Marc Ribar | 84 | 84 | RTS Titans | 2 |  |  |  | 2025-09-16
2025-07-31 | 24051-FS215 | TN Titans Stadium | Marc Ribar | 14 | 14 | RTS Titans | 2 |  |  |  | 2025-09-23
2025-08-04 | 24051-FS43 | TN Titans Stadium | Marc Ribar | 160 | 160 | RTS Titans | 1 |  |  |  | 2025-11-17
2025-08-06 | 24057-BM10 | Rowan BWI 150 | Dillon Bowman | 0 | 11 | Ready to Ship | 2 |  |  |  | 2025-11-21
2025-08-06 | 24057-FL10 | Rowan BWI 150 | Dillon Bowman | 0 | 7 | Ready to Ship | 2 |  |  |  | 2025-11-24
2025-08-08 | 25028-FL02 | TN Soybean Council | Cole Norona | 0 | 4 | Ready to Ship | 1 |  |  |  | 2025-11-26
2025-08-13 | 24051-FS42 | TN Titans Stadium | Marc Ribar | 120 | 120 | RTS Titans | 1 |  |  |  | 2025-12-03
2025-08-14 | 24051-RP11 | TN Titans Stadium | Marc Ribar | 1 | 1 | RTS Titans | 1 |  |  |  | 2025-12-05
2025-08-18 | 24051-FS44 | TN Titans Stadium | Marc Ribar | 120 | 120 | RTS Titans | 1 |  |  |  | 2025-12-06
2025-08-25 | 24051-RP16 | TN Titans Stadium | Marc Ribar | 5 | 5 | RTS Titans | 1 |  |  |  | 2025-12-08
2025-08-28 | 24048-RM02 | QTS NAL2 DC1 | Joe Hoyle | 3 | 3 | Ready to Ship | 1 |  |  |  | 2025-12-12
2025-09-08 | 25016-BM201 | Rockdale CJAC | Dillon Bowman | 12 | 12 | Ready to Ship | 2 |  |  |  | 2025-12-15
2025-09-08 | 25016-FL200 | Rockdale CJAC | Dillon Bowman | 8 | 8 | Ready to Ship | 2 |  |  |  | 2025-12-17
2025-09-16 | 24046-FL12 | UAB Biomedical Research and Psycholgy | Wylie McDougall | 0 | 119 | Ready to Ship | 2 |  |  |  | 2025-12-30
2025-09-16 | 24046-FL13 | UAB Biomedical Research and Psycholgy | Wylie McDougall | 0 | 53 | Ready to Ship | 2 |  |  |  | 2026-01-02
2025-09-23 | 24051-RP20 | TN Titans Stadium | Marc Ribar | 46 | 46 | RTS Titans | 1 |  |  |  | 2026-01-05
2025-11-17 | 24051-FS45C | TN Titans Stadium | Marc Ribar | 26 | 26 | RTS Titans | 1 |  |  |  | 2026-01-06
2025-11-21 | 24051-FS201 | TN Titans Stadium | Marc Ribar | 109 | 109 | RTS Titans | 2 |  |  |  | 2026-01-08
2025-11-21 | 24051-FS205 | TN Titans Stadium | Marc Ribar | 118 | 118 | RTS Titans | 2 |  |  |  | 2026-01-13
2025-11-24 | 24051-FS213 | TN Titans Stadium | Marc Ribar | 138 | 138 | RTS Titans | 2 |  |  |  | 2026-01-14
2025-11-24 | 24051-FS216 | TN Titans Stadium | Marc Ribar | 26 | 26 | RTS Titans | 2 |  |  |  | 2026-01-15
2025-11-26 | 24051-FS45 | TN Titans Stadium | Marc Ribar | 78 | 78 | RTS Titans | 1 |  |  |  | 2026-01-16
2025-12-03 | 24051-FS219 | TN Titans Stadium | Marc Ribar | 109 | 109 | RTS Titans | 1 |  |  |  | 2026-01-19
2025-12-05 | 24051-FS217 | TN Titans Stadium | Marc Ribar | 12 | 12 | RTS Titans | 2 |  |  |  | 2026-01-20
2025-12-05 | 24051-FS218 | TN Titans Stadium | Marc Ribar | 97 | 97 | RTS Titans | 2 |  |  |  | 2026-01-21
2025-12-06 | 25014-11-ST01 | R&D | TBC | 0 | 1 | Ready to Ship | 2 |  |  |  | 2026-01-22
2025-12-06 | 25014-11-ST02 | R&D | TBC | 0 | 232 | Ready to Ship | 2 |  |  |  | 2026-01-23
2025-12-08 | 24051-FS46C | TN Titans Stadium | Marc Ribar | 25 | 25 | RTS Titans | 2 |  |  |  | 2026-01-26
2025-12-08 | 24051-FS46 | TN Titans Stadium | Marc Ribar | 75 | 75 | RTS Titans | 2 |  |  |  | 2026-01-30
2025-12-12 | 24051-FS47C | TN Titans Stadium | Marc Ribar | 99 | 99 | RTS Titans | 2 |  |  |  | 2026-02-02
2025-12-12 | 24051-FS48 | TN Titans Stadium | Marc Ribar | 124 | 124 | RTS Titans | 2 |  |  |  | 2026-02-05
2025-12-15 | 24051-FS49 | TN Titans Stadium | Marc Ribar | 124 | 124 | RTS Titans | 3 |  |  |  | 2026-02-06
2025-12-15 | 24051-FS50 | TN Titans Stadium | Marc Ribar | 124 | 124 | RTS Titans | 3 |  |  |  | 2026-02-09
2025-12-15 | 24051-FS50C | TN Titans Stadium | Marc Ribar | 24 | 24 | RTS Titans | 3 |  |  |  | 2026-02-10
2025-12-17 | 25029-FL97 | Lourdes CC Phase 2 | Dillon Bowman | 0 | 1 | Ready to Ship | 1 |  |  |  | 2026-02-11
2025-12-30 | 25040-FL01 | Moses Lincoln Vitrine | Laura Forero | 0 | 1 | Ready to Ship | 1 |  |  |  | 2026-02-12
2026-01-02 | 24051-FS59 | TN Titans Stadium | Marc Ribar | 158 | 158 | RTS Titans | 1 |  |  |  | 2026-02-13
2026-01-05 | 25007-BM03 | QTS ATL2 DC10 | Nick Akins | 0 | 80 | Ready to Ship | 2 |  |  |  | 2026-02-16
2026-01-05 | 25052-BM01 | TEMA Warehouse | Andre Van Der Merwe | 0 | 16 | Ready to Ship | 2 |  |  |  | 2026-02-18
2026-01-06 | 24051-FS51C | TN Titans Stadium | Marc Ribar | 40 | 40 | RTS Titans | 1 |  |  |  | 2026-02-19
2026-01-08 | 24051-FS51 | TN Titans Stadium | Marc Ribar | 120 | 120 | RTS Titans | 1 |  |  |  | 2026-02-20
2026-01-13 | 24051-FS52C | TN Titans Stadium | Marc Ribar | 70 | 70 | RTS Titans | 2 |  |  |  | 2026-02-23
2026-01-13 | 24051-FS52 | TN Titans Stadium | Marc Ribar | 210 | 210 | RTS Titans | 2 |  |  |  | 2026-02-25
2026-01-14 | 25017-FL99 | Nashville Yards Park | Dillon Bowman | 0 | 2 | Ready to Ship | 1 |  |  |  | 2026-02-26
2026-01-15 | 25052-FL01 | TEMA Warehouse | Andre Van Der Merwe | 0 | 10 | Ready to Ship | 1 |  |  |  | 2026-02-27
2026-01-16 | 23028-FS99 | 1000 Church YMCA | Dillon Bowman | 1 | 1 | Ready to Ship | 1 |  |  |  | 2026-03-02
2026-01-19 | 24051-FS67 | TN Titans Stadium | Marc Ribar | 14 | 14 | RTS Titans | 1 |  |  |  | 2026-03-03
2026-01-20 | 25017-ST02 | Nashville Yards Park | Dillon Bowman | 0 | 16 | QC | 1 |  |  |  | 2026-03-04
2026-01-21 | 24051-FS54 | TN Titans Stadium | Marc Ribar | 149 | 149 | RTS Titans | 3 |  |  |  | 2026-03-06
2026-01-21 | 24051-FS53 | TN Titans Stadium | Marc Ribar | 48 | 48 | RTS Titans | 3 |  |  |  | 2026-03-12
2026-01-21 | 24019-RO07 | QTS PJC1 DC1 | Dillon Bowman | 4 | 4 | Ready to Ship | 3 |  |  |  | 2026-03-13
2026-01-22 | 26014-02-ST01 | 2026 R & D | TBC | 0 | 10 | QC | 2 |  |  |  | 2026-03-16
2026-01-22 | 24051-FS55 | TN Titans Stadium | Marc Ribar | 149 | 149 | RTS Titans | 2 |  |  |  | 2026-03-20
2026-01-26 | 24071-FS10.R | RS Gass State Lab | Cole Norona | 0 | 0 | Ready to Ship | 1 |  |  |  | 2026-03-23
2026-01-30 | 24051-FS56 | TN Titans Stadium | Marc Ribar | 149 | 149 | RTS Titans | 2 |  |  |  | 2026-03-24
2026-01-30 | 24030-FL02 | Vantage TX-21 | Chris Buttrey | 0 | 265 | Partially Shipped | 2 |  |  |  | 2026-03-26
2026-02-02 | 24051-FS46.1 | TN Titans Stadium | Marc Ribar | 56 | 56 | RTS Titans | 5 |  |  |  | 2026-03-27
2026-02-02 | 24051-FS72 | TN Titans Stadium | Marc Ribar | 104 | 104 | RTS Titans | 5 |  |  |  | 2026-03-30
2026-02-02 | 24051-FS73 | TN Titans Stadium | Marc Ribar | 66 | 66 | RTS Titans | 5 |  |  |  | 2026-03-31
2026-02-02 | 24051-FS56C | TN Titans Stadium | Marc Ribar | 149 | 149 | RTS Titans | 5 |  |  |  | 2026-04-03
2026-02-02 | 24051-FS74 | TN Titans Stadium | Marc Ribar | 39 | 39 | RTS Titans | 5 |  |  |  | 2026-04-06
2026-02-05 | 24051-FS25.1 FM | TN Titans Stadium | Marc Ribar | 2 | 2 | RTS Titans | 1 |  |  |  | 2026-04-07
2026-02-06 | 24051-BM02 | TN Titans Stadium | Marc Ribar | 0 | 141 | RTS Titans | 1 |  |  |  | 2026-04-08
2026-02-09 | 24051-FS221 | TN Titans Stadium | Marc Ribar | 13 | 13 | RTS Titans | 5 |  |  |  | 2026-04-10
2026-02-09 | 24051-FS43.1 | TN Titans Stadium | Marc Ribar | 30 | 30 | RTS Titans | 5 |  |  |  | 2026-04-13
2026-02-09 | 24051-FS16C | TN Titans Stadium | Marc Ribar | 27 | 27 | RTS Titans | 5 |  |  |  | 2026-04-14
2026-02-09 | 24051-FS76 | TN Titans Stadium | Marc Ribar | 152 | 152 | RTS Titans | 5 |  |  |  | 2026-04-15
2026-02-09 | 24051-FS77 | TN Titans Stadium | Marc Ribar | 209 | 209 | RTS Titans | 5 |  |  |  | 2026-04-16
2026-02-10 | 24039-FS14 | The Visionary | Carlos Silva | 176 | 197 | Partially Shipped | 1 |  |  |  | 2026-04-17
2026-02-11 | 24051-FS58 | TN Titans Stadium | Marc Ribar | 158 | 158 | RTS Titans | 1 |  |  |  | 2026-04-20
2026-02-12 | 24051-FS57 | TN Titans Stadium | Marc Ribar | 158 | 158 | RTS Titans | 2 |  |  |  | 2026-04-24
2026-02-12 | 24039-FS15 | The Visionary | Carlos Silva | 73 | 99 | Partially Shipped | 2 |  |  |  | 2026-04-28
2026-02-13 | 24051-FS42.1 | TN Titans Stadium | Marc Ribar | 98 | 98 | RTS Titans | 4 |  |  |  | 2026-04-30
2026-02-13 | 24051-FS75 | TN Titans Stadium | Marc Ribar | 83 | 83 | RTS Titans | 4 |  |  |  | 2026-05-01
2026-02-13 | 24051-FS78 | TN Titans Stadium | Marc Ribar | 180 | 180 | RTS Titans | 4 |  |  |  | 2026-05-04
2026-02-13 | 24051-FS78.1 | TN Titans Stadium | Marc Ribar | 168 | 168 | RTS Titans | 4 |  |  |  | 2026-05-05
2026-02-16 | 24051-FS59C | TN Titans Stadium | Marc Ribar | 158 | 158 | RTS Titans | 2 |  |  |  | 2026-05-07
2026-02-16 | 24026-BM01 | 1740 Division | Chris Buttrey | 0 | 200 | Ready to Ship | 2 |  |  |  | 2026-05-11
2026-02-18 | 25008-FS05 | Columbia State Tech Center | Laura Forero | 101 | 101 | Shipped To Painter | 1 |  |  |  | 2026-05-14
2026-02-19 | 24079-BM04C | Nashville Youth Campus | Joe Hoyle | 0 | 3600 | Shear | 4 |  |  |  | 2026-05-15
2026-02-19 | 24079-FL07 | Nashville Youth Campus | Joe Hoyle | 0 | 220 | Ready to Ship | 4 |  |  |  | 2026-05-18
2026-02-19 | 24079-FL08 | Nashville Youth Campus | Joe Hoyle | 0 | 160 | Ready to Ship | 4 |  |  |  | 2026-05-20
2026-02-19 | 24079-FL09 | Nashville Youth Campus | Joe Hoyle | 0 | 295 | Ready to Ship | 4 |  |  |  | 2026-05-21
2026-02-20 | 24081-FS01 | DLR DFW37 | Cole Norona | 109 | 308 | Shipped To Painter | 7 |  |  |  | 2026-05-22
2026-02-20 | 24081-FS02 | DLR DFW37 | Cole Norona | 123 | 349 | Shipped To Painter | 7 |  |  |  | 2026-05-25
2026-02-20 | 24081-FS03 | DLR DFW37 | Cole Norona | 24 | 88 | Shipped To Painter | 7 |  |  |  | 2026-05-26
2026-02-20 | 24081-FS04 | DLR DFW37 | Cole Norona | 94 | 243 | Shipped To Painter | 7 |  |  |  | 2026-05-29
2026-02-20 | 24081-FS05 | DLR DFW37 | Cole Norona | 111 | 345 | Shipped To Painter | 7 |  |  |  | 2026-05-31
2026-02-20 | 24081-FL01 | DLR DFW37 | Cole Norona | 0 | 118 | Shipped To Painter | 7 |  |  |  | 2026-06-03
2026-02-20 | 24051-FS78.2 | TN Titans Stadium | Marc Ribar | 348 | 348 | RTS Titans | 7 |  |  |  | 2026-06-08
2026-02-23 | 24079-FS101 | Nashville Youth Campus | Joe Hoyle | 173 | 176 | Ready to Ship | 2 |  |  |  | 2026-06-10
2026-02-23 | 24079-FS101.1 | Nashville Youth Campus | Joe Hoyle | 163 | 189 | Ready to Ship | 2 |  |  |  | 2026-06-12
2026-02-25 | 25025-BM100 | QTS MAN1 DC6 | Dillon Bowman | 0 | 870 | Shipped | 1 |  |  |  | 2026-06-19
2026-02-26 | 25035-FS02.1 | Titans Jabez | Marc Ribar | 0 | 27 | RTS Titans | 2 |  |  |  | 2026-06-26
2026-02-26 | 26014-03-ST01 | 2026 R & D | TBC | 0 | 3 | 7000 TubeLaser 20 | 2 |  |  |  | 2026-07-06
2026-02-27 | 25035-FS02 | Titans Jabez | Marc Ribar | 109 | 600 | Shipped To Painter | 6 |  |  |  | 2026-07-15
2026-02-27 | 24081-FL02 | DLR DFW37 | Cole Norona | 0 | 78 | Shipped To Painter | 6 |  |  |  | 2026-07-22
2026-02-27 | 26014-03-ST02 | 2026 R & D | TBC | 0 | 9 | TruLaser 3040 | 6 |  |  |  | 2026-07-29
2026-02-27 | 26014-03-ST02.1 | 2026 R & D | TBC | 0 | 10 | 7000 TubeLaser 20 | 6 |  |  |  | 2026-08-07
2026-02-27 | 26014-03-ST03 | 2026 R & D | TBC | 0 | 8 | 7000 TubeLaser 20 | 6 |  |  |  | 2026-08-17
2026-02-27 | 26014-03-ST03.1 | 2026 R & D | TBC | 0 | 6 | TruLaser 3040 | 6
2026-03-02 | 24051-FS209.1 | TN Titans Stadium | Marc Ribar | 36 | 76 | RTS Titans | 2
2026-03-02 | 25002-FS11.1 | Med Center Health | Carlos Silva | 18 | 18 | Clean and Brake | 2
2026-03-04 | 24051-FS86 | TN Titans Stadium | Marc Ribar | 38 | 38 | RTS Titans | 2
2026-03-04 | 25002-BM06 | Med Center Health | Carlos Silva | 0 | 29 | Shipped To Painter | 2
2026-03-06 | 25035-FS03 | Titans Jabez | Marc Ribar | 160 | 320 | Shipped To Painter | 2
2026-03-06 | 23028-FL205 | 1000 Church YMCA | Dillon Bowman | 0 | 4 | Ready to Ship | 2
2026-03-12 | 24051-FS71.1 | TN Titans Stadium | Marc Ribar | 0 | 0 | RTS Titans | 1
2026-03-13 | 25029-MU02 | Lourdes CC Phase 2 | Dillon Bowman | 1 | 1 | TruLaser 3040 | 2
2026-03-13 | 25029-MU03 | Lourdes CC Phase 2 | Dillon Bowman | 0 | 2 | TruLaser 3040 | 2
2026-03-16 | 24051-FS223 | TN Titans Stadium | Marc Ribar | 44 | 90 | Clean and Brake | 13
2026-03-16 | 24051-FS224 | TN Titans Stadium | Marc Ribar | 2 | 2 | RTS Titans | 13
2026-03-16 | 24051-FS29C | TN Titans Stadium | Marc Ribar | 26 | 26 | RTS Titans | 13
2026-03-16 | 24051-FS82 | TN Titans Stadium | Marc Ribar | 4 | 4 | RTS Titans | 13
2026-03-16 | 24051-FS83 | TN Titans Stadium | Marc Ribar | 4 | 4 | RTS Titans | 13
2026-03-16 | 24051-FS84 | TN Titans Stadium | Marc Ribar | 24 | 24 | RTS Titans | 13
2026-03-16 | 24051-FS85 | TN Titans Stadium | Marc Ribar | 4 | 4 | RTS Titans | 13
2026-03-16 | 24079-FS03 | Nashville Youth Campus | Joe Hoyle | 33 | 0 | Evaluation | 13
2026-03-16 | 24079-FS102 | Nashville Youth Campus | Joe Hoyle | 192 | 198 | Sketch Check | 13
2026-03-16 | 24051-FS26C | TN Titans Stadium | Marc Ribar | 26 | 26 | RTS Titans | 13
2026-03-16 | 24051-FS225 | TN Titans Stadium | Marc Ribar | 26 | 0 | LO | 13
2026-03-16 | 25017-RO01 | Nashville Yards Park | Dillon Bowman | 1 | 3 | Ready to Ship | 13
2026-03-16 | 24079-FS102.1 | Nashville Youth Campus | Joe Hoyle | 308 | 0 | Sketch | 13
2026-03-20 | 24051-FS13C | TN Titans Stadium | Marc Ribar | 106 | 106 | RTS Titans | 2
2026-03-20 | 1040-30791-ST08 | AFI - YANCEY | Hannah Sadloski, Lisa Ellison | 0 | 120 | Ready to Ship | 2
2026-03-23 | 25035-FS04 | Titans Jabez | Marc Ribar | 218 | 0 | Sketch | 3
2026-03-23 | 26011-ST01 | 2nd Ave Mockup Build | Wylie McDougall | 0 | 4 | TruLaser 3040 | 3
2026-03-23 | 26011-ST1.1 | 2nd Ave Mockup Build | Wylie McDougall | 0 | 1 | 7000 TubeLaser 20 | 3
2026-03-26 | 24051-FS76.1 | TN Titans Stadium | Marc Ribar | 74 | 74 | RTS Titans | 2
2026-03-26 | 24081-RO01 | DLR DFW37 | Cole Norona | 1 | 1 | Shipped To Painter | 2
2026-03-27 | 25032-FL01 | Amazon IAD181 | Matt Rassmussen | 0 | 287 | Shear | 2
2026-03-27 | 25029-MU10 | Lourdes CC Phase 2 | Dillon Bowman | 1 | 1 | TruLaser 3040 | 2
2026-03-30 | 24079-FS04 | Nashville Youth Campus | Joe Hoyle | 173 | 0 | Evaluation | 2
2026-03-30 | 24069-RM04 | TCAT Pulaski | Chris Buttrey | 1 | 1 | Shipped To Painter | 2
2026-04-06 | 25022-FS11 | Vantage VA15 | Thomas Mooers | 72 | 72 | Ready to Ship | 3
2026-04-06 | 26014-04-ST01 | 2026 R & D | TBC | 0 | 8 | 7000 TubeLaser 20 | 3
2026-04-06 | 26014-04-FS01 | 2026 R & D | TBC | 4 | 4 | 7000 TruMatic | 3
2026-04-07 | 25022-FS07 | Vantage VA15 | Thomas Mooers | 52 | 0 | Ready to Ship | 3
2026-04-07 | 25022-FS10 | Vantage VA15 | Thomas Mooers | 200 | 200 | Ready to Ship | 3
2026-04-07 | 25031-FL06 | LLU Mars US Warehouse | Laura Forero | 0 | 2 | Shipped | 3
2026-04-08 | 25022-FS08 | Vantage VA15 | Thomas Mooers | 60 | 60 | Ready to Ship | 1
2026-04-10 | 24079-FL13 | Nashville Youth Campus | Joe Hoyle | 0 | 146 | Ready to Ship | 2
2026-04-10 | 1040-30791-ST09 | AFI - YANCEY | Hannah Sadloski, Lisa Ellison | 0 | 185 | Assembly | 2
2026-04-13 | 24079-BM04D | Nashville Youth Campus | Joe Hoyle | 185 | 1295 | TruPunch 5000 | 2
2026-04-13 | 25005-ST02 | CAT Financial Nashville HQ | Chris Buttrey | 0 | 4 | TruLaser 3040 | 2
2026-04-14 | 25012-MU07 | St Jude Hospital | Wylie McDougall | 8 | 8 | Clean and Brake | 2
2026-04-14 | 26014-05-FS01 | 2026 R & D | TBC | 25 | 25 | Ready to Ship | 2
2026-04-15 | 24071-FS11 | RS Gass State Lab | Cole Norona | 50 | 69 | Crating | 10
2026-04-15 | 24051-FS87 | TN Titans Stadium | Marc Ribar | 54 | 54 | Clean and Brake | 10
2026-04-15 | 24051-FS88 | TN Titans Stadium | Marc Ribar | 78 | 78 | RTS Titans | 10
2026-04-15 | 24051-FS89 | TN Titans Stadium | Marc Ribar | 40 | 40 | AXYZ 34 | 10
2026-04-15 | 24051-FS36.2 | TN Titans Stadium | Marc Ribar | 38 | 38 | Fabrication | 10
2026-04-15 | 24051-FS226 | TN Titans Stadium | Marc Ribar | 26 | 26 | Fabrication | 10
2026-04-15 | 24079-BM01B | Nashville Youth Campus | Joe Hoyle | 0 | 2217 | Shear | 10
2026-04-15 | 25017-RO02 | Nashville Yards Park | Dillon Bowman | 1 | 3 | Clean and Brake | 10
2026-04-15 | 25010-RO06 | TOA Spring Hill MOB | Cole Norona | 6 | 0 | LO | 10
2026-04-15 | 25010-RO07 | TOA Spring Hill MOB | Cole Norona | 3 | 0 | LO | 10
2026-04-16 | 24074-FS06 | DIDD ACM | Dillon Bowman | 40 | 40 | Ready to Ship | 2
2026-04-16 | 26014-04-ST02 | 2026 R & D | TBC | 0 | 15 | TruLaser 3040 | 2
2026-04-17 | 25075-FS01 | St Thomas West Canopy Replace | Chris Buttrey | 82 | 92 | Crating | 8
2026-04-17 | 25002-FS13 | Med Center Health | Carlos Silva | 30 | 0 | LO | 8
2026-04-17 | 24069-RM05 | TCAT Pulaski | Chris Buttrey | 1 | 1 | Shipped To Painter | 8
2026-04-17 | 26014-06-ST01 | 2026 R & D | TBC | 0 | 45 | 7000 TubeLaser 28 | 8
2026-04-17 | 25007-RM01 | QTS ATL2 DC10 | Nick Akins | 1 | 1 | Crating | 8
2026-04-17 | 25061-BM01 | BNA Concourse A | Andre Van Der Merwe | 0 | 21 | Ready to Ship | 8
2026-04-17 | 25061-FL01 | BNA Concourse A | Andre Van Der Merwe | 0 | 48 | Cidan | 8
2026-04-17 | 25025-FL11 | QTS MAN1 DC6 | Dillon Bowman | 0 | 10 | Ready to Ship | 8
2026-04-20 | 24074-FS07 | DIDD ACM | Dillon Bowman | 155 | 218 | CNC Programming | 2
2026-04-20 | 26009-FS01 | 5th & Summer Leasing Office | Cole Norona | 9 | 0 | LO Check | 2
2026-04-21 | 24039-FL35 | The Visionary | Carlos Silva | 0 | 62 | Ready to Ship | 5
2026-04-21 | 24039-BM18 | The Visionary | Carlos Silva | 0 | 36 | Ready to Ship | 5
2026-04-21 | 24039-FL36 | The Visionary | Carlos Silva | 0 | 60 | Shear | 5
2026-04-21 | 24039-FL37 | The Visionary | Carlos Silva | 0 | 16 | Shear | 5
2026-04-21 | 24039-BM19 | The Visionary | Carlos Silva | 0 | 340 | Shear | 5
2026-04-23 | 25022-RM01 | Vantage VA15 | Thomas Mooers | 4 | 4 | AXYZ 34 | 2
2026-04-23 | 25022-RM02 | Vantage VA15 | Thomas Mooers | 1 | 1 | AXYZ 34 | 2
2026-04-24 | 25030-FS01 | 510 W Tremont | Laura Forero | 88 | 0 | Correction | 8
2026-04-24 | 25030-FS02 | 510 W Tremont | Laura Forero | 84 | 0 | Sketch | 8
2026-04-24 | 24051-FS90 | TN Titans Stadium | Marc Ribar | 117 | 0 | Float | 8
2026-04-24 | 24051-FS91 | TN Titans Stadium | Marc Ribar | 36 | 0 | Float | 8
2026-04-24 | 24051-FS227 | TN Titans Stadium | Marc Ribar | 119 | 0 | Float | 8
2026-04-24 | 25061-FS01 | BNA Concourse A | Andre Van Der Merwe | 3 | 3 | Ready to Ship | 8
2026-04-24 | 25022-FS12 | Vantage VA15 | Thomas Mooers | 76 | 77 | Crating | 8
2026-04-24 | 24051-FL01 | TN Titans Stadium | Marc Ribar | 0 | 25 | Release to Shop | 8
2026-04-27 | 24026-FS01 | 1740 Division | Chris Buttrey | 23 | 23 | AXYZ 34 | 2
2026-04-27 | 25022-RO03 | Vantage VA15 | Thomas Mooers | 3 | 3 | AXYZ 34 | 2
2026-04-28 | 24051-FS93 | TN Titans Stadium | Marc Ribar | 131 | 133 | Correction | 4
2026-04-28 | 24051-FS94 | TN Titans Stadium | Marc Ribar | 79 | 0 | Float | 4
2026-04-28 | 24051-FS95 | TN Titans Stadium | Marc Ribar | 96 | 0 | Float | 4
2026-04-28 | 24051-FS228 | TN Titans Stadium | Marc Ribar | 95 | 0 | Float | 4
2026-04-30 | 25067-FS02 | Harison Bend | Andre Van Der Merwe | 29 | 29 | AXYZ 34 | 1
2026-05-01 | 24051-FS92 | TN Titans Stadium | Marc Ribar | 104 | 0 | Float | 4
2026-05-01 | 24051-FS96 | TN Titans Stadium | Marc Ribar | 52 | 0 | Float | 4
2026-05-01 | 24051-FS229 | TN Titans Stadium | Marc Ribar | 109 | 0 | Float | 4
2026-05-01 | 24051-FS230 | TN Titans Stadium | Marc Ribar | 67 | 0 | Float | 4
2026-05-04 | 24051-FS231 | TN Titans Stadium | Marc Ribar | 1 | 0 | Float | 2
2026-05-04 | 25002-FS14 | Med Center Health | Carlos Silva | 00 | 0 | Evaluation | 2
2026-05-05 | 25006-FS03 | MALETA Housing and Dining | Cole Norona | 216 | 0 | Correction | 1
2026-05-07 | 24074-FS08 | DIDD ACM | Dillon Bowman | 186 | 0 | LO Check | 1
2026-05-11 | 25006-FS05 | MALETA Housing and Dining | Cole Norona | 18 | 0 | LO Check | 4
2026-05-11 | 24079-FS103 | Nashville Youth Campus | Joe Hoyle | 111 | 0 | LO Check | 4
2026-05-11 | 25010-FS09 | TOA Spring Hill MOB | Cole Norona | 111 | 0 | Correction | 4
2026-05-11 | 25029-FS50 | Lourdes CC Phase 2 | Dillon Bowman | 8 | 4 | Correction | 4
2026-05-14 | 24074-FS09 | DIDD ACM | Dillon Bowman | 120 | 0 | LO Check | 1
2026-05-15 | 25006-FS04 | MALETA Housing and Dining | Cole Norona | 232 | 0 | LO Check | 5
2026-05-15 | 25029-ST52 | Lourdes CC Phase 2 | Dillon Bowman | 0 | 10 | Correction | 5
2026-05-15 | 25029-ST70 | Lourdes CC Phase 2 | Dillon Bowman | 0 | 6 | Sketch Check | 5
2026-05-15 | 25029-ST71 | Lourdes CC Phase 2 | Dillon Bowman | 0 | 1 | Sketch | 5
2026-05-15 | 25029-ST72 | Lourdes CC Phase 2 | Dillon Bowman | 0 | 1 | Sketch Check | 5
2026-05-18 | 25029-ST51 | Lourdes CC Phase 2 | Dillon Bowman | 0 | 10 | Correction | 3
2026-05-18 | 24079-FS201 | Nashville Youth Campus | Joe Hoyle | 41 | 0 | LO | 3
2026-05-18 | 24079-FS302 | Nashville Youth Campus | Joe Hoyle | 188 | 0 | LO | 3
2026-05-20 | 25008-FS07 | Columbia State Tech Center | Laura Forero | 58 | 0 | Evaluation | 1
2026-05-21 | 24074-FS10 | DIDD ACM | Dillon Bowman | 130 | 0 | LO Check | 1
2026-05-22 | 24073-FS01 | DIDD Perf | Dillon Bowman | 53 | 0 | Sketch | 4
2026-05-22 | 25044-FS01 | MALETA Firing Range | Cole Norona | 125 | 0 | LO | 4
2026-05-22 | 25044-FS01.1 | MALETA Firing Range | Cole Norona | 34 | 0 | LO | 4
2026-05-22 | 25065-MU01 | Crosswinds Casino Resort | Matt Rassmussen | 18 | 14 | Sketch Check | 4
2026-05-25 | 25006-FS06 | MALETA Housing and Dining | Cole Norona | 246 | 0 | LO Check | 4
2026-05-25 | 25037-FS01 | Chestnut Street Office | Laura Forero | 218 | 0 | LO Check | 4
2026-05-25 | 24079-FS301 | Nashville Youth Campus | Joe Hoyle | 143 | 0 | LO | 4
2026-05-25 | 24079-FS303 | Nashville Youth Campus | Joe Hoyle | 165 | 0 | LO | 4
2026-05-26 | 25041-FS02 | Wedgewood Bldg E | Wylie McDougall | 31 | 0 | LO | 1
2026-05-29 | 25065-MU02 | Crosswinds Casino Resort | Matt Rassmussen | 15 | 13 | LO | 10
2026-05-29 | 25065-MU03 | Crosswinds Casino Resort | Matt Rassmussen | 6 | 6 | LO | 10
2026-05-29 | 25065-MU04 | Crosswinds Casino Resort | Matt Rassmussen | 15 | 13 | LO | 10
2026-05-29 | 25065-MU05 | Crosswinds Casino Resort | Matt Rassmussen | 3 | 1 | Evaluation | 10
2026-05-29 | 25065-MU11 | Crosswinds Casino Resort | Matt Rassmussen | 1 | 1 | Evaluation | 10
2026-05-29 | 25065-MU12 | Crosswinds Casino Resort | Matt Rassmussen | 0 | 2 | Evaluation | 10
2026-05-29 | 25065-MU13 | Crosswinds Casino Resort | Matt Rassmussen | 0 | 1 | Evaluation | 10
2026-05-29 | 25065-MU14 | Crosswinds Casino Resort | Matt Rassmussen | 0 | 3 | Evaluation | 10
2026-05-29 | 25065-MU15 | Crosswinds Casino Resort | Matt Rassmussen | 0 | 6 | Evaluation | 10
2026-05-29 | 25065-MU20 | Crosswinds Casino Resort | Matt Rassmussen | 0 | 3 | Evaluation | 10
2026-05-31 | 25044-FS02 | MALETA Firing Range | Cole Norona | 135 | 0 | LO | 1
2026-06-03 | 25006-FS07 | MALETA Housing and Dining | Cole Norona | 190 | 0 | LO Check | 1
2026-06-08 | 25037-FS02 | Chestnut Street Office | Laura Forero | 204 | 0 | LO | 1
2026-06-10 | 25044-FS03 | MALETA Firing Range | Cole Norona | 150 | 0 | LO | 1
2026-06-12 | 25006-FS08 | MALETA Housing and Dining | Cole Norona | 83 | 0 | LO Check | 2
2026-06-12 | 25012-FS02 | St Jude Hospital | Wylie McDougall | 60 | 60 | AXYZ 34 | 2
2026-06-19 | 25044-FS04 | MALETA Firing Range | Cole Norona | 113 | 0 | LO | 1
2026-06-26 | 25044-FS05 | MALETA Firing Range | Cole Norona | 111 | 0 | LO | 1
2026-07-06 | 25044-FS06 | MALETA Firing Range | Cole Norona | 203 | 0 | LO | 1
2026-07-15 | 25044-FS07 | MALETA Firing Range | Cole Norona | 160 | 0 | LO | 1
2026-07-22 | 25044-FS08 | MALETA Firing Range | Cole Norona | 163 | 0 | LO | 1
2026-07-29 | 25044-FS09 | MALETA Firing Range | Cole Norona | 86 | 0 | LO | 2
2026-07-29 | 25044-FS01.2 | MALETA Firing Range | Cole Norona | 193 | 0 | LO | 2
2026-08-07 | 25044-FS10 | MALETA Firing Range | Cole Norona | 185 | 0 | LO | 1
2026-08-17 | 25044-FS11 | MALETA Firing Range | Cole Norona | 185 | 0 | LO | 1

## Notes
Picture | SEARCH JOB ID: | 25036 FL-22 | ❌ NOT FOUND
1040-30791-ST08 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
1040-30791-ST09 | 04/16/2026…Assembly | Assembly | — | Assembly | —
1040-30791-ST10 |  | Extrusion Saw | — | Extrusion Saw | —
23028-FL205 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
23028-FS99 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
24001-BM14 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
24019-RO07 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
24020-FL07 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
24026-BM01 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
24026-FS01 | 04/15...Date adjusted to 04/27.*04/16/2026…AXYZ 34 | AXYZ 34 | — | AXYZ 34 | —
24030-FL02 | Chris putting in FL03 Monday 03/23 and needs to ship out 03/27.*03/24 Pushed off until 03/30.*03/30…Checking back in*04/16/2026…Partially Shipped | Partially Shipped | — | Partially Shipped | —
24039-BM18 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
24039-BM19 | 04/15/2026…Shear*04/16/2026…Shear | Shear | — | Shear | —
24039-FL35 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
24039-FL36 | 04/15/2026…Shear*04/16/2026…Shear | Shear | — | Shear | —
24039-FL37 | 04/15/2026…Shear*04/16/2026…Shear | Shear | — | Shear | —
24039-FS14 | 04/16/2026…Partially Shipped | Partially Shipped | — | Partially Shipped | —
24039-FS15 | 04/16/2026…Partially Shipped | Partially Shipped | — | Partially Shipped | —
24046-FL12 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
24046-FL13 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
24046-RO06 | 04/16/2026…
24048-RM02 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
24051-BM01 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-BM02 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FL01 | 04/16/2026…Release to Shop | Release to Shop | — | Release to Shop | —
24051-FS01 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS01C | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS02 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS03 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS04 | 04/16/2026…Partially Shipped | Partially Shipped | — | Partially Shipped | —
24051-FS05 | 04/16/2026…Partially Shipped | Partially Shipped | — | Partially Shipped | —
24051-FS06 | 04/16/2026…Partially Shipped | Partially Shipped | — | Partially Shipped | —
24051-FS10 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS10C | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS11 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS12 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS13 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS13C | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS14 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS15 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS16C | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS200 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS201 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS205 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS206 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS209.1 | Need 4 Pcs rolled**Look for RP's**03/23 Fab-Need done ASAP*03/26…RTS*04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS212 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS213 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS215 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS216 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS217 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS218 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS219 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS221 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS223 | 03/23...Next for Titans--1 of 3 still late*03/24 Corrections*03/26…Titans line*03/30…Affected by Roller being down. Panals too large to run in small roller.*03/31…No update*04/02…Roller still down.*04/09…Roller still down.*04/16/2026…Clean and Brake | Clean and Brake | — | Clean and Brake | —
24051-FS224 | 03/23...Next for Titans--1 of 3 still late*03/24 Corrections*03/26…Titans Line*03/30…Crating*03/31…Crating*04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS225 | 03/23...Next for Titans--1 of 3 still late*03/24 Lay Out*03/26…LO*03/30…LO*03/31…LO*04/02…LO*04/09…LO*04/16/2026…LO | LO | — | LO | —
24051-FS226 | 04/16/2026…Fabrication | Fabrication | — | Fabrication | —
24051-FS227 | 04/16/2026…Float | Float | — | Float | —
24051-FS228 | 04/16/2026…Float | Float | — | Float | —
24051-FS229 | 04/16/2026…Float | Float | — | Float | —
24051-FS230 | 04/16/2026…Float | Float | — | Float | —
24051-FS231 | 04/16/2026…Float | Float | — | Float | —
24051-FS25 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS25.1 FM | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS26 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS26C | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS29 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS29C | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS30 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS31 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS32 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS33 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS33C | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS34 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS35 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS36 | Next for Titans*04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS36.2 | 04/16/2026…Fabrication | Fabrication | — | Fabrication | —
24051-FS37 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS38 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS39 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS40 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS41 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS42 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS42.1 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS43 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS43.1 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS44 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS45 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS45C | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS46 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS46.1 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS46C | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS47C | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS48 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS49 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS50 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS50C | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS51 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS51C | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS52 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS52C | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS53 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS54 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS55 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS56 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS56C | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS57 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS58 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS59 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS59C | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS67 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS71.1 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS72 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS73 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS74 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS75 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS76 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS76.1 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS77 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS78 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS78.1 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS78.2 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS82 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS83 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS84 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS85 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS86 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS87 | Must be RTS on Friday 04/17*04/16/2026…Clean and Brake | Clean and Brake | — | Clean and Brake | —
24051-FS88 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-FS89 | 04/14...Next Titans Requesting//Scheduled to be released to the shop 04/16.*04/16/2026…AXYZ 34 | AXYZ 34 | — | AXYZ 34 | —
24051-FS90 | 04/16/2026…Float | Float | — | Float | —
24051-FS91 | 04/16/2026…Float | Float | — | Float | —
24051-FS92 | 04/16/2026…Float | Float | — | Float | —
24051-FS93 | 04/14...Next Titans Requesting//Scheduled to be released to the shop 04/20.*04/16/2026…Correction | Correction | — | Correction | —
24051-FS94 | 04/16/2026…Float | Float | — | Float | —
24051-FS95 | 04/16/2026…Float | Float | — | Float | —
24051-FS96 | 04/16/2026…Float | Float | — | Float | —
24051-RP11 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-RP13 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-RP14 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-RP15 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-RP16 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-RP17 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-RP20 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
24051-RP58 | 04/16/2026…
24057-BM10 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
24057-FL10 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
24060-BM01 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
24069-RM04 | 04/16/2026…Shipped To Painter | Shipped To Painter | — | Shipped To Painter | —
24069-RM05 | 04/16/2026…Shipped To Painter | Shipped To Painter | — | Shipped To Painter | —
24071-FS10.R | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
24071-FS11 | **Must Ship No Later Than 04/17--Last bit of this job**03/23 Eval*03/24 Eval*03/26…Eval*03/30…Sketch*03/31…Sketch*04/02…Sketch…*04/14…Moving date from 04/15 to 04/17. CNC machine was down for 24 hrs.*04/16/2026…Crating | Crating | — | Crating | —
24071-RP14 | 04/16/2026…Shipped | Shipped | — | Shipped | —
24071-RP15 | 04/16/2026…
24073-FS01 | 04/16/2026…Sketch | Sketch | — | Sketch | —
24074-FS06 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
24074-FS07 | *03/30...4' Panals Rolled*04/02…Sketch*04/09…CNC*04/16/2026…CNC Programming | CNC Programming | — | CNC Programming | —
24074-FS08 | 04/16/2026…LO Check | LO Check | — | LO Check | —
24074-FS09 | 04/16/2026…LO Check | LO Check | — | LO Check | —
24074-FS10 | 04/16/2026…LO Check | LO Check | — | LO Check | —
24079-BM01B | 04/15/2026…Shear*04/16/2026…Shear | Shear | — | Shear | —
24079-BM04C | 04/15/2026…Shear*04/16/2026…Shear | Shear | — | Shear | —
24079-BM04D | 04/16/2026…TruPunch 5000 | TruPunch 5000 | — | TruPunch 5000 | —
24079-FL07 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
24079-FL08 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
24079-FL09 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
24079-FL13 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
24079-FL14 | 04/16/2026…
24079-FS03 | 04/16/2026…Evaluation | Evaluation | — | Evaluation | —
24079-FS04 | 04/16/2026…Evaluation | Evaluation | — | Evaluation | —
24079-FS101 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
24079-FS101.1 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
24079-FS102 | 04/16/2026…Sketch Check | Sketch Check | — | Sketch Check | —
24079-FS102.1 | 04/16/2026…Sketch | Sketch | — | Sketch | —
24079-FS103 | 04/16/2026…LO Check | LO Check | — | LO Check | —
24079-FS201 | 04/16/2026…LO | LO | — | LO | —
24079-FS301 | 04/16/2026…LO | LO | — | LO | —
24079-FS302 | 04/16/2026…LO | LO | — | LO | —
24079-FS303 | 04/16/2026…LO | LO | — | LO | —
24079-RM01 | 04/16/2026…Sketch | Sketch | — | Sketch | —
24079-RP03 | 04/16/2026…Shipped | Shipped | — | Shipped | —
24081-FL01 | 04/16/2026…Shipped To Painter | Shipped To Painter | — | Shipped To Painter | —
24081-FL02 | 04/16/2026…Shipped To Painter | Shipped To Painter | — | Shipped To Painter | —
24081-FS01 | 04/16/2026…Shipped To Painter | Shipped To Painter | — | Shipped To Painter | —
24081-FS02 | 04/16/2026…Shipped To Painter | Shipped To Painter | — | Shipped To Painter | —
24081-FS03 | 04/16/2026…Shipped To Painter | Shipped To Painter | — | Shipped To Painter | —
24081-FS04 | 04/16/2026…Shipped To Painter | Shipped To Painter | — | Shipped To Painter | —
24081-FS05 | 04/16/2026…Shipped To Painter | Shipped To Painter | — | Shipped To Painter | —
24081-RO01 | 04/16/2026…Shipped To Painter | Shipped To Painter | — | Shipped To Painter | —
24082-FL03 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25002-BM06 | 04/16/2026…Shipped To Painter | Shipped To Painter | — | Shipped To Painter | —
25002-BM07 | 04/16/2026… | 0 | — | 0 | —
25002-FS11.1 | Received Radius Templete, waiting for Roller Maint.**03/23 Roller should be back up this morning*03/24 Roller still down AM*03/26…C&B*03/27…Still at C&B needs to roll then back to C&B*03/31…No Update*04/02…Roller still down.*04/09…Roller still down.*04/16/2026…Clean and Brake | Clean and Brake | — | Clean and Brake | —
25002-FS13 | 04/16/2026…LO | LO | — | LO | —
25002-FS14 | 04/16/2026…Evaluation | Evaluation | — | Evaluation | —
25002-FS15 | 04/16/2026…Evaluation | Evaluation | — | Evaluation | —
25002-FS16 | 04/16/2026… | 0 | — | 0 | —
25005-ST02 | 04/16/2026…TruLaser 3040 | TruLaser 3040 | — | TruLaser 3040 | —
25006-FS03 | Not expected out of engineering before 04/15…Needs to ship 05/12*HOAR*04/16/2026…Correction | Correction | — | Correction | —
25006-FS04 | HOAR*04/16/2026…LO Check | LO Check | — | LO Check | —
25006-FS05 | Not expected out of engineering before 04/17…Needs to ship 05/12*HOAR*04/16/2026…LO Check | LO Check | — | LO Check | —
25006-FS06 | HOAR*04/16/2026…LO Check | LO Check | — | LO Check | —
25006-FS07 | HOAR*04/16/2026…LO Check | LO Check | — | LO Check | —
25006-FS08 | HOAR*04/16/2026…LO Check | LO Check | — | LO Check | —
25006-FS09 | HOAR*04/16/2026…LO | LO | — | LO | —
25006-FS10 | HOAR*04/16/2026…LO | LO | — | LO | —
25006-FS11 | HOAR*04/16/2026…LO | LO | — | LO | —
25006-FS12 | HOAR*04/16/2026…LO | LO | — | LO | —
25006-FS13 | HOAR*04/16/2026…LO | LO | — | LO | —
25007-BM03 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25007-RM01 | 04/16/2026…Crating | Crating | — | Crating | —
25008-FS05 | 04/16/2026…Shipped To Painter | Shipped To Painter | — | Shipped To Painter | —
25008-FS07 | 04/16/2026…Evaluation | Evaluation | — | Evaluation | —
25010-FS09 | 04/16/2026…Correction | Correction | — | Correction | —
25010-RO06 | 04/16/2026…LO | LO | — | LO | —
25010-RO07 | 04/16/2026…LO | LO | — | LO | —
25012-FS02 | 04/16/2026…AXYZ 34 | AXYZ 34 | — | AXYZ 34 | —
25012-MU07 | 04/16/2026…Clean and Brake | Clean and Brake | — | Clean and Brake | —
25014-11-ST01 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25014-11-ST02 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25016-BM201 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25016-FL200 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25016-MU101 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25016-MU103 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25016-MU121 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25016-MU122 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25016-MU123 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25017-FL99 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25017-RO01 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25017-RO02 | 03/27…C&B, needs to roll then back to C&B*03/30…Affected by Roller being down.*03/31…No Update*04/02…Roller still down.*04/09…Roller still down.*04/16/2026…Clean and Brake | Clean and Brake | — | Clean and Brake | —
25017-ST02 | 04/16/2026…QC | QC | — | QC | —
25022-BM06 | 04/16/2026…Shear..PLEASE RUN THIS JOB NEXT IN SHEAR/CIDAN CANNOT MISS SHIPDATE | Shear | — | Shear | —
25022-FS07 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25022-FS08 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25022-FS10 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25022-FS11 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25022-FS12 | 04/16/2026…Crating | Crating | — | Crating | —
25022-RM01 | 04/16/2026…AXYZ 34 | AXYZ 34 | — | AXYZ 34 | —
25022-RM02 | 04/16/2026…AXYZ 34 | AXYZ 34 | — | AXYZ 34 | —
25022-RO03 | 04/16/2026…AXYZ 34 | AXYZ 34 | — | AXYZ 34 | —
25025-BM100 | 04/16/2026…Shipped | Shipped | — | Shipped | —
25025-FL11 | Ships 04/17…Ship with RO-02*04/15/2026…Shear*04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25025-RO02 | Ships 04/17…Ship with FL-11*04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25028-FL02 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25028-FS01 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25029-FL97 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25029-FS50 | 04/16/2026…Correction | Correction | — | Correction | —
25029-MU02 | 04/16/2026…TruLaser 3040 | TruLaser 3040 | — | TruLaser 3040 | —
25029-MU03 | 04/16/2026…TruLaser 3040 | TruLaser 3040 | — | TruLaser 3040 | —
25029-MU10 | 04/16/2026…TruLaser 3040 | TruLaser 3040 | — | TruLaser 3040 | —
25029-ST51 | 04/16/2026…Correction | Correction | — | Correction | —
25029-ST52 | 04/16/2026…Correction | Correction | — | Correction | —
25029-ST70 | 04/16/2026…Sketch Check | Sketch Check | — | Sketch Check | —
25029-ST71 | 04/16/2026…Sketch | Sketch | — | Sketch | —
25029-ST72 | 04/16/2026…Sketch Check | Sketch Check | — | Sketch Check | —
25029-ST73 | 04/16/2026…Sketch | Sketch | — | Sketch | —
25030-FS01 | 04/16/2026…Correction | Correction | — | Correction | —
25030-FS02 | 04/16/2026…Sketch | Sketch | — | Sketch | —
25031-FL06 | 04/16/2026…Shipped | Shipped | — | Shipped | —
25031-FL08 | 04/16/2026…Shear | Shear | — | Shear | —
25031-RO01 | 04/16/2026…CNC Programming | CNC Programming | — | CNC Programming | —
25032-FL01 | 04/15/2026…Shear*04/16/2026…Shear | Shear | — | Shear | —
25035-FS02 | 04/16/2026…Shipped To Painter | Shipped To Painter | — | Shipped To Painter | —
25035-FS02.1 | 04/16/2026…RTS Titans | RTS Titans | — | RTS Titans | —
25035-FS03 | 04/16/2026…Shipped To Painter | Shipped To Painter | — | Shipped To Painter | —
25035-FS04 | 04/16/2026…Sketch | Sketch | — | Sketch | —
25036-FL22 | 04/16/2026…MUST RUN FRIDAY AND FINISH BY EOS. REFER TO EMAIL.
25037-FS01 | 04/16/2026…LO Check | LO Check | — | LO Check | —
25037-FS02 | 04/16/2026…LO | LO | — | LO | —
25040-FL01 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25041-FS02 | 04/16/2026…LO | LO | — | LO | —
25044-FS01 | 04/16/2026…LO | LO | — | LO | —
25044-FS01.1 | 04/16/2026…LO | LO | — | LO | —
25044-FS01.2 | 04/16/2026…LO | LO | — | LO | —
25044-FS02 | 04/16/2026…LO | LO | — | LO | —
25044-FS03 | 04/16/2026…LO | LO | — | LO | —
25044-FS04 | 04/16/2026…LO | LO | — | LO | —
25044-FS05 | 04/16/2026…LO | LO | — | LO | —
25044-FS06 | 04/16/2026…LO | LO | — | LO | —
25044-FS07 | 04/16/2026…LO | LO | — | LO | —
25044-FS08 | 04/16/2026…LO | LO | — | LO | —
25044-FS09 | 04/16/2026…LO | LO | — | LO | —
25044-FS10 | 04/16/2026…LO | LO | — | LO | —
25044-FS11 | 04/16/2026…LO | LO | — | LO | —
25052-BM01 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25052-FL01 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25059-RM05 | 04/16/2026…CNC Programming | CNC Programming | — | CNC Programming | —
25061-BM01 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25061-FL01 | 04/15/2026…Shear*04/16/2026…Cidan | Cidan | — | Cidan | —
25061-FS01 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
25065-MU01 | 04/16/2026…Sketch Check | Sketch Check | — | Sketch Check | —
25065-MU02 | 04/16/2026…LO | LO | — | LO | —
25065-MU03 | 04/16/2026…LO | LO | — | LO | —
25065-MU04 | 04/16/2026…LO | LO | — | LO | —
25065-MU05 | 04/16/2026…Evaluation | Evaluation | — | Evaluation | —
25065-MU11 | 04/16/2026…Evaluation | Evaluation | — | Evaluation | —
25065-MU12 | 04/16/2026…Evaluation | Evaluation | — | Evaluation | —
25065-MU13 | 04/16/2026…Evaluation | Evaluation | — | Evaluation | —
25065-MU14 | 04/16/2026…Evaluation | Evaluation | — | Evaluation | —
25065-MU15 | 04/16/2026…Evaluation | Evaluation | — | Evaluation | —
25065-MU20 | 04/16/2026…Evaluation | Evaluation | — | Evaluation | —
25067-FL02 | 04/16/2026…Shear | Shear | — | Shear | —
25067-FS02 | 04/15…CNC...Confirmed Shipdate of 04/22 with PM.*04/16/2026…AXYZ 34 | AXYZ 34 | — | AXYZ 34 | —
25075-FS01 | 04/16/2026…Crating | Crating | — | Crating | —
25075-RP01 | 04/16/2026…
26009-FS01 | 04/16/2026…LO Check | LO Check | — | LO Check | —
26011-ST01 | 04/16/2026…TruLaser 3040 | TruLaser 3040 | — | TruLaser 3040 | —
26011-ST1.1 | 04/16/2026…7000 TubeLaser 20 | 7000 TubeLaser 20 | — | 7000 TubeLaser 20 | —
26014-02-ST01 | 04/16/2026…QC | QC | — | QC | —
26014-03-ST01 | 04/16/2026…7000 TubeLaser 20 | 7000 TubeLaser 20 | — | 7000 TubeLaser 20 | —
26014-03-ST02 | 04/16/2026…TruLaser 3040 | TruLaser 3040 | — | TruLaser 3040 | —
26014-03-ST02.1 | 04/16/2026…7000 TubeLaser 20 | 7000 TubeLaser 20 | — | 7000 TubeLaser 20 | —
26014-03-ST03 | 04/16/2026…7000 TubeLaser 20 | 7000 TubeLaser 20 | — | 7000 TubeLaser 20 | —
26014-03-ST03.1 | 04/16/2026…TruLaser 3040 | TruLaser 3040 | — | TruLaser 3040 | —
26014-04-FS01 | 04/16/2026…7000 TruMatic | 7000 TruMatic | — | 7000 TruMatic | —
26014-04-ST01 | 04/16/2026…7000 TubeLaser 20 | 7000 TubeLaser 20 | — | 7000 TubeLaser 20 | —
26014-04-ST02 | 04/16/2026…TruLaser 3040 | TruLaser 3040 | — | TruLaser 3040 | —
26014-05-FS01 | 04/16/2026…Ready to Ship | Ready to Ship | — | Ready to Ship | —
26014-06-ST01 | 04/16/2026…7000 TubeLaser 28 | 7000 TubeLaser 28 | — | 7000 TubeLaser 28 | —
Find the Job ID → Type your note in Column B → It appears on all tabs automatically | 04/16/2026…
ID | Notes*04/16/2026…Current Station | Current Station | Station Changed On | Previous Station | Station Changed?
📝 MASTER NOTES — Type notes here. They auto-appear on ALL schedule tabs. | 04/16/2026…
| SEARCH MASTER NOTES: | 24026-FS01 | Not Found | ← Type Job ID to find & highlight
1:00 PM Updates Daily

## Job Operations
|  | SEARCH JOB ID: | 25006-FS09 | 🟢 ON TIME | Ship: 06/19/2026 | Crating By: 06/17/2026 | Station: LO
ID | Job Name | PM | System | Panel Qty | Part Qty | Material Type | Date Submitted | Ship Target | Shop Hours | Material In Stock | Current Station | Op 1 | Start By | Op 2 | Start By | Op 3 | Start By | Op 4 | Start By | Op 5 | Start By | Op 6 | Start By | Crating By | Notes | SortKey | Hours to complete job.
24079-BM04C | Nashville Youth Campus | Joe Hoyle | 0 | 0 | 3600 | Steel Sheet | 2026-01-15 09:13 | 2026-02-19 | 40 | NO | Shear | 7000 TruMatic | 2025-12-18 | Brake | 2025-12-29 | Powder Coat | 2026-01-08 | Shear | 2026-02-05 |  |  |  |  | 2026-02-17 | 04/15/2026…Shear*04/16/2026…Shear | 1
26014-03-ST01 | 2026 R & D | TBC | CUSTOM ARCH | 0 | 3 | 0 | 2026-02-12 17:00 | 2026-02-26 | 32 | YES | 7000 TubeLaser 20 | Assembly | 2026-02-13 | [10 empty] | 2026-02-24 | 04/16/2026…7000 TubeLaser 20 | 1
26014-03-ST02 | 2026 R & D | TBC | CUSTOM ARCH | 0 | 9 | Alum Sheet | 2026-02-17 17:31 | 2026-02-27 | 24 | YES | TruLaser 3040 | 7000 TruMatic | 2026-01-23 | Brake | 2026-02-03 | Weld | 2026-02-13 | [6 empty] | 2026-02-25 | 04/16/2026…TruLaser 3040 | 1
26014-03-ST02.1 | 2026 R & D | TBC | CUSTOM ARCH | 0 | 10 | Alum Pipe | 2026-02-17 17:34 | 2026-02-27 | 2 | YES | 7000 TubeLaser 20 | Tube Laser | 2026-02-03 | Weld | 2026-02-13 | [8 empty] | 2026-02-25 | 04/16/2026…7000 TubeLaser 20 | 1
26014-03-ST03 | 2026 R & D | TBC | CUSTOM ARCH | 0 | 8 | SS Angle | 2026-02-17 17:53 | 2026-02-27 | 12 | YES | 7000 TubeLaser 20 | Tube Laser | 2026-02-03 | Weld | 2026-02-13 | [8 empty] | 2026-02-25 | 04/16/2026…7000 TubeLaser 20 | 1
26014-03-ST03.1 | 2026 R & D | TBC | CUSTOM ARCH | 0 | 6 | SS Sheet | 2026-02-17 17:57 | 2026-02-27 | 3 | YES | TruLaser 3040 | Brake | 2026-01-23 | TruLaser 3040 | 2026-02-03 | Weld | 2026-02-13 | [6 empty] | 2026-02-25 | 04/16/2026…TruLaser 3040 | 1
25002-FS11.1 | Med Center Health | Carlos Silva | 600 | 18 | 18 | FR ACM | 2026-02-05 10:05 | 2026-03-02 | 20 | YES | Clean and Brake | AXYZ Titans Line | 2026-02-05 | Clean and Brake | 2026-02-06 | Fab | 2026-02-17 | [6 empty] | 2026-02-27 | Received Radius Templete, waiting for Roller Maint.**03/23 Roller should be back up this morning*03/24 Roller still down AM*03/26…C&B*03/27…Still at C&B needs to roll then back to C&B*03/31…No Update*04/02…Roller still down.*04/09…Roller still down.*04/16/2026…Clean and Brake | 1
25029-MU02 | Lourdes CC Phase 2 | Dillon Bowman | CUSTOM ARCH | 1 | 1 | Alum Sheet | 2026-03-03 14:41 | 2026-03-13 | 2 | YES | TruLaser 3040 | TruLaser 3040 | 2026-02-28 | [10 empty] | 2026-03-11 | 04/16/2026…TruLaser 3040 | 1
25029-MU03 | Lourdes CC Phase 2 | Dillon Bowman | CUSTOM ARCH | 0 | 2 | Steel Sheet | 2026-03-11 08:12 | 2026-03-13 | 2 | YES | TruLaser 3040 | TruLaser 3040 | 2026-02-17 | Weld | 2026-02-27 | [8 empty] | 2026-03-11 | 04/16/2026…TruLaser 3040 | 1
24051-FS223 | TN Titans Stadium | Marc Ribar | 400 | 44 | 90 | FR ACM | 2026-02-02 10:58 | 2026-03-16 | 40 | YES | Clean and Brake | AXYZ Titans Line | 2026-02-19 | Clean and Brake | 2026-02-20 | Fab | 2026-03-03 | [6 empty] | 2026-03-13 | 03/23...Next for Titans--1 of 3 still late*03/24 Corrections*03/26…Titans line*03/30…Affected by Roller being down. Panals too large to run in small roller.*03/31…No update*04/02…Roller still down.*04/09…Roller still down.*04/16/2026…Clean and Brake | 1
24079-FS03 | Nashville Youth Campus | Joe Hoyle | --- | 33 | 0 | LAYOUT ONLY | 2026-01-19 15:58 | 2026-03-16 | 0 | YES | Evaluation | [12 empty] | 2026-03-13 | 04/16/2026…Evaluation | 1
24079-FS102 | Nashville Youth Campus | Joe Hoyle | 400 | 192 | 198 | FR ACM | 2026-01-19 15:36 | 2026-03-16 | 462 | YES | Sketch Check | AXYZ Titans Line | 2026-02-16 | Clean and Brake | 2026-02-20 | Fab | 2026-03-03 | [6 empty] | 2026-03-13 | 04/16/2026…Sketch Check | 1
24051-FS225 | TN Titans Stadium | Marc Ribar | 400 | 26 | 0 | FR ACM | 2026-02-02 15:29 | 2026-03-16 | 8 | YES | LO | [12 empty] | 2026-03-13 | 03/23...Next for Titans--1 of 3 still late*03/24 Lay Out*03/26…LO*03/30…LO*03/31…LO*04/02…LO*04/09…LO*04/16/2026…LO | 1
24079-FS102.1 | Nashville Youth Campus | Joe Hoyle | 400 | 308 | 0 | FR ACM | 2026-04-02 17:47 | 2026-03-16 | 462 | YES | Sketch | AXYZ Titans Line | 2026-02-13 | Clean and Brake | 2026-02-20 | Fab | 2026-03-03 | [6 empty] | 2026-03-13 | 04/16/2026…Sketch | 1
25035-FS04 | Titans Jabez | Marc Ribar | 400 | 218 | 0 | FR ACM | 2026-02-04 11:56 | 2026-03-23 | 230 | YES | Sketch | AXYZ Titans Line | 2026-02-23 | Clean and Brake | 2026-02-27 | Fab | 2026-03-10 | [6 empty] | 2026-03-20 | 04/16/2026…Sketch | 1
26011-ST01 | 2nd Ave Mockup Build | Wylie McDougall | CUSTOM ARCH | 0 | 4 | Alum Sheet | 2026-03-11 16:34 | 2026-03-23 | 3 | YES | TruLaser 3040 | Brake | 2026-02-16 | TruLaser 3040 | 2026-02-26 | Weld | 2026-03-09 | [6 empty] | 2026-03-20 | 04/16/2026…TruLaser 3040 | 1
26011-ST1.1 | 2nd Ave Mockup Build | Wylie McDougall | TUBE SUPPORT SYSTEM | 0 | 1 | Alum Angle | 2026-03-11 16:36 | 2026-03-23 | 1 | YES | 7000 TubeLaser 20 | 7000 TubeLaser 20 | 2026-03-20 | [10 empty] | 2026-03-20 | 04/16/2026…7000 TubeLaser 20 | 1
25032-FL01 | Amazon IAD181 | Matt Rassmussen | 0 | 0 | 287 | Steel Sheet | 2026-02-04 08:44 | 2026-03-27 | 16 | YES | Shear | Cidan | 2026-03-02 | Shear | 2026-03-13 | [8 empty] | 2026-03-25 | 04/15/2026…Shear*04/16/2026…Shear | 1
25029-MU10 | Lourdes CC Phase 2 | Dillon Bowman | CUSTOM ARCH | 1 | 1 | Alum Sheet | 2026-03-24 11:17 | 2026-03-27 | 2 | YES | TruLaser 3040 | TruLaser 3040 | 2026-03-14 | [10 empty] | 2026-03-25 | 04/16/2026…TruLaser 3040 | 1
24079-FS04 | Nashville Youth Campus | Joe Hoyle | --- | 173 | 0 | LAYOUT ONLY | 2026-02-16 12:25 | 2026-03-30 | 0 | YES | Evaluation | [12 empty] | 2026-03-27 | 04/16/2026…Evaluation | 1
26014-04-ST01 | 2026 R & D | TBC | GRAVITY | 0 | 8 | Alum Tube | 2026-03-31 07:00 | 2026-04-06 | 10 | YES | 7000 TubeLaser 20 | Tube Laser | 2026-03-12 | Weld | 2026-03-23 | [8 empty] | 2026-04-03 | 04/16/2026…7000 TubeLaser 20 | 1
26014-04-FS01 | 2026 R & D | TBC | GRAVITY | 4 | 4 | Alum Sheet | 2026-03-31 07:10 | 2026-04-06 | 10 | NO | 7000 TruMatic | 7000 TruMatic | 2026-03-13 | Brake | 2026-03-24 | [8 empty] | 2026-04-03 | 04/16/2026…7000 TruMatic | 1
1040-30791-ST09 | AFI - YANCEY | Hannah Sadloski, Lisa Ellison | --- | 0 | 185 | Alum Tube | 2026-04-01 14:21 | 2026-04-10 | 0 | YES | Assembly | Assembly | 2026-03-18 | Extrusion Saw | 2026-03-28 | [8 empty] | 2026-04-08 | 04/16/2026…Assembly | 1
24079-BM04D | Nashville Youth Campus | Joe Hoyle | 0 | 185 | 1295 | Steel Sheet | 2026-03-16 14:01 | 2026-04-13 | 40 | YES | TruPunch 5000 | Brake | 2026-02-19 | Powder Coat | 2026-03-02 | Shear | 2026-03-30 | TruPunch 5000 | 2026-04-10 |  |  |  |  | 2026-04-10 | 04/16/2026…TruPunch 5000 | 1
25005-ST02 | CAT Financial Nashville HQ | Chris Buttrey | CUSTOM ARCH | 0 | 4 | Steel Sheet | 2026-04-02 08:13 | 2026-04-13 | 4 | NO | TruLaser 3040 | Brake | 2026-02-10 | Fab | 2026-02-20 | Powder Coat | 2026-03-03 | TruLaser 3040 | 2026-03-31 |  |  |  |  | 2026-04-10 | 04/16/2026…TruLaser 3040 | 1
25012-MU07 | St Jude Hospital | Wylie McDougall | 400 | 8 | 8 | FR ACM | 2026-04-01 12:16 | 2026-04-14 | 2 | YES | Clean and Brake | AXYZ | 2026-03-31 | Clean and Brake | 2026-04-01 | [8 empty] | 2026-04-11 | 04/16/2026…Clean and Brake | 1
24051-FS87 | TN Titans Stadium | Marc Ribar | 400 | 54 | 54 | FR ACM | 2026-03-04 08:34 | 2026-04-15 | 16 | YES | Clean and Brake | AXYZ Titans Line | 2026-03-21 | Clean and Brake | 2026-03-23 | Fab | 2026-04-02 | [6 empty] | 2026-04-13 | Must be RTS on Friday 04/17*04/16/2026…Clean and Brake | 1
24051-FS89 | TN Titans Stadium | Marc Ribar | 400 | 40 | 40 | FR ACM | 2026-03-04 11:38 | 2026-04-15 | 40 | YES | AXYZ 34 | AXYZ Titans Line | 2026-03-21 | Clean and Brake | 2026-03-23 | Fab | 2026-04-02 | [6 empty] | 2026-04-13 | 04/14...Next Titans Requesting//Scheduled to be released to the shop 04/16.*04/16/2026…AXYZ 34 | 1
24051-FS36.2 | TN Titans Stadium | Marc Ribar | 400 | 38 | 38 | FR ACM | 2026-03-04 13:37 | 2026-04-15 | 40 | YES | Fabrication | AXYZ Titans Line | 2026-03-21 | Clean and Brake | 2026-03-23 | Fab | 2026-04-02 | [6 empty] | 2026-04-13 | 04/16/2026…Fabrication | 1
24051-FS226 | TN Titans Stadium | Marc Ribar | 400 | 26 | 26 | FR ACM | 2026-03-04 13:58 | 2026-04-15 | 40 | YES | Fabrication | AXYZ Titans Line | 2026-03-21 | Clean and Brake | 2026-03-23 | Fab | 2026-04-02 | [6 empty] | 2026-04-13 | 04/16/2026…Fabrication | 1
24079-BM01B | Nashville Youth Campus | Joe Hoyle | 0 | 0 | 2217 | Galv Sheet | 2026-03-18 13:13 | 2026-04-15 | 80 | YES | Shear | Cidan | 2026-03-20 | Shear | 2026-04-01 | TruPunch 5000 | 2026-04-13 | [6 empty] | 2026-04-13 | 04/15/2026…Shear*04/16/2026…Shear | 1
25017-RO02 | Nashville Yards Park | Dillon Bowman | 400 | 1 | 3 | FR ACM | 2026-03-24 12:42 | 2026-04-15 | 3 | YES | Clean and Brake | AXYZ Titans Line | 2026-03-11 | Clean and Brake | 2026-03-12 | Fab | 2026-03-23 | Roller | 2026-04-02 |  |  |  |  | 2026-04-13 | 03/27…C&B, needs to roll then back to C&B*03/30…Affected by Roller being down.*03/31…No Update*04/02…Roller still down.*04/09…Roller still down.*04/16/2026…Clean and Brake | 1
25010-RO06 | TOA Spring Hill MOB | Cole Norona | 400 | 6 | 0 | FR ACM | 2026-04-09 09:02 | 2026-04-15 | 8 | YES | LO | AXYZ | 2026-03-21 | Clean and Brake | 2026-03-23 | Fab | 2026-04-02 | [6 empty] | 2026-04-13 | 04/16/2026…LO | 1
25010-RO07 | TOA Spring Hill MOB | Cole Norona | 400 | 3 | 0 | FR ACM | 2026-04-09 09:06 | 2026-04-15 | 5 | YES | LO | AXYZ | 2026-03-21 | Clean and Brake | 2026-03-23 | Fab | 2026-04-02 | [6 empty] | 2026-04-13 | 04/16/2026…LO | 1
25029-ST73 | Lourdes CC Phase 2 | Dillon Bowman | CUSTOM ARCH | 0 | 6 | Steel Custom Shape | 2026-04-13 10:32 | 2026-04-15 | 2 | YES | Sketch | [12 empty] | 2026-04-13 | 04/16/2026…Sketch | 1
26014-04-ST02 | 2026 R & D | TBC | GRAVITY | 0 | 15 | Alum Sheet | 2026-04-02 09:46 | 2026-04-16 | 1 | NO | TruLaser 3040 | Brake | 2026-02-12 | Powder Coat | 2026-02-23 | TruLaser 3040 | 2026-03-23 | Weld | 2026-04-02 |  |  |  |  | 2026-04-14 | 04/16/2026…TruLaser 3040 | 1
25002-FS13 | Med Center Health | Carlos Silva | 600 | 30 | 0 | FR ACM | 2026-03-13 14:44 | 2026-04-17 | 8 | YES | LO | AXYZ | 2026-03-24 | Clean and Brake | 2026-03-25 | Fab | 2026-04-04 | [6 empty] | 2026-04-15 | 04/16/2026…LO | 1
26014-06-ST01 | 2026 R & D | TBC | CUSTOM ARCH | 0 | 45 | Steel Tube | 2026-04-07 06:56 | 2026-04-17 | 15 | NO | 7000 TubeLaser 28 | Tube Laser | 2026-03-24 | Weld | 2026-04-03 | [8 empty] | 2026-04-15 | 04/16/2026…7000 TubeLaser 28 | 1
25061-FL01 | BNA Concourse A | Andre Van Der Merwe | 0 | 0 | 48 | Galv Sheet | 2026-04-09 16:15 | 2026-04-17 | 16 | YES | Cidan | Cidan | 2026-03-23 | Shear | 2026-04-03 | [8 empty] | 2026-04-15 | 04/15/2026…Shear*04/16/2026…Cidan | 1
25036-FL22 | TCAT Chattanooga | Josh McPherson | 0 | 0 | 10 | Steel Sheet | 2026-04-16 12:34 | 2026-04-17 | 10 | NO | Sketch Check | Cidan | 2026-03-23 | Shear | 2026-04-03 | [8 empty] | 2026-04-15 | 04/16/2026…MUST RUN FRIDAY AND FINISH BY EOS. REFER TO EMAIL. | 1
24074-FS07 | DIDD ACM | Dillon Bowman | 400 | 155 | 218 | FR ACM | 2026-02-09 11:10 | 2026-04-20 | 385 | YES | CNC Programming | AXYZ Titans Line | 2026-03-13 | Clean and Brake | 2026-03-17 | Fab | 2026-03-27 | Roller | 2026-04-07 |  |  |  |  | 2026-04-17 | *03/30...4' Panals Rolled*04/02…Sketch*04/09…CNC*04/16/2026…CNC Programming | 1
26009-FS01 | 5th & Summer Leasing Office | Cole Norona | 400 | 9 | 0 | FR ACM | 2026-03-13 08:18 | 2026-04-20 | 16 | YES | LO Check | AXYZ | 2026-03-26 | Clean and Brake | 2026-03-27 | Fab | 2026-04-07 | [6 empty] | 2026-04-17 | 04/16/2026…LO Check | 1
24046-RO06 | UAB Biomedical Research and Psycholgy | Wylie McDougall | 400 | 17 | 18 | FR ACM | 2026-04-16 13:12 | 2026-04-20 | 4 | YES | 0 | [12 empty] | 2026-04-17 | 04/16/2026… | 1
24039-FL36 | The Visionary | Carlos Silva | 0 | 0 | 60 | Alum Sheet | 2026-04-07 15:16 | 2026-04-21 | 8 | YES | Shear | Cidan | 2026-03-26 | Shear | 2026-04-07 | [8 empty] | 2026-04-18 | 04/15/2026…Shear*04/16/2026…Shear | 1
24039-FL37 | The Visionary | Carlos Silva | 0 | 0 | 16 | Alum Sheet | 2026-04-07 15:24 | 2026-04-21 | 6 | YES | Shear | Cidan | 2026-03-26 | Shear | 2026-04-07 | [8 empty] | 2026-04-18 | 04/15/2026…Shear*04/16/2026…Shear | 1
24039-BM19 | The Visionary | Carlos Silva | 0 | 0 | 340 | Galv Sheet | 2026-04-07 15:38 | 2026-04-21 | 6 | YES | Shear | Cidan | 2026-03-26 | Shear | 2026-04-07 | [8 empty] | 2026-04-18 | 04/15/2026…Shear*04/16/2026…Shear | 1
25022-BM06 | Vantage VA15 | Thomas Mooers | 0 | 0 | 500 | Galv Sheet | 2026-04-15 09:00 | 2026-04-22 | 10 | YES | Shear | Cidan | 2026-03-27 | Shear | 2026-04-08 | [8 empty] | 2026-04-20 | 04/16/2026…Shear..PLEASE RUN THIS JOB NEXT IN SHEAR/CIDAN CANNOT MISS SHIPDATE | 1
25031-RO01 | LLU Mars US Warehouse | Laura Forero | 400 | 3 | 3 | FR ACM | 2026-04-15 11:10 | 2026-04-22 | 5 | YES | CNC Programming | Clean and Brake | 2026-03-30 | Fab | 2026-04-09 | [8 empty] | 2026-04-20 | 04/16/2026…CNC Programming | 1
25031-FL08 | LLU Mars US Warehouse | Laura Forero | 0 | 0 | 6 | Alum Sheet | 2026-04-15 11:13 | 2026-04-22 | 2 | YES | Shear | Cidan | 2026-03-27 | Shear | 2026-04-08 | [8 empty] | 2026-04-20 | 04/16/2026…Shear | 1
25022-RM01 | Vantage VA15 | Thomas Mooers | 400 | 4 | 4 | FR ACM | 2026-04-10 13:52 | 2026-04-23 | 8 | YES | AXYZ 34 | AXYZ | 2026-03-30 | Clean and Brake | 2026-03-31 | Fab | 2026-04-10 | [6 empty] | 2026-04-21 | 04/16/2026…AXYZ 34 | 1
25022-RM02 | Vantage VA15 | Thomas Mooers | 400 | 1 | 1 | FR ACM | 2026-04-10 14:26 | 2026-04-23 | 1 | YES | AXYZ 34 | AXYZ | 2026-03-30 | Clean and Brake | 2026-03-31 | Fab | 2026-04-10 | [6 empty] | 2026-04-21 | 04/16/2026…AXYZ 34 | 1
25067-FL02 | Harison Bend | Andre Van Der Merwe | 0 | 0 | 8 | Alum Sheet | 2026-04-15 07:58 | 2026-04-23 | 4 | YES | Shear | Cidan | 2026-03-28 | Shear | 2026-04-09 | [8 empty] | 2026-04-21 | 04/16/2026…Shear | 1
25059-RM05 | Allen Samuels CDJR and LC | Andre Van Der Merwe | 408 | 1 | 1 | FR ACM | 2026-04-15 16:14 | 2026-04-23 | 4 | YES | CNC Programming | AXYZ | 2026-03-30 | Clean and Brake | 2026-03-31 | Fab | 2026-04-10 | [6 empty] | 2026-04-21 | 04/16/2026…CNC Programming | 1
25030-FS01 | 510 W Tremont | Laura Forero | 400 | 88 | 0 | FR ACM | 2026-03-05 15:18 | 2026-04-24 | 240 | YES | Correction | AXYZ | 2026-03-30 | Clean and Brake | 2026-04-01 | Fab | 2026-04-11 | [6 empty] | 2026-04-22 | 04/16/2026…Correction | 1
25030-FS02 | 510 W Tremont | Laura Forero | 400 | 84 | 0 | FR ACM | 2026-03-05 16:16 | 2026-04-24 | 240 | YES | Sketch | AXYZ | 2026-03-30 | Clean and Brake | 2026-04-01 | Fab | 2026-04-11 | [6 empty] | 2026-04-22 | 04/16/2026…Sketch | 1
24051-FS90 | TN Titans Stadium | Marc Ribar | 400 | 117 | 0 | FR ACM | 2026-03-13 14:13 | 2026-04-24 | 240 | YES | Float | AXYZ | 2026-03-28 | Clean and Brake | 2026-04-01 | Fab | 2026-04-11 | [6 empty] | 2026-04-22 | 04/16/2026…Float | 1
24051-FS91 | TN Titans Stadium | Marc Ribar | 400 | 36 | 0 | FR ACM | 2026-03-13 14:26 | 2026-04-24 | 40 | YES | Float | AXYZ | 2026-03-31 | Clean and Brake | 2026-04-01 | Fab | 2026-04-11 | [6 empty] | 2026-04-22 | 04/16/2026…Float | 1
24051-FS227 | TN Titans Stadium | Marc Ribar | 400 | 119 | 0 | FR ACM | 2026-03-13 14:43 | 2026-04-24 | 200 | YES | Float | AXYZ | 2026-03-28 | Clean and Brake | 2026-04-01 | Fab | 2026-04-11 | [6 empty] | 2026-04-22 | 04/16/2026…Float | 1
24051-FL01 | TN Titans Stadium | Marc Ribar | 0 | 0 | 25 | Alum Sheet | 2026-04-10 09:30 | 2026-04-24 | 16 | YES | Release to Shop | 7000 TruMatic | 2026-04-01 | Brake | 2026-04-11 | [8 empty] | 2026-04-22 | 04/16/2026…Release to Shop | 1
1040-30791-ST10 | AFI - YANCEY | Hannah Sadloski, Lisa Ellison | --- | 0 | 185 | Alum Tube | 2026-04-14 13:08 | 2026-04-24 | 0 | YES | Extrusion Saw | Assembly | 2026-04-01 | Extrusion Saw | 2026-04-11 | [8 empty] | 2026-04-22 |  | 1
24079-RM01 | Nashville Youth Campus | Joe Hoyle | 400 | 37 | 39 | FR ACM | 2026-04-14 15:10 | 2026-04-24 | 40 | YES | Sketch | AXYZ | 2026-03-31 | Clean and Brake | 2026-04-01 | Fab | 2026-04-11 | [6 empty] | 2026-04-22 | 04/16/2026…Sketch | 1
24026-FS01 | 1740 Division | Chris Buttrey | 400 CAULK | 23 | 23 | FR ACM | 2026-01-16 10:53 | 2026-04-27 | 30 | YES | AXYZ 34 | AXYZ Titans Line | 2026-04-02 | Clean and Brake | 2026-04-03 | Fab | 2026-04-14 | [6 empty] | 2026-04-24 | 04/15...Date adjusted to 04/27.*04/16/2026…AXYZ 34 | 1
25022-RO03 | Vantage VA15 | Thomas Mooers | 400 | 3 | 3 | FR ACM | 2026-04-13 08:32 | 2026-04-27 | 3 | YES | AXYZ 34 | AXYZ | 2026-04-02 | Clean and Brake | 2026-04-03 | Fab | 2026-04-14 | [6 empty] | 2026-04-24 | 04/16/2026…AXYZ 34 | 1
24051-FS93 | TN Titans Stadium | Marc Ribar | 400 | 131 | 133 | FR ACM | 2026-03-16 11:30 | 2026-04-28 | 200 | YES | Correction | AXYZ | 2026-04-01 | Clean and Brake | 2026-04-04 | Fab | 2026-04-15 | [6 empty] | 2026-04-25 | 04/14...Next Titans Requesting//Scheduled to be released to the shop 04/20.*04/16/2026…Correction | 1
24051-FS94 | TN Titans Stadium | Marc Ribar | 400 | 79 | 0 | FR ACM | 2026-03-16 12:47 | 2026-04-28 | 140 | YES | Float | AXYZ | 2026-04-02 | Clean and Brake | 2026-04-04 | Fab | 2026-04-15 | [6 empty] | 2026-04-25 | 04/16/2026…Float | 1
24051-FS95 | TN Titans Stadium | Marc Ribar | 400 | 96 | 0 | FR ACM | 2026-03-16 15:35 | 2026-04-28 | 200 | YES | Float | AXYZ | 2026-04-02 | Clean and Brake | 2026-04-04 | Fab | 2026-04-15 | [6 empty] | 2026-04-25 | 04/16/2026…Float | 1
24051-FS228 | TN Titans Stadium | Marc Ribar | 400 | 95 | 0 | FR ACM | 2026-03-16 15:49 | 2026-04-28 | 200 | YES | Float | AXYZ | 2026-04-02 | Clean and Brake | 2026-04-04 | Fab | 2026-04-15 | [6 empty] | 2026-04-25 | 04/16/2026…Float | 1
25002-BM07 | Med Center Health | Carlos Silva | 0 | 0 | 24 | Galv Sheet | 2026-04-15 16:41 | 2026-04-29 | 6 | YES | 0 | [12 empty] | 2026-04-27 | 04/16/2026… | 1
25067-FS02 | Harison Bend | Andre Van Der Merwe | 400 CAULK | 29 | 29 | FR ACM | 2026-02-25 11:23 | 2026-04-30 | 35 | YES | AXYZ 34 | AXYZ Titans Line | 2026-04-06 | Clean and Brake | 2026-04-07 | Fab | 2026-04-17 | [6 empty] | 2026-04-28 | 04/15…CNC...Confirmed Shipdate of 04/22 with PM.*04/16/2026…AXYZ 34 | 1
24051-FS92 | TN Titans Stadium | Marc Ribar | 400 | 104 | 0 | FR ACM | 2026-03-13 16:08 | 2026-05-01 | 80 | YES | Float | AXYZ | 2026-04-06 | Clean and Brake | 2026-04-08 | Fab | 2026-04-18 | [6 empty] | 2026-04-29 | 04/16/2026…Float | 1
24051-FS96 | TN Titans Stadium | Marc Ribar | 400 | 52 | 0 | FR ACM | 2026-03-17 07:25 | 2026-05-01 | 100 | YES | Float | AXYZ | 2026-04-07 | Clean and Brake | 2026-04-08 | Fab | 2026-04-18 | [6 empty] | 2026-04-29 | 04/16/2026…Float | 1
24051-FS229 | TN Titans Stadium | Marc Ribar | 400 | 109 | 0 | FR ACM | 2026-03-17 07:53 | 2026-05-01 | 200 | YES | Float | AXYZ | 2026-04-06 | Clean and Brake | 2026-04-08 | Fab | 2026-04-18 | [6 empty] | 2026-04-29 | 04/16/2026…Float | 1
24051-FS230 | TN Titans Stadium | Marc Ribar | 400 | 67 | 0 | FR ACM | 2026-03-17 09:09 | 2026-05-01 | 40 | YES | Float | AXYZ | 2026-04-06 | Clean and Brake | 2026-04-08 | Fab | 2026-04-18 | [6 empty] | 2026-04-29 | 04/16/2026…Float | 1
24051-FS231 | TN Titans Stadium | Marc Ribar | 400 | 1 | 0 | FR ACM | 2026-04-02 15:00 | 2026-05-04 | 4 | YES | Float | AXYZ | 2026-04-09 | Clean and Brake | 2026-04-10 | Fab | 2026-04-21 | [6 empty] | 2026-05-01 | 04/16/2026…Float | 1
25002-FS14 | Med Center Health | Carlos Silva | 600 | 00 | 0 | FR ACM | 2026-04-06 15:43 | 2026-05-04 | 10 | NO | Evaluation | AXYZ | 2026-04-10 | Clean and Brake | 2026-04-10 | Fab | 2026-04-21 | [6 empty] | 2026-05-01 | 04/16/2026…Evaluation | 1
25006-FS03 | MALETA Housing and Dining | Cole Norona | 400 | 216 | 0 | FR ACM | 2026-03-11 07:54 | 2026-05-05 | 360 | YES | Correction | AXYZ | 2026-04-07 | Clean and Brake | 2026-04-11 | Fab | 2026-04-22 | [6 empty] | 2026-05-02 | Not expected out of engineering before 04/15…Needs to ship 05/12*HOAR*04/16/2026…Correction | 1
25002-FS16 | Med Center Health | Carlos Silva | 600 | 00 | 0 | FR ACM | 2026-04-15 11:50 | 2026-05-06 | 20 | YES | 0 | [12 empty] | 2026-05-04 | 04/16/2026… | 1
24074-FS08 | DIDD ACM | Dillon Bowman | 400 | 186 | 0 | FR ACM | 2026-03-19 08:30 | 2026-05-07 | 335 | YES | LO Check | AXYZ | 2026-04-09 | Clean and Brake | 2026-04-14 | Fab | 2026-04-24 | [6 empty] | 2026-05-05 | 04/16/2026…LO Check | 1
25006-FS05 | MALETA Housing and Dining | Cole Norona | 400 | 18 | 0 | FR ACM | 2026-03-11 08:08 | 2026-05-11 | 30 | YES | LO Check | AXYZ | 2026-04-16 | Clean and Brake | 2026-04-17 | Fab | 2026-04-28 | [6 empty] | 2026-05-08 | Not expected out of engineering before 04/17…Needs to ship 05/12*HOAR*04/16/2026…LO Check | 1
24079-FS103 | Nashville Youth Campus | Joe Hoyle | 400 | 111 | 0 | FR ACM | 2026-03-16 12:29 | 2026-05-11 | 80 | YES | LO Check | AXYZ | 2026-04-15 | Clean and Brake | 2026-04-17 | Fab | 2026-04-28 | [6 empty] | 2026-05-08 | 04/16/2026…LO Check | 1
25010-FS09 | TOA Spring Hill MOB | Cole Norona | 400 | 111 | 0 | FR ACM | 2026-03-23 12:42 | 2026-05-11 | 40 | YES | Correction | AXYZ | 2026-04-15 | Clean and Brake | 2026-04-17 | Fab | 2026-04-28 | [6 empty] | 2026-05-08 | 04/16/2026…Correction | 1
25029-FS50 | Lourdes CC Phase 2 | Dillon Bowman | GRAVITY | 8 | 4 | Alum Sheet | 2026-03-24 13:07 | 2026-05-11 | 16 | NO | Correction | Brake | 2026-04-28 | Punch | 2026-05-08 | [8 empty] | 2026-05-08 | 04/16/2026…Correction | 1
25002-FS15 | Med Center Health | Carlos Silva | 600 | 12 | 0 | FR ACM | 2026-04-13 11:02 | 2026-05-11 | 8 | YES | Evaluation | AXYZ | 2026-04-16 | Clean and Brake | 2026-04-17 | Fab | 2026-04-28 | [6 empty] | 2026-05-08 | 04/16/2026…Evaluation | 1
24074-FS09 | DIDD ACM | Dillon Bowman | 400 | 120 | 0 | FR ACM | 2026-03-19 08:35 | 2026-05-14 | 200 | YES | LO Check | AXYZ | 2026-04-17 | Clean and Brake | 2026-04-21 | Fab | 2026-05-01 | [6 empty] | 2026-05-12 | 04/16/2026…LO Check | 1
24079-FL14 | Nashville Youth Campus | Joe Hoyle | 0 | 0 | 520 | Alum Sheet | 2026-04-16 10:35 | 2026-05-14 | 40 | NO | Evaluation | [12 empty] | 2026-05-12 | 04/16/2026… | 1
25006-FS04 | MALETA Housing and Dining | Cole Norona | 400 | 232 | 0 | FR ACM | 2026-03-11 07:56 | 2026-05-15 | 360 | YES | LO Check | AXYZ | 2026-04-16 | Clean and Brake | 2026-04-22 | Fab | 2026-05-02 | [6 empty] | 2026-05-13 | HOAR*04/16/2026…LO Check | 1
25029-ST52 | Lourdes CC Phase 2 | Dillon Bowman | TUBE SUPPORT SYSTEM | 0 | 10 | Alum Sheet | 2026-03-26 09:44 | 2026-05-15 | 3 | NO | Correction | Flat Laser | 2026-04-11 | Powder Coat | 2026-04-15 | [8 empty] | 2026-05-13 | 04/16/2026…Correction | 1
25029-ST70 | Lourdes CC Phase 2 | Dillon Bowman | CUSTOM ARCH | 0 | 6 | Steel Sheet | 2026-03-31 14:44 | 2026-05-15 | 2 | NO | Sketch Check | Flat Laser | 2026-05-09 | [10 empty] | 2026-05-13 | 04/16/2026…Sketch Check | 1
25029-ST71 | Lourdes CC Phase 2 | Dillon Bowman | CUSTOM ARCH | 0 | 1 | Steel Tube | 2026-03-31 14:47 | 2026-05-15 | 3 | NO | Sketch | Tube Laser | 2026-05-02 | [10 empty] | 2026-05-13 | 04/16/2026…Sketch | 1
25029-ST72 | Lourdes CC Phase 2 | Dillon Bowman | CUSTOM ARCH | 0 | 1 | Steel Sheet | 2026-03-31 14:50 | 2026-05-15 | 10 | NO | Sketch Check | Flat Laser | 2026-05-09 | [10 empty] | 2026-05-13 | 04/16/2026…Sketch Check | 1
25029-ST51 | Lourdes CC Phase 2 | Dillon Bowman | GRAVITY | 0 | 10 | Alum Tube | 2026-03-26 09:30 | 2026-05-18 | 5 | NO | Correction | Powder Coat | 2026-04-17 | [10 empty] | 2026-05-15 | 04/16/2026…Correction | 1
24079-FS201 | Nashville Youth Campus | Joe Hoyle | 400 | 41 | 0 | FR ACM | 2026-04-06 12:56 | 2026-05-18 | 60 | YES | LO | AXYZ | 2026-04-23 | Clean and Brake | 2026-04-24 | Fab | 2026-05-05 | [6 empty] | 2026-05-15 | 04/16/2026…LO | 1
24079-FS302 | Nashville Youth Campus | Joe Hoyle | 400 | 188 | 0 | FR ACM | 2026-04-12 19:47 | 2026-05-18 | 220 | YES | LO | AXYZ | 2026-04-20 | Clean and Brake | 2026-04-24 | Fab | 2026-05-05 | [6 empty] | 2026-05-15 | 04/16/2026…LO | 1
25008-FS07 | Columbia State Tech Center | Laura Forero | 400 CAULK | 58 | 0 | FR ACM | 2026-03-27 11:48 | 2026-05-20 | 110 | YES | Evaluation | AXYZ | 2026-04-24 | Clean and Brake | 2026-04-27 | Fab | 2026-05-07 | [6 empty] | 2026-05-18 | 04/16/2026…Evaluation | 1
24074-FS10 | DIDD ACM | Dillon Bowman | 400 | 130 | 0 | FR ACM | 2026-03-19 08:39 | 2026-05-21 | 234 | YES | LO Check | AXYZ | 2026-04-24 | Clean and Brake | 2026-04-28 | Fab | 2026-05-08 | [6 empty] | 2026-05-19 | 04/16/2026…LO Check | 1
24073-FS01 | DIDD Perf | Dillon Bowman | TUBE SUPPORT SYSTEM | 53 | 0 | Alum Sheet | 2026-03-25 08:36 | 2026-05-22 | 100 | YES | Sketch | Brake | 2026-05-06 | Post Paint | 2026-05-16 | Punch | 2026-05-20 | [6 empty] | 2026-05-20 | 04/16/2026…Sketch | 1
25044-FS01 | MALETA Firing Range | Cole Norona | 400 | 125 | 0 | FR ACM | 2026-03-30 15:06 | 2026-05-22 | 200 | YES | LO | AXYZ | 2026-04-25 | Clean and Brake | 2026-04-29 | Fab | 2026-05-09 | [6 empty] | 2026-05-20 | 04/16/2026…LO | 1
25044-FS01.1 | MALETA Firing Range | Cole Norona | 400 | 34 | 0 | FR ACM | 2026-03-30 15:57 | 2026-05-22 | 57 | YES | LO | AXYZ | 2026-04-28 | Clean and Brake | 2026-04-29 | Fab | 2026-05-09 | [6 empty] | 2026-05-20 | 04/16/2026…LO | 1
25065-MU01 | Crosswinds Casino Resort | Matt Rassmussen | 400 | 18 | 14 | FR ACM | 2026-03-31 10:19 | 2026-05-22 | 20 | NO | Sketch Check | AXYZ | 2026-04-28 | Clean and Brake | 2026-04-29 | Fab | 2026-05-09 | [6 empty] | 2026-05-20 | 04/16/2026…Sketch Check | 1
25006-FS06 | MALETA Housing and Dining | Cole Norona | 400 | 246 | 0 | FR ACM | 2026-03-11 08:13 | 2026-05-25 | 400 | YES | LO Check | AXYZ | 2026-04-25 | Clean and Brake | 2026-05-01 | Fab | 2026-05-12 | [6 empty] | 2026-05-22 | HOAR*04/16/2026…LO Check | 1
25037-FS01 | Chestnut Street Office | Laura Forero | 400 | 218 | 0 | FR ACM | 2026-03-30 09:29 | 2026-05-25 | 475 | YES | LO Check | AXYZ | 2026-04-27 | Clean and Brake | 2026-05-01 | Fab | 2026-05-12 | [6 empty] | 2026-05-22 | 04/16/2026…LO Check | 1
24079-FS301 | Nashville Youth Campus | Joe Hoyle | 400 | 143 | 0 | FR ACM | 2026-04-12 19:38 | 2026-05-25 | 180 | YES | LO | AXYZ | 2026-04-28 | Clean and Brake | 2026-05-01 | Fab | 2026-05-12 | [6 empty] | 2026-05-22 | 04/16/2026…LO | 1
24079-FS303 | Nashville Youth Campus | Joe Hoyle | 400 | 165 | 0 | FR ACM | 2026-04-12 19:54 | 2026-05-25 | 180 | YES | LO | AXYZ | 2026-04-28 | Clean and Brake | 2026-05-01 | Fab | 2026-05-12 | [6 empty] | 2026-05-22 | 04/16/2026…LO | 1
25041-FS02 | Wedgewood Bldg E | Wylie McDougall | 400 | 31 | 0 | FR ACM | 2026-03-31 15:52 | 2026-05-26 | 50 | YES | LO | AXYZ | 2026-04-21 | Clean and Brake | 2026-04-22 | Fab | 2026-05-02 | Roller | 2026-05-13 |  |  |  |  | 2026-05-23 | 04/16/2026…LO | 1
25065-MU02 | Crosswinds Casino Resort | Matt Rassmussen | 400 | 15 | 13 | FR ACM | 2026-03-31 10:22 | 2026-05-29 | 18 | NO | LO | AXYZ | 2026-05-05 | Clean and Brake | 2026-05-06 | Fab | 2026-05-16 | [6 empty] | 2026-05-27 | 04/16/2026…LO | 1
25065-MU03 | Crosswinds Casino Resort | Matt Rassmussen | 400 | 6 | 6 | FR ACM | 2026-03-31 10:25 | 2026-05-29 | 8 | NO | LO | AXYZ | 2026-05-05 | Clean and Brake | 2026-05-06 | Fab | 2026-05-16 | [6 empty] | 2026-05-27 | 04/16/2026…LO | 1
25065-MU04 | Crosswinds Casino Resort | Matt Rassmussen | 400 | 15 | 13 | FR ACM | 2026-03-31 10:27 | 2026-05-29 | 20 | NO | LO | AXYZ | 2026-05-05 | Clean and Brake | 2026-05-06 | Fab | 2026-05-16 | [6 empty] | 2026-05-27 | 04/16/2026…LO | 1
25065-MU05 | Crosswinds Casino Resort | Matt Rassmussen | CUSTOM ARCH | 3 | 1 | Steel Sheet | 2026-03-31 10:33 | 2026-05-29 | 1 | NO | Evaluation | Cidan | 2026-05-04 | Shear | 2026-05-15 | [8 empty] | 2026-05-27 | 04/16/2026…Evaluation | 1
25065-MU11 | Crosswinds Casino Resort | Matt Rassmussen | CUSTOM ARCH | 1 | 1 | Alum Sheet | 2026-03-31 10:38 | 2026-05-29 | 1 | NO | Evaluation | Cidan | 2026-05-04 | Shear | 2026-05-15 | [8 empty] | 2026-05-27 | 04/16/2026…Evaluation | 1
25065-MU12 | Crosswinds Casino Resort | Matt Rassmussen | CUSTOM ARCH | 0 | 2 | Alum Sheet | 2026-03-31 10:40 | 2026-05-29 | 1 | NO | Evaluation | Cidan | 2026-05-04 | Shear | 2026-05-15 | [8 empty] | 2026-05-27 | 04/16/2026…Evaluation | 1
25065-MU13 | Crosswinds Casino Resort | Matt Rassmussen | CUSTOM ARCH | 0 | 1 | Alum Sheet | 2026-03-31 10:41 | 2026-05-29 | 1 | NO | Evaluation | Cidan | 2026-05-04 | Shear | 2026-05-15 | [8 empty] | 2026-05-27 | 04/16/2026…Evaluation | 1
25065-MU14 | Crosswinds Casino Resort | Matt Rassmussen | CUSTOM ARCH | 0 | 3 | Alum Sheet | 2026-03-31 10:43 | 2026-05-29 | 1 | NO | Evaluation | Cidan | 2026-05-04 | Shear | 2026-05-15 | [8 empty] | 2026-05-27 | 04/16/2026…Evaluation | 1
25065-MU15 | Crosswinds Casino Resort | Matt Rassmussen | CUSTOM ARCH | 0 | 6 | Steel Sheet | 2026-03-31 10:45 | 2026-05-29 | 1 | NO | Evaluation | Cidan | 2026-05-04 | Shear | 2026-05-15 | [8 empty] | 2026-05-27 | 04/16/2026…Evaluation | 1
25065-MU20 | Crosswinds Casino Resort | Matt Rassmussen | CUSTOM ARCH | 0 | 3 | Steel Sheet | 2026-03-31 13:38 | 2026-05-29 | 1 | YES | Evaluation | Cidan | 2026-05-04 | Shear | 2026-05-15 | [8 empty] | 2026-05-27 | 04/16/2026…Evaluation | 1
25044-FS02 | MALETA Firing Range | Cole Norona | 400 | 135 | 0 | FR ACM | 2026-03-30 15:10 | 2026-05-31 | 210 | YES | LO | AXYZ | 2026-05-05 | Clean and Brake | 2026-05-08 | Fab | 2026-05-19 | [6 empty] | 2026-05-29 | 04/16/2026…LO | 1
25006-FS07 | MALETA Housing and Dining | Cole Norona | 400 | 190 | 0 | FR ACM | 2026-04-01 08:49 | 2026-06-03 | 300 | YES | LO Check | AXYZ | 2026-05-06 | Clean and Brake | 2026-05-11 | Fab | 2026-05-21 | [6 empty] | 2026-06-01 | HOAR*04/16/2026…LO Check | 1
25037-FS02 | Chestnut Street Office | Laura Forero | 400 | 204 | 0 | FR ACM | 2026-03-30 09:43 | 2026-06-08 | 450 | YES | LO | AXYZ | 2026-05-11 | Clean and Brake | 2026-05-15 | Fab | 2026-05-26 | [6 empty] | 2026-06-05 | 04/16/2026…LO | 1
25044-FS03 | MALETA Firing Range | Cole Norona | 400 | 150 | 0 | FR ACM | 2026-03-30 15:14 | 2026-06-10 | 245 | YES | LO | AXYZ | 2026-05-14 | Clean and Brake | 2026-05-18 | Fab | 2026-05-28 | [6 empty] | 2026-06-08 | 04/16/2026…LO | 1
25006-FS08 | MALETA Housing and Dining | Cole Norona | 400 | 83 | 0 | FR ACM | 2026-04-01 08:51 | 2026-06-12 | 140 | YES | LO Check | AXYZ | 2026-05-18 | Clean and Brake | 2026-05-20 | Fab | 2026-05-30 | [6 empty] | 2026-06-10 | HOAR*04/16/2026…LO Check | 1
25012-FS02 | St Jude Hospital | Wylie McDougall | 400 | 60 | 60 | FR ACM | 2026-04-07 09:19 | 2026-06-12 | 120 | YES | AXYZ 34 | AXYZ Titans Line | 2026-05-18 | Clean and Brake | 2026-05-20 | Fab | 2026-05-30 | [6 empty] | 2026-06-10 | 04/16/2026…AXYZ 34 | 1
25044-FS04 | MALETA Firing Range | Cole Norona | 400 | 113 | 0 | FR ACM | 2026-03-30 15:17 | 2026-06-19 | 190 | YES | LO | AXYZ | 2026-05-23 | Clean and Brake | 2026-05-27 | Fab | 2026-06-06 | [6 empty] | 2026-06-17 | 04/16/2026…LO | 1
25006-FS09 | MALETA Housing and Dining | Cole Norona | 400 | 152 | 0 | FR ACM | 2026-04-13 10:19 | 2026-06-19 | 250 | YES | LO | AXYZ | 2026-05-23 | Clean and Brake | 2026-05-27 | Fab | 2026-06-06 | [6 empty] | 2026-06-17 | HOAR*04/16/2026…LO | 1
25044-FS05 | MALETA Firing Range | Cole Norona | 400 | 111 | 0 | FR ACM | 2026-03-30 15:20 | 2026-06-26 | 190 | YES | LO | AXYZ | 2026-06-01 | Clean and Brake | 2026-06-03 | Fab | 2026-06-13 | [6 empty] | 2026-06-24 | 04/16/2026…LO | 1
25006-FS10 | MALETA Housing and Dining | Cole Norona | 400 | 140 | 0 | FR ACM | 2026-04-13 10:29 | 2026-07-02 | 235 | YES | LO | AXYZ | 2026-06-16 | Fab | 2026-06-19 | [8 empty] | 2026-06-30 | HOAR*04/16/2026…LO | 1
25044-FS06 | MALETA Firing Range | Cole Norona | 400 | 203 | 0 | FR ACM | 2026-03-30 15:24 | 2026-07-06 | 340 | YES | LO | AXYZ | 2026-06-08 | Clean and Brake | 2026-06-12 | Fab | 2026-06-23 | [6 empty] | 2026-07-03 | 04/16/2026…LO | 1
25044-FS07 | MALETA Firing Range | Cole Norona | 400 | 160 | 0 | FR ACM | 2026-03-30 15:28 | 2026-07-15 | 270 | YES | LO | AXYZ | 2026-06-18 | Clean and Brake | 2026-06-22 | Fab | 2026-07-02 | [6 empty] | 2026-07-13 | 04/16/2026…LO | 1
25006-FS11 | MALETA Housing and Dining | Cole Norona | 400 | 201 | 0 | FR ACM | 2026-04-13 10:29 | 2026-07-15 | 340 | YES | LO | AXYZ | 2026-06-17 | Clean and Brake | 2026-06-22 | Fab | 2026-07-02 | [6 empty] | 2026-07-13 | HOAR*04/16/2026…LO | 1
25044-FS08 | MALETA Firing Range | Cole Norona | 400 | 163 | 0 | FR ACM | 2026-03-30 15:30 | 2026-07-22 | 270 | YES | LO | AXYZ | 2026-06-25 | Clean and Brake | 2026-06-29 | Fab | 2026-07-09 | [6 empty] | 2026-07-20 | 04/16/2026…LO | 1
25006-FS12 | MALETA Housing and Dining | Cole Norona | 400 | 192 | 0 | FR ACM | 2026-04-13 10:29 | 2026-07-27 | 323 | YES | LO | AXYZ | 2026-06-29 | Clean and Brake | 2026-07-03 | Fab | 2026-07-14 | [6 empty] | 2026-07-24 | HOAR*04/16/2026…LO | 1
25044-FS09 | MALETA Firing Range | Cole Norona | 400 | 86 | 0 | FR ACM | 2026-03-30 15:33 | 2026-07-29 | 145 | YES | LO | AXYZ | 2026-07-03 | Clean and Brake | 2026-07-06 | Fab | 2026-07-16 | [6 empty] | 2026-07-27 | 04/16/2026…LO | 1
25044-FS01.2 | MALETA Firing Range | Cole Norona | 400 | 193 | 0 | FR ACM | 2026-03-30 16:02 | 2026-07-29 | 325 | YES | LO | AXYZ | 2026-07-01 | Clean and Brake | 2026-07-06 | Fab | 2026-07-16 | [6 empty] | 2026-07-27 | 04/16/2026…LO | 1
25006-FS13 | MALETA Housing and Dining | Cole Norona | 400 | 28 | 0 | FR ACM | 2026-04-13 10:30 | 2026-08-03 | 45 | YES | LO | AXYZ | 2026-07-09 | Clean and Brake | 2026-07-10 | Fab | 2026-07-21 | [6 empty] | 2026-07-31 | HOAR*04/16/2026…LO | 1
25044-FS10 | MALETA Firing Range | Cole Norona | 400 | 185 | 0 | FR ACM | 2026-03-30 15:41 | 2026-08-07 | 300 | YES | LO | AXYZ | 2026-07-10 | Clean and Brake | 2026-07-15 | Fab | 2026-07-25 | [6 empty] | 2026-08-05 | 04/16/2026…LO | 1
25044-FS11 | MALETA Firing Range | Cole Norona | 400 | 185 | 0 | FR ACM | 2026-03-30 15:47 | 2026-08-17 | 300 | YES | LO | AXYZ | 2026-07-20 | Clean and Brake | 2026-07-24 | Fab | 2026-08-04 | [6 empty] | 2026-08-14 | 04/16/2026…LO | 1
25075-RP01 | St Thomas West Canopy Replace | Chris Buttrey | 0 | 2 | 6 | 0 | 2026-04-16 13:15 | 0 | 0 | 0 | CNC Programming | AXYZ 34 | #NUM! | Clean and Brake | #NUM! | Fab | #NUM! | [6 empty] | #NUM! | 04/16/2026… | 1
24051-RP58 | TN Titans Stadium | Marc Ribar | 0 | 1 | 0 | 0 | 2026-04-16 13:18 | 0 | 0 | 0 | CNC Programming | AXYZ 34 | #NUM! | Clean and Brake | #NUM! | Fab | #NUM! | [6 empty] | #NUM! | 04/16/2026… | 1
24071-RP15 | RS Gass State Lab | Cole Norona | 0 | 0 | 3 | 0 | 2026-04-16 13:21 | 0 | 0 | 0 | CNC Programming | AXYZ 34 | #NUM! | Clean and Brake | #NUM! | Fab | #NUM! | [6 empty] | #NUM! | 04/16/2026… | 1
24060-BM01 | Loves Blacksburg | Cole Norona | 0 | 0 | 14 | Steel Sheet | 2025-01-08 16:50 | 2025-02-21 | 28 | YES | Ready to Ship | Cidan | 2025-01-27 | Shear | 2025-02-07 | [8 empty] | 2025-02-19 | 04/16/2026…Ready to Ship | 2
24001-BM14 | McEwen Northside | Josh McPherson | 0 | 0 | 12 | Galv Sheet | 2025-02-11 11:06 | 2025-03-03 | 1 | YES | Ready to Ship | Cidan | 2025-02-05 | Shear | 2025-02-17 | [8 empty] | 2025-02-28 | 04/16/2026…Ready to Ship | 2
24051-FS01 | TN Titans Stadium | Marc Ribar | 400 | 160 | 160 | FR ACM | 2025-03-06 11:18 | 2025-03-31 | 360 | YES | RTS Titans | AXYZ Titans Line | 2025-03-04 | Clean and Brake | 2025-03-07 | Fab | 2025-03-18 | [6 empty] | 2025-03-28 | 04/16/2026…RTS Titans | 2
24051-FS02 | TN Titans Stadium | Marc Ribar | 400 | 158 | 158 | FR ACM | 2025-03-06 11:23 | 2025-04-17 | 300 | YES | RTS Titans | AXYZ Titans Line | 2025-03-21 | Clean and Brake | 2025-03-25 | Fab | 2025-04-04 | [6 empty] | 2025-04-15 | 04/16/2026…RTS Titans | 2
24051-FS03 | TN Titans Stadium | Marc Ribar | 400 | 160 | 160 | FR ACM | 2025-03-06 11:43 | 2025-04-18 | 300 | YES | RTS Titans | AXYZ 34 | 2025-03-26 | Clean and Brake | 2025-03-26 | Fab | 2025-04-05 | [6 empty] | 2025-04-16 | 04/16/2026…RTS Titans | 2
24051-FS04 | TN Titans Stadium | Marc Ribar | 400 | 153 | 153 | FR ACM | 2025-03-06 15:22 | 2025-04-22 | 300 | YES | Partially Shipped | AXYZ Titans Line | 2025-03-26 | Clean and Brake | 2025-03-29 | Fab | 2025-04-09 | [6 empty] | 2025-04-19 | 04/16/2026…Partially Shipped | 2
24051-FS05 | TN Titans Stadium | Marc Ribar | 400 | 153 | 153 | FR ACM | 2025-03-06 15:34 | 2025-04-22 | 300 | YES | Partially Shipped | AXYZ Titans Line | 2025-03-26 | Clean and Brake | 2025-03-29 | Fab | 2025-04-09 | [6 empty] | 2025-04-19 | 04/16/2026…Partially Shipped | 2
24051-FS06 | TN Titans Stadium | Marc Ribar | 400 | 153 | 153 | FR ACM | 2025-03-06 15:37 | 2025-04-23 | 300 | YES | Partially Shipped | AXYZ Titans Line | 2025-03-27 | Clean and Brake | 2025-03-31 | Fab | 2025-04-10 | [6 empty] | 2025-04-21 | 04/16/2026…Partially Shipped | 2
24051-FS10 | TN Titans Stadium | Marc Ribar | 400 | 160 | 160 | FR ACM | 2025-03-21 05:31 | 2025-05-06 | 300 | YES | RTS Titans | AXYZ Titans Line | 2025-04-09 | Clean and Brake | 2025-04-12 | Fab | 2025-04-23 | [6 empty] | 2025-05-03 | 04/16/2026…RTS Titans | 2
24051-FS11 | TN Titans Stadium | Marc Ribar | 400 | 160 | 160 | FR ACM | 2025-03-21 05:35 | 2025-05-07 | 300 | YES | RTS Titans | AXYZ Titans Line | 2025-04-10 | Clean and Brake | 2025-04-14 | Fab | 2025-04-24 | [6 empty] | 2025-05-05 | 04/16/2026…RTS Titans | 2
24051-FS12 | TN Titans Stadium | Marc Ribar | 400 | 160 | 160 | FR ACM | 2025-03-21 05:37 | 2025-05-14 | 300 | YES | RTS Titans | AXYZ Titans Line | 2025-04-17 | Clean and Brake | 2025-04-21 | Fab | 2025-05-01 | [6 empty] | 2025-05-12 | 04/16/2026…RTS Titans | 2
24051-FS13 | TN Titans Stadium | Marc Ribar | 400 | 110 | 110 | FR ACM | 2025-03-21 14:26 | 2025-05-19 | 300 | YES | RTS Titans | AXYZ Titans Line | 2025-04-23 | Clean and Brake | 2025-04-25 | Fab | 2025-05-06 | [6 empty] | 2025-05-16 | 04/16/2026…RTS Titans | 2
24051-FS14 | TN Titans Stadium | Marc Ribar | 400 | 110 | 110 | FR ACM | 2025-03-21 14:31 | 2025-05-21 | 200 | YES | RTS Titans | AXYZ Titans Line | 2025-04-25 | Clean and Brake | 2025-04-28 | Fab | 2025-05-08 | [6 empty] | 2025-05-19 | 04/16/2026…RTS Titans | 2
24051-FS15 | TN Titans Stadium | Marc Ribar | 400 | 110 | 110 | FR ACM | 2025-03-21 14:39 | 2025-05-22 | 200 | YES | RTS Titans | AXYZ Titans Line | 2025-04-26 | Clean and Brake | 2025-04-29 | Fab | 2025-05-09 | [6 empty] | 2025-05-20 | 04/16/2026…RTS Titans | 2
24051-FS25 | TN Titans Stadium | Marc Ribar | 400 | 50 | 50 | FR ACM | 2025-04-04 14:12 | 2025-06-02 | 100 | YES | RTS Titans | AXYZ Titans Line | 2025-05-08 | Clean and Brake | 2025-05-09 | Fab | 2025-05-20 | [6 empty] | 2025-05-30 | 04/16/2026…RTS Titans | 2
24051-FS26 | TN Titans Stadium | Marc Ribar | 400 | 169 | 169 | FR ACM | 2025-04-04 14:16 | 2025-06-02 | 300 | YES | RTS Titans | AXYZ Titans Line | 2025-05-05 | Clean and Brake | 2025-05-09 | Fab | 2025-05-20 | [6 empty] | 2025-05-30 | 04/16/2026…RTS Titans | 2
24051-FS212 | TN Titans Stadium | Marc Ribar | 400 | 26 | 26 | FR ACM | 2025-04-04 15:52 | 2025-06-11 | 50 | NO | RTS Titans | AXYZ Titans Line | 2025-05-17 | Clean and Brake | 2025-05-19 | Fab | 2025-05-29 | [6 empty] | 2025-06-09 | 04/16/2026…RTS Titans | 2
24051-FS29 | TN Titans Stadium | Marc Ribar | 400 | 78 | 78 | FR ACM | 2025-04-04 15:50 | 2025-06-11 | 200 | YES | RTS Titans | AXYZ Titans Line | 2025-05-16 | Clean and Brake | 2025-05-19 | Fab | 2025-05-29 | [6 empty] | 2025-06-09 | 04/16/2026…RTS Titans | 2
24051-FS30 | TN Titans Stadium | Marc Ribar | 400 | 128 | 128 | FR ACM | 2025-04-07 09:12 | 2025-06-11 | 300 | YES | RTS Titans | AXYZ Titans Line | 2025-05-15 | Clean and Brake | 2025-05-19 | Fab | 2025-05-29 | [6 empty] | 2025-06-09 | 04/16/2026…RTS Titans | 2
24051-FS31 | TN Titans Stadium | Marc Ribar | 400 | 128 | 128 | FR ACM | 2025-04-07 09:16 | 2025-06-12 | 300 | YES | RTS Titans | AXYZ Titans Line | 2025-05-16 | Clean and Brake | 2025-05-20 | Fab | 2025-05-30 | [6 empty] | 2025-06-10 | 04/16/2026…RTS Titans | 2
24051-FS32 | TN Titans Stadium | Marc Ribar | 400 | 128 | 128 | FR ACM | 2025-04-07 09:34 | 2025-06-13 | 200 | YES | RTS Titans | AXYZ Titans Line | 2025-05-17 | Clean and Brake | 2025-05-21 | Fab | 2025-05-31 | [6 empty] | 2025-06-11 | 04/16/2026…RTS Titans | 2
24082-FL03 | GTN Cable | Josh McPherson, Nick Akins | 0 | 0 | 32 | Steel Sheet | 2025-06-12 10:56 | 2025-06-17 | 4 | YES | Ready to Ship | Cidan | 2025-05-22 | Shear | 2025-06-03 | [8 empty] | 2025-06-14 | 04/16/2026…Ready to Ship | 2
24051-FS33 | TN Titans Stadium | Marc Ribar | 400 | 161 | 161 | FR ACM | 2025-04-07 16:16 | 2025-06-18 | 300 | YES | RTS Titans | AXYZ Titans Line | 2025-05-22 | Clean and Brake | 2025-05-26 | Fab | 2025-06-05 | [6 empty] | 2025-06-16 | 04/16/2026…RTS Titans | 2
24051-BM01 | TN Titans Stadium | Marc Ribar | 0 | 0 | 1900 | Alum Sheet | 2025-03-05 10:42 | 2025-06-18 | 60 | YES | RTS Titans | Brake | 2025-05-24 | Shear | 2025-06-04 | [8 empty] | 2025-06-16 | 04/16/2026…RTS Titans | 2
24051-FS200 | TN Titans Stadium | Marc Ribar | 400 | 131 | 131 | FR ACM | 2025-03-07 16:19 | 2025-06-19 | 300 | YES | RTS Titans | AXYZ Titans Line | 2025-05-23 | Clean and Brake | 2025-05-27 | Fab | 2025-06-06 | [6 empty] | 2025-06-17 | 04/16/2026…RTS Titans | 2
24051-FS34 | TN Titans Stadium | Marc Ribar | 400 | 161 | 161 | FR ACM | 2025-04-07 16:18 | 2025-06-19 | 300 | YES | RTS Titans | AXYZ Titans Line | 2025-05-23 | Clean and Brake | 2025-05-27 | Fab | 2025-06-06 | [6 empty] | 2025-06-17 | 04/16/2026…RTS Titans | 2
24051-FS35 | TN Titans Stadium | Marc Ribar | 400 | 160 | 160 | FR ACM | 2025-04-07 16:20 | 2025-06-20 | 300 | YES | RTS Titans | AXYZ Titans Line | 2025-05-24 | Clean and Brake | 2025-05-28 | Fab | 2025-06-07 | [6 empty] | 2025-06-18 | 04/16/2026…RTS Titans | 2
24051-FS206 | TN Titans Stadium | Marc Ribar | 400 | 72 | 72 | FR ACM | 2025-03-21 14:52 | 2025-06-25 | 200 | NO | RTS Titans | AXYZ Titans Line | 2025-05-30 | Clean and Brake | 2025-06-02 | Fab | 2025-06-12 | [6 empty] | 2025-06-23 | 04/16/2026…RTS Titans | 2
25016-MU101 | Rockdale CJAC | Dillon Bowman | 400 | 4 | 5 | FR ACM | 2025-05-30 12:26 | 2025-07-01 | 8 | YES | Ready to Ship | AXYZ 34 | 2025-06-07 | Clean and Brake | 2025-06-07 | Fab | 2025-06-18 | [6 empty] | 2025-06-28 | 04/16/2026…Ready to Ship | 2
25016-MU103 | Rockdale CJAC | Dillon Bowman | CUSTOM ARCH | 0 | 8 | Alum Sheet | 2025-05-30 12:33 | 2025-07-01 | 2 | YES | Ready to Ship | Cidan | 2025-06-05 | Shear | 2025-06-17 | [8 empty] | 2025-06-28 | 04/16/2026…Ready to Ship | 2
25016-MU121 | Rockdale CJAC | Dillon Bowman | 400 | 1 | 1 | FR ACM | 2025-05-30 12:37 | 2025-07-01 | 2 | YES | Ready to Ship | AXYZ Titans Line | 2025-06-06 | Clean and Brake | 2025-06-07 | Fab | 2025-06-18 | [6 empty] | 2025-06-28 | 04/16/2026…Ready to Ship | 2
25016-MU122 | Rockdale CJAC | Dillon Bowman | CUSTOM ARCH | 0 | 2 | Galv Sheet | 2025-05-30 12:40 | 2025-07-01 | 1 | YES | Ready to Ship | Cidan | 2025-06-05 | Shear | 2025-06-17 | [8 empty] | 2025-06-28 | 04/16/2026…Ready to Ship | 2
25016-MU123 | Rockdale CJAC | Dillon Bowman | CUSTOM ARCH | 0 | 2 | Alum Sheet | 2025-05-30 12:42 | 2025-07-01 | 1 | YES | Ready to Ship | Cidan | 2025-06-05 | Shear | 2025-06-17 | [8 empty] | 2025-06-28 | 04/16/2026…Ready to Ship | 2
24051-FS01C | TN Titans Stadium | Marc Ribar | 400 | 160 | 160 | FR ACM | 2025-05-04 09:32 | 2025-07-01 | 200 | YES | RTS Titans | AXYZ Titans Line | 2025-06-04 | Clean and Brake | 2025-06-07 | Fab | 2025-06-18 | [6 empty] | 2025-06-28 | 04/16/2026…RTS Titans | 2
24051-FS10C | TN Titans Stadium | Marc Ribar | 400 | 160 | 160 | FR ACM | 2025-05-05 08:59 | 2025-07-03 | 200 | YES | RTS Titans | AXYZ Titans Line | 2025-06-06 | Clean and Brake | 2025-06-10 | Fab | 2025-06-20 | [6 empty] | 2025-07-01 | 04/16/2026…RTS Titans | 2
24051-FS33C | TN Titans Stadium | Marc Ribar | 400 | 161 | 161 | FR ACM | 2025-05-05 09:22 | 2025-07-11 | 200 | YES | RTS Titans | AXYZ Titans Line | 2025-06-14 | Clean and Brake | 2025-06-18 | Fab | 2025-06-28 | [6 empty] | 2025-07-09 | 04/16/2026…RTS Titans | 2
24051-FS37 | TN Titans Stadium | Marc Ribar | 400 | 24 | 24 | FR ACM | 2025-06-09 14:53 | 2025-07-14 | 48 | YES | RTS Titans | AXYZ Titans Line | 2025-06-19 | Clean and Brake | 2025-06-20 | Fab | 2025-07-01 | [6 empty] | 2025-07-11 | 04/16/2026…RTS Titans | 2
24051-FS38 | TN Titans Stadium | Marc Ribar | 400 | 90 | 90 | FR ACM | 2025-06-09 14:56 | 2025-07-14 | 125 | YES | RTS Titans | AXYZ Titans Line | 2025-06-18 | Clean and Brake | 2025-06-20 | Fab | 2025-07-01 | [6 empty] | 2025-07-11 | 04/16/2026…RTS Titans | 2
24051-FS39 | TN Titans Stadium | Marc Ribar | 400 | 96 | 96 | FR ACM | 2025-06-09 15:09 | 2025-07-14 | 125 | YES | RTS Titans | AXYZ Titans Line | 2025-06-18 | Clean and Brake | 2025-06-20 | Fab | 2025-07-01 | [6 empty] | 2025-07-11 | 04/16/2026…RTS Titans | 2
24051-FS40 | TN Titans Stadium | Marc Ribar | 400 | 96 | 96 | FR ACM | 2025-06-09 15:14 | 2025-07-15 | 125 | YES | RTS Titans | AXYZ Titans Line | 2025-06-19 | Clean and Brake | 2025-06-21 | Fab | 2025-07-02 | [6 empty] | 2025-07-12 | 04/16/2026…RTS Titans | 2
24020-FL07 | QTS ATL2 DC2 Osgood | Dillon Bowman | --- | 2 | 2 | Galv Sheet | 2025-07-17 10:36 | 2025-07-18 | 1 | YES | Ready to Ship | Cidan | 2025-06-23 | Shear | 2025-07-04 | [8 empty] | 2025-07-16 | 04/16/2026…Ready to Ship | 2
24051-FS41 | TN Titans Stadium | Marc Ribar | 400 | 96 | 96 | FR ACM | 2025-06-09 15:16 | 2025-07-22 | 125 | YES | RTS Titans | AXYZ Titans Line | 2025-06-26 | Clean and Brake | 2025-06-28 | Fab | 2025-07-09 | [6 empty] | 2025-07-19 | 04/16/2026…RTS Titans | 2
25028-FS01 | TN Soybean Council | Cole Norona | 400 CAULK | 26 | 26 | FR ACM | 2025-06-12 07:58 | 2025-07-23 | 46 | YES | Ready to Ship | AXYZ Titans Line | 2025-06-28 | Clean and Brake | 2025-06-30 | Fab | 2025-07-10 | [6 empty] | 2025-07-21 | 04/16/2026…Ready to Ship | 2
24051-FS36 | TN Titans Stadium | Marc Ribar | 400 | 84 | 84 | FR ACM | 2025-06-04 10:30 | 2025-07-31 | 40 | YES | RTS Titans | AXYZ Titans Line | 2025-07-05 | Clean and Brake | 2025-07-08 | Fab | 2025-07-18 | [6 empty] | 2025-07-29 | Next for Titans*04/16/2026…RTS Titans | 2
24051-FS215 | TN Titans Stadium | Marc Ribar | 400 | 14 | 14 | FR ACM | 2025-06-04 10:28 | 2025-07-31 | 40 | YES | RTS Titans | AXYZ Titans Line | 2025-07-07 | Clean and Brake | 2025-07-08 | Fab | 2025-07-18 | [6 empty] | 2025-07-29 | 04/16/2026…RTS Titans | 2
24051-FS43 | TN Titans Stadium | Marc Ribar | 400 | 160 | 160 | FR ACM | 2025-06-10 16:15 | 2025-08-04 | 250 | YES | RTS Titans | AXYZ Titans Line | 2025-07-08 | Clean and Brake | 2025-07-11 | Fab | 2025-07-22 | [6 empty] | 2025-08-01 | 04/16/2026…RTS Titans | 2
24057-BM10 | Rowan BWI 150 | Dillon Bowman | 0 | 0 | 11 | Galv Sheet | 2025-07-23 10:10 | 2025-08-06 | 2 | YES | Ready to Ship | Cidan | 2025-07-11 | Shear | 2025-07-23 | [8 empty] | 2025-08-04 | 04/16/2026…Ready to Ship | 2
24057-FL10 | Rowan BWI 150 | Dillon Bowman | 0 | 0 | 7 | Alum Sheet | 2025-07-23 09:08 | 2025-08-06 | 2 | YES | Ready to Ship | Cidan | 2025-07-11 | Shear | 2025-07-23 | [8 empty] | 2025-08-04 | 04/16/2026…Ready to Ship | 2
25028-FL02 | TN Soybean Council | Cole Norona | 0 | 0 | 4 | Alum Sheet | 2025-08-07 13:26 | 2025-08-08 | 1 | YES | Ready to Ship | Cidan | 2025-07-14 | Shear | 2025-07-25 | [8 empty] | 2025-08-06 | 04/16/2026…Ready to Ship | 2
24051-FS42 | TN Titans Stadium | Marc Ribar | 400 | 120 | 120 | FR ACM | 2025-06-09 15:46 | 2025-08-13 | 200 | YES | RTS Titans | AXYZ Titans Line | 2025-07-17 | Clean and Brake | 2025-07-21 | Fab | 2025-07-31 | [6 empty] | 2025-08-11 | 04/16/2026…RTS Titans | 2
24051-RP11 | TN Titans Stadium | Marc Ribar | 0 | 1 | 1 | FR ACM | 2025-08-05 06:20 | 2025-08-14 | 0 | YES | RTS Titans | AXYZ Titans Line | 2025-07-21 | Clean and Brake | 2025-07-22 | Fab | 2025-08-01 | [6 empty] | 2025-08-12 | 04/16/2026…RTS Titans | 2
24051-FS44 | TN Titans Stadium | Marc Ribar | 400 | 120 | 120 | FR ACM | 2025-06-10 16:26 | 2025-08-18 | 200 | YES | RTS Titans | AXYZ Titans Line | 2025-07-22 | Clean and Brake | 2025-07-25 | Fab | 2025-08-05 | [6 empty] | 2025-08-15 | 04/16/2026…RTS Titans | 2
24051-RP16 | TN Titans Stadium | Marc Ribar | 0 | 5 | 5 | 0 | 2025-08-12 07:11 | 2025-08-25 | 0 | 0 | RTS Titans | AXYZ Titans Line | 2025-07-31 | Clean and Brake | 2025-08-01 | Fab | 2025-08-12 | [6 empty] | 2025-08-22 | 04/16/2026…RTS Titans | 2
24048-RM02 | QTS NAL2 DC1 | Joe Hoyle | 400 | 3 | 3 | FR ACM | 2025-08-25 06:33 | 2025-08-28 | 4 | YES | Ready to Ship | AXYZ Titans Line | 2025-08-04 | Clean and Brake | 2025-08-05 | Fab | 2025-08-15 | [6 empty] | 2025-08-26 | 04/16/2026…Ready to Ship | 2
25016-BM201 | Rockdale CJAC | Dillon Bowman | CUSTOM ARCH | 12 | 12 | Galv Sheet | 2025-08-21 08:57 | 2025-09-08 | 2 | YES | Ready to Ship | Cidan | 2025-08-13 | Shear | 2025-08-25 | [8 empty] | 2025-09-05 | 04/16/2026…Ready to Ship | 2
25016-FL200 | Rockdale CJAC | Dillon Bowman | CUSTOM ARCH | 8 | 8 | Alum Sheet | 2025-08-21 08:56 | 2025-09-08 | 4 | YES | Ready to Ship | Cidan | 2025-08-13 | Shear | 2025-08-25 | [8 empty] | 2025-09-05 | 04/16/2026…Ready to Ship | 2
24046-FL12 | UAB Biomedical Research and Psycholgy | Wylie McDougall | 0 | 0 | 119 | Alum Sheet | 2025-09-03 08:05 | 2025-09-16 | 7 | YES | Ready to Ship | Cidan | 2025-08-21 | Shear | 2025-09-02 | [8 empty] | 2025-09-13 | 04/16/2026…Ready to Ship | 2
24046-FL13 | UAB Biomedical Research and Psycholgy | Wylie McDougall | 0 | 0 | 53 | Alum Sheet | 2025-09-03 08:08 | 2025-09-16 | 7 | YES | Ready to Ship | Cidan | 2025-08-21 | Shear | 2025-09-02 | [8 empty] | 2025-09-13 | 04/16/2026…Ready to Ship | 2
24051-RP20 | TN Titans Stadium | Marc Ribar | 0 | 46 | 46 | 0 | 2025-09-22 08:43 | 2025-09-23 | 0 | 0 | RTS Titans | AXYZ Titans Line | 2025-08-29 | Clean and Brake | 2025-08-30 | Fab | 2025-09-10 | [6 empty] | 2025-09-20 | 04/16/2026…RTS Titans | 2
24051-FS45C | TN Titans Stadium | Marc Ribar | 400 | 26 | 26 | FR ACM | 2025-10-24 11:28 | 2025-11-17 | 40 | YES | RTS Titans | AXYZ Titans Line | 2025-10-23 | Clean and Brake | 2025-10-24 | Fab | 2025-11-04 | [6 empty] | 2025-11-14 | 04/16/2026…RTS Titans | 2
24051-FS201 | TN Titans Stadium | Marc Ribar | 400 | 109 | 109 | FR ACM | 2025-03-10 09:04 | 2025-11-21 | 200 | YES | RTS Titans | AXYZ Titans Line | 2025-10-27 | Clean and Brake | 2025-10-29 | Fab | 2025-11-08 | [6 empty] | 2025-11-19 | 04/16/2026…RTS Titans | 2
24051-FS205 | TN Titans Stadium | Marc Ribar | 400 | 118 | 118 | FR ACM | 2025-03-21 05:40 | 2025-11-21 | 300 | YES | RTS Titans | AXYZ Titans Line | 2025-10-25 | Clean and Brake | 2025-10-29 | Fab | 2025-11-08 | [6 empty] | 2025-11-19 | 04/16/2026…RTS Titans | 2
24051-FS213 | TN Titans Stadium | Marc Ribar | 400 | 138 | 138 | FR ACM | 2025-04-07 16:22 | 2025-11-24 | 300 | YES | RTS Titans | AXYZ Titans Line | 2025-10-28 | Clean and Brake | 2025-10-31 | Fab | 2025-11-11 | [6 empty] | 2025-11-21 | 04/16/2026…RTS Titans | 2
24051-FS216 | TN Titans Stadium | Marc Ribar | 400 | 26 | 26 | FR ACM | 2025-10-15 15:56 | 2025-11-24 | 40 | YES | RTS Titans | AXYZ Titans Line | 2025-10-30 | Clean and Brake | 2025-10-31 | Fab | 2025-11-11 | [6 empty] | 2025-11-21 | 04/16/2026…RTS Titans | 2
24051-FS45 | TN Titans Stadium | Marc Ribar | 400 | 78 | 78 | FR ACM | 2025-10-15 16:14 | 2025-11-26 | 140 | YES | RTS Titans | AXYZ Titans Line | 2025-10-31 | Clean and Brake | 2025-11-03 | Fab | 2025-11-13 | [6 empty] | 2025-11-24 | 04/16/2026…RTS Titans | 2
24051-FS219 | TN Titans Stadium | Marc Ribar | 400 | 109 | 109 | FR ACM | 2025-10-21 15:15 | 2025-12-03 | 300 | YES | RTS Titans | AXYZ Titans Line | 2025-11-07 | Clean and Brake | 2025-11-10 | Fab | 2025-11-20 | [6 empty] | 2025-12-01 | 04/16/2026…RTS Titans | 2
24051-FS217 | TN Titans Stadium | Marc Ribar | 400 | 12 | 12 | FR ACM | 2025-10-16 14:27 | 2025-12-05 | 16 | YES | RTS Titans | AXYZ Titans Line | 2025-11-11 | Clean and Brake | 2025-11-12 | Fab | 2025-11-22 | [6 empty] | 2025-12-03 | 04/16/2026…RTS Titans | 2
24051-FS218 | TN Titans Stadium | Marc Ribar | 400 | 97 | 97 | FR ACM | 2025-10-20 08:49 | 2025-12-05 | 180 | YES | RTS Titans | AXYZ Titans Line | 2025-11-10 | Clean and Brake | 2025-11-12 | Fab | 2025-11-22 | [6 empty] | 2025-12-03 | 04/16/2026…RTS Titans | 2
25014-11-ST01 | R&D | TBC | --- | 0 | 1 | Steel Sheet | 2025-11-21 06:54 | 2025-12-06 | 2 | YES | Ready to Ship | TruLaser 3040 | 2025-11-24 | [10 empty] | 2025-12-04 | 04/16/2026…Ready to Ship | 2
25014-11-ST02 | R&D | TBC | --- | 0 | 232 | Alum Tube | 2025-11-21 07:01 | 2025-12-06 | 2 | YES | Ready to Ship | Tube Laser | 2025-11-24 | [10 empty] | 2025-12-04 | 04/16/2026…Ready to Ship | 2
24051-FS46C | TN Titans Stadium | Marc Ribar | 400 | 25 | 25 | FR ACM | 2025-10-16 10:32 | 2025-12-08 | 8 | YES | RTS Titans | AXYZ Titans Line | 2025-11-13 | Clean and Brake | 2025-11-14 | Fab | 2025-11-25 | [6 empty] | 2025-12-05 | 04/16/2026…RTS Titans | 2
24051-FS46 | TN Titans Stadium | Marc Ribar | 400 | 75 | 75 | FR ACM | 2025-10-16 10:26 | 2025-12-08 | 150 | YES | RTS Titans | AXYZ Titans Line | 2025-11-12 | Clean and Brake | 2025-11-14 | Fab | 2025-11-25 | [6 empty] | 2025-12-05 | 04/16/2026…RTS Titans | 2
24051-FS47C | TN Titans Stadium | Marc Ribar | 400 | 99 | 99 | FR ACM | 2025-10-16 14:44 | 2025-12-12 | 16 | YES | RTS Titans | AXYZ Titans Line | 2025-11-17 | Clean and Brake | 2025-11-19 | Fab | 2025-11-29 | [6 empty] | 2025-12-10 | 04/16/2026…RTS Titans | 2
24051-FS48 | TN Titans Stadium | Marc Ribar | 400 | 124 | 124 | FR ACM | 2025-10-16 15:36 | 2025-12-12 | 200 | YES | RTS Titans | AXYZ Titans Line | 2025-11-15 | Clean and Brake | 2025-11-19 | Fab | 2025-11-29 | [6 empty] | 2025-12-10 | 04/16/2026…RTS Titans | 2
24051-FS49 | TN Titans Stadium | Marc Ribar | 400 | 124 | 124 | FR ACM | 2025-10-16 15:47 | 2025-12-15 | 200 | YES | RTS Titans | AXYZ Titans Line | 2025-11-18 | Clean and Brake | 2025-11-21 | Fab | 2025-12-02 | [6 empty] | 2025-12-12 | 04/16/2026…RTS Titans | 2
24051-FS50 | TN Titans Stadium | Marc Ribar | 400 | 124 | 124 | FR ACM | 2025-10-16 15:52 | 2025-12-15 | 200 | YES | RTS Titans | AXYZ Titans Line | 2025-11-18 | Clean and Brake | 2025-11-21 | Fab | 2025-12-02 | [6 empty] | 2025-12-12 | 04/16/2026…RTS Titans | 2
24051-FS50C | TN Titans Stadium | Marc Ribar | 400 | 24 | 24 | FR ACM | 2025-10-16 16:01 | 2025-12-15 | 40 | YES | RTS Titans | AXYZ Titans Line | 2025-11-20 | Clean and Brake | 2025-11-21 | Fab | 2025-12-02 | [6 empty] | 2025-12-12 | 04/16/2026…RTS Titans | 2
25029-FL97 | Lourdes CC Phase 2 | Dillon Bowman | 0 | 0 | 1 | Alum Sheet | 2025-12-15 08:56 | 2025-12-17 | 1 | YES | Ready to Ship | Cidan | 2025-11-21 | Shear | 2025-12-03 | [8 empty] | 2025-12-15 | 04/16/2026…Ready to Ship | 2
25040-FL01 | Moses Lincoln Vitrine | Laura Forero | 0 | 0 | 1 | Alum Sheet | 2025-12-02 14:52 | 2025-12-30 | 1 | YES | Ready to Ship | Cidan | 2025-12-04 | Shear | 2025-12-16 | [8 empty] | 2025-12-27 | 04/16/2026…Ready to Ship | 2
24051-FS59 | TN Titans Stadium | Marc Ribar | 400 | 158 | 158 | FR ACM | 2025-10-22 10:43 | 2026-01-02 | 300 | YES | RTS Titans | AXYZ Titans Line | 2025-12-06 | Clean and Brake | 2025-12-10 | Fab | 2025-12-20 | [6 empty] | 2025-12-31 | 04/16/2026…RTS Titans | 2
25007-BM03 | QTS ATL2 DC10 | Nick Akins | 0 | 0 | 80 | Galv Sheet | 2025-11-10 16:26 | 2026-01-05 | 4 | YES | Ready to Ship | Cidan | 2025-12-10 | Shear | 2025-12-22 | [8 empty] | 2026-01-02 | 04/16/2026…Ready to Ship | 2
25052-BM01 | TEMA Warehouse | Andre Van Der Merwe | 0 | 0 | 16 | Galv Sheet | 2025-11-10 15:43 | 2026-01-05 | 5 | YES | Ready to Ship | Cidan | 2025-12-10 | Shear | 2025-12-22 | [8 empty] | 2026-01-02 | 04/16/2026…Ready to Ship | 2
24051-FS51C | TN Titans Stadium | Marc Ribar | 400 | 40 | 40 | FR ACM | 2025-10-21 10:29 | 2026-01-06 | 40 | YES | RTS Titans | AXYZ Titans Line | 2025-12-12 | Clean and Brake | 2025-12-13 | Fab | 2025-12-24 | [6 empty] | 2026-01-03 | 04/16/2026…RTS Titans | 2
24051-FS51 | TN Titans Stadium | Marc Ribar | 400 | 120 | 120 | FR ACM | 2025-10-21 10:25 | 2026-01-08 | 200 | YES | RTS Titans | AXYZ Titans Line | 2025-12-12 | Clean and Brake | 2025-12-16 | Fab | 2025-12-26 | [6 empty] | 2026-01-06 | 04/16/2026…RTS Titans | 2
24051-FS52C | TN Titans Stadium | Marc Ribar | 400 | 70 | 70 | FR ACM | 2025-10-21 11:03 | 2026-01-13 | 140 | YES | RTS Titans | AXYZ Titans Line | 2025-12-18 | Clean and Brake | 2025-12-20 | Fab | 2025-12-31 | [6 empty] | 2026-01-10 | 04/16/2026…RTS Titans | 2
24051-FS52 | TN Titans Stadium | Marc Ribar | 400 | 210 | 210 | FR ACM | 2025-10-21 10:58 | 2026-01-13 | 320 | YES | RTS Titans | AXYZ Titans Line | 2025-12-16 | Clean and Brake | 2025-12-20 | Fab | 2025-12-31 | [6 empty] | 2026-01-10 | 04/16/2026…RTS Titans | 2
25017-FL99 | Nashville Yards Park | Dillon Bowman | 0 | 0 | 2 | Alum Sheet | 2025-12-23 10:24 | 2026-01-14 | 2 | YES | Ready to Ship | Cidan | 2025-12-19 | Shear | 2025-12-31 | [8 empty] | 2026-01-12 | 04/16/2026…Ready to Ship | 2
25052-FL01 | TEMA Warehouse | Andre Van Der Merwe | 0 | 0 | 10 | Alum Sheet | 2025-11-11 09:40 | 2026-01-15 | 6 | YES | Ready to Ship | Cidan | 2025-12-20 | Shear | 2026-01-01 | [8 empty] | 2026-01-13 | 04/16/2026…Ready to Ship | 2
23028-FS99 | 1000 Church YMCA | Dillon Bowman | 600 | 1 | 1 | FR ACM | 2025-12-08 13:34 | 2026-01-16 | 2 | YES | Ready to Ship | AXYZ Titans Line | 2025-12-23 | Clean and Brake | 2025-12-24 | Fab | 2026-01-03 | [6 empty] | 2026-01-14 | 04/16/2026…Ready to Ship | 2
24051-FS67 | TN Titans Stadium | Marc Ribar | 400 | 14 | 14 | FR ACM | 2025-12-16 11:38 | 2026-01-19 | 16 | YES | RTS Titans | AXYZ Titans Line | 2025-12-25 | Clean and Brake | 2025-12-26 | Fab | 2026-01-06 | [6 empty] | 2026-01-16 | 04/16/2026…RTS Titans | 2
25017-ST02 | Nashville Yards Park | Dillon Bowman | CUSTOM ARCH | 0 | 16 | SS Sheet | 2026-01-13 10:54 | 2026-01-20 | 4 | YES | QC | Brake | 2025-12-27 | TruLaser 3040 | 2026-01-07 | [8 empty] | 2026-01-17 | 04/16/2026…QC | 2
24051-FS54 | TN Titans Stadium | Marc Ribar | 400 | 149 | 149 | FR ACM | 2025-10-21 15:52 | 2026-01-21 | 300 | YES | RTS Titans | AXYZ Titans Line | 2025-12-25 | Clean and Brake | 2025-12-29 | Fab | 2026-01-08 | [6 empty] | 2026-01-19 | 04/16/2026…RTS Titans | 2
24051-FS53 | TN Titans Stadium | Marc Ribar | 400 | 48 | 48 | FR ACM | 2025-10-21 14:42 | 2026-01-21 | 80 | YES | RTS Titans | AXYZ Titans Line | 2025-12-27 | Clean and Brake | 2025-12-29 | Fab | 2026-01-08 | [6 empty] | 2026-01-19 | 04/16/2026…RTS Titans | 2
24019-RO07 | QTS PJC1 DC1 | Dillon Bowman | 400 | 4 | 4 | FR ACM | 2026-01-14 05:56 | 2026-01-21 | 3 | YES | Ready to Ship | AXYZ | 2026-01-07 | Clean and Brake | 2026-01-08 | [8 empty] | 2026-01-19 | 04/16/2026…Ready to Ship | 2
26014-02-ST01 | 2026 R & D | TBC | --- | 0 | 10 | SS Sheet | 2026-01-13 15:24 | 2026-01-22 | 2 | YES | QC | Flat Laser | 2025-12-19 | Powder Coat | 2025-12-23 | [8 empty] | 2026-01-20 | 04/16/2026…QC | 2
24051-FS55 | TN Titans Stadium | Marc Ribar | 400 | 149 | 149 | FR ACM | 2025-10-21 15:57 | 2026-01-22 | 300 | YES | RTS Titans | AXYZ Titans Line | 2025-12-26 | Clean and Brake | 2025-12-30 | Fab | 2026-01-09 | [6 empty] | 2026-01-20 | 04/16/2026…RTS Titans | 2
24071-FS10.R | RS Gass State Lab | Cole Norona | 400 | 0 | 0 | FR ACM | 2026-01-21 08:28 | 2026-01-26 | 1 | YES | Ready to Ship | Shear | 2026-01-12 | [10 empty] | 2026-01-23 | 04/16/2026…Ready to Ship | 2
24051-FS56 | TN Titans Stadium | Marc Ribar | 400 | 149 | 149 | FR ACM | 2025-10-21 16:13 | 2026-01-30 | 300 | YES | RTS Titans | AXYZ Titans Line | 2026-01-03 | Clean and Brake | 2026-01-07 | Fab | 2026-01-17 | [6 empty] | 2026-01-28 | 04/16/2026…RTS Titans | 2
24030-FL02 | Vantage TX-21 | Chris Buttrey | 0 | 0 | 265 | Alum Sheet | 2025-11-03 15:01 | 2026-01-30 | 32 | NO | Partially Shipped | Cidan | 2026-01-05 | Shear | 2026-01-16 | [8 empty] | 2026-01-28 | Chris putting in FL03 Monday 03/23 and needs to ship out 03/27.*03/24 Pushed off until 03/30.*03/30…Checking back in*04/16/2026…Partially Shipped | 2
24051-FS46.1 | TN Titans Stadium | Marc Ribar | 400 | 56 | 56 | FR ACM | 2025-12-18 16:23 | 2026-02-02 | 200 | YES | RTS Titans | AXYZ | 2026-01-08 | Clean and Brake | 2026-01-09 | Fab | 2026-01-20 | [6 empty] | 2026-01-30 | 04/16/2026…RTS Titans | 2
24051-FS72 | TN Titans Stadium | Marc Ribar | 400 | 104 | 104 | FR ACM | 2025-12-18 10:38 | 2026-02-02 | 200 | YES | RTS Titans | AXYZ | 2026-01-07 | Clean and Brake | 2026-01-09 | Fab | 2026-01-20 | [6 empty] | 2026-01-30 | 04/16/2026…RTS Titans | 2
24051-FS73 | TN Titans Stadium | Marc Ribar | 400 | 66 | 66 | FR ACM | 2025-12-18 11:12 | 2026-02-02 | 120 | YES | RTS Titans | AXYZ | 2026-01-07 | Clean and Brake | 2026-01-09 | Fab | 2026-01-20 | [6 empty] | 2026-01-30 | 04/16/2026…RTS Titans | 2
24051-FS56C | TN Titans Stadium | Marc Ribar | 400 | 149 | 149 | FR ACM | 2025-10-22 08:48 | 2026-02-02 | 300 | YES | RTS Titans | AXYZ Titans Line | 2026-01-06 | Clean and Brake | 2026-01-09 | Fab | 2026-01-20 | [6 empty] | 2026-01-30 | 04/16/2026…RTS Titans | 2
24051-FS74 | TN Titans Stadium | Marc Ribar | 400 | 39 | 39 | FR ACM | 2025-12-18 15:11 | 2026-02-02 | 300 | YES | RTS Titans | AXYZ | 2026-01-08 | Clean and Brake | 2026-01-09 | Fab | 2026-01-20 | [6 empty] | 2026-01-30 | 04/16/2026…RTS Titans | 2
24051-FS25.1 FM | TN Titans Stadium | Marc Ribar | 400 | 2 | 2 | FR ACM | 2025-12-18 11:28 | 2026-02-05 | 1 | YES | RTS Titans | AXYZ Titans Line | 2026-01-12 | Clean and Brake | 2026-01-13 | Fab | 2026-01-23 | [6 empty] | 2026-02-03 | 04/16/2026…RTS Titans | 2
24051-BM02 | TN Titans Stadium | Marc Ribar | 0 | 0 | 141 | Alum Sheet | 2026-01-05 13:34 | 2026-02-06 | 6 | YES | RTS Titans | Cidan | 2026-01-12 | Shear | 2026-01-23 | [8 empty] | 2026-02-04 | 04/16/2026…RTS Titans | 2
24051-FS221 | TN Titans Stadium | Marc Ribar | 400 | 13 | 13 | FR ACM | 2025-12-19 11:17 | 2026-02-09 | 16 | YES | RTS Titans | AXYZ Titans Line | 2026-01-15 | Clean and Brake | 2026-01-16 | Fab | 2026-01-27 | [6 empty] | 2026-02-06 | 04/16/2026…RTS Titans | 2
24051-FS43.1 | TN Titans Stadium | Marc Ribar | 400 | 30 | 30 | FR ACM | 2025-12-19 09:24 | 2026-02-09 | 80 | YES | RTS Titans | AXYZ Titans Line | 2026-01-15 | Clean and Brake | 2026-01-16 | Fab | 2026-01-27 | [6 empty] | 2026-02-06 | 04/16/2026…RTS Titans | 2
24051-FS16C | TN Titans Stadium | Marc Ribar | 400 | 27 | 27 | FR ACM | 2025-12-18 15:39 | 2026-02-09 | 40 | YES | RTS Titans | AXYZ Titans Line | 2026-01-15 | Clean and Brake | 2026-01-16 | Fab | 2026-01-27 | [6 empty] | 2026-02-06 | 04/16/2026…RTS Titans | 2
24051-FS76 | TN Titans Stadium | Marc Ribar | 400 | 152 | 152 | FR ACM | 2025-12-19 11:43 | 2026-02-09 | 300 | YES | RTS Titans | AXYZ | 2026-01-13 | Clean and Brake | 2026-01-16 | Fab | 2026-01-27 | [6 empty] | 2026-02-06 | 04/16/2026…RTS Titans | 2
24051-FS77 | TN Titans Stadium | Marc Ribar | 400 | 209 | 209 | FR ACM | 2025-12-19 16:11 | 2026-02-09 | 400 | YES | RTS Titans | AXYZ | 2026-01-12 | Clean and Brake | 2026-01-16 | Fab | 2026-01-27 | [6 empty] | 2026-02-06 | 04/16/2026…RTS Titans | 2
24039-FS14 | The Visionary | Carlos Silva | PEX | 176 | 197 | FR ACM | 2025-12-01 16:31 | 2026-02-10 | 80 | YES | Partially Shipped | AXYZ Titans Line | 2026-01-13 | Clean and Brake | 2026-01-17 | Fab | 2026-01-28 | [6 empty] | 2026-02-07 | 04/16/2026…Partially Shipped | 2
24051-FS58 | TN Titans Stadium | Marc Ribar | 400 | 158 | 158 | FR ACM | 2025-10-22 10:32 | 2026-02-11 | 300 | YES | RTS Titans | AXYZ Titans Line | 2026-01-15 | Clean and Brake | 2026-01-19 | Fab | 2026-01-29 | [6 empty] | 2026-02-09 | 04/16/2026…RTS Titans | 2
24051-FS57 | TN Titans Stadium | Marc Ribar | 400 | 158 | 158 | FR ACM | 2025-10-22 10:24 | 2026-02-12 | 300 | YES | RTS Titans | AXYZ Titans Line | 2026-01-16 | Clean and Brake | 2026-01-20 | Fab | 2026-01-30 | [6 empty] | 2026-02-10 | 04/16/2026…RTS Titans | 2
24039-FS15 | The Visionary | Carlos Silva | PEX | 73 | 99 | FR ACM | 2025-12-02 09:06 | 2026-02-12 | 80 | YES | Partially Shipped | AXYZ | 2026-01-17 | Clean and Brake | 2026-01-20 | Fab | 2026-01-30 | [6 empty] | 2026-02-10 | 04/16/2026…Partially Shipped | 2
24051-FS42.1 | TN Titans Stadium | Marc Ribar | 400 | 98 | 98 | FR ACM | 2025-12-20 05:46 | 2026-02-13 | 200 | YES | RTS Titans | AXYZ Titans Line | 2026-01-19 | Clean and Brake | 2026-01-21 | Fab | 2026-01-31 | [6 empty] | 2026-02-11 | 04/16/2026…RTS Titans | 2
24051-FS75 | TN Titans Stadium | Marc Ribar | 400 | 83 | 83 | FR ACM | 2026-01-12 10:58 | 2026-02-13 | 160 | YES | RTS Titans | AXYZ | 2026-01-19 | Clean and Brake | 2026-01-21 | Fab | 2026-01-31 | [6 empty] | 2026-02-11 | 04/16/2026…RTS Titans | 2
24051-FS78 | TN Titans Stadium | Marc Ribar | 400 | 180 | 180 | FR ACM | 2025-12-21 05:56 | 2026-02-13 | 300 | YES | RTS Titans | [12 empty] | 2026-02-11 | 04/16/2026…RTS Titans | 2
24051-FS78.1 | TN Titans Stadium | Marc Ribar | 400 | 168 | 168 | FR ACM | 2025-12-21 06:08 | 2026-02-13 | 300 | YES | RTS Titans | AXYZ Titans Line | 2026-01-17 | Clean and Brake | 2026-01-21 | Fab | 2026-01-31 | [6 empty] | 2026-02-11 | 04/16/2026…RTS Titans | 2
24051-FS59C | TN Titans Stadium | Marc Ribar | 400 | 158 | 158 | FR ACM | 2025-10-22 10:59 | 2026-02-16 | 300 | YES | RTS Titans | AXYZ Titans Line | 2026-01-20 | Clean and Brake | 2026-01-23 | Fab | 2026-02-03 | [6 empty] | 2026-02-13 | 04/16/2026…RTS Titans | 2
24026-BM01 | 1740 Division | Chris Buttrey | 0 | 0 | 200 | Galv Sheet | 2025-10-17 15:04 | 2026-02-16 | 16 | YES | Ready to Ship | Cidan | 2026-01-21 | Shear | 2026-02-02 | [8 empty] | 2026-02-13 | 04/16/2026…Ready to Ship | 2
25008-FS05 | Columbia State Tech Center | Laura Forero | 400 CAULK | 101 | 101 | FR ACM | 2025-12-12 13:30 | 2026-02-18 | 130 | YES | Shipped To Painter | AXYZ Titans Line | 2026-01-23 | Clean and Brake | 2026-01-26 | Fab | 2026-02-05 | [6 empty] | 2026-02-16 | 04/16/2026…Shipped To Painter | 2
24079-FL07 | Nashville Youth Campus | Joe Hoyle | 0 | 0 | 220 | Alum Sheet | 2026-01-29 15:05 | 2026-02-19 | 6 | YES | Ready to Ship | Cidan | 2026-01-24 | Shear | 2026-02-05 | [8 empty] | 2026-02-17 | 04/16/2026…Ready to Ship | 2
24079-FL08 | Nashville Youth Campus | Joe Hoyle | 0 | 0 | 160 | Alum Sheet | 2026-01-29 15:17 | 2026-02-19 | 6 | YES | Ready to Ship | Cidan | 2026-01-24 | Shear | 2026-02-05 | [8 empty] | 2026-02-17 | 04/16/2026…Ready to Ship | 2
24079-FL09 | Nashville Youth Campus | Joe Hoyle | 0 | 0 | 295 | Alum Sheet | 2026-01-29 15:31 | 2026-02-19 | 8 | YES | Ready to Ship | Cidan | 2026-01-24 | Shear | 2026-02-05 | [8 empty] | 2026-02-17 | 04/16/2026…Ready to Ship | 2
24081-FS01 | DLR DFW37 | Cole Norona | 400 | 109 | 308 | Alum Sheet | 2026-01-07 15:34 | 2026-02-20 | 170 | YES | Shipped To Painter | 7000 TruMatic | 2025-12-24 | Brake | 2026-01-03 | Clean and Brake | 2026-01-14 | Extrusion Saw | 2026-01-24 | Fab | 2026-02-04 | Post Paint | 2026-02-14 | 2026-02-18 | 04/16/2026…Shipped To Painter | 2
24081-FS02 | DLR DFW37 | Cole Norona | 400 | 123 | 349 | Alum Sheet | 2026-01-07 15:46 | 2026-02-20 | 195 | YES | Shipped To Painter | 7000 TruMatic | 2026-01-03 | Brake | 2026-01-14 | Extrusion Saw | 2026-01-24 | Fab | 2026-02-04 | Post Paint | 2026-02-14 |  |  | 2026-02-18 | 04/16/2026…Shipped To Painter | 2
24081-FS03 | DLR DFW37 | Cole Norona | 400 | 24 | 88 | Alum Sheet | 2026-01-07 15:54 | 2026-02-20 | 40 | YES | Shipped To Painter | 7000 TruMatic | 2026-01-03 | Clean and Brake | 2026-01-14 | Extrusion Saw | 2026-01-24 | Fab | 2026-02-04 | Post Paint | 2026-02-14 |  |  | 2026-02-18 | 04/16/2026…Shipped To Painter | 2
24081-FS04 | DLR DFW37 | Cole Norona | 400 | 94 | 243 | Alum Sheet | 2026-01-07 15:58 | 2026-02-20 | 150 | YES | Shipped To Painter | 7000 TruMatic | 2025-12-24 | Brake | 2026-01-03 | Clean and Brake | 2026-01-14 | Extrusion Saw | 2026-01-24 | Fab | 2026-02-04 | Post Paint | 2026-02-14 | 2026-02-18 | 04/16/2026…Shipped To Painter | 2
24081-FS05 | DLR DFW37 | Cole Norona | 400 | 111 | 345 | Alum Sheet | 2026-01-09 09:51 | 2026-02-20 | 180 | YES | Shipped To Painter | 7000 TruMatic | 2026-01-24 | Brake | 2026-02-04 | Post Paint | 2026-02-14 | [6 empty] | 2026-02-18 | 04/16/2026…Shipped To Painter | 2
24081-FL01 | DLR DFW37 | Cole Norona | 0 | 0 | 118 | Alum Sheet | 2026-01-30 08:23 | 2026-02-20 | 25 | YES | Shipped To Painter | Brake | 2026-01-23 | Post Paint | 2026-02-03 | Shear | 2026-02-06 | [6 empty] | 2026-02-18 | 04/16/2026…Shipped To Painter | 2
24051-FS78.2 | TN Titans Stadium | Marc Ribar | 400 | 348 | 348 | FR ACM | 2025-12-21 06:18 | 2026-02-20 | 600 | YES | RTS Titans | AXYZ | 2026-01-20 | Clean and Brake | 2026-01-28 | Fab | 2026-02-07 | [6 empty] | 2026-02-18 | 04/16/2026…RTS Titans | 2
24079-FS101 | Nashville Youth Campus | Joe Hoyle | 400 | 173 | 176 | FR ACM | 2025-12-16 07:38 | 2026-02-23 | 200 | YES | Ready to Ship | AXYZ Titans Line | 2026-01-26 | Clean and Brake | 2026-01-30 | Fab | 2026-02-10 | [6 empty] | 2026-02-20 | 04/16/2026…Ready to Ship | 2
24079-FS101.1 | Nashville Youth Campus | Joe Hoyle | 400 | 163 | 189 | FR ACM | 2026-03-24 08:54 | 2026-02-23 | 200 | YES | Ready to Ship | AXYZ Titans Line | 2026-01-27 | Clean and Brake | 2026-01-30 | Fab | 2026-02-10 | [6 empty] | 2026-02-20 | 04/16/2026…Ready to Ship | 2
25025-BM100 | QTS MAN1 DC6 | Dillon Bowman | 0 | 0 | 870 | Galv Sheet | 2026-02-11 00:46 | 2026-02-25 | 60 | YES | Shipped | Brake | 2026-01-31 | Shear | 2026-02-11 | [8 empty] | 2026-02-23 | 04/16/2026…Shipped | 2
25035-FS02.1 | Titans Jabez | Marc Ribar | 400 | 0 | 27 | FR ACM | 2026-01-16 08:35 | 2026-02-26 | 600 | YES | RTS Titans | AXYZ | 2026-02-02 | Clean and Brake | 2026-02-02 | Shear | 2026-02-12 | [6 empty] | 2026-02-24 | 04/16/2026…RTS Titans | 2
25035-FS02 | Titans Jabez | Marc Ribar | CUSTOM ARCH | 109 | 600 | Alum Sheet | 2026-01-05 11:00 | 2026-02-27 | 250 | YES | Shipped To Painter | 7000 TruMatic | 2026-01-10 | Brake | 2026-01-21 | Clean and Brake | 2026-01-31 | Fab | 2026-02-11 | Post Paint | 2026-02-21 |  |  | 2026-02-25 | 04/16/2026…Shipped To Painter | 2
24081-FL02 | DLR DFW37 | Cole Norona | 0 | 0 | 78 | Alum Sheet | 2026-02-12 07:55 | 2026-02-27 | 2 | YES | Shipped To Painter | Brake | 2026-01-31 | Post Paint | 2026-02-11 | TruLaser 3040 | 2026-02-14 | [6 empty] | 2026-02-25 | 04/16/2026…Shipped To Painter | 2
24051-FS209.1 | TN Titans Stadium | Marc Ribar | 400 | 36 | 76 | FR ACM | 2026-01-09 15:46 | 2026-03-02 | 40 | YES | RTS Titans | AXYZ Titans Line | 2026-02-05 | Clean and Brake | 2026-02-06 | Fab | 2026-02-17 | [6 empty] | 2026-02-27 | Need 4 Pcs rolled**Look for RP's**03/23 Fab-Need done ASAP*03/26…RTS*04/16/2026…RTS Titans | 2
24051-FS86 | TN Titans Stadium | Marc Ribar | 400 | 38 | 38 | FR ACM | 2026-02-13 15:30 | 2026-03-04 | 40 | YES | RTS Titans | AXYZ Titans Line | 2026-02-07 | Clean and Brake | 2026-02-09 | Fab | 2026-02-19 | [6 empty] | 2026-03-02 | 04/16/2026…RTS Titans | 2
25002-BM06 | Med Center Health | Carlos Silva | 0 | 0 | 29 | Steel Sheet | 2026-02-18 11:07 | 2026-03-04 | 4 | YES | Shipped To Painter | Powder Coat | 2026-01-22 | TruLaser 3040 | 2026-02-19 | [8 empty] | 2026-03-02 | 04/16/2026…Shipped To Painter | 2
25035-FS03 | Titans Jabez | Marc Ribar | CUSTOM ARCH | 160 | 320 | Alum Sheet | 2026-01-05 11:13 | 2026-03-06 | 240 | YES | Shipped To Painter | 7000 TruMatic | 2025-12-24 | Brake | 2026-01-03 | Clean and Brake | 2026-01-14 | Fab | 2026-01-24 | Powder Coat | 2026-02-04 |  |  | 2026-03-04 | 04/16/2026…Shipped To Painter | 2
23028-FL205 | 1000 Church YMCA | Dillon Bowman | 0 | 0 | 4 | Alum Sheet | 2026-03-02 12:34 | 2026-03-06 | 2 | YES | Ready to Ship | Cidan | 2026-02-09 | Shear | 2026-02-20 | [8 empty] | 2026-03-04 | 04/16/2026…Ready to Ship | 2
24051-FS71.1 | TN Titans Stadium | Marc Ribar | 400 | 0 | 0 | Alum Structural Shape | 2026-03-11 16:12 | 2026-03-12 | 4 | YES | RTS Titans | Extrusion Saw | 2026-02-27 | [10 empty] | 2026-03-10 | 04/16/2026…RTS Titans | 2
24051-FS224 | TN Titans Stadium | Marc Ribar | 400 | 2 | 2 | FR ACM | 2026-02-05 11:31 | 2026-03-16 | 4 | YES | RTS Titans | AXYZ Titans Line | 2026-02-19 | Clean and Brake | 2026-02-20 | Fab | 2026-03-03 | [6 empty] | 2026-03-13 | 03/23...Next for Titans--1 of 3 still late*03/24 Corrections*03/26…Titans Line*03/30…Crating*03/31…Crating*04/16/2026…RTS Titans | 2
24051-FS29C | TN Titans Stadium | Marc Ribar | 400 | 26 | 26 | FR ACM | 2026-02-02 09:42 | 2026-03-16 | 40 | YES | RTS Titans | AXYZ Titans Line | 2026-02-19 | Clean and Brake | 2026-02-20 | Fab | 2026-03-03 | [6 empty] | 2026-03-13 | 04/16/2026…RTS Titans | 2
24051-FS82 | TN Titans Stadium | Marc Ribar | 400 | 4 | 4 | FR ACM | 2026-02-02 13:24 | 2026-03-16 | 8 | YES | RTS Titans | AXYZ Titans Line | 2026-02-19 | Clean and Brake | 2026-02-20 | Fab | 2026-03-03 | [6 empty] | 2026-03-13 | 04/16/2026…RTS Titans | 2
24051-FS83 | TN Titans Stadium | Marc Ribar | 400 | 4 | 4 | FR ACM | 2026-02-02 13:26 | 2026-03-16 | 8 | YES | RTS Titans | AXYZ Titans Line | 2026-02-19 | Clean and Brake | 2026-02-20 | Fab | 2026-03-03 | [6 empty] | 2026-03-13 | 04/16/2026…RTS Titans | 2
24051-FS84 | TN Titans Stadium | Marc Ribar | 400 | 24 | 24 | FR ACM | 2026-02-02 13:59 | 2026-03-16 | 40 | YES | RTS Titans | AXYZ Titans Line | 2026-02-19 | Clean and Brake | 2026-02-20 | Fab | 2026-03-03 | [6 empty] | 2026-03-13 | 04/16/2026…RTS Titans | 2
24051-FS85 | TN Titans Stadium | Marc Ribar | 400 | 4 | 4 | FR ACM | 2026-02-02 14:51 | 2026-03-16 | 8 | YES | RTS Titans | AXYZ Titans Line | 2026-02-19 | Clean and Brake | 2026-02-20 | Fab | 2026-03-03 | [6 empty] | 2026-03-13 | 04/16/2026…RTS Titans | 2
24051-FS26C | TN Titans Stadium | Marc Ribar | 400 | 26 | 26 | FR ACM | 2026-02-02 09:22 | 2026-03-16 | 40 | YES | RTS Titans | AXYZ Titans Line | 2026-02-19 | Clean and Brake | 2026-02-20 | Fab | 2026-03-03 | [6 empty] | 2026-03-13 | 04/16/2026…RTS Titans | 2
25017-RO01 | Nashville Yards Park | Dillon Bowman | 400 | 1 | 3 | FR ACM | 2026-03-02 15:57 | 2026-03-16 | 3 | NO | Ready to Ship | AXYZ Titans Line | 2026-02-19 | Clean and Brake | 2026-02-20 | Fab | 2026-03-03 | [6 empty] | 2026-03-13 | 04/16/2026…Ready to Ship | 2
24051-FS13C | TN Titans Stadium | Marc Ribar | 400 | 106 | 106 | FR ACM | 2026-02-05 11:25 | 2026-03-20 | 200 | YES | RTS Titans | AXYZ Titans Line | 2026-02-23 | Clean and Brake | 2026-02-25 | Fab | 2026-03-07 | [6 empty] | 2026-03-18 | 04/16/2026…RTS Titans | 2
1040-30791-ST08 | AFI - YANCEY | Hannah Sadloski, Lisa Ellison | --- | 0 | 120 | Alum Tube | 2026-02-19 08:10 | 2026-03-20 | 0 | YES | Ready to Ship | Assembly | 2026-02-25 | Extrusion Saw | 2026-03-07 | [8 empty] | 2026-03-18 | 04/16/2026…Ready to Ship | 2
24051-FS76.1 | TN Titans Stadium | Marc Ribar | 400 | 74 | 74 | FR ACM | 2026-02-12 13:56 | 2026-03-26 | 200 | YES | RTS Titans | AXYZ Titans Line | 2026-02-28 | Clean and Brake | 2026-03-03 | Fab | 2026-03-13 | [6 empty] | 2026-03-24 | 04/16/2026…RTS Titans | 2
24081-RO01 | DLR DFW37 | Cole Norona | 400 | 1 | 1 | Alum Sheet | 2026-03-23 08:56 | 2026-03-26 | 2 | YES | Shipped To Painter | 7000 TruMatic | 2026-02-17 | Brake | 2026-02-27 | Fab | 2026-03-10 | Post Paint | 2026-03-20 |  |  |  |  | 2026-03-24 | 04/16/2026…Shipped To Painter | 2
24069-RM04 | TCAT Pulaski | Chris Buttrey | GENESIS | 1 | 1 | Alum Sheet | 2026-03-02 07:46 | 2026-03-30 | 4 | YES | Shipped To Painter | 7000 TruMatic | 2026-03-03 | Brake | 2026-03-13 | Post Paint | 2026-03-24 | [6 empty] | 2026-03-27 | 04/16/2026…Shipped To Painter | 2
25022-FS11 | Vantage VA15 | Thomas Mooers | 400 | 72 | 72 | FR ACM | 2026-03-06 16:08 | 2026-04-06 | 8 | YES | Ready to Ship | AXYZ Titans Line | 2026-03-11 | Clean and Brake | 2026-03-13 | Fab | 2026-03-24 | [6 empty] | 2026-04-03 | 04/16/2026…Ready to Ship | 2
25022-FS07 | Vantage VA15 | Thomas Mooers | 400 | 52 | 0 | FR ACM | 2026-02-24 10:41 | 2026-04-07 | 8 | YES | Ready to Ship | AXYZ Titans Line | 2026-03-13 | Clean and Brake | 2026-03-14 | Fab | 2026-03-25 | [6 empty] | 2026-04-04 | 04/16/2026…Ready to Ship | 2
25022-FS10 | Vantage VA15 | Thomas Mooers | 400 | 200 | 200 | FR ACM | 2026-03-06 15:59 | 2026-04-07 | 16 | YES | Ready to Ship | AXYZ Titans Line | 2026-03-10 | Clean and Brake | 2026-03-14 | Fab | 2026-03-25 | [6 empty] | 2026-04-04 | 04/16/2026…Ready to Ship | 2
25031-FL06 | LLU Mars US Warehouse | Laura Forero | --- | 0 | 2 | Alum Sheet | 2026-04-06 14:59 | 2026-04-07 | 1 | YES | Shipped | Cidan | 2026-03-12 | Shear | 2026-03-24 | [8 empty] | 2026-04-04 | 04/16/2026…Shipped | 2
25022-FS08 | Vantage VA15 | Thomas Mooers | 400 | 60 | 60 | FR ACM | 2026-02-25 16:00 | 2026-04-08 | 8 | YES | Ready to Ship | AXYZ Titans Line | 2026-03-13 | Clean and Brake | 2026-03-16 | Fab | 2026-03-26 | [6 empty] | 2026-04-06 | 04/16/2026…Ready to Ship | 2
24079-FL13 | Nashville Youth Campus | Joe Hoyle | 0 | 0 | 146 | Alum Sheet | 2026-03-24 14:27 | 2026-04-10 | 6 | YES | Ready to Ship | Cidan | 2026-03-16 | Shear | 2026-03-27 | [8 empty] | 2026-04-08 | 04/16/2026…Ready to Ship | 2
26014-05-FS01
24071-FS11
24051-FS88
24074-FS06
25075-FS01
24069-RM05
25007-RM01
25061-BM01
25025-FL11
25025-RO02
24039-FL35
24039-BM18
25061-FS01
25022-FS12
24051-RP13
24051-RP14
24051-RP15
24051-RP17
24079-RP03
24071-RP14
Formulas:
Date Submitted = IF([ID]="","",IFERROR(VLOOKUP([ID],'Production Schedule'!$B:$FU,47,FALSE),""))
Ship Target = IF([ID]="","",IFERROR(VLOOKUP([ID],'Production Schedule'!$B:$FU,54,FALSE),""))
Crating By = IF([Ship Target]="","",WORKDAY.INTL([Ship Target],-2,"0000001"))

## Comments
Row 6 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | Issiah Havens | 04/14/25 8:42 AM
Row 6 | @mribar@jwmcd.com Off hold. No parapets among these moonstone panels. | Denis Usatenko | 03/25/25 7:40 AM
Row 6 | @mribar@jwmcd.com On Hold | Denis Usatenko | 03/21/25 1:25 PM
Row 7 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 10/21/25 3:33 PM
Row 7 | @hstakhurskyi@jwmcd.com Corrections required | Denis Usatenko | 10/21/25 10:37 AM
Row 7 | This release is no longer on hold. Please proceed with fabrication tickets. | Marc Ribar | 10/13/25 2:52 PM
Row 7 | @mribar@jwmcd.com On Hold | Denis Usatenko | 03/21/25 1:26 PM
Row 8 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 10/23/25 7:28 AM
Row 8 | @hstakhurskyi@jwmcd.com Corrections required | Denis Usatenko | 10/22/25 1:27 PM
Row 8 | @dusatenko@jwmcd.com THIS RELEASE IS NOW OFF HOLD. PLEASE PROCEED AND DIMENSION PER OUR LATEST SET OF SHOPS | Marc Ribar | 10/16/25 8:26 AM
Row 8 | @mribar@jwmcd.com On Hold | Denis Usatenko | 03/21/25 1:28 PM
Row 9 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | Issiah Havens | 04/15/25 8:11 AM
Row 10 | @dusatenko@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 02/25/26 9:13 AM
Row 10 | @hstakhurskyi@jwmcd.com Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\03_Check\24051 SOUTH ELEVATION\24051FS209.1 | Denis Usatenko | 02/24/26 10:54 AM
Row 11 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | Issiah Havens | 04/15/25 8:20 AM
Row 12 | Install drawings brought to the floor | Chance Dill | 03/02/26 8:52 AM
Row 12 | @cdill@jwmcd.com @jdavis@jwmcd.com programmed | Issiah Havens | 02/25/26 10:14 AM
Row 12 | @dusatenko@jwmcd.com working on it now | Issiah Havens | 02/25/26 8:12 AM
Row 12 | @ajurado@jwmcd.com @ihavens@jwmcd.com Is this back on your radars? | Denis Usatenko | 02/25/26 8:06 AM
Row 12 | @dusatenko@jwmcd.com Will this be out today? | Drew Adams | 02/25/26 7:01 AM
| Should be. We had to redraw some parts becasue we would have ran out of matherial otherwise. | Denis Usatenko | 02/25/26 8:04 AM
Row 12 | @cdill@jwmcd.com Separate the panels into part a and b please. | Denis Usatenko | 02/24/26 12:13 PM
Row 12 | @csilva@jwmcd.com We are 3 sheets short of fulfilling this order. We have 74 sheets of this material in stock, but need at least 77 sheets of 62 X 196. How do we proceed? @ajurado@jwmcd.com @jmcpherson@jwmcd.com @dusatenko@jwmcd.com | Issiah Havens | 02/24/26 10:55 AM
Row 12 | @cdill@jwmcd.com Corrections required. | Denis Usatenko | 02/23/26 9:12 AM
Row 12 | @dusatenko@jwmcd.com at this link you will find a new scan that shows the wall that was with plastic before. Q:\Jobs\25002 - Med Center Health\03_Engineering\02_FD Docs\MCH - SOUTH SCAN 01.20 | Carlos Silva | 01/20/26 12:58 PM
| This scan is not exported, I cannot use it. | Denis Usatenko | 01/23/26 5:02 PM
| I can use it. | Denis Usatenko | 01/27/26 10:55 AM
| thank you | Carlos Silva | 01/27/26 12:44 PM
Row 12 | @csilva@jwmcd.com Elevations on 227 are nothing but plastic on this scan. There is one place that looks finished on level one, we can project this or need a new scan. Let us know. Will need the dims for the upper soffit and the parapet like we have in the past. | Denis Usatenko | 01/15/26 3:58 PM
Row 13 | @ghoyle@jwmcd.com | Denis Usatenko | 03/11/26 1:13 PM
Row 13 | @dusatenko@jwmcd.com Sketches are ready to check. "Q:\Jobs\25002 - Med Center Health\03_Engineering\03_FS_Issues\03_Check\25002FS11.1\25002FS11.1 Check Set.pdf" | Gabriela Hoyle | 02/27/26 8:36 AM
Row 13 | @csilva@jwmcd.com This is not happening. 4 day turn around on rolled panels for which dims just came in.... @jmcpherson@jwmcd.com | Denis Usatenko | 02/05/26 12:39 PM
Row 14 | @aniedfeld@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 01/14/26 8:25 AM
Row 14 | @aniedfeld@jwmcd.com Corrections required. | Denis Usatenko | 01/12/26 7:02 PM
Row 14 | Direction Received, Expansion Joint Deleted Please proceed as is, no change. Please let me know of Schedule Impacts. @dusatenko@jwmcd.com @aniedfeld@jwmcd.com | Dillon Bowman | 01/08/26 7:06 AM
Row 14 | Oh hold due to expansion joint. | Denis Usatenko | 12/22/25 9:01 AM
Row 16 | print everything in the print all folder | Arnold Jurado | 01/26/26 10:53 AM
| @aniedfeld@jwmcd.com | Arnold Jurado | 01/26/26 10:53 AM
Row 16 | @aniedfeld@jwmcd.com @jdavis@jwmcd.com programmed | Arnold Jurado | 01/26/26 10:52 AM
Row 17 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 11/07/25 9:33 AM
Row 17 | @hstakhurskyi@jwmcd.com Corrections required | Denis Usatenko | 11/05/25 4:15 PM
Row 18 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 11/07/25 9:58 AM
Row 18 | @hstakhurskyi@jwmcd.com Corrections required | Denis Usatenko | 11/05/25 4:26 PM
Row 18 | @dusatenko@jwmcd.com YOU CAN RUN THIS WITH FS 47. IM USING THE C DESIGNATION TO TRACK THE COPING THAT IS RELEASED. | Marc Ribar | 10/16/25 2:49 PM
| I will have to combine the cards. Are you ok with that? Leave it as 47 or 47C? | Denis Usatenko | 10/16/25 3:13 PM
| OKAY - JUST LEAVE IT ALONE. I WANT TO TRACK COPING SEPARATLY | Marc Ribar | 10/16/25 3:27 PM
Row 19 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 11/18/25 12:00 PM
Row 19 | @hstakhurskyi@jwmcd.com NO Corrections Required | Denis Usatenko | 11/13/25 7:06 AM
Row 20 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 11/18/25 12:19 PM
Row 20 | @hstakhurskyi@jwmcd.com NO Corrections Required | Denis Usatenko | 11/13/25 7:06 AM
Row 21 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 11/18/25 1:32 PM
Row 21 | @hstakhurskyi@jwmcd.com Corrections Required | Denis Usatenko | 11/13/25 7:06 AM
Row 22 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 11/18/25 2:08 PM
Row 22 | @hstakhurskyi@jwmcd.com NO Corrections Required | Denis Usatenko | 11/13/25 7:06 AM
Row 23 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 11/18/25 2:40 PM
Row 23 | @hstakhurskyi@jwmcd.com NO Corrections Required | Denis Usatenko | 11/13/25 7:06 AM
Row 24 | @jdavis@jwmcd.com @hstakhurskyi@jwmcd.com PROGRAMMED | Issiah Havens | 11/18/25 3:00 PM
Row 24 | @hstakhurskyi@jwmcd.com NO Corrections Required | Denis Usatenko | 11/13/25 7:07 AM
Row 25 | @jdavis@jwmcd.com @hstakhurskyi@jwmcd.com PROGRAMMED | Issiah Havens | 10/29/25 3:37 PM
Row 25 | @hstakhurskyi@jwmcd.com No corrections required | Denis Usatenko | 10/28/25 4:58 PM
Row 26 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 10/29/25 3:47 PM
Row 26 | @hstakhurskyi@jwmcd.com No corrections required | Denis Usatenko | 10/28/25 5:00 PM
Row 27 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 10/29/25 3:56 PM
Row 27 | @hstakhurskyi@jwmcd.com Corrections required | Denis Usatenko | 10/28/25 5:02 PM
Row 28 | @jdavis@jwmcd.com @aniedfeld@jwmcd.com PROGRAMMED | Issiah Havens | 01/28/26 8:13 AM
Row 29 | @jdavis@jwmcd.com PROGRAMMED. @aniedfeld@jwmcd.com please print all programming documents in the "PROGRAMMING DOCS" folder | Issiah Havens | 01/27/26 2:32 PM
Row 32 | @aniedfeld@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 01/22/26 2:34 PM
Row 33 | @aniedfeld@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 01/22/26 3:22 PM
Row 33 | @aniedfeld@jwmcd.com Correcitons required | Denis Usatenko | 01/21/26 5:18 PM
Row 34 | @aniedfeld@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 01/22/26 4:00 PM
Row 35 | @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 01/30/26 1:17 PM
Row 36 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 02/12/26 11:44 AM
Row 36 | @hstakhurskyi@jwmcd.com Corrections required. | Denis Usatenko | 02/10/26 6:30 PM
Row 37 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 02/12/26 10:31 AM
Row 37 | @hstakhurskyi@jwmcd.com Corrections required. | Denis Usatenko | 02/10/26 6:50 PM
Row 38 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 12/12/25 9:53 AM
Row 38 | @hstakhurskyi@jwmcd.com No corrections required | Denis Usatenko | 12/10/25 6:47 AM
Row 39 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 12/12/25 9:44 AM
Row 39 | @hstakhurskyi@jwmcd.com No corrections required | Denis Usatenko | 12/10/25 6:50 AM
Row 40 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 12/18/25 7:32 AM
Row 40 | @hstakhurskyi@jwmcd.com No corrections required | Denis Usatenko | 12/16/25 5:00 PM
Row 41 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 12/18/25 7:49 AM
Row 41 | @hstakhurskyi@jwmcd.com No correcitons required. | Denis Usatenko | 12/16/25 5:02 PM
Row 42 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 12/18/25 8:04 AM
Row 42 | @hstakhurskyi@jwmcd.com No Corrections required | Denis Usatenko | 12/16/25 5:05 PM
Row 43 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 12/18/25 8:17 AM
Row 43 | @hstakhurskyi@jwmcd.com No corrections required. | Denis Usatenko | 12/16/25 5:06 PM
Row 44 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 12/12/25 8:27 AM
Row 44 | @hstakhurskyi@jwmcd.com Corrections required | Denis Usatenko | 12/10/25 6:42 AM
Row 45 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 12/12/25 9:30 AM
Row 45 | @hstakhurskyi@jwmcd.com No Corrections required | Denis Usatenko | 12/10/25 6:45 AM
Row 46 | Denis, here are those updates for the vestible. I did not send you this update. My apologies. New Scans and Field Notes in the Job Folder. @dusatenko@jwmcd.com @tmooers@jwmcd.com | Dillon Bowman | 02/13/26 10:38 AM
Row 46 | Couple Updates from the Field | Dillon Bowman | 01/20/26 1:29 PM
Row 46 | @dbowman@jwmcd.com This Vestibule is missing all of the glass. I do not know how to even begin guessing where it will land/be installed. Can you please work on getting that information filled in? | Denis Usatenko | 12/22/25 9:31 AM
| I'll work on it! @dusatenko@jwmcd.com | Dillon Bowman | 12/22/25 9:33 AM
Row 46 | Still no dims | Denis Usatenko | 12/17/25 4:34 PM
Row 46 | NO DIMS | Denis Usatenko | 12/09/25 10:03 AM
Row 47 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | Issiah Havens | 04/14/25 2:36 PM
Row 48 | @dusatenko@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 03/05/26 7:20 AM
Row 48 | @hstakhurskyi@jwmcd.com Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\03_Check\24051 NORTH ELEVATION\24051FS29C | Denis Usatenko | 03/04/26 9:53 AM
Row 49 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | Issiah Havens | 04/14/25 3:03 PM
Row 50 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | Issiah Havens | 04/14/25 3:15 PM
Row 51 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | Issiah Havens | 04/14/25 3:31 PM
Row 52 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | Issiah Havens | 04/15/25 7:17 AM
Row 53 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed, Paneltracker | Issiah Havens | 05/07/25 2:12 PM
Row 54 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | Issiah Havens | 04/15/25 7:31 AM
Row 55 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | Issiah Havens | 04/15/25 7:41 AM
Row 56 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed, panel tracker | Issiah Havens | 06/17/25 3:21 PM
Row 56 | @hstakhurskyi@jwmcd.com corrections required | Denis Usatenko | 06/10/25 10:15 AM
Row 59 | @cbuttrey@jwmcd.com When does this need to ship? | Drew Adams | 02/25/26 7:32 AM
| I changed to 4/17. its on hold due to some changes on site. | Chris Buttrey | 02/25/26 9:20 AM
Row 60 | PANELS are RTS. @skrantz@jwmcd.com know about the reveals | Mitch Chancey | 02/17/26 10:40 AM
| @mchancey@jwmcd.com I wasn't aware these got pushed through so they are not done. Will be done tomorrow. @jmcpherson@jwmcd.com @tgraves@jwmcd.com @sjones@jwmcd.com | Samantha Krantz | 02/17/26 10:45 AM
Row 60 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 02/11/26 2:31 PM
Row 61 | @dusatenko@jwmcd.com @jdavis@jwmcd.com programmed | Issiah Havens | 03/10/26 7:38 AM
Row 61 | @hstakhurskyi@jwmcd.com Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\03_Check\24051 NORTH ELEVATION\24051FS82 | Denis Usatenko | 03/09/26 3:36 PM
Row 61 | @mribar@jwmcd.com @dusatenko@jwmcd.com | Hennadii Stakhurskyi | 02/26/26 10:00 AM
Row 62 | @dusatenko@jwmcd.com @jdavis@jwmcd.com programmed | Issiah Havens | 03/10/26 8:53 AM
Row 62 | @hstakhurskyi@jwmcd.com Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\03_Check\24051 SOUTH ELEVATION\24051FS83 | Denis Usatenko | 03/09/26 3:38 PM
Row 63 | @dusatenko@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 03/11/26 11:20 AM
Row 63 | @hstakhurskyi@jwmcd.com Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\03_Check\24051 NORTH ELEVATION\24051FS84 | Denis Usatenko | 03/09/26 3:39 PM
Row 64 | @dusatenko@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 03/11/26 11:57 AM
Row 64 | @hstakhurskyi@jwmcd.com Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\03_Check\24051 SOUTH ELEVATION\24051FS85 | Denis Usatenko | 03/09/26 3:37 PM
Row 65 | @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 08/05/25 7:18 AM
Row 66 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED, SEE NOTES ON MATERIAL SUMMARY REPORT | Issiah Havens | 08/05/25 8:08 AM
Row 67 | @jdavis@jwmcd.com @hstakhurskyi@jwmcd.com PROGRAMMED, SEE NOTES ON MATERIAL SUMMARY REPORT | Issiah Havens | 08/05/25 8:22 AM
Row 68 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED, SEE NOTES ON MATERIAL SUMMARY REPORT | Issiah Havens | 08/05/25 8:29 AM
Row 69 | @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 08/12/25 7:54 AM
Row 70 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAAMMED | Arnold Jurado | 01/20/26 1:48 PM
Row 71 | @gholland@jwmcd.com @jdavis@jwmcd.com @cball@jwmcd.com @tgraves@jwmcd.com THIS RELEASE NEEDS TO GO WITH FS02 TO SPECTRUM FOR COATING WHICH IS READY TO SHIP. BOTH WERE RELEAED AT THE SAME TIME & WE NEED TO GET THIS OUT OF THE SHOP. PLEASE PROVIDE A SHIP DATE. | Marc Ribar | 02/16/26 8:23 AM
Row 71 | @fdean@jwmcd.com @dhasty@jwmcd.com flat programs completed | Chris Gambrel | 01/19/26 6:59 AM
Row 71 | @cgambrel@jwmcd.com Ready to program | Frank Dean | 01/16/26 2:41 PM
Row 74 | @fdean@jwmcd.com @dhasty@jwmcd.com flat program completed. | Chris Gambrel | 11/25/25 8:37 AM
Row 74 | @fdean@jwmcd.com good to go | David Hasty | 11/25/25 7:34 AM
Row 75 | @fdean@jwmcd.com program complete | Issiah Havens | 11/25/25 12:25 PM
Row 75 | @fdean@jwmcd.com corrections required | David Hasty | 11/25/25 7:36 AM
Row 77 | Team, I made a mistake here. Can we update the sketches to add a little system depth? I have included the updates in the job folder. My apologies, I put the updates in when it was uncategorized, but neglected to tag Denis in the card comment. Just need small updates to the sketches before we produce. My apologies. @dusatenko@jwmcd.com @tgraves@jwmcd.com @skrantz@jwmcd.com | Dillon Bowman | 01/27/26 10:32 AM
Row 77 | Small updates to profiles, thanks. | Dillon Bowman | 01/23/26 3:48 PM
Row 78 | @dusatenko@jwmcd.com No sketches in folder | Mitch Chancey | 09/08/25 1:07 PM
| They are there | Denis Usatenko | 09/08/25 1:40 PM
Row 78 | @dbowman@jwmcd.com I am releasing this but noticed there was no Dark Bronze material listed under the job number | Chance Dill | 08/25/25 8:33 AM
| Chance, yes. We'll need to pull from 23022. My Apologies, I meant to get that info in to the ERF. Can you get it onto the in-house? @cdill@jwmcd.com | Dillon Bowman | 08/25/25 8:42 AM
Row 78 | @cdill@jwmcd.com No corrections required | Denis Usatenko | 08/22/25 2:12 PM
Row 79 | @aniedfeld@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 02/05/26 1:50 PM
Row 79 | @aniedfeld@jwmcd.com Corrections required | Denis Usatenko | 02/04/26 6:35 AM
Row 80 | Denis, the crating plan calls out elevations that need to be crated together. FS01 has its own crating direction, and FS02 has its own crating direction. At no point will they overlap in crating direction, as they are different parts of the building. FS01 has crate numbers matched to elevations. FS02 has crate groups matched to elevations. Please help me understand what more information you need on this. Further - if this is holding up production by any means, abandon the crating plan. Its not worth being late. Thanks @dusatenko@jwmcd.com @tmooers@jwmcd.com | Dillon Bowman | 02/11/26 5:05 PM
| I apologize. I did not go to the next page and assumed the verbage on the cover was all it was. It did not hold anything up. We have put it into production and there are now crating list added. They have been printed and supplied to the shop. I would like to remind you that we are not able to control the exact crate numbers so that would have to be coordinated post crating once packing lists are created. | Denis Usatenko | 02/11/26 9:05 PM
Row 80 | @dbowman@jwmcd.com What is your plan regarding the crating plan? | Ailen Niedfeld | 02/10/26 11:38 AM
| @aniedfeld@jwmcd.com The Crating Plan is communicated in the Release Schedule Document in the FD Folder, but I have also attached it here. | Dillon Bowman | 02/10/26 8:56 PM
| Dillion, the note is not a crating plan, that is standard JWM opertion porcedure. Different FS get crated iseparately. A crating plan indicates specifially which panels are to be crated together. For example: panels on sheet 211-215 from elevation 100 - 200 to be crated together, panels on sheet 211-215 from elevation 200 - 600 to be crated together, OR all canopies to be crated together, all panels between windows to ge together. @tmooers@jwmcd.com | Denis Usatenko | 02/11/26 7:38 AM
Row 80 | @aniedfeld@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 02/10/26 11:20 AM
Row 80 | @dbowman@jwmcd.com System required in this card | Denis Usatenko | 12/19/25 8:19 AM
| corrections required | Denis Usatenko | 02/05/26 4:13 PM
| 400 Series @dusatenko@jwmcd.com | Dillon Bowman | 02/05/26 4:16 PM
Row 81 | @gherrera@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed, panel tracker | Issiah Havens | 06/04/25 1:13 PM
Row 81 | @dusatenko@jwmcd.com Q:\Jobs\25016 - Rockdale CJAC\03_Engineering\03_FS_Issues\03_Check\25016MU101 | Gabriela Herrera | 06/02/25 4:41 PM
Row 82 | @dusatenko@jwmcd.com Standard flashing. | Paul J Roberts | 06/02/25 12:55 PM
Row 83 | @gherrera@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed, panel tracker | Issiah Havens | 06/04/25 1:36 PM
Row 83 | @dusatenko@jwmcd.com Q:\Jobs\25016 - Rockdale CJAC\03_Engineering\03_FS_Issues\03_Check\25016MU121 | Gabriela Herrera | 06/03/25 3:29 PM
Row 84 | @dusatenko@jwmcd.com 16 Ga. zees. | Paul J Roberts | 06/02/25 12:56 PM
Row 85 | @aduke@jwmcd.com standard flashings. | Paul J Roberts | 06/02/25 12:58 PM
| For me? Thanks, ALLEN DUKE Processing Estimating Manager John W. McDougall Inc. 615.321.3900 ¦ jwmcd.com | Allen Duke | 06/02/25 1:09 PM
Row 86 | @dbowman@jwmcd.com @swatson@jwmcd.com @tgraves@jwmcd.com LOOSE ON THE TREE | Mitch Chancey | 12/29/25 10:40 AM
Row 87 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed w/ PT | Issiah Havens | 07/02/25 7:30 AM
Row 88 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed w/ PT | Issiah Havens | 07/02/25 12:12 PM
Row 88 | @hstakhurskyi@jwmcd.com Corrections required | Denis Usatenko | 07/01/25 2:04 PM
Row 89 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed w/ PT | Issiah Havens | 07/02/25 7:43 AM
Row 89 | @hstakhurskyi@jwmcd.com corrections required | Denis Usatenko | 07/01/25 2:07 PM
Row 90 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed w/ PT | Issiah Havens | 07/02/25 8:06 AM
Row 91 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed w/ PT | Issiah Havens | 07/02/25 8:20 AM
Row 92 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed w/ PT | Issiah Havens | 07/02/25 3:32 PM
Row 96 | @fdean@jwmcd.com corrections required | David Hasty | 02/11/26 11:34 AM
Row 98 | Reveals done 4-30-25 | Samantha Krantz | 04/30/25 4:10 PM
Row 98 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | Issiah Havens | 04/15/25 7:58 AM
Row 99 | Reveals done 4-7-25 | Samantha Krantz | 04/09/25 9:33 AM
Row 99 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Program complete | Issiah Havens | 03/19/25 7:23 AM
Row 100 | @dusatenko@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 03/04/26 10:57 AM
Row 100 | @hstakhurskyi@jwmcd.com Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\03_Check\24051 WEST ELEVATION\24051FS04C | Denis Usatenko | 03/04/26 7:07 AM
Row 101 | Reveals done 4-7-25 | Samantha Krantz | 04/09/25 9:34 AM
Row 101 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Program complete | Issiah Havens | 03/19/25 11:06 AM
Row 102 | Reveals done 4-10-25 | Samantha Krantz | 04/10/25 12:20 PM
Row 102 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Program complete | Issiah Havens | 03/19/25 2:26 PM
Row 103 | Reveals done 4-13-25 | Samantha Krantz | 04/22/25 7:41 AM
Row 103 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Program complete | Issiah Havens | 03/26/25 3:28 PM
Row 104 | @jdavis@jwmcd.com programmed. @aniedfeld@jwmcd.com please print all documents from the "PROGRAMMING DOCS" folder | Issiah Havens | 01/27/26 3:47 PM
Row 105 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed w/ PT | Issiah Havens | 07/03/25 9:17 AM
Row 106 | @aniedfeld@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 01/23/26 2:29 PM
Row 107 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed w/ PT | Issiah Havens | 07/03/25 9:44 AM
Row 108 | @hstakhurskyi@jwmcd.com @dusatenko@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 11/06/25 3:51 PM
Row 109 | @cdill@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 08/25/25 2:41 PM
Row 109 | @cdill@jwmcd.com No corrections required | Denis Usatenko | 08/25/25 9:31 AM
Row 110 | @dusatenko@jwmcd.com I switched check over to Terry. | Paul J Roberts | 03/07/25 10:05 AM
Row 111 | @mribar@jwmcd.com @dusatenko@jwmcd.com @mchancey@jwmcd.com @sjones@jwmcd.com the in house and the card says we need 140 but the sketch says we need 141. Can someone advise how many we actually need? | Samantha Krantz | 01/19/26 6:21 AM
| 141 | Denis Usatenko | 01/19/26 6:23 AM
Row 113 | @mrassmussen@jwmcd.com I will look and come by your desk. I deleted your note about reviewing. | Denis Usatenko | 02/04/26 8:58 AM
Row 115 | @fdean@jwmcd.com @jdorsey@jwmcd.com @dhasty@jwmcd.com flat programs completed. | Chris Gambrel | 02/04/26 7:43 AM
Row 115 | @cgambrel@jwmcd.com Ready to program, please program corner reveals to be gang formed | Frank Dean | 02/03/26 10:56 AM
Row 115 | @fdean@jwmcd.com corrections required | David Hasty | 02/03/26 7:09 AM
Row 116 | @fdean@jwmcd.com @jdorsey@jwmcd.com @dhasty@jwmcd.com flat programs completed. | Chris Gambrel | 02/05/26 9:57 AM
Row 116 | @cgambrel@jwmcd.com Ready to program, gang form corner reveals | Frank Dean | 02/04/26 4:04 PM
Row 116 | @jdorsey@jwmcd.com corrections required | David Hasty | 02/04/26 1:17 PM
Row 117 | @fdean@jwmcd.com @jdorsey@jwmcd.com @dhasty@jwmcd.com flat program completed. | Chris Gambrel | 02/06/26 11:30 AM
Row 117 | @cgambrel@jwmcd.com Ready to program, gang form corner reveals, both reveals are the same as previous releases | Frank Dean | 02/06/26 8:41 AM
Row 117 | @fdean@jwmcd.com corrections required | David Hasty | 02/05/26 1:53 PM
Row 118 | @fdean@jwmcd.com @jdorsey@jwmcd.com @dhasty@jwmcd.com flat programs completed | Chris Gambrel | 02/10/26 10:46 AM
Row 118 | @cgambrel@jwmcd.com Ready to program | Frank Dean | 02/09/26 1:14 PM
Row 118 | @fdean@jwmcd.com corrections required | David Hasty | 02/09/26 10:52 AM
Row 119 | @fdean@jwmcd.com @jdorsey@jwmcd.com @dhasty@jwmcd.com flat programs completed. | Chris Gambrel | 02/11/26 8:43 AM
| Jonathan Dorsey reacted to your message: | Jonathan Dorsey | 02/11/26 8:44 AM
Row 119 | @cgambrel@jwmcd.com Ready to program | Frank Dean | 02/10/26 2:35 PM
Row 119 | @fdean@jwmcd.com corrections required | David Hasty | 02/10/26 8:30 AM
Row 120 | @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 12/22/25 3:50 PM
Row 120 | @dusatenko@jwmcd.com Q:\Jobs\23028 - 1000 Church YMCA\03_Engineering\03_FS_Issues\03_Check\23028FS99 | Gabriela Herrera | 12/22/25 11:41 AM
| corrections requird | Denis Usatenko | 12/22/25 12:05 PM
Row 120 | Date Changed | Dillon Bowman | 12/17/25 3:44 AM
Row 123 | @dusatenko@jwmcd.com I have not moved the card(to Release to Shop) in order to produce inhouse. Paperwork is ready on my desk awaiting material. Let me know how to proceed. | Ailen Niedfeld | 02/27/26 4:57 PM
Row 123 | @aniedfeld@jwmcd.com @jdavis@jwmcd.com programmed | Issiah Havens | 02/27/26 4:02 PM
Row 123 | @nakins@jwmcd.com We have 63 sheets of ron red in stock, but will need 70 sheets to fulfill this order. @dusatenko@jwmcd.com | Issiah Havens | 02/27/26 3:19 PM
Row 123 | It is now @ihavens@jwmcd.com | Ailen Niedfeld | 02/27/26 1:08 PM
Row 123 | @aniedfeld@jwmcd.com just following up on this one, will this be in coding soon? @ajurado@jwmcd.com | Issiah Havens | 02/27/26 12:12 PM
Row 123 | @aniedfeld@jwmcd.com Corrections required. | Denis Usatenko | 02/25/26 2:14 PM
Row 123 | @dusatenko@jwmcd.com is this tracking? @nakins@jwmcd.com | Chris Ball | 02/16/26 7:12 AM
Row 124 | @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 02/05/26 12:23 PM
Row 124 | @dusatenko@jwmcd.com Q:\Jobs\25008 - Columbia State Tech Center\03_Engineering\03_FS_Issues\03_Check\25008FS05 | Gabriela Herrera | 01/31/26 8:55 PM
| Corrections required. | Denis Usatenko | 02/04/26 12:41 PM
Row 124 | updated pickup date after missing information was provided by AMI @tgraves@jwmcd.com @mchancey@jwmcd.com @rharmon@jwmcd.com @dusatenko@jwmcd.com @gherrera@jwmcd.com | Laura Forero | 01/29/26 11:02 AM
Row 124 | updated pickup date after conversation with AMI @tgraves@jwmcd.com @mchancey@jwmcd.com @rharmon@jwmcd.com @dusatenko@jwmcd.com @gherrera@jwmcd.com | Laura Forero | 01/21/26 1:49 PM
Row 125 | @mchancey@jwmcd.com I spoke with AMI and the PM said he informed Annie that these are ready. Just a heads up to expect them hopefully soon | Cole Norona | 03/11/26 7:31 AM
Row 125 | @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 02/10/26 2:10 PM
Row 125 | @dusatenko@jwmcd.com Q:\Jobs\25010 - TOA Spring Hill MOB\03_Engineering\03_FS_Issues\03_Check\25010FS06 | Gabriela Herrera | 02/05/26 8:43 AM
| corrections required. | Denis Usatenko | 02/05/26 3:25 PM
Row 125 | @dusatenko@jwmcd.com Q:\Jobs\25010 - TOA Spring Hill MOB\03_Engineering\03_FS_Issues\02_LO\25010FS01-06\25010FS06 | Frank Dean | 01/27/26 7:30 AM
Row 126 | @jdavis@jwmcd.com @gherrera@jwmcd.com programmed | Issiah Havens | 02/16/26 8:24 AM
Row 126 | @dusatenko@jwmcd.com Q:\Jobs\25010 - TOA Spring Hill MOB\03_Engineering\03_FS_Issues\03_Check\25010FS06.1 | Gabriela Herrera | 02/10/26 10:35 AM
Row 127 | Reveals done 4-7-25 | Samantha Krantz | 04/09/25 9:33 AM
Row 127 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Program complete | Issiah Havens | 03/17/25 3:24 PM
Row 128 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed and in PanelTracker | Issiah Havens | 05/07/25 1:18 PM
Row 128 | @dusatenko@jwmcd.com I GORGOT ABOUT THIS ELEVATION ON THE RELEASE. PLEASE ADD THESE PANELS. | Marc Ribar | 05/05/25 9:07 AM
| Which one? | Denis Usatenko | 05/05/25 9:10 AM
| SHEET 4031 ADDED IN THE RELEASE. IT IS THE MATERIAL AROUND THE CORNER. | Marc Ribar | 05/05/25 9:29 AM
Row 129 | Reveals done 4-7-25 | Samantha Krantz | 04/09/25 9:33 AM
Row 129 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Program complete | Issiah Havens | 03/18/25 10:31 AM
Row 130 | Reveals done 4-7-25 | Samantha Krantz | 04/09/25 9:33 AM
Row 130 | @jdavis@jwmcd.com This is on hold. Skip this and go to FS04 for now. @tgraves@jwmcd.com @mribar@jwmcd.com @rharmon@jwmcd.com | Denis Usatenko | 03/20/25 1:55 PM
| off hold all good @tgraves@jwmcd.com @jmcpherson@jwmcd.com @mribar@jwmcd.com @rharmon@jwmcd.com | Denis Usatenko | 03/20/25 3:10 PM
Row 130 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Program complete | Issiah Havens | 03/18/25 4:25 PM
Row 132 | 1 BUNDLE ON THE TREE @avdm@jwmcd.com @swatson@jwmcd.com @tgraves@jwmcd.com | Mitch Chancey | 12/24/25 7:31 AM
Row 132 | @avdm@jwmcd.com I need more information on this. | Denis Usatenko | 11/11/25 2:21 PM
Row 133 | @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 08/14/25 11:08 AM
Row 134 | @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 09/10/25 11:43 AM
Row 135 | @jdavis@jwmcd.com PROGRAMED | Arnold Jurado | 09/22/25 10:16 AM
Row 136 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 10/23/25 2:45 PM
Row 136 | THIS RELEASE IS NO LONGER ON HOLD. PLEASE PROCEED WITH THE FABRICTION TICKETS | Marc Ribar | 10/13/25 4:03 PM
Row 137 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed w/ PT | Issiah Havens | 06/27/25 3:36 PM
Row 137 | @hstakhurskyi@jwmcd.com @dusatenko@jwmcd.com Shop is starving for work. Can this be pushed into programming and released? | Paul J Roberts | 06/23/25 2:05 PM
Row 137 | @hstakhurskyi@jwmcd.com corrections required | Denis Usatenko | 06/10/25 10:16 AM
Row 138 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed, panel tracker | Issiah Havens | 06/17/25 3:50 PM
Row 138 | @hstakhurskyi@jwmcd.com corrections required | Denis Usatenko | 06/10/25 10:16 AM
Row 139 | @lforero@jwmcd.com @swatson@jwmcd.com @tgraves@jwmcd.com LOOSE ON THE TREE | Mitch Chancey | 12/09/25 9:48 AM
Row 140 | @dusatenko@jwmcd.com Sketches are ready to check. "Q:\Jobs\25048 - East Nashville FSER\03_Engineering\03_FS_Issues\03_Check\25048FS01\25048FS01 Check Set.pdf" | Gabriela Hoyle | 03/10/26 12:27 PM
Row 140 | @dusatenko@jwmcd.com Can you confirm that the cad file transferred properly | Wylie McDougall | 02/10/26 8:07 AM
| Its here | Denis Usatenko | 02/11/26 6:57 AM
Row 142 | @slucas@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed w/ PanelTracker | Issiah Havens | 06/27/25 11:19 AM
Row 142 | @slucas@jwmcd.com Corrections required | Denis Usatenko | 06/25/25 12:40 PM
Row 142 | @slucas@jwmcd.com this job has 16 hours allocated to Fab Sketch. This job has very little wiggle room with money so if you start to approach 16hrs and think we might bust, let me know. I will check in periodically to see how we are doing on hours as i have to watch this closely. | Cole Norona | 06/13/25 10:22 AM
Row 143 | @dbowman@jwmcd.com @swatson@jwmcd.com @tgraves@jwmcd.com LOOSE ON TREE | Mitch Chancey | 12/17/25 8:58 AM
Row 143 | @dbowman@jwmcd.com What side is the color on? | Denis Usatenko | 12/15/25 9:02 AM
| Thanks! @dusatenko@jwmcd.com | Dillon Bowman | 12/15/25 9:06 AM
| youre welcome? Did you mean to attach something? | Denis Usatenko | 12/15/25 9:09 AM
| took a minute to come through. I got it now!!! | Denis Usatenko | 12/15/25 9:16 AM
Row 144 | Ship Date Changed to 03/11 (ENG + Shop Workload) @dusatenko@jwmcd.com @tgraves@jwmcd.com | Dillon Bowman | 02/09/26 12:30 PM
Row 144 | Color Updated | Dillon Bowman | 02/03/26 2:32 PM
Row 146 | Shipped 200 pieces 2-24-26 | Samantha Krantz | 02/25/26 7:40 AM
Row 146 | Small Card Updates (Hat not Zee) | Dillon Bowman | 02/11/26 12:51 AM
Row 148 | Install Drawings to the floor 3/9/26 | Chance Dill | 03/09/26 11:21 AM
Row 148 | @cdill@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 03/02/26 10:05 AM
Row 148 | @cdill@jwmcd.com Corrections required | Denis Usatenko | 02/27/26 10:20 AM
Row 148 | Changed to "YES" for Material Grain | Dillon Bowman | 12/08/25 7:51 AM
Row 149 | need 2 panels re coded please 207-1N08 and 207-1N11. Thanks | Chance Dill | 03/03/26 3:43 PM
Row 149 | @cdill@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 03/03/26 2:33 PM
Row 149 | @cdill@jwmcd.com Corrections required. | Denis Usatenko | 03/03/26 7:36 AM
Row 149 | Card Updated per AMI Promise Date | Dillon Bowman | 03/02/26 2:10 PM
Row 150 | @cdill@jwmcd.com LO ready to sketch | Denis Usatenko | 03/10/26 5:08 PM
Row 150 | Card Updated Per AMI Promised Date | Dillon Bowman | 03/02/26 2:12 PM
Row 150 | @cdill@jwmcd.com See coment above. | Denis Usatenko | 12/23/25 2:04 PM
Row 150 | Notes Updated (Elevation 36/218) Update in FD Folder @dusatenko@jwmcd.com | Dillon Bowman | 12/23/25 1:48 PM
Row 151 | card updated per AMI promise date | Dillon Bowman | 03/02/26 1:48 PM
Row 151 | @cdill@jwmcd.com @jdavis@jwmcd.com programmed | Issiah Havens | 02/16/26 3:40 PM
Row 151 | @cdill@jwmcd.com Corrections required. | Denis Usatenko | 02/13/26 10:05 AM
Row 151 | @cdill@jwmcd.com keep going on this. we will have to come back to FS02-04. | Denis Usatenko | 01/27/26 2:26 PM
Row 152 | Update to Notes This is only part 1 of 2 not 1 of 3 | Dillon Bowman | 02/09/26 11:15 AM
Row 153 | Denis, I spoke with Rooley, discussing the missing scan data you mentioned yesterday. He would like us to pull these panels from the release until he can verify the dimensions and re-release seperately. The image attached highlights panels on pages 217. Thanks! @dusatenko@jwmcd.com | Dillon Bowman | 03/04/26 3:59 PM
Row 153 | Release Number Changed to FS07 | Dillon Bowman | 02/09/26 11:16 AM
Row 153 | Notes Updated - Release Number FS07 | Dillon Bowman | 02/09/26 11:12 AM
Row 154 | @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 02/02/26 9:30 AM
Row 154 | @dusatenko@jwmcd.com Sketches are ready for checking | Nadira Vlatkovic | 01/28/26 10:31 AM
| Corrections rquired | Denis Usatenko | 01/28/26 8:13 PM
Row 155 | @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 02/11/26 10:34 AM
Row 155 | @dusatenko@jwmcd.com Sketches are ready for checking | Nadira Vlatkovic | 02/05/26 3:28 PM
| Correction required Q:\Jobs\25022 - Vantage VA15\03_Engineering\03_FS_Issues\03_Check\25022FS06 | Denis Usatenko | 02/05/26 8:43 PM
Row 156 | @aniedfeld@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 01/23/26 11:54 AM
Row 157 | @jdorsey@jwmcd.com @dhasty@jwmcd.com flat programs completed. | Chris Gambrel | 01/29/26 6:36 AM
Row 157 | @cgambrel@jwmcd.com Just punching holes and shearing to size. Cutting 328 Total sheets of "1003_SHEET." | Jonathan Dorsey | 01/23/26 11:55 AM
Row 157 | @jdorsey@jwmcd.com corrections required | David Hasty | 01/23/26 10:45 AM
Row 157 | cold rolled if it matters | Joe Hoyle | 01/20/26 9:12 AM
Row 157 | 16 Gauge Steel sheet, got it | Jonathan Dorsey | 01/20/26 8:59 AM
Row 157 | @jhoyle@jwmcd.com just wanted to verify this is 16 Gauge Steel sheet. The drawing I'm referencing is 16 Gauge Galv. so I just wanted to make sure. | Jonathan Dorsey | 01/20/26 8:51 AM
| yes, the material is to be 16 ga steel sheet. NOT GALV | Joe Hoyle | 01/20/26 8:57 AM
Row 157 | @jhoyle@jwmcd.com we are going to need to put a hole in each end so they can batch hang them at PWX. Also, I want to confirm it 3600 pieces, not 3600 ft... Please let me know either way. | David Hasty | 01/19/26 3:11 PM
| Understood on the hole. I'd place it on one of the 1-1/2" legs. Also, 3600 PIECES is correct. | Joe Hoyle | 01/19/26 3:15 PM
Row 157 | @jdorsey@jwmcd.com we are going to hole the hole in then sheer them to size Frank can show you how we did this last time | David Hasty | 01/19/26 3:09 PM
Row 161 | @fdean@jwmcd.com corrections required | David Hasty | 02/12/26 8:44 AM
Row 161 | @cnorona@jwmcd.com This is ready to go, but I need a seperate card put in for 201A, since it has to go on the laser. 201A will have to be 119" to account for the border needed on the laser. | David Hasty | 02/12/26 7:25 AM
| @dhasty@jwmcd.com COMPLETED | Cole Norona | 02/12/26 7:55 AM
Row 162 | @fdean@jwmcd.com @dhasty@jwmcd.com @jdorsey@jwmcd.com flat program completed | Chris Gambrel | 01/15/26 9:25 AM
Row 162 | Good to release | David Hasty | 01/14/26 2:53 PM
Row 162 | Yes, here is a screenshot of the inventory as of yesterday. @dhasty@jwmcd.com | Dillon Bowman | 01/14/26 2:14 PM
Row 162 | @dbowman@jwmcd.com did you confirm we have drop material that we can cut 126" from? | David Hasty | 01/14/26 1:41 PM
Row 163 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | Issiah Havens | 04/14/25 12:15 PM
Row 164 | @cnorona@jwmcd.com This is cutting right now... | Denis Usatenko | 03/11/26 9:17 AM
Row 164 | @cdill@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 03/10/26 8:47 AM
Row 164 | @cdill@jwmcd.com Corrections required. | Denis Usatenko | 03/09/26 10:21 AM
Row 165 | @cdill@jwmcd.com Corrections required. | Denis Usatenko | 03/11/26 1:53 PM
Row 165 | @dusatenko@jwmcd.com Hey when will this be in coding? Hoar Construction wants to visit the facility to see these panels in production and need to give them a date. | Cole Norona | 03/11/26 7:42 AM
| probably today... | Denis Usatenko | 03/11/26 9:16 AM
| thank you! @dusatenko@jwmcd.com | Cole Norona | 03/11/26 9:29 AM
Row 166 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed, paneltracker | Issiah Havens | 05/07/25 1:38 PM
Row 167 | Reveals done 4-21-25 | Samantha Krantz | 04/22/25 7:41 AM
Row 167 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Program complete | Issiah Havens | 03/27/25 7:13 AM
Row 168 | Reveals done 4-21-25 | Samantha Krantz | 04/22/25 7:41 AM
Row 168 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Program complete | Issiah Havens | 03/27/25 7:39 AM
Row 169 | Reveals done 4-30-25 | Samantha Krantz | 04/30/25 4:10 PM
Row 169 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Program complete | Issiah Havens | 03/27/25 10:36 AM
Row 170 | @dusatenko@jwmcd.com @jdavis@jwmcd.com programmed | Issiah Havens | 03/04/26 1:16 PM
Row 170 | @hstakhurskyi@jwmcd.com Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\03_Check\24051 SOUTH ELEVATION\24051FS13C | Denis Usatenko | 03/04/26 8:00 AM
Row 171 | @tgraves@jwmcd.com @jdavis@jwmcd.com @chowse@jwmcd.com @rharmon@jwmcd.com This will be Sunrise Silver Metallic. 62"x196" | Wylie McDougall | 03/02/26 12:40 PM
Row 171 | @slucas@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 02/24/26 2:56 PM
Row 171 | @slucas@jwmcd.com Corrections required | Denis Usatenko | 02/24/26 8:06 AM
Row 171 | @slucas@jwmcd.com All interior columns/panels just do a 400 system | Wylie McDougall | 01/30/26 8:00 AM
Row 172 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 02/12/26 9:41 AM
Row 173 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 02/12/26 8:06 AM
Row 173 | @hstakhurskyi@jwmcd.com Corrections required | Denis Usatenko | 02/10/26 7:11 PM
Row 174 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 02/12/26 9:00 AM
Row 174 | @hstakhurskyi@jwmcd.com Corrections required | Denis Usatenko | 02/10/26 7:11 PM
Row 175 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 12/04/25 2:26 PM
Row 175 | @hstakhurskyi@jwmcd.com No corrections required | Denis Usatenko | 12/03/25 4:34 PM
Row 176 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 12/12/25 8:10 AM
Row 176 | @hstakhurskyi@jwmcd.com No corrections required | Denis Usatenko | 12/10/25 6:36 AM
Row 177 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 12/04/25 11:42 AM
Row 177 | @hstakhurskyi@jwmcd.com No corrections required | Denis Usatenko | 12/03/25 4:28 PM
Row 178 | @dusatenko@jwmcd.com Q:\Jobs\25008 - Columbia State Tech Center\03_Engineering\03_FS_Issues\03_Check\25008FS06 | Gabriela Herrera | 03/09/26 1:04 PM
Row 179 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 10/29/25 3:24 PM
Row 179 | @hstakhurskyi@jwmcd.com No corrections required | Denis Usatenko | 10/28/25 4:55 PM
Row 180 | crate #1 out 1/30/26 | Mitch Chancey | 01/30/26 1:14 PM
Row 180 | @skrantz@jwmcd.com @sjones@jwmcd.com @rharmon@jwmcd.com Please hold on the splice plates and coping until I confirm something. I know they are already sheared, and that's OK, just don't form them. | Chris Buttrey | 11/21/25 10:41 AM
Row 180 | @cbuttrey@jwmcd.com @dusatenko@jwmcd.com the card and the in house shows 199 pieces but with the splice plates its actually 265. Can yall get the count updated and will that generate a new in house? | Samantha Krantz | 11/19/25 8:32 AM
| Done and yes | Denis Usatenko | 11/19/25 8:44 AM
Row 180 | yes splice plates | Chris Buttrey | 11/04/25 2:48 PM
Row 180 | @cbuttrey@jwmcd.com Do you want splice plates for the coping? | Denis Usatenko | 11/04/25 9:32 AM
Row 180 | The cover sheet on the file says FL01 but should be good for FL02, I think I may have fixed it? | Chris Buttrey | 11/03/25 3:03 PM
Row 181 | @aniedfeld@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 01/23/26 11:37 AM
Row 182 | @mchancey@jwmcd.com @swatson@jwmcd.com I show this release has shipped in 3 deliveries from 8-15 to 9-29. Please confirm | Marc Ribar | 01/12/26 10:50 AM
Row 182 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Programmed | Issiah Havens | 04/14/25 1:08 PM
Row 183 | @dusatenko@jwmcd.com @jdavis@jwmcd.com programmed | Issiah Havens | 03/04/26 11:42 AM
Row 183 | @hstakhurskyi@jwmcd.com Missing field cut panel | Denis Usatenko | 03/04/26 8:54 AM
| this panel - FS84 Mark planed it in 2 fs (FS26C &FS84) | Hennadii Stakhurskyi | 03/04/26 10:26 AM
Row 183 | @hstakhurskyi@jwmcd.com Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\03_Check\24051 NORTH ELEVATION\24051FS26C | Denis Usatenko | 03/04/26 8:48 AM
Row 184 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 11/06/25 3:54 PM
Row 184 | @hstakhurskyi@jwmcd.com Corrections required | Denis Usatenko | 11/05/25 4:14 PM
Row 185 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 11/07/25 7:39 AM
Row 186 | @dusatenko@jwmcd.com PROGRAMMED | Arnold Jurado | 02/19/26 5:27 PM
Row 186 | @hstakhurskyi@jwmcd.com Corrections required. | Denis Usatenko | 02/18/26 1:24 PM
Row 187 | Moving back now. Looks like someone made a mistake. | Drew Adams | 02/25/26 8:17 AM
Row 187 | @rharmon@jwmcd.com @tgraves@jwmcd.com @jmcpherson@jwmcd.com Why is this release in "Partially Shipped to Paint"? | Carlos Silva | 02/23/26 9:04 AM
Row 187 | @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 02/10/26 8:39 AM
Row 187 | @dusatenko@jwmcd.com Sketches are ready for checking. | Nadira Vlatkovic | 02/04/26 4:31 PM
| Corrections required. | Denis Usatenko | 02/05/26 8:12 AM
Row 187 | @nvlatkovic@jwmcd.com Remove the panels that need modeling. Nick will be onsite Next week and get us hand dims from the installed panels and on. | Denis Usatenko | 01/30/26 9:26 AM
Row 187 | @nvlatkovic@jwmcd.com Some modeling required: Combine FS01-04 Model and scans in folder "Q:\Jobs\24039 - The Visionary\03_Engineering\02_FD Docs\12_SCAN 112525 CS complete building\RCP_Balconies" | Denis Usatenko | 01/28/26 7:31 PM
Row 188 | @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 02/23/26 11:41 AM
Row 188 | @dusatenko@jwmcd.com Sketches are ready for checking. | Nadira Vlatkovic | 02/19/26 11:10 AM
| Q:\Jobs\24039 - The Visionary\03_Engineering\03_FS_Issues\03_Check\24039FS19 | Denis Usatenko | 02/20/26 9:07 AM
Row 188 | @csilva@jwmcd.com On Hold. See Notes in "Description" @jmcpherson@jwmcd.com | Denis Usatenko | 02/05/26 7:44 PM
Row 189 | @dusatenko@jwmcd.com Sketches are ready for checking | Nadira Vlatkovic | 03/10/26 8:51 AM
| Q:\Jobs\24039 - The Visionary\03_Engineering\03_FS_Issues\03_Check\24039FS20 | Denis Usatenko | 03/10/26 2:25 PM
Row 189 | @csilva@jwmcd.com On Hold. See Notes in "Description" @jmcpherson@jwmcd.com | Denis Usatenko | 02/05/26 7:45 PM
Row 190 | @csilva@jwmcd.com On hold. No answers on 2/9 email. @jmcpherson@jwmcd.com | Denis Usatenko | 02/19/26 8:43 AM
Row 190 | @nvlatkovic@jwmcd.com Added dims to the folder in FD. | Denis Usatenko | 02/09/26 3:56 PM
Row 191 | @jmcpherson@jwmcd.com @csilva@jwmcd.com @dusatenko@jwmcd.com I have finished the pendulum for the 140 sheets. Moving on to the next job | Joshua Davis | 03/02/26 12:44 PM
Row 191 | @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 02/27/26 3:05 PM
Row 191 | @ajurado@jwmcd.com @ihavens@jwmcd.com @dusatenko@jwmcd.com Sketches are ready for coding. | Nadira Vlatkovic | 02/27/26 8:33 AM
Row 191 | @dusatenko@jwmcd.com Please do not code this issue. I have to fix a few sketches. I will inform you when I am done. | Nadira Vlatkovic | 02/27/26 7:43 AM
| @ajurado@jwmcd.com @ihavens@jwmcd.com See coment above. | Denis Usatenko | 02/27/26 7:44 AM
Row 191 | @dusatenko@jwmcd.com Sketches are ready for checking | Nadira Vlatkovic | 02/25/26 9:55 AM
| Corrections required Q:\Jobs\24039 - The Visionary\03_Engineering\03_FS_Issues\03_Check\24039FS23 | Denis Usatenko | 02/26/26 10:51 AM
Row 191 | @csilva@jwmcd.com On Hold. See Notes in "Description" @jmcpherson@jwmcd.com | Denis Usatenko | 02/05/26 7:46 PM
Row 192 | @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 01/15/26 11:24 AM
Row 193 | @dbowman@jwmcd.com @tgraves@jwmcd.com @swatson@jwmcd.com loose on the tree | Mitch Chancey | 07/17/25 12:10 PM
Row 193 | my apologies, it is the galv @dusatenko@jwmcd.com @jmcpherson@jwmcd.com | Dillon Bowman | 07/17/25 10:58 AM
| Changing the whole thing to "FL07". Not sure we have ever ran BreakMetal or Flashing as in RM. RM i believe is reserved for panels (ACM or other). We can iron that out if needed after this is released. | Denis Usatenko | 07/17/25 11:01 AM
| If it's not too late, let's do FL10. @dusatenko@jwmcd.com If you have already done it, its not worth changing, just easier for me to keep it sorted. | Dillon Bowman | 07/17/25 11:03 AM
Row 193 | Thanks @dusatenko@jwmcd.com | Dillon Bowman | 07/17/25 11:00 AM
Row 193 | Card Updated @dusatenko@jwmcd.com @jmcpherson@jwmcd.com | Dillon Bowman | 07/17/25 11:00 AM
Row 193 | @dbowman@jwmcd.com Where is the material coming from? @jmcpherson@jwmcd.com | Denis Usatenko | 07/17/25 10:53 AM
| Isn't that a house stock? @dusatenko@jwmcd.com @jmcpherson@jwmcd.com | Dillon Bowman | 07/17/25 10:56 AM
| SS=Stainless Steel, no Galv. is | Denis Usatenko | 07/17/25 10:57 AM
Row 194 | Reveals done 4-30-25 | Samantha Krantz | 04/30/25 4:11 PM
Row 194 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Program complete | Issiah Havens | 03/27/25 8:43 AM
Row 195 | Reveals done 4-30-25 | Samantha Krantz | 04/30/25 4:11 PM
Row 195 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com @tgraves@jwmcd.com Program complete | Issiah Havens | 03/27/25 9:06 AM
Row 197 | @dusatenko@jwmcd.com @jdavis@jwmcd.com programmed | Issiah Havens | 03/04/26 12:06 PM
Row 197 | @hstakhurskyi@jwmcd.com Need corrections. Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\03_Check\24051 NORTH ELEVATION\24051FS22C | Denis Usatenko | 03/04/26 8:13 AM
Row 197 | @mribar@jwmcd.com @dusatenko@jwmcd.com file corrections??? parapet level 150 north? | Hennadii Stakhurskyi | 02/26/26 9:31 AM
| Coping only. | Denis Usatenko | 02/26/26 9:59 AM
Row 202 | Material is here. Removing Hold. | Drew Adams | 03/05/26 2:26 PM
Row 202 | Placed on Production Hold due to Lack of Material. | Drew Adams | 03/04/26 1:44 PM
Row 202 | @slucas@jwmcd.com @dusatenko@jwmcd.com Reveals added to job and on one nest, pendulum updated. | Issiah Havens | 02/23/26 10:08 AM
Row 202 | @ajurado@jwmcd.com can you code these 15 reveals | Samuel Lucas | 02/23/26 9:13 AM
Row 202 | @slucas@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 02/20/26 4:14 PM
Row 202 | @slucas@jwmcd.com cORRECTIONS REQUIRED | Denis Usatenko | 02/18/26 4:39 PM
Row 202 | @slucas@jwmcd.com All interior columns/panels just do a 400 system | Wylie McDougall | 01/30/26 8:00 AM
Row 202 | @slucas@jwmcd.com @dusatenko@jwmcd.com The square column has some revised dimensions for the profile (not height) but are saved in the fd docs. | Wylie McDougall | 01/27/26 1:15 PM
Row 202 | @slucas@jwmcd.com @dusatenko@jwmcd.com 4 GD columns added in release. | Wylie McDougall | 01/12/26 4:14 PM
Row 202 | Sliver Metallic according to 12/23 email | Denis Usatenko | 12/23/25 4:24 PM
Row 203 | @dusatenko@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 03/11/26 9:38 AM
Row 203 | @hstakhurskyi@jwmcd.com CORECTIONS PLEASE Q:\Jobs\24089 - BSU Innovation Center\03_Engineering\03_FS_Issues\03_Check\24089FS01 | Denis Usatenko | 03/10/26 7:21 AM
Row 203 | @dusatenko@jwmcd.com done Q:\Jobs\24089 - BSU Innovation Center\03_Engineering\03_FS_Issues\03_Check\24089FS01 | Hennadii Stakhurskyi | 02/26/26 6:50 AM
Row 203 | @hstakhurskyi@jwmcd.com Please print panels for check | Denis Usatenko | 02/25/26 4:36 PM
Row 203 | @dusatenko@jwmcd.com We received a CO from Messer to field fab some of the panels since some of the predecessor trade materials were not in place at the time of scan. I will put the drawing's in the folder indicating what I believe these panels would be. We can rout and leave the unknown dimension side raw for field fab. | Marc Ribar | 01/22/26 7:30 AM
Row 204 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 02/11/26 3:22 PM
Row 204 | @hstakhurskyi@jwmcd.com Corrections required. | Denis Usatenko | 02/10/26 7:19 PM
Row 205 | @dusatenko@jwmcd.com @jdavis@jwmcd.com programmed | Issiah Havens | 03/02/26 7:42 AM
Row 205 | @hstakhurskyi@jwmcd.com Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\03_Check\24051 SOUTH ELEVATION\24051FS78 | Denis Usatenko | 02/27/26 7:39 AM
Row 206 | @dusatenko@jwmcd.com @jdavis@jwmcd.com programmed | Issiah Havens | 03/02/26 10:54 AM
Row 206 | @hstakhurskyi@jwmcd.com Corrections required. Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\03_Check\24051 SOUTH ELEVATION\24051FS78.1 | Denis Usatenko | 02/26/26 12:41 PM
Row 207 | @jdavis@jwmcd.com ALL DONE | Arnold Jurado | 02/27/26 10:30 AM
Row 207 | @dusatenko@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 02/26/26 3:46 PM
Row 207 | @hstakhurskyi@jwmcd.com Corrections rquired. Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\03_Check\24051 SOUTH ELEVATION\24051FS78.2 | Denis Usatenko | 02/26/26 11:13 AM
Row 208 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 01/30/26 12:46 PM
Row 208 | Update ship target per @jmcpherson@jwmcd.com | Paul J Roberts | 01/30/26 8:10 AM
Row 208 | @hstakhurskyi@jwmcd.com Corrections required | Denis Usatenko | 01/28/26 1:37 PM
Row 208 | @jmcpherson@jwmcd.com @dusatenko@jwmcd.com what information still missing on this one? | Carlos Silva | 01/20/26 8:21 AM
| none. People prblem on my end. Tomorrow is the sketch start. | Denis Usatenko | 01/20/26 8:40 AM
Row 208 | Is this tracking to go to the shop Monday? @dusatenko@jwmcd.com @csilva@jwmcd.com | Josh McPherson | 01/16/26 2:59 PM
| No | Denis Usatenko | 01/16/26 3:00 PM
Row 208 | @tgraves@jwmcd.com @rharmon@jwmcd.com @csilva@jwmcd.com @dusatenko@jwmcd.com We need to explore OT options for this release. Estimated to the shop date is 1/17-1/18. | Josh McPherson | 01/07/26 2:31 PM
Row 209 | @tgraves@jwmcd.com @mchancey@jwmcd.com this will be the next shipping on 02/13. | Carlos Silva | 02/11/26 2:14 PM
Row 209 | @hstakhurskyi@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 02/03/26 3:02 PM
Row 210 | @jdavis@jwmcd.com please send to CNB before forming | David Hasty | 02/03/26 2:00 PM
Row 210 | @dhasty@jwmcd.com @fdean@jwmcd.com flat programs completed. | Chris Gambrel | 01/16/26 12:40 PM
Row 210 | @cgambrel@jwmcd.com Ready to program. Instead of cutting 382 of part "25035FS1101," cut 9 of "25035FS1101-BAR" and they will shear to size. Please try not to use an extra sheet to cut these. | Frank Dean | 01/16/26 7:42 AM
Row 210 | @fdean@jwmcd.com corrections required | David Hasty | 01/15/26 1:37 PM
Row 211 | this job was sent to EWS for fab and not painter. | Tony Graves | 02/10/26 1:20 PM
Row 211 | Install Drawings dropped off | Chance Dill | 02/09/26 9:26 AM
Row 211 | @cdill@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 01/23/26 10:45 AM
Row 211 | @cdill@jwmcd.com Corrections required. | Denis Usatenko | 01/21/26 2:23 PM
Row 212 | @fdean@jwmcd.com @dhasty@jwmcd.com flat program completed. | Chris Gambrel | 02/12/26 1:11 PM
Row 212 | @cgambrel@jwmcd.com Ready to program | Frank Dean | 02/12/26 11:18 AM
Row 213 | @dusatenko@jwmcd.com @jdavis@jwmcd.com programmed | Issiah Havens | 03/05/26 7:09 AM
Row 213 | @hstakhurskyi@jwmcd.com Q:\Jobs\24051 - TN Titans Stadium\03_Engineering\03_FS_Issues\03_Check\24051 EAST ELEVATION\24051FS76.1 | Denis Usatenko | 03/04/26 10:23 AM
Row 214 | @proberts@jwmcd.com corrections could happen if you feel like doing them :) | David Hasty | 02/17/26 10:56 AM
Row 218 | @proberts@jwmcd.com @dhasty@jwmcd.com @jdorsey@jwmcd.com flat program completed. | Chris Gambrel | 02/18/26 8:46 AM
Row 219 | @dhasty@jwmcd.com done | Arnold Jurado | 02/18/26 9:55 AM
Row 220 | @dhasty@jwmcd.com done | Arnold Jurado | 02/18/26 10:36 AM
Row 221 | @proberts@jwmcd.com @dhasty@jwmcd.com @jdorsey@jwmcd.com flat program completed. | Chris Gambrel | 02/18/26 8:52 AM
Row 222 | @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 02/23/26 9:21 AM
Row 223 | @dhasty@jwmcd.com @tgraves@jwmcd.com @rharmon@jwmcd.com @jmcpherson@jwmcd.com when this will be shipped to PowderWorx615? | Carlos Silva | 03/04/26 8:00 AM
Row 223 | @fdean@jwmcd.com @dhasty@jwmcd.com R1 flat program completed. | Chris Gambrel | 02/26/26 9:41 AM
Row 223 | @cgambrel@jwmcd.com Ready to program, parts are revision 1 | Frank Dean | 02/26/26 9:26 AM
Row 223 | @fdean@jwmcd.com @dhasty@jwmcd.com flat program completed. | Chris Gambrel | 02/25/26 11:35 AM
Row 223 | @cgambrel@jwmcd.com Ready to program | Frank Dean | 02/25/26 7:28 AM
Row 223 | @fdean@jwmcd.com corrections required | David Hasty | 02/24/26 2:31 PM
Row 223 | @csilva@jwmcd.com Just double checking, is the material supposed to be 18 gauge steel or 18 gauge galvanized? | Frank Dean | 02/23/26 7:40 AM
Row 223 | @csilva@jwmcd.com These will need to be cut to 119.75" for the laser. Is there any issue with that? Also, We will need to put a radius on the bends. | David Hasty | 02/19/26 10:53 AM
Row 226 | @dusatenko@jwmcd.com the correct scan is in the network | Laura Forero | 02/25/26 9:34 AM
Row 230 | @tmooers@jwmcd.com we just got this on the shop floor. We need a two week lead time for this and BM05. This will not be ready to ship until 2 weeks from today. @rharmon@jwmcd.com @tgraves@jwmcd.com @sjones@jwmcd.com | Samantha Krantz | 02/24/26 3:43 PM
Row 232 | @gherrera@jwmcd.com @jdavis@jwmcd.com programmed | Issiah Havens | 02/25/26 10:50 AM
Row 232 | @gherrera@jwmcd.com Working on this? | Denis Usatenko | 02/25/26 9:46 AM
| Yes. I'll put it in programming shortly | Gabriela Herrera | 02/25/26 9:48 AM
Row 233 | @gherrera@jwmcd.com @jdavis@jwmcd.com programmed | Issiah Havens | 03/03/26 10:09 AM
Row 233 | @dusatenko@jwmcd.com Sketches are ready for checking | Nadira Vlatkovic | 03/02/26 9:23 AM
| Q:\Jobs\24071 - RS Gass State Lab\03_Engineering\03_FS_Issues\03_Check\24071RO11 | Denis Usatenko | 03/03/26 6:36 AM
Row 240 | @mchancey@jwmcd.com how do you want to ship this? wrap in foam and plastic and send in a sprinter? | Chris Buttrey | 03/11/26 7:42 AM
| i was going to wrap it in foam then shrink wrap it and sprinter | Mitch Chancey | 03/11/26 7:46 AM
Row 240 | @fdean@jwmcd.com @dhasty@jwmcd.com flat program completed. | Chris Gambrel | 03/02/26 1:03 PM
Row 240 | @cgambrel@jwmcd.com Ready to program | Frank Dean | 03/02/26 9:54 AM
Row 242 | @gherrera@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 03/03/26 3:54 PM
Row 244 | @dusatenko@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Issiah Havens | 03/06/26 3:17 PM
Row 244 | @dusatenko@jwmcd.com Sketches are ready to check. "Q:\Jobs\25025 - QTS MAN1 DC6\03_Engineering\03_FS_Issues\03_Check\25025RO01\25025RO01 Check Set.pdf" | Gabriela Hoyle | 03/05/26 3:45 PM
| Q:\Jobs\25025 - QTS MAN1 DC6\03_Engineering\03_FS_Issues\03_Check\25025RO01 | Denis Usatenko | 03/06/26 10:27 AM
Row 245 | @dusatenko@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 03/06/26 3:04 PM
Row 245 | @dusatenko@jwmcd.com Sketches are ready to check. "Q:\Jobs\25059 - Allen Samuels CDJR and LC\03_Engineering\03_FS_Issues\03_Check\25059RM03\25059RM03 Check Set.pdf" | Gabriela Hoyle | 03/05/26 11:42 AM
| Q:\Jobs\25059 - Allen Samuels CDJR and LC\03_Engineering\03_FS_Issues\03_Check\25059RM03 | Denis Usatenko | 03/06/26 8:38 AM
Row 246 | Good Morning John, Weld should not be needed for MU02. Thanks! @jdorsey@jwmcd.com | Dillon Bowman | 03/05/26 6:59 AM
Row 246 | @dbowman@jwmcd.com Is weld needed? That operation is listed on the card | Jonathan Dorsey | 03/04/26 2:22 PM
Row 246 | @jdorsey@jwmcd.com @dhasty@jwmcd.com flat program completed. | Chris Gambrel | 03/04/26 12:48 PM
| Jonathan Dorsey reacted to your message: | Jonathan Dorsey | 03/04/26 12:49 PM
Row 246 | @jdorsey@jwmcd.com Checked, no corrections required | Frank Dean | 03/04/26 11:34 AM
Row 246 | @dhasty@jwmcd.com print is good to check. Q:\Jobs\25029 - Lourdes CC Phase 2\04_Production\25029MU02\JWM CHECK SET | Jonathan Dorsey | 03/04/26 10:28 AM
Row 246 | @jdorsey@jwmcd.com @dhasty@jwmcd.com Hey Team, I found some drop out in the yard. Please program this MU to be cut on it. (Dimensions in photo) | Dillon Bowman | 03/03/26 4:35 PM
Row 248 | @dusatenko@jwmcd.com @hstakhurskyi@jwmcd.com JUST A REMINDER THE INSTALL DIRECTION IS LEFT TO RIGHT | Marc Ribar | 03/04/26 9:09 AM
Row 249 | @gherrera@jwmcd.com @jdavis@jwmcd.com programmed | Issiah Havens | 03/09/26 3:16 PM
Row 254 | @fdean@jwmcd.com @dhasty@jwmcd.com flat program completed. | Chris Gambrel | 03/05/26 10:47 AM
Row 254 | @cgambrel@jwmcd.com Ready to program | Frank Dean | 03/05/26 10:14 AM
Row 254 | @fdean@jwmcd.com Correction required. | Paul J Roberts | 03/05/26 9:54 AM
Row 255 | @fdean@jwmcd.com @dhasty@jwmcd.com flat RM program completed | Chris Gambrel | 03/05/26 10:27 AM
Row 255 | @cgambrel@jwmcd.com Ready to program | Frank Dean | 03/05/26 10:03 AM
Row 255 | @dhasty@jwmcd.com Moved into sketch | Frank Dean | 03/05/26 9:48 AM
Row 256 | @jdorsey@jwmcd.com @fdean@jwmcd.com @dhasty@jwmcd.com flat program completed. | Chris Gambrel | 03/06/26 9:23 AM
| Jonathan Dorsey reacted to your message: | Jonathan Dorsey | 03/06/26 9:27 AM
Row 256 | @jdorsey@jwmcd.com small drafting correction required. | Paul J Roberts | 03/06/26 7:31 AM
Row 256 | @proberts@jwmcd.com will Qty:1 - 0.25" hole on one of the returns be good or different hole size? | Jonathan Dorsey | 03/05/26 10:13 AM
Row 256 | @proberts@jwmcd.com Will do! | Jonathan Dorsey | 03/05/26 9:54 AM
Row 256 | @dbowman@jwmcd.com Assuming this is cosmetic? @jdorsey@jwmcd.com route this through the Trumatic 7000, make sure to mark the drawing as cosmetic before release; it's just adding COSMETIC to the red text in the release package. | Paul J Roberts | 03/05/26 9:51 AM
| Correct, thanks! @proberts@jwmcd.com @jdorsey@jwmcd.com | Dillon Bowman | 03/05/26 9:53 AM
Row 257 | @dusatenko@jwmcd.com This is set to go to powder today. | Paul J Roberts | 03/09/26 7:51 AM
Row 258 | @gherrera@jwmcd.com programmed. @jdavis@jwmcd.com no pendulums, but we are using 2 different sheet sizes for this release. | Issiah Havens | 03/10/26 7:56 AM
Row 258 | @tmooers@jwmcd.com Remake the panels as they were, no change? Where are the 24 parts coming from? | Denis Usatenko | 03/05/26 2:31 PM
| No changes. Ignore the parts. | Thomas Mooers | 03/05/26 2:36 PM
Row 264 | @cnorona@jwmcd.com @mchancey@jwmcd.com @tgraves@jwmcd.com do these need to be crated? two small panels.whats the plan? | Tony Graves | 03/11/26 7:13 AM
| @tgraves@jwmcd.com @mchancey@jwmcd.com we do not need to crate these. if they are ready, i will call my contact | Cole Norona | 03/11/26 7:30 AM
Row 264 | @cdill@jwmcd.com @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 03/09/26 11:28 AM
Row 266 | @jdavis@jwmcd.com PROGRAMMED | Arnold Jurado | 03/09/26 10:24 AM
Row 268 | .040 48 x 120 - RON RED @dusatenko@jwmcd.com | Dillon Bowman | 03/10/26 11:30 AM
Row 268 | @dbowman@jwmcd.com What color, size...196? | Denis Usatenko | 03/10/26 10:23 AM
Row 269 | @jdavis@jwmcd.com programmed | Issiah Havens | 03/11/26 12:14 PM
Row 269 | RDY to Go! | Chance Dill | 03/11/26 12:04 PM
Row 269 | @cdill@jwmcd.com IS THIS READY? | Arnold Jurado | 03/11/26 11:26 AM
Row 273 | @jdorsey@jwmcd.com @dhasty@jwmcd.com flat program completed. | Chris Gambrel | 03/11/26 10:31 AM
Row 273 | @dbowman@jwmcd.com We will need to use HRS Steel in order to weld the allthread to the leafs | David Hasty | 03/11/26 8:36 AM
Sheet | I got the in-house adjusted on the floor. Thanks! @cdill@jwmcd.com | Dillon Bowman | 08/25/25 8:51 AM
Sheet | Removed punch operation. Material from a previous run can be used to complete this order. | Paul J Roberts | 06/19/25 3:30 PM
Sheet | @wmcdougall@jwmcd.com @mchancey@jwmcd.com @tgraves@jwmcd.com @jmcpherson@jwmcd.com @chowse@jwmcd.com @gholland@jwmcd.com still on track. | Tony Graves | 03/28/25 11:56 AM
Sheet | Hey Team, will someone please provide an update on this MU release? Is it done? Is it stuck somewhere? From what I recall it was run through the laser a while ago. @hclouse@jwmcd.com @sjones@jwmcd.com @proberts@jwmcd.com @rharmon@jwmcd.com | Dillon Bowman | 02/27/25 10:24 AM
Sheet | @hclouse@jwmcd.com @rharmon@jwmcd.com I've moved this card to 1st Manual to match where it is in the system. Please make sure it gets moved to the brakes when it gets there. @cnorona@jwmcd.com I updated the notes on the inhouse and sketches to reflect the change from a-side cosmetic to both sides cosmetic and replaced the previous versions on the shop floor with the updated versions. | Paul J Roberts | 09/25/24 9:30 AM
Sheet | Marking as shipped. no paperwork. @swatson@jwmcd.com @tgraves@jwmcd.com | Mitch Chancey | 06/12/24 2:11 PM
Sheet | @cbuttrey@jwmcd.com this date will need to be adjusted. @kpolinski@jwmcd.com @tgraves@jwmcd.com | Tony Graves | 05/13/24 12:09 PM
| I adjusted it, hopefully will have an answer today | Chris Buttrey | 05/13/24 12:12 PM
Sheet | @dusatenko@jwmcd.com The model is saved in the link below Link: Q:\Jobs\22059 - Donelson Library\03_Engineering\03_FS_Issues\02_LO\22059FS01 & FS02 | Laura Forero | 12/14/23 4:28 PM
Sheet | this panel is waiting for panel to come back from the painter to complete | Tony Graves | 11/07/23 11:44 AM
Sheet | Done | Collin Phillips | 10/10/23 8:03 AM
Sheet | Ok, Paul should be able to help you out. | Steve Fudge | 08/18/23 12:25 PM
Sheet | @kpolinski@jwmcd.com @mribar@jwmcd.com I moved this back to the Cidan. Since that is where it is currently located | Mitch Chancey | 04/24/23 1:26 PM
Sheet | These part are good to go to assembly | Terry Jones | 02/06/23 4:16 PM
Sheet | @tgraves@jwmcd.com @tmanning@jwmcd.com @bwynn@jwmcd.com please run this through the shop before 22029 Crossroads Campus. | Hannah Sadloski | 02/01/23 8:22 AM
Sheet | @bwynn@jwmcd.com @ikaplan@jwmcd.com ben, jeff ganas needs an update on this job. Will it be ready by the due date of Tues 12/13? | Hannah Sadloski | 12/08/22 10:22 AM
Sheet | @gholland@jwmcd.com this is ready to ship. | Terry Manning | 11/17/22 9:07 AM
Sheet | @acarmichael@jwmcd.com @mgraham@jwmcd.com 5 pcs have been cut on this. Waiting on @mkinsman@jwmcd.com to get the testing done before we cut the rest of the parts. | Benjamin Wynn | 11/01/22 1:08 PM

## Lookup (hidden)
All IDs | Search Term | Filtered IDs
24079-BM04C | 0 | 1040-30791-ST09
26014-03-ST01 |  | 1040-30791-ST10
26014-03-ST02 |  | 23028-FS99
26014-03-ST02.1 |  | 24001-BM14
26014-03-ST03 |  | 24019-RO07
26014-03-ST03.1 |  | 24020-FL07
25002-FS11.1 |  | 24026-BM01
25029-MU02 |  | 24026-FS01
25029-MU03 |  | 24030-FL02
24051-FS223 |  | 24039-BM19
24079-FS03 |  | 24039-FL36
24079-FS102 |  | 24039-FL37
24051-FS225 |  | 24039-FS14
24079-FS102.1 |  | 24039-FS15
25035-FS04 |  | 24046-FL12
26011-ST01 |  | 24046-FL13
26011-ST1.1 |  | 24046-RO06
25032-FL01 |  | 24048-RM02
25029-MU10 |  | 24051-BM01
24079-FS04 |  | 24051-BM02
26014-04-ST01 |  | 24051-FL01
26014-04-FS01 |  | 24051-FS01
1040-30791-ST09 |  | 24051-FS01C
24079-BM04D |  | 24051-FS02
25005-ST02 |  | 24051-FS03
25012-MU07 |  | 24051-FS04
24051-FS87 |  | 24051-FS05
24051-FS89 |  | 24051-FS06
24051-FS36.2 |  | 24051-FS10
24051-FS226 |  | 24051-FS10C
24079-BM01B |  | 24051-FS11
25017-RO02 |  | 24051-FS12
25010-RO06 |  | 24051-FS13
25010-RO07 |  | 24051-FS14
25029-ST73 |  | 24051-FS15
26014-04-ST02 |  | 24051-FS16C
25002-FS13 |  | 24051-FS200
26014-06-ST01 |  | 24051-FS201
25061-FL01 |  | 24051-FS205
25036-FL22 |  | 24051-FS206
24074-FS07 |  | 24051-FS212
26009-FS01 |  | 24051-FS213
24046-RO06 |  | 24051-FS215
24039-FL36 |  | 24051-FS216
24039-FL37 |  | 24051-FS217
24039-BM19 |  | 24051-FS218
25022-BM06 |  | 24051-FS219
25031-RO01 |  | 24051-FS221
25031-FL08 |  | 24051-FS223
25022-RM01 |  | 24051-FS225
25022-RM02 |  | 24051-FS226
25067-FL02 |  | 24051-FS227
25059-RM05 |  | 24051-FS228
25030-FS01 |  | 24051-FS229
25030-FS02 |  | 24051-FS230
24051-FS90 |  | 24051-FS231
24051-FS91 |  | 24051-FS25
24051-FS227 |  | 24051-FS25.1 FM
24051-FL01 |  | 24051-FS26
1040-30791-ST10 |  | 24051-FS29
24079-RM01 |  | 24051-FS30
24026-FS01 |  | 24051-FS31
25022-RO03 |  | 24051-FS32
24051-FS93 |  | 24051-FS33
24051-FS94 |  | 24051-FS33C
24051-FS95 |  | 24051-FS34
24051-FS228 |  | 24051-FS35
25002-BM07 |  | 24051-FS36
25067-FS02 |  | 24051-FS36.2
24051-FS92 |  | 24051-FS37
24051-FS96 |  | 24051-FS38
24051-FS229 |  | 24051-FS39
24051-FS230 |  | 24051-FS40
24051-FS231 |  | 24051-FS41
25002-FS14 |  | 24051-FS42
25006-FS03 |  | 24051-FS42.1
25002-FS16 |  | 24051-FS43
24074-FS08 |  | 24051-FS43.1
25006-FS05 |  | 24051-FS44
24079-FS103 |  | 24051-FS45
25010-FS09 |  | 24051-FS45C
25029-FS50 |  | 24051-FS46
25002-FS15 |  | 24051-FS46.1
24074-FS09 |  | 24051-FS46C
24079-FL14 |  | 24051-FS47C
25006-FS04 |  | 24051-FS48
25029-ST52 |  | 24051-FS49
25029-ST70 |  | 24051-FS50
25029-ST71 |  | 24051-FS50C
25029-ST72 |  | 24051-FS51
25029-ST51 |  | 24051-FS51C
24079-FS201 |  | 24051-FS52
24079-FS302 |  | 24051-FS52C
25008-FS07 |  | 24051-FS53
24074-FS10 |  | 24051-FS54
24073-FS01 |  | 24051-FS55
25044-FS01 |  | 24051-FS56
25044-FS01.1 |  | 24051-FS56C
25065-MU01 |  | 24051-FS57
25006-FS06 |  | 24051-FS58
25037-FS01 |  | 24051-FS59
24079-FS301 |  | 24051-FS59C
24079-FS303 |  | 24051-FS67
25041-FS02 |  | 24051-FS72
25065-MU02 |  | 24051-FS73
25065-MU03 |  | 24051-FS74
25065-MU04 |  | 24051-FS75
25065-MU05 |  | 24051-FS76
25065-MU11 |  | 24051-FS77
25065-MU12 |  | 24051-FS78
25065-MU13 |  | 24051-FS78.1
25065-MU14 |  | 24051-FS78.2
25065-MU15 |  | 24051-FS87
25065-MU20 |  | 24051-FS89
25044-FS02 |  | 24051-FS90
25006-FS07 |  | 24051-FS91
25037-FS02 |  | 24051-FS92
25044-FS03 |  | 24051-FS93
25006-FS08 |  | 24051-FS94
25012-FS02 |  | 24051-FS95
25044-FS04 |  | 24051-FS96
25006-FS09 |  | 24051-RP11
25044-FS05 |  | 24051-RP16
25006-FS10 |  | 24051-RP20
25044-FS06 |  | 24051-RP58
25044-FS07 |  | 24057-BM10
25006-FS11 |  | 24057-FL10
25044-FS08 |  | 24060-BM01
25006-FS12 |  | 24071-FS10.R
25044-FS09 |  | 24071-RP15
25044-FS01.2 |  | 24073-FS01
25006-FS13 |  | 24074-FS07
25044-FS10 |  | 24074-FS08
25044-FS11 |  | 24074-FS09
25075-RP01 |  | 24074-FS10
24051-RP58 |  | 24079-BM01B
24071-RP15 |  | 24079-BM04C
24060-BM01 |  | 24079-BM04D
24001-BM14 |  | 24079-FL07
24051-FS01 |  | 24079-FL08
24051-FS02 |  | 24079-FL09
24051-FS03 |  | 24079-FL14
24051-FS04 |  | 24079-FS03
24051-FS05 |  | 24079-FS04
24051-FS06 |  | 24079-FS102
24051-FS10 |  | 24079-FS102.1
24051-FS11 |  | 24079-FS103
24051-FS12 |  | 24079-FS201
24051-FS13 |  | 24079-FS301
24051-FS14 |  | 24079-FS302
24051-FS15 |  | 24079-FS303
24051-FS25 |  | 24079-RM01
24051-FS26 |  | 24081-FL01
24051-FS212 |  | 24081-FS01
24051-FS29 |  | 24081-FS02
24051-FS30 |  | 24081-FS03
24051-FS31 |  | 24081-FS04
24051-FS32 |  | 24081-FS05
24082-FL03 |  | 24082-FL03
24051-FS33 |  | 25002-BM07
24051-BM01 |  | 25002-FS11.1
24051-FS200 |  | 25002-FS13
24051-FS34 |  | 25002-FS14
24051-FS35 |  | 25002-FS15
24051-FS206 |  | 25002-FS16
25016-MU101 |  | 25005-ST02
25016-MU103 |  | 25006-FS03
25016-MU121 |  | 25006-FS04
25016-MU122 |  | 25006-FS05
25016-MU123 |  | 25006-FS06
24051-FS01C |  | 25006-FS07
24051-FS10C |  | 25006-FS08
24051-FS33C |  | 25006-FS09
24051-FS37 |  | 25006-FS10
24051-FS38 |  | 25006-FS11
24051-FS39 |  | 25006-FS12
24051-FS40 |  | 25006-FS13
24020-FL07 |  | 25007-BM03
24051-FS41 |  | 25008-FS05
25028-FS01 |  | 25008-FS07
24051-FS36 |  | 25010-FS09
24051-FS215 |  | 25010-RO06
24051-FS43 |  | 25010-RO07
24057-BM10 |  | 25012-FS02
24057-FL10 |  | 25012-MU07
25028-FL02 |  | 25014-11-ST01
24051-FS42 |  | 25014-11-ST02
24051-RP11 |  | 25016-BM201
24051-FS44 |  | 25016-FL200
24051-RP16 |  | 25016-MU101
24048-RM02 |  | 25016-MU103
25016-BM201 |  | 25016-MU121
25016-FL200 |  | 25016-MU122
24046-FL12 |  | 25016-MU123
24046-FL13 |  | 25017-FL99
24051-RP20 |  | 25017-RO02
24051-FS45C |  | 25017-ST02
24051-FS201 |  | 25022-BM06
24051-FS205 |  | 25022-RM01
24051-FS213 |  | 25022-RM02
24051-FS216 |  | 25022-RO03
24051-FS45 |  | 25028-FL02
24051-FS219 |  | 25028-FS01
24051-FS217 |  | 25029-FL97
24051-FS218 |  | 25029-FS50
25014-11-ST01 |  | 25029-MU02
25014-11-ST02 |  | 25029-MU03
24051-FS46C |  | 25029-MU10
24051-FS46 |  | 25029-ST51
24051-FS47C |  | 25029-ST52
24051-FS48 |  | 25029-ST70
24051-FS49 |  | 25029-ST71
24051-FS50 |  | 25029-ST72
24051-FS50C |  | 25029-ST73
25029-FL97 |  | 25030-FS01
25040-FL01 |  | 25030-FS02
24051-FS59 |  | 25031-FL08
25007-BM03 |  | 25031-RO01
25052-BM01 |  | 25032-FL01
24051-FS51C |  | 25035-FS04
24051-FS51 |  | 25036-FL22
24051-FS52C |  | 25037-FS01
24051-FS52 |  | 25037-FS02
25017-FL99 |  | 25040-FL01
25052-FL01 |  | 25041-FS02
23028-FS99 |  | 25044-FS01
24051-FS67 |  | 25044-FS01.1
25017-ST02 |  | 25044-FS01.2
24051-FS54 |  | 25044-FS02
24051-FS53 |  | 25044-FS03
24019-RO07 |  | 25044-FS04
26014-02-ST01 |  | 25044-FS05
24051-FS55 |  | 25044-FS06
24071-FS10.R |  | 25044-FS07
24051-FS56 |  | 25044-FS08
24030-FL02 |  | 25044-FS09
24051-FS46.1 |  | 25044-FS10
24051-FS72 |  | 25044-FS11
24051-FS73 |  | 25052-BM01
24051-FS56C |  | 25052-FL01
24051-FS74 |  | 25059-RM05
24051-FS25.1 FM |  | 25061-FL01
24051-BM02 |  | 25065-MU01
24051-FS221 |  | 25065-MU02
24051-FS43.1 |  | 25065-MU03
24051-FS16C |  | 25065-MU04
24051-FS76 |  | 25065-MU05
24051-FS77 |  | 25065-MU11
24039-FS14 |  | 25065-MU12
24051-FS58 |  | 25065-MU13
24051-FS57 |  | 25065-MU14
24039-FS15 |  | 25065-MU15
24051-FS42.1 |  | 25065-MU20
24051-FS75 |  | 25067-FL02
24051-FS78 |  | 25067-FS02
24051-FS78.1 |  | 25075-RP01
24051-FS59C |  | 26009-FS01
24026-BM01 |  | 26011-ST01
25008-FS05 |  | 26011-ST1.1
24079-FL07 |  | 26014-02-ST01
24079-FL08 |  | 26014-03-ST01
24079-FL09 |  | 26014-03-ST02
24081-FS01 |  | 26014-03-ST02.1
24081-FS02 |  | 26014-03-ST03
24081-FS03 |  | 26014-03-ST03.1
24081-FS04 |  | 26014-04-FS01
24081-FS05 |  | 26014-04-ST01
24081-FL01 |  | 26014-04-ST02
24051-FS78.2 |  | 26014-06-ST01
24079-FS101
24079-FS101.1
25025-BM100
25035-FS02.1
25035-FS02
24081-FL02
24051-FS209.1
24051-FS86
25002-BM06
25035-FS03
23028-FL205
24051-FS71.1
24051-FS224
24051-FS29C
24051-FS82
24051-FS83
24051-FS84
24051-FS85
24051-FS26C
25017-RO01
24051-FS13C
1040-30791-ST08
24051-FS76.1
24081-RO01
24069-RM04
25022-FS11
25022-FS07
25022-FS10
25031-FL06
25022-FS08
24079-FL13

## Future Notes
2026-03-25
PM | Job Number | Job Site | Panal Qty | Note
Laura | 25008-FS07 | Columbia State | 58 | talking to AMI about having these panels ready the week of May 18.
Laura | 25037-FS01 | Chestnut Street Office | 218 | AMI needs these panels the week of May 25.
Laura | 25037-FS02 | Chestnut Street Office | 204 | AMI will need this the week of June 8th
Laura | 25038-FS01 | Chestnut Street Venue | 210 | AMI will need these panels the week of June 15th. Getting FD EARLY APRIL
These are dates that I gave AMI, the first release for 25037; that date cannot be moved.
| 25006 | MALETA |  | 600 | May
| 25051 | East End UMC |  | 182 | May
| 25060 | Legislative Plaza |  | 300 | May
| 25037 | Chestnut Street Office |  | 169 | May
| 25038 | Chestnut Street Office |  | 210 | May
| 25008-FS07 | Columbia State |  | 58 | 2026-05-18
| 25037-FS01 | Chestnut Street Office |  | 218 | 2026-05-25
| 25037-FS02 | Chestnut Street Office |  | 204 | 2026-06-08
| 25038-FS01 | Chestnut Street Venue |  | 210 | 2026-06-15
| 27074 | DIDD ACM |  | 436

## Meleta Schedule
Release | Color | Qty | Elevation | Submitted Date | Pick Up | Current Station | Job ID (with Location) | Monthly Panel Summary
FS01 | GRAPHITE | 88 | 224-227 | 2026-01-22 | 2026-03-23 | Not in System | 25006-FS01-HD | Month | Panels
FS02 | TERRA COTA | 4 | 224-227 | 2026-01-22 | 2026-03-23 | Not in System | 25006-FS02-HD | March | 92
FS03 | GRAPHITE | 216 | 336-38/214, 39/40/215, 41-42/216 | 2026-03-11 | 2026-05-05 | Correction | 25006-FS03-HD | April | 0 |  | From Panal Shop Progression (Forecast) | [12 empty] | MALETA FIRING RANGE
FS05 | TERRA COTA | 18 | 25/213, 50/219 | 2026-03-11 | 2026-05-11 | LO Check | 25006-FS05-HD | May | 1006 |  | 25006 | MALETA |  | 600 | May | [5 empty] | MALETA HOUSING, DINING & KENNEL |  |  | Release | Color | Qty | Elevation | Submitted Date | Pick Up
FS04 | GRAPHITE | 232 | 43/42/216, 45-46/217, 47-49/218 | 2026-03-11 | 2026-05-15 | LO Check | 25006-FS04-HD | June | 647 | [8 empty] | Release | Color | Qty | Elevation | Submitted Date | Pick Up | FS01 | GRAPHITE | 125 | 32-33/213 | 2026-03-30 | 2026-05-22
FS01 | GRAPHITE | 125 | 32-33/213 | 2026-03-29 | 2026-05-21 | Not in System | 25006-FS01-FR | July | 805 | [8 empty] | *FS01 | GRAPHITE | 88 | 224-227 | 2026-01-22 | 2026-03-23 | FS01.1 | TERRA COTA | 34 | 6-8/203, 7/203A, & 12/206 | 2026-03-30 | 2026-05-22
FS01.1 | TERRA COTA | 34 | 6-8/203, 7/203A, 8/12/206 | 2026-03-29 | 2026-05-21 | Not in System | 25006-FS01.1-FR | August | 370 | [8 empty] | *FS02 | TERRA COTA | 4 | 224-227 | 2026-01-22 | 2026-03-23 | FS02 | GRAPHITE | 135 | 34-35/214 | 2026-03-30 | 2026-05-31
FS06 | GRAPHITE | 246 | 25-28/210, 29-31/211, 32-34/212 | 2026-03-11 | 2026-05-25 | LO Check | 25006-FS06-HD | TOTAL | 2920 | [8 empty] | *FS03 | GRAPHITE | 216 | 36-38/214, 39-40/215, 41-42/216 | 2026-03-11 | 2026-05-05 | FS03 | GRAPHITE | 150 | 1-3/201 | 2026-03-30 | 2026-06-10
FS02 | GRAPHITE | 135 | 34-35/214 | 2026-03-29 | 2026-05-30 | Not in System | 25006-FS02-FR | [10 empty] | *FS05 | TERRA COTA | 18 | 25/213, 50/219 | 2026-03-11 | 2026-05-11 | FS04 | GRAPHITE | 113 | 4-5/202 | 2026-03-30 | 2026-06-19
FS07 | GRAPHITE | 190 | 15-17/207 & 18-21/208 | 2026-04-01 | 2026-06-03 | LO Check | 25006-FS07-HD | MALETA Ship Schedule Preview | [5 empty] | (Ship - 21 work days) |  | Lead Time Breakdown: |  | *FS04 | GRAPHITE | 232 | 43-44/216, 45-46/217, 47-49/218 | 2026-03-11 | 2026-05-15 | FS05 | GRAPHITE | 111 | 9-10/204 & 13,15/206 | 2026-03-30 | 2026-06-26
FS03 | GRAPHITE | 150 | 1-3/201 | 2026-03-29 | 2026-06-09 | Correction | 25006-FS03-FR | Ship Date | Job ID | Release | Color | Qty | Station | Eng Release By | Status | Process | Days | *FS06 | GRAPHITE | 246 | 26-28/210, 29-31/211, 32-34/212 | 2026-03-11 | 2026-05-25 | FS06 | GRAPHITE | 203 | 20-21/208 | 2026-03-30 | 2026-07-06
FS08 | GRAPHITE | 83 | 22-25/209 | 2026-04-01 | 2026-06-12 | LO Check | 25006-FS08-HD | 2026-03-23 | 25006-FS01-HD | FS01 | GRAPHITE | 88 | Not in System | 2026-02-26 | Shipped | Engineering (LO/Sketch) | 7 | *FS07 | GRAPHITE | 190 | 15-17/207 & 18-21/208 | 2026-04-01 | 2026-06-03 | FS07 | GRAPHITE | 160 | 22-24/209 & 25/210 | 2026-03-30 | 2026-07-15
FS04 | GRAPHITE | 113 | 4-5/202 | 2026-03-29 | 2026-06-18 | LO Check | 25006-FS04-FR | 2026-03-23 | 25006-FS02-HD | FS02 | TERRA COTA | 4 | Not in System | 2026-02-26 | Shipped | CNC Programming | 2 | *FS08 | GRAPHITE | 83 | 22-25/209 | 2026-04-01 | 2026-06-12 | FS08 | GRAPHITE | 163 | 26/210 & 27/211 | 2026-03-30 | 2026-07-22
FS05 | GRAPHITE | 111 | 9-10/204 & 13, 15/206 | 2026-03-29 | 2026-06-25 | LO Check | 25006-FS05-FR | 2026-05-05 | 25006-FS03-HD | FS03 | GRAPHITE | 216 | Correction | 2026-04-10 | Correction | AXYZ CNC | 3 | [6 empty] | FS01.2 | AZURE BLUE | 193 | 9,11/204, 14-15/206, 16/207, 25-26/210, 1-2/301, 5/303 & 6/304 | 2026-03-30 | 2026-07-29
FS06 | GRAPHITE | 203 | 20-21/208 | 2026-03-29 | 2026-07-05 | LO Check | 25006-FS06-FR | 2026-05-11 | 25006-FS05-HD | FS05 | TERRA COTA | 18 | LO Check | 2026-04-16 | LO Check | Clean & Brake | 3 | [6 empty] | FS09 | GRAPHITE | 86 | 28/211 & 29-31/212 | 2026-03-30 | 2026-07-29
FS07 | GRAPHITE | 160 | 22-24/209 & 25/210 | 2026-03-29 | 2026-07-14 | LO Check | 25006-FS07-FR | 2026-05-15 | 25006-FS04-HD | FS04 | GRAPHITE | 232 | LO Check | 2026-04-21 | LO Check | Fab | 3 | [6 empty] | FS10 | GRAPHITE | 185 | 1-2/301 & 3/302 | 2026-03-30 | 2026-08-07
FS08 | GRAPHITE | 163 | 26/210 & 27/211 | 2026-03-29 | 2026-07-21 | LO Check | 25006-FS08-FR | 2026-05-25 | 25006-FS06-HD | FS06 | GRAPHITE | 246 | LO Check | 2026-04-30 | LO Check | Crating/Ship Prep | 3 | [6 empty] | FS11 | GRAPHITE | 185 | 4-5/303 & 6/304 | 2026-03-30 | 2026-08-17
FS01.2 | AZURE BLUE | 193 | 9,11/204,14-15/206,16/207,25-26/210,1-2/301,5/303 & 6/304 | 2026-03-29 | 2026-07-28 | Not in System | 25006-FS01.2-FR | 2026-06-03 | 25006-FS07-HD | FS07 | GRAPHITE | 190 | LO Check | 2026-05-09 | LO Check | TOTAL LEAD TIME | 21 | [8 empty] | 1843
FS09 | GRAPHITE | 86 | 28/211 & 29-31/212 | 2026-03-29 | 2026-07-28 | LO | 25006-FS09-FR | 2026-06-12 | 25006-FS08-HD | FS08 | GRAPHITE | 83 | LO Check | 2026-05-19 | LO Check
FS10 | GRAPHITE | 185 | 1-2/301 & 3/302 | 2026-03-29 | 2026-08-06 | LO | 25006-FS10-FR | 2026-05-22 | 25006-FS01-FR | FS01 | GRAPHITE | 125 | Not in System | 2026-04-28 | ✅ On Track
FS11 | GRAPHITE | 185 | 4-5/303 & 6/304 | 2026-03-29 | 2026-08-16 | LO | 25006-FS11-FR | 2026-05-22 | 25006-FS01.1-FR | FS01.1 | TERRA COTA | 34 | Not in System | 2026-04-28 | ✅ On Track
[8 empty] | 2026-05-30 | 25006-FS02-FR | FS02 | GRAPHITE | 135 | Not in System | 2026-05-06 | ✅ On Track
[8 empty] | 2026-06-09 | 25006-FS03-FR | FS03 | GRAPHITE | 150 | Correction | 2026-05-15 | Correction
[8 empty] | 2026-06-18 | 25006-FS04-FR | FS04 | GRAPHITE | 113 | LO Check | 2026-05-25 | LO Check
[8 empty] | 2026-06-25 | 25006-FS05-FR | FS05 | GRAPHITE | 111 | LO Check | 2026-06-01 | LO Check
Orange | Housing/Dining | [6 empty] | 2026-07-05 | 25006-FS06-FR | FS06 | GRAPHITE | 203 | LO Check | 2026-06-11 | LO Check
Yellow | Firing Range | [6 empty] | 2026-07-14 | 25006-FS07-FR | FS07 | GRAPHITE | 160 | LO Check | 2026-06-19 | LO Check
[8 empty] | 2026-07-21 | 25006-FS08-FR | FS08 | GRAPHITE | 163 | LO Check | 2026-06-26 | LO Check
[8 empty] | 2026-07-28 | 25006-FS01.2-FR | FS01.2 | AZURE BLUE | 193 | Not in System | 2026-07-03 | ✅ On Track
[8 empty] | 2026-07-28 | 25006-FS09-FR | FS09 | GRAPHITE | 86 | LO | 2026-07-03 | LO
[8 empty] | 2026-08-06 | 25006-FS10-FR | FS10 | GRAPHITE | 185 | LO | 2026-07-13 | LO
[8 empty] | 2026-08-16 | 25006-FS11-FR | FS11 | GRAPHITE | 185 | LO | 2026-07-23 | LO
Summary
[8 empty] | Total Releases: | 21
[8 empty] | Total Panels: | 2920
[8 empty] | In System: | 8
[8 empty] | Not in System: | 13

## Forcast
Panel Shop Projections 2026
Job Number | Job Name | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October
26010 | ASCTE Research and Dorm |  |  |  |  | 674
26015 | Highlands College |  |  | 225
25065 | Crosswinds Casino-Podium |  |  |  | 40 | 750 |  |  | 1000 | 1000 | 1800 | 1500 | 1600 | 1600
24051 | Titans Stadium | 300 | 1500 | 1500 | 1215 | 300 | 300 | 300
25035 | Titans Jabez | 325
25033 | Converge |  |  |  | 400
24026 | 1740 Division |  |  |  | 12
25061 | BNA Concourse A |  |  |  |  | 100 | 1000 | 1000
25075 | St. Thomas | 82
26001 | Edition Hotel -ACM | [7 empty] | 461
26001 | Edition Hotel - Plate | [6 empty] | 200 | 320 | 200
24079 | Nashville Youth | 300 | 600 | 400 | 400 | 300 | 200
24022 | USA Med School |  | 109
25006 | MALETA |  | 600
25051 | East End UMC |  | 182
25060 | Legislative Plaza |  | 300 | 338
24086 | Academic Zone |  |  | 200 | [6 empty] | 2000 |  |  | 1500 |  |  |  |  | 600 | 600
25077 | Andrews Sports Medicine |  |  | 420 | 425
25043 | IAD 183 | [9 empty] | 630 | 630 | 630 | 171
25007 | QTS ATL2 DC10 | 65
25037 | Chestnut Street Office | 338 | 169 | 169
25038 | Chestnut Street Office |  | 210
25058 | Brentsville HS |  | 6
25062 | VUMC | 20
25076 | TSB Buildng |  |  |  | 194
26002 | World Outreach Church |  |  |  | 100 | 100 | 119
26005 | Empower K2 Office | [9 empty] | 423
25029 | Lourdes Phase 2 |  | 15
25012 | St Jude | 157 |  |  | 45 | 71 | 207 | 130
27074 | DIDD ACM | 404 | 436
25041 | Wedgewood |  | 29
25048 | East Nashville
| TOTALS | 1991 | 4156 | 3252 | 2831 | 2295 | 1826 | 1630 | 1781 | 1200 | 4853 | 2130 | 2230 | 3271 | 0 | 0 | 0 | 0 | 600 | 600

## Summary Dashboard
📊 PRODUCTION SUMMARY DASHBOARD
Auto-updates from Production Schedule ¦ Today: 4/16/2026 | [6 empty] | Today's Date: | 2026-04-16
🚚 SHIPS TODAY
Job ID | Job Name | PM | Panel Qty | Part Qty | Current Station
24074-FS06 | DIDD ACM | Dillon Bowman | 40 | 40 | Ready to Ship
26014-04-ST02 | 2026 R & D | TBC | 0 | 15 | TruLaser 3040
📋 RELEASED TO SHOP (Last 24 Hours)
Job ID | Job Name | PM | Panel Qty | Part Qty | Released Date | Current Station | Notes
24051-FS89 | TN Titans Stadium | Marc Ribar | 40 | 40 | 2026-04-15 | AXYZ 34 | 04/14...Next Titans Requesting//Scheduled to be released to the shop 04/16.*04/16/2026…AXYZ 34
25012-FS02 | St Jude Hospital | Wylie McDougall | 60 | 60 | 2026-04-15 | AXYZ 34 | 04/16/2026…AXYZ 34
24051-FL01 | TN Titans Stadium | Marc Ribar | 0 | 25 | 2026-04-16 | Release to Shop | 04/16/2026…Release to Shop
25022-RM01 | Vantage VA15 | Thomas Mooers | 4 | 4 | 2026-04-15 | AXYZ 34 | 04/16/2026…AXYZ 34
🏭 TOP 3 JOBS AT EACH STATION (By Ship Date)
AXYZ Titans Line |  | AXYZ 34 |  | Clean and Brake |  | Fab |  | Shear |  | Cidan |  | Punch
Job ID | Ship Date | Job ID | Ship Date | Job ID | Ship Date | Job ID | Ship Date | Job ID | Ship Date | Job ID | Ship Date | Job ID | Ship Date
- | - | 24026-FS01 | 2026-04-27 | 25002-FS11.1 | 2026-03-02 | - | - | 25032-FL01 | 2026-03-27 | 25061-FL01 | 2026-04-17 | 24060-BM01 | 2025-02-21
- | - | 25067-FS02 | 2026-04-30 | 24051-FS223 | 2026-03-16 | - | - | 24079-BM04C | 2026-02-19 | - | - | 24071-FS10.R | 2026-01-26
- | - | 24051-FS89 | 2026-04-15 | 24051-FS87 | 2026-04-15 | - | - | 24079-BM01B | 2026-04-15 | - | - | 24051-FS200 | 2025-06-19
More Stations: |  | Extrusion Saw: | - |  | Roller: | - |  | TruLaser: | 26014-03-ST02
📈 QUICK STATS
Total Active Jobs: | 297
Jobs Shipping Today: | 2
Jobs Past Due: | 200
Jobs at AXYZ Titans: | 0
Jobs at Clean & Brake: | 5
Jobs at Fab: | 0